## large_construction_project_mana
Project ID | Project Name | Task ID | Task Name | Assigned To | Task Status | Priority | Start Date | Due Date | Completion Date | Progress % | Materials Used | Site Location | Budget Amount ($) | Amount Spent ($) | Comments
C002 | Shopping Complex B | T454 | Interior Painting | Carlos Rivera | Not Started | Medium | 2024-12-08 | 2025-01-04 |  | 0 | Copper Wires | Market Street | 25073.43 | 0 | Not started
C002 | Shopping Complex B | T741 | Interior Painting | John Miller | Not Started | High | 2024-05-09 | 2024-05-22 |  | 0 | Concrete | Market Street | 25587.58 | 0 | Not started
C001 | Residential Building A | T268 | Electrical Wiring | Rachel Green | In Progress | Medium | 2023-09-25 | 2023-10-14 |  | 50 | Cement | Plot 21, Riverside | 5551.29 | 3811.92 | In progress
C003 | Office Tower C | T306 | Foundation Excavation | John Miller | Blocked | Medium | 2023-11-14 | 2023-12-04 |  | 0 | Cement | Downtown Avenue | 43712.38 | 31614.9 | Not started
C001 | Residential Building A | T423 | Roofing | Sarah Johnson | Completed | Low | 2024-02-04 | 2024-02-27 | 2024-02-17 | 100 | Copper Wires | Plot 21, Riverside | 23004.63 | 16695.74 | No issues
C001 | Residential Building A | T368 | Site Survey | Dave Brown | In Progress | Low | 2023-03-02 | 2023-03-10 |  | 15 | Steel Beams | Plot 21, Riverside | 31045.38 | 35164.2 | In progress
C003 | Office Tower C | T916 | Foundation Excavation | Mike Adams | Not Started | Low | 2024-06-17 | 2024-06-27 | 2024-06-19 | 0 | Concrete | Downtown Avenue | 25656.93 | 0 | Not started
C004 | Warehouse D | T193 | Foundation Excavation | Dave Brown | In Progress | High | 2024-01-27 | 2024-02-21 | 2024-02-14 | 15 | Paint | Industrial Park | 8094.55 | 8790.52 | In progress
C003 | Office Tower C | T849 | Steel Framework Setup | Grace Allen | In Progress | Low | 2024-09-24 | 2024-10-06 | 2024-10-03 | 49 | Roofing Sheets | Downtown Avenue | 46433.87 | 50197.61 | In progress
C002 | Shopping Complex B | T264 | Steel Framework Setup | Carlos Rivera | Not Started | High | 2024-04-27 | 2024-05-12 | 2024-05-08 | 0 | Rebar | Market Street | 27486.72 | 0 | Not started
C001 | Residential Building A | T392 | Interior Painting | Rachel Green | Blocked | Medium | 2023-01-17 | 2023-01-31 | 2023-01-20 | 0 | Roofing Sheets | Plot 21, Riverside | 24612.22 | 22010.42 | Not started
C002 | Shopping Complex B | T619 | Steel Framework Setup | Dave Brown | Not Started | Low | 2024-09-20 | 2024-10-11 | 2024-10-08 | 0 | Copper Wires | Market Street | 12827.68 | 0 | Not started
C001 | Residential Building A | T684 | Steel Framework Setup | Emma White | Blocked | Medium | 2023-02-24 | 2023-03-17 | 2023-03-12 | 0 | Concrete | Plot 21, Riverside | 23332.8 | 22002.89 | Not started
C004 | Warehouse D | T580 | Steel Framework Setup | Dave Brown | Blocked | Low | 2024-04-04 | 2024-04-18 |  | 0 | Rebar | Industrial Park | 14732.39 | 9445.66 | Not started
C004 | Warehouse D | T129 | Interior Painting | Mike Adams | Completed | Low | 2023-10-19 | 2023-11-11 | 2023-11-05 | 100 | Cement | Industrial Park | 12823.42 | 14971.97 | No issues
C004 | Warehouse D | T762 | Concrete Pouring | John Miller | In Progress | Low | 2023-11-02 | 2023-12-01 |  | 24 | Rebar | Industrial Park | 7334.09 | 5186.16 | In progress
C004 | Warehouse D | T694 | Roofing | Mike Adams | Completed | Low | 2023-11-18 | 2023-12-10 | 2023-12-09 | 100 | Roofing Sheets | Industrial Park | 23707.26 | 26335.22 | No issues
C004 | Warehouse D | T351 | Plumbing Installations | Mike Adams | In Progress | Low | 2023-07-14 | 2023-08-04 |  | 14 | Paint | Industrial Park | 35124.67 | 32358.65 | In progress
C004 | Warehouse D | T815 | Interior Painting | Dave Brown | Blocked | Low | 2024-06-21 | 2024-07-13 |  | 0 | Paint | Industrial Park | 40753.88 | 40667.67 | Not started
C001 | Residential Building A | T555 | Concrete Pouring | Emma White | Blocked | Medium | 2023-09-23 | 2023-10-02 |  | 0 | Copper Wires | Plot 21, Riverside | 27382.74 | 23566.89 | Not started
C002 | Shopping Complex B | T271 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-11-06 | 2023-11-13 |  | 0 | PVC Pipes | Market Street | 32232.03 | 0 | Not started
C004 | Warehouse D | T112 | Concrete Pouring | Grace Allen | Completed | Medium | 2024-03-16 | 2024-04-14 | 2024-04-07 | 100 | Roofing Sheets | Industrial Park | 36049.48 | 40627.52 | No issues
C002 | Shopping Complex B | T650 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-05-28 | 2023-06-13 |  | 16 | Copper Wires | Market Street | 30903.54 | 47022.69 | In progress
C004 | Warehouse D | T740 | Steel Framework Setup | Carlos Rivera | In Progress | High | 2024-02-20 | 2024-03-20 |  | 19 | Cement | Industrial Park | 47135.56 | 50720.47 | In progress
C004 | Warehouse D | T481 | Site Survey | Sarah Johnson | Blocked | Low | 2024-06-15 | 2024-07-11 |  | 0 | PVC Pipes | Industrial Park | 43916.8 | 36492.44 | Not started
C001 | Residential Building A | T468 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2023-01-17 | 2023-02-02 | 2023-02-02 | 100 | Steel Beams | Plot 21, Riverside | 20441.07 | 19604.77 | No issues
C001 | Residential Building A | T600 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-02-12 | 2023-03-11 | 2023-03-09 | 100 | Steel Beams | Plot 21, Riverside | 8133.08 | 7383.98 | No issues
C002 | Shopping Complex B | T362 | Site Survey | Dave Brown | Blocked | Low | 2023-07-02 | 2023-07-20 |  | 0 | Rebar | Market Street | 28905.31 | 55547.93 | Not started
C001 | Residential Building A | T876 | Foundation Excavation | John Miller | Completed | Low | 2023-12-03 | 2023-12-23 | 2023-12-18 | 100 | Roofing Sheets | Plot 21, Riverside | 36199.51 | 34176.7 | No issues
C004 | Warehouse D | T972 | Site Survey | Rachel Green | In Progress | High | 2024-06-27 | 2024-07-16 |  | 15 | Paint | Industrial Park | 7779.95 | 8591.27 | In progress
C003 | Office Tower C | T490 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2024-10-02 | 2024-10-30 | 2024-10-20 | 100 | Paint | Downtown Avenue | 34509.01 | 23660 | No issues
C001 | Residential Building A | T417 | Interior Painting | Emma White | Blocked | High | 2023-08-24 | 2023-09-02 |  | 0 | Copper Wires | Plot 21, Riverside | 43817.78 | 31689.73 | Not started
C002 | Shopping Complex B | T633 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-08-14 | 2023-09-07 |  | 33 | Rebar | Market Street | 20863.48 | 45991.2 | In progress
C004 | Warehouse D | T737 | Foundation Excavation | Rachel Green | Blocked | High | 2024-01-08 | 2024-01-21 |  | 0 | Copper Wires | Industrial Park | 9523.29 | 8630.89 | Not started
C003 | Office Tower C | T873 | Concrete Pouring | John Miller | Blocked | Medium | 2023-03-06 | 2023-03-15 | 2023-03-10 | 0 | Steel Beams | Downtown Avenue | 33181.48 | 38045.41 | Not started
C002 | Shopping Complex B | T348 | Roofing | Emma White | Not Started | Low | 2023-11-16 | 2023-12-07 | 2023-12-05 | 0 | Paint | Market Street | 44519.51 | 0 | Not started
C004 | Warehouse D | T555 | Roofing | Emma White | Blocked | Low | 2024-06-20 | 2024-07-19 | 2024-07-10 | 0 | Cement | Industrial Park | 40485.2 | 46376.09 | Not started
C003 | Office Tower C | T329 | Roofing | Carlos Rivera | Not Started | Low | 2023-10-09 | 2023-10-17 | 2023-10-10 | 0 | Copper Wires | Downtown Avenue | 7921.87 | 0 | Not started
C004 | Warehouse D | T241 | Electrical Wiring | Rachel Green | In Progress | High | 2024-05-03 | 2024-05-18 | 2024-05-10 | 67 | Cement | Industrial Park | 42899.45 | 43176.61 | In progress
C004 | Warehouse D | T447 | Roofing | Grace Allen | Not Started | High | 2024-04-22 | 2024-05-09 | 2024-05-06 | 0 | Copper Wires | Industrial Park | 32186.49 | 0 | Not started
C002 | Shopping Complex B | T944 | Interior Painting | Grace Allen | In Progress | High | 2024-04-13 | 2024-05-08 | 2024-05-03 | 46 | Paint | Market Street | 19655.74 | 37550.15 | In progress
C003 | Office Tower C | T138 | Concrete Pouring | John Miller | Blocked | Low | 2023-10-15 | 2023-11-07 | 2023-11-03 | 0 | Cement | Downtown Avenue | 44872.35 | 50941.34 | Not started
C004 | Warehouse D | T541 | Foundation Excavation | Rachel Green | Blocked | High | 2024-12-16 | 2025-01-05 | 2025-01-02 | 0 | Concrete | Industrial Park | 41820.7 | 27353.56 | Not started
C004 | Warehouse D | T739 | Foundation Excavation | Emma White | Blocked | Low | 2023-07-24 | 2023-08-14 | 2023-08-09 | 0 | Steel Beams | Industrial Park | 10262.94 | 10072.79 | Not started
C001 | Residential Building A | T843 | Concrete Pouring | Emma White | Blocked | High | 2023-10-19 | 2023-10-30 | 2023-10-20 | 0 | Paint | Plot 21, Riverside | 13658.44 | 9500.29 | Not started
C001 | Residential Building A | T908 | Plumbing Installations | John Miller | Not Started | Low | 2024-07-22 | 2024-08-10 | 2024-08-05 | 0 | Steel Beams | Plot 21, Riverside | 8258.14 | 0 | Not started
C003 | Office Tower C | T611 | Plumbing Installations | Grace Allen | Blocked | Medium | 2023-05-14 | 2023-05-22 | 2023-05-20 | 0 | Paint | Downtown Avenue | 8096.54 | 5193.55 | Not started
C003 | Office Tower C | T834 | Interior Painting | Mike Adams | Blocked | Low | 2024-01-22 | 2024-01-29 | 2024-01-20 | 0 | Concrete | Downtown Avenue | 26159.31 | 29047.21 | Not started
C003 | Office Tower C | T290 | Roofing | Emma White | Blocked | High | 2023-01-18 | 2023-02-07 | 2023-02-03 | 0 | Rebar | Downtown Avenue | 17091.73 | 18027.2 | Not started
C003 | Office Tower C | T572 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2024-09-28 | 2024-10-27 | 2024-10-21 | 0 | Cement | Downtown Avenue | 44387.63 | 0 | Not started
C003 | Office Tower C | T804 | Site Survey | Dave Brown | In Progress | Low | 2023-02-01 | 2023-02-13 |  | 31 | PVC Pipes | Downtown Avenue | 33095.47 | 36761.16 | In progress
C003 | Office Tower C | T754 | Electrical Wiring | Carlos Rivera | Completed | High | 2023-05-23 | 2023-06-01 | 2023-06-01 | 100 | Rebar | Downtown Avenue | 19606.19 | 12320.72 | No issues
C001 | Residential Building A | T645 | Site Survey | Rachel Green | In Progress | Medium | 2023-10-06 | 2023-11-01 |  | 38 | Concrete | Plot 21, Riverside | 31747.09 | 25392.9 | In progress
C002 | Shopping Complex B | T601 | Plumbing Installations | Emma White | Blocked | High | 2024-06-07 | 2024-06-16 |  | 0 | Roofing Sheets | Market Street | 6632.56 | 32438.14 | Not started
C003 | Office Tower C | T528 | Electrical Wiring | Dave Brown | Blocked | High | 2024-12-22 | 2025-01-20 |  | 0 | Cement | Downtown Avenue | 12544.99 | 9444.37 | Not started
C002 | Shopping Complex B | T375 | Site Survey | Carlos Rivera | Not Started | Low | 2024-06-20 | 2024-07-14 |  | 0 | Rebar | Market Street | 44331.47 | 0 | Not started
C004 | Warehouse D | T667 | Electrical Wiring | Emma White | Blocked | High | 2024-01-17 | 2024-02-08 |  | 0 | Concrete | Industrial Park | 40718.73 | 45658.35 | Not started
C001 | Residential Building A | T491 | Roofing | Mike Adams | Not Started | Low | 2024-07-27 | 2024-08-04 |  | 0 | Concrete | Plot 21, Riverside | 24366.96 | 0 | Not started
C002 | Shopping Complex B | T738 | Concrete Pouring | Emma White | Not Started | High | 2024-01-13 | 2024-02-05 |  | 0 | Concrete | Market Street | 20227.38 | 0 | Not started
C001 | Residential Building A | T825 | Foundation Excavation | Mike Adams | In Progress | Low | 2023-11-06 | 2023-11-28 |  | 46 | Rebar | Plot 21, Riverside | 13075.85 | 9738.55 | In progress
C004 | Warehouse D | T192 | Concrete Pouring | Rachel Green | Blocked | Medium | 2024-03-25 | 2024-04-18 |  | 0 | Roofing Sheets | Industrial Park | 42974.9 | 48733.23 | Not started
C001 | Residential Building A | T643 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-05-23 | 2024-06-06 |  | 0 | Copper Wires | Plot 21, Riverside | 7026.71 | 5263.14 | Not started
C004 | Warehouse D | T760 | Foundation Excavation | Emma White | Not Started | High | 2023-06-18 | 2023-06-29 |  | 0 | Roofing Sheets | Industrial Park | 38686.92 | 0 | Not started
C002 | Shopping Complex B | T327 | Plumbing Installations | Rachel Green | Blocked | Medium | 2023-10-04 | 2023-10-30 |  | 0 | Steel Beams | Market Street | 44865.38 | 66572.89 | Not started
C003 | Office Tower C | T241 | Concrete Pouring | Dave Brown | Blocked | Medium | 2024-12-10 | 2025-01-07 |  | 0 | Cement | Downtown Avenue | 27898.42 | 31110.38 | Not started
C003 | Office Tower C | T227 | Electrical Wiring | Grace Allen | Completed | Medium | 2023-08-04 | 2023-08-13 | 2023-08-13 | 100 | Rebar | Downtown Avenue | 22407.09 | 15237.7 | No issues
C002 | Shopping Complex B | T978 | Foundation Excavation | John Miller | In Progress | Medium | 2024-06-13 | 2024-06-27 |  | 80 | Roofing Sheets | Market Street | 8086.62 | 30697.58 | In progress
C001 | Residential Building A | T308 | Steel Framework Setup | Rachel Green | Completed | Medium | 2024-05-28 | 2024-06-14 | 2024-06-14 | 100 | Roofing Sheets | Plot 21, Riverside | 15064.62 | 15974.41 | No issues
C001 | Residential Building A | T652 | Site Survey | Emma White | Not Started | Medium | 2023-11-11 | 2023-11-18 |  | 0 | Paint | Plot 21, Riverside | 20024.1 | 0 | Not started
C003 | Office Tower C | T433 | Electrical Wiring | Carlos Rivera | Blocked | Low | 2023-06-08 | 2023-07-05 |  | 0 | PVC Pipes | Downtown Avenue | 16521.65 | 13990.83 | Not started
C003 | Office Tower C | T541 | Site Survey | Dave Brown | Blocked | Low | 2024-06-17 | 2024-07-05 |  | 0 | Paint | Downtown Avenue | 42428.97 | 39056.4 | Not started
C001 | Residential Building A | T272 | Site Survey | Rachel Green | Not Started | Low | 2024-12-13 | 2025-01-01 |  | 0 | Rebar | Plot 21, Riverside | 46074.67 | 0 | Not started
C001 | Residential Building A | T789 | Concrete Pouring | Emma White | Blocked | Medium | 2024-10-01 | 2024-10-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 20408.72 | 16795.19 | Not started
C003 | Office Tower C | T602 | Steel Framework Setup | John Miller | Not Started | Medium | 2023-12-28 | 2024-01-09 |  | 0 | Copper Wires | Downtown Avenue | 9338.67 | 0 | Not started
C004 | Warehouse D | T528 | Electrical Wiring | Grace Allen | In Progress | High | 2023-05-19 | 2023-05-30 |  | 36 | Rebar | Industrial Park | 48195.22 | 30438.91 | In progress
C004 | Warehouse D | T734 | Foundation Excavation | John Miller | Blocked | High | 2024-03-12 | 2024-03-21 |  | 0 | Roofing Sheets | Industrial Park | 37447.01 | 25872.91 | Not started
C002 | Shopping Complex B | T397 | Concrete Pouring | John Miller | In Progress | Medium | 2023-08-08 | 2023-09-02 |  | 48 | Paint | Market Street | 15543.47 | 39970.34 | In progress
C002 | Shopping Complex B | T254 | Foundation Excavation | Grace Allen | Not Started | Medium | 2023-11-02 | 2023-11-11 |  | 0 | Cement | Market Street | 32298.91 | 0 | Not started
C002 | Shopping Complex B | T128 | Steel Framework Setup | Dave Brown | Completed | Low | 2023-05-09 | 2023-05-28 | 2023-05-28 | 100 | PVC Pipes | Market Street | 9000.99 | 36050.67 | No issues
C004 | Warehouse D | T299 | Plumbing Installations | Sarah Johnson | Blocked | Low | 2023-11-12 | 2023-12-02 |  | 0 | Copper Wires | Industrial Park | 32665.93 | 34953.83 | Not started
C002 | Shopping Complex B | T717 | Plumbing Installations | Sarah Johnson | Blocked | Low | 2023-02-20 | 2023-03-20 |  | 0 | Steel Beams | Market Street | 45084.61 | 64481.3 | Not started
C002 | Shopping Complex B | T750 | Interior Painting | Carlos Rivera | Blocked | High | 2024-10-23 | 2024-11-10 |  | 0 | Cement | Market Street | 27288.92 | 43731.34 | Not started
C003 | Office Tower C | T343 | Plumbing Installations | Dave Brown | In Progress | Low | 2023-05-10 | 2023-06-04 |  | 22 | Concrete | Downtown Avenue | 49860.57 | 50587.32 | In progress
C002 | Shopping Complex B | T351 | Plumbing Installations | Emma White | Completed | Low | 2024-03-02 | 2024-03-09 | 2024-03-09 | 100 | Roofing Sheets | Market Street | 11537.26 | 38695.86 | No issues
C004 | Warehouse D | T564 | Electrical Wiring | Emma White | Not Started | Medium | 2023-04-08 | 2023-04-22 |  | 0 | Paint | Industrial Park | 12507.67 | 0 | Not started
C004 | Warehouse D | T249 | Plumbing Installations | Rachel Green | Completed | Low | 2023-11-18 | 2023-12-13 | 2023-12-13 | 100 | Copper Wires | Industrial Park | 43545.07 | 40469.86 | No issues
C002 | Shopping Complex B | T508 | Plumbing Installations | Mike Adams | Blocked | Low | 2023-04-01 | 2023-04-24 |  | 0 | Copper Wires | Market Street | 8908.19 | 31253.11 | Not started
C001 | Residential Building A | T893 | Steel Framework Setup | Grace Allen | Completed | Medium | 2024-05-06 | 2024-05-31 | 2024-05-31 | 100 | Rebar | Plot 21, Riverside | 47735.48 | 35584.13 | No issues
C004 | Warehouse D | T329 | Site Survey | Carlos Rivera | Not Started | Low | 2024-11-16 | 2024-11-23 |  | 0 | Paint | Industrial Park | 45636.76 | 0 | Not started
C002 | Shopping Complex B | T930 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-09-04 | 2023-10-04 |  | 76 | Rebar | Market Street | 44675.23 | 77236.14 | In progress
C001 | Residential Building A | T211 | Foundation Excavation | Emma White | Blocked | Medium | 2024-01-22 | 2024-02-13 |  | 0 | Roofing Sheets | Plot 21, Riverside | 15630.17 | 14094.98 | Not started
C002 | Shopping Complex B | T777 | Plumbing Installations | John Miller | In Progress | Medium | 2024-08-25 | 2024-09-08 |  | 90 | Steel Beams | Market Street | 44597.35 | 69647.05 | In progress
C002 | Shopping Complex B | T935 | Plumbing Installations | Rachel Green | Blocked | Low | 2024-02-13 | 2024-02-25 |  | 0 | Cement | Market Street | 40664.36 | 69982.02 | Not started
C004 | Warehouse D | T788 | Site Survey | Emma White | Completed | High | 2023-06-23 | 2023-07-07 | 2023-07-07 | 100 | Concrete | Industrial Park | 15132.13 | 10411.84 | No issues
C001 | Residential Building A | T805 | Foundation Excavation | John Miller | Not Started | Low | 2024-06-15 | 2024-06-26 |  | 0 | Steel Beams | Plot 21, Riverside | 43427.71 | 0 | Not started
C001 | Residential Building A | T755 | Plumbing Installations | Grace Allen | Completed | High | 2023-07-17 | 2023-08-10 | 2023-08-10 | 100 | Concrete | Plot 21, Riverside | 22047.72 | 13935.31 | No issues
C004 | Warehouse D | T977 | Concrete Pouring | John Miller | Blocked | Low | 2024-12-17 | 2024-12-31 |  | 0 | Paint | Industrial Park | 16095.58 | 18296.05 | Not started
C003 | Office Tower C | T495 | Roofing | Carlos Rivera | Completed | Low | 2023-01-14 | 2023-01-23 | 2023-01-23 | 100 | Roofing Sheets | Downtown Avenue | 11606.2 | 8048.18 | No issues
C002 | Shopping Complex B | T624 | Steel Framework Setup | Dave Brown | Completed | Low | 2023-12-18 | 2024-01-02 | 2024-01-02 | 100 | Steel Beams | Market Street | 37181.08 | 68546.5 | No issues
C004 | Warehouse D | T773 | Site Survey | Carlos Rivera | Completed | Low | 2024-02-19 | 2024-03-20 | 2024-03-20 | 100 | Copper Wires | Industrial Park | 18692.74 | 20682.49 | No issues
C003 | Office Tower C | T568 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2024-07-01 | 2024-07-24 |  | 56 | PVC Pipes | Downtown Avenue | 7657.8 | 8985.3 | In progress
C004 | Warehouse D | T497 | Foundation Excavation | Carlos Rivera | Completed | Medium | 2023-05-05 | 2023-05-25 | 2023-05-25 | 100 | Roofing Sheets | Industrial Park | 41565.28 | 24965.71 | No issues
C003 | Office Tower C | T706 | Site Survey | Mike Adams | Blocked | High | 2023-12-10 | 2023-12-21 |  | 0 | Copper Wires | Downtown Avenue | 39842.03 | 36490.28 | Not started
C003 | Office Tower C | T320 | Steel Framework Setup | Rachel Green | Blocked | High | 2024-08-09 | 2024-08-29 |  | 0 | Cement | Downtown Avenue | 35650.76 | 34592.77 | Not started
C003 | Office Tower C | T941 | Interior Painting | Emma White | Not Started | Medium | 2023-08-12 | 2023-08-25 |  | 0 | Steel Beams | Downtown Avenue | 49737.59 | 0 | Not started
C003 | Office Tower C | T232 | Electrical Wiring | Grace Allen | In Progress | Medium | 2024-01-10 | 2024-02-08 |  | 9 | Paint | Downtown Avenue | 9549.63 | 6963.4 | In progress
C004 | Warehouse D | T246 | Interior Painting | Grace Allen | Not Started | Medium | 2023-06-19 | 2023-07-02 |  | 0 | Steel Beams | Industrial Park | 15157.28 | 0 | Not started
C004 | Warehouse D | T574 | Plumbing Installations | Sarah Johnson | Not Started | High | 2023-08-26 | 2023-09-17 |  | 0 | Concrete | Industrial Park | 14345.03 | 0 | Not started
C001 | Residential Building A | T711 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2023-02-05 | 2023-03-07 |  | 85 | PVC Pipes | Plot 21, Riverside | 30886.42 | 22616.48 | In progress
C004 | Warehouse D | T767 | Roofing | Mike Adams | Not Started | Low | 2024-09-04 | 2024-09-21 |  | 0 | Concrete | Industrial Park | 7712.75 | 0 | Not started
C001 | Residential Building A | T141 | Steel Framework Setup | Emma White | Completed | Low | 2023-02-08 | 2023-03-06 | 2023-03-06 | 100 | Paint | Plot 21, Riverside | 35016.68 | 30037.15 | No issues
C001 | Residential Building A | T652 | Site Survey | Dave Brown | Not Started | High | 2024-04-01 | 2024-04-24 |  | 0 | Concrete | Plot 21, Riverside | 20423.85 | 0 | Not started
C002 | Shopping Complex B | T130 | Foundation Excavation | Dave Brown | Completed | Low | 2024-01-07 | 2024-01-19 | 2024-01-19 | 100 | Cement | Market Street | 9850.62 | 33069.38 | No issues
C004 | Warehouse D | T245 | Site Survey | Rachel Green | Completed | Medium | 2023-01-01 | 2023-01-21 | 2023-01-21 | 100 | PVC Pipes | Industrial Park | 49213.15 | 42191.71 | No issues
C002 | Shopping Complex B | T620 | Site Survey | Grace Allen | In Progress | Medium | 2024-01-03 | 2024-01-10 |  | 24 | Rebar | Market Street | 47561.78 | 71305.54 | In progress
C001 | Residential Building A | T267 | Roofing | Grace Allen | In Progress | Low | 2024-04-28 | 2024-05-13 |  | 64 | Cement | Plot 21, Riverside | 48758.49 | 52410.1 | In progress
C004 | Warehouse D | T198 | Plumbing Installations | Dave Brown | Blocked | Low | 2023-08-11 | 2023-08-21 |  | 0 | PVC Pipes | Industrial Park | 35033.28 | 24161.5 | Not started
C001 | Residential Building A | T652 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2023-02-06 | 2023-02-26 | 2023-02-26 | 100 | Concrete | Plot 21, Riverside | 49720.3 | 51371.03 | No issues
C003 | Office Tower C | T586 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-09-20 | 2024-10-02 |  | 0 | Cement | Downtown Avenue | 37945.92 | 0 | Not started
C003 | Office Tower C | T374 | Concrete Pouring | Grace Allen | Blocked | Medium | 2024-01-20 | 2024-01-28 |  | 0 | Steel Beams | Downtown Avenue | 12684.37 | 13732.68 | Not started
C002 | Shopping Complex B | T185 | Electrical Wiring | Emma White | Blocked | High | 2024-09-01 | 2024-09-27 |  | 0 | PVC Pipes | Market Street | 13482.77 | 40230.94 | Not started
C001 | Residential Building A | T423 | Plumbing Installations | Grace Allen | Blocked | Medium | 2024-07-10 | 2024-07-27 |  | 0 | Steel Beams | Plot 21, Riverside | 45791.66 | 29547.44 | Not started
C001 | Residential Building A | T985 | Roofing | Emma White | In Progress | Medium | 2024-08-16 | 2024-08-26 |  | 63 | Rebar | Plot 21, Riverside | 38792.22 | 35291.59 | In progress
C002 | Shopping Complex B | T240 | Steel Framework Setup | Emma White | Not Started | Low | 2024-11-15 | 2024-11-24 |  | 0 | Steel Beams | Market Street | 9384.77 | 0 | Not started
C002 | Shopping Complex B | T347 | Roofing | Emma White | Not Started | High | 2023-02-12 | 2023-02-25 |  | 0 | Concrete | Market Street | 26347.82 | 0 | Not started
C003 | Office Tower C | T199 | Site Survey | Mike Adams | Not Started | High | 2023-07-12 | 2023-08-07 |  | 0 | Paint | Downtown Avenue | 13496.64 | 0 | Not started
C001 | Residential Building A | T605 | Foundation Excavation | John Miller | Blocked | Low | 2024-07-09 | 2024-07-31 |  | 0 | Cement | Plot 21, Riverside | 32660.85 | 20433.87 | Not started
C002 | Shopping Complex B | T354 | Concrete Pouring | Rachel Green | Not Started | High | 2024-09-22 | 2024-10-03 |  | 0 | Copper Wires | Market Street | 49406.27 | 0 | Not started
C003 | Office Tower C | T546 | Roofing | Rachel Green | Blocked | Low | 2024-07-22 | 2024-08-05 |  | 0 | Cement | Downtown Avenue | 33948.17 | 34700.28 | Not started
C001 | Residential Building A | T562 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2024-07-04 | 2024-07-26 |  | 0 | Concrete | Plot 21, Riverside | 6434.09 | 7555.22 | Not started
C001 | Residential Building A | T184 | Interior Painting | John Miller | Not Started | Low | 2024-01-25 | 2024-02-18 |  | 0 | Copper Wires | Plot 21, Riverside | 24261.93 | 0 | Not started
C004 | Warehouse D | T908 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-05-23 | 2024-06-19 |  | 0 | Copper Wires | Industrial Park | 45315.68 | 0 | Not started
C004 | Warehouse D | T623 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2023-03-02 | 2023-03-21 | 2023-03-21 | 100 | Paint | Industrial Park | 18573.39 | 15176.96 | No issues
C004 | Warehouse D | T592 | Steel Framework Setup | Mike Adams | Not Started | High | 2024-07-25 | 2024-08-03 |  | 0 | Roofing Sheets | Industrial Park | 17780.85 | 0 | Not started
C001 | Residential Building A | T608 | Interior Painting | Dave Brown | Completed | Medium | 2024-06-10 | 2024-06-17 | 2024-06-17 | 100 | PVC Pipes | Plot 21, Riverside | 49376.01 | 33474.08 | No issues
C001 | Residential Building A | T699 | Site Survey | Rachel Green | In Progress | Medium | 2024-05-27 | 2024-06-11 |  | 7 | Paint | Plot 21, Riverside | 9269.27 | 10768.05 | In progress
C004 | Warehouse D | T184 | Electrical Wiring | Dave Brown | Not Started | Medium | 2023-02-10 | 2023-03-04 |  | 0 | Concrete | Industrial Park | 19227.92 | 0 | Not started
C004 | Warehouse D | T201 | Concrete Pouring | Grace Allen | In Progress | Medium | 2023-08-19 | 2023-08-29 |  | 15 | Concrete | Industrial Park | 42004.57 | 40274.12 | In progress
C002 | Shopping Complex B | T848 | Site Survey | Sarah Johnson | Not Started | Low | 2023-05-08 | 2023-05-23 |  | 0 | Cement | Market Street | 19443.43 | 0 | Not started
C002 | Shopping Complex B | T811 | Interior Painting | Dave Brown | In Progress | Medium | 2023-03-14 | 2023-04-10 |  | 63 | Concrete | Market Street | 22477.82 | 39234.55 | In progress
C001 | Residential Building A | T237 | Concrete Pouring | Emma White | Blocked | High | 2023-08-12 | 2023-08-23 |  | 0 | Steel Beams | Plot 21, Riverside | 38862.23 | 42346.16 | Not started
C001 | Residential Building A | T395 | Electrical Wiring | Mike Adams | Not Started | Medium | 2023-09-11 | 2023-10-02 |  | 0 | Steel Beams | Plot 21, Riverside | 23336.97 | 0 | Not started
C001 | Residential Building A | T464 | Site Survey | Rachel Green | Blocked | Low | 2024-01-23 | 2024-01-30 |  | 0 | Paint | Plot 21, Riverside | 17996.23 | 20184.9 | Not started
C002 | Shopping Complex B | T661 | Interior Painting | John Miller | Not Started | High | 2024-05-20 | 2024-06-09 |  | 0 | Cement | Market Street | 25533.78 | 0 | Not started
C002 | Shopping Complex B | T551 | Interior Painting | Mike Adams | Blocked | Low | 2023-08-28 | 2023-09-08 |  | 0 | Roofing Sheets | Market Street | 7618.96 | 34347.22 | Not started
C003 | Office Tower C | T932 | Site Survey | Grace Allen | Not Started | Low | 2024-09-03 | 2024-09-30 |  | 0 | PVC Pipes | Downtown Avenue | 14737.63 | 0 | Not started
C003 | Office Tower C | T363 | Plumbing Installations | Grace Allen | Completed | Medium | 2024-02-21 | 2024-03-04 | 2024-03-04 | 100 | PVC Pipes | Downtown Avenue | 39204.17 | 29231.4 | No issues
C002 | Shopping Complex B | T999 | Steel Framework Setup | Rachel Green | Completed | Medium | 2023-08-27 | 2023-09-15 | 2023-09-15 | 100 | Rebar | Market Street | 14869.69 | 36909 | No issues
C004 | Warehouse D | T557 | Roofing | John Miller | Not Started | High | 2024-08-23 | 2024-09-06 |  | 0 | Rebar | Industrial Park | 27174.66 | 0 | Not started
C001 | Residential Building A | T461 | Plumbing Installations | Grace Allen | Completed | Medium | 2024-07-26 | 2024-08-15 | 2024-08-15 | 100 | Cement | Plot 21, Riverside | 23127.1 | 17999.96 | No issues
C003 | Office Tower C | T194 | Steel Framework Setup | Emma White | Completed | Low | 2023-11-02 | 2023-11-15 | 2023-11-15 | 100 | Steel Beams | Downtown Avenue | 12049.01 | 8337.63 | No issues
C004 | Warehouse D | T787 | Concrete Pouring | Grace Allen | Completed | High | 2024-04-01 | 2024-04-13 | 2024-04-13 | 100 | Steel Beams | Industrial Park | 16235.38 | 16840.61 | No issues
C004 | Warehouse D | T335 | Foundation Excavation | Rachel Green | In Progress | Medium | 2023-11-17 | 2023-11-30 |  | 68 | Roofing Sheets | Industrial Park | 44119.24 | 45195.64 | In progress
C003 | Office Tower C | T532 | Site Survey | John Miller | Blocked | High | 2024-06-06 | 2024-07-01 |  | 0 | Roofing Sheets | Downtown Avenue | 44310.74 | 38410.17 | Not started
C003 | Office Tower C | T658 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2024-06-13 | 2024-06-30 |  | 0 | Paint | Downtown Avenue | 49544.43 | 34500.7 | Not started
C003 | Office Tower C | T993 | Electrical Wiring | Rachel Green | Blocked | Medium | 2023-11-22 | 2023-12-13 |  | 0 | Roofing Sheets | Downtown Avenue | 19619.35 | 21407.13 | Not started
C004 | Warehouse D | T642 | Foundation Excavation | Emma White | In Progress | Medium | 2024-02-07 | 2024-02-19 |  | 54 | PVC Pipes | Industrial Park | 14072.41 | 16430.29 | In progress
C004 | Warehouse D | T266 | Site Survey | Mike Adams | Blocked | Low | 2023-12-07 | 2023-12-24 |  | 0 | Steel Beams | Industrial Park | 16866.55 | 18587.94 | Not started
C002 | Shopping Complex B | T204 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2023-04-20 | 2023-05-06 |  | 93 | Paint | Market Street | 44600.57 | 57677.91 | In progress
C003 | Office Tower C | T987 | Plumbing Installations | Dave Brown | Completed | High | 2024-07-25 | 2024-08-18 | 2024-08-18 | 100 | Cement | Downtown Avenue | 43716.32 | 39825.64 | No issues
C004 | Warehouse D | T139 | Steel Framework Setup | Emma White | Completed | Low | 2023-07-21 | 2023-08-13 | 2023-08-13 | 100 | PVC Pipes | Industrial Park | 22585.37 | 17326.01 | No issues
C001 | Residential Building A | T708 | Plumbing Installations | Rachel Green | Not Started | High | 2024-03-20 | 2024-04-03 |  | 0 | Rebar | Plot 21, Riverside | 26141.28 | 0 | Not started
C003 | Office Tower C | T855 | Electrical Wiring | Emma White | Blocked | Medium | 2023-09-07 | 2023-09-18 |  | 0 | PVC Pipes | Downtown Avenue | 19881.75 | 13490.6 | Not started
C004 | Warehouse D | T339 | Electrical Wiring | Grace Allen | Completed | Low | 2023-01-05 | 2023-01-15 | 2023-01-15 | 100 | PVC Pipes | Industrial Park | 47657.63 | 47101.74 | No issues
C004 | Warehouse D | T884 | Concrete Pouring | John Miller | Completed | High | 2024-10-24 | 2024-11-01 | 2024-11-01 | 100 | Cement | Industrial Park | 6120.75 | 5483.15 | No issues
C004 | Warehouse D | T713 | Roofing | Sarah Johnson | Not Started | High | 2023-09-19 | 2023-10-01 |  | 0 | Paint | Industrial Park | 5550.89 | 0 | Not started
C001 | Residential Building A | T368 | Foundation Excavation | John Miller | In Progress | Medium | 2024-11-19 | 2024-12-19 |  | 61 | Concrete | Plot 21, Riverside | 39367.32 | 43727.04 | In progress
C004 | Warehouse D | T321 | Foundation Excavation | Grace Allen | Completed | Low | 2024-06-24 | 2024-07-10 | 2024-07-10 | 100 | Rebar | Industrial Park | 25189.22 | 23084.2 | No issues
C001 | Residential Building A | T713 | Plumbing Installations | Dave Brown | Blocked | Low | 2023-06-02 | 2023-06-17 |  | 0 | Concrete | Plot 21, Riverside | 22766.09 | 18419.91 | Not started
C001 | Residential Building A | T292 | Foundation Excavation | Emma White | In Progress | Low | 2024-06-15 | 2024-07-12 |  | 93 | Cement | Plot 21, Riverside | 11347.55 | 9432.08 | In progress
C001 | Residential Building A | T637 | Foundation Excavation | Grace Allen | Not Started | Medium | 2024-11-11 | 2024-12-08 |  | 0 | Paint | Plot 21, Riverside | 47521.2 | 0 | Not started
C001 | Residential Building A | T775 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-03-24 | 2023-04-09 |  | 0 | Rebar | Plot 21, Riverside | 49391.34 | 52180.71 | Not started
C001 | Residential Building A | T370 | Concrete Pouring | John Miller | Blocked | Low | 2023-06-05 | 2023-07-02 |  | 0 | Copper Wires | Plot 21, Riverside | 10445.26 | 11828.78 | Not started
C001 | Residential Building A | T432 | Plumbing Installations | Rachel Green | Blocked | Low | 2023-08-26 | 2023-09-16 |  | 0 | PVC Pipes | Plot 21, Riverside | 8706.69 | 8388.01 | Not started
C004 | Warehouse D | T339 | Site Survey | Emma White | In Progress | High | 2024-09-10 | 2024-10-05 |  | 80 | Concrete | Industrial Park | 45274.29 | 38206.14 | In progress
C003 | Office Tower C | T408 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2024-06-03 | 2024-06-30 | 2024-06-30 | 100 | Concrete | Downtown Avenue | 32572.65 | 29480.75 | No issues
C002 | Shopping Complex B | T404 | Interior Painting | Rachel Green | Blocked | Low | 2023-12-24 | 2024-01-13 |  | 0 | Copper Wires | Market Street | 23044.43 | 46075.96 | Not started
C003 | Office Tower C | T693 | Foundation Excavation | Mike Adams | Not Started | Medium | 2024-03-13 | 2024-04-10 |  | 0 | Concrete | Downtown Avenue | 42762.56 | 0 | Not started
C003 | Office Tower C | T734 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2023-11-20 | 2023-12-17 |  | 94 | Concrete | Downtown Avenue | 32998.7 | 22539.55 | In progress
C002 | Shopping Complex B | T806 | Electrical Wiring | Rachel Green | Blocked | High | 2023-08-21 | 2023-08-28 |  | 0 | Paint | Market Street | 16635.02 | 43703.74 | Not started
C004 | Warehouse D | T611 | Roofing | Dave Brown | Not Started | Medium | 2024-12-16 | 2025-01-05 |  | 0 | Steel Beams | Industrial Park | 28982.65 | 0 | Not started
C003 | Office Tower C | T155 | Roofing | Sarah Johnson | In Progress | Medium | 2024-01-17 | 2024-01-25 |  | 82 | Paint | Downtown Avenue | 45567.5 | 43660.03 | In progress
C004 | Warehouse D | T475 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2024-10-08 | 2024-10-28 |  | 0 | Paint | Industrial Park | 18725.83 | 0 | Not started
C004 | Warehouse D | T358 | Roofing | Sarah Johnson | Blocked | High | 2024-03-04 | 2024-03-31 |  | 0 | Copper Wires | Industrial Park | 39075.32 | 24746.7 | Not started
C002 | Shopping Complex B | T878 | Roofing | Carlos Rivera | In Progress | High | 2024-12-10 | 2024-12-29 |  | 34 | PVC Pipes | Market Street | 46936.01 | 74590.33 | In progress
C004 | Warehouse D | T284 | Plumbing Installations | Rachel Green | In Progress | Low | 2024-09-18 | 2024-10-04 |  | 59 | Roofing Sheets | Industrial Park | 9497.89 | 9643.31 | In progress
C002 | Shopping Complex B | T830 | Site Survey | Dave Brown | In Progress | Low | 2023-08-27 | 2023-09-11 |  | 77 | Copper Wires | Market Street | 15124.02 | 35682.91 | In progress
C003 | Office Tower C | T377 | Site Survey | Dave Brown | Not Started | High | 2023-07-06 | 2023-08-01 |  | 0 | Cement | Downtown Avenue | 5456.09 | 0 | Not started
C003 | Office Tower C | T556 | Interior Painting | Carlos Rivera | Completed | Medium | 2023-11-03 | 2023-11-10 | 2023-11-10 | 100 | Paint | Downtown Avenue | 20611.2 | 20311.7 | No issues
C004 | Warehouse D | T675 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-05-17 | 2024-06-12 |  | 5 | Steel Beams | Industrial Park | 49033.59 | 42891.38 | In progress
C004 | Warehouse D | T465 | Site Survey | Sarah Johnson | Not Started | Medium | 2023-06-16 | 2023-07-15 |  | 0 | Paint | Industrial Park | 22478.57 | 0 | Not started
C003 | Office Tower C | T127 | Foundation Excavation | Grace Allen | Not Started | Low | 2023-03-06 | 2023-03-23 |  | 0 | Cement | Downtown Avenue | 16787.07 | 0 | Not started
C001 | Residential Building A | T468 | Electrical Wiring | Rachel Green | In Progress | Medium | 2023-08-10 | 2023-09-07 |  | 66 | Rebar | Plot 21, Riverside | 40633.96 | 41017.43 | In progress
C004 | Warehouse D | T675 | Foundation Excavation | John Miller | Blocked | Low | 2023-02-19 | 2023-03-17 |  | 0 | Roofing Sheets | Industrial Park | 29993.36 | 32040.27 | Not started
C004 | Warehouse D | T681 | Site Survey | Rachel Green | In Progress | High | 2024-07-02 | 2024-07-29 |  | 89 | PVC Pipes | Industrial Park | 41906.06 | 31172.7 | In progress
C003 | Office Tower C | T732 | Site Survey | Dave Brown | Completed | Medium | 2023-09-27 | 2023-10-15 | 2023-10-15 | 100 | Concrete | Downtown Avenue | 31371.88 | 21799.82 | No issues
C004 | Warehouse D | T908 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2023-08-11 | 2023-08-31 |  | 0 | Rebar | Industrial Park | 27223.74 | 0 | Not started
C004 | Warehouse D | T461 | Concrete Pouring | Emma White | Completed | Low | 2024-12-24 | 2025-01-15 | 2025-01-15 | 100 | PVC Pipes | Industrial Park | 35461.77 | 39652.65 | No issues
C002 | Shopping Complex B | T291 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2024-06-06 | 2024-07-02 | 2024-07-02 | 100 | Cement | Market Street | 18208.47 | 37713.11 | No issues
C002 | Shopping Complex B | T454 | Electrical Wiring | Sarah Johnson | Completed | High | 2024-11-05 | 2024-11-12 | 2024-11-12 | 100 | PVC Pipes | Market Street | 7229.82 | 31915.05 | No issues
C004 | Warehouse D | T377 | Foundation Excavation | Dave Brown | Blocked | Low | 2023-12-16 | 2024-01-12 |  | 0 | Paint | Industrial Park | 18259.28 | 11443.21 | Not started
C002 | Shopping Complex B | T154 | Interior Painting | Grace Allen | In Progress | Low | 2023-03-19 | 2023-04-13 |  | 38 | Roofing Sheets | Market Street | 14918.52 | 40173.09 | In progress
C003 | Office Tower C | T853 | Site Survey | John Miller | Completed | Medium | 2024-07-24 | 2024-08-20 | 2024-08-20 | 100 | Cement | Downtown Avenue | 28388.92 | 21208.98 | No issues
C004 | Warehouse D | T729 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-12-16 | 2024-01-12 |  | 0 | Roofing Sheets | Industrial Park | 18430.48 | 16230.39 | Not started
C001 | Residential Building A | T841 | Electrical Wiring | Emma White | Not Started | Medium | 2023-05-22 | 2023-06-13 |  | 0 | Cement | Plot 21, Riverside | 27098.74 | 0 | Not started
C004 | Warehouse D | T504 | Site Survey | Dave Brown | In Progress | High | 2024-08-26 | 2024-09-08 |  | 23 | Rebar | Industrial Park | 30050.56 | 29011.38 | In progress
C003 | Office Tower C | T769 | Electrical Wiring | Rachel Green | Completed | High | 2023-03-20 | 2023-04-09 | 2023-04-09 | 100 | Copper Wires | Downtown Avenue | 13430.39 | 16110.02 | No issues
C002 | Shopping Complex B | T977 | Foundation Excavation | Mike Adams | In Progress | Medium | 2023-06-28 | 2023-07-28 |  | 58 | Cement | Market Street | 11575.08 | 34510.93 | In progress
C003 | Office Tower C | T893 | Steel Framework Setup | Emma White | Blocked | High | 2023-11-09 | 2023-12-01 |  | 0 | Roofing Sheets | Downtown Avenue | 38747.69 | 33406.69 | Not started
C003 | Office Tower C | T608 | Plumbing Installations | Mike Adams | In Progress | Low | 2023-02-26 | 2023-03-26 |  | 94 | Cement | Downtown Avenue | 6950.52 | 8066.97 | In progress
C001 | Residential Building A | T462 | Interior Painting | Carlos Rivera | In Progress | Medium | 2023-11-18 | 2023-12-15 |  | 74 | Concrete | Plot 21, Riverside | 11255.72 | 13309.64 | In progress
C002 | Shopping Complex B | T642 | Steel Framework Setup | Dave Brown | In Progress | High | 2024-10-02 | 2024-10-28 |  | 47 | Steel Beams | Market Street | 49390.24 | 73426.06 | In progress
C004 | Warehouse D | T540 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-05-13 | 2023-05-20 |  | 0 | Rebar | Industrial Park | 5502.4 | 0 | Not started
C001 | Residential Building A | T915 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-01-20 | 2024-02-14 |  | 83 | Roofing Sheets | Plot 21, Riverside | 7508.35 | 4729.6 | In progress
C002 | Shopping Complex B | T882 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2024-10-01 | 2024-10-25 |  | 3 | Roofing Sheets | Market Street | 11754.5 | 35192.77 | In progress
C001 | Residential Building A | T746 | Roofing | John Miller | Not Started | Medium | 2023-12-24 | 2024-01-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 21000.53 | 0 | Not started
C004 | Warehouse D | T166 | Roofing | Emma White | Blocked | High | 2023-08-11 | 2023-09-08 |  | 0 | Paint | Industrial Park | 47284.52 | 30161.49 | Not started
C003 | Office Tower C | T676 | Concrete Pouring | Dave Brown | In Progress | High | 2024-07-04 | 2024-07-29 |  | 10 | Rebar | Downtown Avenue | 20298.68 | 23116.35 | In progress
C001 | Residential Building A | T879 | Interior Painting | Emma White | Blocked | High | 2023-06-09 | 2023-06-22 |  | 0 | Copper Wires | Plot 21, Riverside | 40998.8 | 31723.83 | Not started
C002 | Shopping Complex B | T309 | Concrete Pouring | Emma White | Blocked | High | 2023-09-12 | 2023-09-21 |  | 0 | Steel Beams | Market Street | 38662.75 | 63472.69 | Not started
C004 | Warehouse D | T516 | Interior Painting | Grace Allen | Completed | High | 2023-08-28 | 2023-09-05 | 2023-09-05 | 100 | Steel Beams | Industrial Park | 21989.44 | 22177.52 | No issues
C004 | Warehouse D | T934 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2023-09-25 | 2023-10-14 |  | 67 | Paint | Industrial Park | 32234.06 | 26417.9 | In progress
C004 | Warehouse D | T427 | Foundation Excavation | Mike Adams | Not Started | High | 2024-04-05 | 2024-04-18 |  | 0 | Concrete | Industrial Park | 35096.2 | 0 | Not started
C001 | Residential Building A | T898 | Interior Painting | Mike Adams | Not Started | High | 2023-08-10 | 2023-08-17 |  | 0 | Rebar | Plot 21, Riverside | 26106.99 | 0 | Not started
C001 | Residential Building A | T694 | Foundation Excavation | Sarah Johnson | Completed | Low | 2023-11-07 | 2023-12-01 | 2023-12-01 | 100 | Cement | Plot 21, Riverside | 14191.12 | 9709 | No issues
C001 | Residential Building A | T739 | Interior Painting | John Miller | Completed | Low | 2023-12-21 | 2024-01-01 | 2024-01-01 | 100 | Copper Wires | Plot 21, Riverside | 20962.72 | 24524.03 | No issues
C003 | Office Tower C | T688 | Roofing | Mike Adams | Completed | Low | 2023-08-28 | 2023-09-12 | 2023-09-12 | 100 | PVC Pipes | Downtown Avenue | 15738.14 | 14519.45 | No issues
C003 | Office Tower C | T666 | Plumbing Installations | Dave Brown | Not Started | Low | 2024-03-20 | 2024-04-18 |  | 0 | Steel Beams | Downtown Avenue | 20968.7 | 0 | Not started
C002 | Shopping Complex B | T608 | Steel Framework Setup | Mike Adams | Completed | Low | 2024-01-25 | 2024-02-17 | 2024-02-17 | 100 | Steel Beams | Market Street | 33359.82 | 52258.69 | No issues
C004 | Warehouse D | T384 | Concrete Pouring | Sarah Johnson | In Progress | High | 2023-07-07 | 2023-07-30 |  | 42 | Paint | Industrial Park | 39250.29 | 45215.12 | In progress
C001 | Residential Building A | T751 | Interior Painting | Grace Allen | Completed | Low | 2024-05-12 | 2024-06-01 | 2024-06-01 | 100 | Copper Wires | Plot 21, Riverside | 23555.05 | 19162.1 | No issues
C004 | Warehouse D | T998 | Steel Framework Setup | Grace Allen | Completed | High | 2024-10-08 | 2024-10-21 | 2024-10-21 | 100 | Rebar | Industrial Park | 9584.23 | 11057.76 | No issues
C004 | Warehouse D | T675 | Site Survey | Grace Allen | Blocked | Low | 2024-09-05 | 2024-09-24 |  | 0 | Concrete | Industrial Park | 43594.55 | 52141.45 | Not started
C001 | Residential Building A | T142 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2024-03-04 | 2024-03-19 |  | 75 | Rebar | Plot 21, Riverside | 32596.73 | 34159.75 | In progress
C004 | Warehouse D | T300 | Interior Painting | Sarah Johnson | In Progress | Low | 2024-05-01 | 2024-05-17 |  | 95 | Rebar | Industrial Park | 30001.76 | 26089.11 | In progress
C004 | Warehouse D | T239 | Interior Painting | Rachel Green | In Progress | High | 2023-09-18 | 2023-09-27 |  | 79 | PVC Pipes | Industrial Park | 9133.42 | 10209.06 | In progress
C004 | Warehouse D | T231 | Electrical Wiring | Dave Brown | In Progress | Low | 2023-09-03 | 2023-09-25 |  | 7 | Copper Wires | Industrial Park | 40455.13 | 26362.31 | In progress
C004 | Warehouse D | T178 | Site Survey | Carlos Rivera | Blocked | High | 2023-10-03 | 2023-10-29 |  | 0 | Roofing Sheets | Industrial Park | 21674.17 | 16149.79 | Not started
C004 | Warehouse D | T459 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-04-01 | 2024-04-18 |  | 96 | PVC Pipes | Industrial Park | 16581.1 | 14539.38 | In progress
C002 | Shopping Complex B | T306 | Steel Framework Setup | Dave Brown | In Progress | High | 2024-11-07 | 2024-11-17 |  | 65 | Copper Wires | Market Street | 9036.56 | 33103.6 | In progress
C002 | Shopping Complex B | T634 | Foundation Excavation | Rachel Green | Blocked | High | 2024-03-26 | 2024-04-10 |  | 0 | Steel Beams | Market Street | 20114.33 | 49152.06 | Not started
C003 | Office Tower C | T324 | Roofing | Carlos Rivera | Completed | High | 2023-08-22 | 2023-09-17 | 2023-09-17 | 100 | Rebar | Downtown Avenue | 34051.51 | 34377.25 | No issues
C004 | Warehouse D | T160 | Foundation Excavation | Emma White | Not Started | High | 2023-01-22 | 2023-02-06 |  | 0 | Roofing Sheets | Industrial Park | 24311.47 | 0 | Not started
C004 | Warehouse D | T275 | Steel Framework Setup | Carlos Rivera | In Progress | High | 2024-09-21 | 2024-10-05 |  | 56 | Rebar | Industrial Park | 34501.17 | 38883.03 | In progress
C002 | Shopping Complex B | T255 | Roofing | Carlos Rivera | Completed | Low | 2023-06-11 | 2023-07-01 | 2023-07-01 | 100 | Cement | Market Street | 40295.71 | 69026.59 | No issues
C004 | Warehouse D | T427 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2024-08-24 | 2024-09-18 |  | 0 | Rebar | Industrial Park | 42649.61 | 37370.55 | Not started
C002 | Shopping Complex B | T692 | Site Survey | John Miller | Completed | High | 2024-09-22 | 2024-10-07 | 2024-10-07 | 100 | Paint | Market Street | 11708.86 | 38326.71 | No issues
C004 | Warehouse D | T953 | Plumbing Installations | Emma White | Not Started | Low | 2023-10-09 | 2023-11-01 |  | 0 | Copper Wires | Industrial Park | 34258.14 | 0 | Not started
C002 | Shopping Complex B | T240 | Roofing | Carlos Rivera | Blocked | High | 2024-12-22 | 2025-01-18 |  | 0 | Cement | Market Street | 22386.67 | 44255.07 | Not started
C003 | Office Tower C | T538 | Electrical Wiring | Rachel Green | Completed | Low | 2023-05-08 | 2023-05-23 | 2023-05-23 | 100 | Cement | Downtown Avenue | 19785.88 | 22111.8 | No issues
C001 | Residential Building A | T144 | Site Survey | Emma White | Completed | Low | 2024-01-03 | 2024-01-30 | 2024-01-30 | 100 | Concrete | Plot 21, Riverside | 37275.82 | 34373.33 | No issues
C002 | Shopping Complex B | T539 | Site Survey | Dave Brown | In Progress | Low | 2024-04-22 | 2024-05-09 |  | 1 | Copper Wires | Market Street | 6800.15 | 30606.18 | In progress
C003 | Office Tower C | T444 | Plumbing Installations | John Miller | Completed | Low | 2023-05-14 | 2023-06-01 | 2023-06-01 | 100 | Rebar | Downtown Avenue | 34749.51 | 38520.76 | No issues
C004 | Warehouse D | T545 | Plumbing Installations | Emma White | Not Started | High | 2023-08-23 | 2023-09-05 |  | 0 | Rebar | Industrial Park | 13561.37 | 0 | Not started
C001 | Residential Building A | T280 | Roofing | Dave Brown | Completed | Low | 2023-12-10 | 2023-12-20 | 2023-12-20 | 100 | Paint | Plot 21, Riverside | 34665.75 | 28272.43 | No issues
C002 | Shopping Complex B | T517 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-05-26 | 2024-06-12 |  | 0 | Paint | Market Street | 41622.88 | 64058.26 | Not started
C001 | Residential Building A | T720 | Concrete Pouring | Emma White | Completed | Medium | 2024-02-08 | 2024-03-04 | 2024-03-04 | 100 | Rebar | Plot 21, Riverside | 39651.56 | 45827.66 | No issues
C003 | Office Tower C | T774 | Plumbing Installations | Grace Allen | In Progress | Medium | 2024-11-16 | 2024-11-25 |  | 40 | PVC Pipes | Downtown Avenue | 42287.82 | 27419.84 | In progress
C004 | Warehouse D | T167 | Plumbing Installations | John Miller | Blocked | High | 2024-03-03 | 2024-03-25 |  | 0 | Cement | Industrial Park | 49240.74 | 54140.86 | Not started
C004 | Warehouse D | T863 | Foundation Excavation | Rachel Green | Not Started | Medium | 2024-12-09 | 2024-12-27 |  | 0 | Roofing Sheets | Industrial Park | 49584.8 | 0 | Not started
C002 | Shopping Complex B | T518 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2024-08-20 | 2024-09-02 |  | 0 | Copper Wires | Market Street | 8739.77 | 31639.7 | Not started
C003 | Office Tower C | T525 | Roofing | Emma White | Completed | Low | 2023-09-01 | 2023-09-12 | 2023-09-12 | 100 | Copper Wires | Downtown Avenue | 7411.41 | 5775.4 | No issues
C002 | Shopping Complex B | T892 | Roofing | John Miller | Not Started | Medium | 2024-09-15 | 2024-10-10 |  | 0 | Roofing Sheets | Market Street | 27361.77 | 0 | Not started
C004 | Warehouse D | T128 | Foundation Excavation | Dave Brown | In Progress | Low | 2024-06-15 | 2024-07-10 |  | 43 | Rebar | Industrial Park | 10987.18 | 10841.28 | In progress
C001 | Residential Building A | T443 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2023-04-03 | 2023-04-20 |  | 0 | Cement | Plot 21, Riverside | 13176.62 | 0 | Not started
C001 | Residential Building A | T886 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2023-01-13 | 2023-01-24 |  | 54 | PVC Pipes | Plot 21, Riverside | 9283.18 | 8217.04 | In progress
C001 | Residential Building A | T447 | Interior Painting | Carlos Rivera | Blocked | Low | 2023-05-06 | 2023-05-16 |  | 0 | Copper Wires | Plot 21, Riverside | 18308.49 | 15586.91 | Not started
C001 | Residential Building A | T915 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-08-06 | 2024-08-30 |  | 13 | Paint | Plot 21, Riverside | 38088.8 | 37200.04 | In progress
C001 | Residential Building A | T423 | Site Survey | Rachel Green | Completed | Medium | 2024-11-13 | 2024-11-30 | 2024-11-30 | 100 | Cement | Plot 21, Riverside | 49273.53 | 48272.63 | No issues
C004 | Warehouse D | T289 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-11-03 | 2024-11-11 |  | 47 | Concrete | Industrial Park | 8525.79 | 7412.35 | In progress
C002 | Shopping Complex B | T516 | Roofing | Sarah Johnson | Blocked | Low | 2023-01-01 | 2023-01-21 |  | 0 | Concrete | Market Street | 5024.39 | 30571.84 | Not started
C002 | Shopping Complex B | T231 | Foundation Excavation | John Miller | Not Started | Medium | 2024-06-08 | 2024-06-18 |  | 0 | Roofing Sheets | Market Street | 40361.06 | 0 | Not started
C004 | Warehouse D | T429 | Roofing | John Miller | Not Started | Low | 2024-05-28 | 2024-06-06 |  | 0 | Roofing Sheets | Industrial Park | 10556.37 | 0 | Not started
C002 | Shopping Complex B | T668 | Foundation Excavation | Rachel Green | Completed | Medium | 2023-12-17 | 2023-12-24 | 2023-12-24 | 100 | Roofing Sheets | Market Street | 22231.69 | 47140.98 | No issues
C003 | Office Tower C | T271 | Plumbing Installations | John Miller | In Progress | Low | 2023-08-18 | 2023-09-11 |  | 52 | Rebar | Downtown Avenue | 47060.71 | 38189.49 | In progress
C002 | Shopping Complex B | T390 | Concrete Pouring | Grace Allen | Blocked | Low | 2023-07-26 | 2023-08-22 |  | 0 | Roofing Sheets | Market Street | 20479.34 | 41834.21 | Not started
C003 | Office Tower C | T275 | Site Survey | Mike Adams | Not Started | Low | 2024-05-11 | 2024-05-20 |  | 0 | Cement | Downtown Avenue | 20485.09 | 0 | Not started
C002 | Shopping Complex B | T574 | Site Survey | Sarah Johnson | Completed | Low | 2024-07-24 | 2024-08-07 | 2024-08-07 | 100 | Paint | Market Street | 30469.95 | 47785.83 | No issues
C004 | Warehouse D | T142 | Foundation Excavation | Dave Brown | Blocked | Low | 2024-04-23 | 2024-05-12 |  | 0 | Copper Wires | Industrial Park | 37537.14 | 34640.34 | Not started
C004 | Warehouse D | T383 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2024-07-16 | 2024-08-01 | 2024-08-01 | 100 | Paint | Industrial Park | 35975.78 | 42744.52 | No issues
C001 | Residential Building A | T267 | Interior Painting | Dave Brown | In Progress | Low | 2024-03-27 | 2024-04-19 |  | 70 | PVC Pipes | Plot 21, Riverside | 26822.63 | 22371.77 | In progress
C004 | Warehouse D | T298 | Interior Painting | Dave Brown | Not Started | Low | 2024-07-02 | 2024-07-21 |  | 0 | Copper Wires | Industrial Park | 22164.86 | 0 | Not started
C001 | Residential Building A | T331 | Site Survey | Sarah Johnson | Not Started | Medium | 2024-08-21 | 2024-09-12 |  | 0 | Rebar | Plot 21, Riverside | 46174.89 | 0 | Not started
C001 | Residential Building A | T299 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-05-05 | 2023-05-20 |  | 81 | Rebar | Plot 21, Riverside | 47183.83 | 37159.04 | In progress
C002 | Shopping Complex B | T109 | Plumbing Installations | Dave Brown | Not Started | Low | 2023-08-17 | 2023-09-16 |  | 0 | Roofing Sheets | Market Street | 6407.14 | 0 | Not started
C004 | Warehouse D | T658 | Steel Framework Setup | Grace Allen | In Progress | High | 2024-05-06 | 2024-06-01 |  | 74 | Concrete | Industrial Park | 22267.02 | 20698.27 | In progress
C004 | Warehouse D | T497 | Plumbing Installations | Dave Brown | Blocked | Low | 2023-11-12 | 2023-11-29 |  | 0 | PVC Pipes | Industrial Park | 41083.27 | 41128.85 | Not started
C003 | Office Tower C | T246 | Concrete Pouring | Mike Adams | In Progress | Medium | 2024-04-19 | 2024-05-02 |  | 85 | Copper Wires | Downtown Avenue | 20567.68 | 19210.38 | In progress
C001 | Residential Building A | T210 | Foundation Excavation | Dave Brown | Not Started | Low | 2024-03-28 | 2024-04-17 |  | 0 | Cement | Plot 21, Riverside | 44680.48 | 0 | Not started
C004 | Warehouse D | T746 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-03-23 | 2024-04-06 |  | 0 | Rebar | Industrial Park | 43508.86 | 0 | Not started
C003 | Office Tower C | T441 | Roofing | Rachel Green | Not Started | Medium | 2024-02-27 | 2024-03-21 |  | 0 | Copper Wires | Downtown Avenue | 5168.3 | 0 | Not started
C003 | Office Tower C | T393 | Roofing | Mike Adams | In Progress | High | 2023-06-28 | 2023-07-27 |  | 5 | Paint | Downtown Avenue | 36358.88 | 23860.67 | In progress
C004 | Warehouse D | T587 | Interior Painting | Emma White | In Progress | Low | 2024-01-13 | 2024-02-03 |  | 77 | Concrete | Industrial Park | 45686.92 | 30544.72 | In progress
C002 | Shopping Complex B | T918 | Interior Painting | Grace Allen | Not Started | High | 2023-01-17 | 2023-02-14 |  | 0 | Steel Beams | Market Street | 12454.45 | 0 | Not started
C004 | Warehouse D | T767 | Site Survey | Mike Adams | Not Started | Low | 2024-09-02 | 2024-09-24 |  | 0 | Copper Wires | Industrial Park | 45694.12 | 0 | Not started
C004 | Warehouse D | T100 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-01-04 | 2023-01-13 |  | 0 | Paint | Industrial Park | 11772.57 | 9248.4 | Not started
C003 | Office Tower C | T516 | Roofing | Carlos Rivera | Blocked | High | 2023-02-10 | 2023-03-05 |  | 0 | Roofing Sheets | Downtown Avenue | 37826.16 | 25882.17 | Not started
C004 | Warehouse D | T390 | Foundation Excavation | Sarah Johnson | Not Started | High | 2024-08-11 | 2024-08-26 |  | 0 | Roofing Sheets | Industrial Park | 29686.41 | 0 | Not started
C003 | Office Tower C | T537 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-06-09 | 2024-06-29 |  | 0 | Steel Beams | Downtown Avenue | 37578.67 | 0 | Not started
C002 | Shopping Complex B | T308 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2023-01-19 | 2023-02-14 |  | 0 | Paint | Market Street | 25980.62 | 45188.94 | Not started
C002 | Shopping Complex B | T556 | Site Survey | Rachel Green | In Progress | Medium | 2024-08-26 | 2024-09-07 |  | 47 | Steel Beams | Market Street | 15430.17 | 41932.44 | In progress
C001 | Residential Building A | T769 | Plumbing Installations | Grace Allen | Not Started | Low | 2024-12-12 | 2025-01-11 |  | 0 | Rebar | Plot 21, Riverside | 11439.18 | 0 | Not started
C004 | Warehouse D | T949 | Foundation Excavation | Emma White | Completed | Medium | 2023-07-28 | 2023-08-06 | 2023-08-06 | 100 | Rebar | Industrial Park | 32353.48 | 36889.05 | No issues
C002 | Shopping Complex B | T956 | Site Survey | John Miller | Blocked | High | 2023-09-23 | 2023-10-08 |  | 0 | Copper Wires | Market Street | 26830.42 | 54842.03 | Not started
C004 | Warehouse D | T262 | Roofing | Grace Allen | Completed | High | 2024-05-23 | 2024-06-21 | 2024-06-21 | 100 | Rebar | Industrial Park | 15243.44 | 17539.55 | No issues
C001 | Residential Building A | T436 | Steel Framework Setup | Emma White | Completed | High | 2024-06-26 | 2024-07-16 | 2024-07-16 | 100 | Copper Wires | Plot 21, Riverside | 20095.47 | 20122.94 | No issues
C004 | Warehouse D | T934 | Foundation Excavation | Emma White | In Progress | Medium | 2024-12-24 | 2025-01-17 |  | 56 | Steel Beams | Industrial Park | 27404.81 | 27525.15 | In progress
C003 | Office Tower C | T345 | Plumbing Installations | Mike Adams | Completed | High | 2023-05-05 | 2023-05-28 | 2023-05-28 | 100 | Roofing Sheets | Downtown Avenue | 36074.27 | 33505.24 | No issues
C001 | Residential Building A | T428 | Concrete Pouring | Grace Allen | Blocked | Medium | 2024-09-16 | 2024-10-06 |  | 0 | Copper Wires | Plot 21, Riverside | 14083.46 | 14174.12 | Not started
C003 | Office Tower C | T467 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2023-09-13 | 2023-09-22 |  | 0 | Paint | Downtown Avenue | 31328.74 | 0 | Not started
C004 | Warehouse D | T127 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-04-02 | 2024-04-28 |  | 0 | Copper Wires | Industrial Park | 36362.74 | 0 | Not started
C004 | Warehouse D | T645 | Interior Painting | Grace Allen | Not Started | Low | 2023-11-20 | 2023-12-14 |  | 0 | Copper Wires | Industrial Park | 29722.03 | 0 | Not started
C004 | Warehouse D | T521 | Steel Framework Setup | Sarah Johnson | Blocked | High | 2024-04-19 | 2024-04-30 |  | 0 | Copper Wires | Industrial Park | 21003.26 | 15740.27 | Not started
C003 | Office Tower C | T221 | Interior Painting | John Miller | Blocked | High | 2024-11-16 | 2024-12-03 |  | 0 | Cement | Downtown Avenue | 47042.07 | 29832.46 | Not started
C001 | Residential Building A | T257 | Interior Painting | Rachel Green | Not Started | Medium | 2024-12-01 | 2024-12-15 |  | 0 | Paint | Plot 21, Riverside | 21409.89 | 0 | Not started
C003 | Office Tower C | T590 | Plumbing Installations | Sarah Johnson | Completed | High | 2024-02-13 | 2024-03-11 | 2024-03-11 | 100 | Concrete | Downtown Avenue | 33629.24 | 22213.73 | No issues
C004 | Warehouse D | T310 | Site Survey | Emma White | Blocked | Medium | 2023-03-12 | 2023-04-05 |  | 0 | Paint | Industrial Park | 7920.47 | 5972.03 | Not started
C002 | Shopping Complex B | T680 | Concrete Pouring | Rachel Green | In Progress | Medium | 2024-12-18 | 2025-01-03 |  | 10 | Rebar | Market Street | 32449.59 | 48955.57 | In progress
C003 | Office Tower C | T187 | Steel Framework Setup | Rachel Green | Blocked | High | 2023-11-02 | 2023-11-27 |  | 0 | Concrete | Downtown Avenue | 41487.91 | 43278.38 | Not started
C003 | Office Tower C | T719 | Roofing | Rachel Green | Not Started | High | 2023-05-10 | 2023-06-01 |  | 0 | Steel Beams | Downtown Avenue | 20335.94 | 0 | Not started
C002 | Shopping Complex B | T977 | Site Survey | Carlos Rivera | In Progress | Medium | 2024-05-22 | 2024-06-01 |  | 60 | Roofing Sheets | Market Street | 36296.62 | 58032.13 | In progress
C004 | Warehouse D | T757 | Site Survey | Carlos Rivera | Completed | Medium | 2023-02-18 | 2023-03-20 | 2023-03-20 | 100 | Roofing Sheets | Industrial Park | 13448.95 | 10770.67 | No issues
C003 | Office Tower C | T995 | Site Survey | Grace Allen | Not Started | Medium | 2024-01-26 | 2024-02-06 |  | 0 | Rebar | Downtown Avenue | 40392.07 | 0 | Not started
C002 | Shopping Complex B | T162 | Site Survey | Carlos Rivera | Not Started | Medium | 2024-06-16 | 2024-07-05 |  | 0 | Paint | Market Street | 22381.82 | 0 | Not started
C003 | Office Tower C | T661 | Electrical Wiring | Emma White | In Progress | Medium | 2023-12-14 | 2024-01-02 |  | 61 | Cement | Downtown Avenue | 27301.28 | 21715.63 | In progress
C001 | Residential Building A | T133 | Roofing | Rachel Green | Blocked | Medium | 2023-09-28 | 2023-10-05 |  | 0 | Concrete | Plot 21, Riverside | 18803.25 | 21117.61 | Not started
C003 | Office Tower C | T796 | Plumbing Installations | Dave Brown | Completed | Medium | 2024-04-14 | 2024-05-13 | 2024-05-13 | 100 | PVC Pipes | Downtown Avenue | 23284.14 | 27394.92 | No issues
C003 | Office Tower C | T175 | Interior Painting | Carlos Rivera | Completed | Medium | 2023-01-28 | 2023-02-17 | 2023-02-17 | 100 | PVC Pipes | Downtown Avenue | 6646.46 | 5730.97 | No issues
C003 | Office Tower C | T921 | Plumbing Installations | Carlos Rivera | Completed | High | 2024-03-13 | 2024-03-30 | 2024-03-30 | 100 | Rebar | Downtown Avenue | 16512.71 | 11059.75 | No issues
C001 | Residential Building A | T894 | Foundation Excavation | Sarah Johnson | Completed | Low | 2024-02-01 | 2024-02-15 | 2024-02-15 | 100 | Steel Beams | Plot 21, Riverside | 30834.63 | 27968.56 | No issues
C001 | Residential Building A | T705 | Site Survey | Grace Allen | Not Started | Low | 2023-12-27 | 2024-01-21 |  | 0 | Paint | Plot 21, Riverside | 19380.73 | 0 | Not started
C002 | Shopping Complex B | T844 | Roofing | Sarah Johnson | Completed | High | 2024-04-07 | 2024-04-28 | 2024-04-28 | 100 | Paint | Market Street | 9514.65 | 36501.82 | No issues
C003 | Office Tower C | T183 | Foundation Excavation | Emma White | Blocked | High | 2023-06-21 | 2023-06-30 |  | 0 | Roofing Sheets | Downtown Avenue | 46766.24 | 36832.39 | Not started
C002 | Shopping Complex B | T840 | Plumbing Installations | Rachel Green | Not Started | Low | 2024-02-14 | 2024-03-08 |  | 0 | Paint | Market Street | 25934.35 | 0 | Not started
C002 | Shopping Complex B | T766 | Roofing | Mike Adams | In Progress | Low | 2024-04-25 | 2024-05-25 |  | 86 | Steel Beams | Market Street | 12454.37 | 36639.52 | In progress
C004 | Warehouse D | T262 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-12-23 | 2024-01-09 |  | 37 | Cement | Industrial Park | 7416.35 | 5311.01 | In progress
C003 | Office Tower C | T921 | Concrete Pouring | John Miller | Not Started | High | 2024-07-20 | 2024-08-08 |  | 0 | Paint | Downtown Avenue | 8618.46 | 0 | Not started
C001 | Residential Building A | T439 | Foundation Excavation | Grace Allen | Completed | Medium | 2024-02-07 | 2024-02-25 | 2024-02-25 | 100 | Paint | Plot 21, Riverside | 47763.05 | 38038.89 | No issues
C001 | Residential Building A | T514 | Electrical Wiring | Grace Allen | Not Started | Low | 2024-01-14 | 2024-02-03 |  | 0 | Paint | Plot 21, Riverside | 32249.63 | 0 | Not started
C004 | Warehouse D | T575 | Foundation Excavation | Dave Brown | Not Started | Low | 2023-09-05 | 2023-09-18 |  | 0 | Cement | Industrial Park | 27129.59 | 0 | Not started
C002 | Shopping Complex B | T431 | Plumbing Installations | John Miller | Not Started | Low | 2024-05-19 | 2024-05-30 |  | 0 | Steel Beams | Market Street | 29144.79 | 0 | Not started
C004 | Warehouse D | T285 | Interior Painting | Grace Allen | Not Started | Medium | 2024-01-26 | 2024-02-12 |  | 0 | Cement | Industrial Park | 7242.98 | 0 | Not started
C002 | Shopping Complex B | T117 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-12-07 | 2023-12-17 |  | 0 | PVC Pipes | Market Street | 36559.67 | 65924.62 | Not started
C003 | Office Tower C | T195 | Concrete Pouring | John Miller | Completed | Medium | 2023-12-13 | 2024-01-06 | 2024-01-06 | 100 | Copper Wires | Downtown Avenue | 18587.05 | 12825.22 | No issues
C003 | Office Tower C | T596 | Electrical Wiring | Grace Allen | In Progress | Medium | 2024-11-07 | 2024-12-06 |  | 8 | Paint | Downtown Avenue | 6001 | 4322.22 | In progress
C003 | Office Tower C | T996 | Plumbing Installations | Rachel Green | Blocked | Medium | 2023-04-27 | 2023-05-25 |  | 0 | PVC Pipes | Downtown Avenue | 20510.89 | 22650.44 | Not started
C004 | Warehouse D | T331 | Electrical Wiring | John Miller | Completed | Medium | 2023-04-09 | 2023-05-01 | 2023-05-01 | 100 | Cement | Industrial Park | 27175.82 | 22682.01 | No issues
C003 | Office Tower C | T382 | Interior Painting | Sarah Johnson | In Progress | Medium | 2023-02-18 | 2023-03-19 |  | 88 | Cement | Downtown Avenue | 11040.86 | 8399.1 | In progress
C001 | Residential Building A | T678 | Foundation Excavation | Mike Adams | Not Started | High | 2024-03-22 | 2024-04-05 |  | 0 | Paint | Plot 21, Riverside | 5761.3 | 0 | Not started
C003 | Office Tower C | T462 | Roofing | Emma White | In Progress | High | 2023-08-09 | 2023-09-03 |  | 63 | PVC Pipes | Downtown Avenue | 29615.06 | 18764.95 | In progress
C002 | Shopping Complex B | T497 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2023-01-17 | 2023-02-03 |  | 45 | Concrete | Market Street | 6642.34 | 30681.09 | In progress
C001 | Residential Building A | T279 | Site Survey | Sarah Johnson | Not Started | High | 2024-01-18 | 2024-01-31 |  | 0 | Rebar | Plot 21, Riverside | 31605.6 | 0 | Not started
C002 | Shopping Complex B | T928 | Plumbing Installations | Emma White | Completed | Low | 2023-10-03 | 2023-10-16 | 2023-10-16 | 100 | Rebar | Market Street | 36196.3 | 66740.05 | No issues
C001 | Residential Building A | T120 | Electrical Wiring | Grace Allen | In Progress | Low | 2023-03-06 | 2023-03-16 |  | 34 | PVC Pipes | Plot 21, Riverside | 35270.37 | 39391.54 | In progress
C003 | Office Tower C | T624 | Roofing | Grace Allen | Completed | Medium | 2024-01-01 | 2024-01-14 | 2024-01-14 | 100 | Steel Beams | Downtown Avenue | 42346.16 | 26974.13 | No issues
C004 | Warehouse D | T694 | Electrical Wiring | Emma White | In Progress | High | 2023-08-27 | 2023-09-05 |  | 51 | Paint | Industrial Park | 20418.95 | 13277.58 | In progress
C002 | Shopping Complex B | T703 | Electrical Wiring | Grace Allen | In Progress | High | 2023-11-26 | 2023-12-19 |  | 98 | Rebar | Market Street | 13168.62 | 33489.27 | In progress
C003 | Office Tower C | T153 | Foundation Excavation | Mike Adams | In Progress | Medium | 2023-01-21 | 2023-01-28 |  | 50 | Copper Wires | Downtown Avenue | 22781.58 | 22054.13 | In progress
C001 | Residential Building A | T624 | Site Survey | Grace Allen | In Progress | Low | 2024-09-04 | 2024-09-23 |  | 82 | Cement | Plot 21, Riverside | 36424.94 | 27624.64 | In progress
C001 | Residential Building A | T963 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2024-07-27 | 2024-08-09 |  | 0 | Steel Beams | Plot 21, Riverside | 22844.97 | 0 | Not started
C003 | Office Tower C | T695 | Foundation Excavation | Mike Adams | Not Started | Medium | 2023-06-11 | 2023-06-29 |  | 0 | Paint | Downtown Avenue | 39397.89 | 0 | Not started
C001 | Residential Building A | T426 | Concrete Pouring | Dave Brown | Blocked | Low | 2023-10-04 | 2023-10-25 |  | 0 | Cement | Plot 21, Riverside | 20706.1 | 21188.49 | Not started
C004 | Warehouse D | T106 | Steel Framework Setup | Dave Brown | Not Started | Low | 2024-06-02 | 2024-06-10 |  | 0 | Steel Beams | Industrial Park | 6096.33 | 0 | Not started
C003 | Office Tower C | T356 | Plumbing Installations | Emma White | Blocked | Low | 2023-09-05 | 2023-10-01 |  | 0 | Paint | Downtown Avenue | 19025.21 | 20190.23 | Not started
C004 | Warehouse D | T355 | Steel Framework Setup | Mike Adams | In Progress | High | 2023-06-17 | 2023-07-05 |  | 76 | Copper Wires | Industrial Park | 25981.95 | 30053.72 | In progress
C003 | Office Tower C | T521 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-04-11 | 2023-04-28 |  | 0 | Paint | Downtown Avenue | 19491.35 | 11775.91 | Not started
C002 | Shopping Complex B | T491 | Concrete Pouring | John Miller | In Progress | High | 2023-08-23 | 2023-09-16 |  | 99 | Copper Wires | Market Street | 16951.03 | 40932.12 | In progress
C001 | Residential Building A | T547 | Foundation Excavation | Grace Allen | Completed | Medium | 2023-07-16 | 2023-08-02 | 2023-08-02 | 100 | Rebar | Plot 21, Riverside | 49810.11 | 57615.68 | No issues
C004 | Warehouse D | T133 | Site Survey | Sarah Johnson | Completed | High | 2024-10-19 | 2024-10-29 | 2024-10-29 | 100 | Cement | Industrial Park | 31225.82 | 30213.52 | No issues
C004 | Warehouse D | T244 | Roofing | Mike Adams | Completed | Medium | 2023-03-12 | 2023-03-25 | 2023-03-25 | 100 | PVC Pipes | Industrial Park | 48492.35 | 49961.8 | No issues
C001 | Residential Building A | T218 | Roofing | John Miller | Completed | Medium | 2024-08-22 | 2024-09-01 | 2024-09-01 | 100 | Paint | Plot 21, Riverside | 33609.65 | 25436.31 | No issues
C003 | Office Tower C | T130 | Steel Framework Setup | John Miller | Completed | Medium | 2024-01-19 | 2024-01-31 | 2024-01-31 | 100 | Rebar | Downtown Avenue | 46201.83 | 32565.43 | No issues
C004 | Warehouse D | T804 | Electrical Wiring | Emma White | Completed | Medium | 2024-03-27 | 2024-04-09 | 2024-04-09 | 100 | Concrete | Industrial Park | 10841.99 | 8949.31 | No issues
C003 | Office Tower C | T869 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-03-08 | 2024-03-22 |  | 0 | Paint | Downtown Avenue | 13665.45 | 12211.04 | Not started
C002 | Shopping Complex B | T933 | Interior Painting | Dave Brown | Not Started | Medium | 2023-01-28 | 2023-02-18 |  | 0 | Paint | Market Street | 29058.71 | 0 | Not started
C004 | Warehouse D | T178 | Roofing | Rachel Green | Not Started | Medium | 2024-09-23 | 2024-10-12 |  | 0 | Paint | Industrial Park | 7635.09 | 0 | Not started
C002 | Shopping Complex B | T597 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2024-01-11 | 2024-01-25 |  | 0 | PVC Pipes | Market Street | 17710.41 | 0 | Not started
C002 | Shopping Complex B | T677 | Site Survey | Dave Brown | Not Started | Low | 2024-10-12 | 2024-10-31 |  | 0 | Paint | Market Street | 11642.13 | 0 | Not started
C003 | Office Tower C | T651 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-03-07 | 2023-03-20 |  | 43 | Rebar | Downtown Avenue | 17558.15 | 20687.16 | In progress
C001 | Residential Building A | T731 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2023-11-04 | 2023-11-18 |  | 20 | Concrete | Plot 21, Riverside | 43191.12 | 42864.63 | In progress
C002 | Shopping Complex B | T509 | Site Survey | Mike Adams | Completed | Medium | 2023-02-15 | 2023-03-11 | 2023-03-11 | 100 | PVC Pipes | Market Street | 5846.44 | 29543.8 | No issues
C003 | Office Tower C | T741 | Roofing | Rachel Green | Not Started | Medium | 2024-09-03 | 2024-09-16 |  | 0 | PVC Pipes | Downtown Avenue | 15178.59 | 0 | Not started
C003 | Office Tower C | T731 | Interior Painting | Grace Allen | Blocked | Low | 2023-06-09 | 2023-06-30 |  | 0 | PVC Pipes | Downtown Avenue | 33046.06 | 34468.8 | Not started
C003 | Office Tower C | T912 | Plumbing Installations | Emma White | Not Started | Medium | 2024-06-09 | 2024-06-24 |  | 0 | Concrete | Downtown Avenue | 32152.35 | 0 | Not started
C004 | Warehouse D | T675 | Roofing | Emma White | Not Started | Medium | 2023-06-06 | 2023-06-26 |  | 0 | Roofing Sheets | Industrial Park | 8142.47 | 0 | Not started
C003 | Office Tower C | T886 | Roofing | Carlos Rivera | Blocked | High | 2023-02-20 | 2023-02-28 |  | 0 | Copper Wires | Downtown Avenue | 37931.85 | 33007.44 | Not started
C003 | Office Tower C | T664 | Concrete Pouring | John Miller | Not Started | Low | 2023-06-23 | 2023-07-12 |  | 0 | Roofing Sheets | Downtown Avenue | 43457.77 | 0 | Not started
C002 | Shopping Complex B | T239 | Plumbing Installations | Carlos Rivera | In Progress | High | 2024-11-02 | 2024-12-02 |  | 4 | Copper Wires | Market Street | 17399.1 | 38895.18 | In progress
C004 | Warehouse D | T228 | Interior Painting | Sarah Johnson | In Progress | Medium | 2023-01-12 | 2023-02-07 |  | 89 | PVC Pipes | Industrial Park | 28384.38 | 19038.2 | In progress
C003 | Office Tower C | T835 | Foundation Excavation | Dave Brown | Completed | High | 2023-07-09 | 2023-07-30 | 2023-07-30 | 100 | Concrete | Downtown Avenue | 10370.87 | 10895.24 | No issues
C004 | Warehouse D | T573 | Foundation Excavation | Dave Brown | Not Started | Medium | 2023-08-26 | 2023-09-22 |  | 0 | Copper Wires | Industrial Park | 9136.4 | 0 | Not started
C001 | Residential Building A | T318 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-06-18 | 2024-07-18 | 2024-07-18 | 100 | Roofing Sheets | Plot 21, Riverside | 42093.34 | 41735.76 | No issues
C002 | Shopping Complex B | T945 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2023-12-08 | 2023-12-24 |  | 0 | Concrete | Market Street | 39655.03 | 0 | Not started
C003 | Office Tower C | T528 | Steel Framework Setup | John Miller | Not Started | Low | 2024-01-14 | 2024-02-06 |  | 0 | Rebar | Downtown Avenue | 21010.54 | 0 | Not started
C002 | Shopping Complex B | T494 | Foundation Excavation | Dave Brown | Completed | Medium | 2024-02-13 | 2024-03-05 | 2024-03-05 | 100 | Copper Wires | Market Street | 38356.81 | 61641.88 | No issues
C003 | Office Tower C | T984 | Foundation Excavation | Grace Allen | Not Started | Medium | 2023-07-05 | 2023-07-13 |  | 0 | Steel Beams | Downtown Avenue | 40646.08 | 0 | Not started
C002 | Shopping Complex B | T926 | Roofing | Emma White | In Progress | Low | 2023-07-08 | 2023-07-22 |  | 55 | Paint | Market Street | 32071.73 | 61346.31 | In progress
C004 | Warehouse D | T968 | Interior Painting | Rachel Green | In Progress | Medium | 2024-07-17 | 2024-07-30 |  | 3 | Cement | Industrial Park | 43157.76 | 34487.4 | In progress
C003 | Office Tower C | T586 | Plumbing Installations | Dave Brown | Completed | High | 2024-03-05 | 2024-04-04 | 2024-04-04 | 100 | Paint | Downtown Avenue | 25702.4 | 28556.09 | No issues
C003 | Office Tower C | T977 | Concrete Pouring | Dave Brown | Blocked | Medium | 2023-05-13 | 2023-06-01 |  | 0 | Rebar | Downtown Avenue | 37555.2 | 35955.73 | Not started
C003 | Office Tower C | T187 | Interior Painting | Sarah Johnson | Not Started | High | 2023-06-14 | 2023-07-02 |  | 0 | Copper Wires | Downtown Avenue | 44860.23 | 0 | Not started
C002 | Shopping Complex B | T494 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2024-04-25 | 2024-05-21 |  | 0 | PVC Pipes | Market Street | 49230.65 | 55967.67 | Not started
C003 | Office Tower C | T207 | Electrical Wiring | Grace Allen | Not Started | Medium | 2023-12-25 | 2024-01-12 |  | 0 | Rebar | Downtown Avenue | 39340.03 | 0 | Not started
C001 | Residential Building A | T929 | Plumbing Installations | Mike Adams | In Progress | High | 2023-06-11 | 2023-06-21 |  | 32 | Roofing Sheets | Plot 21, Riverside | 9901.84 | 8099.08 | In progress
C003 | Office Tower C | T365 | Steel Framework Setup | Grace Allen | Blocked | Low | 2023-08-19 | 2023-09-06 |  | 0 | Steel Beams | Downtown Avenue | 22749.47 | 23840.69 | Not started
C003 | Office Tower C | T308 | Electrical Wiring | Mike Adams | Blocked | High | 2023-07-06 | 2023-07-31 |  | 0 | Paint | Downtown Avenue | 33309.11 | 35222.22 | Not started
C004 | Warehouse D | T636 | Electrical Wiring | Emma White | Not Started | Medium | 2024-02-11 | 2024-02-26 |  | 0 | Cement | Industrial Park | 35124.01 | 0 | Not started
C001 | Residential Building A | T125 | Plumbing Installations | Emma White | Blocked | High | 2023-08-15 | 2023-09-05 |  | 0 | Roofing Sheets | Plot 21, Riverside | 24641.78 | 19103.35 | Not started
C001 | Residential Building A | T772 | Interior Painting | Grace Allen | Not Started | Medium | 2024-06-22 | 2024-07-05 |  | 0 | Copper Wires | Plot 21, Riverside | 40667 | 0 | Not started
C003 | Office Tower C | T361 | Roofing | Dave Brown | Not Started | High | 2023-07-20 | 2023-08-11 |  | 0 | Steel Beams | Downtown Avenue | 9281.41 | 0 | Not started
C004 | Warehouse D | T703 | Site Survey | Sarah Johnson | Not Started | Low | 2024-03-09 | 2024-03-21 |  | 0 | Cement | Industrial Park | 39392.28 | 0 | Not started
C002 | Shopping Complex B | T700 | Interior Painting | Grace Allen | In Progress | Low | 2024-03-09 | 2024-03-18 |  | 25 | Copper Wires | Market Street | 36330.84 | 63513.03 | In progress
C001 | Residential Building A | T829 | Electrical Wiring | Sarah Johnson | Blocked | High | 2023-09-06 | 2023-09-28 |  | 0 | Paint | Plot 21, Riverside | 6565.95 | 6027.48 | Not started
C004 | Warehouse D | T857 | Foundation Excavation | Grace Allen | Not Started | High | 2023-12-01 | 2023-12-18 |  | 0 | PVC Pipes | Industrial Park | 48500.97 | 0 | Not started
C002 | Shopping Complex B | T427 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2023-08-12 | 2023-09-04 |  | 54 | Roofing Sheets | Market Street | 30397.91 | 57453.34 | In progress
C004 | Warehouse D | T433 | Electrical Wiring | Mike Adams | Completed | High | 2023-03-07 | 2023-03-21 | 2023-03-21 | 100 | Rebar | Industrial Park | 24828.28 | 29124.14 | No issues
C001 | Residential Building A | T358 | Foundation Excavation | Grace Allen | In Progress | High | 2024-11-20 | 2024-12-04 |  | 97 | Cement | Plot 21, Riverside | 43803.51 | 41467.09 | In progress
C001 | Residential Building A | T389 | Roofing | Carlos Rivera | Not Started | Low | 2024-03-15 | 2024-04-09 |  | 0 | Copper Wires | Plot 21, Riverside | 26850.78 | 0 | Not started
C003 | Office Tower C | T808 | Concrete Pouring | Grace Allen | In Progress | High | 2024-07-06 | 2024-07-15 |  | 65 | Rebar | Downtown Avenue | 41103.03 | 39858.1 | In progress
C001 | Residential Building A | T703 | Concrete Pouring | Mike Adams | In Progress | High | 2024-02-04 | 2024-02-16 |  | 81 | Paint | Plot 21, Riverside | 41912.24 | 41522.19 | In progress
C003 | Office Tower C | T767 | Plumbing Installations | Mike Adams | Not Started | High | 2024-12-05 | 2025-01-04 |  | 0 | Steel Beams | Downtown Avenue | 6282.7 | 0 | Not started
C004 | Warehouse D | T648 | Foundation Excavation | Mike Adams | Not Started | Low | 2024-04-12 | 2024-05-01 |  | 0 | PVC Pipes | Industrial Park | 19029.72 | 0 | Not started
C001 | Residential Building A | T938 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2023-07-12 | 2023-08-09 | 2023-08-09 | 100 | Paint | Plot 21, Riverside | 43212.43 | 50104.98 | No issues
C001 | Residential Building A | T406 | Foundation Excavation | Emma White | Completed | Medium | 2023-08-17 | 2023-09-01 | 2023-09-01 | 100 | PVC Pipes | Plot 21, Riverside | 39955.77 | 39864.68 | No issues
C004 | Warehouse D | T339 | Roofing | John Miller | In Progress | Medium | 2024-12-25 | 2025-01-08 |  | 15 | PVC Pipes | Industrial Park | 26249.39 | 25454.03 | In progress
C003 | Office Tower C | T401 | Roofing | Carlos Rivera | Blocked | Low | 2024-05-10 | 2024-05-18 |  | 0 | Paint | Downtown Avenue | 26070.86 | 17360.65 | Not started
C003 | Office Tower C | T621 | Interior Painting | Dave Brown | Not Started | High | 2023-09-12 | 2023-10-07 |  | 0 | Rebar | Downtown Avenue | 35012.37 | 0 | Not started
C001 | Residential Building A | T721 | Site Survey | Rachel Green | Blocked | Medium | 2023-01-14 | 2023-01-30 |  | 0 | Roofing Sheets | Plot 21, Riverside | 16797.25 | 11414.87 | Not started
C004 | Warehouse D | T903 | Interior Painting | Emma White | Blocked | Medium | 2023-12-08 | 2024-01-02 |  | 0 | Steel Beams | Industrial Park | 39170.38 | 42682.2 | Not started
C001 | Residential Building A | T201 | Steel Framework Setup | John Miller | Completed | High | 2024-05-10 | 2024-05-23 | 2024-05-23 | 100 | PVC Pipes | Plot 21, Riverside | 33809.58 | 22227.99 | No issues
C003 | Office Tower C | T730 | Concrete Pouring | Grace Allen | Completed | Medium | 2024-08-18 | 2024-09-07 | 2024-09-07 | 100 | Steel Beams | Downtown Avenue | 24162.77 | 28610.54 | No issues
C002 | Shopping Complex B | T127 | Interior Painting | Mike Adams | In Progress | Low | 2024-09-13 | 2024-09-21 |  | 61 | Roofing Sheets | Market Street | 7862.63 | 30900.7 | In progress
C003 | Office Tower C | T182 | Concrete Pouring | Emma White | In Progress | Low | 2024-03-06 | 2024-03-24 |  | 3 | Cement | Downtown Avenue | 35057.43 | 41857.35 | In progress
C003 | Office Tower C | T382 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2024-07-11 | 2024-07-31 |  | 86 | PVC Pipes | Downtown Avenue | 25383.69 | 17963.21 | In progress
C002 | Shopping Complex B | T260 | Concrete Pouring | Mike Adams | In Progress | High | 2023-12-24 | 2023-12-31 |  | 98 | Steel Beams | Market Street | 29843.61 | 53278.67 | In progress
C001 | Residential Building A | T736 | Foundation Excavation | Emma White | Blocked | High | 2024-04-20 | 2024-05-13 |  | 0 | Copper Wires | Plot 21, Riverside | 33115.92 | 24032.78 | Not started
C003 | Office Tower C | T905 | Roofing | Grace Allen | In Progress | Low | 2023-11-05 | 2023-11-27 |  | 36 | Roofing Sheets | Downtown Avenue | 33306.01 | 31192.66 | In progress
C001 | Residential Building A | T867 | Foundation Excavation | Sarah Johnson | Completed | Low | 2023-06-14 | 2023-07-13 | 2023-07-13 | 100 | Rebar | Plot 21, Riverside | 16693.89 | 18847.23 | No issues
C003 | Office Tower C | T874 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-11-19 | 2023-12-13 |  | 0 | PVC Pipes | Downtown Avenue | 22453.27 | 0 | Not started
C003 | Office Tower C | T389 | Roofing | Dave Brown | In Progress | High | 2023-08-04 | 2023-08-16 |  | 66 | Copper Wires | Downtown Avenue | 19619.01 | 18905.89 | In progress
C002 | Shopping Complex B | T120 | Site Survey | John Miller | Completed | High | 2024-12-04 | 2025-01-02 | 2025-01-02 | 100 | Concrete | Market Street | 34597.62 | 54480.87 | No issues
C002 | Shopping Complex B | T717 | Electrical Wiring | Sarah Johnson | Not Started | High | 2023-11-24 | 2023-12-10 |  | 0 | Rebar | Market Street | 11880.51 | 0 | Not started
C004 | Warehouse D | T971 | Foundation Excavation | Carlos Rivera | Completed | Low | 2023-03-15 | 2023-04-01 | 2023-04-01 | 100 | Copper Wires | Industrial Park | 21789.64 | 23367.77 | No issues
C004 | Warehouse D | T140 | Plumbing Installations | Emma White | Not Started | Medium | 2023-09-20 | 2023-10-14 |  | 0 | Rebar | Industrial Park | 24714.23 | 0 | Not started
C003 | Office Tower C | T889 | Steel Framework Setup | Rachel Green | Not Started | Medium | 2024-07-07 | 2024-07-28 |  | 0 | Concrete | Downtown Avenue | 24573.85 | 0 | Not started
C003 | Office Tower C | T594 | Roofing | Mike Adams | Not Started | Low | 2023-10-05 | 2023-10-31 |  | 0 | Steel Beams | Downtown Avenue | 30828.12 | 0 | Not started
C004 | Warehouse D | T222 | Concrete Pouring | Emma White | Completed | High | 2023-12-16 | 2024-01-11 | 2024-01-11 | 100 | Cement | Industrial Park | 21789.26 | 23269.72 | No issues
C003 | Office Tower C | T373 | Steel Framework Setup | Grace Allen | Blocked | Low | 2023-10-17 | 2023-10-24 |  | 0 | Paint | Downtown Avenue | 35282.64 | 41178.5 | Not started
C002 | Shopping Complex B | T456 | Concrete Pouring | Emma White | Completed | Low | 2024-10-03 | 2024-10-10 | 2024-10-10 | 100 | Steel Beams | Market Street | 40058.48 | 59957.8 | No issues
C001 | Residential Building A | T385 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2023-05-08 | 2023-05-23 |  | 0 | Roofing Sheets | Plot 21, Riverside | 11858.8 | 9982.62 | Not started
C004 | Warehouse D | T816 | Site Survey | Rachel Green | Blocked | Medium | 2024-10-14 | 2024-11-12 |  | 0 | Rebar | Industrial Park | 32950.1 | 27861.34 | Not started
C002 | Shopping Complex B | T677 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2023-02-04 | 2023-03-03 |  | 0 | Paint | Market Street | 40050.93 | 0 | Not started
C002 | Shopping Complex B | T596 | Electrical Wiring | Grace Allen | In Progress | Low | 2024-05-11 | 2024-06-10 |  | 84 | Rebar | Market Street | 25150.33 | 49592.46 | In progress
C002 | Shopping Complex B | T339 | Electrical Wiring | Dave Brown | Not Started | High | 2023-03-23 | 2023-04-08 |  | 0 | Concrete | Market Street | 21657.86 | 0 | Not started
C004 | Warehouse D | T330 | Roofing | Carlos Rivera | Blocked | Medium | 2023-03-06 | 2023-03-20 |  | 0 | Copper Wires | Industrial Park | 27994.74 | 28159.26 | Not started
C003 | Office Tower C | T241 | Roofing | Emma White | Blocked | Medium | 2024-12-17 | 2025-01-14 |  | 0 | Rebar | Downtown Avenue | 14515.02 | 10754.35 | Not started
C003 | Office Tower C | T930 | Foundation Excavation | Grace Allen | Not Started | High | 2024-12-12 | 2024-12-31 |  | 0 | Paint | Downtown Avenue | 41258.17 | 0 | Not started
C003 | Office Tower C | T761 | Site Survey | John Miller | Not Started | High | 2024-05-18 | 2024-06-02 |  | 0 | Rebar | Downtown Avenue | 30997.67 | 0 | Not started
C001 | Residential Building A | T692 | Interior Painting | Rachel Green | Not Started | Medium | 2023-06-10 | 2023-07-07 |  | 0 | Paint | Plot 21, Riverside | 22065.25 | 0 | Not started
C001 | Residential Building A | T828 | Interior Painting | Grace Allen | Blocked | High | 2023-09-28 | 2023-10-20 |  | 0 | Roofing Sheets | Plot 21, Riverside | 42148.16 | 35033.53 | Not started
C001 | Residential Building A | T872 | Site Survey | John Miller | Completed | High | 2023-12-24 | 2024-01-11 | 2024-01-11 | 100 | Rebar | Plot 21, Riverside | 26139.98 | 25500.38 | No issues
C003 | Office Tower C | T302 | Interior Painting | Rachel Green | Completed | Medium | 2024-12-06 | 2024-12-15 | 2024-12-15 | 100 | Copper Wires | Downtown Avenue | 30166.02 | 22010.29 | No issues
C003 | Office Tower C | T684 | Plumbing Installations | Emma White | Blocked | High | 2024-02-05 | 2024-02-26 |  | 0 | PVC Pipes | Downtown Avenue | 48511.52 | 46437.76 | Not started
C004 | Warehouse D | T737 | Steel Framework Setup | Mike Adams | Completed | Low | 2023-07-19 | 2023-08-08 | 2023-08-08 | 100 | Roofing Sheets | Industrial Park | 31193.16 | 31570.86 | No issues
C003 | Office Tower C | T937 | Steel Framework Setup | Rachel Green | In Progress | Medium | 2023-07-10 | 2023-08-08 |  | 68 | Roofing Sheets | Downtown Avenue | 11091.5 | 7692.92 | In progress
C002 | Shopping Complex B | T884 | Foundation Excavation | John Miller | Not Started | Low | 2024-11-26 | 2024-12-17 |  | 0 | Concrete | Market Street | 30795.26 | 0 | Not started
C002 | Shopping Complex B | T789 | Steel Framework Setup | Sarah Johnson | Completed | High | 2023-02-12 | 2023-03-11 | 2023-03-11 | 100 | Steel Beams | Market Street | 5830.35 | 30187.74 | No issues
C002 | Shopping Complex B | T482 | Concrete Pouring | Mike Adams | Completed | High | 2023-01-13 | 2023-02-11 | 2023-02-11 | 100 | Roofing Sheets | Market Street | 15428.01 | 35928.99 | No issues
C002 | Shopping Complex B | T890 | Site Survey | Sarah Johnson | Not Started | Medium | 2023-07-20 | 2023-08-06 |  | 0 | Paint | Market Street | 14397.9 | 0 | Not started
C001 | Residential Building A | T157 | Concrete Pouring | Sarah Johnson | Completed | High | 2024-06-11 | 2024-06-20 | 2024-06-20 | 100 | Copper Wires | Plot 21, Riverside | 24898.78 | 21156.45 | No issues
C002 | Shopping Complex B | T820 | Interior Painting | Emma White | Blocked | Medium | 2024-10-04 | 2024-10-12 |  | 0 | Steel Beams | Market Street | 29783.31 | 50326.13 | Not started
C003 | Office Tower C | T127 | Concrete Pouring | Grace Allen | Blocked | Low | 2023-06-05 | 2023-07-05 |  | 0 | Copper Wires | Downtown Avenue | 25772.89 | 26465.68 | Not started
C003 | Office Tower C | T152 | Interior Painting | Sarah Johnson | Completed | Low | 2023-10-13 | 2023-11-12 | 2023-11-12 | 100 | Rebar | Downtown Avenue | 23134.33 | 14525.02 | No issues
C003 | Office Tower C | T246 | Roofing | Sarah Johnson | Not Started | Medium | 2023-01-06 | 2023-01-22 |  | 0 | Cement | Downtown Avenue | 27833.96 | 0 | Not started
C004 | Warehouse D | T253 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2024-02-16 | 2024-03-04 |  | 0 | PVC Pipes | Industrial Park | 38775.84 | 24739.35 | Not started
C002 | Shopping Complex B | T499 | Roofing | Dave Brown | Not Started | Low | 2023-12-05 | 2023-12-13 |  | 0 | Copper Wires | Market Street | 41646.56 | 0 | Not started
C001 | Residential Building A | T905 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-07-02 | 2024-07-10 |  | 0 | Cement | Plot 21, Riverside | 34114.89 | 31960.99 | Not started
C004 | Warehouse D | T640 | Steel Framework Setup | Carlos Rivera | Completed | High | 2024-06-03 | 2024-06-14 | 2024-06-14 | 100 | Concrete | Industrial Park | 23990.4 | 25710.13 | No issues
C004 | Warehouse D | T230 | Concrete Pouring | Rachel Green | Not Started | Low | 2023-08-23 | 2023-08-30 |  | 0 | Rebar | Industrial Park | 33286.93 | 0 | Not started
C002 | Shopping Complex B | T719 | Interior Painting | Rachel Green | Not Started | Medium | 2023-07-27 | 2023-08-09 |  | 0 | Copper Wires | Market Street | 33635.92 | 0 | Not started
C004 | Warehouse D | T145 | Site Survey | Rachel Green | Not Started | Medium | 2024-06-16 | 2024-07-14 |  | 0 | Steel Beams | Industrial Park | 29265.33 | 0 | Not started
C002 | Shopping Complex B | T590 | Electrical Wiring | John Miller | Completed | High | 2024-03-03 | 2024-03-23 | 2024-03-23 | 100 | Steel Beams | Market Street | 11129.17 | 35522.69 | No issues
C003 | Office Tower C | T884 | Plumbing Installations | Grace Allen | In Progress | Medium | 2023-12-10 | 2023-12-19 |  | 35 | Cement | Downtown Avenue | 35636.16 | 27098.28 | In progress
C004 | Warehouse D | T236 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-01-08 | 2023-01-21 |  | 0 | Rebar | Industrial Park | 36300.17 | 0 | Not started
C001 | Residential Building A | T533 | Site Survey | Sarah Johnson | Blocked | Medium | 2023-01-21 | 2023-02-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 30517.12 | 28967.22 | Not started
C001 | Residential Building A | T282 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2023-05-16 | 2023-06-02 |  | 0 | Cement | Plot 21, Riverside | 37262.03 | 0 | Not started
C004 | Warehouse D | T816 | Roofing | Mike Adams | Completed | High | 2024-02-16 | 2024-03-11 | 2024-03-11 | 100 | Copper Wires | Industrial Park | 15994.91 | 11470.41 | No issues
C003 | Office Tower C | T580 | Steel Framework Setup | Rachel Green | In Progress | Medium | 2024-06-22 | 2024-07-20 |  | 58 | PVC Pipes | Downtown Avenue | 15066.17 | 12238.69 | In progress
C001 | Residential Building A | T589 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2023-10-04 | 2023-10-16 |  | 0 | Paint | Plot 21, Riverside | 25575.47 | 17884.52 | Not started
C002 | Shopping Complex B | T892 | Steel Framework Setup | Rachel Green | Not Started | Medium | 2023-07-11 | 2023-08-08 |  | 0 | Concrete | Market Street | 42699.48 | 0 | Not started
C003 | Office Tower C | T530 | Foundation Excavation | John Miller | Not Started | Low | 2024-10-09 | 2024-10-17 |  | 0 | Paint | Downtown Avenue | 39838.02 | 0 | Not started
C004 | Warehouse D | T277 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-05-17 | 2023-06-09 |  | 94 | Roofing Sheets | Industrial Park | 45165.17 | 50198.92 | In progress
C003 | Office Tower C | T322 | Roofing | Carlos Rivera | Blocked | High | 2023-11-14 | 2023-12-09 |  | 0 | Cement | Downtown Avenue | 32965.49 | 31825.59 | Not started
C004 | Warehouse D | T866 | Plumbing Installations | Emma White | Completed | Low | 2024-03-21 | 2024-03-29 | 2024-03-29 | 100 | Copper Wires | Industrial Park | 39840.01 | 45271.04 | No issues
C001 | Residential Building A | T984 | Roofing | Dave Brown | Blocked | High | 2024-06-13 | 2024-06-24 |  | 0 | Rebar | Plot 21, Riverside | 34514.96 | 39883.07 | Not started
C002 | Shopping Complex B | T274 | Roofing | Dave Brown | Completed | Medium | 2023-10-25 | 2023-11-07 | 2023-11-07 | 100 | Copper Wires | Market Street | 7072.06 | 33568.26 | No issues
C004 | Warehouse D | T161 | Plumbing Installations | Rachel Green | Completed | Low | 2024-12-03 | 2024-12-10 | 2024-12-10 | 100 | Rebar | Industrial Park | 41492 | 43929.54 | No issues
C001 | Residential Building A | T576 | Electrical Wiring | Rachel Green | Completed | Medium | 2024-01-20 | 2024-02-08 | 2024-02-08 | 100 | Concrete | Plot 21, Riverside | 32501.47 | 20613.18 | No issues
C001 | Residential Building A | T258 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2023-03-16 | 2023-03-23 |  | 0 | PVC Pipes | Plot 21, Riverside | 10760.19 | 0 | Not started
C001 | Residential Building A | T796 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-07-26 | 2023-08-13 |  | 0 | Rebar | Plot 21, Riverside | 30372.49 | 20472.99 | Not started
C001 | Residential Building A | T726 | Electrical Wiring | John Miller | Completed | Low | 2024-11-19 | 2024-12-07 | 2024-12-07 | 100 | Cement | Plot 21, Riverside | 9346.8 | 7712.56 | No issues
C003 | Office Tower C | T621 | Electrical Wiring | Mike Adams | In Progress | High | 2023-01-09 | 2023-01-29 |  | 5 | Concrete | Downtown Avenue | 46141.53 | 29634.08 | In progress
C003 | Office Tower C | T829 | Concrete Pouring | John Miller | Completed | Medium | 2024-04-18 | 2024-05-13 | 2024-05-13 | 100 | Paint | Downtown Avenue | 25471.28 | 17631.69 | No issues
C001 | Residential Building A | T595 | Foundation Excavation | John Miller | Not Started | High | 2023-05-09 | 2023-05-22 |  | 0 | Rebar | Plot 21, Riverside | 25711.93 | 0 | Not started
C004 | Warehouse D | T781 | Steel Framework Setup | Dave Brown | Blocked | Low | 2023-05-13 | 2023-05-30 |  | 0 | Rebar | Industrial Park | 23812.6 | 17882.58 | Not started
C004 | Warehouse D | T105 | Site Survey | Grace Allen | Not Started | High | 2024-01-18 | 2024-01-29 |  | 0 | Steel Beams | Industrial Park | 48259.1 | 0 | Not started
C004 | Warehouse D | T309 | Site Survey | John Miller | Blocked | High | 2023-01-10 | 2023-01-26 |  | 0 | Cement | Industrial Park | 14206.6 | 15522.84 | Not started
C004 | Warehouse D | T331 | Site Survey | Dave Brown | Blocked | High | 2024-02-18 | 2024-03-16 |  | 0 | Cement | Industrial Park | 34199.05 | 31441.67 | Not started
C004 | Warehouse D | T563 | Concrete Pouring | John Miller | Completed | High | 2024-10-04 | 2024-10-14 | 2024-10-14 | 100 | Copper Wires | Industrial Park | 9165.12 | 7275.42 | No issues
C001 | Residential Building A | T999 | Foundation Excavation | Dave Brown | Completed | High | 2023-08-13 | 2023-09-03 | 2023-09-03 | 100 | Paint | Plot 21, Riverside | 48492.14 | 57292.04 | No issues
C002 | Shopping Complex B | T315 | Concrete Pouring | Dave Brown | In Progress | High | 2024-04-13 | 2024-05-03 |  | 77 | Cement | Market Street | 41412.33 | 57356.37 | In progress
C002 | Shopping Complex B | T230 | Plumbing Installations | Sarah Johnson | Blocked | High | 2024-01-01 | 2024-01-27 |  | 0 | Copper Wires | Market Street | 43915.42 | 64450.94 | Not started
C003 | Office Tower C | T364 | Site Survey | Mike Adams | In Progress | Medium | 2024-04-28 | 2024-05-16 |  | 50 | Copper Wires | Downtown Avenue | 17199.52 | 13976.34 | In progress
C001 | Residential Building A | T131 | Steel Framework Setup | Grace Allen | In Progress | Low | 2024-05-11 | 2024-06-05 |  | 44 | Roofing Sheets | Plot 21, Riverside | 11256.23 | 7857.07 | In progress
C004 | Warehouse D | T989 | Roofing | Dave Brown | In Progress | High | 2024-06-01 | 2024-07-01 |  | 3 | Cement | Industrial Park | 8969.14 | 6429.5 | In progress
C003 | Office Tower C | T672 | Steel Framework Setup | Dave Brown | Completed | Medium | 2024-02-17 | 2024-02-26 | 2024-02-26 | 100 | Rebar | Downtown Avenue | 29476.22 | 21330.69 | No issues
C002 | Shopping Complex B | T617 | Plumbing Installations | Emma White | Completed | Low | 2024-12-03 | 2024-12-21 | 2024-12-21 | 100 | Cement | Market Street | 12385.14 | 34064.68 | No issues
C003 | Office Tower C | T814 | Foundation Excavation | John Miller | In Progress | High | 2023-09-19 | 2023-10-06 |  | 42 | Paint | Downtown Avenue | 37999.48 | 44560.66 | In progress
C002 | Shopping Complex B | T741 | Site Survey | Sarah Johnson | Completed | Medium | 2024-03-14 | 2024-03-29 | 2024-03-29 | 100 | PVC Pipes | Market Street | 24906.4 | 47099.25 | No issues
C002 | Shopping Complex B | T259 | Foundation Excavation | Grace Allen | Blocked | Medium | 2024-11-09 | 2024-11-24 |  | 0 | Roofing Sheets | Market Street | 30792.87 | 57918.48 | Not started
C003 | Office Tower C | T866 | Electrical Wiring | Rachel Green | In Progress | Low | 2023-08-10 | 2023-09-09 |  | 5 | Roofing Sheets | Downtown Avenue | 19601.88 | 12926.33 | In progress
C002 | Shopping Complex B | T675 | Roofing | Mike Adams | In Progress | Medium | 2024-01-08 | 2024-01-26 |  | 77 | Cement | Market Street | 42818.04 | 68664.71 | In progress
C002 | Shopping Complex B | T722 | Interior Painting | Emma White | Blocked | Medium | 2024-05-10 | 2024-06-04 |  | 0 | Steel Beams | Market Street | 29772.14 | 51717.7 | Not started
C001 | Residential Building A | T169 | Electrical Wiring | Dave Brown | Completed | High | 2023-09-12 | 2023-09-25 | 2023-09-25 | 100 | Roofing Sheets | Plot 21, Riverside | 23946.15 | 23815.92 | No issues
C003 | Office Tower C | T852 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-07-04 | 2024-07-29 | 2024-07-29 | 100 | PVC Pipes | Downtown Avenue | 19356.61 | 21176.24 | No issues
C001 | Residential Building A | T841 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2024-02-02 | 2024-02-13 |  | 0 | Copper Wires | Plot 21, Riverside | 31904.58 | 0 | Not started
C001 | Residential Building A | T538 | Electrical Wiring | Emma White | In Progress | Low | 2023-02-03 | 2023-02-18 |  | 7 | Copper Wires | Plot 21, Riverside | 28145.97 | 31584.88 | In progress
C002 | Shopping Complex B | T941 | Electrical Wiring | John Miller | Completed | Medium | 2024-09-28 | 2024-10-24 | 2024-10-24 | 100 | Paint | Market Street | 11992.77 | 33858.66 | No issues
C002 | Shopping Complex B | T655 | Interior Painting | John Miller | Blocked | High | 2024-06-02 | 2024-06-23 |  | 0 | Cement | Market Street | 11210.5 | 37502.7 | Not started
C002 | Shopping Complex B | T206 | Concrete Pouring | Emma White | Not Started | Low | 2024-12-08 | 2024-12-30 |  | 0 | Roofing Sheets | Market Street | 17099.56 | 0 | Not started
C002 | Shopping Complex B | T364 | Foundation Excavation | John Miller | In Progress | Medium | 2024-10-22 | 2024-11-02 |  | 10 | Cement | Market Street | 17850.77 | 43431.81 | In progress
C002 | Shopping Complex B | T912 | Site Survey | Carlos Rivera | In Progress | Medium | 2023-07-20 | 2023-08-13 |  | 30 | Paint | Market Street | 32130.14 | 46001.87 | In progress
C003 | Office Tower C | T267 | Concrete Pouring | Dave Brown | Completed | High | 2024-04-08 | 2024-05-01 | 2024-05-01 | 100 | Rebar | Downtown Avenue | 9968.27 | 6627.1 | No issues
C002 | Shopping Complex B | T783 | Plumbing Installations | Carlos Rivera | Not Started | High | 2024-04-03 | 2024-04-12 |  | 0 | Paint | Market Street | 39263.66 | 0 | Not started
C003 | Office Tower C | T774 | Electrical Wiring | Sarah Johnson | Not Started | High | 2023-08-27 | 2023-09-06 |  | 0 | Roofing Sheets | Downtown Avenue | 11581.27 | 0 | Not started
C004 | Warehouse D | T494 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-07-21 | 2024-08-07 |  | 24 | Concrete | Industrial Park | 32044.7 | 24548.78 | In progress
C003 | Office Tower C | T226 | Roofing | Emma White | In Progress | High | 2023-11-26 | 2023-12-03 |  | 88 | Rebar | Downtown Avenue | 18004.16 | 12833.77 | In progress
C001 | Residential Building A | T944 | Concrete Pouring | John Miller | Not Started | Low | 2024-08-15 | 2024-08-30 |  | 0 | Rebar | Plot 21, Riverside | 18635.49 | 0 | Not started
C003 | Office Tower C | T177 | Electrical Wiring | Mike Adams | Not Started | Low | 2023-07-02 | 2023-08-01 |  | 0 | Concrete | Downtown Avenue | 41129.13 | 0 | Not started
C001 | Residential Building A | T262 | Concrete Pouring | Rachel Green | In Progress | High | 2024-04-21 | 2024-05-20 |  | 76 | Steel Beams | Plot 21, Riverside | 6497.49 | 5838.98 | In progress
C004 | Warehouse D | T893 | Roofing | Mike Adams | Completed | Medium | 2024-11-19 | 2024-12-02 | 2024-12-02 | 100 | Paint | Industrial Park | 38763.8 | 40974.53 | No issues
C004 | Warehouse D | T818 | Foundation Excavation | Sarah Johnson | Completed | High | 2023-05-20 | 2023-06-09 | 2023-06-09 | 100 | Paint | Industrial Park | 37074.5 | 38530.34 | No issues
C001 | Residential Building A | T355 | Plumbing Installations | Dave Brown | Blocked | High | 2024-05-07 | 2024-05-31 |  | 0 | Paint | Plot 21, Riverside | 27613.67 | 29729.29 | Not started
C001 | Residential Building A | T603 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-03-15 | 2024-04-07 |  | 58 | Roofing Sheets | Plot 21, Riverside | 25185.36 | 19088.67 | In progress
C004 | Warehouse D | T519 | Steel Framework Setup | Dave Brown | In Progress | High | 2023-08-07 | 2023-09-05 |  | 52 | Rebar | Industrial Park | 17732.15 | 15035.98 | In progress
C002 | Shopping Complex B | T745 | Interior Painting | Rachel Green | Completed | High | 2023-07-26 | 2023-08-07 | 2023-08-07 | 100 | Rebar | Market Street | 11265.49 | 38498.39 | No issues
C004 | Warehouse D | T419 | Plumbing Installations | John Miller | Not Started | High | 2024-09-03 | 2024-09-28 |  | 0 | Steel Beams | Industrial Park | 28268.97 | 0 | Not started
C004 | Warehouse D | T907 | Site Survey | Grace Allen | Not Started | Medium | 2024-10-23 | 2024-11-17 |  | 0 | Rebar | Industrial Park | 28690.85 | 0 | Not started
C003 | Office Tower C | T753 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-08-25 | 2024-09-14 |  | 0 | Rebar | Downtown Avenue | 11559.53 | 0 | Not started
C002 | Shopping Complex B | T420 | Foundation Excavation | Carlos Rivera | Blocked | Low | 2023-08-19 | 2023-09-01 |  | 0 | Steel Beams | Market Street | 21132.6 | 43548.2 | Not started
C001 | Residential Building A | T850 | Roofing | Grace Allen | Completed | High | 2024-07-13 | 2024-07-30 | 2024-07-30 | 100 | Roofing Sheets | Plot 21, Riverside | 24582.35 | 16387.51 | No issues
C004 | Warehouse D | T243 | Concrete Pouring | Rachel Green | Blocked | Low | 2023-11-09 | 2023-12-04 |  | 0 | Rebar | Industrial Park | 37278.32 | 36360.98 | Not started
C004 | Warehouse D | T630 | Concrete Pouring | Rachel Green | In Progress | Low | 2023-07-26 | 2023-08-18 |  | 58 | PVC Pipes | Industrial Park | 46015.24 | 42255.67 | In progress
C002 | Shopping Complex B | T852 | Plumbing Installations | Grace Allen | Blocked | High | 2023-02-09 | 2023-02-18 |  | 0 | Copper Wires | Market Street | 43189.84 | 59854.68 | Not started
C003 | Office Tower C | T622 | Interior Painting | Grace Allen | Completed | Medium | 2023-12-06 | 2023-12-30 | 2023-12-30 | 100 | Roofing Sheets | Downtown Avenue | 26936.75 | 24400.59 | No issues
C003 | Office Tower C | T896 | Site Survey | Rachel Green | Not Started | High | 2024-06-19 | 2024-07-06 |  | 0 | Concrete | Downtown Avenue | 6439.94 | 0 | Not started
C004 | Warehouse D | T409 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-10-11 | 2024-10-18 |  | 0 | Cement | Industrial Park | 19167.96 | 11815.54 | Not started
C003 | Office Tower C | T804 | Site Survey | Rachel Green | Blocked | Low | 2023-12-22 | 2024-01-11 |  | 0 | Cement | Downtown Avenue | 24939.34 | 29714.54 | Not started
C004 | Warehouse D | T772 | Roofing | Sarah Johnson | In Progress | Low | 2024-10-17 | 2024-11-07 |  | 68 | Steel Beams | Industrial Park | 5934.21 | 5756.32 | In progress
C001 | Residential Building A | T427 | Concrete Pouring | John Miller | Blocked | Medium | 2024-11-08 | 2024-11-15 |  | 0 | Paint | Plot 21, Riverside | 29914.5 | 20295.38 | Not started
C003 | Office Tower C | T823 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2023-01-03 | 2023-01-30 |  | 45 | PVC Pipes | Downtown Avenue | 41761.25 | 25373.85 | In progress
C003 | Office Tower C | T834 | Steel Framework Setup | Mike Adams | Not Started | High | 2024-11-27 | 2024-12-26 |  | 0 | Concrete | Downtown Avenue | 12968.38 | 0 | Not started
C004 | Warehouse D | T195 | Plumbing Installations | Grace Allen | Blocked | Low | 2024-11-26 | 2024-12-16 |  | 0 | Rebar | Industrial Park | 39646.48 | 33171.39 | Not started
C002 | Shopping Complex B | T734 | Site Survey | Dave Brown | Completed | High | 2023-06-07 | 2023-07-01 | 2023-07-01 | 100 | Concrete | Market Street | 36547.72 | 52611.09 | No issues
C004 | Warehouse D | T203 | Concrete Pouring | Mike Adams | In Progress | Medium | 2024-09-24 | 2024-10-11 |  | 58 | Concrete | Industrial Park | 31356.71 | 34968.92 | In progress
C002 | Shopping Complex B | T531 | Site Survey | Carlos Rivera | Blocked | Medium | 2023-10-17 | 2023-11-07 |  | 0 | Paint | Market Street | 43722.69 | 72999.22 | Not started
C004 | Warehouse D | T305 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2023-04-21 | 2023-05-07 |  | 74 | Roofing Sheets | Industrial Park | 13239.04 | 11716.9 | In progress
C004 | Warehouse D | T974 | Roofing | Rachel Green | Not Started | Medium | 2023-05-03 | 2023-05-18 |  | 0 | Copper Wires | Industrial Park | 37270.05 | 0 | Not started
C002 | Shopping Complex B | T117 | Concrete Pouring | Carlos Rivera | Blocked | High | 2024-05-03 | 2024-05-17 |  | 0 | Concrete | Market Street | 9263.3 | 31577.66 | Not started
C002 | Shopping Complex B | T921 | Interior Painting | Emma White | Not Started | High | 2024-06-26 | 2024-07-05 |  | 0 | Cement | Market Street | 36147.14 | 0 | Not started
C004 | Warehouse D | T452 | Electrical Wiring | Sarah Johnson | In Progress | High | 2023-09-25 | 2023-10-23 |  | 66 | PVC Pipes | Industrial Park | 40674.33 | 26578.66 | In progress
C003 | Office Tower C | T892 | Steel Framework Setup | Grace Allen | Completed | High | 2024-01-07 | 2024-01-25 | 2024-01-25 | 100 | Steel Beams | Downtown Avenue | 48809.96 | 55765.81 | No issues
C002 | Shopping Complex B | T340 | Site Survey | Sarah Johnson | Completed | High | 2023-12-13 | 2024-01-01 | 2024-01-01 | 100 | Roofing Sheets | Market Street | 39740.76 | 70796.99 | No issues
C004 | Warehouse D | T188 | Foundation Excavation | Rachel Green | Blocked | Medium | 2024-10-07 | 2024-11-01 |  | 0 | Copper Wires | Industrial Park | 11766.43 | 7201.95 | Not started
C004 | Warehouse D | T730 | Site Survey | Rachel Green | Completed | Low | 2024-09-02 | 2024-09-13 | 2024-09-13 | 100 | Steel Beams | Industrial Park | 10818.38 | 12534.34 | No issues
C003 | Office Tower C | T466 | Electrical Wiring | John Miller | Completed | Low | 2023-03-12 | 2023-03-27 | 2023-03-27 | 100 | Concrete | Downtown Avenue | 37924.52 | 28626.74 | No issues
C003 | Office Tower C | T216 | Steel Framework Setup | John Miller | In Progress | High | 2023-09-19 | 2023-10-02 |  | 42 | Copper Wires | Downtown Avenue | 17569.47 | 15556.16 | In progress
C001 | Residential Building A | T235 | Interior Painting | Mike Adams | Blocked | Medium | 2023-05-04 | 2023-05-31 |  | 0 | Paint | Plot 21, Riverside | 15408.31 | 16994.3 | Not started
C001 | Residential Building A | T985 | Foundation Excavation | Rachel Green | Blocked | High | 2023-07-21 | 2023-08-08 |  | 0 | Roofing Sheets | Plot 21, Riverside | 27583.14 | 17733.9 | Not started
C004 | Warehouse D | T334 | Electrical Wiring | Carlos Rivera | Blocked | High | 2023-05-01 | 2023-05-27 |  | 0 | Concrete | Industrial Park | 16684.54 | 14325.99 | Not started
C004 | Warehouse D | T114 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2024-05-12 | 2024-06-01 | 2024-06-01 | 100 | Copper Wires | Industrial Park | 44711.41 | 46191.94 | No issues
C002 | Shopping Complex B | T555 | Concrete Pouring | John Miller | Blocked | High | 2023-10-22 | 2023-11-20 |  | 0 | Steel Beams | Market Street | 33129.62 | 62416.67 | Not started
C003 | Office Tower C | T988 | Site Survey | Sarah Johnson | Not Started | High | 2023-06-16 | 2023-07-10 |  | 0 | Roofing Sheets | Downtown Avenue | 13716.04 | 0 | Not started
C001 | Residential Building A | T291 | Electrical Wiring | Dave Brown | Blocked | High | 2024-09-23 | 2024-10-19 |  | 0 | Paint | Plot 21, Riverside | 11924 | 12308.19 | Not started
C002 | Shopping Complex B | T785 | Electrical Wiring | Grace Allen | In Progress | Medium | 2023-08-26 | 2023-09-10 |  | 98 | Rebar | Market Street | 40806.03 | 72938.45 | In progress
C001 | Residential Building A | T400 | Site Survey | Rachel Green | In Progress | Low | 2023-11-16 | 2023-12-08 |  | 68 | Copper Wires | Plot 21, Riverside | 44568.87 | 28179.45 | In progress
C002 | Shopping Complex B | T948 | Steel Framework Setup | Rachel Green | Completed | High | 2023-01-08 | 2023-01-24 | 2023-01-24 | 100 | Rebar | Market Street | 42575.6 | 66996.54 | No issues
C002 | Shopping Complex B | T129 | Concrete Pouring | Mike Adams | Not Started | Medium | 2023-03-27 | 2023-04-09 |  | 0 | Rebar | Market Street | 29175.11 | 0 | Not started
C004 | Warehouse D | T215 | Interior Painting | Grace Allen | Not Started | Medium | 2024-06-01 | 2024-06-13 |  | 0 | Paint | Industrial Park | 41745.26 | 0 | Not started
C001 | Residential Building A | T145 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-02-21 | 2023-03-01 |  | 0 | PVC Pipes | Plot 21, Riverside | 39760.17 | 0 | Not started
C004 | Warehouse D | T110 | Interior Painting | Rachel Green | Completed | Medium | 2024-06-13 | 2024-06-26 | 2024-06-26 | 100 | Concrete | Industrial Park | 14372.89 | 14781.69 | No issues
C003 | Office Tower C | T617 | Interior Painting | Rachel Green | In Progress | High | 2024-10-12 | 2024-11-05 |  | 23 | Steel Beams | Downtown Avenue | 11184.81 | 7750.66 | In progress
C001 | Residential Building A | T674 | Concrete Pouring | Rachel Green | Blocked | High | 2023-07-08 | 2023-07-28 |  | 0 | Concrete | Plot 21, Riverside | 7905.35 | 9341.71 | Not started
C002 | Shopping Complex B | T372 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2024-02-23 | 2024-03-11 |  | 0 | Roofing Sheets | Market Street | 32848.75 | 0 | Not started
C001 | Residential Building A | T472 | Site Survey | Emma White | Blocked | Low | 2024-05-20 | 2024-06-04 |  | 0 | Steel Beams | Plot 21, Riverside | 49840.02 | 36062.62 | Not started
C001 | Residential Building A | T803 | Foundation Excavation | Dave Brown | Not Started | Medium | 2023-10-03 | 2023-10-30 |  | 0 | Concrete | Plot 21, Riverside | 27241.2 | 0 | Not started
C004 | Warehouse D | T546 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2024-10-16 | 2024-10-27 |  | 0 | Rebar | Industrial Park | 24077.82 | 0 | Not started
C002 | Shopping Complex B | T849 | Site Survey | Carlos Rivera | Blocked | Low | 2024-08-23 | 2024-09-12 |  | 0 | Rebar | Market Street | 25661.22 | 41247.65 | Not started
C004 | Warehouse D | T529 | Interior Painting | Mike Adams | Blocked | Medium | 2024-12-04 | 2024-12-26 |  | 0 | Steel Beams | Industrial Park | 45903.61 | 31235.15 | Not started
C001 | Residential Building A | T998 | Interior Painting | Carlos Rivera | Blocked | Low | 2023-07-20 | 2023-08-07 |  | 0 | Copper Wires | Plot 21, Riverside | 34300.63 | 35440.61 | Not started
C003 | Office Tower C | T430 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2024-08-16 | 2024-09-06 |  | 0 | Steel Beams | Downtown Avenue | 33694.07 | 0 | Not started
C002 | Shopping Complex B | T267 | Interior Painting | Carlos Rivera | Blocked | Low | 2024-08-11 | 2024-09-08 |  | 0 | Rebar | Market Street | 18226.34 | 39002.66 | Not started
C004 | Warehouse D | T936 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2023-03-10 | 2023-03-21 |  | 0 | Steel Beams | Industrial Park | 43159.2 | 0 | Not started
C003 | Office Tower C | T726 | Roofing | John Miller | In Progress | Medium | 2023-11-19 | 2023-12-01 |  | 29 | Paint | Downtown Avenue | 8727.31 | 5802.74 | In progress
C001 | Residential Building A | T275 | Site Survey | John Miller | Completed | Medium | 2024-02-17 | 2024-03-04 | 2024-03-04 | 100 | Concrete | Plot 21, Riverside | 47525.72 | 49488.05 | No issues
C004 | Warehouse D | T151 | Concrete Pouring | John Miller | Blocked | Medium | 2024-01-14 | 2024-02-12 |  | 0 | Copper Wires | Industrial Park | 11512.19 | 10930.92 | Not started
C002 | Shopping Complex B | T707 | Plumbing Installations | Dave Brown | Blocked | Low | 2023-08-07 | 2023-08-24 |  | 0 | PVC Pipes | Market Street | 23817.13 | 40534.28 | Not started
C004 | Warehouse D | T835 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2023-03-16 | 2023-03-29 |  | 0 | Roofing Sheets | Industrial Park | 21870.52 | 14749.96 | In progress
C001 | Residential Building A | T624 | Interior Painting | Dave Brown | Completed | Medium | 2024-09-16 | 2024-10-09 | 2024-10-09 | 100 | Copper Wires | Plot 21, Riverside | 13977.44 | 12639.09 | No issues
C004 | Warehouse D | T656 | Concrete Pouring | Rachel Green | Completed | High | 2023-03-25 | 2023-04-22 | 2023-04-22 | 100 | Roofing Sheets | Industrial Park | 24174.07 | 26268.21 | No issues
C003 | Office Tower C | T798 | Steel Framework Setup | Dave Brown | Blocked | Low | 2024-02-12 | 2024-03-07 |  | 0 | Steel Beams | Downtown Avenue | 21173.86 | 22398.39 | Not started
C004 | Warehouse D | T898 | Site Survey | Sarah Johnson | In Progress | High | 2024-01-13 | 2024-02-06 |  | 85 | Concrete | Industrial Park | 24763.01 | 15368.66 | In progress
C004 | Warehouse D | T326 | Site Survey | Emma White | Blocked | High | 2023-04-03 | 2023-05-03 |  | 0 | Cement | Industrial Park | 7356.6 | 6677.39 | Not started
C001 | Residential Building A | T492 | Interior Painting | Rachel Green | Not Started | High | 2024-07-10 | 2024-07-19 |  | 0 | PVC Pipes | Plot 21, Riverside | 9174.74 | 0 | Not started
C003 | Office Tower C | T258 | Interior Painting | Dave Brown | In Progress | Medium | 2024-02-12 | 2024-03-03 |  | 93 | Paint | Downtown Avenue | 17394.63 | 14798.15 | In progress
C004 | Warehouse D | T813 | Roofing | Grace Allen | Completed | High | 2023-03-01 | 2023-03-20 | 2023-03-20 | 100 | Copper Wires | Industrial Park | 46618.56 | 50910.33 | No issues
C001 | Residential Building A | T443 | Plumbing Installations | Dave Brown | In Progress | Low | 2023-03-25 | 2023-04-15 |  | 53 | Roofing Sheets | Plot 21, Riverside | 21147.49 | 16282.8 | In progress
C002 | Shopping Complex B | T725 | Site Survey | Emma White | Not Started | Low | 2023-11-09 | 2023-11-18 |  | 0 | Copper Wires | Market Street | 16041.29 | 0 | Not started
C004 | Warehouse D | T233 | Steel Framework Setup | Mike Adams | In Progress | Low | 2023-04-07 | 2023-04-29 |  | 56 | Rebar | Industrial Park | 37564.94 | 44319.61 | In progress
C001 | Residential Building A | T490 | Roofing | Emma White | In Progress | Medium | 2023-07-09 | 2023-08-03 |  | 49 | PVC Pipes | Plot 21, Riverside | 23933.71 | 23681.08 | In progress
C004 | Warehouse D | T218 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-03-12 | 2024-04-02 |  | 0 | Concrete | Industrial Park | 8300.31 | 7629.77 | Not started
C002 | Shopping Complex B | T824 | Interior Painting | Dave Brown | Not Started | Low | 2024-12-19 | 2025-01-11 |  | 0 | Steel Beams | Market Street | 8927.73 | 0 | Not started
C001 | Residential Building A | T796 | Plumbing Installations | John Miller | Blocked | Low | 2023-09-15 | 2023-09-24 |  | 0 | PVC Pipes | Plot 21, Riverside | 21765.5 | 13665.06 | Not started
C004 | Warehouse D | T115 | Plumbing Installations | Grace Allen | Blocked | High | 2023-09-06 | 2023-10-06 |  | 0 | Roofing Sheets | Industrial Park | 5430 | 4249.07 | Not started
C004 | Warehouse D | T249 | Foundation Excavation | Rachel Green | In Progress | Low | 2023-02-16 | 2023-02-26 |  | 16 | Paint | Industrial Park | 18638.01 | 14725.29 | In progress
C003 | Office Tower C | T770 | Foundation Excavation | Carlos Rivera | Completed | High | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100 | Concrete | Downtown Avenue | 25624.22 | 26743.86 | No issues
C001 | Residential Building A | T539 | Steel Framework Setup | John Miller | Blocked | High | 2023-01-14 | 2023-02-05 |  | 0 | PVC Pipes | Plot 21, Riverside | 30526.01 | 34803.49 | Not started
C002 | Shopping Complex B | T427 | Roofing | Emma White | Blocked | Low | 2023-04-05 | 2023-05-01 |  | 0 | Rebar | Market Street | 8761.39 | 35646.36 | Not started
C002 | Shopping Complex B | T695 | Plumbing Installations | Emma White | In Progress | Medium | 2024-09-27 | 2024-10-12 |  | 97 | Paint | Market Street | 23720.98 | 42409.14 | In progress
C004 | Warehouse D | T972 | Electrical Wiring | John Miller | Completed | Low | 2024-11-09 | 2024-11-16 | 2024-11-16 | 100 | Steel Beams | Industrial Park | 37693.88 | 32486.27 | No issues
C003 | Office Tower C | T176 | Interior Painting | Mike Adams | In Progress | High | 2023-02-02 | 2023-02-17 |  | 61 | Copper Wires | Downtown Avenue | 48596.58 | 42487.05 | In progress
C002 | Shopping Complex B | T744 | Plumbing Installations | Dave Brown | In Progress | High | 2023-03-15 | 2023-04-06 |  | 60 | Steel Beams | Market Street | 34385.19 | 61359.7 | In progress
C003 | Office Tower C | T821 | Plumbing Installations | Emma White | Blocked | High | 2023-11-03 | 2023-11-20 |  | 0 | Rebar | Downtown Avenue | 10837.08 | 8719.56 | Not started
C003 | Office Tower C | T739 | Foundation Excavation | Rachel Green | Blocked | Low | 2023-04-15 | 2023-05-11 |  | 0 | Rebar | Downtown Avenue | 16515.69 | 15126.55 | Not started
C003 | Office Tower C | T568 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2024-06-02 | 2024-06-22 |  | 0 | Rebar | Downtown Avenue | 11915.29 | 9193.17 | Not started
C004 | Warehouse D | T165 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2024-08-21 | 2024-09-09 | 2024-09-09 | 100 | Concrete | Industrial Park | 36446.9 | 34032.47 | No issues
C001 | Residential Building A | T912 | Electrical Wiring | John Miller | Not Started | High | 2023-01-18 | 2023-01-26 |  | 0 | Cement | Plot 21, Riverside | 12697.89 | 0 | Not started
C004 | Warehouse D | T405 | Interior Painting | Sarah Johnson | In Progress | Medium | 2023-10-23 | 2023-11-22 |  | 27 | Roofing Sheets | Industrial Park | 27423.89 | 20858.46 | In progress
C003 | Office Tower C | T953 | Electrical Wiring | Mike Adams | Blocked | Low | 2023-07-12 | 2023-08-05 |  | 0 | Paint | Downtown Avenue | 20298.28 | 13666.01 | Not started
C003 | Office Tower C | T665 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2023-07-03 | 2023-07-28 |  | 0 | Steel Beams | Downtown Avenue | 18072.68 | 0 | Not started
C002 | Shopping Complex B | T112 | Foundation Excavation | Grace Allen | In Progress | Low | 2023-05-20 | 2023-06-16 |  | 41 | Copper Wires | Market Street | 48590.47 | 81406.94 | In progress
C001 | Residential Building A | T302 | Foundation Excavation | Mike Adams | Not Started | High | 2023-03-04 | 2023-04-03 |  | 0 | Copper Wires | Plot 21, Riverside | 27290.36 | 0 | Not started
C004 | Warehouse D | T787 | Interior Painting | John Miller | In Progress | Medium | 2024-06-15 | 2024-06-24 |  | 10 | Roofing Sheets | Industrial Park | 6535.13 | 6182.5 | In progress
C001 | Residential Building A | T674 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2023-04-17 | 2023-05-05 |  | 0 | Paint | Plot 21, Riverside | 49026.06 | 0 | Not started
C003 | Office Tower C | T425 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-07-12 | 2023-08-11 |  | 0 | Roofing Sheets | Downtown Avenue | 18008.51 | 0 | Not started
C003 | Office Tower C | T925 | Interior Painting | Emma White | Completed | Medium | 2023-08-23 | 2023-09-09 | 2023-09-09 | 100 | Cement | Downtown Avenue | 47960.17 | 49683.37 | No issues
C004 | Warehouse D | T568 | Roofing | Sarah Johnson | In Progress | High | 2023-01-08 | 2023-01-17 |  | 36 | Paint | Industrial Park | 43470.69 | 27297.08 | In progress
C004 | Warehouse D | T968 | Roofing | Emma White | In Progress | High | 2024-07-13 | 2024-08-08 |  | 40 | Copper Wires | Industrial Park | 12604.57 | 7725.46 | In progress
C001 | Residential Building A | T953 | Site Survey | Emma White | Not Started | High | 2024-01-01 | 2024-01-08 |  | 0 | Steel Beams | Plot 21, Riverside | 22641.46 | 0 | Not started
C002 | Shopping Complex B | T585 | Roofing | Carlos Rivera | In Progress | High | 2024-06-17 | 2024-07-05 |  | 47 | Rebar | Market Street | 16993.25 | 38445.25 | In progress
C004 | Warehouse D | T653 | Concrete Pouring | Dave Brown | Blocked | High | 2023-06-23 | 2023-07-03 |  | 0 | Concrete | Industrial Park | 49140.12 | 52835.14 | Not started
C004 | Warehouse D | T583 | Electrical Wiring | Emma White | Completed | High | 2024-12-26 | 2025-01-12 | 2025-01-12 | 100 | Steel Beams | Industrial Park | 33260.28 | 32032.85 | No issues
C004 | Warehouse D | T978 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-09-20 | 2024-10-01 | 2024-10-01 | 100 | Copper Wires | Industrial Park | 34531.57 | 27852.67 | No issues
C002 | Shopping Complex B | T471 | Roofing | Grace Allen | Blocked | Low | 2024-07-24 | 2024-08-23 |  | 0 | Cement | Market Street | 40699.68 | 60393.4 | Not started
C001 | Residential Building A | T216 | Interior Painting | John Miller | Completed | High | 2024-08-17 | 2024-09-13 | 2024-09-13 | 100 | Copper Wires | Plot 21, Riverside | 12611.82 | 14053.66 | No issues
C002 | Shopping Complex B | T587 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-12-06 | 2024-12-15 |  | 0 | PVC Pipes | Market Street | 8702.25 | 0 | Not started
C002 | Shopping Complex B | T128 | Interior Painting | John Miller | Blocked | High | 2024-09-28 | 2024-10-22 |  | 0 | Concrete | Market Street | 14571.14 | 40164.62 | Not started
C001 | Residential Building A | T936 | Roofing | Mike Adams | Completed | Medium | 2023-10-09 | 2023-10-29 | 2023-10-29 | 100 | Paint | Plot 21, Riverside | 15382.26 | 16628.22 | No issues
C002 | Shopping Complex B | T942 | Interior Painting | Rachel Green | In Progress | Low | 2024-04-13 | 2024-04-25 |  | 54 | Cement | Market Street | 28264.61 | 45419.1 | In progress
C002 | Shopping Complex B | T852 | Foundation Excavation | Emma White | Not Started | High | 2023-11-08 | 2023-11-26 |  | 0 | Copper Wires | Market Street | 24947.63 | 0 | Not started
C003 | Office Tower C | T131 | Steel Framework Setup | Emma White | Completed | High | 2024-02-11 | 2024-02-24 | 2024-02-24 | 100 | Cement | Downtown Avenue | 42887.84 | 27786.58 | No issues
C002 | Shopping Complex B | T916 | Plumbing Installations | Sarah Johnson | Not Started | High | 2023-03-01 | 2023-03-23 |  | 0 | Cement | Market Street | 26258.28 | 0 | Not started
C004 | Warehouse D | T176 | Roofing | Emma White | Blocked | High | 2023-01-24 | 2023-02-10 |  | 0 | Roofing Sheets | Industrial Park | 35805.86 | 28492.16 | Not started
C002 | Shopping Complex B | T139 | Foundation Excavation | Emma White | Completed | High | 2024-12-05 | 2024-12-26 | 2024-12-26 | 100 | Rebar | Market Street | 35982.5 | 65949.4 | No issues
C004 | Warehouse D | T798 | Roofing | John Miller | In Progress | High | 2023-09-01 | 2023-09-25 |  | 73 | Cement | Industrial Park | 11570.62 | 7778.01 | In progress
C002 | Shopping Complex B | T492 | Roofing | Rachel Green | In Progress | Low | 2024-06-21 | 2024-07-05 |  | 41 | Cement | Market Street | 40463.8 | 50800.38 | In progress
C003 | Office Tower C | T270 | Site Survey | Dave Brown | Completed | High | 2023-05-05 | 2023-06-03 | 2023-06-03 | 100 | PVC Pipes | Downtown Avenue | 14738.97 | 10005.79 | No issues
C003 | Office Tower C | T188 | Plumbing Installations | Mike Adams | Completed | High | 2024-01-04 | 2024-01-30 | 2024-01-30 | 100 | Cement | Downtown Avenue | 7058.51 | 7509.47 | No issues
C001 | Residential Building A | T412 | Foundation Excavation | Carlos Rivera | Completed | Medium | 2023-12-18 | 2024-01-08 | 2024-01-08 | 100 | Paint | Plot 21, Riverside | 10435.94 | 7122.38 | No issues
C004 | Warehouse D | T386 | Roofing | Emma White | Not Started | Medium | 2023-06-22 | 2023-06-30 |  | 0 | Steel Beams | Industrial Park | 33231.91 | 0 | Not started
C003 | Office Tower C | T643 | Steel Framework Setup | Emma White | In Progress | Low | 2023-11-24 | 2023-12-16 |  | 86 | PVC Pipes | Downtown Avenue | 43801.77 | 49777.77 | In progress
C004 | Warehouse D | T499 | Foundation Excavation | Grace Allen | Completed | Low | 2023-10-04 | 2023-10-20 | 2023-10-20 | 100 | Concrete | Industrial Park | 24385.77 | 24514.38 | No issues
C001 | Residential Building A | T575 | Interior Painting | Dave Brown | Completed | Low | 2024-08-05 | 2024-08-21 | 2024-08-21 | 100 | Roofing Sheets | Plot 21, Riverside | 26123.19 | 21192.15 | No issues
C001 | Residential Building A | T462 | Roofing | Sarah Johnson | Not Started | Low | 2024-04-13 | 2024-05-05 |  | 0 | PVC Pipes | Plot 21, Riverside | 32951.55 | 0 | Not started
C003 | Office Tower C | T414 | Concrete Pouring | Rachel Green | Completed | Low | 2024-05-25 | 2024-06-05 | 2024-06-05 | 100 | Cement | Downtown Avenue | 45024.98 | 39312.05 | No issues
C001 | Residential Building A | T156 | Roofing | Rachel Green | In Progress | Low | 2024-01-10 | 2024-01-20 |  | 14 | Cement | Plot 21, Riverside | 38172.21 | 40463.59 | In progress
C003 | Office Tower C | T176 | Roofing | John Miller | In Progress | Medium | 2024-07-17 | 2024-08-14 |  | 30 | PVC Pipes | Downtown Avenue | 39145.32 | 37978.44 | In progress
C001 | Residential Building A | T210 | Roofing | Mike Adams | Not Started | Low | 2024-06-10 | 2024-06-22 |  | 0 | PVC Pipes | Plot 21, Riverside | 47126.39 | 0 | Not started
C002 | Shopping Complex B | T226 | Interior Painting | Carlos Rivera | Not Started | Medium | 2023-06-04 | 2023-06-29 |  | 0 | Steel Beams | Market Street | 38392.17 | 0 | Not started
C003 | Office Tower C | T200 | Foundation Excavation | Rachel Green | Not Started | High | 2023-05-15 | 2023-06-03 |  | 0 | Steel Beams | Downtown Avenue | 44471.76 | 0 | Not started
C004 | Warehouse D | T149 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-03-03 | 2023-03-19 |  | 0 | Rebar | Industrial Park | 19957.4 | 0 | Not started
C001 | Residential Building A | T802 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2024-03-08 | 2024-03-17 |  | 0 | Rebar | Plot 21, Riverside | 27285.18 | 21153.9 | Not started
C004 | Warehouse D | T938 | Concrete Pouring | Rachel Green | Completed | Medium | 2024-10-28 | 2024-11-07 | 2024-11-07 | 100 | Steel Beams | Industrial Park | 16697.03 | 14736.66 | No issues
C002 | Shopping Complex B | T324 | Concrete Pouring | Carlos Rivera | Completed | Low | 2024-12-26 | 2025-01-09 | 2025-01-09 | 100 | Steel Beams | Market Street | 39476.53 | 64417.93 | No issues
C003 | Office Tower C | T357 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-12-22 | 2024-01-07 |  | 0 | Cement | Downtown Avenue | 8723.95 | 0 | Not started
C003 | Office Tower C | T236 | Electrical Wiring | Grace Allen | Not Started | Low | 2023-11-10 | 2023-11-17 |  | 0 | Rebar | Downtown Avenue | 17808.82 | 0 | Not started
C001 | Residential Building A | T914 | Interior Painting | Dave Brown | Not Started | Medium | 2024-05-23 | 2024-06-15 |  | 0 | Steel Beams | Plot 21, Riverside | 10539.49 | 0 | Not started
C001 | Residential Building A | T907 | Plumbing Installations | Rachel Green | In Progress | High | 2023-12-10 | 2024-01-08 |  | 33 | Steel Beams | Plot 21, Riverside | 40507.81 | 32421.41 | In progress
C003 | Office Tower C | T660 | Site Survey | Grace Allen | In Progress | Low | 2023-07-20 | 2023-08-08 |  | 73 | Steel Beams | Downtown Avenue | 30409.73 | 35915.2 | In progress
C003 | Office Tower C | T940 | Concrete Pouring | John Miller | In Progress | Low | 2023-03-14 | 2023-03-25 |  | 56 | Copper Wires | Downtown Avenue | 31533.53 | 25328.26 | In progress
C004 | Warehouse D | T155 | Steel Framework Setup | John Miller | Blocked | Low | 2024-09-22 | 2024-10-03 |  | 0 | PVC Pipes | Industrial Park | 42206.55 | 37066.86 | Not started
C002 | Shopping Complex B | T192 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-06-16 | 2023-06-26 |  | 0 | Rebar | Market Street | 48679.58 | 0 | Not started
C002 | Shopping Complex B | T763 | Electrical Wiring | Dave Brown | Blocked | Medium | 2023-10-09 | 2023-11-01 |  | 0 | Cement | Market Street | 27936.24 | 50939.25 | Not started
C002 | Shopping Complex B | T151 | Interior Painting | Emma White | Not Started | High | 2023-02-20 | 2023-03-15 |  | 0 | Paint | Market Street | 30400.78 | 0 | Not started
C004 | Warehouse D | T668 | Roofing | John Miller | Not Started | Low | 2023-06-03 | 2023-06-15 |  | 0 | Cement | Industrial Park | 48797.32 | 0 | Not started
C003 | Office Tower C | T167 | Foundation Excavation | Mike Adams | Not Started | Medium | 2023-04-14 | 2023-05-10 |  | 0 | Concrete | Downtown Avenue | 43367.69 | 0 | Not started
C004 | Warehouse D | T681 | Roofing | Rachel Green | Not Started | Medium | 2023-05-05 | 2023-05-19 |  | 0 | Steel Beams | Industrial Park | 42430.7 | 0 | Not started
C002 | Shopping Complex B | T804 | Plumbing Installations | Carlos Rivera | Not Started | Medium | 2023-06-22 | 2023-07-22 |  | 0 | Roofing Sheets | Market Street | 7728.22 | 0 | Not started
C003 | Office Tower C | T321 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2024-03-03 | 2024-03-16 |  | 0 | Steel Beams | Downtown Avenue | 15629.13 | 9411.79 | Not started
C003 | Office Tower C | T477 | Roofing | Grace Allen | Blocked | High | 2023-12-02 | 2023-12-09 |  | 0 | Steel Beams | Downtown Avenue | 30624.38 | 24295.57 | Not started
C004 | Warehouse D | T288 | Roofing | Grace Allen | Completed | Low | 2024-05-01 | 2024-05-08 | 2024-05-08 | 100 | Roofing Sheets | Industrial Park | 11147.93 | 12095.91 | No issues
C002 | Shopping Complex B | T437 | Steel Framework Setup | John Miller | Not Started | Medium | 2024-04-05 | 2024-05-02 |  | 0 | Concrete | Market Street | 12765.61 | 0 | Not started
C002 | Shopping Complex B | T821 | Site Survey | John Miller | Not Started | High | 2023-04-23 | 2023-05-14 |  | 0 | Roofing Sheets | Market Street | 32471.81 | 0 | Not started
C003 | Office Tower C | T839 | Electrical Wiring | Emma White | In Progress | Medium | 2023-10-27 | 2023-11-15 |  | 87 | Copper Wires | Downtown Avenue | 8544.43 | 9611.36 | In progress
C001 | Residential Building A | T835 | Roofing | Mike Adams | Blocked | High | 2023-06-22 | 2023-07-16 |  | 0 | Rebar | Plot 21, Riverside | 27983.31 | 17555.73 | Not started
C001 | Residential Building A | T149 | Electrical Wiring | Rachel Green | In Progress | High | 2024-12-25 | 2025-01-08 |  | 69 | Copper Wires | Plot 21, Riverside | 5039.14 | 4589.72 | In progress
C002 | Shopping Complex B | T941 | Interior Painting | Emma White | Blocked | Medium | 2024-06-04 | 2024-06-17 |  | 0 | Copper Wires | Market Street | 36207.16 | 63520.11 | Not started
C002 | Shopping Complex B | T845 | Site Survey | Grace Allen | Blocked | Low | 2024-08-10 | 2024-09-07 |  | 0 | Roofing Sheets | Market Street | 19357.42 | 45556.65 | Not started
C002 | Shopping Complex B | T143 | Interior Painting | Grace Allen | In Progress | High | 2023-03-27 | 2023-04-25 |  | 62 | Roofing Sheets | Market Street | 15333.74 | 38885.64 | In progress
C001 | Residential Building A | T903 | Interior Painting | Mike Adams | Completed | Low | 2024-01-12 | 2024-01-28 | 2024-01-28 | 100 | Copper Wires | Plot 21, Riverside | 34832.01 | 39953.36 | No issues
C004 | Warehouse D | T141 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2024-09-14 | 2024-10-05 |  | 0 | Concrete | Industrial Park | 6123.67 | 6021.11 | Not started
C003 | Office Tower C | T101 | Site Survey | John Miller | In Progress | Low | 2024-12-24 | 2025-01-17 |  | 89 | Cement | Downtown Avenue | 19728.32 | 15868.81 | In progress
C002 | Shopping Complex B | T828 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2023-10-13 | 2023-11-11 |  | 0 | Roofing Sheets | Market Street | 23220.07 | 42396.3 | Not started
C004 | Warehouse D | T513 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2024-04-09 | 2024-05-03 |  | 63 | Copper Wires | Industrial Park | 32461.88 | 26241.11 | In progress
C004 | Warehouse D | T137 | Electrical Wiring | John Miller | In Progress | Low | 2024-09-05 | 2024-09-21 |  | 71 | Rebar | Industrial Park | 17057.48 | 14779.7 | In progress
C004 | Warehouse D | T518 | Foundation Excavation | Grace Allen | Blocked | Medium | 2024-05-21 | 2024-06-09 |  | 0 | Steel Beams | Industrial Park | 21231.9 | 24472.85 | Not started
C002 | Shopping Complex B | T504 | Steel Framework Setup | Mike Adams | In Progress | High | 2023-02-06 | 2023-02-28 |  | 1 | Copper Wires | Market Street | 17384.49 | 36447.3 | In progress
C004 | Warehouse D | T433 | Plumbing Installations | Grace Allen | Blocked | Medium | 2024-01-01 | 2024-01-24 |  | 0 | Steel Beams | Industrial Park | 12389.53 | 11367.22 | Not started
C002 | Shopping Complex B | T897 | Plumbing Installations | Grace Allen | In Progress | High | 2023-02-04 | 2023-02-24 |  | 51 | Steel Beams | Market Street | 34126.94 | 54563.9 | In progress
C003 | Office Tower C | T371 | Foundation Excavation | Sarah Johnson | Not Started | High | 2023-01-28 | 2023-02-19 |  | 0 | PVC Pipes | Downtown Avenue | 34137.44 | 0 | Not started
C003 | Office Tower C | T869 | Concrete Pouring | Mike Adams | Not Started | Medium | 2024-04-10 | 2024-04-18 |  | 0 | Paint | Downtown Avenue | 48944.17 | 0 | Not started
C002 | Shopping Complex B | T262 | Site Survey | Grace Allen | Blocked | Low | 2023-07-20 | 2023-08-12 |  | 0 | PVC Pipes | Market Street | 49455.8 | 81475.78 | Not started
C004 | Warehouse D | T889 | Interior Painting | Grace Allen | Not Started | Low | 2024-05-05 | 2024-05-15 |  | 0 | Paint | Industrial Park | 40341.55 | 0 | Not started
C001 | Residential Building A | T580 | Electrical Wiring | Carlos Rivera | Completed | High | 2024-01-09 | 2024-01-21 | 2024-01-21 | 100 | Cement | Plot 21, Riverside | 6297.47 | 3810.59 | No issues
C002 | Shopping Complex B | T424 | Plumbing Installations | John Miller | Completed | Low | 2024-08-16 | 2024-09-02 | 2024-09-02 | 100 | Concrete | Market Street | 32401.42 | 46705.6 | No issues
C004 | Warehouse D | T844 | Electrical Wiring | Rachel Green | Blocked | Medium | 2024-06-14 | 2024-06-28 |  | 0 | PVC Pipes | Industrial Park | 37733.6 | 43358.66 | Not started
C003 | Office Tower C | T903 | Plumbing Installations | Emma White | Not Started | Low | 2024-03-03 | 2024-03-13 |  | 0 | Concrete | Downtown Avenue | 5127.55 | 0 | Not started
C003 | Office Tower C | T641 | Site Survey | Rachel Green | Not Started | Low | 2024-02-03 | 2024-02-20 |  | 0 | Copper Wires | Downtown Avenue | 38690.14 | 0 | Not started
C004 | Warehouse D | T393 | Foundation Excavation | John Miller | Completed | High | 2023-05-10 | 2023-05-27 | 2023-05-27 | 100 | Copper Wires | Industrial Park | 39035.52 | 42166.36 | No issues
C003 | Office Tower C | T384 | Steel Framework Setup | Sarah Johnson | Blocked | High | 2024-01-08 | 2024-01-18 |  | 0 | Roofing Sheets | Downtown Avenue | 34201.06 | 22009.28 | Not started
C002 | Shopping Complex B | T936 | Plumbing Installations | Emma White | In Progress | Low | 2023-12-20 | 2024-01-10 |  | 73 | Copper Wires | Market Street | 13624.22 | 41624.49 | In progress
C003 | Office Tower C | T157 | Electrical Wiring | Mike Adams | In Progress | Low | 2024-06-16 | 2024-06-27 |  | 54 | Cement | Downtown Avenue | 13348.13 | 13561.63 | In progress
C003 | Office Tower C | T570 | Plumbing Installations | Sarah Johnson | In Progress | Medium | 2024-08-12 | 2024-08-22 |  | 11 | Paint | Downtown Avenue | 21099.14 | 23258.52 | In progress
C004 | Warehouse D | T206 | Roofing | Dave Brown | Not Started | Low | 2024-02-05 | 2024-03-04 |  | 0 | PVC Pipes | Industrial Park | 27225.14 | 0 | Not started
C002 | Shopping Complex B | T722 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2023-11-13 | 2023-12-02 |  | 0 | PVC Pipes | Market Street | 40486.11 | 68851.44 | Not started
C004 | Warehouse D | T418 | Electrical Wiring | Dave Brown | In Progress | High | 2024-10-17 | 2024-11-13 |  | 23 | Paint | Industrial Park | 9781.41 | 8693.46 | In progress
C004 | Warehouse D | T482 | Concrete Pouring | Mike Adams | In Progress | High | 2023-03-27 | 2023-04-14 |  | 57 | Concrete | Industrial Park | 6629.34 | 5447.76 | In progress
C002 | Shopping Complex B | T676 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-02-03 | 2023-02-10 |  | 0 | PVC Pipes | Market Street | 38357.61 | 62288.71 | Not started
C001 | Residential Building A | T572 | Site Survey | Rachel Green | Completed | Medium | 2024-11-12 | 2024-11-30 | 2024-11-30 | 100 | Rebar | Plot 21, Riverside | 31649.81 | 19266.44 | No issues
C003 | Office Tower C | T158 | Foundation Excavation | John Miller | In Progress | Medium | 2024-02-06 | 2024-03-04 |  | 66 | Copper Wires | Downtown Avenue | 20242.83 | 21271.48 | In progress
C002 | Shopping Complex B | T560 | Electrical Wiring | Emma White | Not Started | High | 2024-07-16 | 2024-08-13 |  | 0 | Rebar | Market Street | 40965.09 | 0 | Not started
C003 | Office Tower C | T323 | Steel Framework Setup | Mike Adams | Blocked | High | 2024-04-07 | 2024-04-30 |  | 0 | Rebar | Downtown Avenue | 27922.18 | 21233.3 | Not started
C004 | Warehouse D | T567 | Interior Painting | Mike Adams | Not Started | Medium | 2023-09-10 | 2023-09-18 |  | 0 | PVC Pipes | Industrial Park | 10007.3 | 0 | Not started
C003 | Office Tower C | T668 | Steel Framework Setup | Emma White | Not Started | High | 2023-02-13 | 2023-02-25 |  | 0 | Roofing Sheets | Downtown Avenue | 29726.73 | 0 | Not started
C003 | Office Tower C | T862 | Roofing | Sarah Johnson | Not Started | High | 2024-10-12 | 2024-10-28 |  | 0 | Steel Beams | Downtown Avenue | 36053.29 | 0 | Not started
C001 | Residential Building A | T920 | Roofing | John Miller | Completed | Low | 2023-07-27 | 2023-08-17 | 2023-08-17 | 100 | Roofing Sheets | Plot 21, Riverside | 49244.61 | 48634.71 | No issues
C003 | Office Tower C | T579 | Plumbing Installations | Sarah Johnson | In Progress | High | 2024-04-05 | 2024-04-13 |  | 48 | Copper Wires | Downtown Avenue | 20631.29 | 16959.38 | In progress
C004 | Warehouse D | T520 | Plumbing Installations | Sarah Johnson | Blocked | Low | 2023-11-10 | 2023-11-26 |  | 0 | Concrete | Industrial Park | 28578.2 | 31111.51 | Not started
C001 | Residential Building A | T782 | Interior Painting | Dave Brown | In Progress | High | 2024-08-21 | 2024-09-06 |  | 34 | Rebar | Plot 21, Riverside | 12363.52 | 9652.14 | In progress
C002 | Shopping Complex B | T612 | Roofing | Emma White | Blocked | Medium | 2023-09-26 | 2023-10-10 |  | 0 | Concrete | Market Street | 17961.92 | 41363.1 | Not started
C002 | Shopping Complex B | T380 | Interior Painting | John Miller | Completed | Low | 2024-06-07 | 2024-06-25 | 2024-06-25 | 100 | PVC Pipes | Market Street | 13976.16 | 35173.21 | No issues
C004 | Warehouse D | T267 | Concrete Pouring | John Miller | Not Started | High | 2024-03-25 | 2024-04-22 |  | 0 | Concrete | Industrial Park | 28036.94 | 0 | Not started
C001 | Residential Building A | T802 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-11-16 | 2023-11-24 |  | 0 | Steel Beams | Plot 21, Riverside | 23235.23 | 0 | Not started
C001 | Residential Building A | T750 | Electrical Wiring | Dave Brown | In Progress | Low | 2024-08-06 | 2024-08-28 |  | 85 | Copper Wires | Plot 21, Riverside | 30628.78 | 30135.45 | In progress
C004 | Warehouse D | T507 | Foundation Excavation | John Miller | Blocked | High | 2024-04-19 | 2024-04-26 |  | 0 | Steel Beams | Industrial Park | 20333.66 | 13709.16 | Not started
C004 | Warehouse D | T255 | Foundation Excavation | Grace Allen | Completed | Medium | 2024-05-02 | 2024-05-14 | 2024-05-14 | 100 | Cement | Industrial Park | 35970.62 | 36866.8 | No issues
C002 | Shopping Complex B | T671 | Foundation Excavation | Carlos Rivera | Completed | Low | 2024-09-24 | 2024-10-11 | 2024-10-11 | 100 | Copper Wires | Market Street | 33565.8 | 54971.19 | No issues
C002 | Shopping Complex B | T286 | Plumbing Installations | Rachel Green | Not Started | Low | 2023-11-03 | 2023-11-19 |  | 0 | Concrete | Market Street | 32480.49 | 0 | Not started
C001 | Residential Building A | T144 | Foundation Excavation | Emma White | Blocked | Medium | 2023-02-27 | 2023-03-16 |  | 0 | Copper Wires | Plot 21, Riverside | 15697.7 | 14479.45 | Not started
C001 | Residential Building A | T666 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-12-01 | 2023-12-23 | 2023-12-23 | 100 | Copper Wires | Plot 21, Riverside | 16048.13 | 19134.75 | No issues
C002 | Shopping Complex B | T784 | Roofing | Sarah Johnson | Blocked | Low | 2023-01-03 | 2023-01-13 |  | 0 | Paint | Market Street | 12874.02 | 40489.49 | Not started
C002 | Shopping Complex B | T311 | Plumbing Installations | Rachel Green | Blocked | High | 2024-09-01 | 2024-09-18 |  | 0 | Paint | Market Street | 16658.48 | 39786.89 | Not started
C004 | Warehouse D | T177 | Electrical Wiring | Mike Adams | Not Started | High | 2023-12-17 | 2024-01-03 |  | 0 | Cement | Industrial Park | 34798.93 | 0 | Not started
C003 | Office Tower C | T805 | Interior Painting | Carlos Rivera | In Progress | High | 2024-03-14 | 2024-04-02 |  | 9 | Rebar | Downtown Avenue | 25836.04 | 23392.04 | In progress
C001 | Residential Building A | T840 | Interior Painting | John Miller | Completed | Medium | 2023-09-03 | 2023-09-26 | 2023-09-26 | 100 | PVC Pipes | Plot 21, Riverside | 16641.08 | 15585.22 | No issues
C002 | Shopping Complex B | T702 | Roofing | Rachel Green | Completed | Low | 2024-01-13 | 2024-02-09 | 2024-02-09 | 100 | Copper Wires | Market Street | 17779.48 | 36700.68 | No issues
C004 | Warehouse D | T786 | Electrical Wiring | Dave Brown | Not Started | High | 2024-08-01 | 2024-08-19 |  | 0 | Copper Wires | Industrial Park | 35719.22 | 0 | Not started
C001 | Residential Building A | T418 | Roofing | Sarah Johnson | Not Started | Low | 2023-02-09 | 2023-02-16 |  | 0 | Steel Beams | Plot 21, Riverside | 10558.04 | 0 | Not started
C002 | Shopping Complex B | T398 | Steel Framework Setup | John Miller | Blocked | Low | 2023-05-06 | 2023-05-18 |  | 0 | Copper Wires | Market Street | 22439.28 | 49816.47 | Not started
C002 | Shopping Complex B | T779 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2024-08-14 | 2024-09-03 |  | 0 | Concrete | Market Street | 27465.08 | 42701.33 | Not started
C002 | Shopping Complex B | T406 | Electrical Wiring | Emma White | In Progress | High | 2023-02-24 | 2023-03-11 |  | 65 | Steel Beams | Market Street | 8832.12 | 33923.66 | In progress
C002 | Shopping Complex B | T864 | Concrete Pouring | John Miller | Completed | High | 2023-06-18 | 2023-07-03 | 2023-07-03 | 100 | Rebar | Market Street | 48073.07 | 75861.59 | No issues
C003 | Office Tower C | T698 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-05-16 | 2024-05-29 |  | 0 | Paint | Downtown Avenue | 27539.17 | 31099.92 | Not started
C004 | Warehouse D | T720 | Electrical Wiring | Grace Allen | Blocked | High | 2024-10-20 | 2024-11-05 |  | 0 | Paint | Industrial Park | 16847.01 | 12758.71 | Not started
C003 | Office Tower C | T511 | Interior Painting | Carlos Rivera | Not Started | Low | 2024-05-23 | 2024-06-09 |  | 0 | Steel Beams | Downtown Avenue | 38182.54 | 0 | Not started
C004 | Warehouse D | T868 | Concrete Pouring | Emma White | Completed | Medium | 2023-04-26 | 2023-05-03 | 2023-05-03 | 100 | Rebar | Industrial Park | 23706.29 | 24043.24 | No issues
C003 | Office Tower C | T809 | Plumbing Installations | Sarah Johnson | Completed | Low | 2023-06-08 | 2023-06-22 | 2023-06-22 | 100 | Paint | Downtown Avenue | 14722.15 | 10075.96 | No issues
C003 | Office Tower C | T166 | Concrete Pouring | Grace Allen | In Progress | Medium | 2024-01-19 | 2024-02-07 |  | 50 | Steel Beams | Downtown Avenue | 8934.36 | 7447.54 | In progress
C001 | Residential Building A | T979 | Plumbing Installations | Carlos Rivera | Completed | High | 2023-02-21 | 2023-03-17 | 2023-03-17 | 100 | Concrete | Plot 21, Riverside | 25196.94 | 20051.17 | No issues
C004 | Warehouse D | T607 | Foundation Excavation | John Miller | Blocked | Medium | 2023-07-21 | 2023-08-08 |  | 0 | Paint | Industrial Park | 40979.91 | 47032.67 | Not started
C004 | Warehouse D | T646 | Roofing | Emma White | Completed | Low | 2023-05-11 | 2023-05-24 | 2023-05-24 | 100 | Copper Wires | Industrial Park | 36345.96 | 38634.57 | No issues
C001 | Residential Building A | T960 | Roofing | Mike Adams | Not Started | High | 2023-10-21 | 2023-11-15 |  | 0 | Steel Beams | Plot 21, Riverside | 36923.6 | 0 | Not started
C002 | Shopping Complex B | T623 | Concrete Pouring | Emma White | Not Started | Medium | 2024-02-16 | 2024-03-01 |  | 0 | Steel Beams | Market Street | 24295.36 | 0 | Not started
C001 | Residential Building A | T207 | Concrete Pouring | Dave Brown | Blocked | High | 2024-12-21 | 2025-01-10 |  | 0 | Paint | Plot 21, Riverside | 35673.78 | 31259.05 | Not started
C002 | Shopping Complex B | T469 | Plumbing Installations | Rachel Green | Blocked | Low | 2024-03-09 | 2024-04-03 |  | 0 | Cement | Market Street | 43773.81 | 67230.52 | Not started
C002 | Shopping Complex B | T277 | Interior Painting | Carlos Rivera | Not Started | High | 2023-12-04 | 2023-12-25 |  | 0 | Copper Wires | Market Street | 19593.79 | 0 | Not started
C001 | Residential Building A | T918 | Electrical Wiring | John Miller | Completed | High | 2024-12-20 | 2025-01-10 | 2025-01-10 | 100 | Concrete | Plot 21, Riverside | 23198.86 | 15055.37 | No issues
C001 | Residential Building A | T545 | Roofing | Mike Adams | In Progress | High | 2024-05-05 | 2024-05-14 |  | 72 | Copper Wires | Plot 21, Riverside | 11086.15 | 10561.38 | In progress
C002 | Shopping Complex B | T897 | Plumbing Installations | John Miller | Not Started | Medium | 2024-07-02 | 2024-07-23 |  | 0 | Concrete | Market Street | 22537.05 | 0 | Not started
C004 | Warehouse D | T367 | Roofing | Dave Brown | Blocked | Medium | 2023-11-21 | 2023-12-14 |  | 0 | Cement | Industrial Park | 14496.47 | 10980.26 | Not started
C001 | Residential Building A | T594 | Interior Painting | Mike Adams | Not Started | Low | 2023-08-21 | 2023-09-01 |  | 0 | Roofing Sheets | Plot 21, Riverside | 16828.54 | 0 | Not started
C004 | Warehouse D | T476 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2023-11-19 | 2023-12-18 |  | 0 | Roofing Sheets | Industrial Park | 9676.74 | 0 | Not started
C002 | Shopping Complex B | T170 | Steel Framework Setup | John Miller | Not Started | Medium | 2024-08-17 | 2024-08-27 |  | 0 | PVC Pipes | Market Street | 14644.9 | 0 | Not started
C002 | Shopping Complex B | T329 | Site Survey | John Miller | Blocked | Medium | 2024-10-15 | 2024-10-28 |  | 0 | Concrete | Market Street | 25449.98 | 42473.25 | Not started
C001 | Residential Building A | T558 | Roofing | Dave Brown | Not Started | Medium | 2024-11-11 | 2024-12-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 15789.3 | 0 | Not started
C001 | Residential Building A | T228 | Electrical Wiring | Emma White | Not Started | Low | 2023-05-23 | 2023-06-16 |  | 0 | Rebar | Plot 21, Riverside | 19241.63 | 0 | Not started
C001 | Residential Building A | T185 | Interior Painting | John Miller | Completed | Medium | 2023-11-04 | 2023-12-03 | 2023-12-03 | 100 | Cement | Plot 21, Riverside | 43541.85 | 36417.89 | No issues
C001 | Residential Building A | T859 | Concrete Pouring | Emma White | Not Started | Medium | 2023-12-28 | 2024-01-26 |  | 0 | Concrete | Plot 21, Riverside | 49486.28 | 0 | Not started
C003 | Office Tower C | T375 | Site Survey | Emma White | Completed | High | 2024-12-19 | 2025-01-11 | 2025-01-11 | 100 | Rebar | Downtown Avenue | 5089.22 | 4411.04 | No issues
C001 | Residential Building A | T422 | Site Survey | Sarah Johnson | Completed | Low | 2024-03-03 | 2024-03-29 | 2024-03-29 | 100 | Paint | Plot 21, Riverside | 37699.19 | 37343.75 | No issues
C001 | Residential Building A | T760 | Concrete Pouring | Dave Brown | In Progress | Low | 2023-04-16 | 2023-05-10 |  | 63 | Copper Wires | Plot 21, Riverside | 35559.6 | 25988.52 | In progress
C004 | Warehouse D | T266 | Roofing | John Miller | Not Started | Low | 2023-06-27 | 2023-07-08 |  | 0 | PVC Pipes | Industrial Park | 8573.61 | 0 | Not started
C004 | Warehouse D | T636 | Interior Painting | Grace Allen | Completed | Medium | 2023-09-04 | 2023-10-03 | 2023-10-03 | 100 | Concrete | Industrial Park | 10996.35 | 7978.95 | No issues
C001 | Residential Building A | T881 | Plumbing Installations | John Miller | Blocked | High | 2024-06-21 | 2024-07-09 |  | 0 | Concrete | Plot 21, Riverside | 48719.19 | 46678.3 | Not started
C004 | Warehouse D | T693 | Interior Painting | Emma White | Not Started | Low | 2024-09-17 | 2024-10-11 |  | 0 | Roofing Sheets | Industrial Park | 22651.3 | 0 | Not started
C004 | Warehouse D | T879 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-04-12 | 2024-04-20 |  | 0 | PVC Pipes | Industrial Park | 13338.87 | 0 | Not started
C003 | Office Tower C | T260 | Interior Painting | Mike Adams | Completed | High | 2024-02-28 | 2024-03-24 | 2024-03-24 | 100 | PVC Pipes | Downtown Avenue | 22700.77 | 24062.97 | No issues
C001 | Residential Building A | T658 | Interior Painting | Carlos Rivera | Completed | High | 2024-12-05 | 2024-12-27 | 2024-12-27 | 100 | Cement | Plot 21, Riverside | 8702.49 | 7336.65 | No issues
C002 | Shopping Complex B | T188 | Site Survey | Carlos Rivera | In Progress | High | 2023-02-04 | 2023-02-26 |  | 21 | Concrete | Market Street | 28830.66 | 46468.11 | In progress
C003 | Office Tower C | T371 | Interior Painting | Rachel Green | In Progress | Low | 2023-06-21 | 2023-07-09 |  | 10 | Roofing Sheets | Downtown Avenue | 11195 | 13294.64 | In progress
C001 | Residential Building A | T480 | Foundation Excavation | Rachel Green | In Progress | High | 2024-10-14 | 2024-10-28 |  | 53 | Paint | Plot 21, Riverside | 28624.25 | 28878.98 | In progress
C001 | Residential Building A | T149 | Roofing | Sarah Johnson | In Progress | Low | 2023-12-21 | 2024-01-08 |  | 51 | Steel Beams | Plot 21, Riverside | 42226.93 | 46507.22 | In progress
C003 | Office Tower C | T860 | Plumbing Installations | Mike Adams | Blocked | Low | 2023-10-13 | 2023-11-08 |  | 0 | PVC Pipes | Downtown Avenue | 26084.04 | 21388.14 | Not started
C004 | Warehouse D | T591 | Electrical Wiring | Dave Brown | Completed | Low | 2024-04-03 | 2024-04-28 | 2024-04-28 | 100 | Steel Beams | Industrial Park | 19518.38 | 14772.98 | No issues
C002 | Shopping Complex B | T397 | Interior Painting | Carlos Rivera | In Progress | Medium | 2024-06-15 | 2024-07-06 |  | 12 | PVC Pipes | Market Street | 21962.96 | 43550.47 | In progress
C004 | Warehouse D | T164 | Foundation Excavation | Emma White | Not Started | Low | 2024-05-27 | 2024-06-22 |  | 0 | Paint | Industrial Park | 14135.65 | 0 | Not started
C002 | Shopping Complex B | T470 | Foundation Excavation | Dave Brown | In Progress | Medium | 2024-02-16 | 2024-02-29 |  | 15 | Steel Beams | Market Street | 26064.46 | 50879.98 | In progress
C003 | Office Tower C | T538 | Roofing | Carlos Rivera | In Progress | High | 2024-07-07 | 2024-07-27 |  | 31 | PVC Pipes | Downtown Avenue | 22750.2 | 15783.66 | In progress
C002 | Shopping Complex B | T431 | Plumbing Installations | Grace Allen | Completed | High | 2024-05-13 | 2024-05-20 | 2024-05-20 | 100 | Roofing Sheets | Market Street | 17183.06 | 45811.31 | No issues
C002 | Shopping Complex B | T686 | Interior Painting | Dave Brown | In Progress | Medium | 2024-02-08 | 2024-02-19 |  | 5 | Roofing Sheets | Market Street | 32167.8 | 53368.44 | In progress
C004 | Warehouse D | T305 | Roofing | Mike Adams | In Progress | High | 2023-03-06 | 2023-04-04 |  | 17 | Cement | Industrial Park | 40340.61 | 37724.52 | In progress
C001 | Residential Building A | T599 | Interior Painting | Rachel Green | Completed | High | 2023-11-02 | 2023-11-09 | 2023-11-09 | 100 | Copper Wires | Plot 21, Riverside | 39778.66 | 33379.47 | No issues
C002 | Shopping Complex B | T246 | Roofing | Grace Allen | Completed | High | 2024-11-24 | 2024-12-23 | 2024-12-23 | 100 | PVC Pipes | Market Street | 16853.35 | 44762.37 | No issues
C002 | Shopping Complex B | T645 | Steel Framework Setup | Dave Brown | In Progress | High | 2024-09-28 | 2024-10-05 |  | 72 | Copper Wires | Market Street | 49494.72 | 70606.35 | In progress
C004 | Warehouse D | T713 | Steel Framework Setup | Grace Allen | In Progress | High | 2023-06-13 | 2023-06-28 |  | 71 | Roofing Sheets | Industrial Park | 42375.06 | 31156.94 | In progress
C001 | Residential Building A | T553 | Steel Framework Setup | Rachel Green | Blocked | Low | 2023-04-02 | 2023-04-13 |  | 0 | Roofing Sheets | Plot 21, Riverside | 8527.36 | 8106.26 | Not started
C001 | Residential Building A | T818 | Roofing | Grace Allen | In Progress | Low | 2024-02-20 | 2024-03-21 |  | 51 | Roofing Sheets | Plot 21, Riverside | 38029.89 | 28337.94 | In progress
C003 | Office Tower C | T387 | Site Survey | Mike Adams | Blocked | Medium | 2024-05-05 | 2024-05-20 |  | 0 | Rebar | Downtown Avenue | 14258.38 | 15463.63 | Not started
C003 | Office Tower C | T181 | Foundation Excavation | John Miller | Blocked | Medium | 2023-02-09 | 2023-03-11 |  | 0 | Copper Wires | Downtown Avenue | 7238.7 | 5291.69 | Not started
C004 | Warehouse D | T867 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2024-01-13 | 2024-02-07 |  | 30 | PVC Pipes | Industrial Park | 46198.43 | 42041.14 | In progress
C004 | Warehouse D | T388 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2024-06-16 | 2024-07-15 | 2024-07-15 | 100 | PVC Pipes | Industrial Park | 41070.74 | 46016.62 | No issues
C003 | Office Tower C | T810 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2024-11-25 | 2024-12-02 |  | 0 | Paint | Downtown Avenue | 10166.27 | 6401.05 | Not started
C004 | Warehouse D | T418 | Foundation Excavation | Sarah Johnson | Blocked | Low | 2023-06-26 | 2023-07-07 |  | 0 | Roofing Sheets | Industrial Park | 17101.97 | 14768.44 | Not started
C003 | Office Tower C | T570 | Foundation Excavation | Emma White | Completed | High | 2024-11-23 | 2024-12-19 | 2024-12-19 | 100 | Copper Wires | Downtown Avenue | 27423.89 | 16566.2 | No issues
C001 | Residential Building A | T460 | Concrete Pouring | Dave Brown | In Progress | High | 2023-02-20 | 2023-03-09 |  | 29 | Rebar | Plot 21, Riverside | 23172.52 | 16632.89 | In progress
C001 | Residential Building A | T314 | Interior Painting | Grace Allen | In Progress | High | 2023-08-05 | 2023-08-14 |  | 10 | Cement | Plot 21, Riverside | 28671.34 | 27158.02 | In progress
C003 | Office Tower C | T543 | Roofing | Grace Allen | In Progress | Medium | 2023-10-03 | 2023-10-17 |  | 54 | Steel Beams | Downtown Avenue | 44261.47 | 51633.96 | In progress
C001 | Residential Building A | T748 | Interior Painting | Carlos Rivera | Not Started | Low | 2024-09-04 | 2024-10-02 |  | 0 | Rebar | Plot 21, Riverside | 11285.42 | 0 | Not started
C002 | Shopping Complex B | T111 | Foundation Excavation | Emma White | Not Started | Low | 2024-07-28 | 2024-08-12 |  | 0 | PVC Pipes | Market Street | 22731.01 | 0 | Not started
C001 | Residential Building A | T753 | Foundation Excavation | John Miller | In Progress | High | 2024-02-22 | 2024-03-22 |  | 25 | Concrete | Plot 21, Riverside | 27965.06 | 27792.77 | In progress
C003 | Office Tower C | T623 | Roofing | Sarah Johnson | Not Started | Low | 2023-10-28 | 2023-11-19 |  | 0 | Rebar | Downtown Avenue | 6495.39 | 0 | Not started
C001 | Residential Building A | T431 | Site Survey | Rachel Green | Blocked | High | 2024-12-22 | 2025-01-02 |  | 0 | Paint | Plot 21, Riverside | 22244.16 | 14234.93 | Not started
C003 | Office Tower C | T174 | Interior Painting | Grace Allen | Not Started | High | 2023-02-17 | 2023-03-03 |  | 0 | Paint | Downtown Avenue | 14595 | 0 | Not started
C001 | Residential Building A | T534 | Interior Painting | Emma White | In Progress | Medium | 2024-02-13 | 2024-02-23 |  | 54 | Copper Wires | Plot 21, Riverside | 29580.82 | 25774.09 | In progress
C003 | Office Tower C | T399 | Concrete Pouring | John Miller | Completed | Medium | 2023-07-24 | 2023-08-04 | 2023-08-04 | 100 | Copper Wires | Downtown Avenue | 32493.39 | 35285.31 | No issues
C003 | Office Tower C | T719 | Plumbing Installations | Rachel Green | Completed | High | 2023-11-05 | 2023-11-28 | 2023-11-28 | 100 | Steel Beams | Downtown Avenue | 6965.65 | 7065.13 | No issues
C001 | Residential Building A | T879 | Roofing | Mike Adams | Not Started | Low | 2023-01-10 | 2023-01-27 |  | 0 | Cement | Plot 21, Riverside | 10970.31 | 0 | Not started
C003 | Office Tower C | T341 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-08-26 | 2024-09-06 |  | 0 | Steel Beams | Downtown Avenue | 6434.91 | 0 | Not started
C002 | Shopping Complex B | T910 | Interior Painting | Grace Allen | Completed | High | 2024-12-02 | 2024-12-18 | 2024-12-18 | 100 | PVC Pipes | Market Street | 32627.93 | 55621.43 | No issues
C003 | Office Tower C | T859 | Site Survey | Emma White | Completed | Medium | 2024-11-08 | 2024-11-20 | 2024-11-20 | 100 | Copper Wires | Downtown Avenue | 35908.28 | 36058.68 | No issues
C001 | Residential Building A | T249 | Site Survey | John Miller | Completed | Low | 2024-03-27 | 2024-04-11 | 2024-04-11 | 100 | Concrete | Plot 21, Riverside | 47724.79 | 28853.79 | No issues
C004 | Warehouse D | T827 | Steel Framework Setup | Grace Allen | Not Started | Low | 2024-04-13 | 2024-05-10 |  | 0 | Paint | Industrial Park | 14824.42 | 0 | Not started
C003 | Office Tower C | T720 | Site Survey | Grace Allen | Completed | Medium | 2024-06-14 | 2024-06-21 | 2024-06-21 | 100 | PVC Pipes | Downtown Avenue | 22812.28 | 19229.96 | No issues
C001 | Residential Building A | T795 | Roofing | Carlos Rivera | Not Started | Low | 2023-07-17 | 2023-08-09 |  | 0 | Roofing Sheets | Plot 21, Riverside | 27213.29 | 0 | Not started
C002 | Shopping Complex B | T868 | Electrical Wiring | Carlos Rivera | In Progress | High | 2023-10-04 | 2023-10-18 |  | 16 | Steel Beams | Market Street | 23720.14 | 40411.75 | In progress
C004 | Warehouse D | T474 | Interior Painting | John Miller | Blocked | High | 2024-12-14 | 2024-12-21 |  | 0 | Roofing Sheets | Industrial Park | 6840.91 | 7437.17 | Not started
C003 | Office Tower C | T376 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-09-26 | 2024-10-15 |  | 0 | Cement | Downtown Avenue | 29905.75 | 29882.16 | Not started
C001 | Residential Building A | T128 | Roofing | Rachel Green | Completed | Medium | 2024-11-10 | 2024-11-18 | 2024-11-18 | 100 | Cement | Plot 21, Riverside | 34764.66 | 23789.49 | No issues
C004 | Warehouse D | T820 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-03-24 | 2023-04-08 |  | 98 | Concrete | Industrial Park | 26197.59 | 24543.24 | In progress
C004 | Warehouse D | T475 | Electrical Wiring | Sarah Johnson | Not Started | High | 2024-07-02 | 2024-07-24 |  | 0 | Roofing Sheets | Industrial Park | 24796.41 | 0 | Not started
C004 | Warehouse D | T403 | Foundation Excavation | Mike Adams | In Progress | High | 2024-05-05 | 2024-05-17 |  | 60 | PVC Pipes | Industrial Park | 17855.28 | 11443.8 | In progress
C003 | Office Tower C | T674 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-05-04 | 2024-05-27 |  | 93 | Copper Wires | Downtown Avenue | 12676.75 | 11558.59 | In progress
C003 | Office Tower C | T427 | Roofing | Carlos Rivera | In Progress | Medium | 2023-02-23 | 2023-03-19 |  | 88 | Roofing Sheets | Downtown Avenue | 40134.32 | 26617.81 | In progress
C003 | Office Tower C | T231 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2023-11-04 | 2023-11-21 |  | 58 | PVC Pipes | Downtown Avenue | 26608.3 | 23367.56 | In progress
C003 | Office Tower C | T608 | Roofing | Dave Brown | In Progress | High | 2024-04-13 | 2024-04-29 |  | 24 | Paint | Downtown Avenue | 32403.05 | 21456.24 | In progress
C004 | Warehouse D | T179 | Interior Painting | Carlos Rivera | Completed | Low | 2023-05-13 | 2023-05-25 | 2023-05-25 | 100 | Steel Beams | Industrial Park | 40825.45 | 46866.22 | No issues
C003 | Office Tower C | T495 | Site Survey | Dave Brown | Not Started | High | 2023-04-28 | 2023-05-28 |  | 0 | Cement | Downtown Avenue | 40714.87 | 0 | Not started
C001 | Residential Building A | T116 | Foundation Excavation | Emma White | Not Started | High | 2024-01-22 | 2024-02-07 |  | 0 | Paint | Plot 21, Riverside | 25241.14 | 0 | Not started
C001 | Residential Building A | T178 | Concrete Pouring | John Miller | In Progress | Low | 2023-03-16 | 2023-04-13 |  | 56 | Concrete | Plot 21, Riverside | 5839.44 | 5566.85 | In progress
C004 | Warehouse D | T977 | Interior Painting | Dave Brown | In Progress | Medium | 2024-05-24 | 2024-06-07 |  | 79 | Copper Wires | Industrial Park | 32654.5 | 28104.88 | In progress
C002 | Shopping Complex B | T284 | Foundation Excavation | Rachel Green | In Progress | Low | 2023-03-27 | 2023-04-26 |  | 9 | PVC Pipes | Market Street | 41591.02 | 72292.99 | In progress
C004 | Warehouse D | T336 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-11-25 | 2023-12-20 | 2023-12-20 | 100 | Paint | Industrial Park | 20301.13 | 15357.98 | No issues
C003 | Office Tower C | T346 | Interior Painting | Emma White | Blocked | Low | 2023-01-06 | 2023-01-20 |  | 0 | Steel Beams | Downtown Avenue | 39668.56 | 32939.9 | Not started
C002 | Shopping Complex B | T811 | Foundation Excavation | John Miller | Blocked | High | 2023-03-01 | 2023-03-10 |  | 0 | Paint | Market Street | 5312.42 | 30106.52 | Not started
C002 | Shopping Complex B | T819 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-06-19 | 2024-07-09 |  | 0 | Roofing Sheets | Market Street | 29552.39 | 46062.54 | Not started
C004 | Warehouse D | T162 | Site Survey | Mike Adams | In Progress | Medium | 2024-08-27 | 2024-09-08 |  | 48 | Paint | Industrial Park | 14026.43 | 11360.35 | In progress
C003 | Office Tower C | T819 | Roofing | Grace Allen | Blocked | Medium | 2023-09-18 | 2023-10-18 |  | 0 | Steel Beams | Downtown Avenue | 17576.26 | 11626.46 | Not started
C004 | Warehouse D | T417 | Interior Painting | Mike Adams | In Progress | Medium | 2023-11-19 | 2023-12-05 |  | 99 | Concrete | Industrial Park | 45458.68 | 30310.02 | In progress
C002 | Shopping Complex B | T188 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-05-16 | 2023-05-29 | 2023-05-29 | 100 | Roofing Sheets | Market Street | 41038.69 | 70850.27 | No issues
C001 | Residential Building A | T186 | Roofing | Grace Allen | Not Started | Medium | 2023-03-07 | 2023-03-22 |  | 0 | Cement | Plot 21, Riverside | 17994.65 | 0 | Not started
C002 | Shopping Complex B | T173 | Electrical Wiring | Emma White | Completed | Medium | 2024-05-03 | 2024-05-16 | 2024-05-16 | 100 | Copper Wires | Market Street | 44208.12 | 70835.45 | No issues
C003 | Office Tower C | T506 | Interior Painting | Dave Brown | In Progress | High | 2024-10-17 | 2024-11-01 |  | 44 | Cement | Downtown Avenue | 10332.01 | 9668.75 | In progress
C002 | Shopping Complex B | T563 | Plumbing Installations | Rachel Green | In Progress | Low | 2024-05-02 | 2024-05-18 |  | 96 | Roofing Sheets | Market Street | 14473.4 | 41622.36 | In progress
C003 | Office Tower C | T497 | Plumbing Installations | Rachel Green | Completed | Medium | 2024-01-26 | 2024-02-11 | 2024-02-11 | 100 | Roofing Sheets | Downtown Avenue | 26977.77 | 26046.87 | No issues
C003 | Office Tower C | T243 | Steel Framework Setup | Rachel Green | Blocked | High | 2024-07-16 | 2024-08-07 |  | 0 | Paint | Downtown Avenue | 10022.8 | 10090.49 | Not started
C004 | Warehouse D | T364 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2023-02-06 | 2023-02-25 |  | 0 | PVC Pipes | Industrial Park | 12865.91 | 0 | Not started
C002 | Shopping Complex B | T595 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2023-10-08 | 2023-11-06 | 2023-11-06 | 100 | Cement | Market Street | 33226.71 | 45912.32 | No issues
C001 | Residential Building A | T728 | Concrete Pouring | Mike Adams | Blocked | High | 2023-09-25 | 2023-10-08 |  | 0 | Rebar | Plot 21, Riverside | 48743.25 | 41778.14 | Not started
C002 | Shopping Complex B | T400 | Foundation Excavation | Mike Adams | Completed | High | 2024-08-20 | 2024-08-30 | 2024-08-30 | 100 | Concrete | Market Street | 24813.12 | 49179.38 | No issues
C002 | Shopping Complex B | T832 | Roofing | Emma White | Not Started | Low | 2023-04-03 | 2023-04-16 |  | 0 | Roofing Sheets | Market Street | 10397.64 | 0 | Not started
C003 | Office Tower C | T445 | Interior Painting | Rachel Green | In Progress | High | 2023-05-11 | 2023-05-20 |  | 28 | Roofing Sheets | Downtown Avenue | 22170.97 | 20391.07 | In progress
C004 | Warehouse D | T261 | Electrical Wiring | John Miller | Not Started | High | 2024-11-08 | 2024-11-18 |  | 0 | Cement | Industrial Park | 36368.78 | 0 | Not started
C004 | Warehouse D | T662 | Plumbing Installations | Rachel Green | Completed | High | 2024-02-26 | 2024-03-13 | 2024-03-13 | 100 | PVC Pipes | Industrial Park | 14137.02 | 12104.33 | No issues
C001 | Residential Building A | T563 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2023-12-18 | 2024-01-14 |  | 0 | Rebar | Plot 21, Riverside | 46997.82 | 55736.64 | Not started
C003 | Office Tower C | T516 | Concrete Pouring | Grace Allen | Completed | Medium | 2024-08-23 | 2024-09-19 | 2024-09-19 | 100 | Steel Beams | Downtown Avenue | 7783.67 | 5842.61 | No issues
C004 | Warehouse D | T860 | Foundation Excavation | Rachel Green | Not Started | Medium | 2024-06-23 | 2024-07-14 |  | 0 | Rebar | Industrial Park | 42901.65 | 0 | Not started
C004 | Warehouse D | T734 | Electrical Wiring | Rachel Green | Completed | High | 2023-02-25 | 2023-03-14 | 2023-03-14 | 100 | Copper Wires | Industrial Park | 43365.54 | 32004.47 | No issues
C004 | Warehouse D | T214 | Foundation Excavation | Mike Adams | In Progress | Low | 2024-08-24 | 2024-09-15 |  | 18 | Copper Wires | Industrial Park | 36289.54 | 38419.3 | In progress
C003 | Office Tower C | T247 | Plumbing Installations | Dave Brown | In Progress | High | 2024-02-26 | 2024-03-05 |  | 63 | Rebar | Downtown Avenue | 47698.85 | 56246.68 | In progress
C002 | Shopping Complex B | T908 | Interior Painting | Emma White | Not Started | Medium | 2024-02-08 | 2024-02-20 |  | 0 | Steel Beams | Market Street | 30098.39 | 0 | Not started
C003 | Office Tower C | T739 | Site Survey | John Miller | In Progress | Medium | 2024-09-28 | 2024-10-23 |  | 77 | Roofing Sheets | Downtown Avenue | 12011.43 | 14399.59 | In progress
C004 | Warehouse D | T314 | Electrical Wiring | Mike Adams | Completed | Medium | 2024-04-19 | 2024-05-02 | 2024-05-02 | 100 | Paint | Industrial Park | 31216.94 | 29851.09 | No issues
C003 | Office Tower C | T851 | Roofing | Sarah Johnson | Blocked | High | 2023-03-12 | 2023-04-04 |  | 0 | Cement | Downtown Avenue | 11907.65 | 10367.95 | Not started
C003 | Office Tower C | T767 | Steel Framework Setup | Grace Allen | Completed | High | 2023-11-03 | 2023-12-02 | 2023-12-02 | 100 | Paint | Downtown Avenue | 16378.01 | 12628.89 | No issues
C003 | Office Tower C | T898 | Site Survey | Grace Allen | Not Started | High | 2023-10-09 | 2023-10-20 |  | 0 | Cement | Downtown Avenue | 8265.39 | 0 | Not started
C002 | Shopping Complex B | T304 | Interior Painting | John Miller | In Progress | High | 2023-06-05 | 2023-07-01 |  | 83 | PVC Pipes | Market Street | 20166.42 | 37833.39 | In progress
C004 | Warehouse D | T592 | Site Survey | Mike Adams | Completed | High | 2023-06-06 | 2023-07-01 | 2023-07-01 | 100 | Cement | Industrial Park | 33728.04 | 20790.29 | No issues
C004 | Warehouse D | T960 | Plumbing Installations | Grace Allen | Not Started | Low | 2024-09-12 | 2024-10-05 |  | 0 | Cement | Industrial Park | 49055.22 | 0 | Not started
C004 | Warehouse D | T386 | Foundation Excavation | Emma White | Blocked | High | 2023-09-09 | 2023-10-02 |  | 0 | Concrete | Industrial Park | 10313.66 | 11630.94 | Not started
C003 | Office Tower C | T971 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2024-12-11 | 2025-01-10 |  | 0 | Roofing Sheets | Downtown Avenue | 38874.37 | 0 | Not started
C004 | Warehouse D | T680 | Interior Painting | Emma White | Not Started | Low | 2023-12-28 | 2024-01-11 |  | 0 | Cement | Industrial Park | 28212.4 | 0 | Not started
C004 | Warehouse D | T859 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-12-21 | 2024-01-13 |  | 6 | PVC Pipes | Industrial Park | 27423.19 | 26119.07 | In progress
C002 | Shopping Complex B | T117 | Plumbing Installations | John Miller | In Progress | High | 2024-04-26 | 2024-05-05 |  | 11 | Steel Beams | Market Street | 16975.55 | 43667.53 | In progress
C001 | Residential Building A | T934 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2023-08-26 | 2023-09-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 42871.05 | 0 | Not started
C003 | Office Tower C | T917 | Site Survey | Grace Allen | In Progress | Low | 2023-06-02 | 2023-06-29 |  | 38 | Copper Wires | Downtown Avenue | 49591.86 | 41684.46 | In progress
C002 | Shopping Complex B | T187 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-11-07 | 2023-11-20 |  | 99 | Concrete | Market Street | 23396.9 | 42259.08 | In progress
C002 | Shopping Complex B | T489 | Electrical Wiring | Sarah Johnson | Not Started | High | 2024-05-28 | 2024-06-19 |  | 0 | PVC Pipes | Market Street | 48384.52 | 0 | Not started
C002 | Shopping Complex B | T926 | Electrical Wiring | Dave Brown | Not Started | High | 2024-11-13 | 2024-12-06 |  | 0 | Steel Beams | Market Street | 5574.44 | 0 | Not started
C002 | Shopping Complex B | T479 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-03-25 | 2023-04-01 |  | 0 | Cement | Market Street | 11309.61 | 0 | Not started
C004 | Warehouse D | T441 | Roofing | Carlos Rivera | Blocked | High | 2023-07-14 | 2023-07-27 |  | 0 | Paint | Industrial Park | 12292.31 | 8388.31 | Not started
C004 | Warehouse D | T219 | Site Survey | Carlos Rivera | Completed | Low | 2024-02-21 | 2024-03-20 | 2024-03-20 | 100 | Rebar | Industrial Park | 13154.21 | 12547.23 | No issues
C003 | Office Tower C | T559 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2023-04-26 | 2023-05-09 |  | 67 | Steel Beams | Downtown Avenue | 32899.92 | 32109.16 | In progress
C002 | Shopping Complex B | T842 | Steel Framework Setup | John Miller | Completed | Medium | 2023-11-17 | 2023-11-26 | 2023-11-26 | 100 | Copper Wires | Market Street | 7670.16 | 30375.15 | No issues
C003 | Office Tower C | T440 | Roofing | Mike Adams | Blocked | Low | 2024-02-20 | 2024-03-15 |  | 0 | Copper Wires | Downtown Avenue | 47551.9 | 55385.9 | Not started
C002 | Shopping Complex B | T698 | Roofing | John Miller | In Progress | High | 2024-09-22 | 2024-10-14 |  | 96 | Steel Beams | Market Street | 14949.71 | 36273.27 | In progress
C003 | Office Tower C | T321 | Electrical Wiring | Grace Allen | In Progress | High | 2024-09-07 | 2024-09-27 |  | 69 | Rebar | Downtown Avenue | 32633.3 | 21460.87 | In progress
C004 | Warehouse D | T541 | Plumbing Installations | John Miller | Completed | High | 2024-01-11 | 2024-01-31 | 2024-01-31 | 100 | Steel Beams | Industrial Park | 29367.28 | 25913.78 | No issues
C004 | Warehouse D | T759 | Steel Framework Setup | Mike Adams | Completed | Low | 2024-05-25 | 2024-06-13 | 2024-06-13 | 100 | Paint | Industrial Park | 16691.72 | 18603.53 | No issues
C004 | Warehouse D | T140 | Roofing | Mike Adams | Not Started | Medium | 2024-06-04 | 2024-06-17 |  | 0 | PVC Pipes | Industrial Park | 29434.08 | 0 | Not started
C001 | Residential Building A | T556 | Interior Painting | Emma White | Completed | High | 2024-07-03 | 2024-07-29 | 2024-07-29 | 100 | Steel Beams | Plot 21, Riverside | 13708.06 | 11443.75 | No issues
C004 | Warehouse D | T108 | Foundation Excavation | Sarah Johnson | Not Started | High | 2023-09-19 | 2023-10-08 |  | 0 | Concrete | Industrial Park | 39523.68 | 0 | Not started
C003 | Office Tower C | T968 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-08-03 | 2023-08-23 | 2023-08-23 | 100 | Paint | Downtown Avenue | 45738.92 | 54008.64 | No issues
C002 | Shopping Complex B | T481 | Plumbing Installations | Dave Brown | Not Started | High | 2024-05-07 | 2024-05-29 |  | 0 | Paint | Market Street | 18199.29 | 0 | Not started
C002 | Shopping Complex B | T176 | Roofing | Dave Brown | In Progress | Low | 2023-01-02 | 2023-01-27 |  | 14 | Rebar | Market Street | 13408.44 | 41285.47 | In progress
C001 | Residential Building A | T677 | Concrete Pouring | Dave Brown | Not Started | Low | 2023-11-11 | 2023-11-24 |  | 0 | Concrete | Plot 21, Riverside | 26385.73 | 0 | Not started
C004 | Warehouse D | T301 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2023-02-22 | 2023-03-04 |  | 0 | Copper Wires | Industrial Park | 40874.9 | 45028.6 | Not started
C001 | Residential Building A | T233 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-07-04 | 2023-07-11 |  | 0 | Cement | Plot 21, Riverside | 29222.1 | 0 | Not started
C004 | Warehouse D | T276 | Interior Painting | Emma White | In Progress | Low | 2023-11-19 | 2023-12-14 |  | 74 | PVC Pipes | Industrial Park | 13225.41 | 10956.7 | In progress
C001 | Residential Building A | T558 | Site Survey | Grace Allen | Blocked | High | 2023-07-10 | 2023-08-03 |  | 0 | Paint | Plot 21, Riverside | 48347.46 | 35258.25 | Not started
C003 | Office Tower C | T596 | Foundation Excavation | Mike Adams | Not Started | Medium | 2024-06-21 | 2024-07-04 |  | 0 | Roofing Sheets | Downtown Avenue | 39716.36 | 0 | Not started
C003 | Office Tower C | T248 | Concrete Pouring | John Miller | Not Started | High | 2023-02-28 | 2023-03-13 |  | 0 | Roofing Sheets | Downtown Avenue | 39645.71 | 0 | Not started
C003 | Office Tower C | T319 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2023-09-03 | 2023-10-03 |  | 0 | PVC Pipes | Downtown Avenue | 33384.22 | 37885.58 | Not started
C003 | Office Tower C | T558 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-03-03 | 2024-03-11 |  | 16 | Roofing Sheets | Downtown Avenue | 6090.57 | 6285.8 | In progress
C002 | Shopping Complex B | T307 | Plumbing Installations | Emma White | In Progress | Low | 2023-10-01 | 2023-10-10 |  | 81 | Paint | Market Street | 25507.64 | 53278.93 | In progress
C003 | Office Tower C | T391 | Foundation Excavation | John Miller | Completed | Medium | 2023-10-15 | 2023-10-24 | 2023-10-24 | 100 | Paint | Downtown Avenue | 38089.75 | 33626.07 | No issues
C003 | Office Tower C | T348 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-10-07 | 2023-10-21 |  | 0 | Roofing Sheets | Downtown Avenue | 30682.29 | 30422.77 | Not started
C004 | Warehouse D | T650 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-02-17 | 2023-03-02 |  | 0 | Steel Beams | Industrial Park | 25753.47 | 0 | Not started
C003 | Office Tower C | T143 | Electrical Wiring | Dave Brown | Not Started | High | 2023-02-16 | 2023-03-02 |  | 0 | Roofing Sheets | Downtown Avenue | 45740.58 | 0 | Not started
C002 | Shopping Complex B | T929 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2023-02-02 | 2023-02-19 |  | 62 | Paint | Market Street | 27823.51 | 52542.92 | In progress
C002 | Shopping Complex B | T388 | Roofing | Rachel Green | Blocked | Low | 2024-05-08 | 2024-06-03 |  | 0 | Steel Beams | Market Street | 24198.92 | 52362.27 | Not started
C001 | Residential Building A | T982 | Interior Painting | John Miller | Not Started | Medium | 2024-08-26 | 2024-09-23 |  | 0 | Steel Beams | Plot 21, Riverside | 42365.65 | 0 | Not started
C002 | Shopping Complex B | T556 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-11-08 | 2024-11-23 |  | 0 | Paint | Market Street | 46437.06 | 65441.28 | Not started
C004 | Warehouse D | T902 | Roofing | Grace Allen | In Progress | Medium | 2023-11-25 | 2023-12-15 |  | 19 | Concrete | Industrial Park | 20079.44 | 23279.81 | In progress
C003 | Office Tower C | T843 | Plumbing Installations | Emma White | Blocked | High | 2023-01-08 | 2023-01-28 |  | 0 | Paint | Downtown Avenue | 32657.7 | 27289.78 | Not started
C003 | Office Tower C | T474 | Roofing | Mike Adams | Not Started | Medium | 2023-12-13 | 2024-01-12 |  | 0 | Cement | Downtown Avenue | 33024.25 | 0 | Not started
C004 | Warehouse D | T130 | Foundation Excavation | Rachel Green | Blocked | High | 2024-12-27 | 2025-01-04 |  | 0 | Steel Beams | Industrial Park | 8813.64 | 10451.95 | Not started
C001 | Residential Building A | T100 | Roofing | Dave Brown | In Progress | Medium | 2024-10-10 | 2024-11-02 |  | 87 | Roofing Sheets | Plot 21, Riverside | 13071.85 | 15168.58 | In progress
C004 | Warehouse D | T299 | Concrete Pouring | Mike Adams | Not Started | Low | 2023-12-05 | 2023-12-21 |  | 0 | Paint | Industrial Park | 24788.04 | 0 | Not started
C001 | Residential Building A | T122 | Interior Painting | Sarah Johnson | In Progress | Medium | 2023-10-21 | 2023-11-01 |  | 95 | Rebar | Plot 21, Riverside | 44936.43 | 40868.81 | In progress
C004 | Warehouse D | T311 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2023-05-14 | 2023-05-24 |  | 0 | Copper Wires | Industrial Park | 11952.76 | 0 | Not started
C002 | Shopping Complex B | T225 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-10-15 | 2024-11-09 |  | 0 | Paint | Market Street | 38811.73 | 61449.8 | Not started
C003 | Office Tower C | T619 | Site Survey | Emma White | Blocked | Medium | 2023-08-10 | 2023-09-02 |  | 0 | Copper Wires | Downtown Avenue | 34396.16 | 35890.48 | Not started
C003 | Office Tower C | T907 | Plumbing Installations | Mike Adams | Not Started | High | 2024-03-16 | 2024-04-12 |  | 0 | Steel Beams | Downtown Avenue | 29185.1 | 0 | Not started
C003 | Office Tower C | T694 | Roofing | John Miller | In Progress | Medium | 2024-10-21 | 2024-11-05 |  | 34 | Cement | Downtown Avenue | 24574.69 | 26037.57 | In progress
C001 | Residential Building A | T782 | Steel Framework Setup | Dave Brown | Blocked | Low | 2024-07-05 | 2024-07-17 |  | 0 | PVC Pipes | Plot 21, Riverside | 45548.09 | 52782.91 | Not started
C002 | Shopping Complex B | T654 | Foundation Excavation | Rachel Green | In Progress | High | 2023-05-10 | 2023-06-05 |  | 3 | Concrete | Market Street | 27991.78 | 53444.45 | In progress
C004 | Warehouse D | T520 | Interior Painting | Sarah Johnson | Blocked | Low | 2024-11-16 | 2024-11-30 |  | 0 | PVC Pipes | Industrial Park | 27877.39 | 26207.96 | Not started
C004 | Warehouse D | T717 | Foundation Excavation | Mike Adams | In Progress | High | 2023-12-03 | 2023-12-30 |  | 31 | Concrete | Industrial Park | 23106.71 | 23606.27 | In progress
C003 | Office Tower C | T660 | Interior Painting | Sarah Johnson | In Progress | Low | 2023-03-13 | 2023-04-05 |  | 1 | Concrete | Downtown Avenue | 20375.14 | 23574.28 | In progress
C001 | Residential Building A | T237 | Site Survey | John Miller | Not Started | High | 2024-03-18 | 2024-04-02 |  | 0 | Concrete | Plot 21, Riverside | 34355.78 | 0 | Not started
C002 | Shopping Complex B | T121 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2023-08-01 | 2023-08-11 | 2023-08-11 | 100 | Steel Beams | Market Street | 45677.32 | 69213.3 | No issues
C003 | Office Tower C | T899 | Foundation Excavation | Grace Allen | Not Started | High | 2024-03-13 | 2024-03-30 |  | 0 | Cement | Downtown Avenue | 12628.94 | 0 | Not started
C003 | Office Tower C | T192 | Electrical Wiring | Sarah Johnson | In Progress | High | 2024-12-27 | 2025-01-03 |  | 10 | Cement | Downtown Avenue | 5141.45 | 4232.17 | In progress
C001 | Residential Building A | T999 | Plumbing Installations | John Miller | Blocked | Medium | 2023-10-02 | 2023-10-25 |  | 0 | Cement | Plot 21, Riverside | 33364.24 | 29987.34 | Not started
C001 | Residential Building A | T534 | Interior Painting | Grace Allen | Not Started | Medium | 2023-01-09 | 2023-01-19 |  | 0 | PVC Pipes | Plot 21, Riverside | 48139.64 | 0 | Not started
C003 | Office Tower C | T256 | Roofing | Mike Adams | Not Started | Medium | 2024-12-11 | 2025-01-04 |  | 0 | PVC Pipes | Downtown Avenue | 14328.88 | 0 | Not started
C003 | Office Tower C | T312 | Foundation Excavation | John Miller | In Progress | Medium | 2023-11-09 | 2023-12-03 |  | 10 | Roofing Sheets | Downtown Avenue | 30885.16 | 33738.42 | In progress
C001 | Residential Building A | T794 | Site Survey | John Miller | Blocked | Low | 2023-01-23 | 2023-01-30 |  | 0 | Roofing Sheets | Plot 21, Riverside | 19135.59 | 13075.03 | Not started
C001 | Residential Building A | T964 | Interior Painting | Grace Allen | Not Started | Medium | 2024-02-07 | 2024-03-01 |  | 0 | Concrete | Plot 21, Riverside | 18767.27 | 0 | Not started
C001 | Residential Building A | T135 | Plumbing Installations | Dave Brown | Completed | Low | 2024-07-06 | 2024-07-17 | 2024-07-17 | 100 | Copper Wires | Plot 21, Riverside | 11768.64 | 14052.67 | No issues
C002 | Shopping Complex B | T852 | Steel Framework Setup | Emma White | Completed | Low | 2023-10-06 | 2023-10-16 | 2023-10-16 | 100 | Paint | Market Street | 20528.65 | 39287.22 | No issues
C002 | Shopping Complex B | T115 | Site Survey | Dave Brown | Blocked | Low | 2024-08-27 | 2024-09-18 |  | 0 | Copper Wires | Market Street | 39480 | 58626.31 | Not started
C001 | Residential Building A | T736 | Site Survey | Grace Allen | Completed | Medium | 2024-02-17 | 2024-03-05 | 2024-03-05 | 100 | Paint | Plot 21, Riverside | 18972.25 | 19127 | No issues
C003 | Office Tower C | T870 | Foundation Excavation | Dave Brown | Completed | Medium | 2024-05-28 | 2024-06-24 | 2024-06-24 | 100 | Paint | Downtown Avenue | 38064.5 | 28178.18 | No issues
C003 | Office Tower C | T352 | Roofing | Grace Allen | In Progress | Low | 2024-10-09 | 2024-10-31 |  | 91 | PVC Pipes | Downtown Avenue | 17083.92 | 13990.87 | In progress
C002 | Shopping Complex B | T375 | Steel Framework Setup | John Miller | Completed | Medium | 2024-08-05 | 2024-08-14 | 2024-08-14 | 100 | Copper Wires | Market Street | 35666.39 | 68263.66 | No issues
C002 | Shopping Complex B | T632 | Roofing | John Miller | Completed | Low | 2023-12-24 | 2024-01-22 | 2024-01-22 | 100 | Rebar | Market Street | 46981.28 | 75717.99 | No issues
C003 | Office Tower C | T521 | Concrete Pouring | Dave Brown | In Progress | High | 2024-10-01 | 2024-10-22 |  | 59 | Steel Beams | Downtown Avenue | 31080.81 | 36828.5 | In progress
C001 | Residential Building A | T188 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-08-11 | 2024-08-23 | 2024-08-23 | 100 | Cement | Plot 21, Riverside | 38190.99 | 27213.63 | No issues
C003 | Office Tower C | T249 | Steel Framework Setup | Emma White | Not Started | Low | 2023-03-19 | 2023-04-14 |  | 0 | PVC Pipes | Downtown Avenue | 5320.58 | 0 | Not started
C003 | Office Tower C | T931 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2023-04-19 | 2023-05-07 |  | 0 | Paint | Downtown Avenue | 34700.93 | 38325.48 | Not started
C001 | Residential Building A | T167 | Plumbing Installations | Rachel Green | Blocked | Low | 2023-05-03 | 2023-05-25 |  | 0 | PVC Pipes | Plot 21, Riverside | 21959.98 | 19221.48 | Not started
C002 | Shopping Complex B | T983 | Interior Painting | Grace Allen | Not Started | Medium | 2023-11-15 | 2023-12-01 |  | 0 | Cement | Market Street | 34655.31 | 0 | Not started
C001 | Residential Building A | T488 | Roofing | Sarah Johnson | Not Started | Low | 2024-06-17 | 2024-07-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 40959.17 | 0 | Not started
C003 | Office Tower C | T684 | Interior Painting | Emma White | Completed | High | 2024-04-05 | 2024-04-13 | 2024-04-13 | 100 | Rebar | Downtown Avenue | 19819.69 | 12772.17 | No issues
C003 | Office Tower C | T208 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2023-08-18 | 2023-08-28 |  | 0 | Rebar | Downtown Avenue | 29247.33 | 0 | Not started
C004 | Warehouse D | T119 | Roofing | Emma White | Blocked | Low | 2024-12-15 | 2025-01-03 |  | 0 | Rebar | Industrial Park | 31225.69 | 22839.7 | Not started
C002 | Shopping Complex B | T485 | Interior Painting | Grace Allen | Not Started | Low | 2024-03-21 | 2024-03-29 |  | 0 | Copper Wires | Market Street | 48577.49 | 0 | Not started
C004 | Warehouse D | T781 | Steel Framework Setup | John Miller | In Progress | Medium | 2024-05-04 | 2024-05-25 |  | 31 | Rebar | Industrial Park | 26852.19 | 16387.31 | In progress
C002 | Shopping Complex B | T232 | Roofing | Rachel Green | Completed | Low | 2024-08-20 | 2024-09-05 | 2024-09-05 | 100 | PVC Pipes | Market Street | 24211.13 | 48925.15 | No issues
C003 | Office Tower C | T355 | Plumbing Installations | Emma White | Blocked | Low | 2024-09-21 | 2024-09-28 |  | 0 | Rebar | Downtown Avenue | 14784.84 | 17449.68 | Not started
C001 | Residential Building A | T229 | Concrete Pouring | Emma White | In Progress | Medium | 2023-11-02 | 2023-11-23 |  | 41 | PVC Pipes | Plot 21, Riverside | 24298.84 | 27398.29 | In progress
C002 | Shopping Complex B | T863 | Site Survey | Emma White | Completed | Medium | 2023-07-15 | 2023-08-03 | 2023-08-03 | 100 | Rebar | Market Street | 39770.26 | 55221.03 | No issues
C003 | Office Tower C | T637 | Roofing | Mike Adams | Not Started | Low | 2024-08-11 | 2024-09-07 |  | 0 | Cement | Downtown Avenue | 47236.01 | 0 | Not started
C003 | Office Tower C | T690 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2024-09-20 | 2024-10-13 |  | 14 | Copper Wires | Downtown Avenue | 49275.62 | 35144.36 | In progress
C002 | Shopping Complex B | T933 | Concrete Pouring | Dave Brown | Blocked | Low | 2023-06-25 | 2023-07-19 |  | 0 | Roofing Sheets | Market Street | 9246.44 | 35755.62 | Not started
C003 | Office Tower C | T584 | Concrete Pouring | Emma White | In Progress | High | 2023-07-08 | 2023-07-25 |  | 38 | Roofing Sheets | Downtown Avenue | 18086.56 | 13273.8 | In progress
C004 | Warehouse D | T618 | Site Survey | Emma White | In Progress | High | 2024-08-21 | 2024-09-09 |  | 77 | Steel Beams | Industrial Park | 14456.72 | 11011.58 | In progress
C004 | Warehouse D | T154 | Interior Painting | Grace Allen | Not Started | Low | 2023-08-03 | 2023-08-16 |  | 0 | Cement | Industrial Park | 13408.47 | 0 | Not started
C002 | Shopping Complex B | T921 | Site Survey | Mike Adams | Blocked | Medium | 2024-05-06 | 2024-05-30 |  | 0 | Roofing Sheets | Market Street | 9010.51 | 34485.56 | Not started
C004 | Warehouse D | T572 | Site Survey | Rachel Green | Completed | Medium | 2023-06-13 | 2023-07-07 | 2023-07-07 | 100 | Steel Beams | Industrial Park | 37910.22 | 41294.54 | No issues
C002 | Shopping Complex B | T297 | Plumbing Installations | Rachel Green | In Progress | Low | 2024-10-09 | 2024-11-01 |  | 22 | Cement | Market Street | 28970.31 | 44898.5 | In progress
C001 | Residential Building A | T708 | Steel Framework Setup | Mike Adams | Not Started | High | 2023-07-09 | 2023-07-24 |  | 0 | Paint | Plot 21, Riverside | 43663.11 | 0 | Not started
C002 | Shopping Complex B | T522 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-11-11 | 2024-11-30 | 2024-11-30 | 100 | Roofing Sheets | Market Street | 16109.52 | 42107.93 | No issues
C002 | Shopping Complex B | T156 | Interior Painting | Grace Allen | In Progress | High | 2023-05-05 | 2023-05-27 |  | 45 | Rebar | Market Street | 12337.41 | 38003.82 | In progress
C002 | Shopping Complex B | T145 | Site Survey | Carlos Rivera | Blocked | Low | 2023-10-07 | 2023-11-06 |  | 0 | PVC Pipes | Market Street | 46046.59 | 59631.68 | Not started
C001 | Residential Building A | T167 | Roofing | Dave Brown | Blocked | High | 2024-05-22 | 2024-05-30 |  | 0 | Steel Beams | Plot 21, Riverside | 6342.45 | 5075.91 | Not started
C003 | Office Tower C | T500 | Concrete Pouring | Grace Allen | In Progress | Low | 2024-04-14 | 2024-05-03 |  | 8 | Steel Beams | Downtown Avenue | 7740.72 | 8274.69 | In progress
C001 | Residential Building A | T328 | Site Survey | Emma White | In Progress | High | 2023-01-02 | 2023-01-26 |  | 39 | Steel Beams | Plot 21, Riverside | 20500.97 | 15300.47 | In progress
C004 | Warehouse D | T453 | Foundation Excavation | Emma White | Completed | Medium | 2023-06-16 | 2023-06-27 | 2023-06-27 | 100 | Roofing Sheets | Industrial Park | 17843.35 | 12471.52 | No issues
C001 | Residential Building A | T244 | Foundation Excavation | Mike Adams | Completed | Medium | 2024-10-12 | 2024-11-11 | 2024-11-11 | 100 | Roofing Sheets | Plot 21, Riverside | 13855.92 | 12942.41 | No issues
C001 | Residential Building A | T255 | Concrete Pouring | Dave Brown | Not Started | Low | 2023-09-03 | 2023-09-28 |  | 0 | Paint | Plot 21, Riverside | 48046.2 | 0 | Not started
C002 | Shopping Complex B | T396 | Roofing | John Miller | Completed | High | 2024-04-05 | 2024-04-14 | 2024-04-14 | 100 | Copper Wires | Market Street | 20483.53 | 45249.72 | No issues
C003 | Office Tower C | T502 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2023-07-18 | 2023-08-13 |  | 0 | Roofing Sheets | Downtown Avenue | 30370.81 | 0 | Not started
C003 | Office Tower C | T791 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2023-11-18 | 2023-11-25 |  | 82 | Cement | Downtown Avenue | 5658.08 | 4326.58 | In progress
C002 | Shopping Complex B | T768 | Roofing | John Miller | In Progress | Low | 2023-08-26 | 2023-09-24 |  | 54 | Copper Wires | Market Street | 11483.51 | 32466.29 | In progress
C002 | Shopping Complex B | T913 | Steel Framework Setup | John Miller | Completed | Low | 2023-08-03 | 2023-08-19 | 2023-08-19 | 100 | Rebar | Market Street | 10218.07 | 36442.8 | No issues
C004 | Warehouse D | T843 | Plumbing Installations | Dave Brown | Blocked | Medium | 2024-04-26 | 2024-05-06 |  | 0 | Concrete | Industrial Park | 21867.14 | 22656.01 | Not started
C003 | Office Tower C | T120 | Plumbing Installations | Carlos Rivera | Completed | High | 2024-12-27 | 2025-01-25 | 2025-01-25 | 100 | Paint | Downtown Avenue | 45711.06 | 50618.57 | No issues
C004 | Warehouse D | T844 | Roofing | Dave Brown | Blocked | Low | 2024-02-16 | 2024-03-17 |  | 0 | Steel Beams | Industrial Park | 30098.84 | 26221.01 | Not started
C002 | Shopping Complex B | T328 | Roofing | Sarah Johnson | Not Started | Medium | 2024-07-16 | 2024-08-08 |  | 0 | Steel Beams | Market Street | 41273.62 | 0 | Not started
C003 | Office Tower C | T953 | Plumbing Installations | Mike Adams | Not Started | Medium | 2023-01-04 | 2023-01-29 |  | 0 | Steel Beams | Downtown Avenue | 34904.22 | 0 | Not started
C001 | Residential Building A | T166 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2023-09-07 | 2023-09-28 |  | 0 | Concrete | Plot 21, Riverside | 47155.92 | 0 | Not started
C002 | Shopping Complex B | T140 | Electrical Wiring | Grace Allen | Blocked | High | 2023-07-01 | 2023-07-11 |  | 0 | Paint | Market Street | 18694.4 | 40193.13 | Not started
C004 | Warehouse D | T903 | Site Survey | Mike Adams | Not Started | High | 2024-08-06 | 2024-09-02 |  | 0 | Cement | Industrial Park | 33224.07 | 0 | Not started
C002 | Shopping Complex B | T356 | Electrical Wiring | Mike Adams | Completed | Medium | 2023-12-28 | 2024-01-07 | 2024-01-07 | 100 | Cement | Market Street | 34840.01 | 61374.44 | No issues
C004 | Warehouse D | T872 | Plumbing Installations | Rachel Green | Completed | Low | 2024-11-06 | 2024-11-23 | 2024-11-23 | 100 | PVC Pipes | Industrial Park | 39626.43 | 44477.85 | No issues
C002 | Shopping Complex B | T342 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2023-01-25 | 2023-02-14 |  | 0 | Rebar | Market Street | 29912.85 | 0 | Not started
C001 | Residential Building A | T269 | Roofing | Mike Adams | Not Started | Low | 2023-04-28 | 2023-05-25 |  | 0 | PVC Pipes | Plot 21, Riverside | 24435.1 | 0 | Not started
C001 | Residential Building A | T945 | Foundation Excavation | Grace Allen | Not Started | Medium | 2023-10-06 | 2023-10-13 |  | 0 | Copper Wires | Plot 21, Riverside | 20247.28 | 0 | Not started
C004 | Warehouse D | T546 | Roofing | Grace Allen | Blocked | Medium | 2023-04-07 | 2023-04-24 |  | 0 | Rebar | Industrial Park | 6778.52 | 8056.96 | Not started
C003 | Office Tower C | T590 | Roofing | Carlos Rivera | Not Started | Medium | 2024-10-02 | 2024-10-16 |  | 0 | Roofing Sheets | Downtown Avenue | 18484.81 | 0 | Not started
C004 | Warehouse D | T826 | Roofing | Carlos Rivera | In Progress | High | 2023-03-09 | 2023-03-22 |  | 84 | Steel Beams | Industrial Park | 46119.1 | 42482.21 | In progress
C001 | Residential Building A | T547 | Foundation Excavation | Carlos Rivera | Completed | High | 2023-08-21 | 2023-08-28 | 2023-08-28 | 100 | Roofing Sheets | Plot 21, Riverside | 15018.21 | 9415.03 | No issues
C001 | Residential Building A | T782 | Interior Painting | Mike Adams | Completed | Low | 2023-02-27 | 2023-03-25 | 2023-03-25 | 100 | Concrete | Plot 21, Riverside | 40122.87 | 41342.79 | No issues
C003 | Office Tower C | T964 | Electrical Wiring | Sarah Johnson | In Progress | High | 2024-04-25 | 2024-05-22 |  | 80 | PVC Pipes | Downtown Avenue | 13321.08 | 11714.37 | In progress
C001 | Residential Building A | T546 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2024-03-06 | 2024-04-04 |  | 0 | Rebar | Plot 21, Riverside | 10630.43 | 12473.79 | Not started
C004 | Warehouse D | T518 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2024-12-28 | 2025-01-24 |  | 0 | PVC Pipes | Industrial Park | 38053.9 | 0 | Not started
C002 | Shopping Complex B | T114 | Interior Painting | Carlos Rivera | Blocked | High | 2023-02-20 | 2023-03-17 |  | 0 | Copper Wires | Market Street | 22727.04 | 49939.4 | Not started
C002 | Shopping Complex B | T336 | Site Survey | Sarah Johnson | Completed | High | 2023-01-10 | 2023-01-23 | 2023-01-23 | 100 | Rebar | Market Street | 46639.86 | 65631.59 | No issues
C003 | Office Tower C | T856 | Plumbing Installations | Carlos Rivera | In Progress | High | 2023-06-09 | 2023-06-26 |  | 96 | Concrete | Downtown Avenue | 32285.22 | 35278.53 | In progress
C001 | Residential Building A | T233 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2024-09-20 | 2024-10-17 |  | 54 | Cement | Plot 21, Riverside | 9411.92 | 8979.03 | In progress
C004 | Warehouse D | T460 | Electrical Wiring | Grace Allen | Blocked | High | 2023-03-07 | 2023-03-28 |  | 0 | Paint | Industrial Park | 5094.44 | 4960.15 | Not started
C004 | Warehouse D | T737 | Steel Framework Setup | John Miller | Completed | High | 2024-06-27 | 2024-07-12 | 2024-07-12 | 100 | PVC Pipes | Industrial Park | 36688.18 | 25485.85 | No issues
C002 | Shopping Complex B | T476 | Plumbing Installations | John Miller | Blocked | Medium | 2024-12-03 | 2024-12-24 |  | 0 | Cement | Market Street | 31486.7 | 46669.54 | Not started
C002 | Shopping Complex B | T116 | Foundation Excavation | Rachel Green | In Progress | Low | 2023-06-10 | 2023-07-02 |  | 49 | Cement | Market Street | 40266.07 | 66555.73 | In progress
C003 | Office Tower C | T666 | Interior Painting | Grace Allen | Not Started | Medium | 2024-04-19 | 2024-05-11 |  | 0 | PVC Pipes | Downtown Avenue | 49889.53 | 0 | Not started
C001 | Residential Building A | T146 | Plumbing Installations | Emma White | In Progress | Low | 2023-03-13 | 2023-03-23 |  | 45 | PVC Pipes | Plot 21, Riverside | 14626.49 | 11797.35 | In progress
C001 | Residential Building A | T623 | Plumbing Installations | Dave Brown | Not Started | Low | 2023-02-23 | 2023-03-13 |  | 0 | Cement | Plot 21, Riverside | 5799.03 | 0 | Not started
C003 | Office Tower C | T530 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-04-27 | 2023-05-06 |  | 0 | PVC Pipes | Downtown Avenue | 13750.68 | 8379.43 | Not started
C002 | Shopping Complex B | T313 | Steel Framework Setup | John Miller | Not Started | Medium | 2024-10-05 | 2024-10-25 |  | 0 | Concrete | Market Street | 6185.73 | 0 | Not started
C003 | Office Tower C | T655 | Roofing | John Miller | Not Started | High | 2024-01-03 | 2024-02-01 |  | 0 | Cement | Downtown Avenue | 16001 | 0 | Not started
C001 | Residential Building A | T516 | Steel Framework Setup | Emma White | Completed | High | 2024-08-20 | 2024-09-16 | 2024-09-16 | 100 | Cement | Plot 21, Riverside | 12156.92 | 10872.97 | No issues
C004 | Warehouse D | T998 | Concrete Pouring | John Miller | Completed | Medium | 2024-02-28 | 2024-03-20 | 2024-03-20 | 100 | Cement | Industrial Park | 7108.06 | 5347.86 | No issues
C001 | Residential Building A | T144 | Site Survey | Rachel Green | In Progress | Medium | 2024-09-14 | 2024-09-28 |  | 44 | Steel Beams | Plot 21, Riverside | 33167.95 | 20827.16 | In progress
C004 | Warehouse D | T803 | Electrical Wiring | Mike Adams | Blocked | Low | 2023-05-15 | 2023-06-10 |  | 0 | Paint | Industrial Park | 22025.16 | 14962.3 | Not started
C002 | Shopping Complex B | T961 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-03-16 | 2023-04-01 |  | 0 | Copper Wires | Market Street | 12286.24 | 0 | Not started
C001 | Residential Building A | T543 | Foundation Excavation | Carlos Rivera | Completed | Medium | 2023-10-27 | 2023-11-21 | 2023-11-21 | 100 | Steel Beams | Plot 21, Riverside | 11930.37 | 8149.72 | No issues
C001 | Residential Building A | T990 | Concrete Pouring | Dave Brown | Blocked | Medium | 2023-04-03 | 2023-04-21 |  | 0 | Rebar | Plot 21, Riverside | 40532.37 | 44515.79 | Not started
C003 | Office Tower C | T253 | Steel Framework Setup | Mike Adams | Not Started | Low | 2023-04-13 | 2023-05-06 |  | 0 | Copper Wires | Downtown Avenue | 44381.96 | 0 | Not started
C004 | Warehouse D | T784 | Interior Painting | John Miller | Not Started | Low | 2024-07-26 | 2024-08-25 |  | 0 | Rebar | Industrial Park | 39838.56 | 0 | Not started
C001 | Residential Building A | T309 | Concrete Pouring | Rachel Green | Blocked | Medium | 2023-02-16 | 2023-03-04 |  | 0 | PVC Pipes | Plot 21, Riverside | 31560.19 | 34354.19 | Not started
C004 | Warehouse D | T363 | Plumbing Installations | Sarah Johnson | In Progress | High | 2024-04-24 | 2024-05-22 |  | 87 | Concrete | Industrial Park | 12075.45 | 14106.54 | In progress
C002 | Shopping Complex B | T716 | Steel Framework Setup | Grace Allen | Completed | Medium | 2023-10-23 | 2023-11-07 | 2023-11-07 | 100 | Roofing Sheets | Market Street | 18207.04 | 46355.2 | No issues
C002 | Shopping Complex B | T706 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2024-11-13 | 2024-12-11 |  | 90 | Roofing Sheets | Market Street | 18588.12 | 42679.87 | In progress
C001 | Residential Building A | T258 | Roofing | Emma White | Not Started | High | 2024-09-27 | 2024-10-21 |  | 0 | Rebar | Plot 21, Riverside | 6987.03 | 0 | Not started
C004 | Warehouse D | T953 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2023-11-23 | 2023-12-18 |  | 0 | Copper Wires | Industrial Park | 17554.8 | 19900.17 | Not started
C004 | Warehouse D | T454 | Steel Framework Setup | Grace Allen | Completed | High | 2024-04-21 | 2024-05-12 | 2024-05-12 | 100 | Steel Beams | Industrial Park | 11108.71 | 10798.3 | No issues
C004 | Warehouse D | T514 | Plumbing Installations | Rachel Green | Completed | High | 2023-05-12 | 2023-06-01 | 2023-06-01 | 100 | PVC Pipes | Industrial Park | 40603.38 | 24414.98 | No issues
C001 | Residential Building A | T866 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-07-10 | 2024-08-04 | 2024-08-04 | 100 | Roofing Sheets | Plot 21, Riverside | 13930.78 | 9100.73 | No issues
C002 | Shopping Complex B | T202 | Roofing | Grace Allen | Not Started | High | 2024-07-11 | 2024-07-25 |  | 0 | Concrete | Market Street | 6197.5 | 0 | Not started
C004 | Warehouse D | T697 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2023-07-06 | 2023-07-25 |  | 0 | Rebar | Industrial Park | 18183.37 | 14041.63 | Not started
C003 | Office Tower C | T621 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-10-12 | 2023-10-26 |  | 0 | Rebar | Downtown Avenue | 6875.09 | 0 | Not started
C004 | Warehouse D | T957 | Roofing | Carlos Rivera | Not Started | High | 2023-10-03 | 2023-10-29 |  | 0 | Concrete | Industrial Park | 10060.22 | 0 | Not started
C002 | Shopping Complex B | T606 | Roofing | John Miller | Not Started | Low | 2024-05-04 | 2024-05-20 |  | 0 | Steel Beams | Market Street | 42377.65 | 0 | Not started
C002 | Shopping Complex B | T560 | Roofing | John Miller | Not Started | High | 2024-08-01 | 2024-08-20 |  | 0 | Copper Wires | Market Street | 40296.21 | 0 | Not started
C004 | Warehouse D | T536 | Roofing | Dave Brown | Completed | Medium | 2023-11-27 | 2023-12-19 | 2023-12-19 | 100 | Cement | Industrial Park | 8357.08 | 6409.18 | No issues
C003 | Office Tower C | T284 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-07-01 | 2023-07-25 |  | 0 | Steel Beams | Downtown Avenue | 49677.12 | 0 | Not started
C004 | Warehouse D | T186 | Plumbing Installations | Dave Brown | Completed | High | 2023-09-02 | 2023-09-16 | 2023-09-16 | 100 | Copper Wires | Industrial Park | 39021.45 | 33574.07 | No issues
C004 | Warehouse D | T800 | Plumbing Installations | John Miller | In Progress | High | 2024-05-19 | 2024-05-29 |  | 85 | Roofing Sheets | Industrial Park | 39314.23 | 43343.66 | In progress
C001 | Residential Building A | T761 | Site Survey | Mike Adams | In Progress | High | 2023-02-08 | 2023-02-27 |  | 83 | Concrete | Plot 21, Riverside | 30367.35 | 22209.67 | In progress
C004 | Warehouse D | T170 | Roofing | Grace Allen | Not Started | High | 2023-12-06 | 2023-12-15 |  | 0 | Concrete | Industrial Park | 21034.09 | 0 | Not started
C003 | Office Tower C | T676 | Steel Framework Setup | John Miller | Blocked | High | 2024-08-06 | 2024-08-28 |  | 0 | Cement | Downtown Avenue | 8024 | 7324.6 | Not started
C001 | Residential Building A | T996 | Roofing | Rachel Green | Not Started | Medium | 2023-10-26 | 2023-11-19 |  | 0 | Rebar | Plot 21, Riverside | 10545.87 | 0 | Not started
C001 | Residential Building A | T321 | Site Survey | Sarah Johnson | Completed | High | 2024-06-28 | 2024-07-18 | 2024-07-18 | 100 | PVC Pipes | Plot 21, Riverside | 19240.82 | 22581.14 | No issues
C001 | Residential Building A | T950 | Plumbing Installations | Mike Adams | Completed | High | 2023-09-17 | 2023-10-12 | 2023-10-12 | 100 | Rebar | Plot 21, Riverside | 22859.91 | 18951.34 | No issues
C003 | Office Tower C | T220 | Roofing | Sarah Johnson | Completed | High | 2023-06-06 | 2023-06-14 | 2023-06-14 | 100 | Steel Beams | Downtown Avenue | 41016.9 | 43905.76 | No issues
C002 | Shopping Complex B | T654 | Electrical Wiring | Mike Adams | In Progress | Medium | 2024-09-10 | 2024-09-23 |  | 17 | Steel Beams | Market Street | 29611.05 | 47596.51 | In progress
C002 | Shopping Complex B | T498 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2023-04-17 | 2023-05-01 |  | 0 | Rebar | Market Street | 43983.02 | 0 | Not started
C003 | Office Tower C | T205 | Roofing | Grace Allen | Not Started | Low | 2024-05-22 | 2024-06-10 |  | 0 | Cement | Downtown Avenue | 35459.9 | 0 | Not started
C004 | Warehouse D | T193 | Roofing | Dave Brown | Not Started | High | 2023-11-28 | 2023-12-13 |  | 0 | Roofing Sheets | Industrial Park | 48013.54 | 0 | Not started
C002 | Shopping Complex B | T324 | Foundation Excavation | Emma White | In Progress | Low | 2023-04-25 | 2023-05-17 |  | 44 | Paint | Market Street | 21404.65 | 51126.54 | In progress
C002 | Shopping Complex B | T464 | Roofing | Carlos Rivera | In Progress | Low | 2024-10-08 | 2024-10-17 |  | 37 | Rebar | Market Street | 11956.6 | 34980.12 | In progress
C004 | Warehouse D | T442 | Roofing | Dave Brown | In Progress | Low | 2023-07-12 | 2023-08-01 |  | 95 | Steel Beams | Industrial Park | 43705.41 | 30525.75 | In progress
C002 | Shopping Complex B | T461 | Concrete Pouring | Grace Allen | Blocked | Medium | 2024-03-18 | 2024-04-13 |  | 0 | Cement | Market Street | 8454.57 | 32054.16 | Not started
C004 | Warehouse D | T483 | Electrical Wiring | Sarah Johnson | Completed | High | 2023-10-21 | 2023-11-18 | 2023-11-18 | 100 | Rebar | Industrial Park | 29862.48 | 20301.8 | No issues
C004 | Warehouse D | T946 | Concrete Pouring | Dave Brown | Completed | High | 2024-06-04 | 2024-06-17 | 2024-06-17 | 100 | Roofing Sheets | Industrial Park | 12694.51 | 7704.27 | No issues
C004 | Warehouse D | T843 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-03-10 | 2024-03-31 |  | 0 | Roofing Sheets | Industrial Park | 20001.33 | 23256.38 | Not started
C004 | Warehouse D | T716 | Site Survey | Sarah Johnson | Blocked | Low | 2024-12-18 | 2024-12-30 |  | 0 | Paint | Industrial Park | 13657.27 | 16144.17 | Not started
C002 | Shopping Complex B | T683 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-02-28 | 2023-03-27 |  | 0 | Rebar | Market Street | 19826.22 | 49157.31 | Not started
C003 | Office Tower C | T842 | Roofing | Mike Adams | Blocked | High | 2023-10-03 | 2023-10-10 |  | 0 | Paint | Downtown Avenue | 47840.66 | 44059.95 | Not started
C002 | Shopping Complex B | T941 | Plumbing Installations | Emma White | In Progress | High | 2023-05-08 | 2023-06-04 |  | 29 | Concrete | Market Street | 13914.36 | 39278.47 | In progress
C002 | Shopping Complex B | T669 | Interior Painting | John Miller | Blocked | High | 2023-12-22 | 2024-01-06 |  | 0 | Paint | Market Street | 18565.19 | 37034.46 | Not started
C003 | Office Tower C | T524 | Interior Painting | Rachel Green | In Progress | Medium | 2023-06-22 | 2023-07-08 |  | 10 | Paint | Downtown Avenue | 42347.66 | 50739.72 | In progress
C001 | Residential Building A | T172 | Concrete Pouring | Mike Adams | In Progress | Low | 2024-11-12 | 2024-12-12 |  | 16 | Concrete | Plot 21, Riverside | 39920.58 | 44532.46 | In progress
C004 | Warehouse D | T379 | Electrical Wiring | John Miller | Not Started | Low | 2024-03-25 | 2024-04-10 |  | 0 | PVC Pipes | Industrial Park | 17291.19 | 0 | Not started
C003 | Office Tower C | T130 | Foundation Excavation | Emma White | In Progress | High | 2023-02-04 | 2023-02-28 |  | 99 | Roofing Sheets | Downtown Avenue | 47783.21 | 38138.23 | In progress
C004 | Warehouse D | T775 | Site Survey | Grace Allen | Completed | Low | 2024-12-21 | 2025-01-06 | 2025-01-06 | 100 | Steel Beams | Industrial Park | 15774.62 | 12616.64 | No issues
C003 | Office Tower C | T996 | Site Survey | Rachel Green | In Progress | Low | 2024-10-06 | 2024-10-17 |  | 73 | Rebar | Downtown Avenue | 23398.77 | 18332.58 | In progress
C001 | Residential Building A | T378 | Steel Framework Setup | John Miller | Completed | Low | 2024-06-26 | 2024-07-25 | 2024-07-25 | 100 | Roofing Sheets | Plot 21, Riverside | 46403.88 | 49349.15 | No issues
C004 | Warehouse D | T683 | Concrete Pouring | Mike Adams | Not Started | Medium | 2024-11-23 | 2024-12-21 |  | 0 | Rebar | Industrial Park | 38366.51 | 0 | Not started
C002 | Shopping Complex B | T868 | Plumbing Installations | Emma White | Blocked | High | 2024-10-06 | 2024-10-25 |  | 0 | Paint | Market Street | 24662.77 | 52349.56 | Not started
C001 | Residential Building A | T546 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-03-08 | 2024-03-23 |  | 0 | Steel Beams | Plot 21, Riverside | 10280.61 | 0 | Not started
C004 | Warehouse D | T145 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-03-25 | 2023-04-05 |  | 0 | Roofing Sheets | Industrial Park | 33792.31 | 0 | Not started
C002 | Shopping Complex B | T786 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2024-10-22 | 2024-11-10 | 2024-11-10 | 100 | Paint | Market Street | 15145.04 | 41297.29 | No issues
C002 | Shopping Complex B | T633 | Concrete Pouring | Rachel Green | Blocked | High | 2023-03-27 | 2023-04-25 |  | 0 | Rebar | Market Street | 11856.08 | 32717.38 | Not started
C004 | Warehouse D | T256 | Site Survey | Dave Brown | In Progress | High | 2024-06-01 | 2024-06-18 |  | 58 | Cement | Industrial Park | 44468.89 | 43629.14 | In progress
C002 | Shopping Complex B | T954 | Roofing | Grace Allen | In Progress | High | 2024-12-23 | 2025-01-01 |  | 64 | Paint | Market Street | 13854.52 | 40346.95 | In progress
C002 | Shopping Complex B | T873 | Interior Painting | Sarah Johnson | Completed | Low | 2024-06-02 | 2024-06-12 | 2024-06-12 | 100 | Concrete | Market Street | 12226.41 | 36215.42 | No issues
C002 | Shopping Complex B | T169 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2023-07-10 | 2023-07-24 |  | 0 | Paint | Market Street | 7071.21 | 33961.47 | Not started
C002 | Shopping Complex B | T999 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-11-20 | 2023-12-02 |  | 67 | PVC Pipes | Market Street | 29482.62 | 56931.13 | In progress
C003 | Office Tower C | T691 | Concrete Pouring | Sarah Johnson | In Progress | High | 2023-12-28 | 2024-01-04 |  | 86 | Cement | Downtown Avenue | 20067.45 | 20993.39 | In progress
C004 | Warehouse D | T691 | Plumbing Installations | Mike Adams | Blocked | High | 2024-12-13 | 2025-01-09 |  | 0 | Steel Beams | Industrial Park | 32531.74 | 20060.14 | Not started
C003 | Office Tower C | T604 | Electrical Wiring | Carlos Rivera | Completed | High | 2024-02-26 | 2024-03-22 | 2024-03-22 | 100 | Cement | Downtown Avenue | 47488.07 | 31715.14 | No issues
C004 | Warehouse D | T532 | Interior Painting | Rachel Green | Blocked | Medium | 2023-01-27 | 2023-02-12 |  | 0 | Roofing Sheets | Industrial Park | 38644.65 | 28350.35 | Not started
C003 | Office Tower C | T986 | Site Survey | Dave Brown | Completed | Medium | 2024-01-09 | 2024-01-23 | 2024-01-23 | 100 | PVC Pipes | Downtown Avenue | 8487.85 | 8756.12 | No issues
C004 | Warehouse D | T852 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-08-07 | 2023-08-16 |  | 78 | Steel Beams | Industrial Park | 27131.91 | 18056.92 | In progress
C001 | Residential Building A | T745 | Concrete Pouring | Grace Allen | In Progress | High | 2024-11-13 | 2024-12-01 |  | 79 | PVC Pipes | Plot 21, Riverside | 25103.63 | 24211.01 | In progress
C003 | Office Tower C | T901 | Roofing | John Miller | Blocked | Low | 2023-12-18 | 2024-01-02 |  | 0 | Roofing Sheets | Downtown Avenue | 8003.36 | 5637.83 | Not started
C004 | Warehouse D | T949 | Interior Painting | Carlos Rivera | Completed | Medium | 2024-09-20 | 2024-10-02 | 2024-10-02 | 100 | Roofing Sheets | Industrial Park | 19396.66 | 16192.81 | No issues
C004 | Warehouse D | T864 | Roofing | Emma White | In Progress | Medium | 2023-10-25 | 2023-11-16 |  | 17 | PVC Pipes | Industrial Park | 44497.29 | 36642.38 | In progress
C002 | Shopping Complex B | T404 | Plumbing Installations | Sarah Johnson | Not Started | High | 2023-08-20 | 2023-09-08 |  | 0 | Roofing Sheets | Market Street | 28349.04 | 0 | Not started
C002 | Shopping Complex B | T322 | Steel Framework Setup | Mike Adams | Not Started | Medium | 2024-08-19 | 2024-09-01 |  | 0 | Rebar | Market Street | 46007.03 | 0 | Not started
C001 | Residential Building A | T269 | Concrete Pouring | Mike Adams | In Progress | High | 2024-02-23 | 2024-03-11 |  | 82 | Steel Beams | Plot 21, Riverside | 11129.58 | 12229.43 | In progress
C001 | Residential Building A | T710 | Site Survey | John Miller | Blocked | High | 2024-10-14 | 2024-11-07 |  | 0 | Concrete | Plot 21, Riverside | 17838.79 | 20966.85 | Not started
C001 | Residential Building A | T401 | Electrical Wiring | Rachel Green | In Progress | High | 2024-07-14 | 2024-08-12 |  | 62 | Roofing Sheets | Plot 21, Riverside | 32014.01 | 30553.78 | In progress
C003 | Office Tower C | T599 | Plumbing Installations | Mike Adams | In Progress | High | 2023-09-03 | 2023-09-29 |  | 57 | Roofing Sheets | Downtown Avenue | 18287.54 | 14831.1 | In progress
C002 | Shopping Complex B | T570 | Concrete Pouring | John Miller | In Progress | High | 2023-10-25 | 2023-11-22 |  | 0 | Paint | Market Street | 6828.89 | 31247.2 | In progress
C001 | Residential Building A | T603 | Foundation Excavation | Grace Allen | Completed | Medium | 2023-06-26 | 2023-07-20 | 2023-07-20 | 100 | Concrete | Plot 21, Riverside | 25940.19 | 26671.81 | No issues
C002 | Shopping Complex B | T517 | Plumbing Installations | John Miller | Blocked | High | 2024-10-16 | 2024-11-01 |  | 0 | Rebar | Market Street | 34849.8 | 54168.98 | Not started
C004 | Warehouse D | T922 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2023-02-25 | 2023-03-26 |  | 93 | Rebar | Industrial Park | 35455.82 | 24550.91 | In progress
C001 | Residential Building A | T117 | Plumbing Installations | Emma White | Completed | Low | 2023-03-27 | 2023-04-12 | 2023-04-12 | 100 | Steel Beams | Plot 21, Riverside | 25385.19 | 23252.36 | No issues
C003 | Office Tower C | T786 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2024-03-13 | 2024-03-23 |  | 73 | Roofing Sheets | Downtown Avenue | 11902.07 | 12682.32 | In progress
C001 | Residential Building A | T222 | Site Survey | Emma White | In Progress | Low | 2023-03-16 | 2023-03-31 |  | 83 | Paint | Plot 21, Riverside | 45790.44 | 28832.27 | In progress
C001 | Residential Building A | T726 | Electrical Wiring | Emma White | Completed | Medium | 2023-02-13 | 2023-02-26 | 2023-02-26 | 100 | Concrete | Plot 21, Riverside | 19228.12 | 17974.66 | No issues
C001 | Residential Building A | T385 | Interior Painting | Rachel Green | In Progress | Low | 2024-02-11 | 2024-02-29 |  | 47 | Copper Wires | Plot 21, Riverside | 10956.06 | 10642.46 | In progress
C003 | Office Tower C | T712 | Site Survey | Rachel Green | Completed | Medium | 2023-09-09 | 2023-09-24 | 2023-09-24 | 100 | Roofing Sheets | Downtown Avenue | 34690.31 | 37793.45 | No issues
C004 | Warehouse D | T659 | Roofing | Dave Brown | Completed | High | 2024-04-08 | 2024-04-20 | 2024-04-20 | 100 | Roofing Sheets | Industrial Park | 36912.7 | 37517.52 | No issues
C003 | Office Tower C | T197 | Electrical Wiring | John Miller | Blocked | Medium | 2024-12-26 | 2025-01-20 |  | 0 | Paint | Downtown Avenue | 18536.43 | 12381.22 | Not started
C002 | Shopping Complex B | T357 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2024-10-07 | 2024-10-20 |  | 0 | Cement | Market Street | 45412.29 | 0 | Not started
C003 | Office Tower C | T523 | Foundation Excavation | Mike Adams | Not Started | Low | 2024-02-15 | 2024-03-04 |  | 0 | Roofing Sheets | Downtown Avenue | 39508.02 | 0 | Not started
C001 | Residential Building A | T569 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-11-09 | 2024-11-26 |  | 90 | Concrete | Plot 21, Riverside | 9965.6 | 11539.54 | In progress
C001 | Residential Building A | T449 | Steel Framework Setup | Grace Allen | Completed | Low | 2023-01-25 | 2023-02-12 | 2023-02-12 | 100 | Concrete | Plot 21, Riverside | 36583.72 | 38816.51 | No issues
C004 | Warehouse D | T892 | Site Survey | Rachel Green | Completed | Low | 2023-08-12 | 2023-08-20 | 2023-08-20 | 100 | Rebar | Industrial Park | 39515.95 | 42342.06 | No issues
C001 | Residential Building A | T554 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-01-14 | 2024-02-01 |  | 0 | Cement | Plot 21, Riverside | 6044.4 | 0 | Not started
C003 | Office Tower C | T544 | Electrical Wiring | John Miller | Blocked | Medium | 2024-07-17 | 2024-08-08 |  | 0 | Paint | Downtown Avenue | 33480.97 | 37520.73 | Not started
C002 | Shopping Complex B | T927 | Foundation Excavation | Sarah Johnson | Completed | Low | 2024-07-22 | 2024-08-13 | 2024-08-13 | 100 | PVC Pipes | Market Street | 15186.51 | 43710.56 | No issues
C001 | Residential Building A | T635 | Site Survey | Rachel Green | Not Started | Low | 2024-04-05 | 2024-04-13 |  | 0 | Concrete | Plot 21, Riverside | 24546.15 | 0 | Not started
C001 | Residential Building A | T343 | Foundation Excavation | Mike Adams | Not Started | Low | 2023-11-12 | 2023-11-21 |  | 0 | Rebar | Plot 21, Riverside | 5061.55 | 0 | Not started
C001 | Residential Building A | T383 | Plumbing Installations | Carlos Rivera | Not Started | High | 2023-06-03 | 2023-06-20 |  | 0 | Roofing Sheets | Plot 21, Riverside | 8621.47 | 0 | Not started
C001 | Residential Building A | T834 | Steel Framework Setup | Grace Allen | In Progress | Low | 2024-06-07 | 2024-06-27 |  | 80 | Rebar | Plot 21, Riverside | 46805.52 | 51811.85 | In progress
C004 | Warehouse D | T710 | Concrete Pouring | Mike Adams | Not Started | High | 2023-08-18 | 2023-09-15 |  | 0 | Rebar | Industrial Park | 39265.02 | 0 | Not started
C001 | Residential Building A | T702 | Plumbing Installations | Emma White | Completed | Medium | 2023-12-19 | 2024-01-12 | 2024-01-12 | 100 | Paint | Plot 21, Riverside | 5636.44 | 4917.8 | No issues
C003 | Office Tower C | T780 | Foundation Excavation | Emma White | Blocked | High | 2024-12-04 | 2024-12-12 |  | 0 | PVC Pipes | Downtown Avenue | 32964.1 | 35084.49 | Not started
C003 | Office Tower C | T383 | Steel Framework Setup | Carlos Rivera | In Progress | High | 2024-12-16 | 2024-12-29 |  | 12 | Roofing Sheets | Downtown Avenue | 28075.74 | 24785.45 | In progress
C002 | Shopping Complex B | T509 | Concrete Pouring | Dave Brown | Completed | Medium | 2023-08-22 | 2023-09-08 | 2023-09-08 | 100 | Paint | Market Street | 46681.85 | 60964.04 | No issues
C001 | Residential Building A | T526 | Site Survey | Dave Brown | Blocked | High | 2023-10-16 | 2023-10-29 |  | 0 | Paint | Plot 21, Riverside | 37866.94 | 32178.79 | Not started
C003 | Office Tower C | T216 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2024-04-02 | 2024-04-26 |  | 43 | Paint | Downtown Avenue | 46641.97 | 55928.35 | In progress
C001 | Residential Building A | T700 | Site Survey | Dave Brown | Not Started | Medium | 2023-01-12 | 2023-02-02 |  | 0 | Rebar | Plot 21, Riverside | 22577.45 | 0 | Not started
C003 | Office Tower C | T662 | Foundation Excavation | Sarah Johnson | Not Started | High | 2024-09-18 | 2024-09-26 |  | 0 | Rebar | Downtown Avenue | 16215.33 | 0 | Not started
C002 | Shopping Complex B | T985 | Roofing | John Miller | In Progress | High | 2023-04-10 | 2023-04-23 |  | 31 | PVC Pipes | Market Street | 39068.71 | 52343.99 | In progress
C002 | Shopping Complex B | T340 | Concrete Pouring | Mike Adams | In Progress | High | 2024-12-05 | 2024-12-12 |  | 48 | Steel Beams | Market Street | 48790 | 78903.92 | In progress
C001 | Residential Building A | T592 | Foundation Excavation | Mike Adams | Completed | Medium | 2023-12-19 | 2024-01-18 | 2024-01-18 | 100 | Rebar | Plot 21, Riverside | 43747.48 | 47793.96 | No issues
C004 | Warehouse D | T357 | Site Survey | Sarah Johnson | Not Started | High | 2024-03-06 | 2024-04-03 |  | 0 | PVC Pipes | Industrial Park | 7824.67 | 0 | Not started
C001 | Residential Building A | T282 | Interior Painting | Mike Adams | Blocked | Medium | 2023-05-12 | 2023-06-07 |  | 0 | Cement | Plot 21, Riverside | 10492.79 | 6661.33 | Not started
C003 | Office Tower C | T297 | Roofing | Sarah Johnson | Not Started | Low | 2024-10-02 | 2024-10-14 |  | 0 | Concrete | Downtown Avenue | 46863.82 | 0 | Not started
C003 | Office Tower C | T927 | Site Survey | Emma White | In Progress | High | 2024-03-25 | 2024-04-16 |  | 4 | Rebar | Downtown Avenue | 12159 | 8924.52 | In progress
C003 | Office Tower C | T463 | Concrete Pouring | Mike Adams | In Progress | High | 2024-02-13 | 2024-03-09 |  | 66 | Rebar | Downtown Avenue | 40737.09 | 38129.99 | In progress
C004 | Warehouse D | T837 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-05-19 | 2024-05-27 |  | 0 | PVC Pipes | Industrial Park | 7820.74 | 7079.48 | Not started
C004 | Warehouse D | T769 | Foundation Excavation | Carlos Rivera | Blocked | High | 2024-04-13 | 2024-05-13 |  | 0 | Concrete | Industrial Park | 47582.25 | 34666.94 | Not started
C002 | Shopping Complex B | T462 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2024-10-08 | 2024-10-24 | 2024-10-24 | 100 | Concrete | Market Street | 41272.06 | 65361.06 | No issues
C002 | Shopping Complex B | T167 | Electrical Wiring | Sarah Johnson | In Progress | High | 2023-01-08 | 2023-02-07 |  | 7 | Rebar | Market Street | 31974.21 | 61650.27 | In progress
C001 | Residential Building A | T971 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-11-06 | 2023-11-22 |  | 84 | Paint | Plot 21, Riverside | 14647.97 | 12823.92 | In progress
C001 | Residential Building A | T110 | Roofing | Carlos Rivera | Not Started | Low | 2023-08-18 | 2023-08-30 |  | 0 | Copper Wires | Plot 21, Riverside | 43306.33 | 0 | Not started
C002 | Shopping Complex B | T833 | Concrete Pouring | Dave Brown | Blocked | High | 2024-03-23 | 2024-04-07 |  | 0 | Roofing Sheets | Market Street | 22426.96 | 45936.08 | Not started
C001 | Residential Building A | T360 | Concrete Pouring | Grace Allen | In Progress | Medium | 2024-01-09 | 2024-01-24 |  | 51 | Roofing Sheets | Plot 21, Riverside | 6077.51 | 4940.32 | In progress
C004 | Warehouse D | T108 | Foundation Excavation | Dave Brown | Blocked | High | 2023-03-17 | 2023-04-09 |  | 0 | Rebar | Industrial Park | 11427.17 | 12662.91 | Not started
C002 | Shopping Complex B | T321 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-12-23 | 2025-01-10 |  | 0 | Rebar | Market Street | 13115.14 | 37473.5 | Not started
C002 | Shopping Complex B | T979 | Interior Painting | Emma White | Completed | High | 2023-01-24 | 2023-02-05 | 2023-02-05 | 100 | Copper Wires | Market Street | 47456.68 | 72126.22 | No issues
C004 | Warehouse D | T627 | Concrete Pouring | John Miller | In Progress | High | 2023-05-06 | 2023-05-16 |  | 85 | Copper Wires | Industrial Park | 13207.17 | 11111.43 | In progress
C002 | Shopping Complex B | T406 | Concrete Pouring | Emma White | Not Started | Medium | 2024-11-20 | 2024-11-30 |  | 0 | Cement | Market Street | 41092.86 | 0 | Not started
C004 | Warehouse D | T767 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2024-08-12 | 2024-08-23 |  | 90 | Roofing Sheets | Industrial Park | 10916.71 | 13028.94 | In progress
C003 | Office Tower C | T367 | Site Survey | Carlos Rivera | Blocked | High | 2023-03-23 | 2023-04-07 |  | 0 | PVC Pipes | Downtown Avenue | 20809.28 | 16491.99 | Not started
C001 | Residential Building A | T434 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2023-03-17 | 2023-04-04 | 2023-04-04 | 100 | Cement | Plot 21, Riverside | 11593.84 | 13274.9 | No issues
C004 | Warehouse D | T284 | Interior Painting | Grace Allen | Completed | Low | 2023-07-28 | 2023-08-14 | 2023-08-14 | 100 | Concrete | Industrial Park | 16508.03 | 19631.47 | No issues
C003 | Office Tower C | T373 | Concrete Pouring | Sarah Johnson | Completed | Low | 2023-03-04 | 2023-03-22 | 2023-03-22 | 100 | Cement | Downtown Avenue | 10852.59 | 10098.51 | No issues
C002 | Shopping Complex B | T652 | Foundation Excavation | Emma White | Blocked | Medium | 2024-04-16 | 2024-04-26 |  | 0 | Concrete | Market Street | 43555.27 | 76126.9 | Not started
C002 | Shopping Complex B | T592 | Interior Painting | Dave Brown | Blocked | Medium | 2024-10-12 | 2024-11-09 |  | 0 | Rebar | Market Street | 38782.39 | 60015.64 | Not started
C002 | Shopping Complex B | T892 | Interior Painting | Emma White | Completed | Low | 2023-06-15 | 2023-07-11 | 2023-07-11 | 100 | Concrete | Market Street | 8690.15 | 31749.89 | No issues
C001 | Residential Building A | T156 | Electrical Wiring | Dave Brown | Not Started | Medium | 2024-06-08 | 2024-06-18 |  | 0 | Copper Wires | Plot 21, Riverside | 32874.34 | 0 | Not started
C001 | Residential Building A | T761 | Interior Painting | Carlos Rivera | Not Started | Medium | 2023-08-26 | 2023-09-14 |  | 0 | Cement | Plot 21, Riverside | 11463.81 | 0 | Not started
C004 | Warehouse D | T923 | Interior Painting | Carlos Rivera | Blocked | Low | 2024-01-24 | 2024-02-09 |  | 0 | Rebar | Industrial Park | 17159.68 | 15681.94 | Not started
C001 | Residential Building A | T735 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2024-02-23 | 2024-03-22 |  | 0 | Roofing Sheets | Plot 21, Riverside | 38653.75 | 39567.95 | Not started
C002 | Shopping Complex B | T618 | Roofing | Grace Allen | Completed | Low | 2024-07-11 | 2024-08-10 | 2024-08-10 | 100 | Concrete | Market Street | 29473.79 | 51236.56 | No issues
C003 | Office Tower C | T484 | Site Survey | Grace Allen | Not Started | High | 2024-06-13 | 2024-06-27 |  | 0 | Steel Beams | Downtown Avenue | 48463.94 | 0 | Not started
C002 | Shopping Complex B | T292 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2024-04-18 | 2024-05-04 |  | 12 | Cement | Market Street | 39152 | 58508.84 | In progress
C001 | Residential Building A | T827 | Concrete Pouring | Grace Allen | Completed | Medium | 2023-03-07 | 2023-03-16 | 2023-03-16 | 100 | Steel Beams | Plot 21, Riverside | 12210.08 | 7710.79 | No issues
C003 | Office Tower C | T476 | Foundation Excavation | Mike Adams | Completed | Low | 2023-03-11 | 2023-04-09 | 2023-04-09 | 100 | Paint | Downtown Avenue | 41161.42 | 35595.05 | No issues
C002 | Shopping Complex B | T489 | Concrete Pouring | Dave Brown | Blocked | High | 2023-09-09 | 2023-10-09 |  | 0 | Roofing Sheets | Market Street | 24604.12 | 46124.99 | Not started
C003 | Office Tower C | T562 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-01-08 | 2024-01-16 |  | 86 | Copper Wires | Downtown Avenue | 5653.8 | 4003.56 | In progress
C001 | Residential Building A | T313 | Plumbing Installations | Grace Allen | Not Started | High | 2023-04-17 | 2023-05-11 |  | 0 | Steel Beams | Plot 21, Riverside | 10165 | 0 | Not started
C004 | Warehouse D | T604 | Steel Framework Setup | John Miller | Not Started | High | 2023-06-24 | 2023-07-18 |  | 0 | Roofing Sheets | Industrial Park | 41406.73 | 0 | Not started
C001 | Residential Building A | T366 | Concrete Pouring | Dave Brown | Blocked | Medium | 2024-07-04 | 2024-07-21 |  | 0 | PVC Pipes | Plot 21, Riverside | 32135.56 | 34947.57 | Not started
C001 | Residential Building A | T767 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2023-10-17 | 2023-11-09 |  | 0 | Paint | Plot 21, Riverside | 46337.23 | 35110.29 | Not started
C002 | Shopping Complex B | T175 | Electrical Wiring | Dave Brown | Blocked | High | 2024-02-08 | 2024-03-05 |  | 0 | Copper Wires | Market Street | 41676.71 | 60934.55 | Not started
C001 | Residential Building A | T675 | Steel Framework Setup | Emma White | Blocked | High | 2023-05-02 | 2023-05-18 |  | 0 | PVC Pipes | Plot 21, Riverside | 12325.7 | 14157.5 | Not started
C004 | Warehouse D | T140 | Electrical Wiring | John Miller | Blocked | High | 2023-12-24 | 2024-01-18 |  | 0 | Cement | Industrial Park | 5584.58 | 3455.36 | Not started
C002 | Shopping Complex B | T139 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2023-08-22 | 2023-09-06 |  | 0 | Paint | Market Street | 12621.79 | 0 | Not started
C003 | Office Tower C | T761 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2024-12-27 | 2025-01-16 |  | 21 | Cement | Downtown Avenue | 22737.73 | 22729.6 | In progress
C001 | Residential Building A | T485 | Electrical Wiring | John Miller | Blocked | Medium | 2024-12-24 | 2025-01-18 |  | 0 | Cement | Plot 21, Riverside | 12835.35 | 15078.85 | Not started
C004 | Warehouse D | T298 | Foundation Excavation | Emma White | Not Started | High | 2024-02-14 | 2024-03-12 |  | 0 | Rebar | Industrial Park | 46606.62 | 0 | Not started
C004 | Warehouse D | T496 | Roofing | Emma White | In Progress | High | 2024-12-15 | 2024-12-27 |  | 22 | Copper Wires | Industrial Park | 45336.99 | 41945.12 | In progress
C004 | Warehouse D | T793 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-11-21 | 2024-12-05 |  | 0 | Concrete | Industrial Park | 32562.04 | 26217.15 | Not started
C004 | Warehouse D | T397 | Roofing | Rachel Green | In Progress | High | 2024-06-24 | 2024-07-21 |  | 92 | Paint | Industrial Park | 5339.14 | 6057.81 | In progress
C003 | Office Tower C | T229 | Concrete Pouring | Carlos Rivera | Blocked | High | 2024-12-08 | 2024-12-19 |  | 0 | Paint | Downtown Avenue | 9795.25 | 9515.73 | Not started
C002 | Shopping Complex B | T284 | Site Survey | Mike Adams | Completed | High | 2024-10-01 | 2024-10-16 | 2024-10-16 | 100 | Concrete | Market Street | 49862.03 | 55772.29 | No issues
C002 | Shopping Complex B | T922 | Concrete Pouring | Grace Allen | Not Started | High | 2024-01-02 | 2024-01-20 |  | 0 | Copper Wires | Market Street | 12615.76 | 0 | Not started
C003 | Office Tower C | T785 | Plumbing Installations | Grace Allen | Blocked | Medium | 2023-11-08 | 2023-11-28 |  | 0 | Roofing Sheets | Downtown Avenue | 32093.58 | 29242.9 | Not started
C001 | Residential Building A | T305 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-07-06 | 2023-07-23 |  | 21 | Steel Beams | Plot 21, Riverside | 40603.59 | 34557.7 | In progress
C003 | Office Tower C | T509 | Site Survey | Grace Allen | In Progress | Low | 2024-09-22 | 2024-10-11 |  | 25 | Rebar | Downtown Avenue | 40823.85 | 26543.09 | In progress
C001 | Residential Building A | T248 | Site Survey | Rachel Green | In Progress | Medium | 2024-04-15 | 2024-05-09 |  | 82 | Rebar | Plot 21, Riverside | 11115.65 | 11926.9 | In progress
C004 | Warehouse D | T913 | Roofing | John Miller | Completed | Low | 2023-01-03 | 2023-02-01 | 2023-02-01 | 100 | Steel Beams | Industrial Park | 37284.22 | 23026.25 | No issues
C003 | Office Tower C | T968 | Plumbing Installations | Mike Adams | Completed | High | 2023-04-07 | 2023-05-02 | 2023-05-02 | 100 | Concrete | Downtown Avenue | 30439.8 | 20194.23 | No issues
C004 | Warehouse D | T952 | Interior Painting | Mike Adams | Not Started | High | 2023-10-21 | 2023-11-17 |  | 0 | Steel Beams | Industrial Park | 47720.85 | 0 | Not started
C002 | Shopping Complex B | T359 | Site Survey | John Miller | Not Started | Low | 2024-07-13 | 2024-07-25 |  | 0 | Copper Wires | Market Street | 46518.57 | 0 | Not started
C004 | Warehouse D | T494 | Plumbing Installations | Carlos Rivera | In Progress | High | 2024-01-24 | 2024-02-05 |  | 42 | PVC Pipes | Industrial Park | 15331.57 | 9541.73 | In progress
C004 | Warehouse D | T162 | Site Survey | Mike Adams | Completed | Medium | 2023-08-26 | 2023-09-14 | 2023-09-14 | 100 | Roofing Sheets | Industrial Park | 27323.86 | 27934.25 | No issues
C003 | Office Tower C | T797 | Concrete Pouring | John Miller | Blocked | Medium | 2023-12-08 | 2024-01-06 |  | 0 | Paint | Downtown Avenue | 18634.92 | 14990.15 | Not started
C001 | Residential Building A | T161 | Site Survey | Grace Allen | Blocked | Medium | 2024-02-27 | 2024-03-28 |  | 0 | Roofing Sheets | Plot 21, Riverside | 40823.85 | 44122.73 | Not started
C002 | Shopping Complex B | T882 | Interior Painting | Emma White | Blocked | High | 2023-06-07 | 2023-07-06 |  | 0 | Roofing Sheets | Market Street | 26941.59 | 56244.61 | Not started
C002 | Shopping Complex B | T411 | Plumbing Installations | Emma White | In Progress | Medium | 2024-02-24 | 2024-03-18 |  | 23 | PVC Pipes | Market Street | 27657.85 | 47841.07 | In progress
C002 | Shopping Complex B | T531 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-08-22 | 2023-09-06 | 2023-09-06 | 100 | Paint | Market Street | 32191.89 | 62741.32 | No issues
C002 | Shopping Complex B | T240 | Interior Painting | John Miller | In Progress | Low | 2024-12-01 | 2024-12-11 |  | 31 | Copper Wires | Market Street | 34813.62 | 56054.04 | In progress
C001 | Residential Building A | T363 | Concrete Pouring | Dave Brown | Completed | High | 2024-04-12 | 2024-05-08 | 2024-05-08 | 100 | Cement | Plot 21, Riverside | 34593.11 | 32017.89 | No issues
C004 | Warehouse D | T519 | Steel Framework Setup | Sarah Johnson | Completed | Low | 2023-06-05 | 2023-07-01 | 2023-07-01 | 100 | Rebar | Industrial Park | 20891.87 | 18332.18 | No issues
C003 | Office Tower C | T372 | Interior Painting | Mike Adams | Blocked | Medium | 2023-12-28 | 2024-01-14 |  | 0 | Paint | Downtown Avenue | 32944.88 | 21374.85 | Not started
C001 | Residential Building A | T332 | Electrical Wiring | Sarah Johnson | Completed | High | 2023-11-19 | 2023-12-01 | 2023-12-01 | 100 | Rebar | Plot 21, Riverside | 49636.47 | 53535.59 | No issues
C004 | Warehouse D | T286 | Site Survey | John Miller | Not Started | Medium | 2023-10-03 | 2023-10-30 |  | 0 | Copper Wires | Industrial Park | 39371.98 | 0 | Not started
C004 | Warehouse D | T783 | Electrical Wiring | Emma White | Not Started | Low | 2024-04-21 | 2024-05-18 |  | 0 | Copper Wires | Industrial Park | 39471.84 | 0 | Not started
C002 | Shopping Complex B | T258 | Site Survey | John Miller | In Progress | High | 2024-02-18 | 2024-03-12 |  | 97 | Paint | Market Street | 43116.83 | 75485.18 | In progress
C001 | Residential Building A | T148 | Foundation Excavation | Mike Adams | Blocked | High | 2023-12-27 | 2024-01-17 |  | 0 | PVC Pipes | Plot 21, Riverside | 43087.99 | 29013.61 | Not started
C004 | Warehouse D | T490 | Plumbing Installations | John Miller | In Progress | High | 2023-03-28 | 2023-04-26 |  | 47 | Rebar | Industrial Park | 21405.59 | 24263.25 | In progress
C004 | Warehouse D | T204 | Site Survey | Sarah Johnson | Completed | Low | 2024-08-18 | 2024-08-30 | 2024-08-30 | 100 | Copper Wires | Industrial Park | 8950.9 | 5432.33 | No issues
C003 | Office Tower C | T661 | Roofing | Sarah Johnson | Blocked | Medium | 2023-01-12 | 2023-01-23 |  | 0 | Concrete | Downtown Avenue | 37153.67 | 35740.08 | Not started
C003 | Office Tower C | T566 | Foundation Excavation | Carlos Rivera | Blocked | High | 2024-05-27 | 2024-06-04 |  | 0 | PVC Pipes | Downtown Avenue | 34599.6 | 40847.55 | Not started
C003 | Office Tower C | T862 | Concrete Pouring | Emma White | Not Started | Medium | 2024-01-20 | 2024-02-02 |  | 0 | Paint | Downtown Avenue | 43776.69 | 0 | Not started
C001 | Residential Building A | T971 | Plumbing Installations | Mike Adams | In Progress | High | 2024-11-27 | 2024-12-23 |  | 2 | Copper Wires | Plot 21, Riverside | 22682.13 | 19831.88 | In progress
C004 | Warehouse D | T116 | Roofing | Carlos Rivera | Completed | Low | 2024-08-07 | 2024-09-06 | 2024-09-06 | 100 | Roofing Sheets | Industrial Park | 49789.61 | 35009.07 | No issues
C004 | Warehouse D | T432 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2024-05-04 | 2024-05-14 |  | 14 | PVC Pipes | Industrial Park | 43394.31 | 31437.4 | In progress
C003 | Office Tower C | T890 | Electrical Wiring | Mike Adams | Completed | Medium | 2023-10-10 | 2023-10-22 | 2023-10-22 | 100 | Steel Beams | Downtown Avenue | 46314.16 | 28580.87 | No issues
C002 | Shopping Complex B | T737 | Concrete Pouring | Grace Allen | Not Started | High | 2023-11-07 | 2023-11-17 |  | 0 | Roofing Sheets | Market Street | 14329.02 | 0 | Not started
C004 | Warehouse D | T425 | Foundation Excavation | Rachel Green | Not Started | High | 2023-04-17 | 2023-05-04 |  | 0 | Copper Wires | Industrial Park | 15100.75 | 0 | Not started
C004 | Warehouse D | T144 | Steel Framework Setup | John Miller | Blocked | High | 2024-08-23 | 2024-09-19 |  | 0 | Copper Wires | Industrial Park | 45747.56 | 40220.72 | Not started
C003 | Office Tower C | T660 | Foundation Excavation | Rachel Green | Blocked | Medium | 2023-04-15 | 2023-05-09 |  | 0 | Concrete | Downtown Avenue | 43931.14 | 33487.47 | Not started
C003 | Office Tower C | T399 | Foundation Excavation | Dave Brown | Blocked | Low | 2023-03-17 | 2023-03-29 |  | 0 | Roofing Sheets | Downtown Avenue | 35222.27 | 33711.48 | Not started
C003 | Office Tower C | T696 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-11-04 | 2023-12-02 | 2023-12-02 | 100 | Roofing Sheets | Downtown Avenue | 16657.62 | 19416.92 | No issues
C004 | Warehouse D | T243 | Electrical Wiring | Dave Brown | Not Started | High | 2023-12-25 | 2024-01-06 |  | 0 | Concrete | Industrial Park | 33975.95 | 0 | Not started
C004 | Warehouse D | T470 | Concrete Pouring | Rachel Green | Completed | High | 2023-12-24 | 2024-01-17 | 2024-01-17 | 100 | Copper Wires | Industrial Park | 29745.12 | 26126.65 | No issues
C001 | Residential Building A | T618 | Foundation Excavation | John Miller | Not Started | Low | 2023-06-10 | 2023-07-04 |  | 0 | Cement | Plot 21, Riverside | 46912.58 | 0 | Not started
C001 | Residential Building A | T107 | Plumbing Installations | Mike Adams | Not Started | Low | 2023-04-23 | 2023-05-23 |  | 0 | Rebar | Plot 21, Riverside | 25870.58 | 0 | Not started
C001 | Residential Building A | T342 | Steel Framework Setup | Grace Allen | Not Started | Low | 2024-10-01 | 2024-10-22 |  | 0 | Copper Wires | Plot 21, Riverside | 25517.9 | 0 | Not started
C003 | Office Tower C | T971 | Electrical Wiring | Rachel Green | Blocked | High | 2023-12-23 | 2024-01-12 |  | 0 | Cement | Downtown Avenue | 33322.87 | 33638.85 | Not started
C003 | Office Tower C | T115 | Plumbing Installations | Sarah Johnson | In Progress | Medium | 2023-05-21 | 2023-06-03 |  | 62 | Paint | Downtown Avenue | 27231.48 | 30787.42 | In progress
C002 | Shopping Complex B | T548 | Site Survey | John Miller | Not Started | High | 2024-08-18 | 2024-09-16 |  | 0 | Paint | Market Street | 27218.88 | 0 | Not started
C003 | Office Tower C | T284 | Concrete Pouring | Emma White | Not Started | Low | 2024-10-25 | 2024-11-08 |  | 0 | Concrete | Downtown Avenue | 6780.59 | 0 | Not started
C004 | Warehouse D | T178 | Foundation Excavation | Carlos Rivera | Blocked | High | 2023-06-10 | 2023-07-01 |  | 0 | Roofing Sheets | Industrial Park | 16137.43 | 13428.75 | Not started
C002 | Shopping Complex B | T858 | Plumbing Installations | Sarah Johnson | In Progress | High | 2023-05-06 | 2023-05-24 |  | 19 | Cement | Market Street | 46807.7 | 71355.02 | In progress
C002 | Shopping Complex B | T270 | Concrete Pouring | Emma White | Completed | High | 2023-11-03 | 2023-11-15 | 2023-11-15 | 100 | Cement | Market Street | 40571.19 | 67532.6 | No issues
C001 | Residential Building A | T443 | Site Survey | Emma White | Blocked | High | 2023-02-08 | 2023-03-10 |  | 0 | Roofing Sheets | Plot 21, Riverside | 7319.12 | 8502.38 | Not started
C003 | Office Tower C | T491 | Foundation Excavation | Mike Adams | Completed | High | 2023-12-11 | 2024-01-02 | 2024-01-02 | 100 | Steel Beams | Downtown Avenue | 41836.95 | 45481.19 | No issues
C002 | Shopping Complex B | T281 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2023-12-20 | 2024-01-16 | 2024-01-16 | 100 | Roofing Sheets | Market Street | 24392.24 | 44253.12 | No issues
C004 | Warehouse D | T493 | Foundation Excavation | Mike Adams | Not Started | Medium | 2023-04-05 | 2023-05-04 |  | 0 | Rebar | Industrial Park | 19466.81 | 0 | Not started
C002 | Shopping Complex B | T401 | Concrete Pouring | Dave Brown | Not Started | Medium | 2024-05-11 | 2024-06-06 |  | 0 | Paint | Market Street | 15917.85 | 0 | Not started
C001 | Residential Building A | T955 | Plumbing Installations | Grace Allen | Completed | Low | 2024-11-20 | 2024-12-05 | 2024-12-05 | 100 | Roofing Sheets | Plot 21, Riverside | 21069.13 | 13919.2 | No issues
C003 | Office Tower C | T703 | Plumbing Installations | Carlos Rivera | Not Started | Medium | 2023-07-24 | 2023-08-17 |  | 0 | Cement | Downtown Avenue | 28310.02 | 0 | Not started
C003 | Office Tower C | T719 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-05-05 | 2023-05-28 |  | 0 | PVC Pipes | Downtown Avenue | 28803.91 | 0 | Not started
C003 | Office Tower C | T449 | Concrete Pouring | Dave Brown | Blocked | Medium | 2024-03-19 | 2024-04-02 |  | 0 | Roofing Sheets | Downtown Avenue | 25637.38 | 28413.04 | Not started
C003 | Office Tower C | T958 | Steel Framework Setup | John Miller | Blocked | High | 2024-04-01 | 2024-04-27 |  | 0 | Rebar | Downtown Avenue | 41834.66 | 45110.11 | Not started
C001 | Residential Building A | T869 | Roofing | Sarah Johnson | Not Started | Low | 2024-05-13 | 2024-05-26 |  | 0 | Steel Beams | Plot 21, Riverside | 5862.92 | 0 | Not started
C001 | Residential Building A | T481 | Electrical Wiring | Grace Allen | In Progress | High | 2023-04-19 | 2023-05-01 |  | 66 | Paint | Plot 21, Riverside | 11413.21 | 11742.51 | In progress
C003 | Office Tower C | T744 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2023-06-14 | 2023-06-26 |  | 0 | Steel Beams | Downtown Avenue | 24076.92 | 23019.37 | Not started
C002 | Shopping Complex B | T204 | Concrete Pouring | Rachel Green | Completed | Low | 2024-08-07 | 2024-08-22 | 2024-08-22 | 100 | Paint | Market Street | 27713.32 | 45500.59 | No issues
C001 | Residential Building A | T869 | Roofing | Dave Brown | In Progress | Medium | 2024-09-19 | 2024-09-26 |  | 38 | Cement | Plot 21, Riverside | 9714.9 | 9196.06 | In progress
C004 | Warehouse D | T248 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2023-09-19 | 2023-10-02 |  | 49 | PVC Pipes | Industrial Park | 5531.28 | 6502.65 | In progress
C001 | Residential Building A | T703 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2024-09-04 | 2024-10-03 |  | 0 | Rebar | Plot 21, Riverside | 6414.41 | 7562.84 | Not started
C003 | Office Tower C | T632 | Concrete Pouring | Dave Brown | Completed | Medium | 2023-02-27 | 2023-03-22 | 2023-03-22 | 100 | Copper Wires | Downtown Avenue | 17034.03 | 20258.76 | No issues
C001 | Residential Building A | T469 | Interior Painting | Rachel Green | In Progress | High | 2024-03-28 | 2024-04-18 |  | 90 | PVC Pipes | Plot 21, Riverside | 47044.58 | 47190.57 | In progress
C003 | Office Tower C | T418 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2024-05-19 | 2024-06-08 |  | 0 | PVC Pipes | Downtown Avenue | 40977.72 | 0 | Not started
C002 | Shopping Complex B | T474 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-03-19 | 2023-03-31 |  | 0 | Paint | Market Street | 43695.62 | 51859.52 | Not started
C001 | Residential Building A | T412 | Concrete Pouring | Dave Brown | In Progress | Low | 2023-10-04 | 2023-11-02 |  | 96 | Concrete | Plot 21, Riverside | 23604.81 | 15036.93 | In progress
C002 | Shopping Complex B | T385 | Interior Painting | Rachel Green | Completed | High | 2023-04-16 | 2023-05-13 | 2023-05-13 | 100 | PVC Pipes | Market Street | 27490.98 | 42959.95 | No issues
C001 | Residential Building A | T254 | Concrete Pouring | Mike Adams | Blocked | Medium | 2024-11-22 | 2024-12-22 |  | 0 | Paint | Plot 21, Riverside | 25810.87 | 20962.67 | Not started
C001 | Residential Building A | T658 | Site Survey | John Miller | Blocked | Low | 2023-07-10 | 2023-07-23 |  | 0 | Rebar | Plot 21, Riverside | 30340.86 | 25203.7 | Not started
C002 | Shopping Complex B | T704 | Interior Painting | Mike Adams | Not Started | Low | 2023-01-20 | 2023-02-03 |  | 0 | Steel Beams | Market Street | 14924.21 | 0 | Not started
C004 | Warehouse D | T640 | Electrical Wiring | Rachel Green | Blocked | Medium | 2024-10-21 | 2024-11-19 |  | 0 | Roofing Sheets | Industrial Park | 18076.66 | 21137.33 | Not started
C001 | Residential Building A | T713 | Concrete Pouring | John Miller | Blocked | Low | 2023-08-13 | 2023-08-30 |  | 0 | PVC Pipes | Plot 21, Riverside | 37010.21 | 41526.05 | Not started
C004 | Warehouse D | T724 | Concrete Pouring | Carlos Rivera | Completed | Low | 2024-09-02 | 2024-09-25 | 2024-09-25 | 100 | Steel Beams | Industrial Park | 33284.77 | 32786.29 | No issues
C004 | Warehouse D | T486 | Site Survey | Grace Allen | In Progress | Low | 2023-04-02 | 2023-04-18 |  | 53 | Cement | Industrial Park | 21216.46 | 15309.55 | In progress
C004 | Warehouse D | T953 | Roofing | Carlos Rivera | Not Started | Low | 2023-06-17 | 2023-06-30 |  | 0 | Cement | Industrial Park | 45783.54 | 0 | Not started
C004 | Warehouse D | T270 | Plumbing Installations | Carlos Rivera | Not Started | Medium | 2023-03-14 | 2023-04-10 |  | 0 | Roofing Sheets | Industrial Park | 14768.17 | 0 | Not started
C001 | Residential Building A | T306 | Concrete Pouring | Carlos Rivera | Completed | Low | 2024-10-18 | 2024-11-15 | 2024-11-15 | 100 | Rebar | Plot 21, Riverside | 5524.31 | 3884.95 | No issues
C001 | Residential Building A | T766 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-04-01 | 2024-04-21 |  | 74 | Concrete | Plot 21, Riverside | 39155.97 | 42478.09 | In progress
C003 | Office Tower C | T698 | Concrete Pouring | Dave Brown | In Progress | High | 2024-01-01 | 2024-01-13 |  | 60 | Concrete | Downtown Avenue | 44169.53 | 46090.57 | In progress
C002 | Shopping Complex B | T121 | Electrical Wiring | Rachel Green | In Progress | Low | 2023-04-07 | 2023-05-02 |  | 19 | Copper Wires | Market Street | 36182.36 | 60009.67 | In progress
C004 | Warehouse D | T878 | Roofing | Mike Adams | Completed | Low | 2023-04-24 | 2023-05-23 | 2023-05-23 | 100 | Copper Wires | Industrial Park | 11813.83 | 8662.06 | No issues
C004 | Warehouse D | T649 | Site Survey | Grace Allen | Completed | High | 2024-04-16 | 2024-05-03 | 2024-05-03 | 100 | Rebar | Industrial Park | 44332.12 | 30295.33 | No issues
C001 | Residential Building A | T403 | Steel Framework Setup | John Miller | Completed | Low | 2023-04-19 | 2023-05-06 | 2023-05-06 | 100 | Roofing Sheets | Plot 21, Riverside | 14796.94 | 16650.23 | No issues
C003 | Office Tower C | T681 | Foundation Excavation | Rachel Green | Completed | Medium | 2023-06-22 | 2023-07-02 | 2023-07-02 | 100 | Steel Beams | Downtown Avenue | 34570.42 | 31118.7 | No issues
C003 | Office Tower C | T572 | Site Survey | Dave Brown | Completed | High | 2023-05-15 | 2023-05-22 | 2023-05-22 | 100 | Steel Beams | Downtown Avenue | 11393.15 | 13469.59 | No issues
C002 | Shopping Complex B | T182 | Site Survey | Sarah Johnson | Not Started | Low | 2024-02-17 | 2024-02-25 |  | 0 | Paint | Market Street | 36993.54 | 0 | Not started
C001 | Residential Building A | T506 | Steel Framework Setup | Rachel Green | Not Started | High | 2023-02-11 | 2023-02-22 |  | 0 | Roofing Sheets | Plot 21, Riverside | 25645.89 | 0 | Not started
C001 | Residential Building A | T809 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2024-05-12 | 2024-05-30 |  | 24 | Concrete | Plot 21, Riverside | 11158.13 | 9954.17 | In progress
C003 | Office Tower C | T914 | Roofing | Rachel Green | Completed | High | 2023-09-24 | 2023-10-17 | 2023-10-17 | 100 | Concrete | Downtown Avenue | 31864.24 | 31519.18 | No issues
C003 | Office Tower C | T206 | Concrete Pouring | Carlos Rivera | Blocked | High | 2023-01-02 | 2023-02-01 |  | 0 | Cement | Downtown Avenue | 19610.24 | 20031.49 | Not started
C002 | Shopping Complex B | T518 | Site Survey | John Miller | Not Started | Low | 2023-05-10 | 2023-06-07 |  | 0 | Paint | Market Street | 45665.71 | 0 | Not started
C003 | Office Tower C | T615 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2024-09-14 | 2024-09-21 |  | 0 | PVC Pipes | Downtown Avenue | 45159.78 | 41783.95 | Not started
C004 | Warehouse D | T551 | Roofing | John Miller | Not Started | Low | 2024-01-27 | 2024-02-17 |  | 0 | Roofing Sheets | Industrial Park | 44701.88 | 0 | Not started
C003 | Office Tower C | T273 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2024-01-26 | 2024-02-16 |  | 24 | Steel Beams | Downtown Avenue | 11553.52 | 12862.92 | In progress
C003 | Office Tower C | T689 | Electrical Wiring | Mike Adams | Completed | Medium | 2024-06-01 | 2024-06-26 | 2024-06-26 | 100 | Copper Wires | Downtown Avenue | 45754.05 | 34907.35 | No issues
C004 | Warehouse D | T522 | Steel Framework Setup | John Miller | Not Started | Medium | 2023-06-23 | 2023-07-16 |  | 0 | Steel Beams | Industrial Park | 29154.01 | 0 | Not started
C001 | Residential Building A | T968 | Concrete Pouring | Grace Allen | Blocked | Low | 2023-08-12 | 2023-08-30 |  | 0 | Cement | Plot 21, Riverside | 49012.65 | 51247.93 | Not started
C002 | Shopping Complex B | T424 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2023-06-18 | 2023-06-28 |  | 89 | Copper Wires | Market Street | 17697.75 | 45085.17 | In progress
C002 | Shopping Complex B | T390 | Concrete Pouring | Emma White | In Progress | Low | 2023-05-23 | 2023-06-01 |  | 82 | PVC Pipes | Market Street | 44617.04 | 71877.25 | In progress
C003 | Office Tower C | T542 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2024-03-18 | 2024-03-29 |  | 0 | Steel Beams | Downtown Avenue | 29072.77 | 0 | Not started
C004 | Warehouse D | T493 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-05-10 | 2023-06-02 |  | 96 | Steel Beams | Industrial Park | 47704.31 | 31479.51 | In progress
C003 | Office Tower C | T728 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2024-09-02 | 2024-09-16 |  | 0 | Rebar | Downtown Avenue | 28959.54 | 31792.53 | Not started
C002 | Shopping Complex B | T403 | Site Survey | Dave Brown | In Progress | Low | 2024-05-21 | 2024-05-29 |  | 63 | Copper Wires | Market Street | 23820.02 | 48796.82 | In progress
C004 | Warehouse D | T990 | Steel Framework Setup | John Miller | Completed | High | 2024-01-12 | 2024-02-11 | 2024-02-11 | 100 | Steel Beams | Industrial Park | 18770.74 | 15228.7 | No issues
C003 | Office Tower C | T455 | Foundation Excavation | Dave Brown | In Progress | Low | 2023-05-08 | 2023-06-01 |  | 95 | Steel Beams | Downtown Avenue | 46899.86 | 34614.89 | In progress
C004 | Warehouse D | T950 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2023-07-05 | 2023-08-02 |  | 0 | PVC Pipes | Industrial Park | 18378.37 | 0 | Not started
C004 | Warehouse D | T936 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2023-11-20 | 2023-12-13 |  | 0 | Rebar | Industrial Park | 32541.47 | 0 | Not started
C004 | Warehouse D | T651 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-07-26 | 2024-08-06 |  | 52 | Rebar | Industrial Park | 16576.39 | 11222.73 | In progress
C002 | Shopping Complex B | T190 | Steel Framework Setup | Dave Brown | Blocked | High | 2023-03-10 | 2023-03-21 |  | 0 | Concrete | Market Street | 15744.03 | 39671.8 | Not started
C001 | Residential Building A | T871 | Site Survey | Rachel Green | Not Started | Low | 2024-12-10 | 2024-12-21 |  | 0 | Concrete | Plot 21, Riverside | 11730.64 | 0 | Not started
C004 | Warehouse D | T928 | Site Survey | Emma White | Completed | Medium | 2024-01-08 | 2024-02-05 | 2024-02-05 | 100 | Rebar | Industrial Park | 27902.66 | 25498.43 | No issues
C003 | Office Tower C | T561 | Roofing | Emma White | In Progress | Low | 2024-02-19 | 2024-03-10 |  | 3 | Paint | Downtown Avenue | 11039 | 10736.73 | In progress
C003 | Office Tower C | T591 | Roofing | Dave Brown | Completed | Low | 2024-10-16 | 2024-10-31 | 2024-10-31 | 100 | Roofing Sheets | Downtown Avenue | 38713.66 | 38684.08 | No issues
C001 | Residential Building A | T393 | Interior Painting | Grace Allen | Completed | Low | 2023-09-11 | 2023-09-24 | 2023-09-24 | 100 | Cement | Plot 21, Riverside | 33862.59 | 39283.58 | No issues
C001 | Residential Building A | T540 | Concrete Pouring | John Miller | In Progress | Medium | 2023-03-05 | 2023-03-21 |  | 78 | Copper Wires | Plot 21, Riverside | 12006.79 | 12522.39 | In progress
C004 | Warehouse D | T470 | Plumbing Installations | Sarah Johnson | Completed | Low | 2023-07-22 | 2023-08-14 | 2023-08-14 | 100 | Concrete | Industrial Park | 33058.12 | 23422.32 | No issues
C004 | Warehouse D | T692 | Concrete Pouring | John Miller | Blocked | Low | 2024-10-26 | 2024-11-04 |  | 0 | Cement | Industrial Park | 42767.17 | 39599.92 | Not started
C004 | Warehouse D | T145 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2023-08-28 | 2023-09-10 |  | 0 | PVC Pipes | Industrial Park | 49912.13 | 0 | Not started
C002 | Shopping Complex B | T830 | Concrete Pouring | Rachel Green | In Progress | High | 2024-06-02 | 2024-06-27 |  | 53 | Copper Wires | Market Street | 8961.37 | 31926.21 | In progress
C004 | Warehouse D | T580 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2024-07-20 | 2024-08-04 |  | 0 | Roofing Sheets | Industrial Park | 18011.92 | 0 | Not started
C001 | Residential Building A | T810 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-10-22 | 2024-11-11 |  | 0 | Steel Beams | Plot 21, Riverside | 35831.74 | 23605.81 | Not started
C004 | Warehouse D | T121 | Site Survey | Grace Allen | Completed | Medium | 2024-10-22 | 2024-11-20 | 2024-11-20 | 100 | Roofing Sheets | Industrial Park | 43722.09 | 47078.52 | No issues
C001 | Residential Building A | T116 | Roofing | Emma White | In Progress | High | 2023-03-09 | 2023-04-04 |  | 54 | Steel Beams | Plot 21, Riverside | 36066.58 | 40299.39 | In progress
C003 | Office Tower C | T877 | Site Survey | Emma White | Not Started | Low | 2023-06-14 | 2023-06-22 |  | 0 | Roofing Sheets | Downtown Avenue | 19213.69 | 0 | Not started
C001 | Residential Building A | T806 | Foundation Excavation | Carlos Rivera | Blocked | Low | 2023-10-20 | 2023-10-29 |  | 0 | Paint | Plot 21, Riverside | 7947.87 | 6771.14 | Not started
C003 | Office Tower C | T899 | Electrical Wiring | Grace Allen | In Progress | Low | 2024-10-07 | 2024-10-16 |  | 77 | Concrete | Downtown Avenue | 28825.35 | 24905.89 | In progress
C003 | Office Tower C | T326 | Concrete Pouring | Emma White | Completed | Low | 2024-08-28 | 2024-09-13 | 2024-09-13 | 100 | Rebar | Downtown Avenue | 35987.08 | 42584.57 | No issues
C001 | Residential Building A | T871 | Roofing | Emma White | Blocked | High | 2023-06-28 | 2023-07-16 |  | 0 | Concrete | Plot 21, Riverside | 44804.45 | 52103.21 | Not started
C001 | Residential Building A | T426 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-08-01 | 2024-08-23 |  | 0 | Cement | Plot 21, Riverside | 11465.21 | 7082.81 | Not started
C001 | Residential Building A | T736 | Steel Framework Setup | John Miller | In Progress | Low | 2024-06-11 | 2024-07-05 |  | 65 | Steel Beams | Plot 21, Riverside | 44246.44 | 38025.75 | In progress
C001 | Residential Building A | T592 | Steel Framework Setup | John Miller | Not Started | Medium | 2023-02-18 | 2023-03-01 |  | 0 | Cement | Plot 21, Riverside | 25791.37 | 0 | Not started
C001 | Residential Building A | T633 | Plumbing Installations | Mike Adams | Blocked | High | 2024-12-17 | 2024-12-24 |  | 0 | Steel Beams | Plot 21, Riverside | 33418.33 | 38873.94 | Not started
C004 | Warehouse D | T890 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2023-06-17 | 2023-07-11 |  | 0 | Concrete | Industrial Park | 18650.53 | 16022.65 | Not started
C001 | Residential Building A | T470 | Electrical Wiring | Grace Allen | Blocked | Medium | 2023-10-15 | 2023-11-04 |  | 0 | Steel Beams | Plot 21, Riverside | 12389.17 | 12387.83 | Not started
C002 | Shopping Complex B | T538 | Plumbing Installations | Carlos Rivera | Blocked | High | 2023-04-28 | 2023-05-12 |  | 0 | Roofing Sheets | Market Street | 34555.6 | 63353.95 | Not started
C001 | Residential Building A | T247 | Interior Painting | Sarah Johnson | Not Started | Low | 2024-03-13 | 2024-04-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 12450.44 | 0 | Not started
C003 | Office Tower C | T621 | Roofing | Dave Brown | Not Started | Medium | 2023-04-08 | 2023-04-15 |  | 0 | Concrete | Downtown Avenue | 47757.82 | 0 | Not started
C001 | Residential Building A | T386 | Concrete Pouring | Rachel Green | In Progress | High | 2023-01-28 | 2023-02-27 |  | 53 | PVC Pipes | Plot 21, Riverside | 33884.66 | 40364.38 | In progress
C003 | Office Tower C | T404 | Plumbing Installations | Rachel Green | In Progress | Medium | 2024-01-09 | 2024-02-02 |  | 4 | PVC Pipes | Downtown Avenue | 43015.74 | 27622.26 | In progress
C004 | Warehouse D | T305 | Site Survey | Emma White | Not Started | Medium | 2024-02-10 | 2024-03-08 |  | 0 | Cement | Industrial Park | 31988.64 | 0 | Not started
C002 | Shopping Complex B | T498 | Plumbing Installations | Emma White | Completed | Low | 2023-03-03 | 2023-03-30 | 2023-03-30 | 100 | Rebar | Market Street | 27733.5 | 56558.99 | No issues
C004 | Warehouse D | T495 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-12-14 | 2024-12-28 |  | 0 | Copper Wires | Industrial Park | 28734.87 | 30068.81 | Not started
C003 | Office Tower C | T680 | Site Survey | Grace Allen | Blocked | Low | 2023-08-13 | 2023-08-30 |  | 0 | Cement | Downtown Avenue | 11478.34 | 7996.48 | Not started
C002 | Shopping Complex B | T797 | Steel Framework Setup | Dave Brown | Completed | Medium | 2024-04-08 | 2024-04-29 | 2024-04-29 | 100 | Rebar | Market Street | 18512.76 | 38280.88 | No issues
C001 | Residential Building A | T323 | Site Survey | Grace Allen | In Progress | High | 2023-11-28 | 2023-12-10 |  | 76 | Paint | Plot 21, Riverside | 14580.08 | 9067.6 | In progress
C004 | Warehouse D | T322 | Electrical Wiring | Dave Brown | Completed | Medium | 2023-09-19 | 2023-10-12 | 2023-10-12 | 100 | Cement | Industrial Park | 47858.17 | 35961.53 | No issues
C001 | Residential Building A | T313 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-01-18 | 2023-02-15 |  | 0 | PVC Pipes | Plot 21, Riverside | 46468.89 | 0 | Not started
C003 | Office Tower C | T642 | Interior Painting | Rachel Green | Completed | High | 2023-01-11 | 2023-02-04 | 2023-02-04 | 100 | Concrete | Downtown Avenue | 49370.97 | 46414.71 | No issues
C004 | Warehouse D | T755 | Concrete Pouring | Sarah Johnson | In Progress | High | 2023-08-22 | 2023-09-08 |  | 76 | Paint | Industrial Park | 8569.45 | 7071.53 | In progress
C002 | Shopping Complex B | T362 | Interior Painting | Sarah Johnson | Completed | Medium | 2023-10-18 | 2023-11-04 | 2023-11-04 | 100 | Concrete | Market Street | 45646.14 | 75607.76 | No issues
C004 | Warehouse D | T557 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2024-04-14 | 2024-05-11 |  | 84 | Steel Beams | Industrial Park | 32312.83 | 23289.71 | In progress
C001 | Residential Building A | T831 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-01-21 | 2024-02-14 |  | 0 | Paint | Plot 21, Riverside | 29520.34 | 23320.26 | Not started
C003 | Office Tower C | T855 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-10-01 | 2023-10-31 |  | 0 | PVC Pipes | Downtown Avenue | 23831.33 | 0 | Not started
C001 | Residential Building A | T430 | Plumbing Installations | Emma White | Blocked | High | 2023-12-15 | 2023-12-30 |  | 0 | Paint | Plot 21, Riverside | 38229.61 | 38570.77 | Not started
C002 | Shopping Complex B | T993 | Roofing | Sarah Johnson | Completed | High | 2024-03-28 | 2024-04-27 | 2024-04-27 | 100 | Copper Wires | Market Street | 45357.16 | 58642.76 | No issues
C004 | Warehouse D | T619 | Electrical Wiring | Mike Adams | Completed | Low | 2023-03-28 | 2023-04-12 | 2023-04-12 | 100 | Steel Beams | Industrial Park | 34749.74 | 27666.1 | No issues
C002 | Shopping Complex B | T861 | Plumbing Installations | Dave Brown | Completed | Low | 2024-11-10 | 2024-12-05 | 2024-12-05 | 100 | Concrete | Market Street | 38143.25 | 65906.55 | No issues
C001 | Residential Building A | T392 | Electrical Wiring | Emma White | Not Started | Medium | 2023-04-28 | 2023-05-09 |  | 0 | Steel Beams | Plot 21, Riverside | 15032.13 | 0 | Not started
C001 | Residential Building A | T843 | Foundation Excavation | Sarah Johnson | Completed | Low | 2024-05-09 | 2024-05-26 | 2024-05-26 | 100 | Roofing Sheets | Plot 21, Riverside | 9590.72 | 9593.15 | No issues
C003 | Office Tower C | T161 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-09-09 | 2023-09-24 |  | 0 | Roofing Sheets | Downtown Avenue | 45887.19 | 29943.11 | Not started
C003 | Office Tower C | T689 | Site Survey | John Miller | In Progress | Low | 2023-07-10 | 2023-07-17 |  | 47 | PVC Pipes | Downtown Avenue | 7178.57 | 5386.03 | In progress
C003 | Office Tower C | T688 | Steel Framework Setup | Mike Adams | Blocked | High | 2023-11-03 | 2023-11-14 |  | 0 | Cement | Downtown Avenue | 11107.2 | 9659.5 | Not started
C004 | Warehouse D | T898 | Foundation Excavation | Mike Adams | Not Started | High | 2023-12-05 | 2023-12-14 |  | 0 | Copper Wires | Industrial Park | 36631.64 | 0 | Not started
C001 | Residential Building A | T144 | Foundation Excavation | Dave Brown | Not Started | Low | 2023-03-02 | 2023-03-29 |  | 0 | Copper Wires | Plot 21, Riverside | 42870.37 | 0 | Not started
C002 | Shopping Complex B | T430 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2024-06-21 | 2024-07-19 |  | 82 | Roofing Sheets | Market Street | 17104.13 | 41197.62 | In progress
C002 | Shopping Complex B | T436 | Electrical Wiring | John Miller | In Progress | High | 2024-12-05 | 2024-12-19 |  | 15 | Cement | Market Street | 5949.59 | 30959.58 | In progress
C004 | Warehouse D | T668 | Foundation Excavation | Emma White | In Progress | Medium | 2023-09-25 | 2023-10-06 |  | 11 | Cement | Industrial Park | 21482.41 | 13186.61 | In progress
C002 | Shopping Complex B | T444 | Foundation Excavation | Rachel Green | Blocked | Medium | 2024-06-19 | 2024-07-17 |  | 0 | Cement | Market Street | 11689.64 | 39357.89 | Not started
C004 | Warehouse D | T578 | Concrete Pouring | John Miller | Not Started | High | 2024-12-21 | 2025-01-11 |  | 0 | Rebar | Industrial Park | 12390.73 | 0 | Not started
C004 | Warehouse D | T371 | Steel Framework Setup | Rachel Green | Completed | Medium | 2024-04-16 | 2024-05-15 | 2024-05-15 | 100 | Steel Beams | Industrial Park | 32429.19 | 25849.29 | No issues
C003 | Office Tower C | T766 | Electrical Wiring | Emma White | In Progress | High | 2023-10-27 | 2023-11-13 |  | 21 | PVC Pipes | Downtown Avenue | 12996.62 | 10450.95 | In progress
C002 | Shopping Complex B | T492 | Foundation Excavation | John Miller | In Progress | Medium | 2024-09-02 | 2024-09-23 |  | 23 | Cement | Market Street | 7610.11 | 34432.84 | In progress
C004 | Warehouse D | T633 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2024-07-20 | 2024-07-30 |  | 0 | Rebar | Industrial Park | 10329.89 | 0 | Not started
C001 | Residential Building A | T815 | Interior Painting | Emma White | Completed | Low | 2024-01-16 | 2024-02-14 | 2024-02-14 | 100 | Roofing Sheets | Plot 21, Riverside | 5161.22 | 5677.7 | No issues
C003 | Office Tower C | T863 | Site Survey | Grace Allen | In Progress | High | 2023-06-06 | 2023-06-19 |  | 83 | Concrete | Downtown Avenue | 9024.36 | 8304.83 | In progress
C002 | Shopping Complex B | T769 | Interior Painting | John Miller | Not Started | Medium | 2024-07-10 | 2024-08-01 |  | 0 | Concrete | Market Street | 6224.1 | 0 | Not started
C004 | Warehouse D | T752 | Plumbing Installations | Emma White | Blocked | Medium | 2024-01-09 | 2024-01-27 |  | 0 | Cement | Industrial Park | 14384.38 | 16559.74 | Not started
C003 | Office Tower C | T321 | Plumbing Installations | Emma White | In Progress | Medium | 2023-07-01 | 2023-07-14 |  | 25 | Paint | Downtown Avenue | 32452.36 | 27011.93 | In progress
C003 | Office Tower C | T498 | Roofing | Dave Brown | Completed | Low | 2024-01-19 | 2024-02-08 | 2024-02-08 | 100 | Paint | Downtown Avenue | 37143.31 | 24629.35 | No issues
C003 | Office Tower C | T845 | Concrete Pouring | John Miller | In Progress | High | 2024-03-16 | 2024-04-11 |  | 87 | Paint | Downtown Avenue | 15637.06 | 17861.39 | In progress
C002 | Shopping Complex B | T470 | Concrete Pouring | Grace Allen | Completed | Low | 2023-09-11 | 2023-10-03 | 2023-10-03 | 100 | Cement | Market Street | 11543.52 | 33391.28 | No issues
C002 | Shopping Complex B | T225 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-02-10 | 2023-02-20 |  | 65 | Rebar | Market Street | 12554.03 | 35846.14 | In progress
C001 | Residential Building A | T682 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2024-12-25 | 2025-01-01 |  | 0 | Paint | Plot 21, Riverside | 30379.45 | 0 | Not started
C003 | Office Tower C | T785 | Site Survey | Emma White | In Progress | High | 2023-02-09 | 2023-03-08 |  | 88 | Concrete | Downtown Avenue | 15185.5 | 10417.12 | In progress
C002 | Shopping Complex B | T222 | Roofing | Dave Brown | Not Started | High | 2024-03-08 | 2024-04-01 |  | 0 | Steel Beams | Market Street | 40136.31 | 0 | Not started
C004 | Warehouse D | T417 | Site Survey | Rachel Green | Not Started | Low | 2024-04-24 | 2024-05-01 |  | 0 | Steel Beams | Industrial Park | 42137.44 | 0 | Not started
C003 | Office Tower C | T211 | Concrete Pouring | Mike Adams | Completed | Medium | 2023-09-02 | 2023-09-23 | 2023-09-23 | 100 | Copper Wires | Downtown Avenue | 33191.78 | 36225.95 | No issues
C003 | Office Tower C | T536 | Concrete Pouring | Dave Brown | In Progress | Medium | 2024-10-15 | 2024-10-31 |  | 46 | PVC Pipes | Downtown Avenue | 37828.41 | 25195.94 | In progress
C001 | Residential Building A | T408 | Site Survey | Dave Brown | Blocked | Medium | 2024-08-06 | 2024-08-19 |  | 0 | Cement | Plot 21, Riverside | 36111.22 | 25627.46 | Not started
C001 | Residential Building A | T986 | Site Survey | Mike Adams | In Progress | Medium | 2024-07-19 | 2024-08-06 |  | 55 | Concrete | Plot 21, Riverside | 40349.08 | 33098.46 | In progress
C004 | Warehouse D | T342 | Concrete Pouring | Rachel Green | In Progress | High | 2024-04-25 | 2024-05-04 |  | 99 | Concrete | Industrial Park | 18284.49 | 12397.69 | In progress
C003 | Office Tower C | T590 | Steel Framework Setup | Emma White | In Progress | High | 2023-12-20 | 2024-01-01 |  | 94 | Concrete | Downtown Avenue | 45680.05 | 43425.7 | In progress
C002 | Shopping Complex B | T723 | Steel Framework Setup | Emma White | Blocked | Low | 2024-11-13 | 2024-12-10 |  | 0 | Cement | Market Street | 46414.15 | 60420.36 | Not started
C001 | Residential Building A | T123 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2024-12-18 | 2025-01-12 |  | 59 | Rebar | Plot 21, Riverside | 18267.82 | 14688.52 | In progress
C001 | Residential Building A | T562 | Roofing | Mike Adams | Blocked | Medium | 2023-08-13 | 2023-09-09 |  | 0 | Copper Wires | Plot 21, Riverside | 31050.36 | 34723.85 | Not started
C002 | Shopping Complex B | T235 | Electrical Wiring | Mike Adams | In Progress | Medium | 2023-01-27 | 2023-02-15 |  | 80 | Steel Beams | Market Street | 25828.62 | 44765.78 | In progress
C001 | Residential Building A | T768 | Plumbing Installations | Dave Brown | Not Started | High | 2024-07-20 | 2024-08-06 |  | 0 | Cement | Plot 21, Riverside | 6027.83 | 0 | Not started
C002 | Shopping Complex B | T299 | Foundation Excavation | Dave Brown | Blocked | Low | 2024-11-27 | 2024-12-21 |  | 0 | Roofing Sheets | Market Street | 30554.64 | 61162.3 | Not started
C004 | Warehouse D | T981 | Foundation Excavation | Sarah Johnson | Completed | High | 2024-03-28 | 2024-04-18 | 2024-04-18 | 100 | Steel Beams | Industrial Park | 28442.06 | 17988.81 | No issues
C002 | Shopping Complex B | T100 | Concrete Pouring | Rachel Green | Blocked | Medium | 2023-01-07 | 2023-01-21 |  | 0 | Copper Wires | Market Street | 37173.81 | 56127.73 | Not started
C003 | Office Tower C | T529 | Steel Framework Setup | Carlos Rivera | Not Started | High | 2023-07-24 | 2023-08-11 |  | 0 | Concrete | Downtown Avenue | 47179 | 0 | Not started
C001 | Residential Building A | T183 | Roofing | John Miller | Blocked | High | 2023-04-09 | 2023-05-06 |  | 0 | Cement | Plot 21, Riverside | 18038.87 | 16970.98 | Not started
C001 | Residential Building A | T846 | Concrete Pouring | Grace Allen | Blocked | Low | 2024-06-27 | 2024-07-21 |  | 0 | Paint | Plot 21, Riverside | 19033.6 | 17006.44 | Not started
C001 | Residential Building A | T819 | Foundation Excavation | Rachel Green | In Progress | High | 2024-11-06 | 2024-12-05 |  | 74 | Roofing Sheets | Plot 21, Riverside | 5954.37 | 4863.13 | In progress
C002 | Shopping Complex B | T149 | Interior Painting | Mike Adams | Blocked | Medium | 2024-11-26 | 2024-12-18 |  | 0 | Roofing Sheets | Market Street | 32188.35 | 47487.06 | Not started
C002 | Shopping Complex B | T156 | Plumbing Installations | John Miller | Completed | Medium | 2023-01-25 | 2023-02-19 | 2023-02-19 | 100 | Roofing Sheets | Market Street | 6004.43 | 30851.19 | No issues
C003 | Office Tower C | T170 | Concrete Pouring | John Miller | Completed | Low | 2023-02-03 | 2023-02-16 | 2023-02-16 | 100 | Copper Wires | Downtown Avenue | 36996.17 | 26263.86 | No issues
C002 | Shopping Complex B | T514 | Steel Framework Setup | Dave Brown | Blocked | High | 2023-12-14 | 2023-12-27 |  | 0 | Steel Beams | Market Street | 15176.8 | 36583.17 | Not started
C001 | Residential Building A | T685 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2023-11-15 | 2023-12-14 |  | 0 | Roofing Sheets | Plot 21, Riverside | 34200.05 | 39642.26 | Not started
C002 | Shopping Complex B | T357 | Site Survey | John Miller | Not Started | Medium | 2024-05-14 | 2024-06-01 |  | 0 | Paint | Market Street | 39159.73 | 0 | Not started
C001 | Residential Building A | T274 | Interior Painting | Carlos Rivera | In Progress | Medium | 2023-05-23 | 2023-05-31 |  | 64 | Paint | Plot 21, Riverside | 14002.44 | 11718.06 | In progress
C002 | Shopping Complex B | T996 | Interior Painting | John Miller | Blocked | Low | 2024-11-21 | 2024-12-07 |  | 0 | Concrete | Market Street | 25209.13 | 48948.8 | Not started
C003 | Office Tower C | T357 | Steel Framework Setup | John Miller | Completed | Medium | 2023-04-28 | 2023-05-24 | 2023-05-24 | 100 | Concrete | Downtown Avenue | 42574.35 | 25616.54 | No issues
C002 | Shopping Complex B | T137 | Electrical Wiring | Grace Allen | In Progress | Medium | 2024-05-26 | 2024-06-06 |  | 50 | Cement | Market Street | 32920.29 | 56619.91 | In progress
C002 | Shopping Complex B | T569 | Plumbing Installations | John Miller | Completed | High | 2024-04-28 | 2024-05-14 | 2024-05-14 | 100 | Roofing Sheets | Market Street | 47122.8 | 77224.02 | No issues
C003 | Office Tower C | T661 | Electrical Wiring | Dave Brown | Not Started | Medium | 2024-05-15 | 2024-06-09 |  | 0 | Rebar | Downtown Avenue | 43856.56 | 0 | Not started
C003 | Office Tower C | T863 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2023-05-06 | 2023-06-03 |  | 12 | Roofing Sheets | Downtown Avenue | 6760.87 | 6571.2 | In progress
C004 | Warehouse D | T454 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2023-11-09 | 2023-11-27 |  | 90 | Copper Wires | Industrial Park | 5245.86 | 5330.12 | In progress
C001 | Residential Building A | T829 | Site Survey | Sarah Johnson | Completed | Medium | 2023-01-10 | 2023-01-27 | 2023-01-27 | 100 | Steel Beams | Plot 21, Riverside | 44115.33 | 33834.78 | No issues
C003 | Office Tower C | T108 | Electrical Wiring | Dave Brown | In Progress | Medium | 2023-02-13 | 2023-03-14 |  | 43 | Roofing Sheets | Downtown Avenue | 28570.26 | 24473.62 | In progress
C001 | Residential Building A | T944 | Foundation Excavation | Emma White | Not Started | High | 2023-10-11 | 2023-11-07 |  | 0 | Steel Beams | Plot 21, Riverside | 39287.11 | 0 | Not started
C002 | Shopping Complex B | T609 | Roofing | Emma White | Completed | High | 2024-02-22 | 2024-03-12 | 2024-03-12 | 100 | Concrete | Market Street | 42647.67 | 55659.09 | No issues
C003 | Office Tower C | T620 | Plumbing Installations | Mike Adams | In Progress | Medium | 2023-06-23 | 2023-07-17 |  | 96 | Roofing Sheets | Downtown Avenue | 9964.12 | 7604.6 | In progress
C004 | Warehouse D | T665 | Concrete Pouring | Mike Adams | In Progress | Low | 2024-12-28 | 2025-01-12 |  | 73 | Rebar | Industrial Park | 23059.01 | 27104.9 | In progress
C002 | Shopping Complex B | T736 | Interior Painting | Rachel Green | Completed | High | 2023-05-05 | 2023-05-27 | 2023-05-27 | 100 | Rebar | Market Street | 38018.67 | 66842.14 | No issues
C004 | Warehouse D | T703 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-07-27 | 2023-08-23 |  | 0 | PVC Pipes | Industrial Park | 42782.84 | 0 | Not started
C003 | Office Tower C | T874 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-07-09 | 2023-08-07 |  | 0 | Roofing Sheets | Downtown Avenue | 43171.37 | 0 | Not started
C003 | Office Tower C | T456 | Electrical Wiring | John Miller | Not Started | High | 2024-05-08 | 2024-05-19 |  | 0 | Paint | Downtown Avenue | 20821.8 | 0 | Not started
C004 | Warehouse D | T861 | Foundation Excavation | Dave Brown | Blocked | Medium | 2023-07-19 | 2023-08-16 |  | 0 | Roofing Sheets | Industrial Park | 26678.02 | 18368.76 | Not started
C004 | Warehouse D | T785 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-03-04 | 2024-03-15 |  | 0 | Rebar | Industrial Park | 15718.45 | 0 | Not started
C002 | Shopping Complex B | T449 | Electrical Wiring | Rachel Green | In Progress | Medium | 2024-01-16 | 2024-02-14 |  | 38 | Copper Wires | Market Street | 36471.37 | 63358.68 | In progress
C003 | Office Tower C | T261 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-09-09 | 2023-10-02 |  | 60 | PVC Pipes | Downtown Avenue | 12396.18 | 9692.57 | In progress
C003 | Office Tower C | T751 | Concrete Pouring | Emma White | Blocked | Low | 2023-04-14 | 2023-05-06 |  | 0 | Paint | Downtown Avenue | 12590.96 | 10035.35 | Not started
C003 | Office Tower C | T748 | Roofing | Rachel Green | Completed | Low | 2024-06-09 | 2024-07-01 | 2024-07-01 | 100 | Rebar | Downtown Avenue | 48983.66 | 50410.48 | No issues
C003 | Office Tower C | T349 | Concrete Pouring | John Miller | Blocked | High | 2024-07-21 | 2024-08-05 |  | 0 | Steel Beams | Downtown Avenue | 19297.4 | 21665.19 | Not started
C004 | Warehouse D | T144 | Foundation Excavation | Sarah Johnson | Not Started | High | 2023-01-03 | 2023-01-21 |  | 0 | Rebar | Industrial Park | 13320.84 | 0 | Not started
C002 | Shopping Complex B | T463 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-04-21 | 2024-05-04 |  | 0 | PVC Pipes | Market Street | 35936.64 | 0 | Not started
C001 | Residential Building A | T629 | Site Survey | Grace Allen | Not Started | High | 2023-02-19 | 2023-03-16 |  | 0 | Concrete | Plot 21, Riverside | 43629.5 | 0 | Not started
C001 | Residential Building A | T942 | Concrete Pouring | John Miller | In Progress | Low | 2024-08-17 | 2024-09-10 |  | 31 | PVC Pipes | Plot 21, Riverside | 46027.83 | 50592.82 | In progress
C003 | Office Tower C | T151 | Concrete Pouring | Grace Allen | Completed | High | 2023-01-20 | 2023-01-29 | 2023-01-29 | 100 | Paint | Downtown Avenue | 7648.69 | 4934.01 | No issues
C003 | Office Tower C | T364 | Foundation Excavation | Grace Allen | Not Started | Medium | 2024-07-14 | 2024-08-08 |  | 0 | Paint | Downtown Avenue | 40006.4 | 0 | Not started
C001 | Residential Building A | T826 | Roofing | Rachel Green | Completed | High | 2024-05-04 | 2024-05-21 | 2024-05-21 | 100 | Paint | Plot 21, Riverside | 14453.93 | 15262.01 | No issues
C001 | Residential Building A | T337 | Plumbing Installations | Dave Brown | Blocked | Medium | 2024-06-01 | 2024-06-19 |  | 0 | Rebar | Plot 21, Riverside | 17959.12 | 12775.85 | Not started
C004 | Warehouse D | T747 | Plumbing Installations | Emma White | Completed | Medium | 2023-03-21 | 2023-04-02 | 2023-04-02 | 100 | Cement | Industrial Park | 39310.61 | 25184.58 | No issues
C001 | Residential Building A | T840 | Site Survey | Mike Adams | In Progress | Medium | 2024-02-14 | 2024-03-10 |  | 97 | Steel Beams | Plot 21, Riverside | 28517.25 | 29949.04 | In progress
C004 | Warehouse D | T603 | Electrical Wiring | Dave Brown | Completed | Medium | 2024-07-28 | 2024-08-15 | 2024-08-15 | 100 | Concrete | Industrial Park | 26025.49 | 18257.7 | No issues
C001 | Residential Building A | T545 | Foundation Excavation | Grace Allen | In Progress | High | 2024-07-12 | 2024-07-23 |  | 83 | Cement | Plot 21, Riverside | 18081.83 | 15027.26 | In progress
C002 | Shopping Complex B | T269 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2024-01-01 | 2024-01-31 |  | 14 | Rebar | Market Street | 14779.41 | 36403.9 | In progress
C002 | Shopping Complex B | T395 | Foundation Excavation | Rachel Green | In Progress | Medium | 2024-04-24 | 2024-05-14 |  | 1 | Rebar | Market Street | 28467.45 | 53879.76 | In progress
C001 | Residential Building A | T968 | Concrete Pouring | Mike Adams | In Progress | Medium | 2024-03-08 | 2024-03-15 |  | 90 | PVC Pipes | Plot 21, Riverside | 43227.05 | 37282.45 | In progress
C004 | Warehouse D | T611 | Concrete Pouring | Rachel Green | Blocked | Medium | 2023-10-09 | 2023-10-18 |  | 0 | Concrete | Industrial Park | 28691.89 | 18713.53 | Not started
C001 | Residential Building A | T996 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-12-23 | 2024-01-15 |  | 0 | Copper Wires | Plot 21, Riverside | 9672.92 | 7717.33 | Not started
C004 | Warehouse D | T405 | Plumbing Installations | Carlos Rivera | Not Started | High | 2024-09-17 | 2024-10-13 |  | 0 | Paint | Industrial Park | 5679.03 | 0 | Not started
C003 | Office Tower C | T534 | Site Survey | Dave Brown | Completed | Low | 2023-09-25 | 2023-10-22 | 2023-10-22 | 100 | Rebar | Downtown Avenue | 23382.29 | 28011.27 | No issues
C002 | Shopping Complex B | T178 | Electrical Wiring | Carlos Rivera | Not Started | High | 2024-01-27 | 2024-02-26 |  | 0 | Rebar | Market Street | 38301.47 | 0 | Not started
C002 | Shopping Complex B | T424 | Roofing | Grace Allen | In Progress | Low | 2023-02-09 | 2023-03-09 |  | 41 | Steel Beams | Market Street | 48233.28 | 60983.98 | In progress
C002 | Shopping Complex B | T481 | Steel Framework Setup | John Miller | Not Started | Low | 2023-04-03 | 2023-04-10 |  | 0 | Roofing Sheets | Market Street | 33569.03 | 0 | Not started
C003 | Office Tower C | T699 | Electrical Wiring | John Miller | Blocked | Medium | 2024-07-13 | 2024-08-03 |  | 0 | Concrete | Downtown Avenue | 35813.46 | 42631.89 | Not started
C001 | Residential Building A | T592 | Site Survey | Emma White | Blocked | Low | 2023-05-12 | 2023-06-07 |  | 0 | Concrete | Plot 21, Riverside | 10921.35 | 9203.08 | Not started
C004 | Warehouse D | T268 | Electrical Wiring | Mike Adams | Not Started | High | 2024-04-27 | 2024-05-21 |  | 0 | PVC Pipes | Industrial Park | 22429.64 | 0 | Not started
C002 | Shopping Complex B | T986 | Roofing | Mike Adams | Not Started | Medium | 2024-06-03 | 2024-06-11 |  | 0 | Rebar | Market Street | 41293.21 | 0 | Not started
C004 | Warehouse D | T604 | Electrical Wiring | Mike Adams | Completed | High | 2024-09-18 | 2024-10-09 | 2024-10-09 | 100 | Paint | Industrial Park | 40490.66 | 34254.21 | No issues
C004 | Warehouse D | T896 | Concrete Pouring | Mike Adams | Completed | High | 2024-11-14 | 2024-12-11 | 2024-12-11 | 100 | Concrete | Industrial Park | 25151.13 | 25064.29 | No issues
C004 | Warehouse D | T650 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2024-10-21 | 2024-10-28 |  | 0 | PVC Pipes | Industrial Park | 38380.79 | 32699.43 | Not started
C001 | Residential Building A | T649 | Interior Painting | John Miller | Completed | Low | 2024-12-27 | 2025-01-19 | 2025-01-19 | 100 | Rebar | Plot 21, Riverside | 38964.53 | 45128.57 | No issues
C004 | Warehouse D | T156 | Foundation Excavation | Dave Brown | In Progress | High | 2023-08-28 | 2023-09-18 |  | 66 | Paint | Industrial Park | 17455.02 | 16000.28 | In progress
C004 | Warehouse D | T440 | Concrete Pouring | Rachel Green | Blocked | High | 2023-08-04 | 2023-08-15 |  | 0 | Concrete | Industrial Park | 43995.65 | 52143.42 | Not started
C002 | Shopping Complex B | T393 | Plumbing Installations | Rachel Green | Completed | High | 2024-11-25 | 2024-12-14 | 2024-12-14 | 100 | PVC Pipes | Market Street | 33483.29 | 59516.46 | No issues
C003 | Office Tower C | T267 | Interior Painting | Mike Adams | In Progress | Low | 2023-07-19 | 2023-08-06 |  | 40 | Rebar | Downtown Avenue | 25049.14 | 27080.1 | In progress
C001 | Residential Building A | T748 | Foundation Excavation | Grace Allen | Blocked | High | 2024-02-04 | 2024-02-21 |  | 0 | Cement | Plot 21, Riverside | 7748.12 | 6229.45 | Not started
C001 | Residential Building A | T203 | Interior Painting | Mike Adams | Blocked | High | 2023-02-08 | 2023-02-27 |  | 0 | Paint | Plot 21, Riverside | 11554.34 | 9255.67 | Not started
C002 | Shopping Complex B | T998 | Site Survey | Dave Brown | Not Started | Low | 2023-12-03 | 2023-12-22 |  | 0 | Copper Wires | Market Street | 49514.24 | 0 | Not started
C003 | Office Tower C | T314 | Site Survey | Dave Brown | Blocked | Low | 2024-07-12 | 2024-07-20 |  | 0 | Roofing Sheets | Downtown Avenue | 43248.13 | 39916.89 | Not started
C001 | Residential Building A | T518 | Roofing | Sarah Johnson | Completed | Low | 2023-03-24 | 2023-04-06 | 2023-04-06 | 100 | PVC Pipes | Plot 21, Riverside | 42562.68 | 36495.93 | No issues
C003 | Office Tower C | T998 | Site Survey | Carlos Rivera | Not Started | Medium | 2023-04-07 | 2023-04-27 |  | 0 | Concrete | Downtown Avenue | 5119.99 | 0 | Not started
C004 | Warehouse D | T225 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2023-11-05 | 2023-11-15 |  | 62 | Concrete | Industrial Park | 23792.31 | 25216.99 | In progress
C004 | Warehouse D | T761 | Roofing | Carlos Rivera | Completed | Medium | 2024-05-20 | 2024-06-02 | 2024-06-02 | 100 | Cement | Industrial Park | 23691.48 | 24515.87 | No issues
C002 | Shopping Complex B | T334 | Concrete Pouring | Carlos Rivera | Blocked | High | 2023-03-19 | 2023-04-18 |  | 0 | Concrete | Market Street | 29348.35 | 50725.9 | Not started
C001 | Residential Building A | T622 | Site Survey | Emma White | Blocked | High | 2024-04-20 | 2024-05-05 |  | 0 | Cement | Plot 21, Riverside | 47010.45 | 29690.77 | Not started
C001 | Residential Building A | T985 | Interior Painting | Carlos Rivera | Not Started | Medium | 2024-09-05 | 2024-09-17 |  | 0 | Rebar | Plot 21, Riverside | 29347.35 | 0 | Not started
C002 | Shopping Complex B | T615 | Foundation Excavation | Rachel Green | Not Started | Medium | 2023-03-03 | 2023-03-16 |  | 0 | Rebar | Market Street | 42911.24 | 0 | Not started
C001 | Residential Building A | T594 | Electrical Wiring | John Miller | Blocked | Low | 2023-03-07 | 2023-03-28 |  | 0 | Roofing Sheets | Plot 21, Riverside | 37807.51 | 41608.03 | Not started
C002 | Shopping Complex B | T814 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2024-05-16 | 2024-05-24 | 2024-05-24 | 100 | Cement | Market Street | 18926.71 | 47884.28 | No issues
C003 | Office Tower C | T482 | Electrical Wiring | Dave Brown | In Progress | High | 2023-11-21 | 2023-11-30 |  | 70 | Steel Beams | Downtown Avenue | 19379.26 | 13842.71 | In progress
C004 | Warehouse D | T687 | Foundation Excavation | Emma White | In Progress | Low | 2024-06-19 | 2024-07-18 |  | 97 | Paint | Industrial Park | 27004.29 | 17866.91 | In progress
C003 | Office Tower C | T301 | Steel Framework Setup | Sarah Johnson | Completed | Low | 2024-03-17 | 2024-04-10 | 2024-04-10 | 100 | Rebar | Downtown Avenue | 41660.1 | 49717.23 | No issues
C003 | Office Tower C | T137 | Roofing | Emma White | In Progress | Medium | 2023-02-27 | 2023-03-17 |  | 90 | Steel Beams | Downtown Avenue | 44186.31 | 28454.17 | In progress
C002 | Shopping Complex B | T219 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-10-06 | 2023-10-31 |  | 0 | Concrete | Market Street | 7310.07 | 32495.02 | Not started
C002 | Shopping Complex B | T515 | Foundation Excavation | Mike Adams | Not Started | High | 2024-01-11 | 2024-01-18 |  | 0 | PVC Pipes | Market Street | 5698.04 | 0 | Not started
C002 | Shopping Complex B | T457 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-01-08 | 2024-01-25 |  | 0 | Roofing Sheets | Market Street | 30364.15 | 46004.3 | Not started
C001 | Residential Building A | T249 | Electrical Wiring | Sarah Johnson | Blocked | High | 2023-11-24 | 2023-12-03 |  | 0 | Steel Beams | Plot 21, Riverside | 32085.16 | 25071.23 | Not started
C002 | Shopping Complex B | T346 | Interior Painting | Carlos Rivera | Completed | Low | 2023-04-09 | 2023-04-29 | 2023-04-29 | 100 | Concrete | Market Street | 34014.15 | 62145.11 | No issues
C001 | Residential Building A | T514 | Plumbing Installations | Sarah Johnson | Completed | Low | 2024-07-08 | 2024-07-15 | 2024-07-15 | 100 | PVC Pipes | Plot 21, Riverside | 28632.54 | 29504.82 | No issues
C003 | Office Tower C | T253 | Foundation Excavation | Mike Adams | Completed | High | 2024-10-04 | 2024-10-31 | 2024-10-31 | 100 | PVC Pipes | Downtown Avenue | 31913.16 | 36530.01 | No issues
C003 | Office Tower C | T962 | Roofing | Carlos Rivera | Blocked | High | 2024-02-17 | 2024-03-14 |  | 0 | Steel Beams | Downtown Avenue | 5346.28 | 5410.26 | Not started
C003 | Office Tower C | T120 | Interior Painting | Rachel Green | In Progress | Medium | 2024-03-14 | 2024-03-26 |  | 60 | Cement | Downtown Avenue | 40924.38 | 27846.91 | In progress
C003 | Office Tower C | T702 | Interior Painting | Dave Brown | Blocked | Medium | 2024-01-25 | 2024-02-01 |  | 0 | PVC Pipes | Downtown Avenue | 24691.93 | 21539.51 | Not started
C001 | Residential Building A | T570 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-08-09 | 2024-08-24 |  | 0 | Paint | Plot 21, Riverside | 13368.32 | 11521.62 | Not started
C001 | Residential Building A | T901 | Interior Painting | Dave Brown | Not Started | High | 2023-02-04 | 2023-02-28 |  | 0 | Concrete | Plot 21, Riverside | 29815.07 | 0 | Not started
C004 | Warehouse D | T193 | Electrical Wiring | Dave Brown | Blocked | Medium | 2024-08-18 | 2024-08-30 |  | 0 | PVC Pipes | Industrial Park | 6018.64 | 4404.19 | Not started
C003 | Office Tower C | T396 | Roofing | Dave Brown | In Progress | Medium | 2023-07-13 | 2023-08-10 |  | 69 | Paint | Downtown Avenue | 21426.31 | 15476.77 | In progress
C004 | Warehouse D | T171 | Roofing | Grace Allen | Completed | Low | 2024-09-28 | 2024-10-28 | 2024-10-28 | 100 | Paint | Industrial Park | 12068.73 | 7647.26 | No issues
C003 | Office Tower C | T308 | Steel Framework Setup | Dave Brown | In Progress | High | 2024-07-23 | 2024-08-12 |  | 23 | Paint | Downtown Avenue | 19622.06 | 14198.15 | In progress
C001 | Residential Building A | T928 | Site Survey | John Miller | Not Started | High | 2023-12-13 | 2024-01-03 |  | 0 | Copper Wires | Plot 21, Riverside | 19536.55 | 0 | Not started
C002 | Shopping Complex B | T823 | Plumbing Installations | Dave Brown | Not Started | High | 2024-01-12 | 2024-01-29 |  | 0 | Copper Wires | Market Street | 24331.05 | 0 | Not started
C003 | Office Tower C | T302 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2023-03-12 | 2023-03-21 | 2023-03-21 | 100 | PVC Pipes | Downtown Avenue | 35377.7 | 27425.92 | No issues
C002 | Shopping Complex B | T992 | Interior Painting | Rachel Green | Completed | High | 2024-12-03 | 2025-01-01 | 2025-01-01 | 100 | Concrete | Market Street | 34798.39 | 50364.2 | No issues
C002 | Shopping Complex B | T766 | Foundation Excavation | Rachel Green | Not Started | Low | 2024-09-10 | 2024-10-06 |  | 0 | Roofing Sheets | Market Street | 16229.32 | 0 | Not started
C003 | Office Tower C | T725 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-02-16 | 2023-02-27 | 2023-02-27 | 100 | Rebar | Downtown Avenue | 20171.52 | 12241.01 | No issues
C002 | Shopping Complex B | T750 | Roofing | Grace Allen | Completed | Low | 2024-12-11 | 2024-12-25 | 2024-12-25 | 100 | Copper Wires | Market Street | 15442.53 | 42504.42 | No issues
C002 | Shopping Complex B | T741 | Interior Painting | Rachel Green | Blocked | High | 2024-08-22 | 2024-08-30 |  | 0 | Rebar | Market Street | 11247.59 | 33117.08 | Not started
C003 | Office Tower C | T696 | Plumbing Installations | Mike Adams | Completed | High | 2023-09-13 | 2023-09-30 | 2023-09-30 | 100 | Roofing Sheets | Downtown Avenue | 49804.47 | 40236.07 | No issues
C003 | Office Tower C | T941 | Roofing | Rachel Green | Completed | Low | 2023-07-22 | 2023-08-10 | 2023-08-10 | 100 | Concrete | Downtown Avenue | 23585.56 | 26169.17 | No issues
C003 | Office Tower C | T281 | Plumbing Installations | Dave Brown | Completed | Medium | 2024-12-25 | 2025-01-21 | 2025-01-21 | 100 | Steel Beams | Downtown Avenue | 30470.61 | 35487.31 | No issues
C004 | Warehouse D | T462 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2023-08-11 | 2023-08-25 |  | 0 | PVC Pipes | Industrial Park | 11361.1 | 11769.24 | Not started
C004 | Warehouse D | T540 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2023-01-09 | 2023-01-21 |  | 0 | Rebar | Industrial Park | 7662.51 | 5453.16 | Not started
C004 | Warehouse D | T846 | Interior Painting | Dave Brown | Not Started | Medium | 2024-08-21 | 2024-09-16 |  | 0 | Paint | Industrial Park | 38407.02 | 0 | Not started
C002 | Shopping Complex B | T488 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2024-05-10 | 2024-06-09 |  | 0 | PVC Pipes | Market Street | 38715.71 | 0 | Not started
C003 | Office Tower C | T349 | Steel Framework Setup | John Miller | Not Started | High | 2024-04-26 | 2024-05-24 |  | 0 | PVC Pipes | Downtown Avenue | 25349.82 | 0 | Not started
C003 | Office Tower C | T128 | Foundation Excavation | John Miller | Not Started | High | 2023-04-27 | 2023-05-10 |  | 0 | Copper Wires | Downtown Avenue | 21371.02 | 0 | Not started
C003 | Office Tower C | T509 | Roofing | John Miller | Not Started | Low | 2024-01-22 | 2024-02-10 |  | 0 | Cement | Downtown Avenue | 17965.52 | 0 | Not started
C003 | Office Tower C | T373 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2024-12-27 | 2025-01-18 |  | 0 | PVC Pipes | Downtown Avenue | 30846.13 | 36934.49 | Not started
C004 | Warehouse D | T181 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2023-09-10 | 2023-10-01 |  | 63 | Copper Wires | Industrial Park | 22826.99 | 22704.32 | In progress
C003 | Office Tower C | T883 | Foundation Excavation | Grace Allen | Not Started | Low | 2023-03-12 | 2023-04-09 |  | 0 | Copper Wires | Downtown Avenue | 46307.14 | 0 | Not started
C003 | Office Tower C | T580 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-08-03 | 2023-08-13 |  | 0 | Concrete | Downtown Avenue | 46019.7 | 0 | Not started
C003 | Office Tower C | T121 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-08-22 | 2024-09-19 | 2024-09-19 | 100 | Copper Wires | Downtown Avenue | 48075.78 | 33926.02 | No issues
C001 | Residential Building A | T571 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2023-11-22 | 2023-12-12 |  | 47 | Steel Beams | Plot 21, Riverside | 13610.29 | 8755.55 | In progress
C002 | Shopping Complex B | T781 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-04-01 | 2023-04-30 | 2023-04-30 | 100 | Concrete | Market Street | 17076.54 | 40152.2 | No issues
C003 | Office Tower C | T281 | Steel Framework Setup | Mike Adams | Completed | Low | 2023-07-07 | 2023-07-25 | 2023-07-25 | 100 | Roofing Sheets | Downtown Avenue | 25908.63 | 26632.94 | No issues
C002 | Shopping Complex B | T456 | Concrete Pouring | Mike Adams | In Progress | Medium | 2024-01-15 | 2024-02-02 |  | 81 | Steel Beams | Market Street | 13674.67 | 37043.12 | In progress
C003 | Office Tower C | T147 | Interior Painting | Grace Allen | In Progress | High | 2023-12-11 | 2023-12-27 |  | 16 | Paint | Downtown Avenue | 43352.27 | 43727.9 | In progress
C004 | Warehouse D | T306 | Roofing | Rachel Green | Completed | High | 2024-04-04 | 2024-04-18 | 2024-04-18 | 100 | PVC Pipes | Industrial Park | 44002.68 | 28151.77 | No issues
C004 | Warehouse D | T998 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-06-21 | 2023-07-13 |  | 0 | PVC Pipes | Industrial Park | 19377.8 | 0 | Not started
C003 | Office Tower C | T451 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2024-09-25 | 2024-10-13 |  | 95 | Paint | Downtown Avenue | 27732.16 | 33198.15 | In progress
C002 | Shopping Complex B | T883 | Interior Painting | Rachel Green | Completed | Low | 2024-01-15 | 2024-01-26 | 2024-01-26 | 100 | Roofing Sheets | Market Street | 29140.77 | 50547.53 | No issues
C004 | Warehouse D | T367 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-09-19 | 2023-10-14 |  | 0 | Rebar | Industrial Park | 25392.29 | 0 | Not started
C001 | Residential Building A | T332 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2023-02-24 | 2023-03-07 |  | 0 | PVC Pipes | Plot 21, Riverside | 8119.23 | 6826.96 | Not started
C002 | Shopping Complex B | T708 | Interior Painting | John Miller | Completed | Medium | 2024-03-01 | 2024-03-28 | 2024-03-28 | 100 | Roofing Sheets | Market Street | 35019.68 | 66527.11 | No issues
C002 | Shopping Complex B | T101 | Site Survey | Carlos Rivera | Not Started | Medium | 2024-10-21 | 2024-11-20 |  | 0 | Roofing Sheets | Market Street | 27692.98 | 0 | Not started
C002 | Shopping Complex B | T855 | Plumbing Installations | Sarah Johnson | In Progress | Medium | 2024-09-10 | 2024-10-09 |  | 27 | Rebar | Market Street | 46731.49 | 75687.69 | In progress
C003 | Office Tower C | T309 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2024-09-19 | 2024-10-12 | 2024-10-12 | 100 | PVC Pipes | Downtown Avenue | 31856.81 | 20993.78 | No issues
C003 | Office Tower C | T875 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2023-02-21 | 2023-03-12 |  | 0 | PVC Pipes | Downtown Avenue | 33024.99 | 0 | Not started
C002 | Shopping Complex B | T309 | Roofing | Rachel Green | Completed | High | 2024-11-09 | 2024-12-01 | 2024-12-01 | 100 | Cement | Market Street | 34383.07 | 60615.2 | No issues
C004 | Warehouse D | T583 | Roofing | Carlos Rivera | In Progress | Medium | 2024-10-03 | 2024-10-22 |  | 27 | Concrete | Industrial Park | 36937.8 | 26169.39 | In progress
C003 | Office Tower C | T336 | Site Survey | Dave Brown | Completed | High | 2024-06-06 | 2024-06-28 | 2024-06-28 | 100 | Copper Wires | Downtown Avenue | 22712.81 | 20345.75 | No issues
C002 | Shopping Complex B | T212 | Site Survey | Grace Allen | Blocked | Medium | 2024-03-26 | 2024-04-14 |  | 0 | Roofing Sheets | Market Street | 12100.61 | 39143.86 | Not started
C002 | Shopping Complex B | T125 | Plumbing Installations | Mike Adams | Blocked | High | 2024-11-11 | 2024-12-11 |  | 0 | Steel Beams | Market Street | 29730.01 | 58783.55 | Not started
C004 | Warehouse D | T949 | Concrete Pouring | Grace Allen | Completed | Low | 2024-03-24 | 2024-04-18 | 2024-04-18 | 100 | Copper Wires | Industrial Park | 33586.77 | 21511.48 | No issues
C002 | Shopping Complex B | T765 | Roofing | Rachel Green | Blocked | Low | 2024-07-26 | 2024-08-14 |  | 0 | Steel Beams | Market Street | 12760.27 | 35516.75 | Not started
C002 | Shopping Complex B | T621 | Foundation Excavation | Rachel Green | In Progress | Low | 2024-11-05 | 2024-12-05 |  | 22 | Roofing Sheets | Market Street | 15806.26 | 39553.83 | In progress
C003 | Office Tower C | T877 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2023-06-24 | 2023-07-17 |  | 0 | Paint | Downtown Avenue | 38872.36 | 0 | Not started
C004 | Warehouse D | T332 | Roofing | Mike Adams | Blocked | Low | 2024-11-21 | 2024-11-28 |  | 0 | Paint | Industrial Park | 21606.2 | 21844.12 | Not started
C004 | Warehouse D | T765 | Site Survey | Mike Adams | Not Started | High | 2024-12-16 | 2025-01-15 |  | 0 | PVC Pipes | Industrial Park | 12602.56 | 0 | Not started
C004 | Warehouse D | T500 | Plumbing Installations | Rachel Green | Not Started | High | 2024-08-04 | 2024-08-19 |  | 0 | Concrete | Industrial Park | 27366.46 | 0 | Not started
C003 | Office Tower C | T464 | Site Survey | Mike Adams | Not Started | Medium | 2023-09-04 | 2023-09-12 |  | 0 | Concrete | Downtown Avenue | 32272.54 | 0 | Not started
C001 | Residential Building A | T742 | Roofing | Carlos Rivera | In Progress | Medium | 2023-01-21 | 2023-02-07 |  | 25 | Rebar | Plot 21, Riverside | 15819.98 | 17505.9 | In progress
C004 | Warehouse D | T201 | Electrical Wiring | Grace Allen | Blocked | High | 2024-12-09 | 2024-12-25 |  | 0 | Steel Beams | Industrial Park | 26635 | 24846.12 | Not started
C003 | Office Tower C | T741 | Electrical Wiring | Carlos Rivera | Completed | High | 2023-07-26 | 2023-08-11 | 2023-08-11 | 100 | Copper Wires | Downtown Avenue | 27865.92 | 17004.15 | No issues
C004 | Warehouse D | T273 | Electrical Wiring | Grace Allen | In Progress | High | 2023-04-26 | 2023-05-19 |  | 65 | Paint | Industrial Park | 48608.03 | 37405.52 | In progress
C001 | Residential Building A | T347 | Roofing | Grace Allen | Completed | Medium | 2023-09-18 | 2023-10-15 | 2023-10-15 | 100 | Copper Wires | Plot 21, Riverside | 33438.5 | 35182.58 | No issues
C002 | Shopping Complex B | T441 | Concrete Pouring | Mike Adams | Completed | Low | 2024-07-10 | 2024-08-01 | 2024-08-01 | 100 | Rebar | Market Street | 20537.62 | 42706.34 | No issues
C003 | Office Tower C | T221 | Plumbing Installations | Mike Adams | Not Started | High | 2023-12-06 | 2023-12-14 |  | 0 | Copper Wires | Downtown Avenue | 29643.22 | 0 | Not started
C002 | Shopping Complex B | T981 | Interior Painting | Mike Adams | Not Started | High | 2023-11-19 | 2023-12-19 |  | 0 | Steel Beams | Market Street | 7193.19 | 0 | Not started
C004 | Warehouse D | T879 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-06-24 | 2024-07-05 |  | 0 | Roofing Sheets | Industrial Park | 5037.65 | 0 | Not started
C004 | Warehouse D | T114 | Steel Framework Setup | Emma White | Completed | High | 2024-04-23 | 2024-05-12 | 2024-05-12 | 100 | Concrete | Industrial Park | 27526.92 | 26037.84 | No issues
C004 | Warehouse D | T820 | Roofing | Sarah Johnson | In Progress | High | 2024-03-05 | 2024-03-26 |  | 22 | Cement | Industrial Park | 18267.98 | 13008.74 | In progress
C001 | Residential Building A | T950 | Plumbing Installations | Grace Allen | Completed | High | 2024-04-21 | 2024-05-16 | 2024-05-16 | 100 | Cement | Plot 21, Riverside | 29526.77 | 19310.63 | No issues
C001 | Residential Building A | T846 | Electrical Wiring | John Miller | Completed | Low | 2023-02-23 | 2023-03-10 | 2023-03-10 | 100 | Roofing Sheets | Plot 21, Riverside | 12929.05 | 8907.13 | No issues
C003 | Office Tower C | T278 | Plumbing Installations | Emma White | Blocked | Low | 2023-04-17 | 2023-05-17 |  | 0 | Paint | Downtown Avenue | 6503.26 | 6440.92 | Not started
C002 | Shopping Complex B | T766 | Steel Framework Setup | Carlos Rivera | Completed | Low | 2023-12-18 | 2024-01-08 | 2024-01-08 | 100 | Concrete | Market Street | 18095.08 | 45153.01 | No issues
C003 | Office Tower C | T771 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-02-11 | 2023-03-04 |  | 0 | Rebar | Downtown Avenue | 29053.46 | 0 | Not started
C004 | Warehouse D | T351 | Site Survey | Mike Adams | In Progress | Low | 2023-08-04 | 2023-09-02 |  | 81 | PVC Pipes | Industrial Park | 46966.22 | 40826.7 | In progress
C004 | Warehouse D | T478 | Roofing | Sarah Johnson | In Progress | Medium | 2023-12-23 | 2024-01-12 |  | 94 | Paint | Industrial Park | 36576.62 | 28989.24 | In progress
C003 | Office Tower C | T466 | Roofing | Dave Brown | Completed | High | 2024-03-21 | 2024-04-20 | 2024-04-20 | 100 | Steel Beams | Downtown Avenue | 7277.64 | 5482.35 | No issues
C001 | Residential Building A | T944 | Interior Painting | Rachel Green | Completed | High | 2024-01-14 | 2024-02-06 | 2024-02-06 | 100 | Copper Wires | Plot 21, Riverside | 46460.05 | 51240.43 | No issues
C001 | Residential Building A | T897 | Roofing | Dave Brown | In Progress | Low | 2023-06-07 | 2023-06-16 |  | 98 | Paint | Plot 21, Riverside | 34109.3 | 25095.54 | In progress
C002 | Shopping Complex B | T163 | Foundation Excavation | Rachel Green | Completed | Low | 2024-01-24 | 2024-02-04 | 2024-02-04 | 100 | Roofing Sheets | Market Street | 35144.56 | 62183.86 | No issues
C002 | Shopping Complex B | T993 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-02-22 | 2024-03-03 |  | 0 | PVC Pipes | Market Street | 20958.08 | 41349.63 | Not started
C001 | Residential Building A | T680 | Roofing | Dave Brown | Not Started | High | 2024-10-04 | 2024-10-16 |  | 0 | Copper Wires | Plot 21, Riverside | 45308.24 | 0 | Not started
C001 | Residential Building A | T133 | Electrical Wiring | Grace Allen | Completed | High | 2023-03-13 | 2023-04-06 | 2023-04-06 | 100 | PVC Pipes | Plot 21, Riverside | 41546.52 | 36879.15 | No issues
C004 | Warehouse D | T692 | Steel Framework Setup | Emma White | In Progress | High | 2024-02-14 | 2024-02-29 |  | 52 | Steel Beams | Industrial Park | 16789.6 | 19884.38 | In progress
C004 | Warehouse D | T505 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-04-02 | 2023-04-11 |  | 23 | PVC Pipes | Industrial Park | 6865.25 | 5092.29 | In progress
C003 | Office Tower C | T359 | Plumbing Installations | Mike Adams | Not Started | Medium | 2023-07-26 | 2023-08-07 |  | 0 | Steel Beams | Downtown Avenue | 15861.82 | 0 | Not started
C003 | Office Tower C | T238 | Interior Painting | Mike Adams | In Progress | High | 2023-09-17 | 2023-10-06 |  | 57 | Cement | Downtown Avenue | 28113.78 | 28499.06 | In progress
C004 | Warehouse D | T269 | Roofing | Mike Adams | Completed | High | 2023-11-19 | 2023-12-14 | 2023-12-14 | 100 | Copper Wires | Industrial Park | 15372.95 | 14964.27 | No issues
C002 | Shopping Complex B | T942 | Site Survey | Rachel Green | In Progress | High | 2023-05-25 | 2023-06-16 |  | 53 | Copper Wires | Market Street | 30320.95 | 56273.73 | In progress
C003 | Office Tower C | T586 | Roofing | Grace Allen | Not Started | Medium | 2023-11-12 | 2023-12-06 |  | 0 | Roofing Sheets | Downtown Avenue | 6910.9 | 0 | Not started
C004 | Warehouse D | T638 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-01-02 | 2023-01-11 |  | 0 | Steel Beams | Industrial Park | 42307.78 | 30123.9 | Not started
C001 | Residential Building A | T303 | Interior Painting | Rachel Green | In Progress | Medium | 2023-07-22 | 2023-08-20 |  | 44 | Copper Wires | Plot 21, Riverside | 33299.65 | 33599.86 | In progress
C003 | Office Tower C | T371 | Roofing | John Miller | Completed | Medium | 2024-03-12 | 2024-04-04 | 2024-04-04 | 100 | Paint | Downtown Avenue | 36923.89 | 25130.37 | No issues
C003 | Office Tower C | T219 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2023-04-03 | 2023-04-23 |  | 83 | Cement | Downtown Avenue | 26310.63 | 23915.95 | In progress
C002 | Shopping Complex B | T995 | Steel Framework Setup | Mike Adams | Completed | High | 2024-10-20 | 2024-11-18 | 2024-11-18 | 100 | Paint | Market Street | 33524.37 | 57538.04 | No issues
C004 | Warehouse D | T843 | Steel Framework Setup | Grace Allen | Completed | Low | 2023-10-27 | 2023-11-23 | 2023-11-23 | 100 | Roofing Sheets | Industrial Park | 6367.47 | 5538.69 | No issues
C003 | Office Tower C | T503 | Electrical Wiring | John Miller | In Progress | Low | 2023-09-22 | 2023-10-04 |  | 0 | Steel Beams | Downtown Avenue | 12822.09 | 12923.33 | In progress
C001 | Residential Building A | T764 | Concrete Pouring | Emma White | Blocked | High | 2023-05-15 | 2023-06-02 |  | 0 | Concrete | Plot 21, Riverside | 20979.08 | 21763 | Not started
C002 | Shopping Complex B | T787 | Site Survey | Dave Brown | Completed | Low | 2024-04-20 | 2024-05-13 | 2024-05-13 | 100 | PVC Pipes | Market Street | 28361.73 | 47473.53 | No issues
C002 | Shopping Complex B | T348 | Interior Painting | Sarah Johnson | In Progress | High | 2024-04-27 | 2024-05-27 |  | 77 | Steel Beams | Market Street | 8419.1 | 33219.42 | In progress
C004 | Warehouse D | T580 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2023-09-10 | 2023-09-21 |  | 93 | PVC Pipes | Industrial Park | 45369.81 | 33644.51 | In progress
C004 | Warehouse D | T594 | Concrete Pouring | John Miller | In Progress | High | 2024-11-14 | 2024-12-04 |  | 94 | Steel Beams | Industrial Park | 39536.62 | 26175.42 | In progress
C002 | Shopping Complex B | T304 | Electrical Wiring | Dave Brown | Not Started | High | 2023-03-04 | 2023-03-28 |  | 0 | Roofing Sheets | Market Street | 34039.69 | 0 | Not started
C001 | Residential Building A | T884 | Interior Painting | Dave Brown | Completed | Low | 2023-12-15 | 2023-12-29 | 2023-12-29 | 100 | Paint | Plot 21, Riverside | 42189.13 | 26843.1 | No issues
C004 | Warehouse D | T552 | Site Survey | Dave Brown | Not Started | Low | 2024-11-13 | 2024-12-07 |  | 0 | Copper Wires | Industrial Park | 26630.23 | 0 | Not started
C004 | Warehouse D | T552 | Site Survey | Sarah Johnson | Not Started | High | 2024-01-04 | 2024-02-02 |  | 0 | Copper Wires | Industrial Park | 34238.34 | 0 | Not started
C003 | Office Tower C | T602 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-01-12 | 2023-02-07 |  | 46 | Concrete | Downtown Avenue | 49723.91 | 55075.93 | In progress
C003 | Office Tower C | T488 | Electrical Wiring | Grace Allen | Blocked | Medium | 2023-11-04 | 2023-11-17 |  | 0 | Concrete | Downtown Avenue | 11453.27 | 10954.98 | Not started
C001 | Residential Building A | T865 | Interior Painting | Dave Brown | Not Started | High | 2023-07-17 | 2023-08-13 |  | 0 | Roofing Sheets | Plot 21, Riverside | 9905.81 | 0 | Not started
C002 | Shopping Complex B | T889 | Interior Painting | Mike Adams | Blocked | Medium | 2023-12-21 | 2024-01-01 |  | 0 | Cement | Market Street | 47974.36 | 56340.85 | Not started
C002 | Shopping Complex B | T227 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-08-07 | 2023-09-05 |  | 0 | Concrete | Market Street | 6879.52 | 30205.19 | Not started
C002 | Shopping Complex B | T365 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2023-04-12 | 2023-04-30 |  | 0 | Roofing Sheets | Market Street | 35725.08 | 0 | Not started
C004 | Warehouse D | T780 | Interior Painting | Carlos Rivera | Completed | High | 2024-02-15 | 2024-03-16 | 2024-03-16 | 100 | Roofing Sheets | Industrial Park | 14365.42 | 16091.07 | No issues
C002 | Shopping Complex B | T274 | Steel Framework Setup | Emma White | Completed | Low | 2023-05-06 | 2023-05-27 | 2023-05-27 | 100 | Paint | Market Street | 40664.92 | 54462.74 | No issues
C001 | Residential Building A | T303 | Plumbing Installations | Grace Allen | Not Started | Medium | 2024-03-15 | 2024-04-12 |  | 0 | Roofing Sheets | Plot 21, Riverside | 35635.28 | 0 | Not started
C003 | Office Tower C | T544 | Interior Painting | Carlos Rivera | Blocked | High | 2023-02-12 | 2023-02-20 |  | 0 | Roofing Sheets | Downtown Avenue | 27135.66 | 24989.9 | Not started
C001 | Residential Building A | T259 | Concrete Pouring | Rachel Green | Blocked | High | 2024-07-01 | 2024-07-08 |  | 0 | Rebar | Plot 21, Riverside | 36105.15 | 32472.47 | Not started
C002 | Shopping Complex B | T499 | Steel Framework Setup | Mike Adams | Not Started | High | 2023-02-25 | 2023-03-13 |  | 0 | Copper Wires | Market Street | 48276 | 0 | Not started
C003 | Office Tower C | T273 | Steel Framework Setup | Emma White | Blocked | Low | 2024-09-13 | 2024-09-27 |  | 0 | Rebar | Downtown Avenue | 49675.3 | 56953.97 | Not started
C002 | Shopping Complex B | T355 | Interior Painting | Emma White | Blocked | Medium | 2024-11-15 | 2024-12-04 |  | 0 | Cement | Market Street | 9059.48 | 32861.28 | Not started
C004 | Warehouse D | T218 | Interior Painting | Dave Brown | Blocked | Low | 2024-02-03 | 2024-02-19 |  | 0 | Paint | Industrial Park | 16710.38 | 12005.17 | Not started
C004 | Warehouse D | T325 | Plumbing Installations | Rachel Green | Blocked | Medium | 2024-09-25 | 2024-10-12 |  | 0 | Cement | Industrial Park | 6693.29 | 5194.37 | Not started
C004 | Warehouse D | T924 | Foundation Excavation | Dave Brown | Completed | High | 2023-03-21 | 2023-04-05 | 2023-04-05 | 100 | Cement | Industrial Park | 8949.98 | 9186.48 | No issues
C001 | Residential Building A | T366 | Foundation Excavation | John Miller | Not Started | Low | 2023-09-23 | 2023-10-05 |  | 0 | PVC Pipes | Plot 21, Riverside | 10113.09 | 0 | Not started
C002 | Shopping Complex B | T144 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-09-15 | 2023-10-14 |  | 0 | Steel Beams | Market Street | 36260.86 | 68225.52 | Not started
C001 | Residential Building A | T517 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2024-07-10 | 2024-08-04 |  | 31 | Concrete | Plot 21, Riverside | 41763.64 | 48618.46 | In progress
C002 | Shopping Complex B | T110 | Interior Painting | Dave Brown | Completed | High | 2023-12-26 | 2024-01-05 | 2024-01-05 | 100 | Rebar | Market Street | 21878.14 | 49332.53 | No issues
C002 | Shopping Complex B | T527 | Site Survey | Carlos Rivera | In Progress | High | 2024-11-14 | 2024-12-01 |  | 96 | Paint | Market Street | 34508.7 | 58555.71 | In progress
C003 | Office Tower C | T255 | Interior Painting | Dave Brown | In Progress | High | 2024-04-23 | 2024-05-19 |  | 51 | Cement | Downtown Avenue | 6648.78 | 5638.35 | In progress
C002 | Shopping Complex B | T360 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-10-21 | 2023-11-09 |  | 81 | PVC Pipes | Market Street | 45489.61 | 61701.71 | In progress
C001 | Residential Building A | T269 | Plumbing Installations | John Miller | In Progress | Medium | 2024-02-01 | 2024-02-16 |  | 19 | PVC Pipes | Plot 21, Riverside | 35452.61 | 32888.34 | In progress
C002 | Shopping Complex B | T696 | Concrete Pouring | Rachel Green | In Progress | Low | 2024-05-21 | 2024-06-12 |  | 82 | Copper Wires | Market Street | 47852.72 | 54594.32 | In progress
C004 | Warehouse D | T447 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2024-02-06 | 2024-02-27 |  | 0 | Concrete | Industrial Park | 16057.29 | 0 | Not started
C002 | Shopping Complex B | T341 | Foundation Excavation | Rachel Green | Blocked | High | 2024-03-20 | 2024-04-13 |  | 0 | Steel Beams | Market Street | 33147.92 | 53590.18 | Not started
C003 | Office Tower C | T685 | Roofing | Rachel Green | Not Started | Low | 2023-12-26 | 2024-01-08 |  | 0 | Rebar | Downtown Avenue | 23829.57 | 0 | Not started
C001 | Residential Building A | T739 | Concrete Pouring | Rachel Green | Not Started | Low | 2024-12-24 | 2025-01-04 |  | 0 | Steel Beams | Plot 21, Riverside | 28282.04 | 0 | Not started
C004 | Warehouse D | T747 | Electrical Wiring | Rachel Green | Not Started | High | 2023-07-01 | 2023-07-13 |  | 0 | Steel Beams | Industrial Park | 40208.74 | 0 | Not started
C002 | Shopping Complex B | T533 | Interior Painting | Dave Brown | Blocked | Medium | 2024-12-13 | 2024-12-30 |  | 0 | Cement | Market Street | 21253.94 | 43245.29 | Not started
C001 | Residential Building A | T912 | Interior Painting | Grace Allen | In Progress | High | 2023-10-24 | 2023-11-02 |  | 80 | Paint | Plot 21, Riverside | 20759.68 | 23385.97 | In progress
C004 | Warehouse D | T523 | Interior Painting | Rachel Green | Blocked | Medium | 2024-06-27 | 2024-07-25 |  | 0 | Rebar | Industrial Park | 33539.51 | 38857.45 | Not started
C001 | Residential Building A | T165 | Site Survey | Emma White | Not Started | High | 2024-11-09 | 2024-12-04 |  | 0 | PVC Pipes | Plot 21, Riverside | 27980.06 | 0 | Not started
C003 | Office Tower C | T431 | Plumbing Installations | John Miller | In Progress | Medium | 2024-01-16 | 2024-01-24 |  | 68 | PVC Pipes | Downtown Avenue | 31022.77 | 19606.93 | In progress
C003 | Office Tower C | T351 | Foundation Excavation | Rachel Green | Blocked | High | 2024-11-07 | 2024-12-03 |  | 0 | Copper Wires | Downtown Avenue | 10296.84 | 9723.38 | Not started
C001 | Residential Building A | T982 | Site Survey | Dave Brown | In Progress | High | 2023-10-28 | 2023-11-18 |  | 16 | Paint | Plot 21, Riverside | 22454.54 | 16614.23 | In progress
C002 | Shopping Complex B | T723 | Electrical Wiring | John Miller | In Progress | High | 2024-04-06 | 2024-05-05 |  | 40 | Concrete | Market Street | 29279.14 | 52207.88 | In progress
C003 | Office Tower C | T399 | Site Survey | Mike Adams | Blocked | Low | 2023-01-24 | 2023-02-16 |  | 0 | Steel Beams | Downtown Avenue | 6313.48 | 5749.74 | Not started
C003 | Office Tower C | T509 | Roofing | Mike Adams | Completed | Medium | 2024-08-03 | 2024-08-17 | 2024-08-17 | 100 | Copper Wires | Downtown Avenue | 17480.67 | 20241.43 | No issues
C002 | Shopping Complex B | T697 | Plumbing Installations | John Miller | Blocked | Medium | 2024-09-21 | 2024-10-15 |  | 0 | Copper Wires | Market Street | 15310.37 | 43457.25 | Not started
C004 | Warehouse D | T320 | Interior Painting | Mike Adams | Blocked | High | 2024-08-26 | 2024-09-09 |  | 0 | Copper Wires | Industrial Park | 38543.02 | 30375.63 | Not started
C003 | Office Tower C | T807 | Electrical Wiring | Emma White | Completed | High | 2023-05-22 | 2023-06-07 | 2023-06-07 | 100 | Steel Beams | Downtown Avenue | 46875.89 | 28328.4 | No issues
C002 | Shopping Complex B | T138 | Foundation Excavation | Sarah Johnson | In Progress | High | 2024-03-24 | 2024-04-10 |  | 81 | Steel Beams | Market Street | 45717.4 | 70697.65 | In progress
C001 | Residential Building A | T630 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2024-03-15 | 2024-03-29 |  | 0 | Cement | Plot 21, Riverside | 39943.04 | 0 | Not started
C002 | Shopping Complex B | T294 | Electrical Wiring | Grace Allen | Not Started | Medium | 2023-06-27 | 2023-07-06 |  | 0 | Copper Wires | Market Street | 40050.93 | 0 | Not started
C004 | Warehouse D | T999 | Interior Painting | Mike Adams | Blocked | Medium | 2024-06-05 | 2024-06-29 |  | 0 | Roofing Sheets | Industrial Park | 38595.51 | 27398.73 | Not started
C001 | Residential Building A | T267 | Roofing | John Miller | Blocked | Low | 2024-07-15 | 2024-08-04 |  | 0 | Paint | Plot 21, Riverside | 42965.61 | 46170.89 | Not started
C002 | Shopping Complex B | T315 | Concrete Pouring | Carlos Rivera | Completed | Low | 2024-06-12 | 2024-06-25 | 2024-06-25 | 100 | Paint | Market Street | 46309.48 | 67908.06 | No issues
C004 | Warehouse D | T633 | Steel Framework Setup | Mike Adams | Blocked | Low | 2024-08-09 | 2024-09-01 |  | 0 | Cement | Industrial Park | 32580.5 | 30603.65 | Not started
C003 | Office Tower C | T390 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-10-02 | 2024-10-31 | 2024-10-31 | 100 | Rebar | Downtown Avenue | 8316.03 | 8462.9 | No issues
C003 | Office Tower C | T697 | Steel Framework Setup | John Miller | In Progress | Low | 2024-04-23 | 2024-05-22 |  | 34 | Steel Beams | Downtown Avenue | 23705.34 | 25885.17 | In progress
C001 | Residential Building A | T522 | Steel Framework Setup | John Miller | Completed | High | 2024-07-24 | 2024-08-18 | 2024-08-18 | 100 | Concrete | Plot 21, Riverside | 17576.09 | 18630.55 | No issues
C003 | Office Tower C | T275 | Foundation Excavation | Mike Adams | Blocked | Low | 2023-02-03 | 2023-02-22 |  | 0 | Steel Beams | Downtown Avenue | 10850.66 | 12862.15 | Not started
C003 | Office Tower C | T245 | Site Survey | Sarah Johnson | Completed | High | 2024-02-27 | 2024-03-17 | 2024-03-17 | 100 | Steel Beams | Downtown Avenue | 33988.9 | 29969.49 | No issues
C002 | Shopping Complex B | T904 | Site Survey | Grace Allen | Completed | Low | 2023-02-18 | 2023-03-02 | 2023-03-02 | 100 | Paint | Market Street | 14892.06 | 42719.33 | No issues
C001 | Residential Building A | T537 | Interior Painting | Mike Adams | Completed | Low | 2023-05-06 | 2023-06-01 | 2023-06-01 | 100 | Rebar | Plot 21, Riverside | 26296.23 | 22026.71 | No issues
C004 | Warehouse D | T652 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-12-10 | 2024-01-04 |  | 0 | Roofing Sheets | Industrial Park | 9206.75 | 7262.53 | Not started
C002 | Shopping Complex B | T442 | Site Survey | John Miller | Not Started | Medium | 2024-04-11 | 2024-04-26 |  | 0 | Cement | Market Street | 5037.55 | 0 | Not started
C002 | Shopping Complex B | T828 | Plumbing Installations | Sarah Johnson | Blocked | Low | 2024-09-26 | 2024-10-14 |  | 0 | Rebar | Market Street | 36107.8 | 60446.84 | Not started
C001 | Residential Building A | T499 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2024-08-25 | 2024-09-03 |  | 0 | PVC Pipes | Plot 21, Riverside | 13258.19 | 0 | Not started
C003 | Office Tower C | T533 | Interior Painting | Dave Brown | Completed | Low | 2024-07-08 | 2024-08-04 | 2024-08-04 | 100 | Copper Wires | Downtown Avenue | 36930.04 | 35704.11 | No issues
C001 | Residential Building A | T947 | Roofing | Sarah Johnson | Not Started | Low | 2023-11-14 | 2023-12-11 |  | 0 | Concrete | Plot 21, Riverside | 30403.97 | 0 | Not started
C004 | Warehouse D | T190 | Concrete Pouring | Mike Adams | Completed | Low | 2023-10-10 | 2023-10-31 | 2023-10-31 | 100 | Cement | Industrial Park | 16097.66 | 11805 | No issues
C002 | Shopping Complex B | T889 | Steel Framework Setup | Grace Allen | In Progress | Low | 2024-11-05 | 2024-11-21 |  | 97 | Cement | Market Street | 11232.62 | 38683.64 | In progress
C003 | Office Tower C | T447 | Interior Painting | Sarah Johnson | Not Started | Low | 2024-01-09 | 2024-01-29 |  | 0 | Copper Wires | Downtown Avenue | 27259.69 | 0 | Not started
C003 | Office Tower C | T215 | Steel Framework Setup | John Miller | Completed | Medium | 2023-04-28 | 2023-05-12 | 2023-05-12 | 100 | Steel Beams | Downtown Avenue | 45580.38 | 41507.01 | No issues
C001 | Residential Building A | T401 | Roofing | Sarah Johnson | Not Started | Medium | 2023-11-10 | 2023-11-28 |  | 0 | Roofing Sheets | Plot 21, Riverside | 46461.11 | 0 | Not started
C001 | Residential Building A | T720 | Steel Framework Setup | Emma White | Blocked | Medium | 2024-12-24 | 2025-01-14 |  | 0 | Paint | Plot 21, Riverside | 7539.54 | 4790.99 | Not started
C003 | Office Tower C | T202 | Plumbing Installations | John Miller | Not Started | Medium | 2023-10-26 | 2023-11-02 |  | 0 | Copper Wires | Downtown Avenue | 15451.45 | 0 | Not started
C001 | Residential Building A | T119 | Steel Framework Setup | Rachel Green | Blocked | Low | 2023-01-15 | 2023-01-28 |  | 0 | Concrete | Plot 21, Riverside | 16452.16 | 19599.46 | Not started
C001 | Residential Building A | T637 | Foundation Excavation | Sarah Johnson | Blocked | Low | 2024-09-19 | 2024-10-09 |  | 0 | Concrete | Plot 21, Riverside | 7590.25 | 4802.64 | Not started
C003 | Office Tower C | T224 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2024-04-17 | 2024-05-04 |  | 0 | Steel Beams | Downtown Avenue | 33660.55 | 0 | Not started
C002 | Shopping Complex B | T368 | Roofing | Dave Brown | Not Started | High | 2024-11-24 | 2024-12-02 |  | 0 | Rebar | Market Street | 45778.84 | 0 | Not started
C001 | Residential Building A | T124 | Electrical Wiring | Dave Brown | Completed | Medium | 2023-01-28 | 2023-02-21 | 2023-02-21 | 100 | Concrete | Plot 21, Riverside | 12493.97 | 9959.43 | No issues
C003 | Office Tower C | T697 | Foundation Excavation | Emma White | Not Started | Low | 2023-06-03 | 2023-06-21 |  | 0 | PVC Pipes | Downtown Avenue | 49338.88 | 0 | Not started
C004 | Warehouse D | T780 | Electrical Wiring | Emma White | Completed | Medium | 2023-12-15 | 2024-01-14 | 2024-01-14 | 100 | Concrete | Industrial Park | 18144.71 | 17364.82 | No issues
C004 | Warehouse D | T185 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-12-07 | 2023-12-17 |  | 0 | Concrete | Industrial Park | 45038.2 | 0 | Not started
C004 | Warehouse D | T368 | Steel Framework Setup | Mike Adams | Not Started | High | 2024-01-24 | 2024-02-22 |  | 0 | Steel Beams | Industrial Park | 42886.67 | 0 | Not started
C002 | Shopping Complex B | T978 | Interior Painting | Rachel Green | In Progress | High | 2023-11-03 | 2023-11-25 |  | 88 | Cement | Market Street | 18798.14 | 43064.5 | In progress
C002 | Shopping Complex B | T737 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-01-02 | 2023-01-20 |  | 0 | Roofing Sheets | Market Street | 37470.75 | 0 | Not started
C003 | Office Tower C | T626 | Foundation Excavation | Grace Allen | In Progress | Medium | 2023-05-18 | 2023-06-17 |  | 44 | Paint | Downtown Avenue | 45233.33 | 39892.53 | In progress
C001 | Residential Building A | T762 | Roofing | Emma White | In Progress | High | 2024-01-21 | 2024-02-16 |  | 72 | PVC Pipes | Plot 21, Riverside | 12225.52 | 11297.39 | In progress
C003 | Office Tower C | T773 | Steel Framework Setup | Emma White | Blocked | High | 2024-04-04 | 2024-04-11 |  | 0 | Copper Wires | Downtown Avenue | 28281.75 | 18997.53 | Not started
C004 | Warehouse D | T988 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2023-02-16 | 2023-02-27 |  | 0 | Concrete | Industrial Park | 8147.18 | 0 | Not started
C002 | Shopping Complex B | T539 | Interior Painting | Mike Adams | In Progress | Medium | 2023-08-15 | 2023-08-31 |  | 4 | Copper Wires | Market Street | 19504.85 | 41109.25 | In progress
C001 | Residential Building A | T817 | Foundation Excavation | John Miller | Not Started | High | 2024-06-18 | 2024-07-08 |  | 0 | Copper Wires | Plot 21, Riverside | 8294.3 | 0 | Not started
C002 | Shopping Complex B | T624 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-06-16 | 2024-06-26 |  | 0 | Paint | Market Street | 38186.8 | 0 | Not started
C002 | Shopping Complex B | T525 | Plumbing Installations | John Miller | In Progress | Low | 2024-05-14 | 2024-06-01 |  | 35 | Roofing Sheets | Market Street | 19961.53 | 42744.54 | In progress
C002 | Shopping Complex B | T352 | Electrical Wiring | Dave Brown | In Progress | Medium | 2024-12-24 | 2025-01-08 |  | 51 | Roofing Sheets | Market Street | 46174.56 | 67514.6 | In progress
C004 | Warehouse D | T270 | Electrical Wiring | Dave Brown | Blocked | Low | 2023-08-05 | 2023-08-29 |  | 0 | Roofing Sheets | Industrial Park | 16558.48 | 13492.16 | Not started
C001 | Residential Building A | T514 | Concrete Pouring | John Miller | Completed | Medium | 2024-02-26 | 2024-03-22 | 2024-03-22 | 100 | Cement | Plot 21, Riverside | 5586.58 | 4409.65 | No issues
C001 | Residential Building A | T371 | Foundation Excavation | Rachel Green | Completed | Low | 2023-10-03 | 2023-10-26 | 2023-10-26 | 100 | Rebar | Plot 21, Riverside | 31035.06 | 23404.29 | No issues
C002 | Shopping Complex B | T442 | Site Survey | John Miller | Completed | High | 2023-10-28 | 2023-11-21 | 2023-11-21 | 100 | Concrete | Market Street | 19453.38 | 37426.59 | No issues
C001 | Residential Building A | T987 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2024-06-10 | 2024-06-29 |  | 68 | Rebar | Plot 21, Riverside | 12767.19 | 9537.87 | In progress
C002 | Shopping Complex B | T650 | Electrical Wiring | Carlos Rivera | Blocked | Low | 2024-04-16 | 2024-05-09 |  | 0 | PVC Pipes | Market Street | 30943.94 | 52145.83 | Not started
C002 | Shopping Complex B | T304 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-04-28 | 2024-05-27 |  | 0 | Paint | Market Street | 49863.37 | 84283.05 | Not started
C001 | Residential Building A | T398 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2024-04-24 | 2024-05-10 |  | 64 | Copper Wires | Plot 21, Riverside | 15607.68 | 16323.78 | In progress
C001 | Residential Building A | T894 | Electrical Wiring | Rachel Green | Completed | Low | 2023-06-06 | 2023-06-13 | 2023-06-13 | 100 | Paint | Plot 21, Riverside | 9250.5 | 10186.24 | No issues
C001 | Residential Building A | T589 | Site Survey | Grace Allen | Blocked | High | 2024-04-10 | 2024-04-17 |  | 0 | Roofing Sheets | Plot 21, Riverside | 46751.39 | 44019.06 | Not started
C002 | Shopping Complex B | T947 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-06-16 | 2023-06-29 |  | 0 | PVC Pipes | Market Street | 49530.43 | 0 | Not started
C002 | Shopping Complex B | T749 | Roofing | Dave Brown | Blocked | Low | 2024-12-25 | 2025-01-07 |  | 0 | Rebar | Market Street | 36092.92 | 54963.16 | Not started
C004 | Warehouse D | T251 | Steel Framework Setup | Rachel Green | Completed | Low | 2023-03-17 | 2023-04-11 | 2023-04-11 | 100 | Copper Wires | Industrial Park | 32839.85 | 37879.99 | No issues
C001 | Residential Building A | T494 | Foundation Excavation | Mike Adams | Not Started | Low | 2023-07-03 | 2023-07-11 |  | 0 | Cement | Plot 21, Riverside | 43449.33 | 0 | Not started
C002 | Shopping Complex B | T258 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-01-14 | 2024-02-01 |  | 14 | Concrete | Market Street | 38086.28 | 63410.15 | In progress
C002 | Shopping Complex B | T942 | Roofing | Mike Adams | In Progress | Medium | 2024-03-12 | 2024-04-06 |  | 55 | Cement | Market Street | 14439.08 | 35196.73 | In progress
C003 | Office Tower C | T570 | Steel Framework Setup | Grace Allen | Blocked | High | 2023-05-11 | 2023-05-21 |  | 0 | Steel Beams | Downtown Avenue | 5867.86 | 5969.64 | Not started
C003 | Office Tower C | T609 | Steel Framework Setup | Emma White | Blocked | High | 2023-02-27 | 2023-03-07 |  | 0 | Concrete | Downtown Avenue | 46679.63 | 38971.62 | Not started
C001 | Residential Building A | T471 | Roofing | John Miller | Not Started | Low | 2024-12-16 | 2025-01-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 43669.62 | 0 | Not started
C004 | Warehouse D | T545 | Concrete Pouring | Emma White | Not Started | Medium | 2024-05-22 | 2024-06-07 |  | 0 | Concrete | Industrial Park | 38717.12 | 0 | Not started
C001 | Residential Building A | T463 | Roofing | Grace Allen | Blocked | Medium | 2024-04-28 | 2024-05-27 |  | 0 | Copper Wires | Plot 21, Riverside | 27391.55 | 24547.33 | Not started
C004 | Warehouse D | T987 | Electrical Wiring | Carlos Rivera | Completed | High | 2023-03-24 | 2023-04-09 | 2023-04-09 | 100 | Paint | Industrial Park | 48483.44 | 56960.3 | No issues
C003 | Office Tower C | T934 | Interior Painting | Sarah Johnson | Blocked | High | 2023-06-27 | 2023-07-08 |  | 0 | Paint | Downtown Avenue | 37034.22 | 34482.04 | Not started
C002 | Shopping Complex B | T191 | Interior Painting | John Miller | In Progress | Medium | 2023-12-18 | 2023-12-31 |  | 77 | Concrete | Market Street | 15436.27 | 43235.08 | In progress
C003 | Office Tower C | T887 | Plumbing Installations | Grace Allen | Not Started | Low | 2023-04-02 | 2023-04-09 |  | 0 | Steel Beams | Downtown Avenue | 16180.13 | 0 | Not started
C004 | Warehouse D | T599 | Interior Painting | Dave Brown | Blocked | Low | 2024-07-16 | 2024-08-13 |  | 0 | Concrete | Industrial Park | 48762.7 | 56203.19 | Not started
C002 | Shopping Complex B | T231 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-12-03 | 2024-12-17 |  | 0 | Concrete | Market Street | 12419.77 | 0 | Not started
C003 | Office Tower C | T330 | Electrical Wiring | Grace Allen | Completed | Low | 2024-08-23 | 2024-09-21 | 2024-09-21 | 100 | Concrete | Downtown Avenue | 40925.28 | 28224.17 | No issues
C002 | Shopping Complex B | T264 | Electrical Wiring | Dave Brown | Completed | Low | 2024-11-13 | 2024-12-03 | 2024-12-03 | 100 | PVC Pipes | Market Street | 24602.26 | 50219.26 | No issues
C004 | Warehouse D | T847 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2024-01-28 | 2024-02-09 |  | 0 | Cement | Industrial Park | 24358.03 | 27072.02 | Not started
C001 | Residential Building A | T180 | Electrical Wiring | Carlos Rivera | Not Started | High | 2023-07-15 | 2023-08-04 |  | 0 | Steel Beams | Plot 21, Riverside | 10034.65 | 0 | Not started
C002 | Shopping Complex B | T827 | Concrete Pouring | Mike Adams | In Progress | High | 2024-09-27 | 2024-10-16 |  | 55 | Roofing Sheets | Market Street | 41108.53 | 63101.68 | In progress
C001 | Residential Building A | T617 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-02-10 | 2024-02-28 |  | 0 | Rebar | Plot 21, Riverside | 12023.58 | 0 | Not started
C003 | Office Tower C | T567 | Foundation Excavation | Dave Brown | Not Started | Medium | 2023-05-20 | 2023-06-09 |  | 0 | Steel Beams | Downtown Avenue | 37825.76 | 0 | Not started
C002 | Shopping Complex B | T258 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2023-06-24 | 2023-07-21 |  | 0 | Steel Beams | Market Street | 23478.86 | 0 | Not started
C001 | Residential Building A | T601 | Steel Framework Setup | Grace Allen | Blocked | Low | 2024-01-22 | 2024-01-31 |  | 0 | Roofing Sheets | Plot 21, Riverside | 26600.84 | 26258.61 | Not started
C001 | Residential Building A | T567 | Steel Framework Setup | Sarah Johnson | Completed | Low | 2024-12-16 | 2025-01-08 | 2025-01-08 | 100 | Paint | Plot 21, Riverside | 20142.87 | 15032.76 | No issues
C004 | Warehouse D | T949 | Concrete Pouring | Emma White | Blocked | High | 2023-06-18 | 2023-07-11 |  | 0 | Concrete | Industrial Park | 41900.33 | 31407.87 | Not started
C002 | Shopping Complex B | T718 | Foundation Excavation | Mike Adams | Blocked | High | 2024-07-18 | 2024-08-17 |  | 0 | Copper Wires | Market Street | 25227.74 | 43284.88 | Not started
C003 | Office Tower C | T522 | Roofing | Rachel Green | Completed | Medium | 2024-11-07 | 2024-12-03 | 2024-12-03 | 100 | Rebar | Downtown Avenue | 43877.66 | 49537.74 | No issues
C003 | Office Tower C | T256 | Foundation Excavation | Grace Allen | In Progress | High | 2023-02-04 | 2023-03-05 |  | 63 | Roofing Sheets | Downtown Avenue | 6092.11 | 5833.2 | In progress
C001 | Residential Building A | T341 | Interior Painting | Grace Allen | In Progress | Medium | 2024-01-24 | 2024-02-06 |  | 69 | Cement | Plot 21, Riverside | 16686.97 | 19491.58 | In progress
C002 | Shopping Complex B | T909 | Electrical Wiring | Emma White | In Progress | High | 2024-01-21 | 2024-01-31 |  | 50 | Rebar | Market Street | 26997.12 | 50401.23 | In progress
C004 | Warehouse D | T967 | Site Survey | Grace Allen | Blocked | Low | 2023-01-18 | 2023-02-12 |  | 0 | Cement | Industrial Park | 18124.1 | 19414.3 | Not started
C004 | Warehouse D | T525 | Site Survey | Emma White | Blocked | Medium | 2024-06-22 | 2024-07-03 |  | 0 | PVC Pipes | Industrial Park | 10555.87 | 9259.02 | Not started
C004 | Warehouse D | T864 | Plumbing Installations | Sarah Johnson | Completed | Low | 2024-08-15 | 2024-09-13 | 2024-09-13 | 100 | Steel Beams | Industrial Park | 27013.34 | 29528.58 | No issues
C002 | Shopping Complex B | T304 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-04-01 | 2023-04-23 |  | 0 | PVC Pipes | Market Street | 15054.97 | 0 | Not started
C004 | Warehouse D | T769 | Concrete Pouring | Rachel Green | Not Started | Low | 2023-09-07 | 2023-09-26 |  | 0 | Paint | Industrial Park | 15096.23 | 0 | Not started
C003 | Office Tower C | T951 | Concrete Pouring | Grace Allen | Blocked | Medium | 2024-05-16 | 2024-05-27 |  | 0 | Rebar | Downtown Avenue | 36882.05 | 22400.52 | Not started
C004 | Warehouse D | T421 | Foundation Excavation | Emma White | Completed | Low | 2023-07-22 | 2023-08-05 | 2023-08-05 | 100 | Steel Beams | Industrial Park | 22356.86 | 20395.13 | No issues
C003 | Office Tower C | T287 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2023-03-14 | 2023-04-08 |  | 0 | Paint | Downtown Avenue | 8471.62 | 0 | Not started
C001 | Residential Building A | T920 | Interior Painting | Emma White | Blocked | High | 2023-10-26 | 2023-11-15 |  | 0 | Copper Wires | Plot 21, Riverside | 10574.4 | 9001.59 | Not started
C001 | Residential Building A | T170 | Roofing | Emma White | Completed | Medium | 2023-03-17 | 2023-04-16 | 2023-04-16 | 100 | PVC Pipes | Plot 21, Riverside | 37509.19 | 22640.99 | No issues
C002 | Shopping Complex B | T113 | Roofing | Mike Adams | Blocked | High | 2023-12-19 | 2024-01-08 |  | 0 | PVC Pipes | Market Street | 36840.04 | 50637.68 | Not started
C001 | Residential Building A | T613 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-02-01 | 2023-02-25 |  | 54 | Cement | Plot 21, Riverside | 43194.58 | 43196.98 | In progress
C004 | Warehouse D | T412 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2023-01-07 | 2023-01-22 |  | 0 | Copper Wires | Industrial Park | 46472.02 | 44082.47 | Not started
C001 | Residential Building A | T173 | Interior Painting | Carlos Rivera | Blocked | Low | 2024-10-23 | 2024-11-21 |  | 0 | Rebar | Plot 21, Riverside | 13819.24 | 13366.46 | Not started
C004 | Warehouse D | T848 | Plumbing Installations | John Miller | Blocked | High | 2024-09-19 | 2024-10-09 |  | 0 | PVC Pipes | Industrial Park | 42829.03 | 50312.23 | Not started
C002 | Shopping Complex B | T435 | Roofing | Mike Adams | Blocked | High | 2023-11-01 | 2023-11-27 |  | 0 | Steel Beams | Market Street | 5374.71 | 29295.8 | Not started
C002 | Shopping Complex B | T914 | Roofing | Mike Adams | Blocked | High | 2023-10-19 | 2023-11-05 |  | 0 | PVC Pipes | Market Street | 43497.6 | 72619.81 | Not started
C001 | Residential Building A | T987 | Electrical Wiring | John Miller | Completed | Low | 2024-03-14 | 2024-03-29 | 2024-03-29 | 100 | Copper Wires | Plot 21, Riverside | 33917.17 | 30492.75 | No issues
C003 | Office Tower C | T737 | Electrical Wiring | Dave Brown | Completed | Low | 2024-10-27 | 2024-11-10 | 2024-11-10 | 100 | Cement | Downtown Avenue | 16394.73 | 12641.51 | No issues
C003 | Office Tower C | T527 | Foundation Excavation | Mike Adams | Completed | Low | 2024-02-10 | 2024-03-03 | 2024-03-03 | 100 | Copper Wires | Downtown Avenue | 36994.5 | 29114.19 | No issues
C004 | Warehouse D | T556 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-12-22 | 2025-01-04 |  | 11 | Roofing Sheets | Industrial Park | 44825.68 | 43353.82 | In progress
C002 | Shopping Complex B | T572 | Site Survey | Carlos Rivera | Blocked | Medium | 2024-09-11 | 2024-09-26 |  | 0 | Cement | Market Street | 29552.28 | 52669.33 | Not started
C003 | Office Tower C | T724 | Plumbing Installations | Rachel Green | Completed | High | 2024-10-27 | 2024-11-21 | 2024-11-21 | 100 | Copper Wires | Downtown Avenue | 19378.78 | 14890.92 | No issues
C004 | Warehouse D | T272 | Foundation Excavation | Mike Adams | Completed | Low | 2023-02-27 | 2023-03-12 | 2023-03-12 | 100 | Steel Beams | Industrial Park | 42950.02 | 44414.93 | No issues
C004 | Warehouse D | T313 | Site Survey | Grace Allen | Blocked | Medium | 2024-11-12 | 2024-11-24 |  | 0 | Paint | Industrial Park | 11603.14 | 8604.29 | Not started
C001 | Residential Building A | T127 | Foundation Excavation | John Miller | Blocked | Low | 2024-09-27 | 2024-10-16 |  | 0 | Cement | Plot 21, Riverside | 12924.4 | 8524 | Not started
C003 | Office Tower C | T940 | Interior Painting | Dave Brown | Blocked | Low | 2024-12-09 | 2024-12-30 |  | 0 | Paint | Downtown Avenue | 37140.1 | 40960.35 | Not started
C001 | Residential Building A | T164 | Electrical Wiring | Emma White | Completed | Low | 2023-04-26 | 2023-05-17 | 2023-05-17 | 100 | Concrete | Plot 21, Riverside | 6672.25 | 7124.5 | No issues
C002 | Shopping Complex B | T456 | Electrical Wiring | Rachel Green | Not Started | Medium | 2024-09-08 | 2024-10-02 |  | 0 | Paint | Market Street | 37972.32 | 0 | Not started
C002 | Shopping Complex B | T858 | Site Survey | Mike Adams | In Progress | High | 2023-09-11 | 2023-10-04 |  | 87 | Roofing Sheets | Market Street | 46109.23 | 78114.97 | In progress
C001 | Residential Building A | T891 | Roofing | John Miller | Completed | Low | 2024-10-03 | 2024-10-11 | 2024-10-11 | 100 | Paint | Plot 21, Riverside | 49571.49 | 51882.88 | No issues
C001 | Residential Building A | T768 | Steel Framework Setup | Grace Allen | Blocked | High | 2023-06-24 | 2023-07-21 |  | 0 | Rebar | Plot 21, Riverside | 8562.41 | 6030.15 | Not started
C001 | Residential Building A | T565 | Steel Framework Setup | Dave Brown | Completed | High | 2024-01-09 | 2024-01-31 | 2024-01-31 | 100 | Roofing Sheets | Plot 21, Riverside | 41213.78 | 32222.71 | No issues
C001 | Residential Building A | T212 | Foundation Excavation | John Miller | In Progress | High | 2023-01-04 | 2023-02-03 |  | 69 | Steel Beams | Plot 21, Riverside | 43432.99 | 35143.75 | In progress
C003 | Office Tower C | T296 | Roofing | Grace Allen | Not Started | High | 2023-04-17 | 2023-05-14 |  | 0 | Concrete | Downtown Avenue | 16817.35 | 0 | Not started
C001 | Residential Building A | T271 | Foundation Excavation | Grace Allen | Blocked | High | 2023-07-15 | 2023-08-01 |  | 0 | Cement | Plot 21, Riverside | 15945.13 | 14112.84 | Not started
C001 | Residential Building A | T243 | Concrete Pouring | Rachel Green | Blocked | High | 2024-02-14 | 2024-02-29 |  | 0 | Rebar | Plot 21, Riverside | 6012.27 | 5197.37 | Not started
C004 | Warehouse D | T444 | Roofing | Carlos Rivera | Not Started | Low | 2023-01-23 | 2023-02-16 |  | 0 | Cement | Industrial Park | 49846.74 | 0 | Not started
C002 | Shopping Complex B | T356 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-12-23 | 2025-01-02 |  | 0 | Concrete | Market Street | 36712.4 | 0 | Not started
C004 | Warehouse D | T840 | Concrete Pouring | John Miller | Not Started | Low | 2023-11-27 | 2023-12-19 |  | 0 | Paint | Industrial Park | 46572.27 | 0 | Not started
C003 | Office Tower C | T840 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-07-12 | 2023-08-01 |  | 0 | Copper Wires | Downtown Avenue | 17374.69 | 19873.69 | Not started
C001 | Residential Building A | T391 | Foundation Excavation | John Miller | In Progress | Low | 2024-10-07 | 2024-10-17 |  | 53 | Roofing Sheets | Plot 21, Riverside | 44972.99 | 48410.32 | In progress
C004 | Warehouse D | T740 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-12-27 | 2025-01-04 |  | 7 | Roofing Sheets | Industrial Park | 39477.69 | 24959.98 | In progress
C001 | Residential Building A | T928 | Roofing | John Miller | Blocked | Low | 2023-04-08 | 2023-04-29 |  | 0 | Steel Beams | Plot 21, Riverside | 37194.6 | 24301 | Not started
C003 | Office Tower C | T867 | Plumbing Installations | Grace Allen | Not Started | Medium | 2023-01-05 | 2023-01-24 |  | 0 | PVC Pipes | Downtown Avenue | 47418.47 | 0 | Not started
C001 | Residential Building A | T307 | Foundation Excavation | Dave Brown | Not Started | High | 2023-03-22 | 2023-04-12 |  | 0 | Cement | Plot 21, Riverside | 49728.24 | 0 | Not started
C001 | Residential Building A | T556 | Electrical Wiring | Emma White | In Progress | Low | 2023-02-10 | 2023-03-09 |  | 10 | Roofing Sheets | Plot 21, Riverside | 38944.66 | 42823.52 | In progress
C004 | Warehouse D | T705 | Steel Framework Setup | Mike Adams | Blocked | High | 2023-10-16 | 2023-11-15 |  | 0 | PVC Pipes | Industrial Park | 47423.28 | 54174.36 | Not started
C004 | Warehouse D | T840 | Steel Framework Setup | Grace Allen | Completed | Medium | 2024-11-28 | 2024-12-12 | 2024-12-12 | 100 | PVC Pipes | Industrial Park | 36850.6 | 41668.3 | No issues
C003 | Office Tower C | T868 | Steel Framework Setup | Dave Brown | Not Started | Medium | 2024-11-09 | 2024-12-01 |  | 0 | Copper Wires | Downtown Avenue | 40001.7 | 0 | Not started
C003 | Office Tower C | T956 | Interior Painting | Emma White | Completed | Low | 2023-04-22 | 2023-05-12 | 2023-05-12 | 100 | PVC Pipes | Downtown Avenue | 39891.47 | 41490.28 | No issues
C002 | Shopping Complex B | T220 | Roofing | Emma White | Not Started | Low | 2023-11-11 | 2023-11-28 |  | 0 | Roofing Sheets | Market Street | 26758.69 | 0 | Not started
C004 | Warehouse D | T204 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-01-23 | 2024-02-06 |  | 0 | Copper Wires | Industrial Park | 10873.04 | 9913.16 | Not started
C004 | Warehouse D | T319 | Roofing | Mike Adams | Completed | Medium | 2024-04-07 | 2024-04-22 | 2024-04-22 | 100 | Rebar | Industrial Park | 47802.36 | 32877.47 | No issues
C003 | Office Tower C | T514 | Concrete Pouring | Rachel Green | In Progress | Low | 2024-03-11 | 2024-04-02 |  | 30 | Concrete | Downtown Avenue | 13601.8 | 8946.84 | In progress
C001 | Residential Building A | T782 | Concrete Pouring | Mike Adams | Blocked | High | 2024-08-21 | 2024-08-28 |  | 0 | Concrete | Plot 21, Riverside | 42542.85 | 46175.77 | Not started
C002 | Shopping Complex B | T325 | Interior Painting | Rachel Green | Completed | Low | 2023-04-28 | 2023-05-12 | 2023-05-12 | 100 | Rebar | Market Street | 29946.79 | 59915.98 | No issues
C004 | Warehouse D | T416 | Roofing | Carlos Rivera | Completed | Medium | 2024-11-13 | 2024-12-03 | 2024-12-03 | 100 | Cement | Industrial Park | 6601.16 | 7152.24 | No issues
C003 | Office Tower C | T707 | Site Survey | Emma White | Blocked | Medium | 2023-04-18 | 2023-05-08 |  | 0 | Paint | Downtown Avenue | 46288.59 | 36534 | Not started
C003 | Office Tower C | T177 | Site Survey | Emma White | Completed | High | 2023-10-22 | 2023-10-29 | 2023-10-29 | 100 | Rebar | Downtown Avenue | 26799.34 | 16340.08 | No issues
C003 | Office Tower C | T925 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-05-08 | 2023-05-24 |  | 0 | Roofing Sheets | Downtown Avenue | 26391.96 | 0 | Not started
C002 | Shopping Complex B | T860 | Electrical Wiring | John Miller | Completed | High | 2024-03-19 | 2024-04-10 | 2024-04-10 | 100 | Rebar | Market Street | 44925.82 | 57923.5 | No issues
C003 | Office Tower C | T537 | Electrical Wiring | John Miller | Blocked | Medium | 2024-12-10 | 2024-12-17 |  | 0 | Cement | Downtown Avenue | 24189.6 | 16057.67 | Not started
C002 | Shopping Complex B | T276 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2024-11-24 | 2024-12-12 |  | 0 | Steel Beams | Market Street | 47558.88 | 82477.23 | Not started
C004 | Warehouse D | T600 | Steel Framework Setup | Sarah Johnson | Blocked | High | 2024-10-08 | 2024-11-07 |  | 0 | Concrete | Industrial Park | 30455.43 | 28743.85 | Not started
C004 | Warehouse D | T602 | Interior Painting | Carlos Rivera | Completed | Low | 2023-05-18 | 2023-06-11 | 2023-06-11 | 100 | Steel Beams | Industrial Park | 23110.16 | 15149.59 | No issues
C004 | Warehouse D | T183 | Site Survey | Emma White | In Progress | Low | 2023-01-02 | 2023-01-10 |  | 7 | Copper Wires | Industrial Park | 10655.27 | 12440.26 | In progress
C001 | Residential Building A | T764 | Site Survey | Mike Adams | Blocked | Medium | 2023-05-25 | 2023-06-05 |  | 0 | Paint | Plot 21, Riverside | 42784.25 | 49526.88 | Not started
C001 | Residential Building A | T932 | Concrete Pouring | Dave Brown | Not Started | High | 2024-07-05 | 2024-07-13 |  | 0 | Steel Beams | Plot 21, Riverside | 15757.2 | 0 | Not started
C001 | Residential Building A | T741 | Plumbing Installations | Mike Adams | Completed | High | 2024-11-24 | 2024-12-07 | 2024-12-07 | 100 | Copper Wires | Plot 21, Riverside | 41610.25 | 38782.99 | No issues
C004 | Warehouse D | T362 | Interior Painting | Emma White | Completed | High | 2023-01-21 | 2023-01-31 | 2023-01-31 | 100 | Roofing Sheets | Industrial Park | 7360.16 | 6687.68 | No issues
C001 | Residential Building A | T786 | Electrical Wiring | John Miller | Not Started | Low | 2023-01-01 | 2023-01-13 |  | 0 | PVC Pipes | Plot 21, Riverside | 45412.97 | 0 | Not started
C004 | Warehouse D | T980 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-09-11 | 2024-10-09 |  | 0 | PVC Pipes | Industrial Park | 42427.61 | 47118.3 | Not started
C003 | Office Tower C | T392 | Electrical Wiring | Grace Allen | Blocked | Medium | 2024-08-10 | 2024-08-27 |  | 0 | PVC Pipes | Downtown Avenue | 32512.18 | 25744.13 | Not started
C001 | Residential Building A | T215 | Interior Painting | Sarah Johnson | In Progress | Medium | 2024-11-05 | 2024-11-12 |  | 94 | Concrete | Plot 21, Riverside | 12041.94 | 13326.8 | In progress
C003 | Office Tower C | T388 | Site Survey | Rachel Green | Not Started | High | 2023-01-18 | 2023-02-11 |  | 0 | Paint | Downtown Avenue | 38593.53 | 0 | Not started
C003 | Office Tower C | T438 | Plumbing Installations | Grace Allen | Completed | High | 2024-08-01 | 2024-08-24 | 2024-08-24 | 100 | PVC Pipes | Downtown Avenue | 28814.06 | 33022.73 | No issues
C004 | Warehouse D | T517 | Roofing | Grace Allen | In Progress | Medium | 2023-10-22 | 2023-11-17 |  | 39 | Concrete | Industrial Park | 47397.41 | 46360.43 | In progress
C002 | Shopping Complex B | T978 | Plumbing Installations | Grace Allen | Completed | High | 2023-08-03 | 2023-08-13 | 2023-08-13 | 100 | Steel Beams | Market Street | 49041.21 | 69013.58 | No issues
C001 | Residential Building A | T416 | Roofing | John Miller | Blocked | High | 2024-08-17 | 2024-08-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 16639.95 | 18830.69 | Not started
C003 | Office Tower C | T211 | Site Survey | Grace Allen | Blocked | High | 2023-07-03 | 2023-07-24 |  | 0 | Copper Wires | Downtown Avenue | 25132.99 | 17449.01 | Not started
C001 | Residential Building A | T325 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-06-28 | 2024-07-09 |  | 0 | Rebar | Plot 21, Riverside | 29698.19 | 0 | Not started
C003 | Office Tower C | T350 | Concrete Pouring | Mike Adams | Completed | High | 2023-12-25 | 2024-01-06 | 2024-01-06 | 100 | Roofing Sheets | Downtown Avenue | 32728.8 | 35381.79 | No issues
C004 | Warehouse D | T474 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-02-23 | 2023-03-10 |  | 0 | Copper Wires | Industrial Park | 37533.46 | 42041.57 | Not started
C002 | Shopping Complex B | T418 | Steel Framework Setup | John Miller | In Progress | High | 2024-07-21 | 2024-08-05 |  | 30 | Cement | Market Street | 29658.12 | 56759.55 | In progress
C004 | Warehouse D | T437 | Interior Painting | John Miller | Blocked | Medium | 2024-10-28 | 2024-11-19 |  | 0 | Concrete | Industrial Park | 42005.46 | 27469.94 | Not started
C001 | Residential Building A | T552 | Foundation Excavation | John Miller | In Progress | High | 2023-01-07 | 2023-02-06 |  | 18 | Roofing Sheets | Plot 21, Riverside | 22240.78 | 20875.2 | In progress
C003 | Office Tower C | T165 | Concrete Pouring | Dave Brown | Completed | Low | 2023-08-25 | 2023-09-21 | 2023-09-21 | 100 | Copper Wires | Downtown Avenue | 17071.58 | 15531.93 | No issues
C002 | Shopping Complex B | T714 | Foundation Excavation | Mike Adams | Completed | High | 2023-06-20 | 2023-07-09 | 2023-07-09 | 100 | Rebar | Market Street | 15954.25 | 42028.48 | No issues
C004 | Warehouse D | T281 | Site Survey | Mike Adams | In Progress | Low | 2023-08-20 | 2023-09-06 |  | 7 | Roofing Sheets | Industrial Park | 33232.09 | 21482.31 | In progress
C002 | Shopping Complex B | T156 | Roofing | Grace Allen | Not Started | Medium | 2023-01-22 | 2023-02-04 |  | 0 | Roofing Sheets | Market Street | 33915.59 | 0 | Not started
C003 | Office Tower C | T893 | Foundation Excavation | Rachel Green | In Progress | High | 2024-07-05 | 2024-07-31 |  | 9 | Cement | Downtown Avenue | 39529.27 | 35183.28 | In progress
C001 | Residential Building A | T518 | Roofing | Mike Adams | Not Started | Medium | 2023-04-01 | 2023-04-13 |  | 0 | Rebar | Plot 21, Riverside | 30799.38 | 0 | Not started
C004 | Warehouse D | T153 | Roofing | Emma White | Blocked | Low | 2023-03-06 | 2023-03-21 |  | 0 | Steel Beams | Industrial Park | 39793.37 | 31086.81 | Not started
C001 | Residential Building A | T504 | Electrical Wiring | Dave Brown | In Progress | High | 2024-07-26 | 2024-08-19 |  | 37 | PVC Pipes | Plot 21, Riverside | 9057.5 | 8099.28 | In progress
C002 | Shopping Complex B | T471 | Interior Painting | Emma White | Completed | Low | 2023-07-20 | 2023-08-01 | 2023-08-01 | 100 | Steel Beams | Market Street | 38293.01 | 48839.01 | No issues
C002 | Shopping Complex B | T631 | Concrete Pouring | John Miller | Completed | High | 2024-10-17 | 2024-10-31 | 2024-10-31 | 100 | Cement | Market Street | 16451.3 | 39278.69 | No issues
C003 | Office Tower C | T367 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2024-02-23 | 2024-03-03 |  | 0 | Steel Beams | Downtown Avenue | 33543.3 | 0 | Not started
C001 | Residential Building A | T508 | Electrical Wiring | Grace Allen | Completed | High | 2024-09-20 | 2024-09-30 | 2024-09-30 | 100 | PVC Pipes | Plot 21, Riverside | 6088.6 | 3876.63 | No issues
C002 | Shopping Complex B | T782 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2024-07-02 | 2024-07-19 |  | 23 | Copper Wires | Market Street | 13313.22 | 37284.92 | In progress
C002 | Shopping Complex B | T709 | Site Survey | Sarah Johnson | In Progress | High | 2024-02-03 | 2024-02-24 |  | 65 | Steel Beams | Market Street | 26615.77 | 48936.94 | In progress
C002 | Shopping Complex B | T405 | Plumbing Installations | Emma White | Completed | Medium | 2023-05-18 | 2023-06-08 | 2023-06-08 | 100 | Steel Beams | Market Street | 31975.78 | 60653.59 | No issues
C003 | Office Tower C | T357 | Foundation Excavation | Dave Brown | Completed | Medium | 2024-10-05 | 2024-10-12 | 2024-10-12 | 100 | Rebar | Downtown Avenue | 31623.99 | 24551.08 | No issues
C002 | Shopping Complex B | T302 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-08-13 | 2024-08-22 |  | 0 | Roofing Sheets | Market Street | 25956.13 | 53665.7 | Not started
C001 | Residential Building A | T718 | Concrete Pouring | Rachel Green | Completed | Medium | 2024-05-08 | 2024-05-15 | 2024-05-15 | 100 | Copper Wires | Plot 21, Riverside | 12890.29 | 14212.98 | No issues
C003 | Office Tower C | T568 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2023-07-10 | 2023-07-17 |  | 0 | Steel Beams | Downtown Avenue | 8505.67 | 0 | Not started
C001 | Residential Building A | T943 | Plumbing Installations | Dave Brown | Not Started | Low | 2024-12-11 | 2024-12-22 |  | 0 | Copper Wires | Plot 21, Riverside | 27110.86 | 0 | Not started
C004 | Warehouse D | T373 | Site Survey | John Miller | In Progress | Low | 2023-08-13 | 2023-09-05 |  | 47 | Concrete | Industrial Park | 14910.31 | 10337.45 | In progress
C004 | Warehouse D | T151 | Foundation Excavation | Emma White | Completed | Medium | 2024-03-27 | 2024-04-12 | 2024-04-12 | 100 | Steel Beams | Industrial Park | 27394.3 | 28252.98 | No issues
C003 | Office Tower C | T184 | Site Survey | Sarah Johnson | Blocked | Medium | 2024-10-28 | 2024-11-10 |  | 0 | Copper Wires | Downtown Avenue | 11835.17 | 8015.56 | Not started
C002 | Shopping Complex B | T455 | Plumbing Installations | John Miller | Completed | High | 2024-06-18 | 2024-07-07 | 2024-07-07 | 100 | PVC Pipes | Market Street | 42936.26 | 55670.83 | No issues
C002 | Shopping Complex B | T144 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-06-17 | 2024-06-30 |  | 0 | Cement | Market Street | 20925.47 | 39057.94 | Not started
C001 | Residential Building A | T894 | Concrete Pouring | Mike Adams | Blocked | Low | 2023-08-14 | 2023-09-10 |  | 0 | PVC Pipes | Plot 21, Riverside | 29543.68 | 21255.1 | Not started
C003 | Office Tower C | T408 | Interior Painting | John Miller | Blocked | High | 2023-10-20 | 2023-10-31 |  | 0 | Steel Beams | Downtown Avenue | 5737.3 | 3673.07 | Not started
C003 | Office Tower C | T763 | Foundation Excavation | Sarah Johnson | Completed | High | 2024-07-08 | 2024-07-18 | 2024-07-18 | 100 | Copper Wires | Downtown Avenue | 45435.04 | 49097.55 | No issues
C001 | Residential Building A | T771 | Electrical Wiring | Dave Brown | Completed | High | 2024-07-25 | 2024-08-09 | 2024-08-09 | 100 | Steel Beams | Plot 21, Riverside | 16410.37 | 19029.38 | No issues
C004 | Warehouse D | T741 | Plumbing Installations | Mike Adams | Not Started | High | 2023-10-16 | 2023-11-15 |  | 0 | Rebar | Industrial Park | 35783.19 | 0 | Not started
C002 | Shopping Complex B | T730 | Plumbing Installations | Emma White | Blocked | Low | 2024-08-20 | 2024-09-11 |  | 0 | Rebar | Market Street | 8462.07 | 35275.52 | Not started
C003 | Office Tower C | T678 | Site Survey | Sarah Johnson | Completed | Low | 2024-04-15 | 2024-05-05 | 2024-05-05 | 100 | Paint | Downtown Avenue | 8329.53 | 7051.77 | No issues
C004 | Warehouse D | T380 | Site Survey | Carlos Rivera | Completed | Low | 2023-10-11 | 2023-11-09 | 2023-11-09 | 100 | Steel Beams | Industrial Park | 7217.73 | 7157.08 | No issues
C003 | Office Tower C | T143 | Interior Painting | Emma White | In Progress | Medium | 2024-11-09 | 2024-12-04 |  | 85 | Rebar | Downtown Avenue | 20461.45 | 24169.75 | In progress
C001 | Residential Building A | T744 | Interior Painting | Emma White | In Progress | High | 2024-02-17 | 2024-02-26 |  | 4 | Paint | Plot 21, Riverside | 12112.72 | 9105.9 | In progress
C001 | Residential Building A | T300 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-06-23 | 2023-07-11 |  | 0 | Rebar | Plot 21, Riverside | 8295.5 | 0 | Not started
C001 | Residential Building A | T194 | Roofing | Dave Brown | Completed | Low | 2024-03-13 | 2024-03-25 | 2024-03-25 | 100 | Copper Wires | Plot 21, Riverside | 35547.14 | 39594.53 | No issues
C001 | Residential Building A | T663 | Concrete Pouring | Emma White | In Progress | Medium | 2023-12-05 | 2023-12-29 |  | 44 | Steel Beams | Plot 21, Riverside | 8776.67 | 8303.32 | In progress
C002 | Shopping Complex B | T836 | Interior Painting | Carlos Rivera | Not Started | Medium | 2023-01-17 | 2023-02-13 |  | 0 | Steel Beams | Market Street | 38395.21 | 0 | Not started
C003 | Office Tower C | T851 | Roofing | Rachel Green | Blocked | High | 2024-09-27 | 2024-10-07 |  | 0 | PVC Pipes | Downtown Avenue | 16605.33 | 10981.76 | Not started
C001 | Residential Building A | T712 | Interior Painting | Mike Adams | Completed | Low | 2023-03-10 | 2023-04-09 | 2023-04-09 | 100 | Roofing Sheets | Plot 21, Riverside | 9411.6 | 10751.95 | No issues
C003 | Office Tower C | T973 | Plumbing Installations | Mike Adams | Blocked | Medium | 2023-11-09 | 2023-11-30 |  | 0 | Paint | Downtown Avenue | 43842.36 | 52576.77 | Not started
C003 | Office Tower C | T663 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2023-11-06 | 2023-12-03 |  | 0 | Concrete | Downtown Avenue | 6012.06 | 6500.25 | Not started
C001 | Residential Building A | T588 | Concrete Pouring | John Miller | Blocked | High | 2023-01-07 | 2023-01-15 |  | 0 | Paint | Plot 21, Riverside | 33251.06 | 33606.23 | Not started
C003 | Office Tower C | T535 | Concrete Pouring | John Miller | In Progress | Medium | 2024-05-23 | 2024-06-07 |  | 41 | Cement | Downtown Avenue | 45406.98 | 28638.56 | In progress
C002 | Shopping Complex B | T652 | Roofing | Dave Brown | In Progress | Medium | 2023-08-08 | 2023-09-06 |  | 19 | Concrete | Market Street | 18614.3 | 39463.89 | In progress
C002 | Shopping Complex B | T981 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-12-07 | 2023-12-29 |  | 78 | Cement | Market Street | 27468.6 | 56691.53 | In progress
C004 | Warehouse D | T160 | Roofing | Sarah Johnson | Completed | Medium | 2024-04-07 | 2024-05-04 | 2024-05-04 | 100 | Rebar | Industrial Park | 45222.67 | 34612.12 | No issues
C001 | Residential Building A | T698 | Site Survey | Rachel Green | Blocked | Low | 2024-01-27 | 2024-02-16 |  | 0 | Copper Wires | Plot 21, Riverside | 48060.91 | 53122.27 | Not started
C004 | Warehouse D | T455 | Electrical Wiring | Dave Brown | In Progress | Low | 2023-07-28 | 2023-08-19 |  | 19 | Copper Wires | Industrial Park | 5990.26 | 4038.93 | In progress
C002 | Shopping Complex B | T162 | Steel Framework Setup | Dave Brown | Completed | Medium | 2023-03-26 | 2023-04-12 | 2023-04-12 | 100 | Rebar | Market Street | 12770.43 | 34617.42 | No issues
C004 | Warehouse D | T134 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2024-03-18 | 2024-04-15 |  | 57 | Rebar | Industrial Park | 19555.57 | 12772.31 | In progress
C003 | Office Tower C | T632 | Concrete Pouring | Grace Allen | Not Started | High | 2023-10-21 | 2023-11-01 |  | 0 | Paint | Downtown Avenue | 28031.13 | 0 | Not started
C002 | Shopping Complex B | T301 | Roofing | Emma White | Blocked | High | 2024-06-04 | 2024-07-01 |  | 0 | Paint | Market Street | 30643.36 | 54892.01 | Not started
C002 | Shopping Complex B | T116 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-06-26 | 2023-07-08 |  | 10 | Cement | Market Street | 38363.72 | 57565.74 | In progress
C002 | Shopping Complex B | T625 | Site Survey | Carlos Rivera | Completed | Low | 2023-08-04 | 2023-08-23 | 2023-08-23 | 100 | Roofing Sheets | Market Street | 39635.65 | 69856.46 | No issues
C001 | Residential Building A | T294 | Roofing | Mike Adams | Not Started | High | 2023-01-17 | 2023-01-28 |  | 0 | Cement | Plot 21, Riverside | 30704.65 | 0 | Not started
C001 | Residential Building A | T251 | Foundation Excavation | Emma White | Not Started | High | 2023-08-06 | 2023-09-02 |  | 0 | Rebar | Plot 21, Riverside | 26752.12 | 0 | Not started
C001 | Residential Building A | T889 | Site Survey | Emma White | Blocked | Low | 2023-08-16 | 2023-09-14 |  | 0 | PVC Pipes | Plot 21, Riverside | 24937.28 | 23158.47 | Not started
C003 | Office Tower C | T781 | Plumbing Installations | Rachel Green | Completed | High | 2024-04-28 | 2024-05-13 | 2024-05-13 | 100 | Rebar | Downtown Avenue | 35735.93 | 40776.2 | No issues
C001 | Residential Building A | T712 | Electrical Wiring | Grace Allen | Not Started | Medium | 2024-11-15 | 2024-12-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 25197.48 | 0 | Not started
C001 | Residential Building A | T357 | Interior Painting | Rachel Green | Not Started | High | 2024-01-08 | 2024-01-24 |  | 0 | Concrete | Plot 21, Riverside | 37386.04 | 0 | Not started
C001 | Residential Building A | T963 | Site Survey | Mike Adams | Blocked | Low | 2023-10-06 | 2023-10-27 |  | 0 | Rebar | Plot 21, Riverside | 13006.33 | 13137.83 | Not started
C003 | Office Tower C | T696 | Concrete Pouring | Rachel Green | Not Started | Low | 2024-10-07 | 2024-10-20 |  | 0 | PVC Pipes | Downtown Avenue | 26866.38 | 0 | Not started
C004 | Warehouse D | T325 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-06-28 | 2024-07-25 |  | 0 | Copper Wires | Industrial Park | 30811.38 | 0 | Not started
C003 | Office Tower C | T954 | Interior Painting | Rachel Green | In Progress | Medium | 2024-12-14 | 2025-01-04 |  | 11 | Steel Beams | Downtown Avenue | 6901.13 | 4300.9 | In progress
C001 | Residential Building A | T551 | Foundation Excavation | Grace Allen | Not Started | Medium | 2023-07-21 | 2023-08-08 |  | 0 | Rebar | Plot 21, Riverside | 32381.89 | 0 | Not started
C004 | Warehouse D | T601 | Electrical Wiring | Emma White | Not Started | Low | 2024-04-14 | 2024-05-11 |  | 0 | Rebar | Industrial Park | 22316.15 | 0 | Not started
C002 | Shopping Complex B | T187 | Foundation Excavation | Sarah Johnson | Not Started | High | 2024-11-02 | 2024-12-02 |  | 0 | Steel Beams | Market Street | 14418.1 | 0 | Not started
C002 | Shopping Complex B | T298 | Plumbing Installations | Grace Allen | Not Started | Medium | 2024-06-22 | 2024-07-10 |  | 0 | Roofing Sheets | Market Street | 45707.14 | 0 | Not started
C004 | Warehouse D | T110 | Interior Painting | Rachel Green | Blocked | High | 2023-09-05 | 2023-09-30 |  | 0 | Copper Wires | Industrial Park | 37149.68 | 42204.48 | Not started
C001 | Residential Building A | T822 | Foundation Excavation | Mike Adams | Blocked | High | 2024-02-20 | 2024-03-04 |  | 0 | Paint | Plot 21, Riverside | 49263.91 | 41164.56 | Not started
C004 | Warehouse D | T279 | Electrical Wiring | Rachel Green | In Progress | High | 2023-06-18 | 2023-07-06 |  | 30 | Copper Wires | Industrial Park | 45509.26 | 37865.8 | In progress
C003 | Office Tower C | T354 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-02-21 | 2024-03-03 |  | 0 | Rebar | Downtown Avenue | 27446.08 | 0 | Not started
C002 | Shopping Complex B | T985 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2023-04-28 | 2023-05-20 |  | 10 | Cement | Market Street | 31964.77 | 46596.78 | In progress
C004 | Warehouse D | T539 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-08-13 | 2023-08-23 |  | 0 | Rebar | Industrial Park | 34162.36 | 0 | Not started
C004 | Warehouse D | T250 | Steel Framework Setup | Emma White | Not Started | High | 2024-12-27 | 2025-01-21 |  | 0 | Paint | Industrial Park | 32048.69 | 0 | Not started
C001 | Residential Building A | T540 | Electrical Wiring | Emma White | In Progress | High | 2023-06-21 | 2023-07-09 |  | 14 | Rebar | Plot 21, Riverside | 28861.01 | 31179.18 | In progress
C001 | Residential Building A | T317 | Roofing | Grace Allen | Blocked | High | 2023-02-05 | 2023-02-23 |  | 0 | Paint | Plot 21, Riverside | 31017.07 | 23282.79 | Not started
C003 | Office Tower C | T113 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2023-06-20 | 2023-07-06 |  | 75 | Rebar | Downtown Avenue | 12823.29 | 12616.2 | In progress
C003 | Office Tower C | T649 | Site Survey | Rachel Green | Blocked | Medium | 2023-12-21 | 2024-01-16 |  | 0 | Roofing Sheets | Downtown Avenue | 43539.22 | 32280.88 | Not started
C001 | Residential Building A | T344 | Electrical Wiring | Mike Adams | Not Started | High | 2023-11-17 | 2023-12-09 |  | 0 | Roofing Sheets | Plot 21, Riverside | 47456.91 | 0 | Not started
C002 | Shopping Complex B | T354 | Plumbing Installations | Mike Adams | Not Started | High | 2024-10-14 | 2024-11-11 |  | 0 | Rebar | Market Street | 23281.02 | 0 | Not started
C003 | Office Tower C | T586 | Site Survey | John Miller | Not Started | Medium | 2024-08-02 | 2024-08-26 |  | 0 | Copper Wires | Downtown Avenue | 43506.79 | 0 | Not started
C003 | Office Tower C | T229 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-12-06 | 2025-01-02 |  | 0 | Copper Wires | Downtown Avenue | 29064.58 | 29417.62 | Not started
C002 | Shopping Complex B | T368 | Roofing | Rachel Green | In Progress | High | 2024-10-14 | 2024-10-24 |  | 78 | Steel Beams | Market Street | 30505.02 | 48635.16 | In progress
C002 | Shopping Complex B | T754 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2023-08-10 | 2023-09-05 |  | 59 | Copper Wires | Market Street | 46114.43 | 72534.16 | In progress
C002 | Shopping Complex B | T368 | Steel Framework Setup | John Miller | In Progress | Low | 2023-03-18 | 2023-03-29 |  | 43 | Rebar | Market Street | 47019.5 | 81707.31 | In progress
C003 | Office Tower C | T713 | Site Survey | John Miller | In Progress | Low | 2024-09-24 | 2024-10-17 |  | 22 | Steel Beams | Downtown Avenue | 32134.23 | 22240.51 | In progress
C002 | Shopping Complex B | T491 | Foundation Excavation | Dave Brown | In Progress | Medium | 2024-01-20 | 2024-02-04 |  | 80 | Roofing Sheets | Market Street | 39352.72 | 67994.01 | In progress
C004 | Warehouse D | T652 | Plumbing Installations | Carlos Rivera | Not Started | High | 2024-12-16 | 2025-01-08 |  | 0 | Cement | Industrial Park | 25657.07 | 0 | Not started
C001 | Residential Building A | T334 | Site Survey | John Miller | Blocked | Low | 2023-04-27 | 2023-05-12 |  | 0 | Roofing Sheets | Plot 21, Riverside | 36514.19 | 29305.37 | Not started
C002 | Shopping Complex B | T130 | Roofing | Grace Allen | Not Started | Low | 2023-04-04 | 2023-05-04 |  | 0 | Cement | Market Street | 36951.79 | 0 | Not started
C003 | Office Tower C | T206 | Roofing | Emma White | Blocked | High | 2024-01-28 | 2024-02-09 |  | 0 | PVC Pipes | Downtown Avenue | 5305.78 | 4769.79 | Not started
C002 | Shopping Complex B | T586 | Site Survey | Sarah Johnson | Blocked | Low | 2023-03-26 | 2023-04-03 |  | 0 | Rebar | Market Street | 20115.24 | 49174.97 | Not started
C004 | Warehouse D | T841 | Concrete Pouring | Dave Brown | In Progress | High | 2023-08-06 | 2023-08-23 |  | 66 | Cement | Industrial Park | 32805.79 | 33673.09 | In progress
C001 | Residential Building A | T919 | Concrete Pouring | Grace Allen | Completed | High | 2023-03-20 | 2023-04-16 | 2023-04-16 | 100 | Rebar | Plot 21, Riverside | 24653.06 | 29087.74 | No issues
C003 | Office Tower C | T400 | Foundation Excavation | Dave Brown | Completed | High | 2023-03-19 | 2023-04-16 | 2023-04-16 | 100 | Steel Beams | Downtown Avenue | 38758.54 | 29552.99 | No issues
C002 | Shopping Complex B | T209 | Site Survey | Grace Allen | Blocked | Medium | 2023-02-17 | 2023-03-17 |  | 0 | Steel Beams | Market Street | 49916.9 | 74638.73 | Not started
C003 | Office Tower C | T513 | Interior Painting | John Miller | Completed | Medium | 2024-06-24 | 2024-07-17 | 2024-07-17 | 100 | Rebar | Downtown Avenue | 24894.54 | 18986.85 | No issues
C001 | Residential Building A | T373 | Foundation Excavation | Mike Adams | Completed | Low | 2023-11-24 | 2023-12-21 | 2023-12-21 | 100 | Copper Wires | Plot 21, Riverside | 42565.22 | 29322.87 | No issues
C004 | Warehouse D | T127 | Steel Framework Setup | John Miller | In Progress | High | 2023-03-07 | 2023-03-15 |  | 35 | Roofing Sheets | Industrial Park | 35742.79 | 27057.47 | In progress
C002 | Shopping Complex B | T544 | Foundation Excavation | Emma White | In Progress | Low | 2023-01-25 | 2023-02-09 |  | 26 | PVC Pipes | Market Street | 26638.45 | 48388.16 | In progress
C001 | Residential Building A | T126 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-05-19 | 2024-06-14 | 2024-06-14 | 100 | Roofing Sheets | Plot 21, Riverside | 30404.85 | 28359.5 | No issues
C001 | Residential Building A | T975 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2023-05-04 | 2023-05-13 | 2023-05-13 | 100 | Concrete | Plot 21, Riverside | 49398.49 | 38244.6 | No issues
C004 | Warehouse D | T889 | Steel Framework Setup | Emma White | Completed | Medium | 2023-03-02 | 2023-03-12 | 2023-03-12 | 100 | Steel Beams | Industrial Park | 38145.04 | 32772.44 | No issues
C001 | Residential Building A | T887 | Interior Painting | Dave Brown | Completed | Medium | 2024-09-20 | 2024-10-06 | 2024-10-06 | 100 | Copper Wires | Plot 21, Riverside | 14006.82 | 8539.3 | No issues
C003 | Office Tower C | T756 | Electrical Wiring | Rachel Green | Blocked | Low | 2023-07-19 | 2023-08-16 |  | 0 | Steel Beams | Downtown Avenue | 25491.07 | 16598.62 | Not started
C002 | Shopping Complex B | T134 | Site Survey | Mike Adams | Blocked | Medium | 2023-05-19 | 2023-05-26 |  | 0 | PVC Pipes | Market Street | 30198.98 | 58565.18 | Not started
C003 | Office Tower C | T586 | Plumbing Installations | Rachel Green | Not Started | High | 2023-03-17 | 2023-03-24 |  | 0 | Concrete | Downtown Avenue | 9315.24 | 0 | Not started
C004 | Warehouse D | T535 | Electrical Wiring | John Miller | Blocked | Low | 2023-05-16 | 2023-06-13 |  | 0 | PVC Pipes | Industrial Park | 16306.7 | 14997.25 | Not started
C003 | Office Tower C | T816 | Concrete Pouring | Grace Allen | Completed | Medium | 2023-04-20 | 2023-04-27 | 2023-04-27 | 100 | Paint | Downtown Avenue | 28594.57 | 34306.08 | No issues
C001 | Residential Building A | T552 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-09-13 | 2024-09-25 |  | 0 | PVC Pipes | Plot 21, Riverside | 20767.06 | 24776.39 | Not started
C002 | Shopping Complex B | T656 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-12-03 | 2025-01-01 |  | 0 | Paint | Market Street | 22474.5 | 49739.86 | Not started
C002 | Shopping Complex B | T759 | Foundation Excavation | Grace Allen | Blocked | High | 2024-04-23 | 2024-05-10 |  | 0 | Rebar | Market Street | 6689.59 | 33231.71 | Not started
C003 | Office Tower C | T734 | Electrical Wiring | Emma White | Not Started | Low | 2024-05-21 | 2024-06-20 |  | 0 | Copper Wires | Downtown Avenue | 19683.84 | 0 | Not started
C003 | Office Tower C | T986 | Plumbing Installations | Grace Allen | Not Started | Medium | 2024-07-08 | 2024-08-01 |  | 0 | Rebar | Downtown Avenue | 26443.04 | 0 | Not started
C002 | Shopping Complex B | T784 | Interior Painting | Emma White | In Progress | Low | 2024-09-06 | 2024-09-19 |  | 97 | Roofing Sheets | Market Street | 5723.93 | 29750.37 | In progress
C003 | Office Tower C | T155 | Interior Painting | Carlos Rivera | Completed | Medium | 2024-04-19 | 2024-04-29 | 2024-04-29 | 100 | Copper Wires | Downtown Avenue | 38601.48 | 45146.82 | No issues
C003 | Office Tower C | T400 | Interior Painting | Emma White | Not Started | Low | 2023-11-28 | 2023-12-16 |  | 0 | Roofing Sheets | Downtown Avenue | 34726.75 | 0 | Not started
C001 | Residential Building A | T828 | Plumbing Installations | Emma White | Completed | High | 2024-03-22 | 2024-04-06 | 2024-04-06 | 100 | Concrete | Plot 21, Riverside | 13691.6 | 16281.26 | No issues
C002 | Shopping Complex B | T722 | Roofing | Mike Adams | Not Started | Low | 2024-05-28 | 2024-06-11 |  | 0 | Steel Beams | Market Street | 15979.74 | 0 | Not started
C003 | Office Tower C | T768 | Site Survey | Carlos Rivera | Not Started | Medium | 2023-12-23 | 2024-01-02 |  | 0 | Roofing Sheets | Downtown Avenue | 48235.97 | 0 | Not started
C002 | Shopping Complex B | T107 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-06-07 | 2024-06-29 |  | 0 | Steel Beams | Market Street | 40150.76 | 0 | Not started
C001 | Residential Building A | T693 | Concrete Pouring | Rachel Green | Blocked | Medium | 2023-07-21 | 2023-08-15 |  | 0 | Concrete | Plot 21, Riverside | 25570.9 | 20511.32 | Not started
C001 | Residential Building A | T524 | Roofing | John Miller | Not Started | High | 2024-11-24 | 2024-12-24 |  | 0 | Paint | Plot 21, Riverside | 12103.32 | 0 | Not started
C002 | Shopping Complex B | T497 | Site Survey | Rachel Green | In Progress | Medium | 2023-09-02 | 2023-09-19 |  | 36 | Cement | Market Street | 42058.14 | 54229.18 | In progress
C001 | Residential Building A | T459 | Electrical Wiring | Emma White | Completed | Medium | 2023-07-11 | 2023-08-09 | 2023-08-09 | 100 | Rebar | Plot 21, Riverside | 30367.05 | 24214.01 | No issues
C004 | Warehouse D | T976 | Foundation Excavation | Grace Allen | In Progress | High | 2023-10-05 | 2023-10-17 |  | 67 | Rebar | Industrial Park | 45821.03 | 32025.03 | In progress
C001 | Residential Building A | T701 | Concrete Pouring | John Miller | Blocked | High | 2023-04-16 | 2023-04-29 |  | 0 | Copper Wires | Plot 21, Riverside | 33994.21 | 38877.28 | Not started
C004 | Warehouse D | T829 | Foundation Excavation | Mike Adams | Not Started | Low | 2023-01-25 | 2023-02-05 |  | 0 | Concrete | Industrial Park | 29014.61 | 0 | Not started
C002 | Shopping Complex B | T437 | Site Survey | Sarah Johnson | Not Started | High | 2023-06-28 | 2023-07-10 |  | 0 | Roofing Sheets | Market Street | 18790.49 | 0 | Not started
C001 | Residential Building A | T474 | Site Survey | Rachel Green | Blocked | Medium | 2023-12-18 | 2024-01-08 |  | 0 | Concrete | Plot 21, Riverside | 5837.19 | 5593.04 | Not started
C001 | Residential Building A | T844 | Plumbing Installations | Emma White | Not Started | High | 2023-12-23 | 2024-01-21 |  | 0 | Rebar | Plot 21, Riverside | 35895.1 | 0 | Not started
C004 | Warehouse D | T342 | Interior Painting | Emma White | Not Started | High | 2024-02-09 | 2024-02-28 |  | 0 | Cement | Industrial Park | 24864.55 | 0 | Not started
C001 | Residential Building A | T371 | Electrical Wiring | Mike Adams | Blocked | High | 2024-05-04 | 2024-05-25 |  | 0 | Paint | Plot 21, Riverside | 5659.23 | 5758.72 | Not started
C002 | Shopping Complex B | T315 | Steel Framework Setup | Grace Allen | In Progress | High | 2023-05-03 | 2023-05-15 |  | 90 | Roofing Sheets | Market Street | 45159.94 | 72576.6 | In progress
C002 | Shopping Complex B | T690 | Electrical Wiring | John Miller | Blocked | Low | 2023-08-14 | 2023-08-24 |  | 0 | PVC Pipes | Market Street | 26736.69 | 49616.44 | Not started
C001 | Residential Building A | T460 | Interior Painting | Dave Brown | In Progress | Low | 2023-08-04 | 2023-08-26 |  | 78 | Rebar | Plot 21, Riverside | 30284.41 | 23762.62 | In progress
C001 | Residential Building A | T763 | Interior Painting | John Miller | Not Started | Medium | 2023-03-03 | 2023-03-28 |  | 0 | Rebar | Plot 21, Riverside | 40632.63 | 0 | Not started
C003 | Office Tower C | T394 | Site Survey | Emma White | Completed | Low | 2023-12-17 | 2024-01-11 | 2024-01-11 | 100 | Roofing Sheets | Downtown Avenue | 21677.06 | 21839.44 | No issues
C002 | Shopping Complex B | T515 | Steel Framework Setup | John Miller | Completed | Medium | 2023-11-10 | 2023-11-29 | 2023-11-29 | 100 | Rebar | Market Street | 14063.77 | 35081.76 | No issues
C004 | Warehouse D | T645 | Foundation Excavation | Grace Allen | Not Started | Medium | 2024-03-12 | 2024-04-01 |  | 0 | Rebar | Industrial Park | 18431.98 | 0 | Not started
C002 | Shopping Complex B | T811 | Foundation Excavation | Mike Adams | In Progress | Medium | 2024-12-25 | 2025-01-18 |  | 27 | Concrete | Market Street | 21108.36 | 46885.42 | In progress
C001 | Residential Building A | T952 | Electrical Wiring | Rachel Green | Completed | Low | 2024-03-01 | 2024-03-27 | 2024-03-27 | 100 | Copper Wires | Plot 21, Riverside | 26824.27 | 18217.32 | No issues
C001 | Residential Building A | T612 | Interior Painting | Mike Adams | Not Started | High | 2024-09-23 | 2024-10-22 |  | 0 | Roofing Sheets | Plot 21, Riverside | 38841.46 | 0 | Not started
C001 | Residential Building A | T148 | Electrical Wiring | Emma White | Completed | Low | 2023-11-06 | 2023-11-18 | 2023-11-18 | 100 | Steel Beams | Plot 21, Riverside | 11821.32 | 8042.08 | No issues
C002 | Shopping Complex B | T433 | Site Survey | Rachel Green | Completed | Medium | 2023-09-22 | 2023-10-15 | 2023-10-15 | 100 | PVC Pipes | Market Street | 39670.47 | 69465.97 | No issues
C002 | Shopping Complex B | T399 | Interior Painting | Sarah Johnson | Blocked | Low | 2024-11-19 | 2024-12-01 |  | 0 | Concrete | Market Street | 26398.78 | 47025.59 | Not started
C001 | Residential Building A | T841 | Roofing | Emma White | Completed | Medium | 2023-09-10 | 2023-09-30 | 2023-09-30 | 100 | Concrete | Plot 21, Riverside | 30674.94 | 36141.32 | No issues
C004 | Warehouse D | T479 | Steel Framework Setup | Grace Allen | Not Started | Low | 2023-08-17 | 2023-09-12 |  | 0 | PVC Pipes | Industrial Park | 46061.86 | 0 | Not started
C002 | Shopping Complex B | T816 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-01-04 | 2023-02-02 | 2023-02-02 | 100 | Cement | Market Street | 46776.26 | 77863.38 | No issues
C003 | Office Tower C | T326 | Roofing | Dave Brown | Completed | Medium | 2023-06-25 | 2023-07-19 | 2023-07-19 | 100 | Steel Beams | Downtown Avenue | 27019.4 | 22725.01 | No issues
C003 | Office Tower C | T868 | Steel Framework Setup | John Miller | Blocked | Low | 2024-03-18 | 2024-04-03 |  | 0 | PVC Pipes | Downtown Avenue | 16505.35 | 13591.4 | Not started
C003 | Office Tower C | T119 | Plumbing Installations | Dave Brown | Blocked | High | 2023-07-07 | 2023-08-03 |  | 0 | Rebar | Downtown Avenue | 42590.27 | 50593.76 | Not started
C001 | Residential Building A | T543 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-04-24 | 2023-05-22 |  | 32 | Concrete | Plot 21, Riverside | 14872.12 | 13257.45 | In progress
C002 | Shopping Complex B | T433 | Plumbing Installations | Emma White | Not Started | Low | 2023-10-03 | 2023-10-22 |  | 0 | Copper Wires | Market Street | 24697.12 | 0 | Not started
C002 | Shopping Complex B | T101 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2024-05-18 | 2024-05-28 |  | 0 | Rebar | Market Street | 22970.25 | 39537.58 | Not started
C001 | Residential Building A | T332 | Site Survey | Dave Brown | In Progress | Low | 2023-11-25 | 2023-12-17 |  | 38 | Steel Beams | Plot 21, Riverside | 40605.71 | 35335.15 | In progress
C003 | Office Tower C | T998 | Concrete Pouring | John Miller | Blocked | Medium | 2023-09-23 | 2023-10-01 |  | 0 | Copper Wires | Downtown Avenue | 41546.95 | 25912.79 | Not started
C002 | Shopping Complex B | T222 | Roofing | John Miller | Completed | Low | 2023-08-28 | 2023-09-25 | 2023-09-25 | 100 | Steel Beams | Market Street | 18769.69 | 46266.48 | No issues
C003 | Office Tower C | T647 | Foundation Excavation | Grace Allen | In Progress | Medium | 2023-02-26 | 2023-03-05 |  | 42 | Roofing Sheets | Downtown Avenue | 14053.8 | 16108.89 | In progress
C001 | Residential Building A | T693 | Electrical Wiring | John Miller | Not Started | Medium | 2024-02-07 | 2024-02-23 |  | 0 | Cement | Plot 21, Riverside | 26125.11 | 0 | Not started
C002 | Shopping Complex B | T370 | Roofing | Mike Adams | Not Started | High | 2023-03-03 | 2023-03-24 |  | 0 | PVC Pipes | Market Street | 27878.33 | 0 | Not started
C001 | Residential Building A | T652 | Concrete Pouring | Grace Allen | Completed | Low | 2023-12-25 | 2024-01-13 | 2024-01-13 | 100 | Paint | Plot 21, Riverside | 6758.74 | 6979.54 | No issues
C001 | Residential Building A | T966 | Plumbing Installations | Emma White | Blocked | High | 2024-01-11 | 2024-01-19 |  | 0 | Cement | Plot 21, Riverside | 27441.94 | 22140.73 | Not started
C001 | Residential Building A | T962 | Plumbing Installations | Sarah Johnson | Completed | High | 2023-05-18 | 2023-06-03 | 2023-06-03 | 100 | Cement | Plot 21, Riverside | 31317.72 | 25384.27 | No issues
C002 | Shopping Complex B | T878 | Interior Painting | John Miller | Completed | Medium | 2023-11-26 | 2023-12-25 | 2023-12-25 | 100 | Copper Wires | Market Street | 11139.25 | 35711.54 | No issues
C003 | Office Tower C | T837 | Roofing | Mike Adams | In Progress | Low | 2023-02-20 | 2023-03-15 |  | 18 | Copper Wires | Downtown Avenue | 42168.77 | 47144.84 | In progress
C002 | Shopping Complex B | T256 | Foundation Excavation | Dave Brown | In Progress | Medium | 2024-02-15 | 2024-02-29 |  | 69 | Roofing Sheets | Market Street | 12282.66 | 35940.55 | In progress
C004 | Warehouse D | T261 | Concrete Pouring | Dave Brown | Completed | Medium | 2024-12-24 | 2025-01-22 | 2025-01-22 | 100 | PVC Pipes | Industrial Park | 43790.94 | 40597.07 | No issues
C001 | Residential Building A | T448 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-11-27 | 2023-12-23 | 2023-12-23 | 100 | Cement | Plot 21, Riverside | 6147.65 | 4847.82 | No issues
C002 | Shopping Complex B | T797 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2023-02-18 | 2023-03-05 |  | 11 | Cement | Market Street | 30196.35 | 48246.92 | In progress
C004 | Warehouse D | T447 | Roofing | Emma White | Completed | High | 2024-11-05 | 2024-11-21 | 2024-11-21 | 100 | Roofing Sheets | Industrial Park | 33399.16 | 28010.84 | No issues
C003 | Office Tower C | T857 | Steel Framework Setup | Emma White | In Progress | Low | 2023-07-14 | 2023-07-24 |  | 68 | Copper Wires | Downtown Avenue | 21759.46 | 23020.35 | In progress
C003 | Office Tower C | T480 | Concrete Pouring | Dave Brown | Blocked | Low | 2024-09-11 | 2024-09-21 |  | 0 | Rebar | Downtown Avenue | 27588.48 | 32676.28 | Not started
C003 | Office Tower C | T714 | Steel Framework Setup | Emma White | In Progress | Low | 2023-02-21 | 2023-03-01 |  | 52 | Roofing Sheets | Downtown Avenue | 21723.45 | 14744.16 | In progress
C001 | Residential Building A | T334 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2024-06-08 | 2024-06-15 |  | 71 | PVC Pipes | Plot 21, Riverside | 22715.78 | 21515.25 | In progress
C004 | Warehouse D | T981 | Site Survey | Emma White | Blocked | Low | 2023-01-02 | 2023-01-16 |  | 0 | Cement | Industrial Park | 21482.11 | 23125.69 | Not started
C001 | Residential Building A | T864 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-08-19 | 2024-09-17 | 2024-09-17 | 100 | Roofing Sheets | Plot 21, Riverside | 26534.59 | 21322.36 | No issues
C003 | Office Tower C | T906 | Plumbing Installations | Emma White | Not Started | Medium | 2023-09-14 | 2023-09-25 |  | 0 | Copper Wires | Downtown Avenue | 19170.13 | 0 | Not started
C004 | Warehouse D | T227 | Site Survey | Mike Adams | Not Started | High | 2024-05-09 | 2024-05-18 |  | 0 | Paint | Industrial Park | 38458.45 | 0 | Not started
C002 | Shopping Complex B | T837 | Steel Framework Setup | Emma White | Not Started | Medium | 2024-08-04 | 2024-08-17 |  | 0 | Concrete | Market Street | 9001.51 | 0 | Not started
C002 | Shopping Complex B | T360 | Concrete Pouring | Sarah Johnson | Completed | Low | 2024-01-08 | 2024-01-27 | 2024-01-27 | 100 | Concrete | Market Street | 42517.34 | 72197.57 | No issues
C001 | Residential Building A | T282 | Concrete Pouring | John Miller | Not Started | Medium | 2024-02-06 | 2024-02-22 |  | 0 | Cement | Plot 21, Riverside | 11738.54 | 0 | Not started
C001 | Residential Building A | T756 | Roofing | Rachel Green | Blocked | High | 2023-10-12 | 2023-11-02 |  | 0 | Steel Beams | Plot 21, Riverside | 16526.67 | 11922.01 | Not started
C002 | Shopping Complex B | T793 | Interior Painting | Sarah Johnson | Not Started | Low | 2023-09-16 | 2023-10-15 |  | 0 | PVC Pipes | Market Street | 9778.83 | 0 | Not started
C002 | Shopping Complex B | T970 | Site Survey | Rachel Green | In Progress | Medium | 2024-05-16 | 2024-06-15 |  | 40 | Rebar | Market Street | 40248.99 | 55694.73 | In progress
C001 | Residential Building A | T516 | Interior Painting | Mike Adams | Completed | Medium | 2023-10-20 | 2023-11-16 | 2023-11-16 | 100 | Paint | Plot 21, Riverside | 30583.13 | 21923.31 | No issues
C004 | Warehouse D | T806 | Site Survey | Grace Allen | Blocked | High | 2023-05-16 | 2023-06-10 |  | 0 | Copper Wires | Industrial Park | 10738.88 | 9555.63 | Not started
C004 | Warehouse D | T586 | Steel Framework Setup | Dave Brown | Blocked | Low | 2023-01-05 | 2023-01-25 |  | 0 | Concrete | Industrial Park | 39303.38 | 45598.1 | Not started
C003 | Office Tower C | T344 | Plumbing Installations | Emma White | Not Started | High | 2023-01-25 | 2023-02-22 |  | 0 | PVC Pipes | Downtown Avenue | 28874.85 | 0 | Not started
C004 | Warehouse D | T283 | Site Survey | Grace Allen | In Progress | Low | 2023-03-17 | 2023-04-01 |  | 59 | Concrete | Industrial Park | 16044.6 | 13214.22 | In progress
C001 | Residential Building A | T981 | Roofing | Rachel Green | Not Started | High | 2024-05-25 | 2024-06-08 |  | 0 | Cement | Plot 21, Riverside | 40196.92 | 0 | Not started
C003 | Office Tower C | T292 | Electrical Wiring | Grace Allen | Not Started | Low | 2024-11-10 | 2024-11-19 |  | 0 | Roofing Sheets | Downtown Avenue | 18889.19 | 0 | Not started
C003 | Office Tower C | T767 | Foundation Excavation | Rachel Green | Not Started | Medium | 2023-07-04 | 2023-07-20 |  | 0 | Concrete | Downtown Avenue | 38353.9 | 0 | Not started
C003 | Office Tower C | T780 | Steel Framework Setup | Emma White | Not Started | High | 2023-02-09 | 2023-03-07 |  | 0 | Concrete | Downtown Avenue | 27611.97 | 0 | Not started
C003 | Office Tower C | T228 | Electrical Wiring | Dave Brown | Blocked | Low | 2023-06-07 | 2023-06-28 |  | 0 | PVC Pipes | Downtown Avenue | 45258.85 | 36667.92 | Not started
C001 | Residential Building A | T573 | Electrical Wiring | John Miller | Blocked | Low | 2023-06-08 | 2023-06-25 |  | 0 | Paint | Plot 21, Riverside | 36055.91 | 30896.46 | Not started
C003 | Office Tower C | T921 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-08-06 | 2024-08-19 |  | 97 | PVC Pipes | Downtown Avenue | 13283.07 | 9480.84 | In progress
C002 | Shopping Complex B | T671 | Interior Painting | Emma White | Completed | Medium | 2023-09-24 | 2023-10-22 | 2023-10-22 | 100 | Concrete | Market Street | 24671.11 | 43739.38 | No issues
C001 | Residential Building A | T689 | Plumbing Installations | Sarah Johnson | Completed | High | 2023-03-05 | 2023-03-30 | 2023-03-30 | 100 | Steel Beams | Plot 21, Riverside | 45221.13 | 36586.77 | No issues
C002 | Shopping Complex B | T871 | Roofing | Grace Allen | Blocked | High | 2023-08-08 | 2023-08-19 |  | 0 | Roofing Sheets | Market Street | 25656.85 | 46012.63 | Not started
C004 | Warehouse D | T164 | Site Survey | Grace Allen | Not Started | Low | 2023-03-16 | 2023-04-01 |  | 0 | Steel Beams | Industrial Park | 40080.86 | 0 | Not started
C004 | Warehouse D | T737 | Plumbing Installations | Rachel Green | Blocked | Medium | 2024-05-04 | 2024-05-24 |  | 0 | Paint | Industrial Park | 9786.05 | 11053.22 | Not started
C004 | Warehouse D | T164 | Foundation Excavation | Rachel Green | In Progress | Low | 2023-05-05 | 2023-05-26 |  | 98 | Roofing Sheets | Industrial Park | 14318.25 | 9850.51 | In progress
C001 | Residential Building A | T580 | Foundation Excavation | John Miller | In Progress | Low | 2023-12-25 | 2024-01-14 |  | 79 | Copper Wires | Plot 21, Riverside | 46983.8 | 28932.88 | In progress
C001 | Residential Building A | T620 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-06-06 | 2024-06-20 |  | 0 | Concrete | Plot 21, Riverside | 26875.08 | 0 | Not started
C004 | Warehouse D | T165 | Plumbing Installations | Dave Brown | Blocked | Low | 2023-04-25 | 2023-05-25 |  | 0 | Copper Wires | Industrial Park | 34145.76 | 39834.61 | Not started
C003 | Office Tower C | T915 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-08-21 | 2024-09-05 |  | 0 | Roofing Sheets | Downtown Avenue | 17768.62 | 0 | Not started
C002 | Shopping Complex B | T893 | Foundation Excavation | Rachel Green | Completed | High | 2024-08-07 | 2024-08-16 | 2024-08-16 | 100 | Rebar | Market Street | 16981.97 | 41134.01 | No issues
C003 | Office Tower C | T562 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-07-23 | 2024-08-07 |  | 71 | Steel Beams | Downtown Avenue | 39784.28 | 44117.89 | In progress
C001 | Residential Building A | T572 | Plumbing Installations | Carlos Rivera | Blocked | High | 2023-04-07 | 2023-04-23 |  | 0 | PVC Pipes | Plot 21, Riverside | 43810.15 | 40935.97 | Not started
C001 | Residential Building A | T282 | Site Survey | Dave Brown | Completed | Low | 2024-12-10 | 2024-12-31 | 2024-12-31 | 100 | Copper Wires | Plot 21, Riverside | 29338.74 | 22776.9 | No issues
C004 | Warehouse D | T692 | Foundation Excavation | Emma White | In Progress | Medium | 2024-02-28 | 2024-03-26 |  | 71 | Paint | Industrial Park | 43437.16 | 29502.38 | In progress
C002 | Shopping Complex B | T985 | Steel Framework Setup | Mike Adams | Blocked | Low | 2023-06-12 | 2023-06-23 |  | 0 | Steel Beams | Market Street | 28163.07 | 50923.63 | Not started
C003 | Office Tower C | T734 | Electrical Wiring | Carlos Rivera | Completed | High | 2023-12-14 | 2024-01-11 | 2024-01-11 | 100 | Concrete | Downtown Avenue | 12185.9 | 13633.25 | No issues
C001 | Residential Building A | T551 | Steel Framework Setup | Rachel Green | Not Started | Medium | 2023-09-06 | 2023-10-03 |  | 0 | Roofing Sheets | Plot 21, Riverside | 28714.32 | 0 | Not started
C004 | Warehouse D | T172 | Foundation Excavation | Carlos Rivera | Completed | Low | 2024-01-22 | 2024-02-13 | 2024-02-13 | 100 | Rebar | Industrial Park | 30671.36 | 21763.65 | No issues
C001 | Residential Building A | T899 | Interior Painting | Grace Allen | Blocked | Medium | 2023-07-04 | 2023-07-14 |  | 0 | Roofing Sheets | Plot 21, Riverside | 31996.28 | 27133.84 | Not started
C003 | Office Tower C | T550 | Electrical Wiring | Rachel Green | Not Started | Low | 2024-07-20 | 2024-08-07 |  | 0 | Cement | Downtown Avenue | 22760.58 | 0 | Not started
C003 | Office Tower C | T497 | Roofing | Emma White | In Progress | Low | 2023-07-08 | 2023-07-29 |  | 88 | Copper Wires | Downtown Avenue | 28136.53 | 29714.24 | In progress
C002 | Shopping Complex B | T787 | Electrical Wiring | Mike Adams | Completed | High | 2024-01-15 | 2024-02-11 | 2024-02-11 | 100 | Concrete | Market Street | 11874.68 | 34954.95 | No issues
C002 | Shopping Complex B | T959 | Electrical Wiring | John Miller | Not Started | Low | 2023-03-05 | 2023-03-31 |  | 0 | Roofing Sheets | Market Street | 32950.63 | 0 | Not started
C002 | Shopping Complex B | T892 | Concrete Pouring | Emma White | In Progress | Medium | 2024-06-08 | 2024-06-22 |  | 6 | Concrete | Market Street | 45597.09 | 61485.52 | In progress
C004 | Warehouse D | T841 | Roofing | Rachel Green | Completed | Low | 2024-04-01 | 2024-04-12 | 2024-04-12 | 100 | Roofing Sheets | Industrial Park | 10397.54 | 12166.2 | No issues
C003 | Office Tower C | T419 | Foundation Excavation | Sarah Johnson | Not Started | High | 2024-05-03 | 2024-05-12 |  | 0 | PVC Pipes | Downtown Avenue | 21756.82 | 0 | Not started
C004 | Warehouse D | T396 | Site Survey | Grace Allen | Not Started | Medium | 2023-07-06 | 2023-07-22 |  | 0 | Copper Wires | Industrial Park | 41613.25 | 0 | Not started
C004 | Warehouse D | T320 | Roofing | Emma White | Blocked | Medium | 2023-02-02 | 2023-02-25 |  | 0 | Copper Wires | Industrial Park | 15251.61 | 10711.69 | Not started
C003 | Office Tower C | T232 | Interior Painting | Dave Brown | In Progress | Medium | 2024-07-14 | 2024-08-10 |  | 2 | Paint | Downtown Avenue | 37873.62 | 24499.83 | In progress
C003 | Office Tower C | T275 | Roofing | Mike Adams | Not Started | High | 2024-10-19 | 2024-11-14 |  | 0 | Rebar | Downtown Avenue | 21375.01 | 0 | Not started
C004 | Warehouse D | T340 | Site Survey | Mike Adams | Blocked | High | 2023-06-13 | 2023-07-10 |  | 0 | Rebar | Industrial Park | 37100.87 | 29442.46 | Not started
C004 | Warehouse D | T308 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2024-08-07 | 2024-09-01 |  | 19 | Roofing Sheets | Industrial Park | 11164.62 | 10074.34 | In progress
C003 | Office Tower C | T335 | Electrical Wiring | Dave Brown | In Progress | High | 2024-04-03 | 2024-04-24 |  | 74 | PVC Pipes | Downtown Avenue | 40173.25 | 25210.34 | In progress
C002 | Shopping Complex B | T132 | Roofing | Grace Allen | Completed | Medium | 2024-08-20 | 2024-09-09 | 2024-09-09 | 100 | PVC Pipes | Market Street | 20289.5 | 49156.41 | No issues
C001 | Residential Building A | T130 | Roofing | Rachel Green | Completed | High | 2024-06-07 | 2024-06-21 | 2024-06-21 | 100 | Steel Beams | Plot 21, Riverside | 7195.66 | 5331.01 | No issues
C002 | Shopping Complex B | T261 | Site Survey | Emma White | Blocked | Medium | 2023-05-10 | 2023-05-31 |  | 0 | Roofing Sheets | Market Street | 23522.83 | 44421.08 | Not started
C004 | Warehouse D | T889 | Site Survey | Mike Adams | Blocked | Medium | 2024-04-07 | 2024-05-02 |  | 0 | Paint | Industrial Park | 16522.66 | 16090.77 | Not started
C001 | Residential Building A | T697 | Concrete Pouring | Dave Brown | Blocked | Low | 2024-05-06 | 2024-05-13 |  | 0 | Roofing Sheets | Plot 21, Riverside | 43165.86 | 37709.6 | Not started
C001 | Residential Building A | T366 | Roofing | Mike Adams | In Progress | Low | 2024-03-16 | 2024-04-15 |  | 15 | Roofing Sheets | Plot 21, Riverside | 37501.8 | 41415.17 | In progress
C002 | Shopping Complex B | T339 | Roofing | Dave Brown | In Progress | Medium | 2023-07-01 | 2023-07-14 |  | 93 | Cement | Market Street | 30648.09 | 48616.03 | In progress
C002 | Shopping Complex B | T646 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-11-28 | 2024-12-19 |  | 65 | Concrete | Market Street | 39402.91 | 58883.3 | In progress
C004 | Warehouse D | T880 | Electrical Wiring | Dave Brown | Not Started | High | 2024-10-08 | 2024-11-05 |  | 0 | Paint | Industrial Park | 29512.01 | 0 | Not started
C004 | Warehouse D | T214 | Electrical Wiring | Rachel Green | In Progress | Medium | 2024-01-08 | 2024-01-25 |  | 88 | Roofing Sheets | Industrial Park | 6489.95 | 4367.1 | In progress
C001 | Residential Building A | T343 | Site Survey | Sarah Johnson | Completed | High | 2023-03-16 | 2023-04-05 | 2023-04-05 | 100 | Cement | Plot 21, Riverside | 47384.28 | 51415.19 | No issues
C004 | Warehouse D | T818 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2024-08-20 | 2024-09-04 | 2024-09-04 | 100 | Rebar | Industrial Park | 39596.33 | 45494.51 | No issues
C003 | Office Tower C | T114 | Roofing | Grace Allen | Blocked | Low | 2024-08-02 | 2024-08-31 |  | 0 | Cement | Downtown Avenue | 25138.48 | 19664.27 | Not started
C004 | Warehouse D | T294 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-02-16 | 2024-03-04 |  | 16 | Rebar | Industrial Park | 18456.59 | 13886.63 | In progress
C001 | Residential Building A | T539 | Steel Framework Setup | Rachel Green | Not Started | High | 2024-01-02 | 2024-01-16 |  | 0 | Rebar | Plot 21, Riverside | 42494.33 | 0 | Not started
C003 | Office Tower C | T937 | Roofing | Dave Brown | Completed | High | 2024-09-10 | 2024-09-26 | 2024-09-26 | 100 | Cement | Downtown Avenue | 46540.56 | 43792.45 | No issues
C004 | Warehouse D | T337 | Steel Framework Setup | Emma White | Completed | High | 2023-02-10 | 2023-03-03 | 2023-03-03 | 100 | Cement | Industrial Park | 35609.41 | 33185.17 | No issues
C001 | Residential Building A | T571 | Concrete Pouring | Dave Brown | Completed | High | 2024-07-03 | 2024-07-12 | 2024-07-12 | 100 | Roofing Sheets | Plot 21, Riverside | 48573.5 | 52377.96 | No issues
C004 | Warehouse D | T771 | Roofing | Sarah Johnson | Not Started | Low | 2023-12-07 | 2023-12-15 |  | 0 | Cement | Industrial Park | 40025.7 | 0 | Not started
C003 | Office Tower C | T273 | Roofing | Sarah Johnson | Completed | Medium | 2023-01-27 | 2023-02-08 | 2023-02-08 | 100 | Roofing Sheets | Downtown Avenue | 5000.88 | 4794.4 | No issues
C003 | Office Tower C | T473 | Plumbing Installations | John Miller | Completed | High | 2023-01-17 | 2023-02-12 | 2023-02-12 | 100 | Steel Beams | Downtown Avenue | 16902.32 | 13396.33 | No issues
C001 | Residential Building A | T196 | Plumbing Installations | Emma White | Not Started | Medium | 2024-04-04 | 2024-05-01 |  | 0 | Concrete | Plot 21, Riverside | 6239.09 | 0 | Not started
C001 | Residential Building A | T243 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-08-26 | 2023-09-06 |  | 0 | Concrete | Plot 21, Riverside | 33749.13 | 26725.98 | Not started
C004 | Warehouse D | T243 | Steel Framework Setup | John Miller | In Progress | Low | 2023-06-23 | 2023-07-11 |  | 73 | Concrete | Industrial Park | 44042.93 | 30493.29 | In progress
C001 | Residential Building A | T491 | Concrete Pouring | Sarah Johnson | Not Started | High | 2023-04-06 | 2023-04-22 |  | 0 | Concrete | Plot 21, Riverside | 14697.61 | 0 | Not started
C001 | Residential Building A | T535 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2024-06-08 | 2024-07-01 | 2024-07-01 | 100 | Paint | Plot 21, Riverside | 32853.34 | 37825.84 | No issues
C003 | Office Tower C | T828 | Plumbing Installations | Dave Brown | In Progress | High | 2023-03-10 | 2023-03-20 |  | 42 | Steel Beams | Downtown Avenue | 31710.17 | 29627.3 | In progress
C004 | Warehouse D | T243 | Foundation Excavation | Rachel Green | Completed | Medium | 2024-03-05 | 2024-03-23 | 2024-03-23 | 100 | Steel Beams | Industrial Park | 14126.07 | 9340.71 | No issues
C001 | Residential Building A | T787 | Site Survey | Grace Allen | Blocked | High | 2023-09-11 | 2023-09-21 |  | 0 | Cement | Plot 21, Riverside | 27971.64 | 25118.44 | Not started
C001 | Residential Building A | T234 | Concrete Pouring | John Miller | Completed | High | 2023-01-28 | 2023-02-20 | 2023-02-20 | 100 | Steel Beams | Plot 21, Riverside | 13666.96 | 9569.51 | No issues
C003 | Office Tower C | T775 | Plumbing Installations | John Miller | In Progress | Medium | 2023-02-09 | 2023-02-16 |  | 67 | Paint | Downtown Avenue | 32107.42 | 36572.95 | In progress
C001 | Residential Building A | T651 | Plumbing Installations | Rachel Green | Not Started | Low | 2024-02-19 | 2024-02-26 |  | 0 | Roofing Sheets | Plot 21, Riverside | 48909.2 | 0 | Not started
C003 | Office Tower C | T963 | Plumbing Installations | Carlos Rivera | Completed | Low | 2023-05-10 | 2023-05-27 | 2023-05-27 | 100 | PVC Pipes | Downtown Avenue | 17087.97 | 13703.73 | No issues
C002 | Shopping Complex B | T706 | Concrete Pouring | Dave Brown | Not Started | Low | 2023-06-14 | 2023-07-09 |  | 0 | Rebar | Market Street | 49395.22 | 0 | Not started
C001 | Residential Building A | T294 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2024-11-16 | 2024-11-29 |  | 63 | Concrete | Plot 21, Riverside | 9957.13 | 11836.59 | In progress
C001 | Residential Building A | T685 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2024-07-28 | 2024-08-15 |  | 29 | PVC Pipes | Plot 21, Riverside | 36309.08 | 29466.39 | In progress
C003 | Office Tower C | T328 | Roofing | Carlos Rivera | In Progress | High | 2024-09-25 | 2024-10-08 |  | 2 | Concrete | Downtown Avenue | 29685.53 | 25662.82 | In progress
C002 | Shopping Complex B | T461 | Site Survey | Carlos Rivera | In Progress | Medium | 2024-09-20 | 2024-09-27 |  | 72 | Cement | Market Street | 43841.37 | 52715.3 | In progress
C004 | Warehouse D | T383 | Interior Painting | Sarah Johnson | Blocked | High | 2023-11-27 | 2023-12-07 |  | 0 | Paint | Industrial Park | 11289.89 | 10196.36 | Not started
C002 | Shopping Complex B | T624 | Plumbing Installations | Dave Brown | In Progress | High | 2024-08-06 | 2024-08-25 |  | 79 | Paint | Market Street | 38579.77 | 62871.6 | In progress
C004 | Warehouse D | T742 | Concrete Pouring | John Miller | Not Started | High | 2024-05-10 | 2024-06-07 |  | 0 | Paint | Industrial Park | 6499.41 | 0 | Not started
C001 | Residential Building A | T913 | Roofing | Emma White | Blocked | Medium | 2024-12-16 | 2025-01-02 |  | 0 | Copper Wires | Plot 21, Riverside | 22351.37 | 25628.95 | Not started
C002 | Shopping Complex B | T365 | Concrete Pouring | Grace Allen | Blocked | Medium | 2023-06-24 | 2023-07-05 |  | 0 | Steel Beams | Market Street | 46599.12 | 56705.76 | Not started
C003 | Office Tower C | T659 | Steel Framework Setup | Dave Brown | Not Started | Medium | 2023-07-12 | 2023-07-23 |  | 0 | Concrete | Downtown Avenue | 14865.46 | 0 | Not started
C001 | Residential Building A | T595 | Concrete Pouring | Rachel Green | Not Started | Medium | 2023-07-17 | 2023-07-30 |  | 0 | Steel Beams | Plot 21, Riverside | 34399.57 | 0 | Not started
C004 | Warehouse D | T854 | Foundation Excavation | Sarah Johnson | Completed | High | 2024-02-14 | 2024-03-14 | 2024-03-14 | 100 | Paint | Industrial Park | 46701.12 | 52004.4 | No issues
C003 | Office Tower C | T175 | Electrical Wiring | Rachel Green | Completed | Low | 2023-05-10 | 2023-06-03 | 2023-06-03 | 100 | PVC Pipes | Downtown Avenue | 34100.15 | 32947.93 | No issues
C002 | Shopping Complex B | T380 | Interior Painting | Mike Adams | Blocked | Medium | 2024-05-12 | 2024-06-02 |  | 0 | Paint | Market Street | 46774.42 | 76760.8 | Not started
C003 | Office Tower C | T867 | Roofing | Emma White | Completed | Low | 2024-03-25 | 2024-04-24 | 2024-04-24 | 100 | Concrete | Downtown Avenue | 8776.41 | 10381.21 | No issues
C002 | Shopping Complex B | T774 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2024-02-23 | 2024-03-20 |  | 98 | Paint | Market Street | 7562.04 | 32593.92 | In progress
C003 | Office Tower C | T634 | Plumbing Installations | Emma White | Blocked | Low | 2023-04-06 | 2023-04-30 |  | 0 | Paint | Downtown Avenue | 9452.85 | 9435.19 | Not started
C002 | Shopping Complex B | T483 | Concrete Pouring | Dave Brown | Not Started | Medium | 2024-09-17 | 2024-09-26 |  | 0 | Paint | Market Street | 12951.85 | 0 | Not started
C004 | Warehouse D | T574 | Steel Framework Setup | Mike Adams | Not Started | High | 2023-11-06 | 2023-11-27 |  | 0 | Steel Beams | Industrial Park | 38828.07 | 0 | Not started
C003 | Office Tower C | T745 | Electrical Wiring | Rachel Green | Not Started | High | 2024-09-10 | 2024-09-21 |  | 0 | Steel Beams | Downtown Avenue | 33010.14 | 0 | Not started
C004 | Warehouse D | T531 | Interior Painting | Mike Adams | Completed | High | 2023-09-06 | 2023-09-20 | 2023-09-20 | 100 | Copper Wires | Industrial Park | 19730.93 | 21999.52 | No issues
C004 | Warehouse D | T594 | Interior Painting | Carlos Rivera | In Progress | Medium | 2023-05-11 | 2023-05-25 |  | 44 | Concrete | Industrial Park | 19968.57 | 21768.06 | In progress
C004 | Warehouse D | T545 | Electrical Wiring | Sarah Johnson | Completed | High | 2023-09-12 | 2023-09-24 | 2023-09-24 | 100 | Copper Wires | Industrial Park | 7466.64 | 5486.15 | No issues
C002 | Shopping Complex B | T438 | Electrical Wiring | John Miller | Completed | Low | 2023-06-11 | 2023-07-03 | 2023-07-03 | 100 | PVC Pipes | Market Street | 22791.39 | 48284.1 | No issues
C001 | Residential Building A | T844 | Electrical Wiring | Emma White | In Progress | High | 2024-12-12 | 2025-01-06 |  | 59 | Steel Beams | Plot 21, Riverside | 5938.31 | 6429.11 | In progress
C002 | Shopping Complex B | T874 | Plumbing Installations | Emma White | Not Started | Medium | 2024-08-21 | 2024-09-15 |  | 0 | PVC Pipes | Market Street | 35346.56 | 0 | Not started
C004 | Warehouse D | T380 | Interior Painting | Emma White | Completed | Low | 2024-01-22 | 2024-01-30 | 2024-01-30 | 100 | Copper Wires | Industrial Park | 18809.24 | 14200.65 | No issues
C001 | Residential Building A | T282 | Site Survey | Dave Brown | Blocked | Medium | 2024-03-09 | 2024-03-22 |  | 0 | Rebar | Plot 21, Riverside | 14782.38 | 10743.79 | Not started
C002 | Shopping Complex B | T996 | Electrical Wiring | Emma White | Completed | Medium | 2024-06-27 | 2024-07-05 | 2024-07-05 | 100 | Rebar | Market Street | 34165.12 | 46207.69 | No issues
C001 | Residential Building A | T280 | Plumbing Installations | Dave Brown | Not Started | Medium | 2024-08-06 | 2024-09-03 |  | 0 | Paint | Plot 21, Riverside | 41892.15 | 0 | Not started
C001 | Residential Building A | T175 | Foundation Excavation | Sarah Johnson | In Progress | High | 2024-06-20 | 2024-07-14 |  | 30 | Concrete | Plot 21, Riverside | 43754.53 | 29298.05 | In progress
C002 | Shopping Complex B | T621 | Site Survey | Carlos Rivera | Completed | Medium | 2023-02-02 | 2023-02-20 | 2023-02-20 | 100 | Concrete | Market Street | 14131.62 | 39302.19 | No issues
C001 | Residential Building A | T859 | Foundation Excavation | Dave Brown | In Progress | High | 2023-05-20 | 2023-06-16 |  | 47 | Cement | Plot 21, Riverside | 39043.36 | 23877.11 | In progress
C004 | Warehouse D | T704 | Interior Painting | Grace Allen | Blocked | Low | 2023-11-01 | 2023-11-17 |  | 0 | Roofing Sheets | Industrial Park | 47386.09 | 44077.9 | Not started
C001 | Residential Building A | T266 | Interior Painting | Grace Allen | In Progress | Low | 2024-11-06 | 2024-11-30 |  | 58 | Copper Wires | Plot 21, Riverside | 18117.48 | 18421.72 | In progress
C002 | Shopping Complex B | T127 | Electrical Wiring | Mike Adams | Completed | Low | 2024-08-11 | 2024-09-06 | 2024-09-06 | 100 | Rebar | Market Street | 20754.45 | 42856.87 | No issues
C002 | Shopping Complex B | T910 | Interior Painting | Grace Allen | In Progress | Low | 2024-08-11 | 2024-08-26 |  | 35 | PVC Pipes | Market Street | 7369.65 | 30002.98 | In progress
C001 | Residential Building A | T920 | Concrete Pouring | Dave Brown | Blocked | High | 2024-08-23 | 2024-08-31 |  | 0 | Roofing Sheets | Plot 21, Riverside | 31070.74 | 19674.47 | Not started
C004 | Warehouse D | T637 | Interior Painting | Dave Brown | Not Started | Low | 2024-04-05 | 2024-05-02 |  | 0 | Concrete | Industrial Park | 8516.18 | 0 | Not started
C001 | Residential Building A | T847 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2024-11-01 | 2024-11-18 |  | 0 | Concrete | Plot 21, Riverside | 49012.74 | 0 | Not started
C001 | Residential Building A | T160 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2024-05-23 | 2024-06-10 | 2024-06-10 | 100 | Paint | Plot 21, Riverside | 46173.86 | 34790.46 | No issues
C002 | Shopping Complex B | T477 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-08-21 | 2024-08-31 | 2024-08-31 | 100 | Copper Wires | Market Street | 16232.13 | 38945.68 | No issues
C001 | Residential Building A | T462 | Foundation Excavation | Emma White | Not Started | Medium | 2023-02-15 | 2023-02-26 |  | 0 | Cement | Plot 21, Riverside | 36092.39 | 0 | Not started
C004 | Warehouse D | T527 | Roofing | Sarah Johnson | In Progress | Low | 2023-02-02 | 2023-02-10 |  | 42 | Steel Beams | Industrial Park | 48438.18 | 53614.31 | In progress
C002 | Shopping Complex B | T606 | Concrete Pouring | Mike Adams | In Progress | Medium | 2024-12-22 | 2025-01-03 |  | 84 | Paint | Market Street | 18409.5 | 40925.29 | In progress
C002 | Shopping Complex B | T835 | Interior Painting | Grace Allen | Blocked | High | 2023-01-19 | 2023-01-30 |  | 0 | PVC Pipes | Market Street | 20617.91 | 44218.3 | Not started
C003 | Office Tower C | T456 | Roofing | Emma White | In Progress | Low | 2023-03-20 | 2023-04-10 |  | 36 | Concrete | Downtown Avenue | 12807 | 15306.74 | In progress
C002 | Shopping Complex B | T640 | Interior Painting | Sarah Johnson | Not Started | Low | 2024-12-26 | 2025-01-21 |  | 0 | Copper Wires | Market Street | 29474.23 | 0 | Not started
C003 | Office Tower C | T194 | Interior Painting | Emma White | Completed | Medium | 2023-12-20 | 2024-01-15 | 2024-01-15 | 100 | Cement | Downtown Avenue | 30400.47 | 29647.14 | No issues
C002 | Shopping Complex B | T266 | Plumbing Installations | Mike Adams | Blocked | High | 2023-05-22 | 2023-06-09 |  | 0 | Steel Beams | Market Street | 36418.35 | 65273.01 | Not started
C001 | Residential Building A | T593 | Foundation Excavation | Mike Adams | Not Started | Medium | 2024-07-05 | 2024-07-28 |  | 0 | Paint | Plot 21, Riverside | 48318.25 | 0 | Not started
C001 | Residential Building A | T812 | Plumbing Installations | John Miller | Completed | Medium | 2023-05-20 | 2023-06-02 | 2023-06-02 | 100 | Roofing Sheets | Plot 21, Riverside | 12147.61 | 11587.73 | No issues
C004 | Warehouse D | T624 | Foundation Excavation | Mike Adams | In Progress | High | 2024-09-08 | 2024-09-30 |  | 0 | PVC Pipes | Industrial Park | 6628.52 | 7505.61 | In progress
C003 | Office Tower C | T279 | Foundation Excavation | Emma White | In Progress | High | 2023-02-04 | 2023-02-27 |  | 4 | Rebar | Downtown Avenue | 37594.29 | 38736.49 | In progress
C004 | Warehouse D | T389 | Plumbing Installations | Mike Adams | Not Started | High | 2023-02-10 | 2023-02-28 |  | 0 | Steel Beams | Industrial Park | 13834.41 | 0 | Not started
C003 | Office Tower C | T544 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-10-14 | 2023-10-31 |  | 0 | Paint | Downtown Avenue | 17569.55 | 0 | Not started
C003 | Office Tower C | T220 | Concrete Pouring | John Miller | In Progress | Low | 2024-09-08 | 2024-09-21 |  | 97 | PVC Pipes | Downtown Avenue | 42776.52 | 34741.48 | In progress
C001 | Residential Building A | T109 | Electrical Wiring | Mike Adams | Blocked | Low | 2023-09-05 | 2023-09-29 |  | 0 | Steel Beams | Plot 21, Riverside | 29239.16 | 28465.73 | Not started
C003 | Office Tower C | T954 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2023-03-07 | 2023-03-23 |  | 95 | Roofing Sheets | Downtown Avenue | 6977.82 | 6480.56 | In progress
C003 | Office Tower C | T595 | Roofing | Mike Adams | Blocked | Medium | 2023-06-21 | 2023-07-14 |  | 0 | Steel Beams | Downtown Avenue | 30324.04 | 35718.09 | Not started
C004 | Warehouse D | T186 | Site Survey | Emma White | In Progress | High | 2024-03-12 | 2024-04-06 |  | 61 | Copper Wires | Industrial Park | 37224.76 | 29621.54 | In progress
C001 | Residential Building A | T363 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-10-26 | 2023-11-20 |  | 0 | Copper Wires | Plot 21, Riverside | 31957.28 | 28626.86 | Not started
C003 | Office Tower C | T677 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2024-03-02 | 2024-03-11 |  | 33 | Paint | Downtown Avenue | 7180.21 | 8343.74 | In progress
C004 | Warehouse D | T803 | Site Survey | Dave Brown | Completed | Medium | 2024-07-02 | 2024-07-30 | 2024-07-30 | 100 | Concrete | Industrial Park | 11243.05 | 12363.49 | No issues
C004 | Warehouse D | T747 | Interior Painting | Emma White | Not Started | Low | 2023-08-13 | 2023-09-02 |  | 0 | PVC Pipes | Industrial Park | 44925.19 | 0 | Not started
C003 | Office Tower C | T161 | Interior Painting | John Miller | Blocked | Low | 2024-10-03 | 2024-10-30 |  | 0 | Cement | Downtown Avenue | 38009.81 | 41226.58 | Not started
C004 | Warehouse D | T160 | Site Survey | John Miller | In Progress | Medium | 2023-01-03 | 2023-01-31 |  | 45 | Steel Beams | Industrial Park | 32532.79 | 37872.41 | In progress
C002 | Shopping Complex B | T372 | Roofing | John Miller | Blocked | Low | 2024-03-16 | 2024-04-14 |  | 0 | PVC Pipes | Market Street | 42539.23 | 59381.5 | Not started
C001 | Residential Building A | T830 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2023-01-01 | 2023-01-20 |  | 0 | PVC Pipes | Plot 21, Riverside | 16977.75 | 0 | Not started
C004 | Warehouse D | T923 | Plumbing Installations | Emma White | Completed | Medium | 2023-08-09 | 2023-08-30 | 2023-08-30 | 100 | Rebar | Industrial Park | 12806.97 | 8861.59 | No issues
C001 | Residential Building A | T409 | Interior Painting | Emma White | Completed | High | 2023-12-26 | 2024-01-14 | 2024-01-14 | 100 | Cement | Plot 21, Riverside | 31848.58 | 30483.72 | No issues
C004 | Warehouse D | T138 | Site Survey | Dave Brown | Not Started | Low | 2023-04-22 | 2023-05-10 |  | 0 | Steel Beams | Industrial Park | 23712.28 | 0 | Not started
C003 | Office Tower C | T933 | Electrical Wiring | John Miller | Blocked | Low | 2023-12-27 | 2024-01-08 |  | 0 | Cement | Downtown Avenue | 16513.49 | 11045.46 | Not started
C001 | Residential Building A | T813 | Site Survey | John Miller | Not Started | High | 2024-07-15 | 2024-07-25 |  | 0 | Paint | Plot 21, Riverside | 12419.87 | 0 | Not started
C003 | Office Tower C | T601 | Plumbing Installations | John Miller | Completed | Low | 2023-06-17 | 2023-06-25 | 2023-06-25 | 100 | Copper Wires | Downtown Avenue | 34570.58 | 23526.68 | No issues
C003 | Office Tower C | T701 | Electrical Wiring | Mike Adams | In Progress | High | 2024-05-22 | 2024-06-20 |  | 37 | Roofing Sheets | Downtown Avenue | 46408.24 | 52694.9 | In progress
C003 | Office Tower C | T763 | Electrical Wiring | Dave Brown | Not Started | High | 2023-06-25 | 2023-07-16 |  | 0 | PVC Pipes | Downtown Avenue | 8885.63 | 0 | Not started
C001 | Residential Building A | T281 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2023-08-11 | 2023-08-29 |  | 95 | Copper Wires | Plot 21, Riverside | 37826.7 | 39827.12 | In progress
C003 | Office Tower C | T428 | Roofing | Rachel Green | In Progress | Low | 2024-07-09 | 2024-08-05 |  | 44 | Rebar | Downtown Avenue | 42771.09 | 41320.05 | In progress
C002 | Shopping Complex B | T280 | Interior Painting | John Miller | In Progress | Low | 2024-05-13 | 2024-06-06 |  | 55 | Cement | Market Street | 30839.12 | 48870.62 | In progress
C002 | Shopping Complex B | T538 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-06-05 | 2023-06-16 | 2023-06-16 | 100 | Steel Beams | Market Street | 44647.04 | 60471.78 | No issues
C001 | Residential Building A | T377 | Roofing | Grace Allen | Blocked | Low | 2024-01-16 | 2024-01-29 |  | 0 | Copper Wires | Plot 21, Riverside | 25873.48 | 19662.04 | Not started
C004 | Warehouse D | T660 | Roofing | Rachel Green | Completed | Low | 2023-12-08 | 2023-12-25 | 2023-12-25 | 100 | Concrete | Industrial Park | 45682.38 | 38758.83 | No issues
C004 | Warehouse D | T346 | Interior Painting | Mike Adams | Blocked | Low | 2023-06-06 | 2023-07-04 |  | 0 | Roofing Sheets | Industrial Park | 6464.74 | 5562.41 | Not started
C003 | Office Tower C | T993 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-01-13 | 2024-01-30 |  | 0 | Roofing Sheets | Downtown Avenue | 25462.4 | 16674.72 | Not started
C001 | Residential Building A | T185 | Foundation Excavation | Carlos Rivera | Blocked | Low | 2024-01-20 | 2024-02-16 |  | 0 | Steel Beams | Plot 21, Riverside | 29679.17 | 31491.46 | Not started
C004 | Warehouse D | T360 | Electrical Wiring | Grace Allen | Blocked | High | 2023-06-22 | 2023-07-12 |  | 0 | Copper Wires | Industrial Park | 35945.88 | 25860.96 | Not started
C001 | Residential Building A | T333 | Site Survey | John Miller | Completed | Low | 2024-02-21 | 2024-03-20 | 2024-03-20 | 100 | Cement | Plot 21, Riverside | 19459.12 | 19997.86 | No issues
C003 | Office Tower C | T779 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2023-06-22 | 2023-07-07 |  | 0 | Paint | Downtown Avenue | 37827.92 | 29766.91 | Not started
C003 | Office Tower C | T721 | Site Survey | Grace Allen | In Progress | Medium | 2024-01-16 | 2024-02-04 |  | 55 | Steel Beams | Downtown Avenue | 28535.98 | 23155.2 | In progress
C001 | Residential Building A | T607 | Foundation Excavation | Emma White | Blocked | Medium | 2024-12-23 | 2024-12-30 |  | 0 | Copper Wires | Plot 21, Riverside | 10846.53 | 9809.2 | Not started
C004 | Warehouse D | T488 | Plumbing Installations | Dave Brown | Not Started | Low | 2024-11-19 | 2024-11-27 |  | 0 | Rebar | Industrial Park | 25736.35 | 0 | Not started
C004 | Warehouse D | T780 | Roofing | Emma White | In Progress | Low | 2024-01-03 | 2024-02-02 |  | 63 | Roofing Sheets | Industrial Park | 44726.35 | 31779.95 | In progress
C003 | Office Tower C | T552 | Concrete Pouring | Mike Adams | Blocked | Low | 2023-05-05 | 2023-05-25 |  | 0 | Cement | Downtown Avenue | 6033.4 | 5193.3 | Not started
C002 | Shopping Complex B | T950 | Steel Framework Setup | John Miller | Blocked | Medium | 2024-08-06 | 2024-08-14 |  | 0 | Rebar | Market Street | 16571.21 | 38508.17 | Not started
C002 | Shopping Complex B | T782 | Interior Painting | Grace Allen | Blocked | Low | 2024-07-05 | 2024-07-19 |  | 0 | Paint | Market Street | 12964.02 | 36389.44 | Not started
C002 | Shopping Complex B | T342 | Steel Framework Setup | John Miller | Blocked | Medium | 2024-04-19 | 2024-05-17 |  | 0 | Rebar | Market Street | 8867.47 | 31852.78 | Not started
C004 | Warehouse D | T172 | Concrete Pouring | Mike Adams | Not Started | High | 2023-10-05 | 2023-10-14 |  | 0 | Paint | Industrial Park | 36784.63 | 0 | Not started
C001 | Residential Building A | T147 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-01-19 | 2024-02-07 |  | 0 | Copper Wires | Plot 21, Riverside | 11056.1 | 0 | Not started
C003 | Office Tower C | T138 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2024-10-21 | 2024-11-17 |  | 0 | PVC Pipes | Downtown Avenue | 41425.75 | 33248.85 | Not started
C003 | Office Tower C | T111 | Electrical Wiring | Mike Adams | Not Started | High | 2023-08-22 | 2023-08-31 |  | 0 | Roofing Sheets | Downtown Avenue | 35572.48 | 0 | Not started
C002 | Shopping Complex B | T565 | Roofing | Mike Adams | Completed | High | 2023-08-02 | 2023-08-25 | 2023-08-25 | 100 | PVC Pipes | Market Street | 47952.2 | 63604.36 | No issues
C001 | Residential Building A | T274 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-07-02 | 2024-07-25 |  | 0 | Rebar | Plot 21, Riverside | 43632.9 | 50704.54 | Not started
C001 | Residential Building A | T478 | Plumbing Installations | Emma White | Completed | Medium | 2024-07-27 | 2024-08-17 | 2024-08-17 | 100 | Copper Wires | Plot 21, Riverside | 17078.4 | 15767.19 | No issues
C003 | Office Tower C | T636 | Foundation Excavation | Rachel Green | In Progress | High | 2024-02-13 | 2024-03-08 |  | 81 | Concrete | Downtown Avenue | 49394.03 | 58474.1 | In progress
C001 | Residential Building A | T400 | Site Survey | John Miller | Blocked | High | 2023-08-05 | 2023-08-30 |  | 0 | PVC Pipes | Plot 21, Riverside | 24046.61 | 22521.34 | Not started
C001 | Residential Building A | T608 | Concrete Pouring | John Miller | Completed | Low | 2024-08-26 | 2024-09-09 | 2024-09-09 | 100 | Copper Wires | Plot 21, Riverside | 14190.96 | 10664.52 | No issues
C001 | Residential Building A | T509 | Plumbing Installations | John Miller | Not Started | Low | 2023-09-18 | 2023-10-15 |  | 0 | Rebar | Plot 21, Riverside | 7646.17 | 0 | Not started
C001 | Residential Building A | T899 | Foundation Excavation | Emma White | Not Started | Medium | 2024-03-24 | 2024-04-19 |  | 0 | Roofing Sheets | Plot 21, Riverside | 36492.26 | 0 | Not started
C003 | Office Tower C | T522 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2024-03-17 | 2024-04-14 |  | 55 | Copper Wires | Downtown Avenue | 12859.16 | 9953.88 | In progress
C002 | Shopping Complex B | T950 | Interior Painting | Grace Allen | Not Started | Medium | 2023-01-19 | 2023-02-12 |  | 0 | Roofing Sheets | Market Street | 19801.53 | 0 | Not started
C003 | Office Tower C | T198 | Site Survey | Dave Brown | In Progress | High | 2023-08-15 | 2023-09-07 |  | 46 | Roofing Sheets | Downtown Avenue | 25194.89 | 25329.25 | In progress
C001 | Residential Building A | T467 | Interior Painting | Carlos Rivera | Completed | Medium | 2023-06-03 | 2023-06-26 | 2023-06-26 | 100 | Paint | Plot 21, Riverside | 32262.85 | 35435.4 | No issues
C002 | Shopping Complex B | T710 | Foundation Excavation | Mike Adams | Blocked | Medium | 2023-04-14 | 2023-05-04 |  | 0 | Cement | Market Street | 41757.01 | 58192.45 | Not started
C003 | Office Tower C | T393 | Plumbing Installations | Dave Brown | Completed | Medium | 2023-02-02 | 2023-02-23 | 2023-02-23 | 100 | Roofing Sheets | Downtown Avenue | 38113.99 | 27136.7 | No issues
C003 | Office Tower C | T438 | Electrical Wiring | Mike Adams | Completed | High | 2023-08-15 | 2023-08-29 | 2023-08-29 | 100 | Paint | Downtown Avenue | 11309.88 | 13156.43 | No issues
C003 | Office Tower C | T715 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2023-07-03 | 2023-07-31 |  | 0 | Copper Wires | Downtown Avenue | 21193.48 | 0 | Not started
C004 | Warehouse D | T669 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2023-08-08 | 2023-09-07 |  | 0 | Roofing Sheets | Industrial Park | 14228.23 | 10095.06 | Not started
C002 | Shopping Complex B | T130 | Foundation Excavation | Carlos Rivera | Not Started | High | 2024-09-19 | 2024-10-04 |  | 0 | Roofing Sheets | Market Street | 13180.11 | 0 | Not started
C004 | Warehouse D | T164 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2023-09-15 | 2023-09-26 | 2023-09-26 | 100 | Rebar | Industrial Park | 19624.73 | 16699.54 | No issues
C004 | Warehouse D | T594 | Electrical Wiring | Sarah Johnson | Completed | Low | 2024-09-13 | 2024-10-13 | 2024-10-13 | 100 | Paint | Industrial Park | 32712.92 | 35299.07 | No issues
C001 | Residential Building A | T864 | Steel Framework Setup | John Miller | Completed | Low | 2023-05-15 | 2023-05-28 | 2023-05-28 | 100 | Roofing Sheets | Plot 21, Riverside | 30010.4 | 34893.06 | No issues
C003 | Office Tower C | T618 | Foundation Excavation | John Miller | Not Started | Low | 2024-08-11 | 2024-09-06 |  | 0 | Copper Wires | Downtown Avenue | 8813.19 | 0 | Not started
C002 | Shopping Complex B | T526 | Site Survey | Emma White | Completed | Low | 2024-08-24 | 2024-09-12 | 2024-09-12 | 100 | Steel Beams | Market Street | 32511.74 | 63162.79 | No issues
C004 | Warehouse D | T298 | Steel Framework Setup | Rachel Green | Blocked | High | 2024-10-28 | 2024-11-20 |  | 0 | Rebar | Industrial Park | 37426.63 | 43664.19 | Not started
C001 | Residential Building A | T620 | Plumbing Installations | John Miller | Completed | Medium | 2024-05-20 | 2024-05-31 | 2024-05-31 | 100 | Steel Beams | Plot 21, Riverside | 18877.02 | 19082.23 | No issues
C004 | Warehouse D | T507 | Foundation Excavation | Emma White | In Progress | High | 2024-10-20 | 2024-11-19 |  | 8 | PVC Pipes | Industrial Park | 30726.24 | 23618.68 | In progress
C004 | Warehouse D | T341 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-05-27 | 2024-06-09 |  | 0 | PVC Pipes | Industrial Park | 27237.79 | 0 | Not started
C004 | Warehouse D | T500 | Roofing | Carlos Rivera | Completed | Medium | 2024-12-03 | 2024-12-25 | 2024-12-25 | 100 | Copper Wires | Industrial Park | 11236.62 | 9037.45 | No issues
C002 | Shopping Complex B | T112 | Roofing | Rachel Green | Completed | Medium | 2024-06-07 | 2024-06-26 | 2024-06-26 | 100 | Copper Wires | Market Street | 44360.86 | 52229.55 | No issues
C004 | Warehouse D | T166 | Plumbing Installations | Emma White | Not Started | High | 2023-09-15 | 2023-10-14 |  | 0 | Cement | Industrial Park | 18769.22 | 0 | Not started
C002 | Shopping Complex B | T528 | Electrical Wiring | John Miller | Blocked | High | 2023-05-25 | 2023-06-18 |  | 0 | Concrete | Market Street | 12895.76 | 37188.25 | Not started
C001 | Residential Building A | T311 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2023-08-20 | 2023-09-10 |  | 0 | PVC Pipes | Plot 21, Riverside | 14810.67 | 14742.3 | Not started
C004 | Warehouse D | T169 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2023-01-18 | 2023-02-05 | 2023-02-05 | 100 | Cement | Industrial Park | 48098.74 | 34310.54 | No issues
C002 | Shopping Complex B | T856 | Electrical Wiring | Mike Adams | In Progress | Medium | 2024-04-19 | 2024-05-11 |  | 5 | Steel Beams | Market Street | 47743.03 | 75137.91 | In progress
C002 | Shopping Complex B | T627 | Site Survey | Rachel Green | Blocked | High | 2024-07-24 | 2024-08-10 |  | 0 | Cement | Market Street | 5578.27 | 30895.54 | Not started
C002 | Shopping Complex B | T429 | Concrete Pouring | Emma White | Blocked | High | 2024-05-24 | 2024-06-12 |  | 0 | Copper Wires | Market Street | 43917.8 | 73733.56 | Not started
C004 | Warehouse D | T732 | Roofing | Rachel Green | Not Started | Medium | 2023-01-24 | 2023-02-12 |  | 0 | Concrete | Industrial Park | 13240.41 | 0 | Not started
C003 | Office Tower C | T678 | Concrete Pouring | Grace Allen | Completed | High | 2023-06-02 | 2023-06-14 | 2023-06-14 | 100 | Cement | Downtown Avenue | 30247.83 | 28181.71 | No issues
C002 | Shopping Complex B | T656 | Electrical Wiring | Emma White | Blocked | Medium | 2024-10-20 | 2024-11-07 |  | 0 | Copper Wires | Market Street | 33088.06 | 52305.2 | Not started
C002 | Shopping Complex B | T531 | Roofing | Mike Adams | In Progress | High | 2024-12-14 | 2024-12-31 |  | 9 | Steel Beams | Market Street | 35111.52 | 52964.69 | In progress
C003 | Office Tower C | T965 | Foundation Excavation | Carlos Rivera | Completed | Low | 2023-06-06 | 2023-06-22 | 2023-06-22 | 100 | Cement | Downtown Avenue | 43051.61 | 30242.46 | No issues
C004 | Warehouse D | T324 | Foundation Excavation | Rachel Green | In Progress | Medium | 2024-01-09 | 2024-01-17 |  | 32 | Roofing Sheets | Industrial Park | 15276.3 | 13340.93 | In progress
C001 | Residential Building A | T416 | Site Survey | Grace Allen | Not Started | Medium | 2024-10-26 | 2024-11-05 |  | 0 | Steel Beams | Plot 21, Riverside | 32227.77 | 0 | Not started
C004 | Warehouse D | T932 | Electrical Wiring | Rachel Green | Completed | Low | 2023-12-12 | 2023-12-28 | 2023-12-28 | 100 | Cement | Industrial Park | 12713.54 | 11980.65 | No issues
C003 | Office Tower C | T101 | Electrical Wiring | John Miller | Completed | High | 2024-12-07 | 2024-12-17 | 2024-12-17 | 100 | Rebar | Downtown Avenue | 19254.5 | 13512.89 | No issues
C002 | Shopping Complex B | T310 | Plumbing Installations | John Miller | Blocked | Medium | 2023-02-11 | 2023-02-27 |  | 0 | Rebar | Market Street | 39315 | 69944.71 | Not started
C004 | Warehouse D | T918 | Electrical Wiring | Rachel Green | In Progress | High | 2023-01-22 | 2023-01-30 |  | 68 | Rebar | Industrial Park | 45278.65 | 34635.56 | In progress
C001 | Residential Building A | T587 | Interior Painting | Grace Allen | In Progress | Medium | 2024-02-06 | 2024-03-04 |  | 45 | Roofing Sheets | Plot 21, Riverside | 49482.04 | 52801.17 | In progress
C001 | Residential Building A | T587 | Plumbing Installations | Sarah Johnson | In Progress | High | 2023-04-26 | 2023-05-05 |  | 74 | Roofing Sheets | Plot 21, Riverside | 45694.52 | 47364.63 | In progress
C004 | Warehouse D | T614 | Roofing | Rachel Green | In Progress | Medium | 2023-05-19 | 2023-06-02 |  | 26 | Rebar | Industrial Park | 47876.44 | 39429.73 | In progress
C003 | Office Tower C | T819 | Interior Painting | Carlos Rivera | Not Started | High | 2024-03-06 | 2024-03-20 |  | 0 | Roofing Sheets | Downtown Avenue | 49290 | 0 | Not started
C001 | Residential Building A | T629 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-09-07 | 2024-10-02 |  | 0 | Concrete | Plot 21, Riverside | 38136.58 | 24460.26 | Not started
C001 | Residential Building A | T517 | Site Survey | John Miller | Completed | High | 2023-02-07 | 2023-02-27 | 2023-02-27 | 100 | Paint | Plot 21, Riverside | 6852.64 | 7668.11 | No issues
C004 | Warehouse D | T336 | Concrete Pouring | Carlos Rivera | In Progress | High | 2024-11-11 | 2024-11-23 |  | 33 | PVC Pipes | Industrial Park | 16822.02 | 12581.41 | In progress
C002 | Shopping Complex B | T750 | Roofing | Grace Allen | In Progress | Medium | 2024-09-08 | 2024-10-03 |  | 19 | PVC Pipes | Market Street | 27570.85 | 55467.11 | In progress
C002 | Shopping Complex B | T445 | Roofing | Grace Allen | In Progress | Low | 2024-06-10 | 2024-06-30 |  | 7 | Paint | Market Street | 15888.68 | 42495.89 | In progress
C002 | Shopping Complex B | T691 | Concrete Pouring | Mike Adams | Not Started | Medium | 2024-05-25 | 2024-06-20 |  | 0 | Rebar | Market Street | 44549.55 | 0 | Not started
C004 | Warehouse D | T232 | Site Survey | Grace Allen | Completed | Medium | 2023-11-07 | 2023-11-16 | 2023-11-16 | 100 | PVC Pipes | Industrial Park | 9484.34 | 9152.27 | No issues
C002 | Shopping Complex B | T808 | Plumbing Installations | John Miller | Not Started | Medium | 2024-12-05 | 2024-12-18 |  | 0 | Roofing Sheets | Market Street | 43618.78 | 0 | Not started
C002 | Shopping Complex B | T114 | Roofing | Mike Adams | Completed | High | 2023-04-03 | 2023-04-11 | 2023-04-11 | 100 | Cement | Market Street | 44950.38 | 55112.38 | No issues
C002 | Shopping Complex B | T218 | Foundation Excavation | Dave Brown | Completed | Medium | 2024-08-15 | 2024-09-13 | 2024-09-13 | 100 | Rebar | Market Street | 8813.45 | 32259.58 | No issues
C003 | Office Tower C | T428 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-03-06 | 2023-03-19 |  | 0 | Paint | Downtown Avenue | 23563.72 | 18115.04 | Not started
C002 | Shopping Complex B | T338 | Foundation Excavation | John Miller | In Progress | Low | 2024-04-28 | 2024-05-26 |  | 76 | Steel Beams | Market Street | 40549.09 | 65836.79 | In progress
C002 | Shopping Complex B | T739 | Electrical Wiring | John Miller | In Progress | Medium | 2023-01-01 | 2023-01-23 |  | 53 | PVC Pipes | Market Street | 12244.88 | 39583.26 | In progress
C004 | Warehouse D | T364 | Interior Painting | Emma White | In Progress | Medium | 2024-08-27 | 2024-09-22 |  | 84 | Paint | Industrial Park | 30962.76 | 33132.17 | In progress
C001 | Residential Building A | T802 | Plumbing Installations | John Miller | Completed | Low | 2023-12-12 | 2023-12-21 | 2023-12-21 | 100 | Cement | Plot 21, Riverside | 48214.18 | 30152.37 | No issues
C001 | Residential Building A | T209 | Interior Painting | Emma White | In Progress | High | 2024-04-18 | 2024-04-29 |  | 87 | Concrete | Plot 21, Riverside | 18302.52 | 12459.73 | In progress
C003 | Office Tower C | T701 | Electrical Wiring | John Miller | Completed | High | 2024-03-05 | 2024-04-02 | 2024-04-02 | 100 | PVC Pipes | Downtown Avenue | 19687.68 | 20181.76 | No issues
C003 | Office Tower C | T622 | Plumbing Installations | Dave Brown | In Progress | Medium | 2023-07-23 | 2023-08-21 |  | 12 | PVC Pipes | Downtown Avenue | 33581.28 | 32703.36 | In progress
C001 | Residential Building A | T670 | Interior Painting | Sarah Johnson | Blocked | High | 2023-06-17 | 2023-06-28 |  | 0 | Cement | Plot 21, Riverside | 26272.83 | 16128.64 | Not started
C001 | Residential Building A | T575 | Site Survey | Rachel Green | Blocked | Low | 2023-08-26 | 2023-09-11 |  | 0 | PVC Pipes | Plot 21, Riverside | 17507.06 | 12975.68 | Not started
C001 | Residential Building A | T216 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2024-06-16 | 2024-06-30 |  | 0 | Copper Wires | Plot 21, Riverside | 16621.14 | 0 | Not started
C001 | Residential Building A | T733 | Roofing | Grace Allen | Completed | High | 2023-06-16 | 2023-06-29 | 2023-06-29 | 100 | Steel Beams | Plot 21, Riverside | 43721.35 | 39319.35 | No issues
C004 | Warehouse D | T592 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-12-20 | 2024-01-13 |  | 0 | Cement | Industrial Park | 48074.03 | 0 | Not started
C001 | Residential Building A | T232 | Interior Painting | Carlos Rivera | Blocked | High | 2023-11-09 | 2023-11-23 |  | 0 | Copper Wires | Plot 21, Riverside | 14730.47 | 11080.9 | Not started
C001 | Residential Building A | T958 | Roofing | Emma White | Completed | High | 2024-08-25 | 2024-09-13 | 2024-09-13 | 100 | Rebar | Plot 21, Riverside | 7490.51 | 8688.28 | No issues
C002 | Shopping Complex B | T957 | Roofing | John Miller | Not Started | Low | 2023-05-12 | 2023-06-05 |  | 0 | Cement | Market Street | 25087.53 | 0 | Not started
C004 | Warehouse D | T155 | Interior Painting | Carlos Rivera | In Progress | Medium | 2024-05-06 | 2024-05-19 |  | 86 | Rebar | Industrial Park | 44864.74 | 53527.6 | In progress
C004 | Warehouse D | T864 | Steel Framework Setup | Grace Allen | Blocked | Low | 2023-12-07 | 2023-12-30 |  | 0 | Paint | Industrial Park | 48715.59 | 40344.42 | Not started
C001 | Residential Building A | T633 | Steel Framework Setup | Emma White | Completed | High | 2023-07-14 | 2023-08-11 | 2023-08-11 | 100 | Cement | Plot 21, Riverside | 27156.86 | 31301.61 | No issues
C004 | Warehouse D | T824 | Roofing | Carlos Rivera | Blocked | Medium | 2024-04-04 | 2024-04-12 |  | 0 | Roofing Sheets | Industrial Park | 10517.2 | 9214.79 | Not started
C004 | Warehouse D | T477 | Electrical Wiring | Mike Adams | Not Started | Medium | 2024-04-16 | 2024-05-09 |  | 0 | PVC Pipes | Industrial Park | 6570.98 | 0 | Not started
C003 | Office Tower C | T470 | Electrical Wiring | John Miller | Blocked | High | 2024-06-20 | 2024-07-17 |  | 0 | Concrete | Downtown Avenue | 6511.15 | 5743.59 | Not started
C002 | Shopping Complex B | T921 | Interior Painting | John Miller | Blocked | High | 2023-11-15 | 2023-11-29 |  | 0 | Rebar | Market Street | 29487.41 | 50936.84 | Not started
C003 | Office Tower C | T320 | Electrical Wiring | Dave Brown | Blocked | High | 2023-08-16 | 2023-09-14 |  | 0 | Copper Wires | Downtown Avenue | 15567.43 | 17045.22 | Not started
C004 | Warehouse D | T597 | Foundation Excavation | Rachel Green | Not Started | High | 2024-01-02 | 2024-01-27 |  | 0 | Paint | Industrial Park | 35255.03 | 0 | Not started
C004 | Warehouse D | T822 | Electrical Wiring | Emma White | Not Started | Medium | 2023-05-21 | 2023-05-31 |  | 0 | PVC Pipes | Industrial Park | 26901.54 | 0 | Not started
C004 | Warehouse D | T189 | Roofing | Sarah Johnson | In Progress | Low | 2023-10-06 | 2023-10-21 |  | 65 | Rebar | Industrial Park | 41129.56 | 40082.72 | In progress
C001 | Residential Building A | T490 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2023-06-08 | 2023-06-26 |  | 0 | Cement | Plot 21, Riverside | 37350.49 | 0 | Not started
C001 | Residential Building A | T655 | Concrete Pouring | John Miller | Not Started | Low | 2024-10-12 | 2024-10-21 |  | 0 | Concrete | Plot 21, Riverside | 7380.81 | 0 | Not started
C004 | Warehouse D | T406 | Site Survey | Dave Brown | In Progress | High | 2024-02-06 | 2024-02-13 |  | 81 | PVC Pipes | Industrial Park | 10303.83 | 11998.75 | In progress
C001 | Residential Building A | T712 | Electrical Wiring | Dave Brown | In Progress | Medium | 2023-09-26 | 2023-10-14 |  | 52 | Concrete | Plot 21, Riverside | 26701.29 | 30617.21 | In progress
C001 | Residential Building A | T984 | Electrical Wiring | Mike Adams | Not Started | Medium | 2024-09-26 | 2024-10-10 |  | 0 | Concrete | Plot 21, Riverside | 40750.38 | 0 | Not started
C001 | Residential Building A | T325 | Foundation Excavation | Emma White | Completed | Low | 2023-05-07 | 2023-06-06 | 2023-06-06 | 100 | PVC Pipes | Plot 21, Riverside | 36184.36 | 31577.02 | No issues
C003 | Office Tower C | T615 | Roofing | Rachel Green | In Progress | High | 2023-10-23 | 2023-11-14 |  | 72 | Concrete | Downtown Avenue | 49595.62 | 36989.47 | In progress
C004 | Warehouse D | T609 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-05-27 | 2024-06-26 |  | 41 | Concrete | Industrial Park | 39225.64 | 29825.07 | In progress
C001 | Residential Building A | T670 | Concrete Pouring | Rachel Green | Blocked | High | 2023-09-17 | 2023-10-16 |  | 0 | Cement | Plot 21, Riverside | 11882.5 | 8748.89 | Not started
C003 | Office Tower C | T131 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2024-12-22 | 2025-01-09 |  | 96 | Concrete | Downtown Avenue | 34741.3 | 33365.04 | In progress
C003 | Office Tower C | T553 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2024-08-12 | 2024-08-28 | 2024-08-28 | 100 | Steel Beams | Downtown Avenue | 47538.06 | 48525 | No issues
C002 | Shopping Complex B | T294 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2023-10-16 | 2023-10-29 |  | 0 | Cement | Market Street | 18421.66 | 0 | Not started
C003 | Office Tower C | T980 | Roofing | John Miller | Completed | Low | 2024-02-20 | 2024-03-04 | 2024-03-04 | 100 | Rebar | Downtown Avenue | 6743.63 | 7643.1 | No issues
C002 | Shopping Complex B | T939 | Electrical Wiring | Rachel Green | In Progress | Medium | 2024-06-07 | 2024-06-16 |  | 75 | Copper Wires | Market Street | 19194.94 | 38509.4 | In progress
C003 | Office Tower C | T557 | Plumbing Installations | Grace Allen | Blocked | Medium | 2023-04-27 | 2023-05-15 |  | 0 | Steel Beams | Downtown Avenue | 15524.99 | 14435.56 | Not started
C003 | Office Tower C | T539 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2023-11-18 | 2023-12-01 | 2023-12-01 | 100 | Roofing Sheets | Downtown Avenue | 14667.88 | 16270.35 | No issues
C004 | Warehouse D | T404 | Interior Painting | Carlos Rivera | Not Started | Medium | 2024-09-11 | 2024-10-06 |  | 0 | Cement | Industrial Park | 11699.2 | 0 | Not started
C004 | Warehouse D | T740 | Plumbing Installations | Mike Adams | Blocked | Low | 2023-07-14 | 2023-07-30 |  | 0 | Concrete | Industrial Park | 40638.56 | 38717 | Not started
C003 | Office Tower C | T176 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2024-05-16 | 2024-06-09 |  | 0 | Concrete | Downtown Avenue | 14151.23 | 0 | Not started
C001 | Residential Building A | T837 | Interior Painting | Emma White | Blocked | Medium | 2024-11-02 | 2024-11-10 |  | 0 | PVC Pipes | Plot 21, Riverside | 5117.5 | 4436.33 | Not started
C002 | Shopping Complex B | T765 | Plumbing Installations | Emma White | In Progress | High | 2023-09-13 | 2023-10-12 |  | 51 | Cement | Market Street | 44060.64 | 65445.09 | In progress
C002 | Shopping Complex B | T464 | Steel Framework Setup | Dave Brown | Not Started | Low | 2024-09-19 | 2024-10-08 |  | 0 | Cement | Market Street | 29129.95 | 0 | Not started
C001 | Residential Building A | T354 | Interior Painting | Grace Allen | Blocked | High | 2024-01-10 | 2024-01-18 |  | 0 | Cement | Plot 21, Riverside | 19113.12 | 16277 | Not started
C003 | Office Tower C | T932 | Electrical Wiring | Emma White | In Progress | Low | 2024-10-21 | 2024-11-06 |  | 17 | Copper Wires | Downtown Avenue | 29026.46 | 23529.16 | In progress
C003 | Office Tower C | T351 | Electrical Wiring | John Miller | Completed | High | 2023-07-22 | 2023-08-04 | 2023-08-04 | 100 | Cement | Downtown Avenue | 32678.93 | 30512.48 | No issues
C001 | Residential Building A | T437 | Site Survey | Carlos Rivera | In Progress | Medium | 2024-09-03 | 2024-09-27 |  | 52 | Roofing Sheets | Plot 21, Riverside | 10391.43 | 10325.23 | In progress
C001 | Residential Building A | T846 | Steel Framework Setup | Mike Adams | Not Started | Medium | 2023-11-16 | 2023-12-09 |  | 0 | Rebar | Plot 21, Riverside | 6319.11 | 0 | Not started
C004 | Warehouse D | T186 | Interior Painting | Dave Brown | In Progress | Low | 2023-03-27 | 2023-04-17 |  | 25 | Steel Beams | Industrial Park | 26198.92 | 17084.72 | In progress
C004 | Warehouse D | T974 | Steel Framework Setup | Grace Allen | Completed | High | 2024-02-16 | 2024-03-16 | 2024-03-16 | 100 | Concrete | Industrial Park | 41317.21 | 42468.13 | No issues
C002 | Shopping Complex B | T578 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2024-01-07 | 2024-02-05 |  | 0 | Steel Beams | Market Street | 8819.06 | 0 | Not started
C003 | Office Tower C | T646 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2024-03-13 | 2024-03-31 |  | 97 | Concrete | Downtown Avenue | 42407.26 | 42183.09 | In progress
C003 | Office Tower C | T480 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-09-16 | 2024-10-07 |  | 0 | Rebar | Downtown Avenue | 18031.6 | 15538.22 | Not started
C003 | Office Tower C | T651 | Electrical Wiring | John Miller | In Progress | High | 2024-02-12 | 2024-03-03 |  | 59 | Concrete | Downtown Avenue | 43328.95 | 29540.45 | In progress
C001 | Residential Building A | T541 | Site Survey | John Miller | In Progress | Low | 2024-06-26 | 2024-07-18 |  | 87 | Roofing Sheets | Plot 21, Riverside | 11413.48 | 13406.45 | In progress
C002 | Shopping Complex B | T687 | Foundation Excavation | John Miller | Blocked | High | 2024-12-28 | 2025-01-12 |  | 0 | Copper Wires | Market Street | 27561.42 | 47015.09 | Not started
C004 | Warehouse D | T603 | Electrical Wiring | Mike Adams | Not Started | Medium | 2023-10-28 | 2023-11-05 |  | 0 | Paint | Industrial Park | 16069.53 | 0 | Not started
C004 | Warehouse D | T910 | Electrical Wiring | Emma White | In Progress | Medium | 2024-02-08 | 2024-02-28 |  | 55 | PVC Pipes | Industrial Park | 48810.95 | 52157.58 | In progress
C002 | Shopping Complex B | T848 | Interior Painting | Mike Adams | Not Started | High | 2024-10-20 | 2024-11-01 |  | 0 | Copper Wires | Market Street | 42851.53 | 0 | Not started
C001 | Residential Building A | T493 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2023-07-10 | 2023-08-09 |  | 0 | Cement | Plot 21, Riverside | 38277.89 | 0 | Not started
C004 | Warehouse D | T954 | Steel Framework Setup | Emma White | Completed | Low | 2024-08-05 | 2024-08-24 | 2024-08-24 | 100 | PVC Pipes | Industrial Park | 32740.56 | 39260.28 | No issues
C004 | Warehouse D | T753 | Site Survey | Dave Brown | Completed | High | 2024-03-28 | 2024-04-27 | 2024-04-27 | 100 | Rebar | Industrial Park | 11007.32 | 6832.06 | No issues
C003 | Office Tower C | T496 | Roofing | Rachel Green | In Progress | Medium | 2024-10-21 | 2024-10-28 |  | 9 | Paint | Downtown Avenue | 5823.7 | 6005.16 | In progress
C002 | Shopping Complex B | T847 | Concrete Pouring | Emma White | Blocked | Low | 2023-05-09 | 2023-05-23 |  | 0 | Copper Wires | Market Street | 16030.63 | 41651.09 | Not started
C001 | Residential Building A | T882 | Roofing | Emma White | Blocked | High | 2024-03-09 | 2024-04-07 |  | 0 | Rebar | Plot 21, Riverside | 18304.5 | 14094.6 | Not started
C003 | Office Tower C | T255 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-09-07 | 2023-09-21 |  | 0 | PVC Pipes | Downtown Avenue | 49430.67 | 0 | Not started
C003 | Office Tower C | T526 | Foundation Excavation | Mike Adams | Blocked | High | 2024-05-25 | 2024-06-24 |  | 0 | Cement | Downtown Avenue | 29083.53 | 22543.5 | Not started
C003 | Office Tower C | T119 | Foundation Excavation | Mike Adams | Completed | Medium | 2023-12-14 | 2023-12-22 | 2023-12-22 | 100 | Roofing Sheets | Downtown Avenue | 42008.49 | 40584.15 | No issues
C004 | Warehouse D | T455 | Foundation Excavation | John Miller | Completed | Medium | 2024-07-19 | 2024-07-29 | 2024-07-29 | 100 | Copper Wires | Industrial Park | 39542.08 | 30263.78 | No issues
C002 | Shopping Complex B | T694 | Roofing | Emma White | Completed | Medium | 2023-06-06 | 2023-06-18 | 2023-06-18 | 100 | Copper Wires | Market Street | 19239.24 | 41015.3 | No issues
C002 | Shopping Complex B | T775 | Electrical Wiring | Carlos Rivera | Blocked | High | 2023-12-25 | 2024-01-18 |  | 0 | Cement | Market Street | 47330.43 | 57450.54 | Not started
C002 | Shopping Complex B | T255 | Site Survey | John Miller | Blocked | High | 2024-03-28 | 2024-04-19 |  | 0 | Roofing Sheets | Market Street | 35978.17 | 67942.59 | Not started
C004 | Warehouse D | T801 | Steel Framework Setup | John Miller | In Progress | Medium | 2023-07-17 | 2023-08-08 |  | 0 | Concrete | Industrial Park | 16540.8 | 14256.53 | In progress
C004 | Warehouse D | T819 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-01-22 | 2024-01-30 |  | 40 | Paint | Industrial Park | 46193.5 | 35213.29 | In progress
C001 | Residential Building A | T226 | Steel Framework Setup | Emma White | Completed | High | 2024-06-10 | 2024-06-24 | 2024-06-24 | 100 | Paint | Plot 21, Riverside | 43124.04 | 48541.91 | No issues
C001 | Residential Building A | T482 | Concrete Pouring | John Miller | Blocked | Low | 2024-12-24 | 2025-01-07 |  | 0 | Paint | Plot 21, Riverside | 28099.75 | 24135.37 | Not started
C002 | Shopping Complex B | T286 | Foundation Excavation | Dave Brown | Not Started | Medium | 2024-06-05 | 2024-07-01 |  | 0 | Steel Beams | Market Street | 33864.67 | 0 | Not started
C002 | Shopping Complex B | T864 | Electrical Wiring | Emma White | Completed | Medium | 2023-07-08 | 2023-08-03 | 2023-08-03 | 100 | Paint | Market Street | 22978.59 | 52794.87 | No issues
C003 | Office Tower C | T629 | Steel Framework Setup | Emma White | In Progress | Medium | 2024-12-22 | 2025-01-17 |  | 5 | Roofing Sheets | Downtown Avenue | 39471.05 | 30225.26 | In progress
C002 | Shopping Complex B | T939 | Electrical Wiring | John Miller | In Progress | Low | 2024-04-20 | 2024-05-12 |  | 78 | PVC Pipes | Market Street | 28104.54 | 43670.02 | In progress
C003 | Office Tower C | T107 | Site Survey | Emma White | Blocked | Medium | 2023-09-24 | 2023-10-01 |  | 0 | Steel Beams | Downtown Avenue | 41095.62 | 34710.89 | Not started
C004 | Warehouse D | T680 | Plumbing Installations | Emma White | Blocked | Medium | 2024-01-13 | 2024-02-08 |  | 0 | Roofing Sheets | Industrial Park | 27706.35 | 17811.66 | Not started
C001 | Residential Building A | T878 | Site Survey | Carlos Rivera | Completed | High | 2023-02-05 | 2023-03-04 | 2023-03-04 | 100 | Roofing Sheets | Plot 21, Riverside | 26489.92 | 24236.03 | No issues
C002 | Shopping Complex B | T418 | Electrical Wiring | John Miller | Completed | High | 2024-07-28 | 2024-08-11 | 2024-08-11 | 100 | Paint | Market Street | 45894.25 | 56957.03 | No issues
C003 | Office Tower C | T829 | Concrete Pouring | Mike Adams | Blocked | High | 2023-08-10 | 2023-09-05 |  | 0 | Paint | Downtown Avenue | 27414.45 | 32271.25 | Not started
C001 | Residential Building A | T191 | Roofing | Grace Allen | In Progress | Low | 2024-08-01 | 2024-08-23 |  | 50 | PVC Pipes | Plot 21, Riverside | 9216.67 | 8542.02 | In progress
C004 | Warehouse D | T840 | Steel Framework Setup | Emma White | Completed | High | 2023-03-21 | 2023-04-12 | 2023-04-12 | 100 | Rebar | Industrial Park | 7934.27 | 4892.31 | No issues
C003 | Office Tower C | T345 | Site Survey | Grace Allen | Completed | Low | 2023-06-02 | 2023-07-01 | 2023-07-01 | 100 | PVC Pipes | Downtown Avenue | 11472.18 | 7789.31 | No issues
C004 | Warehouse D | T485 | Interior Painting | Dave Brown | In Progress | High | 2023-01-11 | 2023-01-23 |  | 76 | PVC Pipes | Industrial Park | 10744.49 | 11871.23 | In progress
C001 | Residential Building A | T893 | Concrete Pouring | Grace Allen | Not Started | Low | 2023-11-13 | 2023-11-25 |  | 0 | Copper Wires | Plot 21, Riverside | 13318.29 | 0 | Not started
C004 | Warehouse D | T466 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2023-06-17 | 2023-07-06 |  | 12 | Rebar | Industrial Park | 6970.03 | 7466.51 | In progress
C003 | Office Tower C | T938 | Foundation Excavation | Mike Adams | Completed | Low | 2024-11-26 | 2024-12-22 | 2024-12-22 | 100 | Paint | Downtown Avenue | 15507.1 | 10835.34 | No issues
C004 | Warehouse D | T669 | Concrete Pouring | Rachel Green | Completed | Medium | 2024-07-04 | 2024-07-21 | 2024-07-21 | 100 | Roofing Sheets | Industrial Park | 39865.46 | 30223.84 | No issues
C004 | Warehouse D | T724 | Steel Framework Setup | John Miller | Completed | High | 2023-07-12 | 2023-08-10 | 2023-08-10 | 100 | Roofing Sheets | Industrial Park | 38654.18 | 31402.29 | No issues
C004 | Warehouse D | T242 | Roofing | Carlos Rivera | Blocked | Low | 2024-01-11 | 2024-02-10 |  | 0 | Concrete | Industrial Park | 13830.88 | 10743.32 | Not started
C002 | Shopping Complex B | T264 | Foundation Excavation | John Miller | Not Started | Medium | 2024-09-11 | 2024-09-26 |  | 0 | PVC Pipes | Market Street | 10489.33 | 0 | Not started
C001 | Residential Building A | T543 | Roofing | Mike Adams | Blocked | Low | 2024-06-07 | 2024-06-19 |  | 0 | Cement | Plot 21, Riverside | 22539.97 | 13663.68 | Not started
C003 | Office Tower C | T748 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2024-06-23 | 2024-07-08 |  | 40 | Cement | Downtown Avenue | 21048.2 | 18845.08 | In progress
C004 | Warehouse D | T573 | Roofing | Carlos Rivera | Completed | Medium | 2024-07-10 | 2024-07-20 | 2024-07-20 | 100 | Rebar | Industrial Park | 9312.77 | 7038.93 | No issues
C001 | Residential Building A | T759 | Electrical Wiring | Grace Allen | In Progress | High | 2024-12-04 | 2024-12-15 |  | 77 | Copper Wires | Plot 21, Riverside | 37342.52 | 31990.47 | In progress
C001 | Residential Building A | T713 | Site Survey | Dave Brown | Completed | High | 2024-07-01 | 2024-07-13 | 2024-07-13 | 100 | Paint | Plot 21, Riverside | 24399.33 | 19621.24 | No issues
C004 | Warehouse D | T340 | Interior Painting | Mike Adams | In Progress | Medium | 2023-05-14 | 2023-05-23 |  | 52 | Paint | Industrial Park | 29989.5 | 22155.7 | In progress
C001 | Residential Building A | T814 | Interior Painting | Emma White | Completed | Medium | 2024-08-03 | 2024-08-28 | 2024-08-28 | 100 | Copper Wires | Plot 21, Riverside | 5382.85 | 5871.25 | No issues
C002 | Shopping Complex B | T657 | Site Survey | Emma White | Blocked | Medium | 2024-11-19 | 2024-12-13 |  | 0 | Cement | Market Street | 14496.16 | 34647.89 | Not started
C003 | Office Tower C | T721 | Electrical Wiring | John Miller | Blocked | High | 2023-09-03 | 2023-10-01 |  | 0 | Rebar | Downtown Avenue | 21137.49 | 19444.24 | Not started
C004 | Warehouse D | T697 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2024-04-21 | 2024-05-19 |  | 0 | Cement | Industrial Park | 5631.63 | 0 | Not started
C001 | Residential Building A | T647 | Electrical Wiring | Emma White | Not Started | High | 2024-09-27 | 2024-10-20 |  | 0 | Roofing Sheets | Plot 21, Riverside | 26735.46 | 0 | Not started
C002 | Shopping Complex B | T247 | Roofing | Grace Allen | Not Started | Medium | 2024-01-25 | 2024-02-13 |  | 0 | Rebar | Market Street | 46108.21 | 0 | Not started
C003 | Office Tower C | T630 | Roofing | Carlos Rivera | Completed | High | 2024-08-25 | 2024-09-10 | 2024-09-10 | 100 | Paint | Downtown Avenue | 26580.94 | 29196.67 | No issues
C003 | Office Tower C | T526 | Interior Painting | Sarah Johnson | In Progress | Low | 2023-05-21 | 2023-06-14 |  | 57 | Concrete | Downtown Avenue | 46119.72 | 35589.83 | In progress
C001 | Residential Building A | T725 | Steel Framework Setup | Grace Allen | Not Started | Low | 2023-12-25 | 2024-01-08 |  | 0 | PVC Pipes | Plot 21, Riverside | 37237.08 | 0 | Not started
C001 | Residential Building A | T800 | Concrete Pouring | Grace Allen | Blocked | Low | 2023-07-28 | 2023-08-16 |  | 0 | Cement | Plot 21, Riverside | 22977.16 | 26396.55 | Not started
C001 | Residential Building A | T455 | Steel Framework Setup | John Miller | Blocked | Low | 2023-07-26 | 2023-08-24 |  | 0 | PVC Pipes | Plot 21, Riverside | 5822.45 | 4219.01 | Not started
C001 | Residential Building A | T887 | Plumbing Installations | Grace Allen | Blocked | Low | 2024-07-25 | 2024-08-05 |  | 0 | Cement | Plot 21, Riverside | 36149.01 | 36876 | Not started
C004 | Warehouse D | T225 | Interior Painting | Emma White | In Progress | Medium | 2023-04-06 | 2023-04-21 |  | 84 | Roofing Sheets | Industrial Park | 41170.97 | 44996.4 | In progress
C003 | Office Tower C | T655 | Roofing | Rachel Green | Blocked | Medium | 2024-10-09 | 2024-10-16 |  | 0 | Rebar | Downtown Avenue | 34973.83 | 23864.58 | Not started
C003 | Office Tower C | T109 | Site Survey | Grace Allen | Not Started | High | 2023-08-02 | 2023-08-23 |  | 0 | PVC Pipes | Downtown Avenue | 21132.96 | 0 | Not started
C004 | Warehouse D | T832 | Foundation Excavation | Mike Adams | Completed | Medium | 2024-05-01 | 2024-05-12 | 2024-05-12 | 100 | Copper Wires | Industrial Park | 12417.32 | 12522.38 | No issues
C003 | Office Tower C | T601 | Interior Painting | Mike Adams | Not Started | Low | 2024-09-14 | 2024-10-08 |  | 0 | Paint | Downtown Avenue | 28845.45 | 0 | Not started
C004 | Warehouse D | T459 | Foundation Excavation | Dave Brown | Blocked | Low | 2024-03-11 | 2024-04-07 |  | 0 | Steel Beams | Industrial Park | 8040.25 | 9219.98 | Not started
C003 | Office Tower C | T902 | Electrical Wiring | Carlos Rivera | Not Started | High | 2023-06-13 | 2023-07-01 |  | 0 | Roofing Sheets | Downtown Avenue | 31067.34 | 0 | Not started
C003 | Office Tower C | T618 | Site Survey | Grace Allen | Not Started | Medium | 2023-12-05 | 2023-12-12 |  | 0 | Cement | Downtown Avenue | 49466.24 | 0 | Not started
C001 | Residential Building A | T512 | Roofing | Grace Allen | Completed | Medium | 2023-05-22 | 2023-06-16 | 2023-06-16 | 100 | Roofing Sheets | Plot 21, Riverside | 28901 | 28720.15 | No issues
C003 | Office Tower C | T893 | Concrete Pouring | Dave Brown | Not Started | High | 2023-06-18 | 2023-07-15 |  | 0 | Paint | Downtown Avenue | 13218.57 | 0 | Not started
C002 | Shopping Complex B | T404 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-06-12 | 2024-07-02 |  | 0 | Copper Wires | Market Street | 21979.09 | 0 | Not started
C003 | Office Tower C | T621 | Plumbing Installations | Rachel Green | In Progress | Low | 2024-10-09 | 2024-10-16 |  | 37 | Steel Beams | Downtown Avenue | 8438.74 | 9331.51 | In progress
C001 | Residential Building A | T888 | Interior Painting | Carlos Rivera | In Progress | Low | 2023-02-19 | 2023-03-18 |  | 73 | Rebar | Plot 21, Riverside | 21662.72 | 25018.55 | In progress
C001 | Residential Building A | T626 | Steel Framework Setup | Emma White | In Progress | Medium | 2024-08-19 | 2024-09-08 |  | 0 | Copper Wires | Plot 21, Riverside | 39403.95 | 27276.15 | In progress
C004 | Warehouse D | T166 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2024-04-11 | 2024-04-24 |  | 44 | Steel Beams | Industrial Park | 13401.77 | 15067.71 | In progress
C001 | Residential Building A | T440 | Concrete Pouring | Sarah Johnson | In Progress | High | 2023-07-16 | 2023-07-24 |  | 19 | Steel Beams | Plot 21, Riverside | 24283.6 | 16061.54 | In progress
C001 | Residential Building A | T306 | Concrete Pouring | Grace Allen | Blocked | Medium | 2023-11-25 | 2023-12-21 |  | 0 | Copper Wires | Plot 21, Riverside | 20078.53 | 19142.13 | Not started
C003 | Office Tower C | T330 | Roofing | Mike Adams | In Progress | High | 2024-04-23 | 2024-05-19 |  | 74 | Roofing Sheets | Downtown Avenue | 10104.74 | 10307.22 | In progress
C001 | Residential Building A | T110 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-07-23 | 2023-08-01 |  | 0 | Roofing Sheets | Plot 21, Riverside | 35442.56 | 25655.4 | Not started
C003 | Office Tower C | T376 | Steel Framework Setup | Emma White | Completed | Low | 2023-07-14 | 2023-08-08 | 2023-08-08 | 100 | Concrete | Downtown Avenue | 44205.56 | 49831.05 | No issues
C003 | Office Tower C | T116 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-01-22 | 2024-02-03 |  | 0 | Roofing Sheets | Downtown Avenue | 27215.35 | 0 | Not started
C001 | Residential Building A | T783 | Steel Framework Setup | Emma White | Not Started | High | 2023-11-07 | 2023-11-14 |  | 0 | Roofing Sheets | Plot 21, Riverside | 35208.5 | 0 | Not started
C004 | Warehouse D | T263 | Site Survey | Mike Adams | Not Started | Low | 2023-09-13 | 2023-10-13 |  | 0 | Copper Wires | Industrial Park | 24390.66 | 0 | Not started
C001 | Residential Building A | T843 | Concrete Pouring | John Miller | Completed | Medium | 2024-08-15 | 2024-08-24 | 2024-08-24 | 100 | Rebar | Plot 21, Riverside | 43451.13 | 48670.28 | No issues
C001 | Residential Building A | T915 | Plumbing Installations | Grace Allen | Not Started | Medium | 2023-07-14 | 2023-08-05 |  | 0 | Concrete | Plot 21, Riverside | 17870.82 | 0 | Not started
C001 | Residential Building A | T490 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2023-12-08 | 2023-12-21 | 2023-12-21 | 100 | Concrete | Plot 21, Riverside | 38222.47 | 29968.44 | No issues
C003 | Office Tower C | T282 | Concrete Pouring | Emma White | Not Started | High | 2023-02-10 | 2023-02-25 |  | 0 | PVC Pipes | Downtown Avenue | 35704.98 | 0 | Not started
C004 | Warehouse D | T980 | Steel Framework Setup | Rachel Green | Blocked | Low | 2023-03-14 | 2023-04-12 |  | 0 | Paint | Industrial Park | 11045.17 | 7098.85 | Not started
C003 | Office Tower C | T116 | Electrical Wiring | John Miller | Blocked | High | 2023-08-06 | 2023-08-20 |  | 0 | Cement | Downtown Avenue | 12548.23 | 8979.07 | Not started
C002 | Shopping Complex B | T499 | Electrical Wiring | Grace Allen | Not Started | Medium | 2023-09-28 | 2023-10-10 |  | 0 | Cement | Market Street | 34454.26 | 0 | Not started
C003 | Office Tower C | T699 | Electrical Wiring | Rachel Green | Blocked | High | 2024-03-16 | 2024-04-01 |  | 0 | Concrete | Downtown Avenue | 8679.38 | 5377.52 | Not started
C004 | Warehouse D | T775 | Plumbing Installations | Dave Brown | Blocked | High | 2024-02-15 | 2024-03-16 |  | 0 | Copper Wires | Industrial Park | 37172.69 | 31720.4 | Not started
C004 | Warehouse D | T511 | Concrete Pouring | Rachel Green | Completed | Low | 2024-11-09 | 2024-11-29 | 2024-11-29 | 100 | PVC Pipes | Industrial Park | 5320.48 | 3714.49 | No issues
C003 | Office Tower C | T268 | Electrical Wiring | John Miller | Blocked | Low | 2023-09-25 | 2023-10-15 |  | 0 | Copper Wires | Downtown Avenue | 31757.46 | 34167.52 | Not started
C004 | Warehouse D | T632 | Site Survey | Emma White | In Progress | Medium | 2024-08-10 | 2024-08-26 |  | 39 | Rebar | Industrial Park | 17846.64 | 12987.81 | In progress
C002 | Shopping Complex B | T570 | Electrical Wiring | John Miller | In Progress | Medium | 2023-04-09 | 2023-04-24 |  | 43 | Paint | Market Street | 43350.5 | 54278.44 | In progress
C003 | Office Tower C | T860 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2023-10-03 | 2023-11-02 |  | 11 | Paint | Downtown Avenue | 6195.5 | 4480.07 | In progress
C004 | Warehouse D | T837 | Foundation Excavation | Dave Brown | Not Started | High | 2024-12-11 | 2025-01-08 |  | 0 | Roofing Sheets | Industrial Park | 16830.77 | 0 | Not started
C002 | Shopping Complex B | T440 | Electrical Wiring | Sarah Johnson | Not Started | High | 2023-06-02 | 2023-06-10 |  | 0 | Steel Beams | Market Street | 26959.48 | 0 | Not started
C004 | Warehouse D | T845 | Site Survey | Sarah Johnson | Not Started | Low | 2023-08-05 | 2023-09-04 |  | 0 | Roofing Sheets | Industrial Park | 30432.8 | 0 | Not started
C003 | Office Tower C | T321 | Foundation Excavation | Rachel Green | Not Started | High | 2023-04-05 | 2023-04-29 |  | 0 | Paint | Downtown Avenue | 43575.34 | 0 | Not started
C004 | Warehouse D | T762 | Foundation Excavation | Mike Adams | In Progress | Low | 2023-12-01 | 2023-12-08 |  | 95 | Rebar | Industrial Park | 29866.4 | 30407.35 | In progress
C001 | Residential Building A | T101 | Foundation Excavation | Rachel Green | Not Started | High | 2024-04-26 | 2024-05-21 |  | 0 | Copper Wires | Plot 21, Riverside | 40468.02 | 0 | Not started
C003 | Office Tower C | T750 | Electrical Wiring | Grace Allen | In Progress | Medium | 2023-03-03 | 2023-03-17 |  | 73 | Copper Wires | Downtown Avenue | 44011.6 | 41066.15 | In progress
C002 | Shopping Complex B | T415 | Concrete Pouring | Dave Brown | Blocked | Low | 2024-08-04 | 2024-08-17 |  | 0 | Steel Beams | Market Street | 8082.69 | 34582.7 | Not started
C004 | Warehouse D | T211 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2023-01-25 | 2023-02-17 |  | 0 | Paint | Industrial Park | 39329.88 | 0 | Not started
C002 | Shopping Complex B | T590 | Foundation Excavation | Mike Adams | Not Started | Medium | 2024-11-17 | 2024-12-02 |  | 0 | Copper Wires | Market Street | 15917.7 | 0 | Not started
C004 | Warehouse D | T556 | Concrete Pouring | Rachel Green | In Progress | Medium | 2024-02-13 | 2024-02-22 |  | 40 | Steel Beams | Industrial Park | 30757.02 | 31894.82 | In progress
C002 | Shopping Complex B | T247 | Concrete Pouring | Grace Allen | Completed | High | 2023-11-15 | 2023-12-03 | 2023-12-03 | 100 | Rebar | Market Street | 34373.76 | 65056.65 | No issues
C001 | Residential Building A | T904 | Site Survey | John Miller | In Progress | Medium | 2024-04-20 | 2024-05-13 |  | 18 | Concrete | Plot 21, Riverside | 38385.04 | 33580.62 | In progress
C002 | Shopping Complex B | T299 | Roofing | Mike Adams | Blocked | High | 2024-03-14 | 2024-04-01 |  | 0 | Paint | Market Street | 48676.37 | 71658.75 | Not started
C003 | Office Tower C | T978 | Electrical Wiring | Dave Brown | Not Started | High | 2024-06-03 | 2024-06-21 |  | 0 | Concrete | Downtown Avenue | 48433.38 | 0 | Not started
C002 | Shopping Complex B | T187 | Concrete Pouring | John Miller | Completed | Low | 2023-04-22 | 2023-04-30 | 2023-04-30 | 100 | PVC Pipes | Market Street | 39912.59 | 67331.2 | No issues
C003 | Office Tower C | T848 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2023-01-12 | 2023-01-21 |  | 0 | PVC Pipes | Downtown Avenue | 42939.99 | 0 | Not started
C003 | Office Tower C | T337 | Roofing | Dave Brown | In Progress | High | 2024-05-18 | 2024-06-13 |  | 36 | Rebar | Downtown Avenue | 20930.78 | 21377.44 | In progress
C003 | Office Tower C | T186 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-04-17 | 2024-04-26 |  | 54 | Paint | Downtown Avenue | 17747.62 | 15725.54 | In progress
C002 | Shopping Complex B | T283 | Steel Framework Setup | John Miller | Completed | Medium | 2023-12-28 | 2024-01-09 | 2024-01-09 | 100 | Concrete | Market Street | 5888.39 | 31282.37 | No issues
C003 | Office Tower C | T572 | Concrete Pouring | Emma White | In Progress | High | 2023-04-08 | 2023-04-22 |  | 30 | Cement | Downtown Avenue | 5071.36 | 5126.61 | In progress
C002 | Shopping Complex B | T255 | Steel Framework Setup | John Miller | Blocked | High | 2024-10-23 | 2024-11-03 |  | 0 | Copper Wires | Market Street | 27347.69 | 44896.02 | Not started
C001 | Residential Building A | T689 | Plumbing Installations | Carlos Rivera | Not Started | Medium | 2023-02-13 | 2023-02-20 |  | 0 | Copper Wires | Plot 21, Riverside | 47643.78 | 0 | Not started
C003 | Office Tower C | T532 | Site Survey | John Miller | Completed | Low | 2023-03-20 | 2023-03-31 | 2023-03-31 | 100 | Copper Wires | Downtown Avenue | 34128.47 | 37855.17 | No issues
C004 | Warehouse D | T882 | Electrical Wiring | John Miller | Not Started | Medium | 2023-10-11 | 2023-10-26 |  | 0 | Concrete | Industrial Park | 17393 | 0 | Not started
C003 | Office Tower C | T439 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2023-09-12 | 2023-10-08 |  | 39 | Copper Wires | Downtown Avenue | 17450.57 | 16885.06 | In progress
C002 | Shopping Complex B | T165 | Interior Painting | Emma White | Blocked | Medium | 2024-05-02 | 2024-05-16 |  | 0 | Roofing Sheets | Market Street | 40972.45 | 72718.01 | Not started
C002 | Shopping Complex B | T545 | Plumbing Installations | Emma White | Blocked | High | 2024-02-17 | 2024-03-13 |  | 0 | PVC Pipes | Market Street | 16493.99 | 35399.11 | Not started
C001 | Residential Building A | T852 | Interior Painting | Grace Allen | Blocked | High | 2023-07-07 | 2023-07-27 |  | 0 | Paint | Plot 21, Riverside | 28994.7 | 27307.31 | Not started
C004 | Warehouse D | T149 | Roofing | Mike Adams | Blocked | Medium | 2023-09-15 | 2023-10-14 |  | 0 | Rebar | Industrial Park | 23835.11 | 26812.98 | Not started
C004 | Warehouse D | T581 | Interior Painting | John Miller | Blocked | Low | 2024-01-22 | 2024-02-15 |  | 0 | Concrete | Industrial Park | 49202.59 | 51571.13 | Not started
C001 | Residential Building A | T952 | Foundation Excavation | Rachel Green | Completed | High | 2023-01-15 | 2023-01-27 | 2023-01-27 | 100 | PVC Pipes | Plot 21, Riverside | 6766.54 | 6483.83 | No issues
C001 | Residential Building A | T397 | Concrete Pouring | Rachel Green | In Progress | High | 2023-11-27 | 2023-12-04 |  | 76 | Steel Beams | Plot 21, Riverside | 5703.21 | 6120.42 | In progress
C003 | Office Tower C | T838 | Plumbing Installations | Carlos Rivera | In Progress | High | 2023-07-16 | 2023-07-30 |  | 60 | Paint | Downtown Avenue | 34946.32 | 33848.24 | In progress
C002 | Shopping Complex B | T906 | Foundation Excavation | Rachel Green | Not Started | High | 2023-06-27 | 2023-07-23 |  | 0 | Rebar | Market Street | 32040.77 | 0 | Not started
C001 | Residential Building A | T825 | Roofing | Sarah Johnson | In Progress | Medium | 2023-01-15 | 2023-02-03 |  | 72 | Copper Wires | Plot 21, Riverside | 33434.47 | 25677.15 | In progress
C001 | Residential Building A | T783 | Foundation Excavation | Grace Allen | Completed | High | 2023-04-18 | 2023-05-15 | 2023-05-15 | 100 | Concrete | Plot 21, Riverside | 9927.8 | 8476.1 | No issues
C003 | Office Tower C | T131 | Plumbing Installations | Dave Brown | Completed | Medium | 2024-09-20 | 2024-10-01 | 2024-10-01 | 100 | Paint | Downtown Avenue | 23430.22 | 27005.47 | No issues
C002 | Shopping Complex B | T503 | Steel Framework Setup | Rachel Green | Completed | High | 2024-09-24 | 2024-10-13 | 2024-10-13 | 100 | Roofing Sheets | Market Street | 31908.77 | 55843.33 | No issues
C002 | Shopping Complex B | T576 | Foundation Excavation | Emma White | In Progress | Low | 2024-04-17 | 2024-04-30 |  | 77 | Rebar | Market Street | 24985.82 | 51522.43 | In progress
C002 | Shopping Complex B | T496 | Electrical Wiring | Dave Brown | Blocked | High | 2023-06-08 | 2023-06-25 |  | 0 | Concrete | Market Street | 9454.65 | 33103.03 | Not started
C003 | Office Tower C | T923 | Roofing | Dave Brown | In Progress | High | 2023-08-18 | 2023-09-14 |  | 53 | Rebar | Downtown Avenue | 21664.83 | 19358.38 | In progress
C002 | Shopping Complex B | T809 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2024-04-10 | 2024-05-06 |  | 5 | Roofing Sheets | Market Street | 35346.26 | 60626.97 | In progress
C004 | Warehouse D | T838 | Site Survey | Rachel Green | Not Started | Low | 2024-12-17 | 2025-01-14 |  | 0 | Steel Beams | Industrial Park | 39343.13 | 0 | Not started
C001 | Residential Building A | T611 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2023-02-02 | 2023-02-20 |  | 9 | Paint | Plot 21, Riverside | 35937.22 | 39785.41 | In progress
C003 | Office Tower C | T739 | Interior Painting | Grace Allen | Not Started | High | 2023-06-27 | 2023-07-19 |  | 0 | Concrete | Downtown Avenue | 33695.54 | 0 | Not started
C004 | Warehouse D | T851 | Steel Framework Setup | Emma White | Completed | Low | 2024-09-28 | 2024-10-24 | 2024-10-24 | 100 | Paint | Industrial Park | 49445.13 | 58231.43 | No issues
C001 | Residential Building A | T884 | Steel Framework Setup | Rachel Green | Not Started | High | 2023-08-22 | 2023-09-05 |  | 0 | Roofing Sheets | Plot 21, Riverside | 47306.95 | 0 | Not started
C001 | Residential Building A | T718 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-06-24 | 2024-07-18 | 2024-07-18 | 100 | PVC Pipes | Plot 21, Riverside | 39320.21 | 29661.3 | No issues
C002 | Shopping Complex B | T200 | Interior Painting | Emma White | Completed | High | 2023-06-07 | 2023-06-14 | 2023-06-14 | 100 | Concrete | Market Street | 37340.07 | 56335.84 | No issues
C001 | Residential Building A | T426 | Plumbing Installations | Grace Allen | Completed | High | 2023-12-27 | 2024-01-25 | 2024-01-25 | 100 | Steel Beams | Plot 21, Riverside | 7477.99 | 8518.61 | No issues
C002 | Shopping Complex B | T517 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2023-08-23 | 2023-09-05 | 2023-09-05 | 100 | Concrete | Market Street | 15062.54 | 37245.6 | No issues
C004 | Warehouse D | T339 | Plumbing Installations | Grace Allen | Not Started | Low | 2024-02-25 | 2024-03-17 |  | 0 | Rebar | Industrial Park | 26493.79 | 0 | Not started
C004 | Warehouse D | T255 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-06-10 | 2023-06-25 |  | 0 | PVC Pipes | Industrial Park | 23464.83 | 0 | Not started
C002 | Shopping Complex B | T128 | Steel Framework Setup | Grace Allen | Completed | Low | 2024-02-04 | 2024-02-26 | 2024-02-26 | 100 | Cement | Market Street | 15996.02 | 44051.08 | No issues
C004 | Warehouse D | T659 | Roofing | Grace Allen | Blocked | High | 2024-04-23 | 2024-05-11 |  | 0 | Rebar | Industrial Park | 11788.83 | 13617.83 | Not started
C003 | Office Tower C | T527 | Foundation Excavation | John Miller | Not Started | High | 2023-03-06 | 2023-03-27 |  | 0 | Rebar | Downtown Avenue | 43771.17 | 0 | Not started
C003 | Office Tower C | T776 | Electrical Wiring | Emma White | In Progress | Medium | 2023-11-19 | 2023-12-11 |  | 30 | Cement | Downtown Avenue | 35805.95 | 32207.71 | In progress
C003 | Office Tower C | T467 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2024-10-28 | 2024-11-23 | 2024-11-23 | 100 | Roofing Sheets | Downtown Avenue | 32587.28 | 20042.86 | No issues
C001 | Residential Building A | T966 | Concrete Pouring | John Miller | Blocked | Low | 2023-07-26 | 2023-08-19 |  | 0 | Cement | Plot 21, Riverside | 14547.66 | 14338.6 | Not started
C004 | Warehouse D | T313 | Interior Painting | Grace Allen | In Progress | Medium | 2024-10-22 | 2024-11-10 |  | 88 | Copper Wires | Industrial Park | 9446.13 | 6587.31 | In progress
C001 | Residential Building A | T238 | Interior Painting | Dave Brown | Blocked | Medium | 2024-08-02 | 2024-08-31 |  | 0 | Concrete | Plot 21, Riverside | 22491.98 | 18254.91 | Not started
C002 | Shopping Complex B | T273 | Roofing | John Miller | In Progress | Low | 2024-03-08 | 2024-03-19 |  | 83 | Copper Wires | Market Street | 34590.8 | 49040.37 | In progress
C001 | Residential Building A | T898 | Interior Painting | Emma White | In Progress | Medium | 2024-07-21 | 2024-08-19 |  | 63 | Rebar | Plot 21, Riverside | 22874.43 | 17674.6 | In progress
C004 | Warehouse D | T634 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2023-04-09 | 2023-04-21 |  | 0 | Roofing Sheets | Industrial Park | 23800.01 | 15393.99 | Not started
C002 | Shopping Complex B | T912 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2023-12-24 | 2024-01-08 |  | 0 | Roofing Sheets | Market Street | 36812.92 | 52767.62 | Not started
C002 | Shopping Complex B | T242 | Concrete Pouring | John Miller | In Progress | Medium | 2023-03-23 | 2023-04-17 |  | 1 | Roofing Sheets | Market Street | 18639.25 | 45961.02 | In progress
C004 | Warehouse D | T121 | Concrete Pouring | John Miller | Not Started | Medium | 2024-07-20 | 2024-08-08 |  | 0 | Rebar | Industrial Park | 28522.84 | 0 | Not started
C001 | Residential Building A | T887 | Site Survey | John Miller | Completed | High | 2023-08-09 | 2023-09-06 | 2023-09-06 | 100 | Steel Beams | Plot 21, Riverside | 21129.27 | 18677.16 | No issues
C003 | Office Tower C | T215 | Plumbing Installations | Emma White | In Progress | High | 2023-03-09 | 2023-03-17 |  | 97 | Cement | Downtown Avenue | 15236.78 | 14005.36 | In progress
C004 | Warehouse D | T942 | Concrete Pouring | Dave Brown | In Progress | Low | 2023-11-10 | 2023-12-04 |  | 82 | Copper Wires | Industrial Park | 14040.13 | 10029.58 | In progress
C004 | Warehouse D | T915 | Interior Painting | Carlos Rivera | Not Started | High | 2023-09-27 | 2023-10-05 |  | 0 | PVC Pipes | Industrial Park | 40888.48 | 0 | Not started
C001 | Residential Building A | T792 | Site Survey | Rachel Green | Blocked | High | 2024-08-15 | 2024-09-02 |  | 0 | Concrete | Plot 21, Riverside | 48942.26 | 52395.45 | Not started
C004 | Warehouse D | T735 | Roofing | Sarah Johnson | Completed | Low | 2024-03-08 | 2024-04-04 | 2024-04-04 | 100 | PVC Pipes | Industrial Park | 37710.49 | 36200.07 | No issues
C002 | Shopping Complex B | T196 | Roofing | Grace Allen | Completed | Low | 2024-05-17 | 2024-05-31 | 2024-05-31 | 100 | Roofing Sheets | Market Street | 13345.48 | 35191.93 | No issues
C002 | Shopping Complex B | T613 | Steel Framework Setup | John Miller | Completed | High | 2024-11-07 | 2024-12-01 | 2024-12-01 | 100 | Roofing Sheets | Market Street | 22832.95 | 40930.43 | No issues
C003 | Office Tower C | T124 | Interior Painting | Dave Brown | Not Started | Medium | 2024-01-11 | 2024-01-26 |  | 0 | PVC Pipes | Downtown Avenue | 26487.83 | 0 | Not started
C004 | Warehouse D | T346 | Electrical Wiring | Emma White | Not Started | High | 2024-12-15 | 2025-01-13 |  | 0 | Copper Wires | Industrial Park | 22929.22 | 0 | Not started
C002 | Shopping Complex B | T266 | Interior Painting | Carlos Rivera | Not Started | High | 2024-06-25 | 2024-07-14 |  | 0 | Copper Wires | Market Street | 14499.29 | 0 | Not started
C003 | Office Tower C | T825 | Roofing | Rachel Green | Not Started | Low | 2024-02-09 | 2024-03-02 |  | 0 | Paint | Downtown Avenue | 9851.35 | 0 | Not started
C003 | Office Tower C | T992 | Plumbing Installations | Rachel Green | In Progress | High | 2023-04-22 | 2023-05-16 |  | 64 | Concrete | Downtown Avenue | 26296.48 | 19864.86 | In progress
C003 | Office Tower C | T306 | Concrete Pouring | Dave Brown | Completed | Low | 2023-09-10 | 2023-09-30 | 2023-09-30 | 100 | PVC Pipes | Downtown Avenue | 41234.62 | 42828.77 | No issues
C003 | Office Tower C | T842 | Steel Framework Setup | Mike Adams | Completed | Medium | 2023-07-01 | 2023-07-26 | 2023-07-26 | 100 | Steel Beams | Downtown Avenue | 49975.21 | 56860.71 | No issues
C003 | Office Tower C | T302 | Plumbing Installations | Grace Allen | Completed | High | 2024-10-06 | 2024-11-03 | 2024-11-03 | 100 | Copper Wires | Downtown Avenue | 12212.97 | 13776.21 | No issues
C003 | Office Tower C | T738 | Concrete Pouring | Emma White | Blocked | High | 2023-07-05 | 2023-07-20 |  | 0 | Rebar | Downtown Avenue | 41236.13 | 36731.22 | Not started
C003 | Office Tower C | T592 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-01-22 | 2023-02-04 |  | 0 | Rebar | Downtown Avenue | 15588.12 | 11336.36 | Not started
C003 | Office Tower C | T102 | Foundation Excavation | Mike Adams | Not Started | High | 2023-01-21 | 2023-02-10 |  | 0 | Paint | Downtown Avenue | 25395.81 | 0 | Not started
C003 | Office Tower C | T183 | Roofing | Sarah Johnson | Completed | High | 2023-09-23 | 2023-10-02 | 2023-10-02 | 100 | PVC Pipes | Downtown Avenue | 34090.59 | 24518.55 | No issues
C003 | Office Tower C | T964 | Interior Painting | Emma White | Completed | High | 2023-04-25 | 2023-05-16 | 2023-05-16 | 100 | Rebar | Downtown Avenue | 7277.02 | 6105.78 | No issues
C003 | Office Tower C | T302 | Foundation Excavation | Grace Allen | In Progress | Low | 2024-11-12 | 2024-11-30 |  | 66 | PVC Pipes | Downtown Avenue | 43614.88 | 37066.33 | In progress
C003 | Office Tower C | T173 | Electrical Wiring | Rachel Green | Not Started | Medium | 2024-12-13 | 2025-01-09 |  | 0 | Paint | Downtown Avenue | 24767 | 0 | Not started
C002 | Shopping Complex B | T442 | Steel Framework Setup | Rachel Green | Not Started | Low | 2024-03-17 | 2024-04-07 |  | 0 | Roofing Sheets | Market Street | 8021.29 | 0 | Not started
C003 | Office Tower C | T192 | Site Survey | Carlos Rivera | Blocked | Low | 2023-05-21 | 2023-06-17 |  | 0 | Rebar | Downtown Avenue | 9766.59 | 6416.52 | Not started
C004 | Warehouse D | T287 | Steel Framework Setup | John Miller | In Progress | Medium | 2023-09-23 | 2023-10-13 |  | 39 | PVC Pipes | Industrial Park | 38184.2 | 30916.86 | In progress
C003 | Office Tower C | T650 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-01-05 | 2024-02-02 | 2024-02-02 | 100 | PVC Pipes | Downtown Avenue | 41017 | 27396.43 | No issues
C001 | Residential Building A | T113 | Electrical Wiring | Emma White | Completed | High | 2024-04-08 | 2024-05-04 | 2024-05-04 | 100 | Paint | Plot 21, Riverside | 44563.59 | 38823.61 | No issues
C001 | Residential Building A | T998 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2023-07-27 | 2023-08-08 | 2023-08-08 | 100 | Cement | Plot 21, Riverside | 21867.18 | 24404.83 | No issues
C001 | Residential Building A | T624 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-04-12 | 2023-05-07 |  | 0 | Roofing Sheets | Plot 21, Riverside | 12967.31 | 0 | Not started
C004 | Warehouse D | T451 | Plumbing Installations | Dave Brown | Not Started | Medium | 2023-08-12 | 2023-09-10 |  | 0 | PVC Pipes | Industrial Park | 17753.56 | 0 | Not started
C002 | Shopping Complex B | T254 | Steel Framework Setup | Grace Allen | Completed | Medium | 2023-03-22 | 2023-04-19 | 2023-04-19 | 100 | Steel Beams | Market Street | 29987.54 | 58096.49 | No issues
C004 | Warehouse D | T389 | Steel Framework Setup | John Miller | Completed | High | 2024-06-16 | 2024-07-06 | 2024-07-06 | 100 | Copper Wires | Industrial Park | 17780.9 | 11904.73 | No issues
C003 | Office Tower C | T740 | Concrete Pouring | Rachel Green | Not Started | High | 2023-04-10 | 2023-05-08 |  | 0 | Steel Beams | Downtown Avenue | 26589.75 | 0 | Not started
C003 | Office Tower C | T566 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2024-10-03 | 2024-10-12 |  | 0 | Cement | Downtown Avenue | 19812.01 | 0 | Not started
C004 | Warehouse D | T407 | Site Survey | Mike Adams | Blocked | Low | 2023-10-08 | 2023-11-06 |  | 0 | Rebar | Industrial Park | 15317.23 | 14985.58 | Not started
C002 | Shopping Complex B | T520 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2024-02-07 | 2024-03-02 |  | 0 | Concrete | Market Street | 40505.76 | 72252.55 | Not started
C002 | Shopping Complex B | T757 | Roofing | Grace Allen | Completed | Medium | 2023-01-25 | 2023-02-08 | 2023-02-08 | 100 | Roofing Sheets | Market Street | 12994.44 | 37374.63 | No issues
C001 | Residential Building A | T501 | Electrical Wiring | Mike Adams | Completed | High | 2023-04-23 | 2023-05-09 | 2023-05-09 | 100 | Copper Wires | Plot 21, Riverside | 42170.95 | 35225.3 | No issues
C003 | Office Tower C | T353 | Steel Framework Setup | Grace Allen | Completed | Medium | 2024-12-08 | 2024-12-17 | 2024-12-17 | 100 | Copper Wires | Downtown Avenue | 37207.67 | 36599.15 | No issues
C003 | Office Tower C | T680 | Site Survey | Carlos Rivera | Not Started | High | 2023-05-18 | 2023-05-29 |  | 0 | Paint | Downtown Avenue | 29593.04 | 0 | Not started
C001 | Residential Building A | T638 | Concrete Pouring | Grace Allen | Blocked | Low | 2024-09-21 | 2024-10-05 |  | 0 | Steel Beams | Plot 21, Riverside | 13735.49 | 15863.16 | Not started
C002 | Shopping Complex B | T301 | Electrical Wiring | John Miller | Blocked | High | 2024-02-18 | 2024-02-26 |  | 0 | Steel Beams | Market Street | 29647 | 57574.62 | Not started
C001 | Residential Building A | T600 | Interior Painting | Dave Brown | Blocked | Low | 2024-03-02 | 2024-03-15 |  | 0 | Steel Beams | Plot 21, Riverside | 28183.5 | 20329.19 | Not started
C001 | Residential Building A | T264 | Interior Painting | Emma White | Completed | Low | 2023-09-11 | 2023-09-21 | 2023-09-21 | 100 | Concrete | Plot 21, Riverside | 26720.74 | 24076.62 | No issues
C003 | Office Tower C | T801 | Roofing | John Miller | Not Started | Medium | 2023-01-20 | 2023-02-10 |  | 0 | Copper Wires | Downtown Avenue | 42431.61 | 0 | Not started
C004 | Warehouse D | T382 | Site Survey | John Miller | Completed | Low | 2023-07-10 | 2023-07-25 | 2023-07-25 | 100 | Cement | Industrial Park | 45723.37 | 32911.9 | No issues
C004 | Warehouse D | T788 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-10-27 | 2024-11-12 |  | 0 | Roofing Sheets | Industrial Park | 6577.07 | 4582.37 | Not started
C001 | Residential Building A | T253 | Roofing | John Miller | In Progress | Low | 2023-02-09 | 2023-02-28 |  | 63 | Steel Beams | Plot 21, Riverside | 22003.85 | 14492.38 | In progress
C001 | Residential Building A | T886 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2023-02-05 | 2023-02-13 |  | 0 | Concrete | Plot 21, Riverside | 45649.23 | 50621.49 | Not started
C001 | Residential Building A | T518 | Interior Painting | Dave Brown | Not Started | High | 2024-05-12 | 2024-05-28 |  | 0 | Copper Wires | Plot 21, Riverside | 33109.53 | 0 | Not started
C003 | Office Tower C | T233 | Site Survey | Carlos Rivera | Blocked | Low | 2023-12-04 | 2023-12-23 |  | 0 | Steel Beams | Downtown Avenue | 45736.1 | 53721.88 | Not started
C002 | Shopping Complex B | T682 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2024-11-13 | 2024-12-12 |  | 16 | Steel Beams | Market Street | 17146.49 | 37034.56 | In progress
C003 | Office Tower C | T488 | Electrical Wiring | Rachel Green | Blocked | Medium | 2023-04-05 | 2023-04-20 |  | 0 | Steel Beams | Downtown Avenue | 35320.19 | 31921.36 | Not started
C004 | Warehouse D | T673 | Site Survey | Carlos Rivera | Completed | High | 2024-04-25 | 2024-05-08 | 2024-05-08 | 100 | Paint | Industrial Park | 28707.55 | 33928.81 | No issues
C001 | Residential Building A | T771 | Site Survey | Sarah Johnson | In Progress | High | 2024-05-06 | 2024-05-15 |  | 34 | Copper Wires | Plot 21, Riverside | 25518.34 | 19218.43 | In progress
C002 | Shopping Complex B | T869 | Interior Painting | Rachel Green | In Progress | Low | 2023-09-09 | 2023-10-01 |  | 84 | Copper Wires | Market Street | 23503.75 | 46438.85 | In progress
C003 | Office Tower C | T325 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2023-06-20 | 2023-07-04 |  | 0 | PVC Pipes | Downtown Avenue | 36398.03 | 0 | Not started
C001 | Residential Building A | T263 | Foundation Excavation | Rachel Green | Completed | Medium | 2023-12-04 | 2023-12-30 | 2023-12-30 | 100 | Paint | Plot 21, Riverside | 18172.11 | 11102.87 | No issues
C001 | Residential Building A | T215 | Plumbing Installations | Mike Adams | Blocked | Medium | 2023-05-23 | 2023-06-07 |  | 0 | Paint | Plot 21, Riverside | 10013.23 | 9443.64 | Not started
C002 | Shopping Complex B | T968 | Interior Painting | Rachel Green | Completed | Medium | 2024-06-23 | 2024-07-01 | 2024-07-01 | 100 | Rebar | Market Street | 20006.48 | 41799.88 | No issues
C001 | Residential Building A | T290 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2023-11-07 | 2023-12-03 |  | 0 | Concrete | Plot 21, Riverside | 8070.42 | 7343.27 | Not started
C001 | Residential Building A | T145 | Concrete Pouring | John Miller | Completed | Low | 2023-07-28 | 2023-08-27 | 2023-08-27 | 100 | Paint | Plot 21, Riverside | 23008.24 | 19526.84 | No issues
C002 | Shopping Complex B | T420 | Electrical Wiring | Carlos Rivera | Blocked | High | 2023-10-02 | 2023-10-30 |  | 0 | Concrete | Market Street | 33011.84 | 57370.61 | Not started
C002 | Shopping Complex B | T762 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-08-15 | 2023-08-22 |  | 16 | Rebar | Market Street | 32541.19 | 49745.78 | In progress
C003 | Office Tower C | T612 | Roofing | John Miller | Completed | Medium | 2023-08-05 | 2023-09-04 | 2023-09-04 | 100 | Roofing Sheets | Downtown Avenue | 43191.06 | 26672.77 | No issues
C002 | Shopping Complex B | T685 | Interior Painting | Mike Adams | Not Started | Medium | 2023-10-19 | 2023-11-10 |  | 0 | Cement | Market Street | 17998.44 | 0 | Not started
C002 | Shopping Complex B | T664 | Plumbing Installations | Emma White | In Progress | Low | 2023-10-20 | 2023-10-28 |  | 59 | Paint | Market Street | 15618.14 | 34962.22 | In progress
C002 | Shopping Complex B | T143 | Concrete Pouring | John Miller | Not Started | High | 2024-10-24 | 2024-11-10 |  | 0 | Concrete | Market Street | 35471.07 | 0 | Not started
C001 | Residential Building A | T621 | Interior Painting | Grace Allen | In Progress | Low | 2024-07-24 | 2024-08-16 |  | 27 | Copper Wires | Plot 21, Riverside | 41593.42 | 42903.55 | In progress
C002 | Shopping Complex B | T713 | Site Survey | Carlos Rivera | Completed | Low | 2023-12-25 | 2024-01-23 | 2024-01-23 | 100 | PVC Pipes | Market Street | 7580.52 | 33068.48 | No issues
C003 | Office Tower C | T175 | Interior Painting | Dave Brown | Completed | Low | 2024-03-11 | 2024-03-31 | 2024-03-31 | 100 | PVC Pipes | Downtown Avenue | 28387.72 | 24371.13 | No issues
C003 | Office Tower C | T287 | Concrete Pouring | Rachel Green | Completed | Low | 2024-09-17 | 2024-10-07 | 2024-10-07 | 100 | Steel Beams | Downtown Avenue | 8547.5 | 8269.52 | No issues
C002 | Shopping Complex B | T994 | Interior Painting | Rachel Green | Not Started | Medium | 2023-06-24 | 2023-07-13 |  | 0 | Roofing Sheets | Market Street | 44724.86 | 0 | Not started
C004 | Warehouse D | T936 | Roofing | Emma White | Blocked | Low | 2023-09-28 | 2023-10-28 |  | 0 | Cement | Industrial Park | 40720.85 | 45028.96 | Not started
C001 | Residential Building A | T440 | Plumbing Installations | Dave Brown | Not Started | High | 2024-06-24 | 2024-07-03 |  | 0 | Paint | Plot 21, Riverside | 44808.25 | 0 | Not started
C004 | Warehouse D | T210 | Plumbing Installations | Emma White | Not Started | High | 2024-11-20 | 2024-12-03 |  | 0 | Copper Wires | Industrial Park | 23860.77 | 0 | Not started
C004 | Warehouse D | T659 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2024-09-06 | 2024-09-16 |  | 0 | Paint | Industrial Park | 47698.25 | 0 | Not started
C004 | Warehouse D | T433 | Interior Painting | Grace Allen | Not Started | High | 2023-12-04 | 2023-12-28 |  | 0 | Roofing Sheets | Industrial Park | 41648.88 | 0 | Not started
C004 | Warehouse D | T326 | Roofing | Dave Brown | Completed | Low | 2023-04-10 | 2023-05-04 | 2023-05-04 | 100 | PVC Pipes | Industrial Park | 30901.79 | 30799.68 | No issues
C001 | Residential Building A | T737 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-04-04 | 2024-04-27 | 2024-04-27 | 100 | Cement | Plot 21, Riverside | 35510.87 | 28249.26 | No issues
C003 | Office Tower C | T919 | Foundation Excavation | Grace Allen | Completed | High | 2023-05-15 | 2023-06-04 | 2023-06-04 | 100 | PVC Pipes | Downtown Avenue | 39505.9 | 24136.04 | No issues
C001 | Residential Building A | T202 | Concrete Pouring | Mike Adams | Not Started | High | 2024-03-14 | 2024-03-24 |  | 0 | Steel Beams | Plot 21, Riverside | 24107.77 | 0 | Not started
C001 | Residential Building A | T332 | Steel Framework Setup | John Miller | Not Started | Low | 2024-08-19 | 2024-08-31 |  | 0 | Copper Wires | Plot 21, Riverside | 25946.5 | 0 | Not started
C001 | Residential Building A | T249 | Roofing | Mike Adams | Blocked | Medium | 2023-01-07 | 2023-01-25 |  | 0 | Paint | Plot 21, Riverside | 34900.77 | 31157.59 | Not started
C001 | Residential Building A | T338 | Plumbing Installations | Emma White | In Progress | High | 2024-08-19 | 2024-08-29 |  | 11 | Steel Beams | Plot 21, Riverside | 49745.66 | 33372.37 | In progress
C002 | Shopping Complex B | T204 | Interior Painting | Grace Allen | Blocked | Low | 2023-10-08 | 2023-10-22 |  | 0 | Concrete | Market Street | 44917.33 | 75673.58 | Not started
C001 | Residential Building A | T609 | Steel Framework Setup | Grace Allen | In Progress | Low | 2023-06-15 | 2023-07-09 |  | 6 | Roofing Sheets | Plot 21, Riverside | 10225.6 | 9750.91 | In progress
C003 | Office Tower C | T312 | Site Survey | Grace Allen | Blocked | High | 2023-03-09 | 2023-04-06 |  | 0 | PVC Pipes | Downtown Avenue | 9383.79 | 6053.15 | Not started
C001 | Residential Building A | T488 | Plumbing Installations | Grace Allen | Not Started | Medium | 2023-04-01 | 2023-04-21 |  | 0 | Roofing Sheets | Plot 21, Riverside | 19560.25 | 0 | Not started
C002 | Shopping Complex B | T275 | Steel Framework Setup | Dave Brown | In Progress | Low | 2023-02-11 | 2023-02-18 |  | 86 | PVC Pipes | Market Street | 37464.8 | 48863.7 | In progress
C001 | Residential Building A | T109 | Site Survey | Sarah Johnson | Completed | High | 2024-12-09 | 2025-01-06 | 2025-01-06 | 100 | Roofing Sheets | Plot 21, Riverside | 35072.76 | 26576.35 | No issues
C003 | Office Tower C | T525 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2024-03-14 | 2024-04-08 |  | 0 | Paint | Downtown Avenue | 35164.85 | 0 | Not started
C002 | Shopping Complex B | T953 | Roofing | Carlos Rivera | Not Started | Low | 2024-10-21 | 2024-11-18 |  | 0 | Rebar | Market Street | 17723.13 | 0 | Not started
C004 | Warehouse D | T273 | Roofing | Carlos Rivera | Completed | Low | 2023-09-09 | 2023-09-22 | 2023-09-22 | 100 | Roofing Sheets | Industrial Park | 23605.66 | 19477.24 | No issues
C004 | Warehouse D | T108 | Roofing | Carlos Rivera | Blocked | Low | 2024-10-05 | 2024-10-24 |  | 0 | Steel Beams | Industrial Park | 40912.17 | 38645.62 | Not started
C004 | Warehouse D | T728 | Site Survey | Emma White | Blocked | Low | 2024-04-28 | 2024-05-06 |  | 0 | Steel Beams | Industrial Park | 44035.19 | 43748.36 | Not started
C001 | Residential Building A | T734 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2023-08-16 | 2023-09-08 |  | 69 | Steel Beams | Plot 21, Riverside | 12834.88 | 9811.58 | In progress
C004 | Warehouse D | T323 | Electrical Wiring | Mike Adams | Blocked | Medium | 2024-01-27 | 2024-02-12 |  | 0 | PVC Pipes | Industrial Park | 45861.06 | 40691.3 | Not started
C001 | Residential Building A | T596 | Electrical Wiring | Rachel Green | Completed | High | 2024-11-14 | 2024-12-06 | 2024-12-06 | 100 | PVC Pipes | Plot 21, Riverside | 49135.12 | 49358.63 | No issues
C004 | Warehouse D | T825 | Roofing | John Miller | Not Started | Low | 2023-12-13 | 2024-01-09 |  | 0 | PVC Pipes | Industrial Park | 17232.09 | 0 | Not started
C002 | Shopping Complex B | T395 | Foundation Excavation | Grace Allen | Completed | High | 2023-03-07 | 2023-03-24 | 2023-03-24 | 100 | Copper Wires | Market Street | 9455.25 | 31907.86 | No issues
C001 | Residential Building A | T551 | Roofing | Mike Adams | Blocked | Medium | 2023-03-24 | 2023-03-31 |  | 0 | Paint | Plot 21, Riverside | 36829.38 | 23986.49 | Not started
C003 | Office Tower C | T834 | Concrete Pouring | Emma White | Completed | Medium | 2023-03-28 | 2023-04-07 | 2023-04-07 | 100 | Cement | Downtown Avenue | 9350.83 | 10840.54 | No issues
C004 | Warehouse D | T605 | Plumbing Installations | John Miller | Not Started | Medium | 2023-07-05 | 2023-07-12 |  | 0 | PVC Pipes | Industrial Park | 42358.22 | 0 | Not started
C003 | Office Tower C | T184 | Foundation Excavation | Carlos Rivera | Completed | High | 2023-03-23 | 2023-04-22 | 2023-04-22 | 100 | Rebar | Downtown Avenue | 11088.69 | 10879.1 | No issues
C002 | Shopping Complex B | T531 | Steel Framework Setup | Rachel Green | Blocked | High | 2023-08-11 | 2023-08-18 |  | 0 | Rebar | Market Street | 22968.64 | 50178.49 | Not started
C002 | Shopping Complex B | T682 | Interior Painting | Mike Adams | In Progress | Low | 2023-06-10 | 2023-07-01 |  | 73 | Cement | Market Street | 45238.72 | 62661.64 | In progress
C001 | Residential Building A | T717 | Interior Painting | Rachel Green | Completed | High | 2023-09-18 | 2023-10-09 | 2023-10-09 | 100 | Copper Wires | Plot 21, Riverside | 39896.94 | 26013.41 | No issues
C004 | Warehouse D | T638 | Site Survey | John Miller | In Progress | Low | 2023-06-28 | 2023-07-28 |  | 58 | Concrete | Industrial Park | 16504.61 | 11485.42 | In progress
C001 | Residential Building A | T163 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-11-02 | 2024-11-14 |  | 97 | Paint | Plot 21, Riverside | 5753.8 | 4916.84 | In progress
C004 | Warehouse D | T564 | Roofing | Sarah Johnson | Blocked | Low | 2023-10-08 | 2023-11-01 |  | 0 | Cement | Industrial Park | 49025.13 | 58771.19 | Not started
C004 | Warehouse D | T451 | Site Survey | Grace Allen | Not Started | Low | 2023-10-10 | 2023-10-23 |  | 0 | Copper Wires | Industrial Park | 46674.4 | 0 | Not started
C004 | Warehouse D | T813 | Site Survey | Grace Allen | Not Started | Medium | 2024-09-25 | 2024-10-18 |  | 0 | Concrete | Industrial Park | 21468.76 | 0 | Not started
C003 | Office Tower C | T994 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-10-17 | 2024-10-29 |  | 0 | Copper Wires | Downtown Avenue | 6671.09 | 0 | Not started
C004 | Warehouse D | T618 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-01-23 | 2024-02-20 | 2024-02-20 | 100 | Concrete | Industrial Park | 13570.85 | 8763.55 | No issues
C003 | Office Tower C | T941 | Foundation Excavation | Emma White | Blocked | High | 2024-11-11 | 2024-12-06 |  | 0 | Cement | Downtown Avenue | 41259.86 | 49050.66 | Not started
C003 | Office Tower C | T122 | Roofing | Carlos Rivera | Blocked | Low | 2024-09-05 | 2024-10-03 |  | 0 | Concrete | Downtown Avenue | 23041.79 | 17617.04 | Not started
C003 | Office Tower C | T581 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2024-03-14 | 2024-04-02 |  | 0 | PVC Pipes | Downtown Avenue | 9717.24 | 0 | Not started
C002 | Shopping Complex B | T349 | Electrical Wiring | Sarah Johnson | Completed | High | 2024-06-04 | 2024-06-21 | 2024-06-21 | 100 | PVC Pipes | Market Street | 5160.65 | 31482.37 | No issues
C001 | Residential Building A | T149 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-06-01 | 2023-06-16 |  | 88 | Rebar | Plot 21, Riverside | 21494.2 | 24370.67 | In progress
C003 | Office Tower C | T789 | Interior Painting | Mike Adams | Not Started | Low | 2023-08-21 | 2023-09-08 |  | 0 | PVC Pipes | Downtown Avenue | 25834.81 | 0 | Not started
C004 | Warehouse D | T357 | Electrical Wiring | Dave Brown | In Progress | Medium | 2023-09-02 | 2023-09-14 |  | 21 | Roofing Sheets | Industrial Park | 36658.87 | 36316.88 | In progress
C001 | Residential Building A | T852 | Roofing | John Miller | In Progress | Low | 2023-09-26 | 2023-10-17 |  | 75 | Steel Beams | Plot 21, Riverside | 26259.91 | 28400.94 | In progress
C003 | Office Tower C | T439 | Interior Painting | Grace Allen | Completed | Medium | 2023-04-21 | 2023-05-10 | 2023-05-10 | 100 | Copper Wires | Downtown Avenue | 40885.02 | 42381.67 | No issues
C003 | Office Tower C | T254 | Concrete Pouring | Dave Brown | Completed | Low | 2024-03-19 | 2024-04-08 | 2024-04-08 | 100 | Concrete | Downtown Avenue | 44170.57 | 27286.97 | No issues
C004 | Warehouse D | T577 | Site Survey | Rachel Green | In Progress | Medium | 2023-06-22 | 2023-06-29 |  | 82 | Paint | Industrial Park | 38457.53 | 32029.5 | In progress
C002 | Shopping Complex B | T227 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-09-18 | 2024-09-28 |  | 0 | Steel Beams | Market Street | 35479.19 | 0 | Not started
C004 | Warehouse D | T274 | Steel Framework Setup | Carlos Rivera | Not Started | High | 2023-12-23 | 2024-01-18 |  | 0 | Copper Wires | Industrial Park | 7381.54 | 0 | Not started
C001 | Residential Building A | T865 | Interior Painting | Grace Allen | In Progress | High | 2024-10-11 | 2024-11-05 |  | 6 | PVC Pipes | Plot 21, Riverside | 47495.56 | 52358.24 | In progress
C001 | Residential Building A | T651 | Roofing | Dave Brown | Blocked | Low | 2024-04-03 | 2024-04-17 |  | 0 | Roofing Sheets | Plot 21, Riverside | 49012.57 | 54408.02 | Not started
C002 | Shopping Complex B | T424 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-05-07 | 2023-05-20 |  | 0 | Paint | Market Street | 44863.61 | 0 | Not started
C004 | Warehouse D | T317 | Steel Framework Setup | Dave Brown | Blocked | Low | 2023-10-14 | 2023-11-05 |  | 0 | Roofing Sheets | Industrial Park | 6042.85 | 4024.13 | Not started
C004 | Warehouse D | T233 | Roofing | Dave Brown | Completed | Medium | 2023-09-12 | 2023-10-07 | 2023-10-07 | 100 | PVC Pipes | Industrial Park | 8448.78 | 6724.57 | No issues
C001 | Residential Building A | T741 | Roofing | Mike Adams | Completed | Medium | 2024-03-02 | 2024-03-15 | 2024-03-15 | 100 | Steel Beams | Plot 21, Riverside | 46182.64 | 42329.52 | No issues
C001 | Residential Building A | T956 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2023-11-26 | 2023-12-10 |  | 0 | Cement | Plot 21, Riverside | 11682.56 | 0 | Not started
C001 | Residential Building A | T415 | Electrical Wiring | Emma White | Not Started | Low | 2024-10-25 | 2024-11-03 |  | 0 | Copper Wires | Plot 21, Riverside | 11455.87 | 0 | Not started
C001 | Residential Building A | T154 | Electrical Wiring | Sarah Johnson | Not Started | High | 2023-12-25 | 2024-01-04 |  | 0 | Steel Beams | Plot 21, Riverside | 7733.59 | 0 | Not started
C003 | Office Tower C | T799 | Site Survey | John Miller | Completed | High | 2023-07-13 | 2023-08-06 | 2023-08-06 | 100 | Cement | Downtown Avenue | 44272.84 | 35273.81 | No issues
C004 | Warehouse D | T415 | Electrical Wiring | Dave Brown | Blocked | Medium | 2023-02-19 | 2023-03-03 |  | 0 | Rebar | Industrial Park | 31612.53 | 28203.73 | Not started
C003 | Office Tower C | T329 | Roofing | Emma White | In Progress | High | 2023-11-09 | 2023-11-26 |  | 29 | Steel Beams | Downtown Avenue | 6599.36 | 5213.84 | In progress
C003 | Office Tower C | T783 | Interior Painting | Sarah Johnson | Blocked | High | 2023-05-18 | 2023-05-29 |  | 0 | Cement | Downtown Avenue | 48813.09 | 34083.32 | Not started
C001 | Residential Building A | T417 | Foundation Excavation | Grace Allen | Not Started | Low | 2024-11-19 | 2024-12-07 |  | 0 | Paint | Plot 21, Riverside | 32895.02 | 0 | Not started
C003 | Office Tower C | T368 | Plumbing Installations | Grace Allen | In Progress | High | 2023-06-21 | 2023-07-17 |  | 97 | Roofing Sheets | Downtown Avenue | 17453.51 | 11904.95 | In progress
C002 | Shopping Complex B | T224 | Site Survey | Emma White | Blocked | High | 2023-12-20 | 2024-01-03 |  | 0 | Concrete | Market Street | 6536.94 | 31988.52 | Not started
C003 | Office Tower C | T452 | Plumbing Installations | Mike Adams | In Progress | Medium | 2024-06-10 | 2024-06-30 |  | 86 | PVC Pipes | Downtown Avenue | 10464.44 | 6744.15 | In progress
C003 | Office Tower C | T786 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2023-04-10 | 2023-04-24 |  | 0 | Cement | Downtown Avenue | 20304.08 | 12892.4 | Not started
C002 | Shopping Complex B | T273 | Plumbing Installations | Mike Adams | Not Started | High | 2024-02-05 | 2024-03-05 |  | 0 | Rebar | Market Street | 43225.33 | 0 | Not started
C002 | Shopping Complex B | T175 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2023-08-14 | 2023-08-24 |  | 0 | Copper Wires | Market Street | 24639.24 | 40410.28 | Not started
C004 | Warehouse D | T606 | Site Survey | Emma White | In Progress | High | 2024-10-11 | 2024-10-30 |  | 51 | Steel Beams | Industrial Park | 30098.16 | 33746.48 | In progress
C002 | Shopping Complex B | T148 | Site Survey | John Miller | Completed | High | 2023-07-25 | 2023-08-15 | 2023-08-15 | 100 | Copper Wires | Market Street | 13598.21 | 39193.77 | No issues
C002 | Shopping Complex B | T236 | Plumbing Installations | Dave Brown | Completed | Low | 2024-09-14 | 2024-09-27 | 2024-09-27 | 100 | Steel Beams | Market Street | 22306.49 | 41065.8 | No issues
C004 | Warehouse D | T600 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2023-05-01 | 2023-05-17 |  | 76 | Roofing Sheets | Industrial Park | 38511.32 | 35014.38 | In progress
C002 | Shopping Complex B | T191 | Interior Painting | Sarah Johnson | Blocked | Medium | 2023-11-26 | 2023-12-17 |  | 0 | Cement | Market Street | 11799.66 | 36904.43 | Not started
C004 | Warehouse D | T201 | Roofing | Carlos Rivera | Not Started | High | 2024-01-15 | 2024-01-22 |  | 0 | Concrete | Industrial Park | 11707.35 | 0 | Not started
C002 | Shopping Complex B | T478 | Steel Framework Setup | Emma White | Not Started | Medium | 2024-06-11 | 2024-06-18 |  | 0 | Steel Beams | Market Street | 8040.15 | 0 | Not started
C002 | Shopping Complex B | T908 | Plumbing Installations | John Miller | Completed | High | 2024-07-15 | 2024-08-07 | 2024-08-07 | 100 | Paint | Market Street | 22210.72 | 41083.92 | No issues
C004 | Warehouse D | T841 | Concrete Pouring | Grace Allen | Completed | High | 2023-12-13 | 2023-12-28 | 2023-12-28 | 100 | PVC Pipes | Industrial Park | 20040.85 | 14538.21 | No issues
C001 | Residential Building A | T990 | Foundation Excavation | Grace Allen | Completed | Medium | 2023-07-20 | 2023-08-18 | 2023-08-18 | 100 | Paint | Plot 21, Riverside | 31928.18 | 32432.67 | No issues
C003 | Office Tower C | T328 | Plumbing Installations | Emma White | Not Started | Medium | 2024-07-02 | 2024-07-30 |  | 0 | Roofing Sheets | Downtown Avenue | 36966.31 | 0 | Not started
C003 | Office Tower C | T313 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-05-28 | 2023-06-25 |  | 0 | Concrete | Downtown Avenue | 46408.54 | 0 | Not started
C001 | Residential Building A | T184 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2023-01-12 | 2023-01-21 |  | 0 | Paint | Plot 21, Riverside | 14705.18 | 0 | Not started
C002 | Shopping Complex B | T227 | Roofing | John Miller | Not Started | Low | 2023-02-05 | 2023-02-22 |  | 0 | Paint | Market Street | 46107.69 | 0 | Not started
C004 | Warehouse D | T968 | Site Survey | Mike Adams | Completed | Low | 2024-05-20 | 2024-06-16 | 2024-06-16 | 100 | PVC Pipes | Industrial Park | 7727.29 | 5492.04 | No issues
C001 | Residential Building A | T556 | Plumbing Installations | John Miller | Blocked | High | 2023-09-07 | 2023-10-06 |  | 0 | PVC Pipes | Plot 21, Riverside | 33482.23 | 38219.64 | Not started
C003 | Office Tower C | T307 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-04-01 | 2024-04-26 |  | 69 | Copper Wires | Downtown Avenue | 13642.22 | 12349.33 | In progress
C003 | Office Tower C | T478 | Plumbing Installations | Dave Brown | Not Started | High | 2023-10-19 | 2023-11-02 |  | 0 | Paint | Downtown Avenue | 10029.45 | 0 | Not started
C001 | Residential Building A | T846 | Site Survey | Emma White | Blocked | Low | 2024-02-03 | 2024-02-21 |  | 0 | Copper Wires | Plot 21, Riverside | 44822 | 51086.01 | Not started
C003 | Office Tower C | T316 | Foundation Excavation | Rachel Green | Not Started | Low | 2023-01-03 | 2023-01-26 |  | 0 | Rebar | Downtown Avenue | 46865.23 | 0 | Not started
C003 | Office Tower C | T374 | Concrete Pouring | Mike Adams | Completed | Medium | 2023-02-01 | 2023-02-17 | 2023-02-17 | 100 | Rebar | Downtown Avenue | 5273.92 | 3423.87 | No issues
C002 | Shopping Complex B | T959 | Roofing | Sarah Johnson | Completed | High | 2023-03-27 | 2023-04-10 | 2023-04-10 | 100 | Concrete | Market Street | 13678.74 | 36327.54 | No issues
C003 | Office Tower C | T834 | Concrete Pouring | Emma White | Completed | High | 2023-01-14 | 2023-01-26 | 2023-01-26 | 100 | Concrete | Downtown Avenue | 10206.24 | 7667.69 | No issues
C002 | Shopping Complex B | T979 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-03-28 | 2023-04-19 |  | 0 | Paint | Market Street | 35421.94 | 54404.12 | Not started
C003 | Office Tower C | T903 | Roofing | Dave Brown | In Progress | Low | 2024-11-20 | 2024-12-17 |  | 5 | Rebar | Downtown Avenue | 10128.89 | 9834.72 | In progress
C004 | Warehouse D | T683 | Site Survey | Mike Adams | Not Started | High | 2024-11-22 | 2024-12-20 |  | 0 | Cement | Industrial Park | 8044.39 | 0 | Not started
C003 | Office Tower C | T708 | Interior Painting | Carlos Rivera | Not Started | Low | 2024-02-05 | 2024-03-01 |  | 0 | Concrete | Downtown Avenue | 6772.69 | 0 | Not started
C002 | Shopping Complex B | T965 | Steel Framework Setup | Grace Allen | Blocked | High | 2023-09-11 | 2023-10-09 |  | 0 | Roofing Sheets | Market Street | 6166.93 | 32728.17 | Not started
C003 | Office Tower C | T993 | Site Survey | Dave Brown | Not Started | Medium | 2023-04-15 | 2023-05-12 |  | 0 | Concrete | Downtown Avenue | 40762.59 | 0 | Not started
C002 | Shopping Complex B | T788 | Roofing | Rachel Green | Completed | Low | 2024-02-06 | 2024-02-19 | 2024-02-19 | 100 | PVC Pipes | Market Street | 22941.81 | 48399.28 | No issues
C001 | Residential Building A | T385 | Interior Painting | Carlos Rivera | Not Started | High | 2023-09-18 | 2023-09-25 |  | 0 | Copper Wires | Plot 21, Riverside | 27952.1 | 0 | Not started
C001 | Residential Building A | T764 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-07-05 | 2024-07-13 |  | 94 | Cement | Plot 21, Riverside | 24937.82 | 22897.62 | In progress
C001 | Residential Building A | T487 | Foundation Excavation | Mike Adams | In Progress | Medium | 2023-07-19 | 2023-08-15 |  | 42 | Paint | Plot 21, Riverside | 30336.46 | 35759.4 | In progress
C004 | Warehouse D | T433 | Foundation Excavation | Grace Allen | Blocked | High | 2024-10-15 | 2024-11-12 |  | 0 | Paint | Industrial Park | 21072.77 | 17355.46 | Not started
C004 | Warehouse D | T793 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2024-04-13 | 2024-05-13 |  | 0 | Concrete | Industrial Park | 7916.08 | 7024.53 | Not started
C002 | Shopping Complex B | T301 | Site Survey | Sarah Johnson | Completed | Medium | 2023-01-12 | 2023-02-08 | 2023-02-08 | 100 | PVC Pipes | Market Street | 11614.04 | 36118.7 | No issues
C003 | Office Tower C | T733 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2023-03-15 | 2023-04-09 |  | 0 | PVC Pipes | Downtown Avenue | 49383.63 | 36452.79 | Not started
C004 | Warehouse D | T204 | Concrete Pouring | Mike Adams | Completed | Low | 2023-12-25 | 2024-01-01 | 2024-01-01 | 100 | Concrete | Industrial Park | 27820.15 | 17765.99 | No issues
C001 | Residential Building A | T902 | Concrete Pouring | John Miller | In Progress | High | 2023-02-06 | 2023-02-17 |  | 1 | Copper Wires | Plot 21, Riverside | 36426.03 | 37378.93 | In progress
C004 | Warehouse D | T737 | Plumbing Installations | John Miller | Not Started | Low | 2023-10-13 | 2023-10-22 |  | 0 | Paint | Industrial Park | 6300.24 | 0 | Not started
C004 | Warehouse D | T297 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-11-06 | 2024-11-15 |  | 0 | Copper Wires | Industrial Park | 25408.72 | 0 | Not started
C004 | Warehouse D | T916 | Concrete Pouring | Sarah Johnson | Completed | Low | 2024-08-26 | 2024-09-21 | 2024-09-21 | 100 | Paint | Industrial Park | 29768.92 | 19857.1 | No issues
C004 | Warehouse D | T112 | Interior Painting | Grace Allen | Completed | Medium | 2023-12-22 | 2024-01-04 | 2024-01-04 | 100 | Copper Wires | Industrial Park | 26433.44 | 20591.04 | No issues
C001 | Residential Building A | T919 | Electrical Wiring | Dave Brown | Completed | Low | 2024-07-23 | 2024-08-01 | 2024-08-01 | 100 | Copper Wires | Plot 21, Riverside | 27153.48 | 21360.33 | No issues
C001 | Residential Building A | T805 | Concrete Pouring | Rachel Green | Completed | High | 2023-08-04 | 2023-08-30 | 2023-08-30 | 100 | PVC Pipes | Plot 21, Riverside | 15121.36 | 13855.06 | No issues
C003 | Office Tower C | T984 | Interior Painting | Rachel Green | Completed | Medium | 2024-10-20 | 2024-11-18 | 2024-11-18 | 100 | Copper Wires | Downtown Avenue | 37412.69 | 28492.26 | No issues
C002 | Shopping Complex B | T719 | Interior Painting | Dave Brown | Blocked | High | 2023-04-07 | 2023-04-17 |  | 0 | Cement | Market Street | 33938.24 | 56805.28 | Not started
C001 | Residential Building A | T393 | Foundation Excavation | John Miller | In Progress | High | 2024-10-16 | 2024-10-29 |  | 5 | Concrete | Plot 21, Riverside | 41136.27 | 45213.43 | In progress
C001 | Residential Building A | T478 | Foundation Excavation | Rachel Green | Completed | High | 2023-05-05 | 2023-05-30 | 2023-05-30 | 100 | Paint | Plot 21, Riverside | 18163.14 | 11339.35 | No issues
C002 | Shopping Complex B | T773 | Foundation Excavation | Rachel Green | Completed | High | 2023-12-14 | 2023-12-25 | 2023-12-25 | 100 | Roofing Sheets | Market Street | 38603.9 | 49901.46 | No issues
C003 | Office Tower C | T989 | Concrete Pouring | Grace Allen | Completed | High | 2023-04-06 | 2023-04-24 | 2023-04-24 | 100 | Concrete | Downtown Avenue | 39191.12 | 43384.26 | No issues
C003 | Office Tower C | T922 | Steel Framework Setup | Emma White | Completed | High | 2023-04-19 | 2023-05-19 | 2023-05-19 | 100 | Copper Wires | Downtown Avenue | 31205.66 | 21546.19 | No issues
C003 | Office Tower C | T987 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-10-27 | 2023-11-05 |  | 40 | Roofing Sheets | Downtown Avenue | 10593.25 | 9280.65 | In progress
C002 | Shopping Complex B | T302 | Concrete Pouring | John Miller | Not Started | High | 2024-05-07 | 2024-06-02 |  | 0 | Cement | Market Street | 30756.28 | 0 | Not started
C003 | Office Tower C | T560 | Concrete Pouring | Mike Adams | Blocked | Medium | 2023-12-11 | 2023-12-19 |  | 0 | Paint | Downtown Avenue | 6726.68 | 7550.73 | Not started
C002 | Shopping Complex B | T664 | Site Survey | Dave Brown | Blocked | Medium | 2024-09-12 | 2024-09-20 |  | 0 | PVC Pipes | Market Street | 33339.19 | 56625.94 | Not started
C003 | Office Tower C | T807 | Roofing | John Miller | Completed | Low | 2023-02-24 | 2023-03-18 | 2023-03-18 | 100 | Rebar | Downtown Avenue | 48251.1 | 48190.79 | No issues
C001 | Residential Building A | T821 | Plumbing Installations | Dave Brown | Completed | Medium | 2023-05-01 | 2023-05-10 | 2023-05-10 | 100 | Concrete | Plot 21, Riverside | 32369.55 | 38567.38 | No issues
C002 | Shopping Complex B | T513 | Foundation Excavation | Mike Adams | Not Started | Medium | 2024-12-24 | 2025-01-17 |  | 0 | Paint | Market Street | 31920.51 | 0 | Not started
C001 | Residential Building A | T649 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-12-05 | 2024-12-13 |  | 52 | Rebar | Plot 21, Riverside | 9571.45 | 9350.83 | In progress
C001 | Residential Building A | T371 | Site Survey | Sarah Johnson | Blocked | Low | 2023-07-22 | 2023-08-03 |  | 0 | Roofing Sheets | Plot 21, Riverside | 46477.39 | 48217.65 | Not started
C003 | Office Tower C | T826 | Interior Painting | John Miller | Blocked | Medium | 2024-01-02 | 2024-01-24 |  | 0 | Concrete | Downtown Avenue | 20392.37 | 13549.4 | Not started
C002 | Shopping Complex B | T288 | Plumbing Installations | Grace Allen | Blocked | High | 2023-02-06 | 2023-02-21 |  | 0 | PVC Pipes | Market Street | 21692.33 | 50704.88 | Not started
C004 | Warehouse D | T258 | Interior Painting | Emma White | Completed | Medium | 2024-05-09 | 2024-05-22 | 2024-05-22 | 100 | Steel Beams | Industrial Park | 44997.37 | 32010.85 | No issues
C002 | Shopping Complex B | T765 | Steel Framework Setup | John Miller | Not Started | Medium | 2023-02-15 | 2023-03-15 |  | 0 | Roofing Sheets | Market Street | 7117.22 | 0 | Not started
C004 | Warehouse D | T214 | Roofing | Grace Allen | In Progress | Medium | 2023-02-17 | 2023-02-25 |  | 11 | PVC Pipes | Industrial Park | 22354.19 | 23533.17 | In progress
C003 | Office Tower C | T262 | Site Survey | Dave Brown | In Progress | Low | 2024-01-27 | 2024-02-21 |  | 97 | Concrete | Downtown Avenue | 31749.7 | 35092.85 | In progress
C001 | Residential Building A | T136 | Site Survey | Carlos Rivera | Blocked | Low | 2024-09-03 | 2024-09-17 |  | 0 | Steel Beams | Plot 21, Riverside | 36251.2 | 42882.15 | Not started
C001 | Residential Building A | T178 | Foundation Excavation | John Miller | Blocked | High | 2023-02-06 | 2023-02-19 |  | 0 | Steel Beams | Plot 21, Riverside | 36624.32 | 39739.39 | Not started
C001 | Residential Building A | T404 | Interior Painting | Dave Brown | Blocked | Medium | 2024-07-06 | 2024-08-03 |  | 0 | Copper Wires | Plot 21, Riverside | 45340.93 | 40963.7 | Not started
C004 | Warehouse D | T595 | Interior Painting | John Miller | In Progress | High | 2024-05-20 | 2024-06-11 |  | 49 | Cement | Industrial Park | 14872.21 | 9577.57 | In progress
C003 | Office Tower C | T458 | Plumbing Installations | Dave Brown | Not Started | Low | 2023-02-02 | 2023-03-01 |  | 0 | Roofing Sheets | Downtown Avenue | 39691.58 | 0 | Not started
C002 | Shopping Complex B | T411 | Site Survey | Mike Adams | Completed | Medium | 2024-04-27 | 2024-05-14 | 2024-05-14 | 100 | Copper Wires | Market Street | 37855.1 | 70434.94 | No issues
C001 | Residential Building A | T407 | Electrical Wiring | Sarah Johnson | In Progress | High | 2024-11-19 | 2024-12-11 |  | 70 | Roofing Sheets | Plot 21, Riverside | 6060.83 | 5501.26 | In progress
C004 | Warehouse D | T343 | Steel Framework Setup | John Miller | Completed | High | 2023-07-08 | 2023-07-28 | 2023-07-28 | 100 | Copper Wires | Industrial Park | 25604.89 | 18789.64 | No issues
C004 | Warehouse D | T248 | Concrete Pouring | John Miller | Blocked | Medium | 2024-10-15 | 2024-10-22 |  | 0 | Steel Beams | Industrial Park | 38660.87 | 26671.99 | Not started
C001 | Residential Building A | T597 | Electrical Wiring | Grace Allen | Completed | Low | 2024-04-01 | 2024-04-12 | 2024-04-12 | 100 | Steel Beams | Plot 21, Riverside | 15719.68 | 12435.37 | No issues
C003 | Office Tower C | T477 | Site Survey | Carlos Rivera | In Progress | High | 2023-01-16 | 2023-02-03 |  | 55 | Paint | Downtown Avenue | 12578.55 | 13758.61 | In progress
C002 | Shopping Complex B | T218 | Electrical Wiring | John Miller | In Progress | High | 2024-03-12 | 2024-03-27 |  | 27 | Roofing Sheets | Market Street | 13114 | 37755.49 | In progress
C001 | Residential Building A | T222 | Plumbing Installations | Mike Adams | In Progress | High | 2024-01-24 | 2024-02-12 |  | 17 | Cement | Plot 21, Riverside | 19290.28 | 17387.7 | In progress
C001 | Residential Building A | T644 | Interior Painting | Mike Adams | Blocked | Medium | 2024-02-02 | 2024-02-18 |  | 0 | Copper Wires | Plot 21, Riverside | 21387.55 | 20943.17 | Not started
C004 | Warehouse D | T530 | Site Survey | Rachel Green | Completed | High | 2024-03-20 | 2024-04-12 | 2024-04-12 | 100 | Cement | Industrial Park | 34962.55 | 33943.63 | No issues
C003 | Office Tower C | T595 | Roofing | Rachel Green | Completed | Low | 2024-10-07 | 2024-11-03 | 2024-11-03 | 100 | Concrete | Downtown Avenue | 26467.36 | 19464.58 | No issues
C002 | Shopping Complex B | T382 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-08-13 | 2023-09-07 |  | 0 | Cement | Market Street | 18302.32 | 0 | Not started
C001 | Residential Building A | T884 | Plumbing Installations | Emma White | Completed | Low | 2024-06-18 | 2024-07-05 | 2024-07-05 | 100 | Cement | Plot 21, Riverside | 38539.47 | 29078.73 | No issues
C004 | Warehouse D | T361 | Interior Painting | Dave Brown | Blocked | High | 2023-01-27 | 2023-02-15 |  | 0 | Concrete | Industrial Park | 8795.88 | 9029.2 | Not started
C002 | Shopping Complex B | T836 | Electrical Wiring | Dave Brown | In Progress | Low | 2024-08-05 | 2024-08-17 |  | 12 | Roofing Sheets | Market Street | 25973.72 | 46596.85 | In progress
C002 | Shopping Complex B | T147 | Concrete Pouring | Dave Brown | Completed | High | 2023-09-18 | 2023-10-05 | 2023-10-05 | 100 | PVC Pipes | Market Street | 16180.09 | 41837.09 | No issues
C001 | Residential Building A | T937 | Plumbing Installations | Emma White | Completed | High | 2024-11-09 | 2024-11-26 | 2024-11-26 | 100 | Steel Beams | Plot 21, Riverside | 45369.54 | 53982.24 | No issues
C001 | Residential Building A | T523 | Roofing | John Miller | Completed | Medium | 2023-11-19 | 2023-12-11 | 2023-12-11 | 100 | Paint | Plot 21, Riverside | 23652.89 | 14412.44 | No issues
C002 | Shopping Complex B | T665 | Site Survey | Grace Allen | Completed | Low | 2023-03-10 | 2023-04-06 | 2023-04-06 | 100 | Steel Beams | Market Street | 27860.73 | 51472.67 | No issues
C002 | Shopping Complex B | T989 | Foundation Excavation | Rachel Green | Blocked | Medium | 2023-07-24 | 2023-08-06 |  | 0 | Copper Wires | Market Street | 21717.47 | 44060.35 | Not started
C003 | Office Tower C | T392 | Electrical Wiring | John Miller | Completed | Medium | 2023-10-27 | 2023-11-07 | 2023-11-07 | 100 | Roofing Sheets | Downtown Avenue | 36782.23 | 27430.85 | No issues
C002 | Shopping Complex B | T375 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2024-11-28 | 2024-12-15 |  | 0 | Steel Beams | Market Street | 37668.41 | 61355.55 | Not started
C001 | Residential Building A | T826 | Foundation Excavation | Dave Brown | Blocked | Low | 2024-12-02 | 2024-12-15 |  | 0 | Steel Beams | Plot 21, Riverside | 21132.93 | 23733.3 | Not started
C004 | Warehouse D | T962 | Foundation Excavation | Emma White | In Progress | Low | 2023-11-01 | 2023-11-24 |  | 1 | Paint | Industrial Park | 25956.55 | 16386.11 | In progress
C004 | Warehouse D | T307 | Interior Painting | Rachel Green | Not Started | High | 2024-07-04 | 2024-07-15 |  | 0 | Paint | Industrial Park | 10252.64 | 0 | Not started
C003 | Office Tower C | T211 | Plumbing Installations | Emma White | Not Started | Low | 2024-09-03 | 2024-09-24 |  | 0 | Rebar | Downtown Avenue | 27260.31 | 0 | Not started
C002 | Shopping Complex B | T283 | Steel Framework Setup | John Miller | Completed | High | 2023-08-08 | 2023-08-21 | 2023-08-21 | 100 | Paint | Market Street | 47951.91 | 75627.36 | No issues
C003 | Office Tower C | T935 | Steel Framework Setup | Emma White | Completed | Medium | 2023-06-08 | 2023-06-26 | 2023-06-26 | 100 | Steel Beams | Downtown Avenue | 47327.65 | 35670.89 | No issues
C004 | Warehouse D | T397 | Interior Painting | Emma White | Blocked | Medium | 2024-10-10 | 2024-11-03 |  | 0 | Copper Wires | Industrial Park | 29539.73 | 27789.2 | Not started
C001 | Residential Building A | T310 | Site Survey | Sarah Johnson | Completed | Low | 2024-11-08 | 2024-12-02 | 2024-12-02 | 100 | Concrete | Plot 21, Riverside | 41718.84 | 37070.76 | No issues
C004 | Warehouse D | T988 | Concrete Pouring | Rachel Green | Completed | Low | 2024-02-28 | 2024-03-17 | 2024-03-17 | 100 | Roofing Sheets | Industrial Park | 37410.86 | 42740.99 | No issues
C004 | Warehouse D | T421 | Foundation Excavation | Rachel Green | Not Started | Low | 2024-01-12 | 2024-02-07 |  | 0 | PVC Pipes | Industrial Park | 20895.45 | 0 | Not started
C001 | Residential Building A | T901 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-12-09 | 2023-12-23 |  | 0 | PVC Pipes | Plot 21, Riverside | 16720.03 | 0 | Not started
C001 | Residential Building A | T522 | Site Survey | Mike Adams | Blocked | Medium | 2024-01-25 | 2024-02-16 |  | 0 | Copper Wires | Plot 21, Riverside | 8756.8 | 9180.58 | Not started
C003 | Office Tower C | T467 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2023-05-06 | 2023-06-03 |  | 0 | Paint | Downtown Avenue | 24503.31 | 0 | Not started
C002 | Shopping Complex B | T969 | Electrical Wiring | Grace Allen | In Progress | Medium | 2023-02-17 | 2023-03-14 |  | 71 | Copper Wires | Market Street | 11345.13 | 33232.92 | In progress
C002 | Shopping Complex B | T276 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-02-08 | 2023-02-19 | 2023-02-19 | 100 | Cement | Market Street | 17932.22 | 44302.78 | No issues
C004 | Warehouse D | T677 | Site Survey | Carlos Rivera | Not Started | Medium | 2023-08-26 | 2023-09-03 |  | 0 | Roofing Sheets | Industrial Park | 18794.05 | 0 | Not started
C001 | Residential Building A | T536 | Roofing | Emma White | Completed | High | 2024-08-14 | 2024-08-26 | 2024-08-26 | 100 | Paint | Plot 21, Riverside | 34919.81 | 27577.7 | No issues
C003 | Office Tower C | T822 | Site Survey | Carlos Rivera | Blocked | Medium | 2023-11-03 | 2023-11-27 |  | 0 | Rebar | Downtown Avenue | 30481.17 | 20206.15 | Not started
C002 | Shopping Complex B | T146 | Foundation Excavation | Emma White | In Progress | Medium | 2024-11-03 | 2024-11-19 |  | 78 | Copper Wires | Market Street | 44032.35 | 62463.79 | In progress
C003 | Office Tower C | T748 | Steel Framework Setup | Sarah Johnson | Completed | Low | 2024-10-04 | 2024-10-22 | 2024-10-22 | 100 | Steel Beams | Downtown Avenue | 9443.35 | 9935.75 | No issues
C002 | Shopping Complex B | T976 | Interior Painting | Sarah Johnson | In Progress | High | 2024-12-06 | 2024-12-25 |  | 94 | Concrete | Market Street | 46042.43 | 75060.23 | In progress
C003 | Office Tower C | T141 | Electrical Wiring | Dave Brown | In Progress | High | 2024-05-23 | 2024-05-31 |  | 62 | Rebar | Downtown Avenue | 25577.71 | 29355.67 | In progress
C001 | Residential Building A | T839 | Plumbing Installations | Sarah Johnson | Blocked | High | 2023-09-26 | 2023-10-11 |  | 0 | PVC Pipes | Plot 21, Riverside | 17149.74 | 14955.15 | Not started
C003 | Office Tower C | T887 | Steel Framework Setup | Mike Adams | Not Started | High | 2024-05-28 | 2024-06-07 |  | 0 | Rebar | Downtown Avenue | 27226.26 | 0 | Not started
C001 | Residential Building A | T546 | Site Survey | Emma White | Completed | Medium | 2023-05-03 | 2023-05-12 | 2023-05-12 | 100 | Cement | Plot 21, Riverside | 39142.94 | 27573.79 | No issues
C003 | Office Tower C | T711 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2024-04-06 | 2024-04-27 |  | 38 | Cement | Downtown Avenue | 9757.12 | 7027.84 | In progress
C001 | Residential Building A | T464 | Site Survey | Mike Adams | Not Started | Medium | 2023-05-18 | 2023-06-15 |  | 0 | Paint | Plot 21, Riverside | 15651.87 | 0 | Not started
C002 | Shopping Complex B | T954 | Interior Painting | Carlos Rivera | In Progress | Low | 2024-07-28 | 2024-08-19 |  | 27 | Steel Beams | Market Street | 40370.15 | 60283.07 | In progress
C003 | Office Tower C | T974 | Steel Framework Setup | Emma White | Not Started | Medium | 2024-03-26 | 2024-04-19 |  | 0 | PVC Pipes | Downtown Avenue | 46725.38 | 0 | Not started
C002 | Shopping Complex B | T254 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-07-05 | 2024-07-17 |  | 89 | Paint | Market Street | 6677.32 | 32422.59 | In progress
C003 | Office Tower C | T469 | Site Survey | Carlos Rivera | Completed | Medium | 2024-04-28 | 2024-05-09 | 2024-05-09 | 100 | Concrete | Downtown Avenue | 19570.46 | 23157.68 | No issues
C003 | Office Tower C | T909 | Site Survey | Emma White | Not Started | Low | 2023-12-21 | 2023-12-31 |  | 0 | Steel Beams | Downtown Avenue | 38215.4 | 0 | Not started
C002 | Shopping Complex B | T786 | Interior Painting | John Miller | In Progress | Low | 2024-02-02 | 2024-02-18 |  | 12 | Paint | Market Street | 36421.64 | 64097.31 | In progress
C003 | Office Tower C | T119 | Steel Framework Setup | John Miller | Not Started | Medium | 2024-12-16 | 2024-12-26 |  | 0 | Paint | Downtown Avenue | 24765.06 | 0 | Not started
C004 | Warehouse D | T444 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-06-13 | 2024-06-30 |  | 0 | Rebar | Industrial Park | 9135.16 | 10192.18 | Not started
C002 | Shopping Complex B | T320 | Interior Painting | Rachel Green | Completed | Low | 2024-12-13 | 2024-12-22 | 2024-12-22 | 100 | PVC Pipes | Market Street | 39514.37 | 56780.33 | No issues
C002 | Shopping Complex B | T569 | Foundation Excavation | Sarah Johnson | Completed | High | 2023-12-03 | 2023-12-31 | 2023-12-31 | 100 | PVC Pipes | Market Street | 33538 | 49511.33 | No issues
C002 | Shopping Complex B | T265 | Concrete Pouring | Dave Brown | In Progress | Medium | 2023-04-20 | 2023-04-30 |  | 55 | Paint | Market Street | 46059.77 | 58311.56 | In progress
C003 | Office Tower C | T971 | Plumbing Installations | John Miller | Blocked | High | 2024-09-21 | 2024-10-04 |  | 0 | Steel Beams | Downtown Avenue | 16114.08 | 13247.64 | Not started
C004 | Warehouse D | T347 | Plumbing Installations | Sarah Johnson | Not Started | High | 2023-11-28 | 2023-12-08 |  | 0 | Copper Wires | Industrial Park | 37649.69 | 0 | Not started
C002 | Shopping Complex B | T989 | Plumbing Installations | Dave Brown | Completed | Low | 2023-06-01 | 2023-06-10 | 2023-06-10 | 100 | Concrete | Market Street | 46840.52 | 65769.4 | No issues
C001 | Residential Building A | T796 | Steel Framework Setup | Rachel Green | Not Started | High | 2024-03-16 | 2024-03-24 |  | 0 | Rebar | Plot 21, Riverside | 12855.05 | 0 | Not started
C003 | Office Tower C | T883 | Electrical Wiring | Carlos Rivera | Completed | Low | 2024-05-09 | 2024-06-02 | 2024-06-02 | 100 | Roofing Sheets | Downtown Avenue | 29059.93 | 34794.8 | No issues
C004 | Warehouse D | T794 | Foundation Excavation | John Miller | Blocked | High | 2023-03-23 | 2023-04-22 |  | 0 | Paint | Industrial Park | 27014.83 | 20929.37 | Not started
C002 | Shopping Complex B | T263 | Site Survey | John Miller | Completed | High | 2024-08-23 | 2024-09-12 | 2024-09-12 | 100 | Steel Beams | Market Street | 26308.03 | 54436.35 | No issues
C001 | Residential Building A | T397 | Roofing | Carlos Rivera | Not Started | Medium | 2023-09-21 | 2023-10-03 |  | 0 | Concrete | Plot 21, Riverside | 42809.68 | 0 | Not started
C003 | Office Tower C | T363 | Concrete Pouring | Emma White | Completed | Medium | 2024-05-19 | 2024-06-13 | 2024-06-13 | 100 | Cement | Downtown Avenue | 42556.33 | 28978.28 | No issues
C001 | Residential Building A | T461 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-05-19 | 2024-06-05 |  | 0 | Roofing Sheets | Plot 21, Riverside | 14005.73 | 0 | Not started
C001 | Residential Building A | T862 | Plumbing Installations | Mike Adams | Not Started | Medium | 2023-06-25 | 2023-07-16 |  | 0 | PVC Pipes | Plot 21, Riverside | 25298.97 | 0 | Not started
C003 | Office Tower C | T959 | Interior Painting | Sarah Johnson | Blocked | Medium | 2024-02-13 | 2024-03-06 |  | 0 | Roofing Sheets | Downtown Avenue | 19319 | 13566.86 | Not started
C004 | Warehouse D | T578 | Steel Framework Setup | Emma White | Blocked | Medium | 2024-08-24 | 2024-09-14 |  | 0 | Copper Wires | Industrial Park | 18163.83 | 15064.06 | Not started
C001 | Residential Building A | T289 | Site Survey | Grace Allen | Blocked | Medium | 2023-07-08 | 2023-07-22 |  | 0 | Copper Wires | Plot 21, Riverside | 22127.62 | 19799.57 | Not started
C002 | Shopping Complex B | T691 | Plumbing Installations | Carlos Rivera | Completed | Low | 2023-05-03 | 2023-05-13 | 2023-05-13 | 100 | Roofing Sheets | Market Street | 20420.3 | 39858.76 | No issues
C001 | Residential Building A | T571 | Interior Painting | Sarah Johnson | Blocked | High | 2024-01-15 | 2024-02-02 |  | 0 | Rebar | Plot 21, Riverside | 19872.28 | 13968.48 | Not started
C004 | Warehouse D | T891 | Electrical Wiring | Grace Allen | Not Started | Medium | 2024-02-19 | 2024-03-04 |  | 0 | Steel Beams | Industrial Park | 44133.96 | 0 | Not started
C001 | Residential Building A | T550 | Interior Painting | Grace Allen | Blocked | Medium | 2023-03-10 | 2023-03-26 |  | 0 | PVC Pipes | Plot 21, Riverside | 42013.73 | 29100.3 | Not started
C002 | Shopping Complex B | T605 | Site Survey | Emma White | Completed | Low | 2023-02-05 | 2023-02-18 | 2023-02-18 | 100 | PVC Pipes | Market Street | 9516.02 | 33169.39 | No issues
C002 | Shopping Complex B | T104 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2024-02-02 | 2024-02-21 |  | 0 | Copper Wires | Market Street | 32805.72 | 53195.91 | Not started
C002 | Shopping Complex B | T486 | Steel Framework Setup | Emma White | Blocked | Low | 2024-12-27 | 2025-01-04 |  | 0 | Steel Beams | Market Street | 24968.78 | 54816.04 | Not started
C003 | Office Tower C | T634 | Site Survey | John Miller | Not Started | Low | 2024-07-08 | 2024-07-28 |  | 0 | PVC Pipes | Downtown Avenue | 39832.25 | 0 | Not started
C002 | Shopping Complex B | T348 | Plumbing Installations | Dave Brown | Completed | Medium | 2024-09-13 | 2024-10-04 | 2024-10-04 | 100 | Copper Wires | Market Street | 8298.97 | 30867.19 | No issues
C001 | Residential Building A | T532 | Electrical Wiring | Dave Brown | Blocked | Medium | 2023-02-04 | 2023-02-14 |  | 0 | PVC Pipes | Plot 21, Riverside | 35703.19 | 34076.68 | Not started
C002 | Shopping Complex B | T117 | Plumbing Installations | Emma White | Blocked | Medium | 2024-03-23 | 2024-03-30 |  | 0 | Paint | Market Street | 39478.21 | 56585.17 | Not started
C003 | Office Tower C | T592 | Foundation Excavation | Emma White | Completed | Medium | 2023-12-07 | 2023-12-18 | 2023-12-18 | 100 | Concrete | Downtown Avenue | 46451.51 | 34426.7 | No issues
C002 | Shopping Complex B | T702 | Concrete Pouring | Dave Brown | Completed | Low | 2024-06-11 | 2024-06-29 | 2024-06-29 | 100 | PVC Pipes | Market Street | 12061.35 | 33988.14 | No issues
C004 | Warehouse D | T945 | Interior Painting | Carlos Rivera | Not Started | High | 2023-02-04 | 2023-02-16 |  | 0 | Roofing Sheets | Industrial Park | 13088.09 | 0 | Not started
C004 | Warehouse D | T140 | Foundation Excavation | Carlos Rivera | Completed | High | 2023-02-26 | 2023-03-14 | 2023-03-14 | 100 | Rebar | Industrial Park | 45898.32 | 42723.95 | No issues
C003 | Office Tower C | T426 | Electrical Wiring | Mike Adams | Blocked | High | 2023-10-21 | 2023-10-28 |  | 0 | Roofing Sheets | Downtown Avenue | 26030.91 | 26462.65 | Not started
C002 | Shopping Complex B | T433 | Roofing | Rachel Green | Completed | Low | 2023-03-20 | 2023-04-05 | 2023-04-05 | 100 | Rebar | Market Street | 31475.61 | 46070.53 | No issues
C003 | Office Tower C | T221 | Foundation Excavation | Grace Allen | In Progress | Low | 2023-05-27 | 2023-06-20 |  | 6 | Steel Beams | Downtown Avenue | 22265.43 | 21663.48 | In progress
C004 | Warehouse D | T160 | Site Survey | Sarah Johnson | Blocked | High | 2024-12-04 | 2024-12-14 |  | 0 | Copper Wires | Industrial Park | 8928.18 | 10276.37 | Not started
C002 | Shopping Complex B | T897 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2023-11-07 | 2023-11-15 |  | 96 | Steel Beams | Market Street | 30434.1 | 51894.53 | In progress
C003 | Office Tower C | T162 | Concrete Pouring | Mike Adams | Completed | Medium | 2024-09-16 | 2024-09-30 | 2024-09-30 | 100 | PVC Pipes | Downtown Avenue | 18876.74 | 19438.42 | No issues
C001 | Residential Building A | T131 | Electrical Wiring | Grace Allen | Blocked | Medium | 2023-12-25 | 2024-01-02 |  | 0 | Concrete | Plot 21, Riverside | 14536.31 | 11661.15 | Not started
C003 | Office Tower C | T468 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2024-05-13 | 2024-06-09 |  | 0 | Steel Beams | Downtown Avenue | 44791.74 | 31257.92 | Not started
C004 | Warehouse D | T267 | Roofing | Rachel Green | Blocked | Low | 2023-04-01 | 2023-04-18 |  | 0 | Steel Beams | Industrial Park | 11159.06 | 12216.5 | Not started
C003 | Office Tower C | T667 | Foundation Excavation | Grace Allen | Blocked | High | 2024-02-07 | 2024-02-27 |  | 0 | Steel Beams | Downtown Avenue | 35836.97 | 30497.54 | Not started
C004 | Warehouse D | T343 | Steel Framework Setup | Grace Allen | In Progress | Low | 2023-11-15 | 2023-11-26 |  | 85 | Copper Wires | Industrial Park | 11777.92 | 8138.49 | In progress
C003 | Office Tower C | T599 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2024-04-07 | 2024-04-30 |  | 52 | Cement | Downtown Avenue | 21385.77 | 16041.88 | In progress
C004 | Warehouse D | T677 | Site Survey | Carlos Rivera | In Progress | Medium | 2023-05-23 | 2023-06-15 |  | 11 | Steel Beams | Industrial Park | 34747.8 | 25820.21 | In progress
C003 | Office Tower C | T161 | Interior Painting | Dave Brown | In Progress | High | 2024-11-05 | 2024-11-20 |  | 32 | Steel Beams | Downtown Avenue | 47223.51 | 50012.37 | In progress
C002 | Shopping Complex B | T770 | Site Survey | Emma White | Not Started | Medium | 2024-11-08 | 2024-12-06 |  | 0 | Roofing Sheets | Market Street | 26913.45 | 0 | Not started
C004 | Warehouse D | T261 | Electrical Wiring | Rachel Green | Not Started | High | 2023-11-24 | 2023-12-22 |  | 0 | Copper Wires | Industrial Park | 11277.73 | 0 | Not started
C004 | Warehouse D | T480 | Site Survey | Sarah Johnson | Not Started | High | 2023-05-13 | 2023-06-10 |  | 0 | Roofing Sheets | Industrial Park | 40755.13 | 0 | Not started
C001 | Residential Building A | T296 | Electrical Wiring | Emma White | Blocked | High | 2024-01-08 | 2024-01-16 |  | 0 | Steel Beams | Plot 21, Riverside | 31554.07 | 29578.96 | Not started
C003 | Office Tower C | T633 | Roofing | Emma White | Not Started | Low | 2023-07-16 | 2023-08-12 |  | 0 | Paint | Downtown Avenue | 27686.51 | 0 | Not started
C002 | Shopping Complex B | T430 | Interior Painting | Carlos Rivera | Completed | High | 2023-04-09 | 2023-04-18 | 2023-04-18 | 100 | Concrete | Market Street | 47856.69 | 70635.13 | No issues
C002 | Shopping Complex B | T289 | Electrical Wiring | Emma White | Completed | High | 2023-03-17 | 2023-04-12 | 2023-04-12 | 100 | Steel Beams | Market Street | 8169.69 | 33921.81 | No issues
C003 | Office Tower C | T820 | Plumbing Installations | Mike Adams | In Progress | Low | 2024-06-28 | 2024-07-09 |  | 64 | Rebar | Downtown Avenue | 45280.18 | 34596.53 | In progress
C001 | Residential Building A | T568 | Roofing | Carlos Rivera | Blocked | Low | 2023-08-18 | 2023-09-10 |  | 0 | Paint | Plot 21, Riverside | 32169.79 | 25030.65 | Not started
C002 | Shopping Complex B | T430 | Foundation Excavation | Rachel Green | Completed | Low | 2024-07-04 | 2024-07-25 | 2024-07-25 | 100 | Cement | Market Street | 43052.78 | 55626.46 | No issues
C002 | Shopping Complex B | T183 | Concrete Pouring | Emma White | Blocked | High | 2024-07-02 | 2024-07-17 |  | 0 | Rebar | Market Street | 42415.8 | 51403.77 | Not started
C001 | Residential Building A | T410 | Foundation Excavation | John Miller | Blocked | Low | 2024-09-02 | 2024-09-22 |  | 0 | Steel Beams | Plot 21, Riverside | 32071.55 | 35953.95 | Not started
C001 | Residential Building A | T807 | Interior Painting | Mike Adams | Completed | High | 2023-12-10 | 2023-12-21 | 2023-12-21 | 100 | Cement | Plot 21, Riverside | 44977.95 | 35708.8 | No issues
C002 | Shopping Complex B | T356 | Plumbing Installations | Dave Brown | Completed | Low | 2024-09-08 | 2024-10-07 | 2024-10-07 | 100 | Copper Wires | Market Street | 33603.02 | 51236.72 | No issues
C002 | Shopping Complex B | T290 | Roofing | Dave Brown | Blocked | High | 2023-09-15 | 2023-10-01 |  | 0 | Rebar | Market Street | 23632.5 | 49373.3 | Not started
C001 | Residential Building A | T722 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2024-05-23 | 2024-06-13 |  | 31 | Copper Wires | Plot 21, Riverside | 13779.86 | 15146.48 | In progress
C004 | Warehouse D | T982 | Plumbing Installations | Mike Adams | Not Started | High | 2023-10-03 | 2023-10-22 |  | 0 | Concrete | Industrial Park | 28666.62 | 0 | Not started
C003 | Office Tower C | T452 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-04-11 | 2023-04-22 | 2023-04-22 | 100 | Rebar | Downtown Avenue | 16758.62 | 11201.7 | No issues
C001 | Residential Building A | T978 | Roofing | Rachel Green | In Progress | Medium | 2024-12-16 | 2025-01-03 |  | 10 | Rebar | Plot 21, Riverside | 48182.84 | 56717.55 | In progress
C002 | Shopping Complex B | T621 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-04-20 | 2024-05-10 | 2024-05-10 | 100 | Copper Wires | Market Street | 13188.7 | 37626.16 | No issues
C004 | Warehouse D | T850 | Site Survey | Mike Adams | Completed | High | 2023-06-04 | 2023-07-01 | 2023-07-01 | 100 | Rebar | Industrial Park | 45765.29 | 41049.56 | No issues
C004 | Warehouse D | T521 | Plumbing Installations | John Miller | Completed | Medium | 2023-02-09 | 2023-03-09 | 2023-03-09 | 100 | Paint | Industrial Park | 11644.64 | 8648.29 | No issues
C003 | Office Tower C | T721 | Interior Painting | Dave Brown | In Progress | Medium | 2023-07-03 | 2023-07-27 |  | 73 | Concrete | Downtown Avenue | 18401.64 | 17094.93 | In progress
C001 | Residential Building A | T634 | Steel Framework Setup | Grace Allen | Blocked | Low | 2023-12-21 | 2024-01-13 |  | 0 | Roofing Sheets | Plot 21, Riverside | 13514.56 | 10077.75 | Not started
C002 | Shopping Complex B | T556 | Site Survey | Emma White | Completed | Medium | 2023-04-22 | 2023-05-11 | 2023-05-11 | 100 | Steel Beams | Market Street | 40050.04 | 59314.1 | No issues
C002 | Shopping Complex B | T553 | Foundation Excavation | Grace Allen | In Progress | Medium | 2023-01-28 | 2023-02-07 |  | 93 | Roofing Sheets | Market Street | 27590.75 | 50208.69 | In progress
C004 | Warehouse D | T337 | Electrical Wiring | Rachel Green | Completed | Medium | 2023-10-13 | 2023-10-22 | 2023-10-22 | 100 | PVC Pipes | Industrial Park | 42248.31 | 44564.5 | No issues
C004 | Warehouse D | T999 | Roofing | Carlos Rivera | Completed | High | 2023-01-05 | 2023-01-24 | 2023-01-24 | 100 | Steel Beams | Industrial Park | 17007.72 | 17893.1 | No issues
C001 | Residential Building A | T916 | Site Survey | Carlos Rivera | In Progress | Low | 2023-07-23 | 2023-08-15 |  | 16 | Steel Beams | Plot 21, Riverside | 9372.57 | 8816.79 | In progress
C003 | Office Tower C | T441 | Foundation Excavation | Dave Brown | Not Started | Medium | 2024-06-15 | 2024-07-11 |  | 0 | Steel Beams | Downtown Avenue | 25613.82 | 0 | Not started
C003 | Office Tower C | T747 | Foundation Excavation | Emma White | Not Started | Medium | 2023-05-06 | 2023-05-18 |  | 0 | PVC Pipes | Downtown Avenue | 13279.01 | 0 | Not started
C002 | Shopping Complex B | T647 | Concrete Pouring | Mike Adams | Blocked | Medium | 2024-05-28 | 2024-06-06 |  | 0 | Steel Beams | Market Street | 44623.43 | 62093.94 | Not started
C003 | Office Tower C | T779 | Interior Painting | Grace Allen | Not Started | High | 2023-04-04 | 2023-04-18 |  | 0 | Roofing Sheets | Downtown Avenue | 9998.02 | 0 | Not started
C001 | Residential Building A | T236 | Foundation Excavation | Mike Adams | Not Started | High | 2024-11-07 | 2024-11-19 |  | 0 | Steel Beams | Plot 21, Riverside | 45812.91 | 0 | Not started
C003 | Office Tower C | T349 | Concrete Pouring | Emma White | Completed | Medium | 2024-10-11 | 2024-11-05 | 2024-11-05 | 100 | Rebar | Downtown Avenue | 18792.54 | 21790.75 | No issues
C002 | Shopping Complex B | T797 | Electrical Wiring | Mike Adams | Completed | High | 2023-02-08 | 2023-03-10 | 2023-03-10 | 100 | Roofing Sheets | Market Street | 24955.44 | 51387.41 | No issues
C003 | Office Tower C | T870 | Electrical Wiring | Rachel Green | Not Started | Low | 2023-08-06 | 2023-08-14 |  | 0 | Paint | Downtown Avenue | 12561.64 | 0 | Not started
C002 | Shopping Complex B | T180 | Concrete Pouring | Emma White | Not Started | High | 2023-07-04 | 2023-07-19 |  | 0 | Roofing Sheets | Market Street | 6110.71 | 0 | Not started
C004 | Warehouse D | T314 | Steel Framework Setup | Mike Adams | In Progress | High | 2024-02-04 | 2024-02-25 |  | 93 | Steel Beams | Industrial Park | 26697.23 | 18834.04 | In progress
C002 | Shopping Complex B | T137 | Roofing | Carlos Rivera | Not Started | Low | 2024-11-02 | 2024-11-27 |  | 0 | PVC Pipes | Market Street | 14437.39 | 0 | Not started
C003 | Office Tower C | T841 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-09-25 | 2024-10-16 |  | 0 | Paint | Downtown Avenue | 37898.36 | 31111.33 | Not started
C003 | Office Tower C | T557 | Roofing | Dave Brown | Completed | Low | 2023-04-07 | 2023-04-27 | 2023-04-27 | 100 | Copper Wires | Downtown Avenue | 19099.86 | 19117.07 | No issues
C002 | Shopping Complex B | T457 | Interior Painting | Rachel Green | Completed | Medium | 2023-10-11 | 2023-11-08 | 2023-11-08 | 100 | Rebar | Market Street | 15448.6 | 36187.15 | No issues
C003 | Office Tower C | T698 | Roofing | John Miller | Not Started | Medium | 2024-06-23 | 2024-07-15 |  | 0 | Concrete | Downtown Avenue | 35018.15 | 0 | Not started
C002 | Shopping Complex B | T962 | Interior Painting | Grace Allen | In Progress | Low | 2023-06-17 | 2023-06-27 |  | 21 | Rebar | Market Street | 49371.34 | 75188.85 | In progress
C001 | Residential Building A | T384 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-10-23 | 2024-11-22 |  | 0 | Concrete | Plot 21, Riverside | 31661.69 | 0 | Not started
C002 | Shopping Complex B | T551 | Electrical Wiring | Dave Brown | Blocked | Medium | 2023-10-26 | 2023-11-21 |  | 0 | Concrete | Market Street | 39401.36 | 62033.39 | Not started
C002 | Shopping Complex B | T507 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2024-02-23 | 2024-03-13 |  | 32 | Steel Beams | Market Street | 45322.61 | 79424.44 | In progress
C003 | Office Tower C | T444 | Foundation Excavation | Emma White | Blocked | Medium | 2023-03-11 | 2023-03-23 |  | 0 | Roofing Sheets | Downtown Avenue | 7625.96 | 5381.74 | Not started
C001 | Residential Building A | T747 | Foundation Excavation | John Miller | In Progress | High | 2024-09-28 | 2024-10-13 |  | 73 | Steel Beams | Plot 21, Riverside | 45580.17 | 48803.78 | In progress
C004 | Warehouse D | T845 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2023-07-24 | 2023-08-11 |  | 0 | Paint | Industrial Park | 35163.49 | 0 | Not started
C002 | Shopping Complex B | T593 | Steel Framework Setup | Grace Allen | Not Started | High | 2024-06-06 | 2024-07-03 |  | 0 | Rebar | Market Street | 35982.81 | 0 | Not started
C002 | Shopping Complex B | T364 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2023-02-07 | 2023-02-24 |  | 0 | Paint | Market Street | 21963.77 | 39403.5 | Not started
C001 | Residential Building A | T157 | Plumbing Installations | Dave Brown | Not Started | High | 2024-09-25 | 2024-10-12 |  | 0 | Steel Beams | Plot 21, Riverside | 6707.32 | 0 | Not started
C001 | Residential Building A | T343 | Concrete Pouring | Dave Brown | Not Started | High | 2023-06-01 | 2023-06-09 |  | 0 | Concrete | Plot 21, Riverside | 13355.66 | 0 | Not started
C001 | Residential Building A | T879 | Interior Painting | Dave Brown | Not Started | Medium | 2024-05-28 | 2024-06-21 |  | 0 | Paint | Plot 21, Riverside | 22166.95 | 0 | Not started
C001 | Residential Building A | T309 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-10-13 | 2023-11-12 |  | 0 | Rebar | Plot 21, Riverside | 16527.61 | 19106.5 | Not started
C002 | Shopping Complex B | T260 | Interior Painting | Dave Brown | Completed | Low | 2023-12-11 | 2023-12-20 | 2023-12-20 | 100 | Paint | Market Street | 22676.92 | 40515.61 | No issues
C001 | Residential Building A | T889 | Electrical Wiring | Rachel Green | In Progress | Low | 2024-01-13 | 2024-01-21 |  | 7 | Paint | Plot 21, Riverside | 9375.95 | 6133.91 | In progress
C002 | Shopping Complex B | T237 | Electrical Wiring | John Miller | In Progress | Low | 2023-11-06 | 2023-11-24 |  | 30 | PVC Pipes | Market Street | 38197.03 | 57643.26 | In progress
C002 | Shopping Complex B | T551 | Plumbing Installations | John Miller | Not Started | Low | 2023-03-18 | 2023-03-25 |  | 0 | Cement | Market Street | 8789.13 | 0 | Not started
C001 | Residential Building A | T398 | Foundation Excavation | Dave Brown | Completed | Medium | 2023-03-17 | 2023-04-09 | 2023-04-09 | 100 | Cement | Plot 21, Riverside | 8233.65 | 9190.61 | No issues
C002 | Shopping Complex B | T368 | Interior Painting | Grace Allen | Completed | High | 2024-12-12 | 2024-12-30 | 2024-12-30 | 100 | Rebar | Market Street | 25656.41 | 47489.4 | No issues
C003 | Office Tower C | T453 | Site Survey | Sarah Johnson | Completed | High | 2023-03-03 | 2023-03-10 | 2023-03-10 | 100 | Concrete | Downtown Avenue | 37741.44 | 40162.5 | No issues
C003 | Office Tower C | T257 | Interior Painting | Emma White | Not Started | Medium | 2023-04-15 | 2023-05-04 |  | 0 | Rebar | Downtown Avenue | 8231.46 | 0 | Not started
C001 | Residential Building A | T477 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-08-17 | 2024-08-25 | 2024-08-25 | 100 | Paint | Plot 21, Riverside | 30691.1 | 29884.56 | No issues
C002 | Shopping Complex B | T897 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-01-12 | 2024-01-28 |  | 0 | Paint | Market Street | 18100.04 | 0 | Not started
C004 | Warehouse D | T804 | Interior Painting | Sarah Johnson | In Progress | Medium | 2024-03-07 | 2024-03-26 |  | 74 | Rebar | Industrial Park | 10015.86 | 11823.9 | In progress
C004 | Warehouse D | T154 | Plumbing Installations | Emma White | Not Started | Low | 2023-06-24 | 2023-07-09 |  | 0 | Steel Beams | Industrial Park | 27007.66 | 0 | Not started
C002 | Shopping Complex B | T615 | Interior Painting | Sarah Johnson | In Progress | Low | 2023-11-09 | 2023-11-16 |  | 49 | Copper Wires | Market Street | 46027.52 | 72491.28 | In progress
C001 | Residential Building A | T165 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-01-18 | 2023-01-29 |  | 0 | PVC Pipes | Plot 21, Riverside | 18971.84 | 0 | Not started
C002 | Shopping Complex B | T501 | Steel Framework Setup | John Miller | Completed | High | 2023-12-08 | 2023-12-23 | 2023-12-23 | 100 | Concrete | Market Street | 13889.32 | 35241.6 | No issues
C001 | Residential Building A | T213 | Electrical Wiring | Sarah Johnson | Not Started | High | 2024-10-23 | 2024-10-30 |  | 0 | Copper Wires | Plot 21, Riverside | 8641.26 | 0 | Not started
C001 | Residential Building A | T206 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-11-14 | 2023-12-13 |  | 0 | Roofing Sheets | Plot 21, Riverside | 7008.34 | 0 | Not started
C002 | Shopping Complex B | T181 | Plumbing Installations | Rachel Green | Blocked | Medium | 2023-05-01 | 2023-05-24 |  | 0 | PVC Pipes | Market Street | 38512.38 | 60824.44 | Not started
C004 | Warehouse D | T376 | Plumbing Installations | Sarah Johnson | Completed | High | 2023-02-18 | 2023-03-09 | 2023-03-09 | 100 | Steel Beams | Industrial Park | 18420.92 | 20489.15 | No issues
C004 | Warehouse D | T267 | Steel Framework Setup | Emma White | Blocked | Medium | 2024-10-25 | 2024-11-09 |  | 0 | Roofing Sheets | Industrial Park | 45105.03 | 44570.62 | Not started
C002 | Shopping Complex B | T858 | Plumbing Installations | Sarah Johnson | Not Started | High | 2023-12-11 | 2023-12-20 |  | 0 | Roofing Sheets | Market Street | 7051.92 | 0 | Not started
C001 | Residential Building A | T967 | Plumbing Installations | Mike Adams | Not Started | High | 2023-09-17 | 2023-10-05 |  | 0 | Paint | Plot 21, Riverside | 28622.54 | 0 | Not started
C001 | Residential Building A | T751 | Site Survey | Mike Adams | Blocked | High | 2024-07-22 | 2024-08-04 |  | 0 | Cement | Plot 21, Riverside | 19412.71 | 16949.94 | Not started
C004 | Warehouse D | T721 | Electrical Wiring | Emma White | Not Started | Low | 2024-08-12 | 2024-08-23 |  | 0 | Roofing Sheets | Industrial Park | 44423.74 | 0 | Not started
C004 | Warehouse D | T475 | Concrete Pouring | Rachel Green | Blocked | Medium | 2024-03-08 | 2024-03-15 |  | 0 | Rebar | Industrial Park | 38656.47 | 45964.63 | Not started
C004 | Warehouse D | T854 | Plumbing Installations | Emma White | Completed | High | 2023-08-12 | 2023-09-05 | 2023-09-05 | 100 | Steel Beams | Industrial Park | 5663.09 | 5013.8 | No issues
C003 | Office Tower C | T465 | Electrical Wiring | Mike Adams | Blocked | High | 2024-11-13 | 2024-12-13 |  | 0 | Cement | Downtown Avenue | 43231.51 | 27700.67 | Not started
C003 | Office Tower C | T228 | Site Survey | John Miller | Completed | Medium | 2024-11-19 | 2024-12-05 | 2024-12-05 | 100 | Rebar | Downtown Avenue | 14518.34 | 14723.09 | No issues
C003 | Office Tower C | T380 | Foundation Excavation | Emma White | Blocked | Medium | 2023-12-17 | 2024-01-16 |  | 0 | Paint | Downtown Avenue | 31121.79 | 27771.55 | Not started
C003 | Office Tower C | T784 | Concrete Pouring | Grace Allen | In Progress | Medium | 2023-08-25 | 2023-09-20 |  | 19 | Copper Wires | Downtown Avenue | 47040.66 | 46977.08 | In progress
C001 | Residential Building A | T603 | Foundation Excavation | Grace Allen | Not Started | High | 2023-05-28 | 2023-06-18 |  | 0 | Concrete | Plot 21, Riverside | 36352.75 | 0 | Not started
C001 | Residential Building A | T937 | Roofing | Grace Allen | Completed | Low | 2023-04-20 | 2023-05-10 | 2023-05-10 | 100 | Copper Wires | Plot 21, Riverside | 49722.88 | 35429.67 | No issues
C002 | Shopping Complex B | T467 | Electrical Wiring | Sarah Johnson | Not Started | High | 2024-06-28 | 2024-07-20 |  | 0 | Cement | Market Street | 17513.11 | 0 | Not started
C002 | Shopping Complex B | T189 | Steel Framework Setup | Grace Allen | Blocked | Low | 2024-10-06 | 2024-10-26 |  | 0 | Rebar | Market Street | 37412.43 | 60946.61 | Not started
C001 | Residential Building A | T185 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-09-11 | 2024-09-21 |  | 0 | Concrete | Plot 21, Riverside | 20790.54 | 0 | Not started
C003 | Office Tower C | T114 | Foundation Excavation | John Miller | Blocked | Low | 2024-03-18 | 2024-04-05 |  | 0 | Paint | Downtown Avenue | 31541.65 | 20014.27 | Not started
C003 | Office Tower C | T825 | Site Survey | Emma White | In Progress | Low | 2024-12-11 | 2025-01-04 |  | 26 | Rebar | Downtown Avenue | 17284.9 | 11194.86 | In progress
C003 | Office Tower C | T790 | Steel Framework Setup | Grace Allen | In Progress | High | 2023-05-13 | 2023-05-28 |  | 14 | Concrete | Downtown Avenue | 25797.4 | 24882.73 | In progress
C002 | Shopping Complex B | T458 | Steel Framework Setup | Grace Allen | Completed | Medium | 2023-08-24 | 2023-09-02 | 2023-09-02 | 100 | Paint | Market Street | 17036.69 | 38053.3 | No issues
C003 | Office Tower C | T579 | Foundation Excavation | Mike Adams | Not Started | High | 2023-11-03 | 2023-11-17 |  | 0 | Steel Beams | Downtown Avenue | 49890.29 | 0 | Not started
C003 | Office Tower C | T222 | Site Survey | Sarah Johnson | In Progress | High | 2023-04-14 | 2023-05-06 |  | 38 | Paint | Downtown Avenue | 47408.51 | 48023.26 | In progress
C001 | Residential Building A | T500 | Site Survey | Dave Brown | In Progress | Low | 2024-10-08 | 2024-10-27 |  | 74 | Rebar | Plot 21, Riverside | 30384.15 | 26884.43 | In progress
C004 | Warehouse D | T511 | Steel Framework Setup | Dave Brown | Blocked | Low | 2024-06-12 | 2024-06-27 |  | 0 | Copper Wires | Industrial Park | 47303.9 | 37988.77 | Not started
C002 | Shopping Complex B | T486 | Concrete Pouring | Carlos Rivera | Completed | Low | 2024-12-01 | 2024-12-27 | 2024-12-27 | 100 | PVC Pipes | Market Street | 43303.1 | 54434.18 | No issues
C002 | Shopping Complex B | T183 | Plumbing Installations | Grace Allen | Not Started | Low | 2023-10-12 | 2023-11-02 |  | 0 | Roofing Sheets | Market Street | 8934.42 | 0 | Not started
C003 | Office Tower C | T786 | Steel Framework Setup | Emma White | Not Started | High | 2023-08-06 | 2023-08-26 |  | 0 | Copper Wires | Downtown Avenue | 15885.05 | 0 | Not started
C004 | Warehouse D | T546 | Interior Painting | Dave Brown | Not Started | Medium | 2023-05-16 | 2023-06-14 |  | 0 | Steel Beams | Industrial Park | 19800.24 | 0 | Not started
C001 | Residential Building A | T188 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2024-12-01 | 2024-12-31 |  | 0 | PVC Pipes | Plot 21, Riverside | 15529.65 | 14331.26 | Not started
C004 | Warehouse D | T857 | Plumbing Installations | Grace Allen | Not Started | High | 2023-04-17 | 2023-05-15 |  | 0 | Rebar | Industrial Park | 48101.93 | 0 | Not started
C001 | Residential Building A | T454 | Plumbing Installations | Emma White | Completed | Medium | 2024-03-04 | 2024-03-19 | 2024-03-19 | 100 | Cement | Plot 21, Riverside | 20293.33 | 14463.41 | No issues
C004 | Warehouse D | T554 | Roofing | Dave Brown | Blocked | High | 2024-04-03 | 2024-04-22 |  | 0 | Cement | Industrial Park | 33857.3 | 26667.16 | Not started
C001 | Residential Building A | T658 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2023-01-13 | 2023-01-29 |  | 0 | Cement | Plot 21, Riverside | 25139.64 | 0 | Not started
C003 | Office Tower C | T527 | Plumbing Installations | John Miller | Blocked | High | 2024-01-11 | 2024-01-27 |  | 0 | PVC Pipes | Downtown Avenue | 11200.82 | 10870.07 | Not started
C003 | Office Tower C | T737 | Site Survey | John Miller | Blocked | Low | 2023-05-13 | 2023-06-07 |  | 0 | Roofing Sheets | Downtown Avenue | 38935.16 | 29107.67 | Not started
C004 | Warehouse D | T296 | Foundation Excavation | Emma White | In Progress | High | 2024-02-11 | 2024-03-12 |  | 84 | Roofing Sheets | Industrial Park | 7423.54 | 8668.93 | In progress
C002 | Shopping Complex B | T749 | Plumbing Installations | Sarah Johnson | Completed | Low | 2024-10-25 | 2024-11-19 | 2024-11-19 | 100 | Paint | Market Street | 34230.44 | 63373.17 | No issues
C004 | Warehouse D | T718 | Roofing | Grace Allen | Completed | Low | 2024-07-02 | 2024-07-29 | 2024-07-29 | 100 | Copper Wires | Industrial Park | 47271.26 | 41549.57 | No issues
C004 | Warehouse D | T411 | Steel Framework Setup | Rachel Green | Completed | Medium | 2023-06-19 | 2023-07-09 | 2023-07-09 | 100 | PVC Pipes | Industrial Park | 20671.96 | 22843.14 | No issues
C001 | Residential Building A | T472 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2023-03-04 | 2023-04-03 | 2023-04-03 | 100 | Roofing Sheets | Plot 21, Riverside | 23610.82 | 18210.36 | No issues
C004 | Warehouse D | T661 | Site Survey | John Miller | Not Started | High | 2024-11-01 | 2024-12-01 |  | 0 | Paint | Industrial Park | 36286.87 | 0 | Not started
C001 | Residential Building A | T833 | Electrical Wiring | Carlos Rivera | Completed | Low | 2023-07-03 | 2023-07-11 | 2023-07-11 | 100 | PVC Pipes | Plot 21, Riverside | 10521.32 | 9453.89 | No issues
C002 | Shopping Complex B | T476 | Concrete Pouring | Grace Allen | Blocked | Low | 2024-04-19 | 2024-05-10 |  | 0 | PVC Pipes | Market Street | 7805.68 | 32390.51 | Not started
C003 | Office Tower C | T931 | Electrical Wiring | Grace Allen | Not Started | High | 2023-05-02 | 2023-05-18 |  | 0 | PVC Pipes | Downtown Avenue | 9427.79 | 0 | Not started
C003 | Office Tower C | T818 | Electrical Wiring | Rachel Green | Not Started | High | 2023-09-15 | 2023-09-27 |  | 0 | Cement | Downtown Avenue | 36060.08 | 0 | Not started
C001 | Residential Building A | T228 | Plumbing Installations | Carlos Rivera | Completed | Low | 2024-05-06 | 2024-05-21 | 2024-05-21 | 100 | Roofing Sheets | Plot 21, Riverside | 40627.19 | 38210.03 | No issues
C003 | Office Tower C | T906 | Steel Framework Setup | Emma White | Completed | High | 2024-08-27 | 2024-09-06 | 2024-09-06 | 100 | Steel Beams | Downtown Avenue | 22891.01 | 24751.17 | No issues
C003 | Office Tower C | T699 | Site Survey | Emma White | In Progress | Medium | 2023-02-19 | 2023-03-06 |  | 24 | Roofing Sheets | Downtown Avenue | 27561.69 | 27687.87 | In progress
C002 | Shopping Complex B | T987 | Plumbing Installations | Emma White | Not Started | Low | 2024-09-15 | 2024-10-12 |  | 0 | PVC Pipes | Market Street | 35709.74 | 0 | Not started
C001 | Residential Building A | T398 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2023-02-18 | 2023-03-02 |  | 0 | Cement | Plot 21, Riverside | 29558.97 | 0 | Not started
C001 | Residential Building A | T214 | Electrical Wiring | Grace Allen | Not Started | High | 2023-11-02 | 2023-11-17 |  | 0 | Rebar | Plot 21, Riverside | 19141.33 | 0 | Not started
C003 | Office Tower C | T174 | Roofing | Rachel Green | Completed | Medium | 2023-08-24 | 2023-09-19 | 2023-09-19 | 100 | Concrete | Downtown Avenue | 31284.26 | 37409.09 | No issues
C004 | Warehouse D | T335 | Interior Painting | Grace Allen | In Progress | High | 2023-09-17 | 2023-10-17 |  | 24 | Roofing Sheets | Industrial Park | 41917.05 | 48834.08 | In progress
C003 | Office Tower C | T929 | Plumbing Installations | Mike Adams | Completed | Low | 2023-10-08 | 2023-10-30 | 2023-10-30 | 100 | PVC Pipes | Downtown Avenue | 27960.11 | 30277.8 | No issues
C004 | Warehouse D | T511 | Steel Framework Setup | John Miller | Not Started | Medium | 2024-02-16 | 2024-03-03 |  | 0 | Concrete | Industrial Park | 13950.7 | 0 | Not started
C002 | Shopping Complex B | T509 | Interior Painting | John Miller | Not Started | High | 2024-01-16 | 2024-01-30 |  | 0 | Roofing Sheets | Market Street | 34761.02 | 0 | Not started
C002 | Shopping Complex B | T703 | Foundation Excavation | Sarah Johnson | Blocked | High | 2024-01-12 | 2024-02-10 |  | 0 | Concrete | Market Street | 18765.45 | 41954.7 | Not started
C004 | Warehouse D | T114 | Site Survey | Dave Brown | Not Started | High | 2024-01-01 | 2024-01-23 |  | 0 | Copper Wires | Industrial Park | 8548.7 | 0 | Not started
C002 | Shopping Complex B | T679 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2023-05-27 | 2023-06-26 |  | 0 | Paint | Market Street | 40657.57 | 0 | Not started
C004 | Warehouse D | T544 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2023-06-14 | 2023-06-24 |  | 49 | Rebar | Industrial Park | 23368.57 | 24226.9 | In progress
C002 | Shopping Complex B | T414 | Electrical Wiring | Dave Brown | Completed | High | 2023-02-03 | 2023-03-04 | 2023-03-04 | 100 | Roofing Sheets | Market Street | 48805.13 | 63633.72 | No issues
C004 | Warehouse D | T141 | Site Survey | Sarah Johnson | Completed | High | 2023-09-07 | 2023-09-19 | 2023-09-19 | 100 | Steel Beams | Industrial Park | 27975.49 | 24549.56 | No issues
C004 | Warehouse D | T997 | Roofing | Sarah Johnson | Not Started | Medium | 2023-02-12 | 2023-03-10 |  | 0 | PVC Pipes | Industrial Park | 37698.33 | 0 | Not started
C004 | Warehouse D | T456 | Roofing | Mike Adams | In Progress | Low | 2024-07-25 | 2024-08-09 |  | 22 | Roofing Sheets | Industrial Park | 34245.23 | 28862.14 | In progress
C004 | Warehouse D | T742 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-04-17 | 2024-05-12 |  | 37 | Roofing Sheets | Industrial Park | 32729.25 | 35816.66 | In progress
C004 | Warehouse D | T657 | Foundation Excavation | John Miller | Completed | Medium | 2023-11-07 | 2023-11-26 | 2023-11-26 | 100 | Paint | Industrial Park | 44361.36 | 27069.1 | No issues
C004 | Warehouse D | T695 | Steel Framework Setup | Dave Brown | Not Started | Low | 2023-10-16 | 2023-11-08 |  | 0 | Cement | Industrial Park | 17190.05 | 0 | Not started
C003 | Office Tower C | T683 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2023-12-01 | 2023-12-11 |  | 0 | PVC Pipes | Downtown Avenue | 7551.48 | 4680.84 | Not started
C003 | Office Tower C | T545 | Steel Framework Setup | Emma White | Completed | Medium | 2024-12-02 | 2024-12-26 | 2024-12-26 | 100 | Cement | Downtown Avenue | 48712.82 | 30314.48 | No issues
C003 | Office Tower C | T962 | Roofing | Mike Adams | In Progress | High | 2024-05-13 | 2024-05-21 |  | 29 | Copper Wires | Downtown Avenue | 39674.2 | 39468.71 | In progress
C003 | Office Tower C | T761 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-08-08 | 2023-08-19 | 2023-08-19 | 100 | Cement | Downtown Avenue | 34357.85 | 38065.5 | No issues
C004 | Warehouse D | T954 | Interior Painting | Sarah Johnson | Not Started | High | 2023-09-11 | 2023-10-07 |  | 0 | Rebar | Industrial Park | 40018.75 | 0 | Not started
C002 | Shopping Complex B | T465 | Foundation Excavation | Mike Adams | Completed | Low | 2024-10-22 | 2024-11-14 | 2024-11-14 | 100 | Rebar | Market Street | 41752.67 | 52009.04 | No issues
C001 | Residential Building A | T184 | Roofing | Rachel Green | In Progress | Medium | 2023-05-07 | 2023-06-02 |  | 28 | Copper Wires | Plot 21, Riverside | 36723.61 | 24818.53 | In progress
C002 | Shopping Complex B | T779 | Foundation Excavation | Dave Brown | Not Started | Medium | 2023-12-12 | 2023-12-19 |  | 0 | Roofing Sheets | Market Street | 44723.23 | 0 | Not started
C004 | Warehouse D | T490 | Roofing | Carlos Rivera | In Progress | High | 2023-09-12 | 2023-09-30 |  | 40 | Steel Beams | Industrial Park | 21121.58 | 24126.79 | In progress
C003 | Office Tower C | T237 | Foundation Excavation | Emma White | In Progress | Low | 2023-03-02 | 2023-03-21 |  | 7 | Cement | Downtown Avenue | 10466.37 | 9535.71 | In progress
C001 | Residential Building A | T989 | Roofing | Mike Adams | Completed | Medium | 2024-01-04 | 2024-02-01 | 2024-02-01 | 100 | PVC Pipes | Plot 21, Riverside | 5154.36 | 4410.25 | No issues
C003 | Office Tower C | T195 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2023-08-06 | 2023-09-03 |  | 70 | Steel Beams | Downtown Avenue | 9394.5 | 10584.89 | In progress
C002 | Shopping Complex B | T189 | Roofing | John Miller | In Progress | Low | 2023-01-19 | 2023-01-28 |  | 73 | Paint | Market Street | 14322.15 | 39450.45 | In progress
C001 | Residential Building A | T715 | Foundation Excavation | Emma White | Completed | Medium | 2023-03-06 | 2023-04-04 | 2023-04-04 | 100 | Roofing Sheets | Plot 21, Riverside | 20424.21 | 21590.19 | No issues
C004 | Warehouse D | T275 | Plumbing Installations | John Miller | In Progress | High | 2024-02-02 | 2024-02-14 |  | 66 | Paint | Industrial Park | 30490.41 | 36064.91 | In progress
C003 | Office Tower C | T345 | Electrical Wiring | Dave Brown | Not Started | Medium | 2024-08-24 | 2024-09-05 |  | 0 | Cement | Downtown Avenue | 25577.43 | 0 | Not started
C001 | Residential Building A | T645 | Interior Painting | Dave Brown | Completed | High | 2024-04-26 | 2024-05-05 | 2024-05-05 | 100 | Rebar | Plot 21, Riverside | 46618.28 | 38092.84 | No issues
C003 | Office Tower C | T779 | Site Survey | Carlos Rivera | Completed | Medium | 2024-08-10 | 2024-08-19 | 2024-08-19 | 100 | PVC Pipes | Downtown Avenue | 43578.18 | 27779.09 | No issues
C001 | Residential Building A | T162 | Concrete Pouring | Emma White | In Progress | High | 2024-10-17 | 2024-11-04 |  | 10 | Copper Wires | Plot 21, Riverside | 26943.98 | 20833.57 | In progress
C001 | Residential Building A | T182 | Steel Framework Setup | Rachel Green | Blocked | High | 2024-02-22 | 2024-03-07 |  | 0 | Rebar | Plot 21, Riverside | 27739.42 | 27835.66 | Not started
C002 | Shopping Complex B | T634 | Roofing | Sarah Johnson | Completed | Medium | 2023-04-15 | 2023-05-08 | 2023-05-08 | 100 | Rebar | Market Street | 34723.4 | 49435.3 | No issues
C003 | Office Tower C | T838 | Foundation Excavation | Dave Brown | Not Started | Low | 2023-03-23 | 2023-04-02 |  | 0 | Copper Wires | Downtown Avenue | 22108.17 | 0 | Not started
C003 | Office Tower C | T975 | Steel Framework Setup | Mike Adams | In Progress | Low | 2023-09-17 | 2023-10-14 |  | 2 | Cement | Downtown Avenue | 24963.47 | 23956.52 | In progress
C001 | Residential Building A | T988 | Roofing | Emma White | In Progress | Low | 2024-04-26 | 2024-05-09 |  | 87 | Roofing Sheets | Plot 21, Riverside | 18211.36 | 14980.59 | In progress
C003 | Office Tower C | T639 | Plumbing Installations | Dave Brown | Not Started | High | 2023-10-21 | 2023-11-03 |  | 0 | PVC Pipes | Downtown Avenue | 24513.79 | 0 | Not started
C001 | Residential Building A | T657 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2023-07-10 | 2023-07-23 |  | 81 | Steel Beams | Plot 21, Riverside | 16353.69 | 18187.24 | In progress
C004 | Warehouse D | T930 | Steel Framework Setup | Dave Brown | Blocked | High | 2023-01-12 | 2023-01-21 |  | 0 | Copper Wires | Industrial Park | 5203.73 | 5997.51 | Not started
C004 | Warehouse D | T930 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-01-23 | 2023-02-06 |  | 86 | PVC Pipes | Industrial Park | 28989.83 | 29750.58 | In progress
C002 | Shopping Complex B | T399 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2023-02-18 | 2023-03-14 |  | 0 | Paint | Market Street | 15098.48 | 0 | Not started
C004 | Warehouse D | T309 | Site Survey | Sarah Johnson | Completed | Low | 2024-06-03 | 2024-06-11 | 2024-06-11 | 100 | Cement | Industrial Park | 29589.81 | 33018.31 | No issues
C004 | Warehouse D | T829 | Steel Framework Setup | Grace Allen | In Progress | Low | 2023-07-22 | 2023-07-31 |  | 15 | Concrete | Industrial Park | 17096.53 | 19512.54 | In progress
C004 | Warehouse D | T476 | Electrical Wiring | Grace Allen | Completed | High | 2023-01-12 | 2023-01-19 | 2023-01-19 | 100 | Concrete | Industrial Park | 21297.75 | 20288.76 | No issues
C002 | Shopping Complex B | T613 | Roofing | Dave Brown | Blocked | Medium | 2023-01-09 | 2023-02-08 |  | 0 | Cement | Market Street | 39325.42 | 62967.87 | Not started
C003 | Office Tower C | T869 | Interior Painting | Carlos Rivera | Blocked | Medium | 2023-05-13 | 2023-05-28 |  | 0 | PVC Pipes | Downtown Avenue | 47629.94 | 38986.58 | Not started
C004 | Warehouse D | T451 | Concrete Pouring | Mike Adams | In Progress | High | 2024-02-26 | 2024-03-19 |  | 20 | PVC Pipes | Industrial Park | 40333.67 | 44898.52 | In progress
C001 | Residential Building A | T770 | Steel Framework Setup | Emma White | Not Started | Low | 2024-12-14 | 2025-01-05 |  | 0 | Concrete | Plot 21, Riverside | 27191.61 | 0 | Not started
C002 | Shopping Complex B | T362 | Foundation Excavation | John Miller | Completed | Low | 2023-06-10 | 2023-06-23 | 2023-06-23 | 100 | Roofing Sheets | Market Street | 43268.46 | 68233.17 | No issues
C002 | Shopping Complex B | T222 | Plumbing Installations | Carlos Rivera | Completed | Low | 2023-10-11 | 2023-10-25 | 2023-10-25 | 100 | Cement | Market Street | 12534.33 | 37358.83 | No issues
C004 | Warehouse D | T380 | Electrical Wiring | Sarah Johnson | In Progress | High | 2024-03-12 | 2024-03-31 |  | 8 | Rebar | Industrial Park | 36442.53 | 42312.49 | In progress
C003 | Office Tower C | T308 | Electrical Wiring | Grace Allen | Blocked | Medium | 2024-08-17 | 2024-08-30 |  | 0 | Cement | Downtown Avenue | 17268.82 | 13506.12 | Not started
C003 | Office Tower C | T299 | Site Survey | John Miller | In Progress | Low | 2024-03-08 | 2024-03-21 |  | 56 | Concrete | Downtown Avenue | 38087.77 | 26426.34 | In progress
C004 | Warehouse D | T966 | Steel Framework Setup | Grace Allen | In Progress | Low | 2024-05-20 | 2024-06-07 |  | 30 | Rebar | Industrial Park | 41505.16 | 30991.94 | In progress
C004 | Warehouse D | T372 | Steel Framework Setup | John Miller | In Progress | High | 2023-10-25 | 2023-11-21 |  | 47 | Paint | Industrial Park | 24728.46 | 24168.36 | In progress
C003 | Office Tower C | T912 | Steel Framework Setup | Rachel Green | Blocked | Low | 2023-09-15 | 2023-10-03 |  | 0 | Concrete | Downtown Avenue | 45276.53 | 43272.41 | Not started
C002 | Shopping Complex B | T617 | Roofing | Emma White | Blocked | Low | 2023-11-14 | 2023-12-05 |  | 0 | Concrete | Market Street | 38958.93 | 66560.43 | Not started
C001 | Residential Building A | T418 | Electrical Wiring | Emma White | Completed | Low | 2023-02-14 | 2023-03-16 | 2023-03-16 | 100 | Steel Beams | Plot 21, Riverside | 5660.56 | 5359.61 | No issues
C003 | Office Tower C | T100 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2024-12-10 | 2024-12-28 | 2024-12-28 | 100 | Steel Beams | Downtown Avenue | 31527.95 | 37197.19 | No issues
C004 | Warehouse D | T943 | Plumbing Installations | John Miller | In Progress | High | 2023-03-06 | 2023-03-16 |  | 77 | Paint | Industrial Park | 23595.78 | 23389.61 | In progress
C003 | Office Tower C | T809 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-09-09 | 2023-09-23 |  | 0 | Roofing Sheets | Downtown Avenue | 14056.23 | 0 | Not started
C003 | Office Tower C | T983 | Site Survey | Sarah Johnson | Completed | High | 2024-09-12 | 2024-10-10 | 2024-10-10 | 100 | Copper Wires | Downtown Avenue | 12421.84 | 9761.76 | No issues
C004 | Warehouse D | T252 | Plumbing Installations | Dave Brown | Blocked | Low | 2023-11-18 | 2023-12-02 |  | 0 | Rebar | Industrial Park | 39464.33 | 39916.56 | Not started
C002 | Shopping Complex B | T444 | Site Survey | Sarah Johnson | Blocked | Low | 2024-11-19 | 2024-12-08 |  | 0 | Cement | Market Street | 32408.13 | 47910.81 | Not started
C001 | Residential Building A | T778 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2023-09-20 | 2023-10-03 |  | 0 | PVC Pipes | Plot 21, Riverside | 20452.7 | 0 | Not started
C003 | Office Tower C | T787 | Concrete Pouring | Carlos Rivera | Completed | Low | 2023-01-06 | 2023-01-14 | 2023-01-14 | 100 | Steel Beams | Downtown Avenue | 34258.48 | 25593.65 | No issues
C003 | Office Tower C | T697 | Electrical Wiring | Sarah Johnson | Completed | Low | 2024-01-19 | 2024-02-02 | 2024-02-02 | 100 | Rebar | Downtown Avenue | 32874.1 | 27335.03 | No issues
C001 | Residential Building A | T965 | Steel Framework Setup | Emma White | In Progress | Medium | 2024-02-18 | 2024-03-02 |  | 58 | Cement | Plot 21, Riverside | 27647.82 | 25600.79 | In progress
C003 | Office Tower C | T213 | Steel Framework Setup | Sarah Johnson | Completed | High | 2023-06-14 | 2023-06-26 | 2023-06-26 | 100 | Copper Wires | Downtown Avenue | 29157.07 | 29141.53 | No issues
C004 | Warehouse D | T273 | Site Survey | Rachel Green | In Progress | High | 2023-11-11 | 2023-12-03 |  | 49 | Roofing Sheets | Industrial Park | 38605.47 | 35638.23 | In progress
C003 | Office Tower C | T802 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2023-04-16 | 2023-04-28 |  | 0 | Copper Wires | Downtown Avenue | 27793.95 | 17805.73 | Not started
C001 | Residential Building A | T200 | Roofing | Mike Adams | Blocked | Low | 2023-04-03 | 2023-04-24 |  | 0 | PVC Pipes | Plot 21, Riverside | 30845.17 | 22779.8 | Not started
C003 | Office Tower C | T763 | Interior Painting | Carlos Rivera | Completed | Low | 2023-04-21 | 2023-04-28 | 2023-04-28 | 100 | Roofing Sheets | Downtown Avenue | 49328.52 | 38529.6 | No issues
C001 | Residential Building A | T266 | Foundation Excavation | Mike Adams | In Progress | Low | 2023-03-02 | 2023-03-27 |  | 36 | Copper Wires | Plot 21, Riverside | 43590.12 | 28922.11 | In progress
C004 | Warehouse D | T625 | Foundation Excavation | Mike Adams | Not Started | Medium | 2023-04-22 | 2023-05-05 |  | 0 | Roofing Sheets | Industrial Park | 14457.67 | 0 | Not started
C004 | Warehouse D | T785 | Site Survey | John Miller | In Progress | High | 2024-03-07 | 2024-04-06 |  | 39 | Roofing Sheets | Industrial Park | 8894.81 | 8268.23 | In progress
C003 | Office Tower C | T126 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2024-07-07 | 2024-07-31 | 2024-07-31 | 100 | Rebar | Downtown Avenue | 7511.95 | 7275.14 | No issues
C004 | Warehouse D | T941 | Plumbing Installations | Carlos Rivera | Not Started | High | 2023-10-17 | 2023-11-05 |  | 0 | Cement | Industrial Park | 26873.55 | 0 | Not started
C001 | Residential Building A | T329 | Concrete Pouring | Emma White | Completed | Low | 2023-10-25 | 2023-11-12 | 2023-11-12 | 100 | Paint | Plot 21, Riverside | 32918.41 | 25480.11 | No issues
C002 | Shopping Complex B | T709 | Concrete Pouring | Mike Adams | Completed | Medium | 2023-07-16 | 2023-07-31 | 2023-07-31 | 100 | PVC Pipes | Market Street | 26851.27 | 44509.18 | No issues
C001 | Residential Building A | T891 | Foundation Excavation | John Miller | In Progress | High | 2023-04-12 | 2023-04-25 |  | 53 | Concrete | Plot 21, Riverside | 41472.72 | 46440.76 | In progress
C001 | Residential Building A | T136 | Foundation Excavation | Mike Adams | Completed | Medium | 2024-12-04 | 2024-12-17 | 2024-12-17 | 100 | Copper Wires | Plot 21, Riverside | 37210.87 | 42278.45 | No issues
C002 | Shopping Complex B | T235 | Roofing | Grace Allen | Not Started | High | 2024-07-25 | 2024-08-11 |  | 0 | Cement | Market Street | 45952.7 | 0 | Not started
C003 | Office Tower C | T404 | Concrete Pouring | Sarah Johnson | Completed | Low | 2023-11-10 | 2023-12-08 | 2023-12-08 | 100 | PVC Pipes | Downtown Avenue | 36919.87 | 38951.79 | No issues
C003 | Office Tower C | T167 | Interior Painting | Grace Allen | Blocked | High | 2024-11-20 | 2024-12-18 |  | 0 | Copper Wires | Downtown Avenue | 13537.05 | 9538.46 | Not started
C002 | Shopping Complex B | T339 | Site Survey | Sarah Johnson | Blocked | Low | 2023-10-25 | 2023-11-22 |  | 0 | Roofing Sheets | Market Street | 23311.03 | 43287.01 | Not started
C001 | Residential Building A | T374 | Roofing | Grace Allen | Blocked | High | 2024-06-28 | 2024-07-19 |  | 0 | Cement | Plot 21, Riverside | 29008.35 | 25037.04 | Not started
C002 | Shopping Complex B | T945 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2023-04-20 | 2023-05-11 |  | 0 | Concrete | Market Street | 32582.8 | 60338.88 | Not started
C002 | Shopping Complex B | T768 | Steel Framework Setup | Mike Adams | Completed | Low | 2023-01-15 | 2023-01-25 | 2023-01-25 | 100 | Roofing Sheets | Market Street | 31939.8 | 50225.49 | No issues
C002 | Shopping Complex B | T654 | Interior Painting | Mike Adams | Completed | High | 2023-09-09 | 2023-09-23 | 2023-09-23 | 100 | Rebar | Market Street | 10848.21 | 33529.67 | No issues
C003 | Office Tower C | T186 | Foundation Excavation | Sarah Johnson | Completed | High | 2024-06-05 | 2024-06-16 | 2024-06-16 | 100 | Roofing Sheets | Downtown Avenue | 9329.51 | 6946.44 | No issues
C001 | Residential Building A | T273 | Foundation Excavation | Rachel Green | In Progress | Medium | 2024-10-13 | 2024-10-24 |  | 93 | Cement | Plot 21, Riverside | 37277.56 | 27211.68 | In progress
C002 | Shopping Complex B | T246 | Electrical Wiring | Rachel Green | In Progress | High | 2024-02-19 | 2024-03-02 |  | 40 | Cement | Market Street | 24063.77 | 53537.9 | In progress
C001 | Residential Building A | T471 | Plumbing Installations | Emma White | In Progress | Low | 2023-07-15 | 2023-08-11 |  | 36 | Rebar | Plot 21, Riverside | 36647.35 | 42647.59 | In progress
C004 | Warehouse D | T694 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-01-24 | 2024-02-11 |  | 15 | Steel Beams | Industrial Park | 30701.43 | 31780.61 | In progress
C003 | Office Tower C | T497 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2024-07-15 | 2024-08-01 |  | 0 | Cement | Downtown Avenue | 26052.53 | 0 | Not started
C002 | Shopping Complex B | T712 | Interior Painting | Grace Allen | Completed | High | 2024-05-25 | 2024-06-06 | 2024-06-06 | 100 | Copper Wires | Market Street | 42222.33 | 75290.7 | No issues
C003 | Office Tower C | T996 | Interior Painting | Sarah Johnson | Not Started | High | 2024-06-24 | 2024-07-11 |  | 0 | Roofing Sheets | Downtown Avenue | 10658.34 | 0 | Not started
C003 | Office Tower C | T454 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-03-19 | 2024-03-29 |  | 0 | Cement | Downtown Avenue | 5394.59 | 0 | Not started
C002 | Shopping Complex B | T720 | Electrical Wiring | Emma White | In Progress | Medium | 2023-09-14 | 2023-09-21 |  | 71 | Paint | Market Street | 11734.88 | 34851.32 | In progress
C003 | Office Tower C | T321 | Foundation Excavation | Grace Allen | Not Started | Low | 2023-06-20 | 2023-07-13 |  | 0 | Rebar | Downtown Avenue | 30624.04 | 0 | Not started
C002 | Shopping Complex B | T809 | Foundation Excavation | Rachel Green | Blocked | Low | 2023-07-14 | 2023-08-01 |  | 0 | Rebar | Market Street | 47423.16 | 81346.84 | Not started
C003 | Office Tower C | T862 | Electrical Wiring | Carlos Rivera | Not Started | High | 2024-04-10 | 2024-05-09 |  | 0 | PVC Pipes | Downtown Avenue | 18884.15 | 0 | Not started
C003 | Office Tower C | T515 | Site Survey | Dave Brown | Completed | Medium | 2024-06-18 | 2024-07-07 | 2024-07-07 | 100 | Concrete | Downtown Avenue | 15722.39 | 11976.45 | No issues
C001 | Residential Building A | T284 | Electrical Wiring | Mike Adams | Blocked | Low | 2024-10-19 | 2024-11-17 |  | 0 | PVC Pipes | Plot 21, Riverside | 47463.35 | 52967.89 | Not started
C002 | Shopping Complex B | T396 | Foundation Excavation | Grace Allen | Not Started | Low | 2024-12-09 | 2024-12-16 |  | 0 | Rebar | Market Street | 24195.14 | 0 | Not started
C003 | Office Tower C | T435 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-10-08 | 2024-10-19 |  | 0 | Roofing Sheets | Downtown Avenue | 38201.96 | 0 | Not started
C001 | Residential Building A | T406 | Site Survey | John Miller | Not Started | High | 2024-08-18 | 2024-09-04 |  | 0 | Steel Beams | Plot 21, Riverside | 22551.08 | 0 | Not started
C004 | Warehouse D | T733 | Plumbing Installations | Grace Allen | In Progress | Low | 2023-08-06 | 2023-08-29 |  | 85 | Concrete | Industrial Park | 28436.38 | 34087.64 | In progress
C004 | Warehouse D | T558 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2024-08-12 | 2024-09-07 |  | 0 | Cement | Industrial Park | 10589.14 | 0 | Not started
C003 | Office Tower C | T200 | Foundation Excavation | Rachel Green | Blocked | Low | 2023-01-23 | 2023-02-13 |  | 0 | Rebar | Downtown Avenue | 9171.4 | 6050.09 | Not started
C001 | Residential Building A | T767 | Site Survey | Grace Allen | Blocked | Medium | 2024-06-01 | 2024-06-13 |  | 0 | Cement | Plot 21, Riverside | 36601.16 | 25886 | Not started
C001 | Residential Building A | T676 | Plumbing Installations | Emma White | Completed | Low | 2024-08-09 | 2024-08-30 | 2024-08-30 | 100 | Rebar | Plot 21, Riverside | 44617.06 | 47303.76 | No issues
C003 | Office Tower C | T471 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-12-06 | 2023-12-19 |  | 0 | Concrete | Downtown Avenue | 8868.79 | 7659.84 | Not started
C003 | Office Tower C | T884 | Concrete Pouring | John Miller | In Progress | High | 2023-06-08 | 2023-07-06 |  | 88 | Steel Beams | Downtown Avenue | 10774.36 | 10731.23 | In progress
C002 | Shopping Complex B | T643 | Steel Framework Setup | John Miller | In Progress | Medium | 2024-02-19 | 2024-03-05 |  | 49 | Paint | Market Street | 42086.35 | 66934.64 | In progress
C001 | Residential Building A | T237 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-02-01 | 2024-02-16 |  | 0 | Roofing Sheets | Plot 21, Riverside | 12472.78 | 0 | Not started
C003 | Office Tower C | T236 | Foundation Excavation | Rachel Green | Completed | Medium | 2024-07-09 | 2024-07-22 | 2024-07-22 | 100 | Copper Wires | Downtown Avenue | 44160.83 | 29259.18 | No issues
C002 | Shopping Complex B | T307 | Steel Framework Setup | Emma White | Blocked | Medium | 2023-02-07 | 2023-03-08 |  | 0 | Paint | Market Street | 42617.15 | 53004.97 | Not started
C002 | Shopping Complex B | T499 | Plumbing Installations | Sarah Johnson | In Progress | High | 2023-06-19 | 2023-07-18 |  | 93 | Paint | Market Street | 33863.02 | 50632.94 | In progress
C002 | Shopping Complex B | T825 | Concrete Pouring | Sarah Johnson | Completed | High | 2024-09-27 | 2024-10-06 | 2024-10-06 | 100 | Rebar | Market Street | 13881.34 | 38097.27 | No issues
C003 | Office Tower C | T951 | Site Survey | Emma White | In Progress | Medium | 2023-06-02 | 2023-06-26 |  | 19 | PVC Pipes | Downtown Avenue | 8126.33 | 6738.02 | In progress
C004 | Warehouse D | T138 | Concrete Pouring | John Miller | Completed | Low | 2024-04-19 | 2024-04-28 | 2024-04-28 | 100 | Paint | Industrial Park | 8432.16 | 9815.92 | No issues
C002 | Shopping Complex B | T346 | Concrete Pouring | Grace Allen | Not Started | High | 2024-06-26 | 2024-07-22 |  | 0 | Paint | Market Street | 28539.19 | 0 | Not started
C001 | Residential Building A | T513 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-09-11 | 2024-09-23 |  | 0 | Concrete | Plot 21, Riverside | 43531.6 | 50476.32 | Not started
C004 | Warehouse D | T153 | Roofing | Dave Brown | Completed | Low | 2023-07-25 | 2023-08-03 | 2023-08-03 | 100 | Concrete | Industrial Park | 24392.3 | 17986.12 | No issues
C003 | Office Tower C | T102 | Plumbing Installations | Dave Brown | Blocked | Medium | 2024-07-18 | 2024-07-28 |  | 0 | Copper Wires | Downtown Avenue | 29180.41 | 18443.3 | Not started
C004 | Warehouse D | T692 | Foundation Excavation | Sarah Johnson | Not Started | High | 2023-01-14 | 2023-02-06 |  | 0 | Roofing Sheets | Industrial Park | 35272.02 | 0 | Not started
C001 | Residential Building A | T474 | Plumbing Installations | Mike Adams | In Progress | High | 2023-04-03 | 2023-04-24 |  | 70 | Roofing Sheets | Plot 21, Riverside | 42510.77 | 48477.27 | In progress
C003 | Office Tower C | T977 | Foundation Excavation | Mike Adams | Blocked | Low | 2023-07-13 | 2023-08-07 |  | 0 | PVC Pipes | Downtown Avenue | 8581.95 | 9778.23 | Not started
C002 | Shopping Complex B | T884 | Concrete Pouring | Mike Adams | Completed | Low | 2024-10-19 | 2024-11-16 | 2024-11-16 | 100 | Steel Beams | Market Street | 9232.44 | 34451.03 | No issues
C004 | Warehouse D | T458 | Electrical Wiring | Mike Adams | Blocked | Low | 2024-03-26 | 2024-04-07 |  | 0 | Steel Beams | Industrial Park | 44044.76 | 31611.58 | Not started
C003 | Office Tower C | T572 | Foundation Excavation | Rachel Green | In Progress | Low | 2023-03-14 | 2023-04-06 |  | 65 | Paint | Downtown Avenue | 15973.36 | 10059.65 | In progress
C002 | Shopping Complex B | T585 | Steel Framework Setup | Emma White | In Progress | Medium | 2024-11-26 | 2024-12-18 |  | 71 | Steel Beams | Market Street | 9623.42 | 34973.49 | In progress
C001 | Residential Building A | T570 | Interior Painting | Sarah Johnson | Not Started | High | 2024-05-25 | 2024-06-14 |  | 0 | Rebar | Plot 21, Riverside | 40006.34 | 0 | Not started
C001 | Residential Building A | T913 | Roofing | Mike Adams | Completed | Low | 2023-07-19 | 2023-07-28 | 2023-07-28 | 100 | PVC Pipes | Plot 21, Riverside | 35115.16 | 21858.15 | No issues
C002 | Shopping Complex B | T224 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2024-10-17 | 2024-11-04 |  | 75 | Roofing Sheets | Market Street | 10152.96 | 34675.63 | In progress
C002 | Shopping Complex B | T147 | Steel Framework Setup | Grace Allen | In Progress | Low | 2023-05-07 | 2023-06-03 |  | 91 | PVC Pipes | Market Street | 33146.91 | 61553.85 | In progress
C001 | Residential Building A | T711 | Site Survey | Grace Allen | In Progress | Medium | 2024-04-12 | 2024-04-28 |  | 67 | Roofing Sheets | Plot 21, Riverside | 25716.97 | 19984.16 | In progress
C004 | Warehouse D | T187 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-04-09 | 2023-04-17 |  | 8 | Concrete | Industrial Park | 30052.25 | 33188.07 | In progress
C004 | Warehouse D | T429 | Plumbing Installations | Grace Allen | Blocked | Medium | 2024-11-26 | 2024-12-17 |  | 0 | PVC Pipes | Industrial Park | 17464.2 | 18816.55 | Not started
C003 | Office Tower C | T146 | Site Survey | Mike Adams | Completed | High | 2023-12-16 | 2023-12-24 | 2023-12-24 | 100 | Rebar | Downtown Avenue | 35317.12 | 31674 | No issues
C004 | Warehouse D | T237 | Plumbing Installations | Grace Allen | Not Started | Low | 2024-06-12 | 2024-07-08 |  | 0 | Concrete | Industrial Park | 8752.33 | 0 | Not started
C004 | Warehouse D | T477 | Site Survey | Rachel Green | In Progress | Low | 2023-04-08 | 2023-05-04 |  | 83 | Concrete | Industrial Park | 5237.51 | 4522.65 | In progress
C003 | Office Tower C | T618 | Foundation Excavation | Dave Brown | In Progress | High | 2024-03-12 | 2024-03-25 |  | 29 | Roofing Sheets | Downtown Avenue | 18465.57 | 11420.78 | In progress
C002 | Shopping Complex B | T191 | Plumbing Installations | John Miller | In Progress | Medium | 2024-10-07 | 2024-10-28 |  | 16 | Cement | Market Street | 44319.75 | 73209.97 | In progress
C002 | Shopping Complex B | T422 | Foundation Excavation | Emma White | Completed | High | 2024-09-22 | 2024-10-06 | 2024-10-06 | 100 | Rebar | Market Street | 44063.3 | 76971.82 | No issues
C002 | Shopping Complex B | T346 | Steel Framework Setup | Rachel Green | Not Started | Medium | 2023-09-22 | 2023-10-05 |  | 0 | Paint | Market Street | 36982.01 | 0 | Not started
C003 | Office Tower C | T887 | Interior Painting | Dave Brown | Blocked | Low | 2024-10-19 | 2024-11-01 |  | 0 | PVC Pipes | Downtown Avenue | 17607.52 | 17681.02 | Not started
C001 | Residential Building A | T131 | Site Survey | Grace Allen | Not Started | High | 2024-03-11 | 2024-04-10 |  | 0 | Steel Beams | Plot 21, Riverside | 24715.73 | 0 | Not started
C001 | Residential Building A | T366 | Foundation Excavation | Emma White | Not Started | Medium | 2024-03-16 | 2024-03-24 |  | 0 | PVC Pipes | Plot 21, Riverside | 21233.01 | 0 | Not started
C003 | Office Tower C | T700 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-12-14 | 2024-12-30 |  | 0 | Concrete | Downtown Avenue | 8329.53 | 9876.95 | Not started
C002 | Shopping Complex B | T690 | Concrete Pouring | Sarah Johnson | Blocked | High | 2024-03-24 | 2024-04-04 |  | 0 | PVC Pipes | Market Street | 28130.93 | 52095.09 | Not started
C004 | Warehouse D | T390 | Plumbing Installations | Dave Brown | Blocked | High | 2023-07-12 | 2023-08-11 |  | 0 | Cement | Industrial Park | 35503.92 | 42409.64 | Not started
C002 | Shopping Complex B | T896 | Interior Painting | Sarah Johnson | Blocked | Low | 2023-06-23 | 2023-07-16 |  | 0 | Steel Beams | Market Street | 38913.1 | 69631.2 | Not started
C001 | Residential Building A | T216 | Site Survey | Grace Allen | Not Started | High | 2023-01-15 | 2023-02-12 |  | 0 | PVC Pipes | Plot 21, Riverside | 22181.1 | 0 | Not started
C001 | Residential Building A | T236 | Interior Painting | Sarah Johnson | Not Started | High | 2024-05-20 | 2024-05-29 |  | 0 | Rebar | Plot 21, Riverside | 36447.99 | 0 | Not started
C001 | Residential Building A | T147 | Site Survey | Dave Brown | Completed | Low | 2024-06-22 | 2024-07-06 | 2024-07-06 | 100 | Copper Wires | Plot 21, Riverside | 26238.26 | 24673.68 | No issues
C003 | Office Tower C | T721 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-11-23 | 2023-12-10 | 2023-12-10 | 100 | Rebar | Downtown Avenue | 42781.41 | 33804.58 | No issues
C001 | Residential Building A | T864 | Electrical Wiring | Grace Allen | Completed | Medium | 2023-02-04 | 2023-02-11 | 2023-02-11 | 100 | PVC Pipes | Plot 21, Riverside | 37508.09 | 41409.26 | No issues
C001 | Residential Building A | T621 | Plumbing Installations | John Miller | Completed | Low | 2024-11-15 | 2024-12-11 | 2024-12-11 | 100 | Paint | Plot 21, Riverside | 37388.19 | 35404.68 | No issues
C001 | Residential Building A | T236 | Electrical Wiring | Emma White | Completed | Low | 2023-04-23 | 2023-05-06 | 2023-05-06 | 100 | Roofing Sheets | Plot 21, Riverside | 44992.93 | 44312.86 | No issues
C001 | Residential Building A | T912 | Plumbing Installations | Emma White | In Progress | High | 2023-01-20 | 2023-02-03 |  | 72 | Cement | Plot 21, Riverside | 27229.2 | 19688.98 | In progress
C002 | Shopping Complex B | T674 | Foundation Excavation | John Miller | In Progress | Medium | 2024-03-07 | 2024-03-31 |  | 49 | PVC Pipes | Market Street | 21506.55 | 44918.51 | In progress
C004 | Warehouse D | T370 | Foundation Excavation | Rachel Green | In Progress | High | 2024-05-09 | 2024-05-23 |  | 38 | Paint | Industrial Park | 26986.33 | 22128.83 | In progress
C003 | Office Tower C | T470 | Foundation Excavation | Rachel Green | Blocked | Medium | 2023-04-22 | 2023-05-02 |  | 0 | Paint | Downtown Avenue | 25586.47 | 20566.72 | Not started
C004 | Warehouse D | T688 | Interior Painting | Emma White | Blocked | Medium | 2023-12-11 | 2023-12-29 |  | 0 | Paint | Industrial Park | 26998.98 | 21974.14 | Not started
C002 | Shopping Complex B | T198 | Foundation Excavation | Sarah Johnson | Blocked | High | 2024-08-05 | 2024-08-16 |  | 0 | Cement | Market Street | 34410.84 | 46930.83 | Not started
C001 | Residential Building A | T730 | Roofing | Dave Brown | In Progress | Medium | 2023-11-15 | 2023-12-12 |  | 54 | PVC Pipes | Plot 21, Riverside | 43176.86 | 38222.8 | In progress
C001 | Residential Building A | T611 | Roofing | John Miller | Not Started | Medium | 2024-02-01 | 2024-02-19 |  | 0 | Steel Beams | Plot 21, Riverside | 38563.58 | 0 | Not started
C003 | Office Tower C | T983 | Interior Painting | Grace Allen | Completed | High | 2023-09-07 | 2023-09-29 | 2023-09-29 | 100 | Rebar | Downtown Avenue | 41014.86 | 33217.5 | No issues
C002 | Shopping Complex B | T839 | Site Survey | Grace Allen | Not Started | Medium | 2023-08-02 | 2023-08-28 |  | 0 | Rebar | Market Street | 34355.17 | 0 | Not started
C002 | Shopping Complex B | T870 | Site Survey | Mike Adams | Blocked | Medium | 2024-01-18 | 2024-01-30 |  | 0 | Cement | Market Street | 31597.05 | 58062.79 | Not started
C003 | Office Tower C | T756 | Interior Painting | Emma White | Blocked | High | 2024-04-21 | 2024-05-18 |  | 0 | Cement | Downtown Avenue | 31303.69 | 27445.16 | Not started
C001 | Residential Building A | T150 | Steel Framework Setup | Rachel Green | Blocked | High | 2023-03-06 | 2023-03-24 |  | 0 | Rebar | Plot 21, Riverside | 31904.04 | 21439.01 | Not started
C001 | Residential Building A | T782 | Electrical Wiring | John Miller | Completed | Medium | 2024-01-17 | 2024-02-08 | 2024-02-08 | 100 | Steel Beams | Plot 21, Riverside | 32691.16 | 38705.5 | No issues
C001 | Residential Building A | T366 | Site Survey | Sarah Johnson | Completed | Medium | 2023-11-12 | 2023-11-23 | 2023-11-23 | 100 | Steel Beams | Plot 21, Riverside | 37819.97 | 36609.36 | No issues
C004 | Warehouse D | T456 | Roofing | Carlos Rivera | Blocked | Low | 2023-02-26 | 2023-03-08 |  | 0 | Copper Wires | Industrial Park | 37211.31 | 32598.23 | Not started
C003 | Office Tower C | T813 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2023-03-20 | 2023-03-28 |  | 0 | PVC Pipes | Downtown Avenue | 31551 | 23725.34 | Not started
C002 | Shopping Complex B | T275 | Plumbing Installations | Emma White | Completed | High | 2024-04-07 | 2024-05-03 | 2024-05-03 | 100 | Roofing Sheets | Market Street | 19386.26 | 37359.17 | No issues
C003 | Office Tower C | T915 | Foundation Excavation | Rachel Green | Completed | Medium | 2023-06-11 | 2023-06-28 | 2023-06-28 | 100 | PVC Pipes | Downtown Avenue | 16346.67 | 15362.78 | No issues
C001 | Residential Building A | T433 | Interior Painting | Carlos Rivera | In Progress | Medium | 2023-11-15 | 2023-12-14 |  | 82 | PVC Pipes | Plot 21, Riverside | 33037.23 | 25735.69 | In progress
C002 | Shopping Complex B | T205 | Steel Framework Setup | Rachel Green | Completed | Low | 2024-01-23 | 2024-02-15 | 2024-02-15 | 100 | Roofing Sheets | Market Street | 40048.89 | 65494.71 | No issues
C001 | Residential Building A | T400 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2023-09-25 | 2023-10-23 |  | 36 | Paint | Plot 21, Riverside | 16003.94 | 17324.69 | In progress
C001 | Residential Building A | T293 | Steel Framework Setup | Grace Allen | Not Started | High | 2023-07-13 | 2023-08-04 |  | 0 | Paint | Plot 21, Riverside | 16799.17 | 0 | Not started
C002 | Shopping Complex B | T848 | Interior Painting | Sarah Johnson | Not Started | High | 2023-01-17 | 2023-02-05 |  | 0 | Rebar | Market Street | 27934.02 | 0 | Not started
C001 | Residential Building A | T188 | Electrical Wiring | Grace Allen | Completed | Medium | 2023-11-03 | 2023-11-10 | 2023-11-10 | 100 | Concrete | Plot 21, Riverside | 29552.13 | 27779.56 | No issues
C003 | Office Tower C | T183 | Interior Painting | Grace Allen | In Progress | Low | 2024-04-15 | 2024-05-14 |  | 1 | Roofing Sheets | Downtown Avenue | 36903.67 | 35267.34 | In progress
C001 | Residential Building A | T511 | Concrete Pouring | Mike Adams | Not Started | High | 2024-07-06 | 2024-07-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 30467.21 | 0 | Not started
C003 | Office Tower C | T326 | Plumbing Installations | Emma White | In Progress | Medium | 2024-08-02 | 2024-08-11 |  | 38 | Steel Beams | Downtown Avenue | 20297.37 | 18551.99 | In progress
C004 | Warehouse D | T351 | Site Survey | Dave Brown | Blocked | Medium | 2023-10-09 | 2023-10-27 |  | 0 | Concrete | Industrial Park | 35287.34 | 32170.65 | Not started
C003 | Office Tower C | T989 | Steel Framework Setup | Mike Adams | In Progress | High | 2023-07-08 | 2023-07-29 |  | 58 | Paint | Downtown Avenue | 31214.26 | 28973.94 | In progress
C003 | Office Tower C | T766 | Electrical Wiring | Dave Brown | In Progress | Medium | 2023-06-26 | 2023-07-26 |  | 92 | Paint | Downtown Avenue | 33060 | 30028.33 | In progress
C003 | Office Tower C | T657 | Plumbing Installations | Grace Allen | Blocked | Medium | 2023-11-24 | 2023-12-19 |  | 0 | Concrete | Downtown Avenue | 19519.47 | 15537.65 | Not started
C003 | Office Tower C | T236 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-04-15 | 2023-05-02 |  | 55 | Paint | Downtown Avenue | 40578.94 | 43146.52 | In progress
C004 | Warehouse D | T287 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2023-04-09 | 2023-05-04 |  | 0 | Cement | Industrial Park | 49071.14 | 58555.76 | Not started
C004 | Warehouse D | T454 | Plumbing Installations | Dave Brown | Completed | High | 2023-03-28 | 2023-04-21 | 2023-04-21 | 100 | Copper Wires | Industrial Park | 17165.86 | 13491.68 | No issues
C004 | Warehouse D | T981 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-03-28 | 2023-04-25 |  | 14 | Cement | Industrial Park | 39108.52 | 24910.51 | In progress
C002 | Shopping Complex B | T443 | Roofing | Grace Allen | Not Started | Low | 2024-01-06 | 2024-02-04 |  | 0 | Steel Beams | Market Street | 30573.7 | 0 | Not started
C004 | Warehouse D | T286 | Foundation Excavation | Rachel Green | Not Started | Medium | 2024-04-21 | 2024-05-06 |  | 0 | PVC Pipes | Industrial Park | 32103.98 | 0 | Not started
C004 | Warehouse D | T485 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2023-06-02 | 2023-06-29 | 2023-06-29 | 100 | Rebar | Industrial Park | 30713.1 | 34898.72 | No issues
C001 | Residential Building A | T212 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-06-27 | 2023-07-05 |  | 22 | Cement | Plot 21, Riverside | 29999.53 | 33069.85 | In progress
C002 | Shopping Complex B | T213 | Site Survey | Rachel Green | Completed | High | 2024-10-06 | 2024-10-26 | 2024-10-26 | 100 | Rebar | Market Street | 26240.64 | 45096.69 | No issues
C001 | Residential Building A | T517 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-11-27 | 2023-12-10 |  | 0 | Steel Beams | Plot 21, Riverside | 44635.19 | 44377.24 | Not started
C001 | Residential Building A | T915 | Foundation Excavation | Emma White | Completed | Low | 2024-10-13 | 2024-10-30 | 2024-10-30 | 100 | Cement | Plot 21, Riverside | 5310.55 | 4773.93 | No issues
C003 | Office Tower C | T632 | Concrete Pouring | John Miller | Not Started | Medium | 2023-12-20 | 2024-01-09 |  | 0 | Concrete | Downtown Avenue | 5928.13 | 0 | Not started
C002 | Shopping Complex B | T296 | Foundation Excavation | John Miller | In Progress | Medium | 2023-05-03 | 2023-05-20 |  | 58 | Concrete | Market Street | 15761.58 | 41790.21 | In progress
C004 | Warehouse D | T713 | Roofing | Carlos Rivera | Not Started | Low | 2024-09-19 | 2024-10-16 |  | 0 | Rebar | Industrial Park | 27172.27 | 0 | Not started
C001 | Residential Building A | T592 | Interior Painting | Emma White | Not Started | Low | 2024-11-11 | 2024-12-07 |  | 0 | PVC Pipes | Plot 21, Riverside | 5037.31 | 0 | Not started
C004 | Warehouse D | T368 | Foundation Excavation | Carlos Rivera | Completed | Low | 2023-09-28 | 2023-10-14 | 2023-10-14 | 100 | Paint | Industrial Park | 38256.76 | 27261.41 | No issues
C002 | Shopping Complex B | T378 | Site Survey | John Miller | Not Started | High | 2024-09-22 | 2024-10-06 |  | 0 | PVC Pipes | Market Street | 14304 | 0 | Not started
C001 | Residential Building A | T308 | Concrete Pouring | Sarah Johnson | Not Started | High | 2024-10-28 | 2024-11-06 |  | 0 | Concrete | Plot 21, Riverside | 31282.34 | 0 | Not started
C001 | Residential Building A | T354 | Foundation Excavation | Dave Brown | Blocked | High | 2023-10-27 | 2023-11-16 |  | 0 | Rebar | Plot 21, Riverside | 34496.53 | 34728.86 | Not started
C002 | Shopping Complex B | T130 | Site Survey | Rachel Green | Completed | Low | 2023-06-02 | 2023-06-15 | 2023-06-15 | 100 | PVC Pipes | Market Street | 49650.8 | 76489.01 | No issues
C002 | Shopping Complex B | T650 | Plumbing Installations | Mike Adams | In Progress | Medium | 2024-09-14 | 2024-09-23 |  | 68 | Paint | Market Street | 15098.28 | 36575.42 | In progress
C003 | Office Tower C | T915 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2024-11-24 | 2024-12-14 |  | 0 | Cement | Downtown Avenue | 47987.39 | 0 | Not started
C003 | Office Tower C | T113 | Interior Painting | Sarah Johnson | Not Started | Medium | 2023-06-09 | 2023-07-05 |  | 0 | Steel Beams | Downtown Avenue | 13909.42 | 0 | Not started
C004 | Warehouse D | T346 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-03-16 | 2024-04-06 |  | 0 | Concrete | Industrial Park | 34440.36 | 38113.76 | Not started
C003 | Office Tower C | T725 | Steel Framework Setup | Sarah Johnson | Completed | High | 2023-04-20 | 2023-05-09 | 2023-05-09 | 100 | Roofing Sheets | Downtown Avenue | 6528.97 | 3919.92 | No issues
C001 | Residential Building A | T723 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-12-03 | 2023-12-17 |  | 0 | PVC Pipes | Plot 21, Riverside | 35541.33 | 0 | Not started
C002 | Shopping Complex B | T271 | Electrical Wiring | Rachel Green | In Progress | High | 2023-05-15 | 2023-05-31 |  | 18 | PVC Pipes | Market Street | 30077.92 | 55765.21 | In progress
C002 | Shopping Complex B | T752 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-08-21 | 2024-09-07 | 2024-09-07 | 100 | Roofing Sheets | Market Street | 18006.25 | 45908.09 | No issues
C002 | Shopping Complex B | T558 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2023-11-06 | 2023-11-23 |  | 0 | Rebar | Market Street | 5472.23 | 0 | Not started
C004 | Warehouse D | T832 | Steel Framework Setup | Rachel Green | Not Started | Low | 2024-08-13 | 2024-09-06 |  | 0 | Rebar | Industrial Park | 5907.1 | 0 | Not started
C003 | Office Tower C | T953 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2023-06-21 | 2023-07-03 |  | 74 | Concrete | Downtown Avenue | 6514.65 | 6969.22 | In progress
C002 | Shopping Complex B | T936 | Roofing | Sarah Johnson | In Progress | Low | 2024-10-09 | 2024-10-19 |  | 11 | Paint | Market Street | 5769.47 | 30909.65 | In progress
C004 | Warehouse D | T323 | Plumbing Installations | Mike Adams | Not Started | High | 2024-12-08 | 2024-12-18 |  | 0 | Roofing Sheets | Industrial Park | 49541.89 | 0 | Not started
C003 | Office Tower C | T949 | Steel Framework Setup | Emma White | Blocked | Medium | 2024-01-23 | 2024-02-11 |  | 0 | Copper Wires | Downtown Avenue | 23937.07 | 27558.31 | Not started
C003 | Office Tower C | T876 | Site Survey | Sarah Johnson | Completed | High | 2024-08-22 | 2024-09-21 | 2024-09-21 | 100 | Cement | Downtown Avenue | 29203.46 | 24989.06 | No issues
C001 | Residential Building A | T403 | Concrete Pouring | John Miller | Completed | High | 2023-04-10 | 2023-04-22 | 2023-04-22 | 100 | Steel Beams | Plot 21, Riverside | 23864.82 | 24115.36 | No issues
C003 | Office Tower C | T266 | Site Survey | Grace Allen | Blocked | Medium | 2023-10-23 | 2023-11-13 |  | 0 | Roofing Sheets | Downtown Avenue | 40126.45 | 24849.08 | Not started
C003 | Office Tower C | T591 | Steel Framework Setup | Rachel Green | Not Started | High | 2023-09-11 | 2023-10-04 |  | 0 | PVC Pipes | Downtown Avenue | 21941.47 | 0 | Not started
C002 | Shopping Complex B | T931 | Foundation Excavation | Emma White | Completed | High | 2024-11-10 | 2024-12-07 | 2024-12-07 | 100 | PVC Pipes | Market Street | 5783.73 | 29507.13 | No issues
C003 | Office Tower C | T340 | Site Survey | Rachel Green | Completed | Low | 2023-11-11 | 2023-11-29 | 2023-11-29 | 100 | Cement | Downtown Avenue | 49301.57 | 38859.11 | No issues
C004 | Warehouse D | T290 | Interior Painting | Sarah Johnson | Blocked | Medium | 2023-07-10 | 2023-07-30 |  | 0 | Paint | Industrial Park | 22315.42 | 13754.2 | Not started
C002 | Shopping Complex B | T491 | Interior Painting | Carlos Rivera | Completed | High | 2023-10-10 | 2023-10-21 | 2023-10-21 | 100 | Steel Beams | Market Street | 12796.92 | 34975.25 | No issues
C002 | Shopping Complex B | T791 | Foundation Excavation | Grace Allen | Completed | Medium | 2023-07-05 | 2023-07-17 | 2023-07-17 | 100 | Steel Beams | Market Street | 20454.41 | 38333.21 | No issues
C002 | Shopping Complex B | T133 | Site Survey | Dave Brown | Completed | High | 2023-10-05 | 2023-10-25 | 2023-10-25 | 100 | Copper Wires | Market Street | 35936.59 | 49346.7 | No issues
C002 | Shopping Complex B | T578 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-02-27 | 2024-03-27 |  | 0 | PVC Pipes | Market Street | 7657.13 | 31241.09 | Not started
C001 | Residential Building A | T823 | Interior Painting | Carlos Rivera | Completed | High | 2024-06-28 | 2024-07-27 | 2024-07-27 | 100 | Copper Wires | Plot 21, Riverside | 33769.18 | 25658.21 | No issues
C004 | Warehouse D | T853 | Concrete Pouring | Carlos Rivera | Completed | Low | 2024-09-01 | 2024-09-24 | 2024-09-24 | 100 | Paint | Industrial Park | 39472.05 | 34247.94 | No issues
C001 | Residential Building A | T263 | Concrete Pouring | John Miller | In Progress | Low | 2023-08-05 | 2023-08-19 |  | 9 | Steel Beams | Plot 21, Riverside | 27172.52 | 27210.32 | In progress
C003 | Office Tower C | T219 | Electrical Wiring | John Miller | Completed | High | 2023-09-09 | 2023-09-24 | 2023-09-24 | 100 | Copper Wires | Downtown Avenue | 6787.43 | 4600.95 | No issues
C001 | Residential Building A | T727 | Concrete Pouring | Grace Allen | Completed | High | 2024-10-10 | 2024-10-24 | 2024-10-24 | 100 | PVC Pipes | Plot 21, Riverside | 35724.05 | 38833.29 | No issues
C003 | Office Tower C | T789 | Electrical Wiring | Dave Brown | Not Started | High | 2024-03-12 | 2024-03-20 |  | 0 | Concrete | Downtown Avenue | 45710.71 | 0 | Not started
C002 | Shopping Complex B | T259 | Electrical Wiring | Sarah Johnson | Completed | High | 2023-06-01 | 2023-06-15 | 2023-06-15 | 100 | Paint | Market Street | 48099.08 | 65083.33 | No issues
C003 | Office Tower C | T975 | Interior Painting | Mike Adams | Blocked | High | 2023-01-25 | 2023-02-23 |  | 0 | Paint | Downtown Avenue | 47688.18 | 29209.46 | Not started
C001 | Residential Building A | T909 | Plumbing Installations | Rachel Green | Not Started | High | 2023-09-05 | 2023-09-24 |  | 0 | Paint | Plot 21, Riverside | 16081.57 | 0 | Not started
C004 | Warehouse D | T146 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-08-21 | 2023-09-17 |  | 30 | Paint | Industrial Park | 41827.31 | 42546.51 | In progress
C003 | Office Tower C | T480 | Concrete Pouring | Grace Allen | In Progress | Low | 2023-09-11 | 2023-10-07 |  | 44 | Roofing Sheets | Downtown Avenue | 24051.38 | 23371.71 | In progress
C001 | Residential Building A | T899 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2024-10-25 | 2024-11-17 |  | 31 | Roofing Sheets | Plot 21, Riverside | 15241.76 | 9471.24 | In progress
C004 | Warehouse D | T492 | Site Survey | Sarah Johnson | Completed | Medium | 2023-07-07 | 2023-07-18 | 2023-07-18 | 100 | Steel Beams | Industrial Park | 35797.19 | 31711.84 | No issues
C003 | Office Tower C | T910 | Concrete Pouring | Mike Adams | Not Started | High | 2024-12-05 | 2024-12-14 |  | 0 | Concrete | Downtown Avenue | 29634.81 | 0 | Not started
C002 | Shopping Complex B | T913 | Steel Framework Setup | Emma White | Not Started | High | 2023-06-27 | 2023-07-22 |  | 0 | Steel Beams | Market Street | 29045.83 | 0 | Not started
C003 | Office Tower C | T286 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-06-20 | 2023-07-13 |  | 0 | Rebar | Downtown Avenue | 15363.52 | 14832.92 | Not started
C003 | Office Tower C | T513 | Interior Painting | Sarah Johnson | In Progress | Low | 2024-01-21 | 2024-02-12 |  | 35 | Steel Beams | Downtown Avenue | 29689.02 | 22845.33 | In progress
C003 | Office Tower C | T334 | Plumbing Installations | Rachel Green | Blocked | Medium | 2023-05-14 | 2023-05-24 |  | 0 | Steel Beams | Downtown Avenue | 20319.37 | 18534.85 | Not started
C002 | Shopping Complex B | T216 | Roofing | Dave Brown | Not Started | Medium | 2023-04-15 | 2023-05-15 |  | 0 | PVC Pipes | Market Street | 35151.19 | 0 | Not started
C002 | Shopping Complex B | T401 | Plumbing Installations | John Miller | Not Started | High | 2024-10-10 | 2024-10-21 |  | 0 | Cement | Market Street | 14232.03 | 0 | Not started
C003 | Office Tower C | T470 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-01-17 | 2023-02-13 |  | 0 | Copper Wires | Downtown Avenue | 10876.65 | 0 | Not started
C004 | Warehouse D | T388 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2023-09-16 | 2023-10-09 |  | 0 | Rebar | Industrial Park | 34090.9 | 0 | Not started
C004 | Warehouse D | T997 | Concrete Pouring | John Miller | Not Started | High | 2024-07-02 | 2024-08-01 |  | 0 | Paint | Industrial Park | 28820.78 | 0 | Not started
C003 | Office Tower C | T743 | Site Survey | Rachel Green | Blocked | Medium | 2024-04-22 | 2024-04-30 |  | 0 | PVC Pipes | Downtown Avenue | 37704.45 | 44538.06 | Not started
C002 | Shopping Complex B | T371 | Site Survey | Grace Allen | In Progress | High | 2023-03-20 | 2023-03-29 |  | 27 | Paint | Market Street | 9297.34 | 33849.19 | In progress
C004 | Warehouse D | T265 | Interior Painting | Emma White | Completed | High | 2023-07-20 | 2023-08-15 | 2023-08-15 | 100 | Steel Beams | Industrial Park | 28804.34 | 34441.85 | No issues
C004 | Warehouse D | T388 | Concrete Pouring | Grace Allen | In Progress | High | 2023-05-05 | 2023-05-18 |  | 45 | Roofing Sheets | Industrial Park | 22116.75 | 18069.76 | In progress
C003 | Office Tower C | T305 | Roofing | Carlos Rivera | In Progress | Medium | 2024-07-06 | 2024-07-25 |  | 64 | Concrete | Downtown Avenue | 48839.18 | 34414.59 | In progress
C003 | Office Tower C | T297 | Interior Painting | Sarah Johnson | Completed | High | 2024-07-25 | 2024-08-20 | 2024-08-20 | 100 | Copper Wires | Downtown Avenue | 41492.05 | 40777.25 | No issues
C002 | Shopping Complex B | T811 | Interior Painting | Emma White | Completed | Medium | 2023-04-25 | 2023-05-18 | 2023-05-18 | 100 | Concrete | Market Street | 33742.58 | 49494.38 | No issues
C003 | Office Tower C | T514 | Plumbing Installations | Dave Brown | Blocked | High | 2024-06-19 | 2024-07-15 |  | 0 | Paint | Downtown Avenue | 7339.76 | 4449.6 | Not started
C003 | Office Tower C | T663 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2023-10-16 | 2023-11-02 |  | 0 | PVC Pipes | Downtown Avenue | 15171.39 | 16862.03 | Not started
C003 | Office Tower C | T736 | Roofing | Mike Adams | In Progress | High | 2024-02-19 | 2024-03-03 |  | 66 | Cement | Downtown Avenue | 34815.83 | 37226.02 | In progress
C004 | Warehouse D | T102 | Interior Painting | Grace Allen | In Progress | Low | 2023-03-09 | 2023-03-16 |  | 63 | Copper Wires | Industrial Park | 14539.08 | 16500.55 | In progress
C002 | Shopping Complex B | T788 | Electrical Wiring | Dave Brown | Blocked | Medium | 2023-07-25 | 2023-08-13 |  | 0 | Concrete | Market Street | 13804.23 | 34682.45 | Not started
C004 | Warehouse D | T703 | Foundation Excavation | Rachel Green | Blocked | Low | 2024-03-12 | 2024-03-28 |  | 0 | Roofing Sheets | Industrial Park | 5692.02 | 5150.77 | Not started
C003 | Office Tower C | T562 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-04-28 | 2024-05-12 |  | 26 | Paint | Downtown Avenue | 29772.74 | 25338.48 | In progress
C003 | Office Tower C | T477 | Electrical Wiring | Dave Brown | Not Started | Low | 2024-04-24 | 2024-05-01 |  | 0 | Roofing Sheets | Downtown Avenue | 47312.58 | 0 | Not started
C004 | Warehouse D | T340 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-06-15 | 2023-07-05 |  | 0 | Steel Beams | Industrial Park | 14309.25 | 9122.76 | Not started
C003 | Office Tower C | T661 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-12-20 | 2024-01-04 |  | 0 | Rebar | Downtown Avenue | 29812.48 | 0 | Not started
C002 | Shopping Complex B | T222 | Foundation Excavation | Emma White | Completed | Medium | 2024-11-01 | 2024-11-14 | 2024-11-14 | 100 | Cement | Market Street | 27952.18 | 42932.91 | No issues
C003 | Office Tower C | T630 | Site Survey | Grace Allen | Blocked | Medium | 2023-09-22 | 2023-10-14 |  | 0 | Copper Wires | Downtown Avenue | 17503.09 | 16445.81 | Not started
C002 | Shopping Complex B | T222 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-08-18 | 2024-09-04 |  | 0 | Cement | Market Street | 39773.97 | 64405.34 | Not started
C003 | Office Tower C | T249 | Concrete Pouring | Rachel Green | Not Started | High | 2023-05-09 | 2023-06-08 |  | 0 | Copper Wires | Downtown Avenue | 29070.11 | 0 | Not started
C003 | Office Tower C | T909 | Site Survey | Carlos Rivera | Not Started | Medium | 2024-12-03 | 2024-12-29 |  | 0 | PVC Pipes | Downtown Avenue | 21058.63 | 0 | Not started
C003 | Office Tower C | T302 | Interior Painting | Carlos Rivera | Not Started | High | 2023-07-17 | 2023-08-16 |  | 0 | Roofing Sheets | Downtown Avenue | 38971.04 | 0 | Not started
C003 | Office Tower C | T835 | Interior Painting | John Miller | Not Started | High | 2024-05-16 | 2024-05-25 |  | 0 | Concrete | Downtown Avenue | 36376.78 | 0 | Not started
C001 | Residential Building A | T599 | Interior Painting | John Miller | Not Started | High | 2023-11-19 | 2023-12-16 |  | 0 | Roofing Sheets | Plot 21, Riverside | 9864.57 | 0 | Not started
C004 | Warehouse D | T123 | Site Survey | John Miller | Not Started | High | 2023-09-19 | 2023-10-11 |  | 0 | Copper Wires | Industrial Park | 19859.15 | 0 | Not started
C002 | Shopping Complex B | T819 | Foundation Excavation | Sarah Johnson | Completed | High | 2024-09-28 | 2024-10-23 | 2024-10-23 | 100 | Concrete | Market Street | 34592.28 | 53970.72 | No issues
C003 | Office Tower C | T273 | Electrical Wiring | Emma White | Not Started | Low | 2024-06-25 | 2024-07-21 |  | 0 | PVC Pipes | Downtown Avenue | 13316.31 | 0 | Not started
C003 | Office Tower C | T375 | Concrete Pouring | Emma White | Not Started | Medium | 2024-07-18 | 2024-08-01 |  | 0 | Roofing Sheets | Downtown Avenue | 38542.25 | 0 | Not started
C003 | Office Tower C | T421 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2024-02-13 | 2024-03-12 |  | 0 | Concrete | Downtown Avenue | 28907.41 | 0 | Not started
C001 | Residential Building A | T281 | Roofing | Rachel Green | Not Started | Medium | 2023-02-08 | 2023-02-17 |  | 0 | PVC Pipes | Plot 21, Riverside | 31094.04 | 0 | Not started
C001 | Residential Building A | T908 | Plumbing Installations | Mike Adams | Blocked | High | 2024-05-16 | 2024-05-28 |  | 0 | Steel Beams | Plot 21, Riverside | 18170.32 | 19574.24 | Not started
C002 | Shopping Complex B | T148 | Roofing | Rachel Green | In Progress | Medium | 2023-09-01 | 2023-09-25 |  | 25 | Roofing Sheets | Market Street | 36516.44 | 60896.03 | In progress
C001 | Residential Building A | T351 | Site Survey | Sarah Johnson | In Progress | High | 2023-04-05 | 2023-04-20 |  | 21 | PVC Pipes | Plot 21, Riverside | 17884.26 | 13095.54 | In progress
C004 | Warehouse D | T457 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-08-04 | 2024-08-23 | 2024-08-23 | 100 | Cement | Industrial Park | 17383 | 12601.67 | No issues
C002 | Shopping Complex B | T840 | Foundation Excavation | Emma White | Not Started | Medium | 2023-03-20 | 2023-03-31 |  | 0 | Rebar | Market Street | 37012.34 | 0 | Not started
C001 | Residential Building A | T569 | Roofing | Grace Allen | Completed | Medium | 2024-05-28 | 2024-06-22 | 2024-06-22 | 100 | Copper Wires | Plot 21, Riverside | 38447.66 | 31392.96 | No issues
C003 | Office Tower C | T195 | Steel Framework Setup | Emma White | Not Started | Medium | 2024-08-05 | 2024-09-04 |  | 0 | Cement | Downtown Avenue | 19837.04 | 0 | Not started
C003 | Office Tower C | T866 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2023-01-27 | 2023-02-22 | 2023-02-22 | 100 | Steel Beams | Downtown Avenue | 16027.2 | 14810.94 | No issues
C002 | Shopping Complex B | T501 | Electrical Wiring | Rachel Green | In Progress | Low | 2024-11-22 | 2024-12-21 |  | 8 | Roofing Sheets | Market Street | 11715.65 | 39229.98 | In progress
C004 | Warehouse D | T401 | Plumbing Installations | Emma White | Completed | High | 2024-05-16 | 2024-06-12 | 2024-06-12 | 100 | PVC Pipes | Industrial Park | 42613.59 | 32987.73 | No issues
C002 | Shopping Complex B | T616 | Concrete Pouring | Grace Allen | In Progress | Medium | 2023-02-10 | 2023-03-09 |  | 99 | Steel Beams | Market Street | 7125.08 | 32502.47 | In progress
C001 | Residential Building A | T103 | Concrete Pouring | John Miller | Completed | Low | 2024-06-08 | 2024-06-26 | 2024-06-26 | 100 | Cement | Plot 21, Riverside | 35590.4 | 33059.6 | No issues
C002 | Shopping Complex B | T616 | Plumbing Installations | Mike Adams | Blocked | High | 2023-10-14 | 2023-10-26 |  | 0 | Cement | Market Street | 40227.77 | 70971.08 | Not started
C001 | Residential Building A | T933 | Electrical Wiring | Rachel Green | Not Started | Low | 2023-02-15 | 2023-03-04 |  | 0 | Cement | Plot 21, Riverside | 35710.96 | 0 | Not started
C003 | Office Tower C | T815 | Concrete Pouring | John Miller | In Progress | High | 2024-05-15 | 2024-06-09 |  | 62 | Concrete | Downtown Avenue | 47960.36 | 30154.75 | In progress
C003 | Office Tower C | T595 | Site Survey | Rachel Green | Completed | Low | 2024-08-12 | 2024-08-29 | 2024-08-29 | 100 | Cement | Downtown Avenue | 21580.64 | 15617.25 | No issues
C004 | Warehouse D | T831 | Electrical Wiring | Grace Allen | Completed | High | 2024-11-28 | 2024-12-22 | 2024-12-22 | 100 | Roofing Sheets | Industrial Park | 32957.97 | 28660.02 | No issues
C002 | Shopping Complex B | T931 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2024-10-20 | 2024-11-09 | 2024-11-09 | 100 | PVC Pipes | Market Street | 6257.3 | 32799.03 | No issues
C003 | Office Tower C | T749 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-07-22 | 2023-08-13 |  | 20 | Copper Wires | Downtown Avenue | 37642.94 | 30332.99 | In progress
C003 | Office Tower C | T240 | Steel Framework Setup | Rachel Green | In Progress | High | 2023-07-23 | 2023-07-31 |  | 31 | Paint | Downtown Avenue | 41669.48 | 31251.54 | In progress
C004 | Warehouse D | T315 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2023-11-04 | 2023-11-27 |  | 0 | Cement | Industrial Park | 14873.66 | 16252.71 | Not started
C001 | Residential Building A | T142 | Electrical Wiring | Emma White | Completed | Low | 2023-05-14 | 2023-05-28 | 2023-05-28 | 100 | Cement | Plot 21, Riverside | 28448.25 | 31548.73 | No issues
C003 | Office Tower C | T247 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2024-10-12 | 2024-11-10 |  | 28 | Copper Wires | Downtown Avenue | 33105.67 | 24209.63 | In progress
C001 | Residential Building A | T511 | Steel Framework Setup | Rachel Green | Blocked | High | 2024-02-01 | 2024-02-16 |  | 0 | Steel Beams | Plot 21, Riverside | 42826.05 | 36963.3 | Not started
C001 | Residential Building A | T201 | Foundation Excavation | Mike Adams | Completed | Medium | 2024-09-01 | 2024-09-21 | 2024-09-21 | 100 | Concrete | Plot 21, Riverside | 44661.19 | 36233.25 | No issues
C002 | Shopping Complex B | T977 | Plumbing Installations | Emma White | In Progress | Medium | 2023-03-27 | 2023-04-23 |  | 13 | Rebar | Market Street | 8097.41 | 34539.41 | In progress
C004 | Warehouse D | T619 | Steel Framework Setup | Emma White | In Progress | High | 2023-04-04 | 2023-04-23 |  | 28 | Roofing Sheets | Industrial Park | 11105.72 | 8618.21 | In progress
C004 | Warehouse D | T218 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2023-08-06 | 2023-09-05 |  | 24 | Roofing Sheets | Industrial Park | 25332.49 | 16259.33 | In progress
C002 | Shopping Complex B | T679 | Steel Framework Setup | Rachel Green | Completed | Medium | 2024-04-03 | 2024-04-23 | 2024-04-23 | 100 | PVC Pipes | Market Street | 7816.93 | 32343.19 | No issues
C001 | Residential Building A | T252 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-04-24 | 2023-05-11 |  | 34 | PVC Pipes | Plot 21, Riverside | 7410.91 | 7877.35 | In progress
C002 | Shopping Complex B | T709 | Site Survey | Rachel Green | In Progress | Medium | 2023-09-19 | 2023-09-29 |  | 12 | Copper Wires | Market Street | 36797.31 | 51227.47 | In progress
C001 | Residential Building A | T665 | Interior Painting | Sarah Johnson | Not Started | Low | 2023-01-04 | 2023-01-30 |  | 0 | Paint | Plot 21, Riverside | 45640.82 | 0 | Not started
C002 | Shopping Complex B | T155 | Plumbing Installations | Carlos Rivera | Not Started | Medium | 2023-02-04 | 2023-02-26 |  | 0 | Roofing Sheets | Market Street | 18832.78 | 0 | Not started
C001 | Residential Building A | T491 | Foundation Excavation | Dave Brown | In Progress | High | 2024-12-20 | 2025-01-16 |  | 2 | PVC Pipes | Plot 21, Riverside | 30634.11 | 19247.05 | In progress
C001 | Residential Building A | T594 | Foundation Excavation | Rachel Green | Blocked | Low | 2024-06-14 | 2024-07-09 |  | 0 | Rebar | Plot 21, Riverside | 13394 | 9358.73 | Not started
C004 | Warehouse D | T230 | Electrical Wiring | John Miller | In Progress | Medium | 2024-06-06 | 2024-06-20 |  | 97 | Concrete | Industrial Park | 19105.86 | 14467.14 | In progress
C003 | Office Tower C | T714 | Concrete Pouring | Dave Brown | Not Started | High | 2024-11-21 | 2024-11-30 |  | 0 | PVC Pipes | Downtown Avenue | 22579.03 | 0 | Not started
C001 | Residential Building A | T487 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-10-06 | 2024-10-22 |  | 48 | Paint | Plot 21, Riverside | 46210.39 | 39232.2 | In progress
C004 | Warehouse D | T971 | Interior Painting | Rachel Green | Not Started | Medium | 2024-02-10 | 2024-02-19 |  | 0 | Cement | Industrial Park | 11673.96 | 0 | Not started
C002 | Shopping Complex B | T907 | Steel Framework Setup | Mike Adams | Not Started | Low | 2023-11-07 | 2023-12-05 |  | 0 | Copper Wires | Market Street | 17582.36 | 0 | Not started
C002 | Shopping Complex B | T774 | Site Survey | Carlos Rivera | Blocked | High | 2024-04-03 | 2024-04-18 |  | 0 | Steel Beams | Market Street | 37612.08 | 60220.97 | Not started
C003 | Office Tower C | T876 | Foundation Excavation | Emma White | In Progress | Medium | 2023-07-01 | 2023-07-14 |  | 64 | Rebar | Downtown Avenue | 36795.04 | 33399.49 | In progress
C004 | Warehouse D | T155 | Electrical Wiring | John Miller | Completed | High | 2023-04-16 | 2023-05-02 | 2023-05-02 | 100 | Roofing Sheets | Industrial Park | 28417.38 | 33632.03 | No issues
C003 | Office Tower C | T482 | Steel Framework Setup | John Miller | In Progress | High | 2023-03-28 | 2023-04-10 |  | 8 | PVC Pipes | Downtown Avenue | 27403.99 | 19498.42 | In progress
C004 | Warehouse D | T327 | Roofing | Sarah Johnson | Not Started | Medium | 2024-06-20 | 2024-07-15 |  | 0 | PVC Pipes | Industrial Park | 6814.2 | 0 | Not started
C002 | Shopping Complex B | T411 | Steel Framework Setup | Dave Brown | In Progress | Low | 2024-04-01 | 2024-04-23 |  | 8 | PVC Pipes | Market Street | 43721.78 | 71639.78 | In progress
C003 | Office Tower C | T641 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-05-12 | 2023-06-03 |  | 0 | Rebar | Downtown Avenue | 6292.19 | 0 | Not started
C004 | Warehouse D | T719 | Interior Painting | John Miller | Completed | High | 2023-09-19 | 2023-10-12 | 2023-10-12 | 100 | PVC Pipes | Industrial Park | 49845.98 | 34152.72 | No issues
C002 | Shopping Complex B | T238 | Roofing | John Miller | Blocked | Medium | 2023-06-19 | 2023-07-01 |  | 0 | Paint | Market Street | 27151.09 | 58032.99 | Not started
C004 | Warehouse D | T169 | Interior Painting | John Miller | In Progress | High | 2023-07-16 | 2023-08-12 |  | 36 | Cement | Industrial Park | 14129.52 | 13981.45 | In progress
C003 | Office Tower C | T982 | Plumbing Installations | Grace Allen | Completed | Medium | 2023-06-14 | 2023-06-26 | 2023-06-26 | 100 | PVC Pipes | Downtown Avenue | 19515.56 | 20251.66 | No issues
C003 | Office Tower C | T468 | Interior Painting | John Miller | Not Started | Low | 2023-09-17 | 2023-10-15 |  | 0 | Paint | Downtown Avenue | 18729.25 | 0 | Not started
C001 | Residential Building A | T151 | Site Survey | Emma White | In Progress | High | 2023-04-28 | 2023-05-17 |  | 40 | Paint | Plot 21, Riverside | 39849.68 | 38332.86 | In progress
C003 | Office Tower C | T622 | Concrete Pouring | John Miller | In Progress | Medium | 2023-03-03 | 2023-04-02 |  | 24 | Cement | Downtown Avenue | 16821.12 | 15049.19 | In progress
C001 | Residential Building A | T353 | Steel Framework Setup | Grace Allen | Completed | High | 2024-12-05 | 2025-01-04 | 2025-01-04 | 100 | Rebar | Plot 21, Riverside | 31040.23 | 25377.49 | No issues
C001 | Residential Building A | T503 | Plumbing Installations | Grace Allen | Completed | Low | 2023-07-24 | 2023-08-16 | 2023-08-16 | 100 | Concrete | Plot 21, Riverside | 36995.16 | 32576.7 | No issues
C004 | Warehouse D | T618 | Steel Framework Setup | John Miller | In Progress | Medium | 2024-01-22 | 2024-02-15 |  | 19 | Concrete | Industrial Park | 16399.59 | 13284.56 | In progress
C001 | Residential Building A | T915 | Roofing | Sarah Johnson | Not Started | Low | 2023-07-16 | 2023-08-03 |  | 0 | Concrete | Plot 21, Riverside | 21427.29 | 0 | Not started
C002 | Shopping Complex B | T721 | Site Survey | Mike Adams | Completed | Low | 2023-09-14 | 2023-10-04 | 2023-10-04 | 100 | Paint | Market Street | 30967.49 | 61212.22 | No issues
C003 | Office Tower C | T515 | Site Survey | Rachel Green | Completed | High | 2023-09-24 | 2023-10-03 | 2023-10-03 | 100 | Steel Beams | Downtown Avenue | 10171.09 | 8376.1 | No issues
C004 | Warehouse D | T231 | Steel Framework Setup | Mike Adams | Completed | Medium | 2023-02-17 | 2023-03-11 | 2023-03-11 | 100 | Roofing Sheets | Industrial Park | 39082.57 | 25964.54 | No issues
C001 | Residential Building A | T275 | Interior Painting | Mike Adams | In Progress | Low | 2024-04-15 | 2024-05-07 |  | 22 | Paint | Plot 21, Riverside | 17396.17 | 20733.69 | In progress
C001 | Residential Building A | T860 | Foundation Excavation | Emma White | Not Started | Low | 2024-04-23 | 2024-05-10 |  | 0 | Paint | Plot 21, Riverside | 18996.63 | 0 | Not started
C002 | Shopping Complex B | T819 | Concrete Pouring | Emma White | Blocked | Low | 2024-05-24 | 2024-06-13 |  | 0 | Rebar | Market Street | 35699.21 | 58909.33 | Not started
C002 | Shopping Complex B | T443 | Steel Framework Setup | John Miller | Completed | High | 2024-05-13 | 2024-06-01 | 2024-06-01 | 100 | Cement | Market Street | 11681.52 | 37841.81 | No issues
C003 | Office Tower C | T327 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2024-08-22 | 2024-09-12 |  | 9 | Cement | Downtown Avenue | 33631.25 | 39985.3 | In progress
C004 | Warehouse D | T914 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-01-16 | 2023-02-06 | 2023-02-06 | 100 | Copper Wires | Industrial Park | 28896.17 | 28490.94 | No issues
C001 | Residential Building A | T891 | Roofing | Grace Allen | Completed | High | 2024-01-11 | 2024-01-31 | 2024-01-31 | 100 | Steel Beams | Plot 21, Riverside | 48959.62 | 31217.7 | No issues
C002 | Shopping Complex B | T760 | Concrete Pouring | Rachel Green | Blocked | High | 2023-12-05 | 2023-12-18 |  | 0 | Roofing Sheets | Market Street | 17875.8 | 42099.07 | Not started
C001 | Residential Building A | T443 | Plumbing Installations | Grace Allen | Not Started | Medium | 2024-05-23 | 2024-06-16 |  | 0 | Cement | Plot 21, Riverside | 48999.92 | 0 | Not started
C001 | Residential Building A | T632 | Electrical Wiring | John Miller | Completed | Low | 2023-09-07 | 2023-09-22 | 2023-09-22 | 100 | Copper Wires | Plot 21, Riverside | 10655.7 | 8834.69 | No issues
C003 | Office Tower C | T647 | Foundation Excavation | Carlos Rivera | Completed | Low | 2023-08-15 | 2023-08-28 | 2023-08-28 | 100 | Paint | Downtown Avenue | 39891.87 | 39562.3 | No issues
C003 | Office Tower C | T598 | Electrical Wiring | John Miller | Blocked | High | 2024-01-19 | 2024-01-27 |  | 0 | PVC Pipes | Downtown Avenue | 20447.52 | 20124.53 | Not started
C003 | Office Tower C | T194 | Plumbing Installations | John Miller | Completed | High | 2023-10-26 | 2023-11-16 | 2023-11-16 | 100 | Steel Beams | Downtown Avenue | 41017.16 | 36323.08 | No issues
C001 | Residential Building A | T355 | Foundation Excavation | John Miller | Not Started | High | 2023-03-19 | 2023-04-17 |  | 0 | Steel Beams | Plot 21, Riverside | 22077.95 | 0 | Not started
C004 | Warehouse D | T848 | Plumbing Installations | Mike Adams | Not Started | Low | 2023-03-21 | 2023-04-03 |  | 0 | Rebar | Industrial Park | 31359.03 | 0 | Not started
C001 | Residential Building A | T783 | Roofing | Rachel Green | In Progress | Medium | 2023-10-14 | 2023-10-27 |  | 72 | Roofing Sheets | Plot 21, Riverside | 29591.22 | 23816.04 | In progress
C003 | Office Tower C | T734 | Concrete Pouring | Sarah Johnson | Blocked | High | 2024-07-27 | 2024-08-25 |  | 0 | Paint | Downtown Avenue | 21761.92 | 23597.3 | Not started
C003 | Office Tower C | T815 | Plumbing Installations | Carlos Rivera | In Progress | High | 2023-08-21 | 2023-08-30 |  | 4 | PVC Pipes | Downtown Avenue | 23398.48 | 16612.15 | In progress
C003 | Office Tower C | T162 | Foundation Excavation | Rachel Green | In Progress | Medium | 2023-10-28 | 2023-11-13 |  | 11 | Rebar | Downtown Avenue | 22078.05 | 19341.05 | In progress
C002 | Shopping Complex B | T469 | Concrete Pouring | Grace Allen | Blocked | High | 2024-12-22 | 2025-01-21 |  | 0 | PVC Pipes | Market Street | 46742.48 | 77329.53 | Not started
C002 | Shopping Complex B | T868 | Roofing | Emma White | Blocked | Medium | 2024-05-20 | 2024-06-12 |  | 0 | Roofing Sheets | Market Street | 11773.53 | 33405.38 | Not started
C003 | Office Tower C | T807 | Concrete Pouring | Grace Allen | Completed | Low | 2024-08-06 | 2024-08-24 | 2024-08-24 | 100 | Steel Beams | Downtown Avenue | 25042.76 | 19126.7 | No issues
C002 | Shopping Complex B | T546 | Roofing | Emma White | Blocked | Medium | 2023-01-24 | 2023-02-07 |  | 0 | Roofing Sheets | Market Street | 25156.95 | 53096.64 | Not started
C004 | Warehouse D | T447 | Plumbing Installations | Mike Adams | Blocked | High | 2023-11-27 | 2023-12-21 |  | 0 | Roofing Sheets | Industrial Park | 47520.8 | 34405.64 | Not started
C003 | Office Tower C | T438 | Plumbing Installations | Emma White | Not Started | High | 2023-11-26 | 2023-12-05 |  | 0 | Steel Beams | Downtown Avenue | 17210.09 | 0 | Not started
C003 | Office Tower C | T924 | Interior Painting | Dave Brown | Blocked | Low | 2023-06-04 | 2023-06-21 |  | 0 | Rebar | Downtown Avenue | 32645.53 | 31946.18 | Not started
C004 | Warehouse D | T458 | Interior Painting | Rachel Green | In Progress | Medium | 2023-01-09 | 2023-01-23 |  | 58 | Concrete | Industrial Park | 38022.49 | 36217.43 | In progress
C004 | Warehouse D | T356 | Foundation Excavation | Emma White | Completed | High | 2023-05-12 | 2023-06-01 | 2023-06-01 | 100 | Roofing Sheets | Industrial Park | 16819.35 | 17132.04 | No issues
C003 | Office Tower C | T850 | Roofing | Mike Adams | Blocked | High | 2023-01-23 | 2023-02-21 |  | 0 | Rebar | Downtown Avenue | 22904.47 | 23807.87 | Not started
C003 | Office Tower C | T109 | Interior Painting | Grace Allen | Not Started | Medium | 2024-08-03 | 2024-08-23 |  | 0 | Steel Beams | Downtown Avenue | 38503.51 | 0 | Not started
C004 | Warehouse D | T286 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2023-09-19 | 2023-10-09 | 2023-10-09 | 100 | Concrete | Industrial Park | 24884.19 | 25331.02 | No issues
C004 | Warehouse D | T648 | Concrete Pouring | Emma White | In Progress | High | 2024-06-23 | 2024-07-22 |  | 20 | Rebar | Industrial Park | 47783.48 | 36529.41 | In progress
C003 | Office Tower C | T600 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2023-10-04 | 2023-10-18 |  | 83 | Steel Beams | Downtown Avenue | 39243.03 | 36953.97 | In progress
C002 | Shopping Complex B | T677 | Steel Framework Setup | Carlos Rivera | Completed | High | 2024-10-15 | 2024-10-27 | 2024-10-27 | 100 | PVC Pipes | Market Street | 5556.23 | 29172.48 | No issues
C001 | Residential Building A | T607 | Concrete Pouring | John Miller | In Progress | Low | 2024-04-26 | 2024-05-24 |  | 0 | Paint | Plot 21, Riverside | 42129.49 | 46236.96 | In progress
C001 | Residential Building A | T434 | Roofing | John Miller | Not Started | Low | 2023-11-06 | 2023-11-13 |  | 0 | Paint | Plot 21, Riverside | 15822.95 | 0 | Not started
C004 | Warehouse D | T449 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2024-06-06 | 2024-06-17 | 2024-06-17 | 100 | Steel Beams | Industrial Park | 31778.65 | 34533.78 | No issues
C001 | Residential Building A | T694 | Plumbing Installations | Mike Adams | In Progress | High | 2024-04-04 | 2024-04-13 |  | 82 | Copper Wires | Plot 21, Riverside | 21654.89 | 24618.37 | In progress
C004 | Warehouse D | T539 | Interior Painting | Rachel Green | Completed | Low | 2023-11-07 | 2023-12-05 | 2023-12-05 | 100 | Cement | Industrial Park | 43605.38 | 40825.73 | No issues
C003 | Office Tower C | T788 | Roofing | Grace Allen | Blocked | Medium | 2024-10-08 | 2024-10-22 |  | 0 | Paint | Downtown Avenue | 30854.53 | 21063.22 | Not started
C003 | Office Tower C | T518 | Concrete Pouring | Dave Brown | In Progress | Low | 2023-01-04 | 2023-01-28 |  | 26 | Cement | Downtown Avenue | 19672.92 | 15097.94 | In progress
C004 | Warehouse D | T447 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2023-04-20 | 2023-04-27 |  | 0 | Cement | Industrial Park | 18618.53 | 18828.24 | Not started
C001 | Residential Building A | T505 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2024-04-26 | 2024-05-25 |  | 0 | Rebar | Plot 21, Riverside | 9867.63 | 10108.02 | Not started
C002 | Shopping Complex B | T784 | Foundation Excavation | John Miller | In Progress | Low | 2024-01-20 | 2024-01-30 |  | 71 | Copper Wires | Market Street | 45703.08 | 59945.8 | In progress
C004 | Warehouse D | T138 | Site Survey | Grace Allen | Blocked | Low | 2024-09-28 | 2024-10-24 |  | 0 | Concrete | Industrial Park | 33952.11 | 23494.6 | Not started
C002 | Shopping Complex B | T375 | Roofing | Mike Adams | Not Started | Low | 2023-04-19 | 2023-05-03 |  | 0 | PVC Pipes | Market Street | 36597.4 | 0 | Not started
C001 | Residential Building A | T429 | Steel Framework Setup | Emma White | Completed | High | 2023-11-09 | 2023-11-20 | 2023-11-20 | 100 | Paint | Plot 21, Riverside | 14216.56 | 12326.18 | No issues
C004 | Warehouse D | T184 | Plumbing Installations | Grace Allen | Blocked | Medium | 2023-11-19 | 2023-12-17 |  | 0 | Cement | Industrial Park | 10188.3 | 9116.55 | Not started
C002 | Shopping Complex B | T236 | Roofing | Dave Brown | Completed | Medium | 2023-10-26 | 2023-11-24 | 2023-11-24 | 100 | Copper Wires | Market Street | 6228.44 | 31049.64 | No issues
C002 | Shopping Complex B | T796 | Roofing | Mike Adams | In Progress | Medium | 2024-07-06 | 2024-08-01 |  | 43 | Concrete | Market Street | 10791.64 | 34487.4 | In progress
C003 | Office Tower C | T228 | Roofing | Sarah Johnson | Blocked | High | 2024-11-02 | 2024-11-23 |  | 0 | Roofing Sheets | Downtown Avenue | 24227.04 | 22371.17 | Not started
C003 | Office Tower C | T453 | Plumbing Installations | Dave Brown | Completed | High | 2023-11-26 | 2023-12-03 | 2023-12-03 | 100 | Concrete | Downtown Avenue | 23435.81 | 21620.56 | No issues
C004 | Warehouse D | T845 | Site Survey | Rachel Green | Blocked | Medium | 2023-02-25 | 2023-03-05 |  | 0 | Cement | Industrial Park | 28406.71 | 25490.29 | Not started
C002 | Shopping Complex B | T608 | Concrete Pouring | Mike Adams | Completed | High | 2024-07-28 | 2024-08-10 | 2024-08-10 | 100 | Cement | Market Street | 18398.3 | 41247.81 | No issues
C001 | Residential Building A | T670 | Steel Framework Setup | Emma White | Blocked | High | 2023-07-02 | 2023-07-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 19563.14 | 15431.28 | Not started
C003 | Office Tower C | T935 | Plumbing Installations | Grace Allen | Blocked | Medium | 2023-02-22 | 2023-03-01 |  | 0 | Cement | Downtown Avenue | 39334.3 | 27931.33 | Not started
C004 | Warehouse D | T107 | Steel Framework Setup | Emma White | Blocked | Low | 2024-02-26 | 2024-03-07 |  | 0 | Cement | Industrial Park | 35935.46 | 29048.12 | Not started
C003 | Office Tower C | T663 | Interior Painting | Grace Allen | In Progress | High | 2023-10-17 | 2023-10-24 |  | 50 | Steel Beams | Downtown Avenue | 18694.25 | 17492.49 | In progress
C002 | Shopping Complex B | T786 | Foundation Excavation | Grace Allen | Not Started | Medium | 2024-09-13 | 2024-10-13 |  | 0 | PVC Pipes | Market Street | 46543.07 | 0 | Not started
C003 | Office Tower C | T773 | Site Survey | Carlos Rivera | Not Started | Medium | 2024-05-11 | 2024-05-18 |  | 0 | Copper Wires | Downtown Avenue | 29119.33 | 0 | Not started
C004 | Warehouse D | T797 | Electrical Wiring | Dave Brown | Not Started | Medium | 2024-03-19 | 2024-04-08 |  | 0 | Cement | Industrial Park | 44538.87 | 0 | Not started
C002 | Shopping Complex B | T641 | Foundation Excavation | Rachel Green | Not Started | Medium | 2023-03-24 | 2023-04-18 |  | 0 | Concrete | Market Street | 5653.8 | 0 | Not started
C004 | Warehouse D | T585 | Plumbing Installations | Grace Allen | In Progress | Medium | 2023-12-26 | 2024-01-05 |  | 16 | Concrete | Industrial Park | 18773.4 | 19626.33 | In progress
C004 | Warehouse D | T222 | Site Survey | Dave Brown | Blocked | Medium | 2024-10-26 | 2024-11-09 |  | 0 | Concrete | Industrial Park | 47842.7 | 50959.15 | Not started
C003 | Office Tower C | T173 | Steel Framework Setup | Dave Brown | Blocked | Low | 2023-05-27 | 2023-06-09 |  | 0 | Concrete | Downtown Avenue | 13516.85 | 11369.92 | Not started
C003 | Office Tower C | T151 | Plumbing Installations | Dave Brown | Not Started | Medium | 2023-01-28 | 2023-02-14 |  | 0 | Copper Wires | Downtown Avenue | 15045.13 | 0 | Not started
C002 | Shopping Complex B | T544 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-01-12 | 2024-01-19 |  | 26 | Copper Wires | Market Street | 28633.94 | 46861.75 | In progress
C001 | Residential Building A | T804 | Interior Painting | Grace Allen | Completed | High | 2023-01-08 | 2023-01-16 | 2023-01-16 | 100 | Roofing Sheets | Plot 21, Riverside | 12857.46 | 12282.82 | No issues
C002 | Shopping Complex B | T656 | Foundation Excavation | Mike Adams | Blocked | High | 2023-09-05 | 2023-09-19 |  | 0 | Steel Beams | Market Street | 24253.9 | 53661.02 | Not started
C002 | Shopping Complex B | T739 | Concrete Pouring | Mike Adams | Completed | High | 2024-09-21 | 2024-10-03 | 2024-10-03 | 100 | Cement | Market Street | 33938.43 | 60915.36 | No issues
C003 | Office Tower C | T332 | Foundation Excavation | Mike Adams | Completed | High | 2023-02-10 | 2023-02-18 | 2023-02-18 | 100 | Steel Beams | Downtown Avenue | 22046.58 | 19132.35 | No issues
C002 | Shopping Complex B | T980 | Steel Framework Setup | Dave Brown | Completed | High | 2024-02-25 | 2024-03-10 | 2024-03-10 | 100 | Cement | Market Street | 21991.44 | 51493.34 | No issues
C001 | Residential Building A | T799 | Roofing | Grace Allen | Completed | High | 2024-10-14 | 2024-11-13 | 2024-11-13 | 100 | Cement | Plot 21, Riverside | 10805 | 10366.43 | No issues
C002 | Shopping Complex B | T372 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-07-05 | 2024-07-13 |  | 0 | PVC Pipes | Market Street | 40293.47 | 57280.04 | In progress
C002 | Shopping Complex B | T134 | Site Survey | John Miller | Not Started | High | 2023-03-26 | 2023-04-10 |  | 0 | Roofing Sheets | Market Street | 14254.93 | 0 | Not started
C002 | Shopping Complex B | T698 | Site Survey | Sarah Johnson | In Progress | Medium | 2023-05-05 | 2023-05-13 |  | 27 | Rebar | Market Street | 31826.49 | 55963.36 | In progress
C001 | Residential Building A | T769 | Foundation Excavation | Carlos Rivera | Blocked | Low | 2024-08-21 | 2024-08-31 |  | 0 | Concrete | Plot 21, Riverside | 37405.66 | 37171.32 | Not started
C002 | Shopping Complex B | T666 | Interior Painting | Rachel Green | In Progress | High | 2023-05-14 | 2023-06-12 |  | 4 | Cement | Market Street | 22309.2 | 40465.54 | In progress
C001 | Residential Building A | T915 | Concrete Pouring | John Miller | Completed | High | 2024-07-12 | 2024-07-30 | 2024-07-30 | 100 | Roofing Sheets | Plot 21, Riverside | 33484.04 | 37608.77 | No issues
C001 | Residential Building A | T109 | Foundation Excavation | Rachel Green | Blocked | Medium | 2023-04-22 | 2023-05-12 |  | 0 | PVC Pipes | Plot 21, Riverside | 26668.44 | 17598.04 | Not started
C004 | Warehouse D | T144 | Foundation Excavation | Rachel Green | Not Started | Low | 2023-06-22 | 2023-07-21 |  | 0 | Rebar | Industrial Park | 38823.61 | 0 | Not started
C001 | Residential Building A | T702 | Steel Framework Setup | John Miller | Blocked | Low | 2023-02-17 | 2023-03-01 |  | 0 | Cement | Plot 21, Riverside | 31157.9 | 34636.1 | Not started
C004 | Warehouse D | T915 | Roofing | John Miller | Completed | Low | 2023-08-21 | 2023-09-01 | 2023-09-01 | 100 | Paint | Industrial Park | 44966.19 | 29422.09 | No issues
C002 | Shopping Complex B | T943 | Roofing | Rachel Green | Not Started | Low | 2024-07-02 | 2024-07-15 |  | 0 | Copper Wires | Market Street | 40502.6 | 0 | Not started
C004 | Warehouse D | T907 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2024-06-14 | 2024-07-10 |  | 19 | Rebar | Industrial Park | 43154.4 | 46769.15 | In progress
C003 | Office Tower C | T377 | Site Survey | Grace Allen | Completed | High | 2024-09-09 | 2024-09-17 | 2024-09-17 | 100 | PVC Pipes | Downtown Avenue | 13511.16 | 15932.26 | No issues
C001 | Residential Building A | T564 | Foundation Excavation | John Miller | Not Started | Low | 2023-03-24 | 2023-04-09 |  | 0 | Concrete | Plot 21, Riverside | 29454.59 | 0 | Not started
C003 | Office Tower C | T564 | Interior Painting | Dave Brown | Blocked | Medium | 2024-03-19 | 2024-04-02 |  | 0 | Rebar | Downtown Avenue | 38305.67 | 35799.33 | Not started
C004 | Warehouse D | T615 | Site Survey | Mike Adams | Completed | Low | 2024-09-17 | 2024-09-24 | 2024-09-24 | 100 | Concrete | Industrial Park | 6999.85 | 7752.67 | No issues
C003 | Office Tower C | T378 | Foundation Excavation | John Miller | Completed | Low | 2024-01-19 | 2024-02-04 | 2024-02-04 | 100 | Paint | Downtown Avenue | 9895.47 | 9862.2 | No issues
C001 | Residential Building A | T694 | Electrical Wiring | Emma White | Completed | Medium | 2024-09-09 | 2024-09-30 | 2024-09-30 | 100 | Rebar | Plot 21, Riverside | 28088.86 | 29355.38 | No issues
C002 | Shopping Complex B | T110 | Steel Framework Setup | Rachel Green | In Progress | Medium | 2024-12-25 | 2025-01-19 |  | 37 | Copper Wires | Market Street | 21024.19 | 48934.27 | In progress
C003 | Office Tower C | T193 | Electrical Wiring | Emma White | Completed | Low | 2023-03-07 | 2023-03-22 | 2023-03-22 | 100 | Cement | Downtown Avenue | 5537.01 | 5386.32 | No issues
C003 | Office Tower C | T327 | Roofing | Carlos Rivera | In Progress | Medium | 2024-08-14 | 2024-09-09 |  | 77 | Cement | Downtown Avenue | 35318 | 21359.88 | In progress
C003 | Office Tower C | T580 | Plumbing Installations | Grace Allen | In Progress | Medium | 2024-05-01 | 2024-05-19 |  | 3 | Rebar | Downtown Avenue | 23130.94 | 21002.63 | In progress
C004 | Warehouse D | T573 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-03-18 | 2023-04-11 |  | 7 | Roofing Sheets | Industrial Park | 48871.52 | 52654.29 | In progress
C001 | Residential Building A | T860 | Foundation Excavation | Dave Brown | Completed | Low | 2024-02-14 | 2024-02-24 | 2024-02-24 | 100 | Roofing Sheets | Plot 21, Riverside | 26294.21 | 23786.9 | No issues
C001 | Residential Building A | T235 | Steel Framework Setup | Rachel Green | Completed | Low | 2023-03-04 | 2023-04-03 | 2023-04-03 | 100 | PVC Pipes | Plot 21, Riverside | 45216.68 | 49462.8 | No issues
C001 | Residential Building A | T125 | Interior Painting | Carlos Rivera | In Progress | Medium | 2023-07-27 | 2023-08-23 |  | 48 | Rebar | Plot 21, Riverside | 37036.34 | 29968.33 | In progress
C003 | Office Tower C | T878 | Plumbing Installations | Grace Allen | In Progress | Medium | 2024-06-03 | 2024-06-15 |  | 26 | Cement | Downtown Avenue | 43841.98 | 45793.23 | In progress
C002 | Shopping Complex B | T961 | Interior Painting | Mike Adams | Not Started | Low | 2024-03-27 | 2024-04-17 |  | 0 | Copper Wires | Market Street | 16252.82 | 0 | Not started
C003 | Office Tower C | T200 | Concrete Pouring | Emma White | In Progress | Medium | 2023-06-22 | 2023-07-06 |  | 76 | Roofing Sheets | Downtown Avenue | 27405.95 | 25015.8 | In progress
C004 | Warehouse D | T919 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2023-03-05 | 2023-03-27 |  | 0 | Rebar | Industrial Park | 42575.88 | 31046.14 | Not started
C004 | Warehouse D | T393 | Plumbing Installations | Grace Allen | Completed | Medium | 2024-09-20 | 2024-10-05 | 2024-10-05 | 100 | Concrete | Industrial Park | 46716.97 | 53247.43 | No issues
C003 | Office Tower C | T870 | Steel Framework Setup | John Miller | In Progress | Low | 2023-07-23 | 2023-08-19 |  | 34 | Rebar | Downtown Avenue | 20380.87 | 18830.95 | In progress
C001 | Residential Building A | T420 | Site Survey | Rachel Green | Not Started | Medium | 2023-03-16 | 2023-04-11 |  | 0 | Copper Wires | Plot 21, Riverside | 6872.28 | 0 | Not started
C003 | Office Tower C | T190 | Roofing | Sarah Johnson | Completed | Low | 2023-01-23 | 2023-02-04 | 2023-02-04 | 100 | Roofing Sheets | Downtown Avenue | 43248.92 | 48953.92 | No issues
C002 | Shopping Complex B | T667 | Plumbing Installations | Grace Allen | In Progress | High | 2023-09-22 | 2023-10-05 |  | 22 | PVC Pipes | Market Street | 23535.93 | 53304.94 | In progress
C004 | Warehouse D | T919 | Steel Framework Setup | John Miller | In Progress | Low | 2024-10-10 | 2024-10-24 |  | 69 | Cement | Industrial Park | 16087.57 | 19111.94 | In progress
C003 | Office Tower C | T416 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2023-01-23 | 2023-02-16 |  | 85 | Copper Wires | Downtown Avenue | 28618.37 | 32797.66 | In progress
C002 | Shopping Complex B | T895 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-07-11 | 2023-08-06 |  | 14 | Roofing Sheets | Market Street | 18801.07 | 40383.19 | In progress
C001 | Residential Building A | T333 | Electrical Wiring | John Miller | Blocked | High | 2024-04-11 | 2024-05-11 |  | 0 | Roofing Sheets | Plot 21, Riverside | 29414.18 | 32895.54 | Not started
C001 | Residential Building A | T465 | Foundation Excavation | Carlos Rivera | Completed | High | 2023-02-03 | 2023-02-24 | 2023-02-24 | 100 | PVC Pipes | Plot 21, Riverside | 13608.39 | 11425.12 | No issues
C003 | Office Tower C | T990 | Foundation Excavation | John Miller | Blocked | High | 2024-07-12 | 2024-08-04 |  | 0 | Steel Beams | Downtown Avenue | 10544.48 | 7342.41 | Not started
C003 | Office Tower C | T989 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2024-12-06 | 2024-12-30 |  | 0 | Roofing Sheets | Downtown Avenue | 30951.84 | 0 | Not started
C002 | Shopping Complex B | T203 | Concrete Pouring | John Miller | Completed | High | 2023-05-05 | 2023-05-21 | 2023-05-21 | 100 | Rebar | Market Street | 9274.05 | 35298.77 | No issues
C004 | Warehouse D | T559 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-04-12 | 2023-04-25 |  | 0 | Paint | Industrial Park | 20056.56 | 0 | Not started
C003 | Office Tower C | T645 | Roofing | Grace Allen | Not Started | Medium | 2023-04-03 | 2023-05-03 |  | 0 | Steel Beams | Downtown Avenue | 17734.11 | 0 | Not started
C001 | Residential Building A | T826 | Foundation Excavation | Sarah Johnson | Completed | Low | 2024-01-26 | 2024-02-12 | 2024-02-12 | 100 | Copper Wires | Plot 21, Riverside | 39767.04 | 40989.27 | No issues
C004 | Warehouse D | T532 | Electrical Wiring | Dave Brown | Not Started | Medium | 2024-11-24 | 2024-12-20 |  | 0 | Roofing Sheets | Industrial Park | 49664.1 | 0 | Not started
C001 | Residential Building A | T172 | Interior Painting | Carlos Rivera | Not Started | High | 2023-04-09 | 2023-04-21 |  | 0 | Roofing Sheets | Plot 21, Riverside | 41166.7 | 0 | Not started
C004 | Warehouse D | T516 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-11-06 | 2023-11-18 | 2023-11-18 | 100 | Roofing Sheets | Industrial Park | 13671.08 | 14808.38 | No issues
C001 | Residential Building A | T777 | Site Survey | Dave Brown | Not Started | Medium | 2024-02-27 | 2024-03-05 |  | 0 | Roofing Sheets | Plot 21, Riverside | 43973.39 | 0 | Not started
C001 | Residential Building A | T221 | Foundation Excavation | Grace Allen | In Progress | Medium | 2023-08-10 | 2023-09-04 |  | 7 | Rebar | Plot 21, Riverside | 11375.94 | 12066 | In progress
C003 | Office Tower C | T201 | Electrical Wiring | Rachel Green | In Progress | Medium | 2023-09-20 | 2023-09-27 |  | 8 | Concrete | Downtown Avenue | 24525.9 | 25406.5 | In progress
C003 | Office Tower C | T470 | Concrete Pouring | Rachel Green | Blocked | Medium | 2024-09-09 | 2024-10-01 |  | 0 | Rebar | Downtown Avenue | 39832.51 | 31677.41 | Not started
C003 | Office Tower C | T783 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2024-06-23 | 2024-07-02 |  | 0 | Copper Wires | Downtown Avenue | 38116.68 | 0 | Not started
C002 | Shopping Complex B | T805 | Foundation Excavation | John Miller | Blocked | Medium | 2023-11-25 | 2023-12-18 |  | 0 | Cement | Market Street | 36066.62 | 66441.84 | Not started
C002 | Shopping Complex B | T202 | Roofing | Mike Adams | In Progress | Low | 2023-09-27 | 2023-10-18 |  | 56 | Steel Beams | Market Street | 33347.4 | 60867.81 | In progress
C003 | Office Tower C | T995 | Foundation Excavation | Rachel Green | Completed | High | 2023-11-21 | 2023-12-05 | 2023-12-05 | 100 | Copper Wires | Downtown Avenue | 22284.43 | 16550.21 | No issues
C002 | Shopping Complex B | T488 | Plumbing Installations | Grace Allen | Not Started | Medium | 2024-12-13 | 2025-01-08 |  | 0 | Copper Wires | Market Street | 26925.56 | 0 | Not started
C002 | Shopping Complex B | T313 | Interior Painting | Grace Allen | Completed | Low | 2023-12-21 | 2024-01-08 | 2024-01-08 | 100 | Steel Beams | Market Street | 27150.9 | 41914.18 | No issues
C003 | Office Tower C | T357 | Roofing | Dave Brown | In Progress | High | 2023-01-27 | 2023-02-10 |  | 2 | Copper Wires | Downtown Avenue | 28352.32 | 33355.93 | In progress
C003 | Office Tower C | T657 | Concrete Pouring | Grace Allen | Completed | Low | 2024-07-20 | 2024-08-19 | 2024-08-19 | 100 | Concrete | Downtown Avenue | 15171.4 | 17341.48 | No issues
C002 | Shopping Complex B | T600 | Plumbing Installations | Carlos Rivera | Completed | High | 2024-02-16 | 2024-03-05 | 2024-03-05 | 100 | Paint | Market Street | 30302.7 | 44251.49 | No issues
C004 | Warehouse D | T392 | Interior Painting | Sarah Johnson | Blocked | High | 2024-08-14 | 2024-09-07 |  | 0 | Copper Wires | Industrial Park | 6185.46 | 4560.03 | Not started
C004 | Warehouse D | T340 | Concrete Pouring | Dave Brown | Not Started | High | 2023-02-03 | 2023-02-24 |  | 0 | Steel Beams | Industrial Park | 13783.73 | 0 | Not started
C003 | Office Tower C | T808 | Steel Framework Setup | John Miller | Not Started | High | 2023-06-22 | 2023-07-16 |  | 0 | Rebar | Downtown Avenue | 14091.19 | 0 | Not started
C002 | Shopping Complex B | T828 | Roofing | Grace Allen | Completed | High | 2024-11-07 | 2024-11-24 | 2024-11-24 | 100 | PVC Pipes | Market Street | 33750.01 | 45813.4 | No issues
C001 | Residential Building A | T114 | Steel Framework Setup | Rachel Green | Not Started | Low | 2024-06-01 | 2024-06-29 |  | 0 | PVC Pipes | Plot 21, Riverside | 23686.47 | 0 | Not started
C001 | Residential Building A | T285 | Steel Framework Setup | John Miller | Not Started | Medium | 2023-01-24 | 2023-02-11 |  | 0 | Copper Wires | Plot 21, Riverside | 35190.92 | 0 | Not started
C003 | Office Tower C | T245 | Interior Painting | Carlos Rivera | In Progress | Low | 2023-11-21 | 2023-12-13 |  | 16 | Paint | Downtown Avenue | 29495.12 | 24326.16 | In progress
C003 | Office Tower C | T475 | Interior Painting | Mike Adams | Blocked | Medium | 2024-05-18 | 2024-06-10 |  | 0 | Rebar | Downtown Avenue | 15049.61 | 10967.56 | Not started
C001 | Residential Building A | T713 | Interior Painting | Grace Allen | Not Started | Medium | 2023-11-02 | 2023-11-14 |  | 0 | PVC Pipes | Plot 21, Riverside | 49644.92 | 0 | Not started
C004 | Warehouse D | T996 | Electrical Wiring | Rachel Green | Blocked | Medium | 2023-07-15 | 2023-07-23 |  | 0 | PVC Pipes | Industrial Park | 28627.6 | 29969.37 | Not started
C001 | Residential Building A | T664 | Electrical Wiring | Emma White | Blocked | Medium | 2023-10-26 | 2023-11-24 |  | 0 | Concrete | Plot 21, Riverside | 44448.58 | 40637.75 | Not started
C001 | Residential Building A | T691 | Foundation Excavation | Emma White | In Progress | High | 2024-05-12 | 2024-05-23 |  | 20 | Concrete | Plot 21, Riverside | 47936.75 | 44486.61 | In progress
C001 | Residential Building A | T450 | Site Survey | Emma White | In Progress | Medium | 2024-05-21 | 2024-06-14 |  | 89 | Paint | Plot 21, Riverside | 37008.73 | 39251.76 | In progress
C002 | Shopping Complex B | T618 | Electrical Wiring | Carlos Rivera | In Progress | High | 2024-03-15 | 2024-03-31 |  | 31 | Copper Wires | Market Street | 30303.47 | 49447.02 | In progress
C002 | Shopping Complex B | T255 | Plumbing Installations | Emma White | Blocked | Low | 2024-07-06 | 2024-07-15 |  | 0 | Roofing Sheets | Market Street | 5491.78 | 30117.5 | Not started
C003 | Office Tower C | T138 | Foundation Excavation | Mike Adams | Not Started | High | 2024-10-18 | 2024-11-17 |  | 0 | Copper Wires | Downtown Avenue | 18237.02 | 0 | Not started
C002 | Shopping Complex B | T841 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2024-03-05 | 2024-03-14 |  | 0 | Roofing Sheets | Market Street | 40288.03 | 66473.39 | Not started
C002 | Shopping Complex B | T111 | Roofing | Sarah Johnson | In Progress | High | 2023-12-02 | 2023-12-18 |  | 79 | Cement | Market Street | 30310.32 | 49567.67 | In progress
C003 | Office Tower C | T430 | Concrete Pouring | Dave Brown | Not Started | High | 2024-10-20 | 2024-11-03 |  | 0 | Concrete | Downtown Avenue | 9687.27 | 0 | Not started
C004 | Warehouse D | T385 | Concrete Pouring | Dave Brown | Completed | Medium | 2024-09-26 | 2024-10-19 | 2024-10-19 | 100 | Paint | Industrial Park | 44974.11 | 27447.55 | No issues
C001 | Residential Building A | T888 | Electrical Wiring | Mike Adams | Not Started | Low | 2023-01-22 | 2023-02-19 |  | 0 | Cement | Plot 21, Riverside | 27109.9 | 0 | Not started
C003 | Office Tower C | T354 | Foundation Excavation | Emma White | In Progress | High | 2024-02-11 | 2024-03-06 |  | 14 | Paint | Downtown Avenue | 14954.94 | 10202.71 | In progress
C004 | Warehouse D | T390 | Roofing | Sarah Johnson | In Progress | Low | 2024-07-05 | 2024-07-16 |  | 95 | Paint | Industrial Park | 14320.21 | 13412.51 | In progress
C002 | Shopping Complex B | T910 | Interior Painting | Emma White | Blocked | Medium | 2023-10-25 | 2023-11-05 |  | 0 | Cement | Market Street | 49333.06 | 57454.9 | Not started
C004 | Warehouse D | T678 | Electrical Wiring | Rachel Green | Blocked | High | 2024-11-22 | 2024-12-18 |  | 0 | Cement | Industrial Park | 23548.3 | 21282.31 | Not started
C002 | Shopping Complex B | T758 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2023-09-02 | 2023-09-13 | 2023-09-13 | 100 | PVC Pipes | Market Street | 10344.14 | 31877.41 | No issues
C004 | Warehouse D | T592 | Concrete Pouring | Mike Adams | Blocked | Medium | 2024-12-26 | 2025-01-03 |  | 0 | PVC Pipes | Industrial Park | 26183.59 | 28406.17 | Not started
C002 | Shopping Complex B | T446 | Electrical Wiring | Carlos Rivera | Not Started | High | 2024-01-11 | 2024-01-24 |  | 0 | Cement | Market Street | 10055.01 | 0 | Not started
C001 | Residential Building A | T682 | Site Survey | Dave Brown | Not Started | High | 2023-01-23 | 2023-02-19 |  | 0 | PVC Pipes | Plot 21, Riverside | 36835.9 | 0 | Not started
C002 | Shopping Complex B | T248 | Concrete Pouring | John Miller | Blocked | Low | 2023-02-22 | 2023-03-03 |  | 0 | Cement | Market Street | 41940.23 | 59613.21 | Not started
C002 | Shopping Complex B | T952 | Interior Painting | Dave Brown | Blocked | High | 2023-02-24 | 2023-03-21 |  | 0 | Cement | Market Street | 8340.82 | 33480.02 | Not started
C001 | Residential Building A | T968 | Site Survey | Mike Adams | In Progress | High | 2023-09-14 | 2023-09-30 |  | 21 | Roofing Sheets | Plot 21, Riverside | 33723.17 | 29157.68 | In progress
C001 | Residential Building A | T388 | Electrical Wiring | Mike Adams | Completed | High | 2024-06-28 | 2024-07-18 | 2024-07-18 | 100 | Cement | Plot 21, Riverside | 11614.88 | 10458.29 | No issues
C001 | Residential Building A | T819 | Plumbing Installations | John Miller | Blocked | High | 2024-07-09 | 2024-07-16 |  | 0 | Rebar | Plot 21, Riverside | 25966.55 | 28520.61 | Not started
C002 | Shopping Complex B | T504 | Interior Painting | Rachel Green | Not Started | Medium | 2024-01-14 | 2024-02-09 |  | 0 | PVC Pipes | Market Street | 6953.38 | 0 | Not started
C003 | Office Tower C | T570 | Interior Painting | Emma White | Not Started | Low | 2023-06-21 | 2023-07-21 |  | 0 | PVC Pipes | Downtown Avenue | 37053.31 | 0 | Not started
C003 | Office Tower C | T533 | Interior Painting | John Miller | Not Started | High | 2024-02-04 | 2024-02-17 |  | 0 | Copper Wires | Downtown Avenue | 24459.78 | 0 | Not started
C002 | Shopping Complex B | T469 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-06-26 | 2023-07-03 |  | 0 | Cement | Market Street | 25180.59 | 0 | Not started
C004 | Warehouse D | T508 | Roofing | Dave Brown | Blocked | High | 2024-09-22 | 2024-10-06 |  | 0 | Rebar | Industrial Park | 28429.86 | 30918.03 | Not started
C004 | Warehouse D | T506 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2023-03-04 | 2023-03-13 |  | 0 | Steel Beams | Industrial Park | 20352.85 | 0 | Not started
C001 | Residential Building A | T560 | Roofing | Carlos Rivera | Not Started | High | 2023-09-10 | 2023-10-05 |  | 0 | Cement | Plot 21, Riverside | 32256.73 | 0 | Not started
C001 | Residential Building A | T803 | Site Survey | Emma White | Not Started | Low | 2024-04-13 | 2024-04-27 |  | 0 | PVC Pipes | Plot 21, Riverside | 25034.68 | 0 | Not started
C002 | Shopping Complex B | T834 | Concrete Pouring | Emma White | Not Started | Medium | 2023-03-25 | 2023-04-24 |  | 0 | Cement | Market Street | 22476.02 | 0 | Not started
C001 | Residential Building A | T520 | Site Survey | Mike Adams | In Progress | High | 2023-10-28 | 2023-11-05 |  | 81 | Roofing Sheets | Plot 21, Riverside | 9837.15 | 7593.7 | In progress
C003 | Office Tower C | T925 | Foundation Excavation | Rachel Green | Blocked | Medium | 2024-07-04 | 2024-07-26 |  | 0 | Roofing Sheets | Downtown Avenue | 29172.52 | 25591.08 | Not started
C002 | Shopping Complex B | T528 | Plumbing Installations | Rachel Green | In Progress | High | 2024-03-23 | 2024-04-05 |  | 12 | Rebar | Market Street | 34524.08 | 62122.92 | In progress
C003 | Office Tower C | T966 | Plumbing Installations | Emma White | Not Started | Medium | 2023-02-06 | 2023-02-21 |  | 0 | Cement | Downtown Avenue | 5156.13 | 0 | Not started
C004 | Warehouse D | T823 | Electrical Wiring | Dave Brown | Not Started | High | 2023-01-06 | 2023-02-01 |  | 0 | Copper Wires | Industrial Park | 27212.57 | 0 | Not started
C004 | Warehouse D | T564 | Foundation Excavation | John Miller | Completed | High | 2023-11-03 | 2023-12-03 | 2023-12-03 | 100 | Steel Beams | Industrial Park | 22791.9 | 26929.86 | No issues
C001 | Residential Building A | T184 | Site Survey | Grace Allen | Not Started | High | 2024-04-08 | 2024-04-29 |  | 0 | Concrete | Plot 21, Riverside | 5051.8 | 0 | Not started
C003 | Office Tower C | T337 | Foundation Excavation | Grace Allen | Completed | Low | 2023-04-12 | 2023-04-21 | 2023-04-21 | 100 | Copper Wires | Downtown Avenue | 7943.84 | 8178.64 | No issues
C002 | Shopping Complex B | T390 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-07-14 | 2024-07-30 |  | 47 | Steel Beams | Market Street | 34856.6 | 55088.33 | In progress
C003 | Office Tower C | T134 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-08-27 | 2023-09-10 |  | 22 | Paint | Downtown Avenue | 27611.43 | 30668.27 | In progress
C001 | Residential Building A | T921 | Steel Framework Setup | Grace Allen | Not Started | Low | 2023-02-10 | 2023-02-21 |  | 0 | Copper Wires | Plot 21, Riverside | 33457.49 | 0 | Not started
C004 | Warehouse D | T130 | Concrete Pouring | Grace Allen | Completed | Medium | 2024-07-18 | 2024-08-11 | 2024-08-11 | 100 | Copper Wires | Industrial Park | 45535.89 | 42136.96 | No issues
C002 | Shopping Complex B | T391 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-04-28 | 2024-05-17 |  | 95 | PVC Pipes | Market Street | 10817.15 | 32102.26 | In progress
C003 | Office Tower C | T465 | Interior Painting | Mike Adams | In Progress | Low | 2023-07-07 | 2023-07-25 |  | 67 | PVC Pipes | Downtown Avenue | 19751.88 | 17869.01 | In progress
C001 | Residential Building A | T250 | Steel Framework Setup | John Miller | Blocked | High | 2024-02-20 | 2024-03-02 |  | 0 | Concrete | Plot 21, Riverside | 19096.31 | 22393.37 | Not started
C001 | Residential Building A | T699 | Foundation Excavation | Dave Brown | In Progress | Low | 2023-03-24 | 2023-04-08 |  | 42 | Rebar | Plot 21, Riverside | 18430.61 | 21536.05 | In progress
C003 | Office Tower C | T100 | Roofing | Dave Brown | In Progress | Low | 2024-04-16 | 2024-04-30 |  | 48 | Steel Beams | Downtown Avenue | 9419.6 | 6822.54 | In progress
C001 | Residential Building A | T645 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2023-03-03 | 2023-03-25 |  | 5 | Steel Beams | Plot 21, Riverside | 8544.33 | 8170.84 | In progress
C001 | Residential Building A | T302 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2023-11-22 | 2023-12-15 |  | 0 | Rebar | Plot 21, Riverside | 17191.89 | 0 | Not started
C003 | Office Tower C | T994 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-12-12 | 2023-12-29 |  | 27 | Concrete | Downtown Avenue | 20034.99 | 16898.6 | In progress
C003 | Office Tower C | T656 | Site Survey | Rachel Green | Not Started | Medium | 2023-03-26 | 2023-04-10 |  | 0 | Paint | Downtown Avenue | 31642.07 | 0 | Not started
C004 | Warehouse D | T199 | Steel Framework Setup | Grace Allen | Blocked | Low | 2023-03-16 | 2023-03-31 |  | 0 | Rebar | Industrial Park | 15025.95 | 15697.57 | Not started
C003 | Office Tower C | T708 | Site Survey | John Miller | Completed | Low | 2024-06-02 | 2024-06-30 | 2024-06-30 | 100 | Concrete | Downtown Avenue | 39979.83 | 43847.57 | No issues
C004 | Warehouse D | T794 | Site Survey | Sarah Johnson | Blocked | High | 2023-02-28 | 2023-03-08 |  | 0 | Concrete | Industrial Park | 28023.51 | 31484.98 | Not started
C001 | Residential Building A | T282 | Electrical Wiring | Emma White | Not Started | High | 2024-02-16 | 2024-03-09 |  | 0 | Copper Wires | Plot 21, Riverside | 29253.94 | 0 | Not started
C001 | Residential Building A | T920 | Concrete Pouring | Carlos Rivera | Completed | High | 2023-06-03 | 2023-07-01 | 2023-07-01 | 100 | Cement | Plot 21, Riverside | 38090.14 | 44928.81 | No issues
C003 | Office Tower C | T180 | Electrical Wiring | Rachel Green | In Progress | Medium | 2023-11-27 | 2023-12-21 |  | 24 | PVC Pipes | Downtown Avenue | 13049.72 | 13493.49 | In progress
C002 | Shopping Complex B | T871 | Interior Painting | Grace Allen | Blocked | High | 2024-02-22 | 2024-03-23 |  | 0 | Paint | Market Street | 33864.9 | 57306.36 | Not started
C001 | Residential Building A | T770 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2024-03-08 | 2024-03-29 |  | 0 | Rebar | Plot 21, Riverside | 14803.28 | 0 | Not started
C003 | Office Tower C | T269 | Site Survey | Mike Adams | Completed | Medium | 2023-04-04 | 2023-04-22 | 2023-04-22 | 100 | Rebar | Downtown Avenue | 35689.57 | 40391.64 | No issues
C001 | Residential Building A | T544 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-01-27 | 2024-02-20 |  | 0 | Roofing Sheets | Plot 21, Riverside | 19175.85 | 0 | Not started
C003 | Office Tower C | T180 | Electrical Wiring | Rachel Green | Not Started | Low | 2024-07-25 | 2024-08-15 |  | 0 | Copper Wires | Downtown Avenue | 25146.73 | 0 | Not started
C002 | Shopping Complex B | T841 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2024-10-23 | 2024-10-31 |  | 0 | Roofing Sheets | Market Street | 6894.82 | 29713.05 | Not started
C004 | Warehouse D | T490 | Site Survey | Dave Brown | Blocked | Medium | 2024-02-12 | 2024-02-24 |  | 0 | Concrete | Industrial Park | 37819.79 | 43075.62 | Not started
C002 | Shopping Complex B | T965 | Site Survey | Carlos Rivera | In Progress | High | 2023-07-21 | 2023-08-17 |  | 75 | Concrete | Market Street | 28679.07 | 58995.24 | In progress
C001 | Residential Building A | T657 | Foundation Excavation | Grace Allen | Completed | Low | 2023-06-21 | 2023-07-15 | 2023-07-15 | 100 | Cement | Plot 21, Riverside | 40610.65 | 27562.72 | No issues
C002 | Shopping Complex B | T142 | Electrical Wiring | Emma White | Blocked | Medium | 2023-06-14 | 2023-06-29 |  | 0 | Concrete | Market Street | 25912.69 | 55717.76 | Not started
C003 | Office Tower C | T659 | Interior Painting | Emma White | Blocked | Low | 2024-12-19 | 2025-01-10 |  | 0 | Rebar | Downtown Avenue | 18448.82 | 17343.37 | Not started
C002 | Shopping Complex B | T487 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2023-10-07 | 2023-10-20 |  | 0 | Copper Wires | Market Street | 20539.36 | 39745.88 | Not started
C003 | Office Tower C | T535 | Roofing | Sarah Johnson | In Progress | High | 2023-05-09 | 2023-05-20 |  | 19 | Steel Beams | Downtown Avenue | 21256.58 | 17706.71 | In progress
C001 | Residential Building A | T122 | Plumbing Installations | Dave Brown | Not Started | Medium | 2024-05-02 | 2024-05-21 |  | 0 | PVC Pipes | Plot 21, Riverside | 11640.19 | 0 | Not started
C002 | Shopping Complex B | T930 | Interior Painting | Sarah Johnson | In Progress | Medium | 2023-10-23 | 2023-11-07 |  | 18 | Steel Beams | Market Street | 39425.88 | 57774.54 | In progress
C003 | Office Tower C | T596 | Foundation Excavation | John Miller | In Progress | Low | 2023-02-13 | 2023-02-20 |  | 43 | Copper Wires | Downtown Avenue | 44056.14 | 43071.78 | In progress
C003 | Office Tower C | T886 | Electrical Wiring | Emma White | Blocked | Medium | 2023-03-11 | 2023-03-20 |  | 0 | Steel Beams | Downtown Avenue | 7017.46 | 4890.18 | Not started
C002 | Shopping Complex B | T787 | Site Survey | Carlos Rivera | Blocked | High | 2024-03-15 | 2024-03-31 |  | 0 | Rebar | Market Street | 39994.43 | 62623.73 | Not started
C002 | Shopping Complex B | T179 | Foundation Excavation | Emma White | Completed | High | 2023-04-17 | 2023-05-14 | 2023-05-14 | 100 | Copper Wires | Market Street | 5756.53 | 30594.82 | No issues
C002 | Shopping Complex B | T591 | Site Survey | Sarah Johnson | Completed | Low | 2023-03-22 | 2023-04-06 | 2023-04-06 | 100 | Concrete | Market Street | 36509.99 | 64267.46 | No issues
C002 | Shopping Complex B | T792 | Roofing | John Miller | In Progress | High | 2023-03-11 | 2023-04-06 |  | 14 | Steel Beams | Market Street | 15087.05 | 38967.31 | In progress
C001 | Residential Building A | T413 | Site Survey | Carlos Rivera | Blocked | Low | 2024-10-11 | 2024-10-23 |  | 0 | Copper Wires | Plot 21, Riverside | 25214.12 | 19464 | Not started
C001 | Residential Building A | T953 | Plumbing Installations | Rachel Green | Blocked | Low | 2024-09-27 | 2024-10-06 |  | 0 | Copper Wires | Plot 21, Riverside | 6842.8 | 6583.29 | Not started
C004 | Warehouse D | T960 | Electrical Wiring | Sarah Johnson | Blocked | High | 2024-01-14 | 2024-01-31 |  | 0 | Steel Beams | Industrial Park | 19753.76 | 21182.97 | Not started
C004 | Warehouse D | T143 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-09-11 | 2024-10-01 |  | 85 | Cement | Industrial Park | 46971.12 | 29679.36 | In progress
C001 | Residential Building A | T350 | Plumbing Installations | Rachel Green | Not Started | Low | 2023-01-02 | 2023-01-23 |  | 0 | Copper Wires | Plot 21, Riverside | 30738.45 | 0 | Not started
C001 | Residential Building A | T699 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-07-25 | 2024-08-18 |  | 57 | PVC Pipes | Plot 21, Riverside | 32844.31 | 22614.64 | In progress
C001 | Residential Building A | T270 | Steel Framework Setup | Mike Adams | Completed | Low | 2024-04-08 | 2024-04-26 | 2024-04-26 | 100 | Concrete | Plot 21, Riverside | 5328.33 | 4828.16 | No issues
C003 | Office Tower C | T342 | Steel Framework Setup | Sarah Johnson | Completed | High | 2024-08-18 | 2024-09-04 | 2024-09-04 | 100 | Rebar | Downtown Avenue | 5081.61 | 5327.23 | No issues
C003 | Office Tower C | T285 | Plumbing Installations | Grace Allen | Not Started | Low | 2024-08-02 | 2024-08-22 |  | 0 | Rebar | Downtown Avenue | 37079.9 | 0 | Not started
C003 | Office Tower C | T677 | Concrete Pouring | Rachel Green | Completed | Low | 2024-02-18 | 2024-03-09 | 2024-03-09 | 100 | Roofing Sheets | Downtown Avenue | 34621.5 | 36669.47 | No issues
C003 | Office Tower C | T646 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2024-04-01 | 2024-04-11 |  | 33 | Concrete | Downtown Avenue | 38945.21 | 40632.56 | In progress
C001 | Residential Building A | T771 | Roofing | Dave Brown | Not Started | Medium | 2023-01-10 | 2023-02-03 |  | 0 | Paint | Plot 21, Riverside | 34052.81 | 0 | Not started
C002 | Shopping Complex B | T356 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-10-14 | 2023-10-21 |  | 0 | Steel Beams | Market Street | 47842.01 | 80996.16 | Not started
C002 | Shopping Complex B | T556 | Site Survey | John Miller | Not Started | Medium | 2023-11-03 | 2023-11-26 |  | 0 | Steel Beams | Market Street | 38659.06 | 0 | Not started
C003 | Office Tower C | T605 | Plumbing Installations | Grace Allen | Completed | High | 2023-10-03 | 2023-11-01 | 2023-11-01 | 100 | Cement | Downtown Avenue | 47913.87 | 29695.98 | No issues
C001 | Residential Building A | T849 | Interior Painting | Emma White | Completed | Medium | 2024-11-27 | 2024-12-14 | 2024-12-14 | 100 | Paint | Plot 21, Riverside | 47029.73 | 51967.95 | No issues
C002 | Shopping Complex B | T909 | Foundation Excavation | Rachel Green | Completed | Medium | 2023-12-12 | 2023-12-23 | 2023-12-23 | 100 | Cement | Market Street | 29827.75 | 50241.19 | No issues
C004 | Warehouse D | T585 | Plumbing Installations | Rachel Green | Not Started | Low | 2024-02-10 | 2024-03-08 |  | 0 | Rebar | Industrial Park | 12878.08 | 0 | Not started
C004 | Warehouse D | T129 | Concrete Pouring | Rachel Green | Blocked | Medium | 2024-12-19 | 2024-12-28 |  | 0 | Steel Beams | Industrial Park | 22384 | 20467.36 | Not started
C002 | Shopping Complex B | T746 | Steel Framework Setup | Carlos Rivera | Completed | High | 2024-04-24 | 2024-05-09 | 2024-05-09 | 100 | Copper Wires | Market Street | 12352.48 | 33404.67 | No issues
C004 | Warehouse D | T932 | Steel Framework Setup | Mike Adams | Blocked | Low | 2024-07-11 | 2024-07-22 |  | 0 | Concrete | Industrial Park | 37501.41 | 35256.82 | Not started
C002 | Shopping Complex B | T396 | Electrical Wiring | Grace Allen | Completed | High | 2023-08-21 | 2023-08-30 | 2023-08-30 | 100 | Steel Beams | Market Street | 45995.99 | 80515.3 | No issues
C004 | Warehouse D | T719 | Concrete Pouring | Emma White | Completed | Low | 2023-02-11 | 2023-03-04 | 2023-03-04 | 100 | Roofing Sheets | Industrial Park | 20120.94 | 23020.51 | No issues
C004 | Warehouse D | T351 | Interior Painting | Mike Adams | In Progress | Low | 2023-04-08 | 2023-04-27 |  | 59 | Concrete | Industrial Park | 36631.93 | 41767.9 | In progress
C004 | Warehouse D | T167 | Interior Painting | Dave Brown | In Progress | Medium | 2024-06-02 | 2024-06-10 |  | 28 | Roofing Sheets | Industrial Park | 20610.71 | 15802.89 | In progress
C003 | Office Tower C | T870 | Site Survey | Grace Allen | Not Started | Low | 2023-08-03 | 2023-08-16 |  | 0 | PVC Pipes | Downtown Avenue | 47162.66 | 0 | Not started
C001 | Residential Building A | T232 | Concrete Pouring | Emma White | Blocked | Low | 2023-12-10 | 2024-01-07 |  | 0 | Rebar | Plot 21, Riverside | 19203.35 | 16780.07 | Not started
C004 | Warehouse D | T368 | Site Survey | Rachel Green | Not Started | Low | 2023-08-01 | 2023-08-12 |  | 0 | Rebar | Industrial Park | 40626.98 | 0 | Not started
C003 | Office Tower C | T834 | Steel Framework Setup | Grace Allen | Blocked | Low | 2023-10-17 | 2023-11-16 |  | 0 | Rebar | Downtown Avenue | 23525.08 | 21117.04 | Not started
C004 | Warehouse D | T502 | Interior Painting | Rachel Green | In Progress | High | 2023-10-16 | 2023-10-31 |  | 69 | Concrete | Industrial Park | 13703.92 | 8676.02 | In progress
C004 | Warehouse D | T220 | Interior Painting | Dave Brown | Blocked | Low | 2024-02-14 | 2024-03-10 |  | 0 | Rebar | Industrial Park | 13649.01 | 13119.61 | Not started
C004 | Warehouse D | T103 | Interior Painting | Rachel Green | Not Started | Low | 2024-07-24 | 2024-08-18 |  | 0 | Concrete | Industrial Park | 45651.32 | 0 | Not started
C001 | Residential Building A | T741 | Concrete Pouring | Emma White | Not Started | High | 2023-06-11 | 2023-06-29 |  | 0 | Rebar | Plot 21, Riverside | 9196.8 | 0 | Not started
C002 | Shopping Complex B | T588 | Interior Painting | Dave Brown | Blocked | Medium | 2023-10-06 | 2023-10-30 |  | 0 | Concrete | Market Street | 39869.29 | 54662.23 | Not started
C004 | Warehouse D | T598 | Electrical Wiring | Dave Brown | Blocked | High | 2024-08-06 | 2024-08-27 |  | 0 | Concrete | Industrial Park | 10827.72 | 7094.43 | Not started
C003 | Office Tower C | T121 | Interior Painting | Rachel Green | Blocked | Medium | 2024-12-09 | 2024-12-27 |  | 0 | Paint | Downtown Avenue | 37194.63 | 34147.9 | Not started
C002 | Shopping Complex B | T453 | Steel Framework Setup | John Miller | Completed | Low | 2024-10-25 | 2024-11-12 | 2024-11-12 | 100 | Cement | Market Street | 28794.13 | 45813.47 | No issues
C004 | Warehouse D | T517 | Plumbing Installations | Mike Adams | Not Started | High | 2023-09-12 | 2023-09-29 |  | 0 | Concrete | Industrial Park | 33938.78 | 0 | Not started
C002 | Shopping Complex B | T145 | Foundation Excavation | Dave Brown | Not Started | Low | 2024-04-05 | 2024-04-20 |  | 0 | Concrete | Market Street | 29040.83 | 0 | Not started
C004 | Warehouse D | T244 | Steel Framework Setup | Grace Allen | Not Started | Low | 2023-10-12 | 2023-11-05 |  | 0 | Copper Wires | Industrial Park | 41069.66 | 0 | Not started
C003 | Office Tower C | T564 | Roofing | Sarah Johnson | Not Started | High | 2024-10-04 | 2024-10-18 |  | 0 | Steel Beams | Downtown Avenue | 38962.33 | 0 | Not started
C004 | Warehouse D | T239 | Electrical Wiring | John Miller | Not Started | High | 2023-10-21 | 2023-11-18 |  | 0 | Cement | Industrial Park | 40290.66 | 0 | Not started
C001 | Residential Building A | T363 | Roofing | Sarah Johnson | Completed | Medium | 2023-01-02 | 2023-01-30 | 2023-01-30 | 100 | Copper Wires | Plot 21, Riverside | 6684.45 | 4497.96 | No issues
C002 | Shopping Complex B | T275 | Steel Framework Setup | John Miller | Not Started | Medium | 2024-09-14 | 2024-10-10 |  | 0 | Steel Beams | Market Street | 42176.54 | 0 | Not started
C004 | Warehouse D | T601 | Steel Framework Setup | Rachel Green | Not Started | High | 2024-03-21 | 2024-04-11 |  | 0 | Concrete | Industrial Park | 32329.82 | 0 | Not started
C003 | Office Tower C | T584 | Plumbing Installations | Mike Adams | In Progress | Low | 2024-06-24 | 2024-07-11 |  | 92 | Cement | Downtown Avenue | 35341.08 | 33763.92 | In progress
C001 | Residential Building A | T397 | Interior Painting | Mike Adams | Completed | Medium | 2023-09-20 | 2023-10-13 | 2023-10-13 | 100 | Copper Wires | Plot 21, Riverside | 21516.15 | 16643.11 | No issues
C001 | Residential Building A | T492 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-05-05 | 2024-05-31 |  | 0 | Paint | Plot 21, Riverside | 18308.31 | 21200.44 | Not started
C004 | Warehouse D | T490 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-09-19 | 2024-10-08 |  | 1 | Roofing Sheets | Industrial Park | 46748.81 | 39271.68 | In progress
C004 | Warehouse D | T447 | Roofing | John Miller | Not Started | High | 2024-04-13 | 2024-05-05 |  | 0 | Roofing Sheets | Industrial Park | 33349.66 | 0 | Not started
C002 | Shopping Complex B | T176 | Site Survey | Rachel Green | Not Started | High | 2023-06-06 | 2023-06-21 |  | 0 | Paint | Market Street | 19360.74 | 0 | Not started
C003 | Office Tower C | T234 | Electrical Wiring | Mike Adams | Blocked | High | 2023-05-05 | 2023-05-19 |  | 0 | Paint | Downtown Avenue | 40719.9 | 45202.31 | Not started
C004 | Warehouse D | T442 | Electrical Wiring | John Miller | Completed | High | 2023-05-22 | 2023-06-09 | 2023-06-09 | 100 | Paint | Industrial Park | 41399.52 | 25040.89 | No issues
C001 | Residential Building A | T210 | Electrical Wiring | Emma White | Not Started | Medium | 2023-04-11 | 2023-05-08 |  | 0 | Paint | Plot 21, Riverside | 43769.94 | 0 | Not started
C001 | Residential Building A | T208 | Electrical Wiring | Emma White | Not Started | Low | 2023-04-18 | 2023-04-29 |  | 0 | Rebar | Plot 21, Riverside | 36668.94 | 0 | Not started
C002 | Shopping Complex B | T188 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2023-05-20 | 2023-05-28 |  | 0 | PVC Pipes | Market Street | 24901.21 | 46682.76 | Not started
C001 | Residential Building A | T589 | Steel Framework Setup | Rachel Green | Completed | Low | 2024-01-08 | 2024-01-30 | 2024-01-30 | 100 | Rebar | Plot 21, Riverside | 12841.55 | 10693.83 | No issues
C004 | Warehouse D | T160 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2024-01-01 | 2024-01-28 |  | 47 | Paint | Industrial Park | 31371.16 | 35286.67 | In progress
C004 | Warehouse D | T741 | Foundation Excavation | Carlos Rivera | Blocked | High | 2024-11-20 | 2024-12-14 |  | 0 | PVC Pipes | Industrial Park | 13893.51 | 13251.87 | Not started
C003 | Office Tower C | T370 | Foundation Excavation | Dave Brown | Not Started | High | 2024-10-24 | 2024-11-20 |  | 0 | Paint | Downtown Avenue | 49807.27 | 0 | Not started
C004 | Warehouse D | T979 | Site Survey | Dave Brown | Completed | Medium | 2023-10-27 | 2023-11-14 | 2023-11-14 | 100 | PVC Pipes | Industrial Park | 42957.42 | 33081.22 | No issues
C003 | Office Tower C | T410 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2023-07-27 | 2023-08-05 |  | 0 | Roofing Sheets | Downtown Avenue | 44286.08 | 0 | Not started
C004 | Warehouse D | T684 | Site Survey | Mike Adams | Not Started | Medium | 2024-06-21 | 2024-07-11 |  | 0 | PVC Pipes | Industrial Park | 31137.31 | 0 | Not started
C004 | Warehouse D | T189 | Steel Framework Setup | Rachel Green | Blocked | Low | 2023-06-25 | 2023-07-08 |  | 0 | Copper Wires | Industrial Park | 21680.81 | 22563.94 | Not started
C004 | Warehouse D | T305 | Site Survey | Carlos Rivera | Blocked | Medium | 2024-02-02 | 2024-02-16 |  | 0 | Paint | Industrial Park | 19503.62 | 19550.84 | Not started
C002 | Shopping Complex B | T324 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-08-15 | 2023-09-01 |  | 0 | Roofing Sheets | Market Street | 30912.49 | 0 | Not started
C004 | Warehouse D | T967 | Plumbing Installations | John Miller | In Progress | Medium | 2023-08-14 | 2023-08-24 |  | 50 | Roofing Sheets | Industrial Park | 26981.84 | 27665.41 | In progress
C003 | Office Tower C | T552 | Plumbing Installations | John Miller | Completed | Medium | 2023-06-04 | 2023-06-14 | 2023-06-14 | 100 | Steel Beams | Downtown Avenue | 39597.84 | 31871.33 | No issues
C002 | Shopping Complex B | T923 | Site Survey | Mike Adams | In Progress | High | 2023-06-01 | 2023-06-12 |  | 62 | PVC Pipes | Market Street | 39612.26 | 63698.15 | In progress
C003 | Office Tower C | T408 | Concrete Pouring | Grace Allen | Not Started | Medium | 2024-09-23 | 2024-10-15 |  | 0 | PVC Pipes | Downtown Avenue | 10452.8 | 0 | Not started
C002 | Shopping Complex B | T508 | Interior Painting | Dave Brown | Not Started | Medium | 2024-10-10 | 2024-10-24 |  | 0 | Paint | Market Street | 23469.86 | 0 | Not started
C003 | Office Tower C | T777 | Interior Painting | Grace Allen | Completed | High | 2023-06-02 | 2023-06-23 | 2023-06-23 | 100 | Cement | Downtown Avenue | 19685.94 | 16560.2 | No issues
C003 | Office Tower C | T788 | Site Survey | Rachel Green | In Progress | Medium | 2024-11-11 | 2024-11-19 |  | 17 | Paint | Downtown Avenue | 30763.66 | 32174.86 | In progress
C004 | Warehouse D | T190 | Concrete Pouring | Mike Adams | Blocked | Low | 2023-10-13 | 2023-10-28 |  | 0 | Concrete | Industrial Park | 49598.02 | 39875.23 | Not started
C004 | Warehouse D | T903 | Roofing | Mike Adams | Not Started | Medium | 2023-09-20 | 2023-10-03 |  | 0 | Paint | Industrial Park | 9278.49 | 0 | Not started
C003 | Office Tower C | T202 | Plumbing Installations | Carlos Rivera | Not Started | Medium | 2024-09-11 | 2024-09-29 |  | 0 | Paint | Downtown Avenue | 31716.7 | 0 | Not started
C003 | Office Tower C | T806 | Foundation Excavation | Rachel Green | Completed | Medium | 2024-02-16 | 2024-02-29 | 2024-02-29 | 100 | Concrete | Downtown Avenue | 42967.34 | 48685.54 | No issues
C001 | Residential Building A | T572 | Concrete Pouring | Rachel Green | Completed | Low | 2023-04-10 | 2023-05-05 | 2023-05-05 | 100 | Concrete | Plot 21, Riverside | 32809.23 | 23978.9 | No issues
C003 | Office Tower C | T856 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-04-11 | 2023-04-28 |  | 0 | Roofing Sheets | Downtown Avenue | 44526.2 | 0 | Not started
C004 | Warehouse D | T129 | Foundation Excavation | Emma White | In Progress | High | 2023-07-28 | 2023-08-15 |  | 78 | Copper Wires | Industrial Park | 39312.81 | 30289.74 | In progress
C002 | Shopping Complex B | T210 | Concrete Pouring | Rachel Green | Not Started | High | 2023-04-05 | 2023-04-23 |  | 0 | Concrete | Market Street | 13029.22 | 0 | Not started
C003 | Office Tower C | T629 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2024-11-28 | 2024-12-16 |  | 48 | Concrete | Downtown Avenue | 5834.86 | 4045.1 | In progress
C003 | Office Tower C | T883 | Foundation Excavation | Emma White | Completed | Medium | 2024-11-24 | 2024-12-10 | 2024-12-10 | 100 | PVC Pipes | Downtown Avenue | 22277.63 | 20180.89 | No issues
C003 | Office Tower C | T399 | Plumbing Installations | Dave Brown | Not Started | Medium | 2024-07-27 | 2024-08-18 |  | 0 | Paint | Downtown Avenue | 12904.27 | 0 | Not started
C001 | Residential Building A | T206 | Roofing | Carlos Rivera | Not Started | High | 2023-02-23 | 2023-03-13 |  | 0 | PVC Pipes | Plot 21, Riverside | 38468.32 | 0 | Not started
C003 | Office Tower C | T306 | Foundation Excavation | Rachel Green | Not Started | High | 2023-07-10 | 2023-07-20 |  | 0 | Steel Beams | Downtown Avenue | 21023.33 | 0 | Not started
C002 | Shopping Complex B | T415 | Roofing | Emma White | Blocked | Low | 2023-02-16 | 2023-02-26 |  | 0 | Copper Wires | Market Street | 12360.88 | 33141.1 | Not started
C001 | Residential Building A | T235 | Steel Framework Setup | Dave Brown | In Progress | Low | 2024-06-16 | 2024-07-02 |  | 48 | Rebar | Plot 21, Riverside | 35178.09 | 27161.49 | In progress
C001 | Residential Building A | T443 | Plumbing Installations | John Miller | Completed | High | 2024-08-08 | 2024-08-21 | 2024-08-21 | 100 | Copper Wires | Plot 21, Riverside | 23372.26 | 22965.85 | No issues
C004 | Warehouse D | T711 | Electrical Wiring | Dave Brown | Blocked | Medium | 2024-04-17 | 2024-05-14 |  | 0 | Copper Wires | Industrial Park | 8244.29 | 5874.44 | Not started
C002 | Shopping Complex B | T988 | Plumbing Installations | John Miller | Not Started | High | 2023-05-05 | 2023-05-24 |  | 0 | Roofing Sheets | Market Street | 12814.54 | 0 | Not started
C001 | Residential Building A | T413 | Electrical Wiring | Mike Adams | Not Started | Medium | 2023-09-02 | 2023-09-15 |  | 0 | Steel Beams | Plot 21, Riverside | 34065.59 | 0 | Not started
C002 | Shopping Complex B | T936 | Roofing | John Miller | Blocked | Low | 2024-01-12 | 2024-02-10 |  | 0 | Steel Beams | Market Street | 46951.33 | 64800.43 | Not started
C002 | Shopping Complex B | T627 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-01-08 | 2023-02-04 | 2023-02-04 | 100 | Copper Wires | Market Street | 11379.7 | 35188.39 | No issues
C001 | Residential Building A | T189 | Site Survey | Rachel Green | Completed | Medium | 2024-11-25 | 2024-12-04 | 2024-12-04 | 100 | Steel Beams | Plot 21, Riverside | 33460.16 | 39423.7 | No issues
C004 | Warehouse D | T566 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2024-11-16 | 2024-12-07 |  | 0 | PVC Pipes | Industrial Park | 14294.36 | 12012.13 | Not started
C004 | Warehouse D | T154 | Electrical Wiring | Grace Allen | In Progress | Medium | 2024-07-20 | 2024-07-27 |  | 33 | PVC Pipes | Industrial Park | 41598.98 | 25598.35 | In progress
C004 | Warehouse D | T290 | Roofing | Dave Brown | Blocked | Low | 2023-02-16 | 2023-03-07 |  | 0 | Rebar | Industrial Park | 26364.96 | 17520.6 | Not started
C004 | Warehouse D | T526 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-03-26 | 2024-04-07 |  | 64 | Rebar | Industrial Park | 12894.08 | 8446.05 | In progress
C002 | Shopping Complex B | T263 | Plumbing Installations | Rachel Green | In Progress | Medium | 2023-03-20 | 2023-04-02 |  | 64 | Steel Beams | Market Street | 17706.8 | 45475.56 | In progress
C004 | Warehouse D | T916 | Site Survey | Mike Adams | Blocked | High | 2023-07-06 | 2023-07-21 |  | 0 | Concrete | Industrial Park | 22574.19 | 16723.28 | Not started
C003 | Office Tower C | T888 | Foundation Excavation | Emma White | Blocked | High | 2024-02-21 | 2024-03-22 |  | 0 | Rebar | Downtown Avenue | 39146.53 | 32027.76 | Not started
C001 | Residential Building A | T226 | Interior Painting | Grace Allen | Completed | High | 2023-03-02 | 2023-03-30 | 2023-03-30 | 100 | Steel Beams | Plot 21, Riverside | 7434.58 | 4970.22 | No issues
C003 | Office Tower C | T173 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-12-23 | 2024-01-14 |  | 0 | Rebar | Downtown Avenue | 40635.37 | 0 | Not started
C001 | Residential Building A | T369 | Plumbing Installations | Emma White | Blocked | Low | 2024-02-21 | 2024-03-11 |  | 0 | Cement | Plot 21, Riverside | 40261.61 | 29311.71 | Not started
C003 | Office Tower C | T469 | Interior Painting | Emma White | In Progress | Low | 2023-01-27 | 2023-02-19 |  | 8 | Copper Wires | Downtown Avenue | 18475.75 | 17468.04 | In progress
C003 | Office Tower C | T413 | Site Survey | John Miller | Blocked | Medium | 2024-05-09 | 2024-05-18 |  | 0 | Rebar | Downtown Avenue | 11093.09 | 12302.87 | Not started
C003 | Office Tower C | T803 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2024-12-14 | 2025-01-02 |  | 0 | Copper Wires | Downtown Avenue | 41888.82 | 26481.05 | Not started
C003 | Office Tower C | T121 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2024-01-09 | 2024-01-27 |  | 0 | Roofing Sheets | Downtown Avenue | 22544.96 | 0 | Not started
C003 | Office Tower C | T924 | Steel Framework Setup | Emma White | Blocked | Medium | 2023-08-13 | 2023-08-31 |  | 0 | Steel Beams | Downtown Avenue | 10209.38 | 8589.28 | Not started
C004 | Warehouse D | T361 | Interior Painting | Carlos Rivera | In Progress | High | 2023-11-15 | 2023-11-30 |  | 50 | PVC Pipes | Industrial Park | 25595.96 | 27185.25 | In progress
C002 | Shopping Complex B | T795 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2024-06-01 | 2024-06-15 |  | 0 | Rebar | Market Street | 26922.94 | 54034.19 | Not started
C004 | Warehouse D | T621 | Foundation Excavation | Grace Allen | Completed | Low | 2023-02-13 | 2023-03-10 | 2023-03-10 | 100 | Steel Beams | Industrial Park | 9406.96 | 10493.23 | No issues
C002 | Shopping Complex B | T227 | Interior Painting | Dave Brown | Not Started | Medium | 2024-05-19 | 2024-05-31 |  | 0 | Steel Beams | Market Street | 32750.92 | 0 | Not started
C003 | Office Tower C | T728 | Foundation Excavation | Dave Brown | In Progress | Low | 2024-01-09 | 2024-01-26 |  | 75 | Steel Beams | Downtown Avenue | 25895.97 | 20253.5 | In progress
C004 | Warehouse D | T680 | Site Survey | Grace Allen | Not Started | Medium | 2023-10-19 | 2023-11-05 |  | 0 | Paint | Industrial Park | 6661.72 | 0 | Not started
C001 | Residential Building A | T739 | Interior Painting | Grace Allen | Completed | Low | 2023-08-22 | 2023-09-19 | 2023-09-19 | 100 | Copper Wires | Plot 21, Riverside | 23567.46 | 27912.82 | No issues
C003 | Office Tower C | T538 | Plumbing Installations | Rachel Green | Not Started | Low | 2023-08-05 | 2023-08-15 |  | 0 | Cement | Downtown Avenue | 27770.43 | 0 | Not started
C002 | Shopping Complex B | T750 | Foundation Excavation | Grace Allen | Not Started | Low | 2024-08-15 | 2024-09-04 |  | 0 | Roofing Sheets | Market Street | 20121.41 | 0 | Not started
C004 | Warehouse D | T104 | Foundation Excavation | Rachel Green | In Progress | Low | 2024-12-20 | 2024-12-30 |  | 51 | Copper Wires | Industrial Park | 48795.26 | 42701.4 | In progress
C004 | Warehouse D | T945 | Electrical Wiring | Rachel Green | Not Started | High | 2023-01-23 | 2023-02-18 |  | 0 | Roofing Sheets | Industrial Park | 37116.53 | 0 | Not started
C002 | Shopping Complex B | T816 | Foundation Excavation | Dave Brown | Not Started | Medium | 2023-12-28 | 2024-01-13 |  | 0 | Paint | Market Street | 39427.53 | 0 | Not started
C004 | Warehouse D | T492 | Interior Painting | Sarah Johnson | Not Started | Medium | 2023-02-28 | 2023-03-09 |  | 0 | Copper Wires | Industrial Park | 34331.87 | 0 | Not started
C001 | Residential Building A | T495 | Steel Framework Setup | John Miller | Not Started | Low | 2024-10-17 | 2024-11-15 |  | 0 | Rebar | Plot 21, Riverside | 44921.52 | 0 | Not started
C001 | Residential Building A | T271 | Steel Framework Setup | Rachel Green | Completed | Low | 2023-09-28 | 2023-10-22 | 2023-10-22 | 100 | Paint | Plot 21, Riverside | 33797.8 | 40150.21 | No issues
C004 | Warehouse D | T408 | Concrete Pouring | Dave Brown | Not Started | Low | 2023-03-02 | 2023-03-16 |  | 0 | Paint | Industrial Park | 10299.59 | 0 | Not started
C002 | Shopping Complex B | T887 | Foundation Excavation | Rachel Green | Not Started | Low | 2024-06-13 | 2024-07-07 |  | 0 | Concrete | Market Street | 14177.96 | 0 | Not started
C002 | Shopping Complex B | T171 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-09-08 | 2024-09-28 |  | 4 | PVC Pipes | Market Street | 14054.8 | 35696.36 | In progress
C004 | Warehouse D | T697 | Roofing | John Miller | Blocked | Low | 2024-03-23 | 2024-04-18 |  | 0 | Concrete | Industrial Park | 11813.31 | 8959.19 | Not started
C003 | Office Tower C | T662 | Roofing | Dave Brown | Completed | Low | 2024-07-13 | 2024-08-04 | 2024-08-04 | 100 | PVC Pipes | Downtown Avenue | 11128 | 10085.47 | No issues
C002 | Shopping Complex B | T722 | Steel Framework Setup | Rachel Green | Not Started | Medium | 2024-02-11 | 2024-03-03 |  | 0 | Rebar | Market Street | 43421.02 | 0 | Not started
C001 | Residential Building A | T747 | Foundation Excavation | Carlos Rivera | Not Started | High | 2024-11-05 | 2024-11-26 |  | 0 | Cement | Plot 21, Riverside | 40589.3 | 0 | Not started
C003 | Office Tower C | T656 | Site Survey | Carlos Rivera | Completed | Low | 2023-02-19 | 2023-03-15 | 2023-03-15 | 100 | Cement | Downtown Avenue | 48962.57 | 58683.74 | No issues
C004 | Warehouse D | T812 | Foundation Excavation | Carlos Rivera | Blocked | High | 2024-08-28 | 2024-09-21 |  | 0 | Concrete | Industrial Park | 22040.18 | 18994.07 | Not started
C002 | Shopping Complex B | T274 | Roofing | Sarah Johnson | Blocked | High | 2023-03-21 | 2023-04-15 |  | 0 | Copper Wires | Market Street | 7385.29 | 33127.11 | Not started
C002 | Shopping Complex B | T305 | Foundation Excavation | Rachel Green | Completed | Medium | 2023-08-05 | 2023-08-30 | 2023-08-30 | 100 | Steel Beams | Market Street | 31414.76 | 60602.47 | No issues
C004 | Warehouse D | T715 | Foundation Excavation | Grace Allen | Blocked | Medium | 2023-03-24 | 2023-04-15 |  | 0 | Paint | Industrial Park | 45418.62 | 48435.89 | Not started
C003 | Office Tower C | T405 | Interior Painting | Grace Allen | Blocked | High | 2023-02-16 | 2023-03-18 |  | 0 | PVC Pipes | Downtown Avenue | 10558.02 | 8803.11 | Not started
C001 | Residential Building A | T962 | Site Survey | Carlos Rivera | In Progress | High | 2024-01-28 | 2024-02-15 |  | 46 | Copper Wires | Plot 21, Riverside | 42934.31 | 46014.59 | In progress
C004 | Warehouse D | T681 | Site Survey | John Miller | Not Started | Low | 2023-07-16 | 2023-07-23 |  | 0 | Copper Wires | Industrial Park | 23320.19 | 0 | Not started
C001 | Residential Building A | T532 | Roofing | Rachel Green | Not Started | Low | 2024-12-25 | 2025-01-22 |  | 0 | Paint | Plot 21, Riverside | 49634.92 | 0 | Not started
C004 | Warehouse D | T140 | Site Survey | Mike Adams | Not Started | Low | 2024-08-08 | 2024-09-01 |  | 0 | Steel Beams | Industrial Park | 36093.71 | 0 | Not started
C003 | Office Tower C | T283 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2023-06-22 | 2023-07-15 |  | 0 | Cement | Downtown Avenue | 25412.68 | 0 | Not started
C003 | Office Tower C | T282 | Plumbing Installations | John Miller | Completed | High | 2023-07-28 | 2023-08-16 | 2023-08-16 | 100 | Roofing Sheets | Downtown Avenue | 16474.11 | 10414.53 | No issues
C003 | Office Tower C | T654 | Concrete Pouring | John Miller | Not Started | Medium | 2023-01-15 | 2023-02-08 |  | 0 | Paint | Downtown Avenue | 11242.91 | 0 | Not started
C004 | Warehouse D | T573 | Concrete Pouring | Mike Adams | Not Started | High | 2024-02-02 | 2024-02-27 |  | 0 | Copper Wires | Industrial Park | 11133.49 | 0 | Not started
C003 | Office Tower C | T173 | Concrete Pouring | John Miller | Completed | Low | 2024-09-08 | 2024-10-02 | 2024-10-02 | 100 | Concrete | Downtown Avenue | 16210.79 | 16330.59 | No issues
C001 | Residential Building A | T395 | Interior Painting | Emma White | Completed | Low | 2024-11-13 | 2024-11-23 | 2024-11-23 | 100 | Copper Wires | Plot 21, Riverside | 12336.73 | 8543.92 | No issues
C002 | Shopping Complex B | T855 | Roofing | Rachel Green | Blocked | High | 2024-05-15 | 2024-06-04 |  | 0 | Cement | Market Street | 12342.5 | 39892.93 | Not started
C003 | Office Tower C | T738 | Plumbing Installations | Rachel Green | Completed | High | 2024-02-14 | 2024-03-10 | 2024-03-10 | 100 | Copper Wires | Downtown Avenue | 19626.59 | 12297.35 | No issues
C001 | Residential Building A | T288 | Concrete Pouring | Mike Adams | Completed | Low | 2024-01-22 | 2024-02-08 | 2024-02-08 | 100 | Concrete | Plot 21, Riverside | 7263.05 | 5101.6 | No issues
C003 | Office Tower C | T464 | Plumbing Installations | Rachel Green | In Progress | High | 2023-08-26 | 2023-09-23 |  | 63 | Concrete | Downtown Avenue | 21067.53 | 22328.48 | In progress
C001 | Residential Building A | T291 | Roofing | Rachel Green | Blocked | High | 2024-02-15 | 2024-03-10 |  | 0 | Copper Wires | Plot 21, Riverside | 5764.04 | 4222.78 | Not started
C001 | Residential Building A | T379 | Foundation Excavation | Rachel Green | Completed | Low | 2023-02-07 | 2023-02-26 | 2023-02-26 | 100 | Copper Wires | Plot 21, Riverside | 30818.65 | 24748.67 | No issues
C002 | Shopping Complex B | T316 | Roofing | Grace Allen | In Progress | Medium | 2023-07-12 | 2023-08-02 |  | 60 | Paint | Market Street | 12306.77 | 33936.67 | In progress
C004 | Warehouse D | T509 | Steel Framework Setup | Emma White | In Progress | High | 2023-12-19 | 2024-01-18 |  | 52 | Concrete | Industrial Park | 26492.69 | 30153.21 | In progress
C003 | Office Tower C | T562 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2023-01-21 | 2023-02-15 |  | 0 | Paint | Downtown Avenue | 37414.17 | 0 | Not started
C004 | Warehouse D | T483 | Steel Framework Setup | Carlos Rivera | Not Started | High | 2024-05-02 | 2024-05-28 |  | 0 | Steel Beams | Industrial Park | 41472.9 | 0 | Not started
C001 | Residential Building A | T173 | Steel Framework Setup | Emma White | Not Started | Medium | 2024-03-14 | 2024-03-24 |  | 0 | Steel Beams | Plot 21, Riverside | 33650.16 | 0 | Not started
C004 | Warehouse D | T899 | Concrete Pouring | Grace Allen | Completed | Medium | 2023-09-05 | 2023-09-22 | 2023-09-22 | 100 | Rebar | Industrial Park | 19157.3 | 16321.16 | No issues
C001 | Residential Building A | T508 | Electrical Wiring | Sarah Johnson | In Progress | High | 2024-07-10 | 2024-07-22 |  | 51 | Cement | Plot 21, Riverside | 12117.62 | 9276.14 | In progress
C003 | Office Tower C | T102 | Roofing | John Miller | Blocked | Medium | 2023-05-09 | 2023-05-19 |  | 0 | Cement | Downtown Avenue | 12050.78 | 10125.01 | Not started
C002 | Shopping Complex B | T623 | Roofing | Rachel Green | Blocked | Medium | 2024-11-24 | 2024-12-03 |  | 0 | Paint | Market Street | 22644.88 | 44710.99 | Not started
C003 | Office Tower C | T974 | Foundation Excavation | Emma White | Not Started | High | 2024-02-11 | 2024-03-11 |  | 0 | Roofing Sheets | Downtown Avenue | 38908.64 | 0 | Not started
C003 | Office Tower C | T833 | Site Survey | Mike Adams | Completed | Medium | 2023-05-23 | 2023-06-04 | 2023-06-04 | 100 | Rebar | Downtown Avenue | 33830.01 | 30215.07 | No issues
C002 | Shopping Complex B | T699 | Site Survey | John Miller | In Progress | High | 2024-09-16 | 2024-09-25 |  | 58 | Cement | Market Street | 32205.57 | 48506.54 | In progress
C002 | Shopping Complex B | T449 | Site Survey | Grace Allen | Blocked | Low | 2024-01-01 | 2024-01-22 |  | 0 | PVC Pipes | Market Street | 34731.72 | 55978.8 | Not started
C004 | Warehouse D | T134 | Plumbing Installations | Carlos Rivera | Completed | Low | 2023-05-08 | 2023-05-22 | 2023-05-22 | 100 | PVC Pipes | Industrial Park | 11550.72 | 13175.52 | No issues
C002 | Shopping Complex B | T412 | Interior Painting | John Miller | Blocked | High | 2024-05-06 | 2024-05-13 |  | 0 | Steel Beams | Market Street | 29244.13 | 44142.47 | Not started
C001 | Residential Building A | T795 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-06-27 | 2023-07-04 | 2023-07-04 | 100 | Concrete | Plot 21, Riverside | 40802 | 37876.21 | No issues
C002 | Shopping Complex B | T753 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2023-04-07 | 2023-04-15 |  | 65 | Concrete | Market Street | 33119.76 | 58721.69 | In progress
C004 | Warehouse D | T859 | Site Survey | Emma White | In Progress | High | 2023-11-27 | 2023-12-17 |  | 31 | PVC Pipes | Industrial Park | 21578.12 | 14173.01 | In progress
C004 | Warehouse D | T971 | Electrical Wiring | Sarah Johnson | Blocked | High | 2023-07-24 | 2023-08-04 |  | 0 | Steel Beams | Industrial Park | 17321.94 | 17575.87 | Not started
C004 | Warehouse D | T524 | Site Survey | Grace Allen | In Progress | Low | 2023-03-24 | 2023-04-11 |  | 49 | Cement | Industrial Park | 29225.36 | 31710.72 | In progress
C003 | Office Tower C | T105 | Electrical Wiring | Mike Adams | Completed | Low | 2024-05-24 | 2024-06-17 | 2024-06-17 | 100 | Cement | Downtown Avenue | 19087.1 | 14681.81 | No issues
C001 | Residential Building A | T772 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2023-01-20 | 2023-02-05 |  | 0 | Concrete | Plot 21, Riverside | 22623.45 | 0 | Not started
C004 | Warehouse D | T835 | Concrete Pouring | Mike Adams | Completed | High | 2024-07-04 | 2024-07-28 | 2024-07-28 | 100 | Roofing Sheets | Industrial Park | 41500.19 | 33489.89 | No issues
C002 | Shopping Complex B | T949 | Roofing | Emma White | Not Started | Low | 2024-11-21 | 2024-12-12 |  | 0 | PVC Pipes | Market Street | 6689.94 | 0 | Not started
C001 | Residential Building A | T278 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2023-12-21 | 2024-01-16 |  | 0 | Concrete | Plot 21, Riverside | 28713.05 | 24330.88 | Not started
C003 | Office Tower C | T797 | Site Survey | Rachel Green | In Progress | Medium | 2023-01-03 | 2023-01-25 |  | 4 | Concrete | Downtown Avenue | 36076.16 | 36377.86 | In progress
C001 | Residential Building A | T701 | Steel Framework Setup | Dave Brown | Completed | Medium | 2024-08-19 | 2024-09-05 | 2024-09-05 | 100 | Concrete | Plot 21, Riverside | 37443.04 | 40949.1 | No issues
C002 | Shopping Complex B | T707 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2024-12-27 | 2025-01-11 |  | 0 | Roofing Sheets | Market Street | 20586.75 | 39982.75 | Not started
C003 | Office Tower C | T361 | Site Survey | Sarah Johnson | Completed | Low | 2023-07-09 | 2023-07-17 | 2023-07-17 | 100 | PVC Pipes | Downtown Avenue | 7712.03 | 4833.5 | No issues
C002 | Shopping Complex B | T576 | Plumbing Installations | Grace Allen | Blocked | Medium | 2024-10-27 | 2024-11-25 |  | 0 | Cement | Market Street | 43784.86 | 68250.77 | Not started
C001 | Residential Building A | T896 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2024-03-11 | 2024-04-09 |  | 0 | Steel Beams | Plot 21, Riverside | 46762.89 | 37500.13 | Not started
C003 | Office Tower C | T511 | Roofing | Rachel Green | Blocked | Medium | 2024-05-13 | 2024-06-10 |  | 0 | Rebar | Downtown Avenue | 12540.74 | 9006.21 | Not started
C004 | Warehouse D | T287 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-06-03 | 2023-06-20 |  | 0 | Concrete | Industrial Park | 37533.94 | 31605.08 | Not started
C003 | Office Tower C | T223 | Plumbing Installations | John Miller | Not Started | High | 2024-01-14 | 2024-01-29 |  | 0 | Paint | Downtown Avenue | 41630.65 | 0 | Not started
C004 | Warehouse D | T704 | Steel Framework Setup | Dave Brown | In Progress | High | 2024-07-09 | 2024-07-29 |  | 36 | Concrete | Industrial Park | 28260.77 | 32690.94 | In progress
C001 | Residential Building A | T425 | Plumbing Installations | Mike Adams | Completed | Low | 2023-04-09 | 2023-05-07 | 2023-05-07 | 100 | Roofing Sheets | Plot 21, Riverside | 46533.77 | 29078.09 | No issues
C002 | Shopping Complex B | T201 | Electrical Wiring | Grace Allen | Blocked | Medium | 2024-02-08 | 2024-02-23 |  | 0 | Copper Wires | Market Street | 46938.57 | 64793.6 | Not started
C002 | Shopping Complex B | T305 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-03-02 | 2024-03-10 |  | 0 | Roofing Sheets | Market Street | 21011.55 | 39278.09 | Not started
C001 | Residential Building A | T748 | Foundation Excavation | Rachel Green | In Progress | Low | 2024-12-18 | 2025-01-14 |  | 52 | Paint | Plot 21, Riverside | 13391.02 | 9295.09 | In progress
C002 | Shopping Complex B | T797 | Roofing | Dave Brown | Not Started | Medium | 2024-09-21 | 2024-10-13 |  | 0 | Rebar | Market Street | 23180.8 | 0 | Not started
C004 | Warehouse D | T549 | Plumbing Installations | John Miller | Completed | Medium | 2024-01-18 | 2024-01-30 | 2024-01-30 | 100 | Cement | Industrial Park | 7865.69 | 6197.59 | No issues
C001 | Residential Building A | T302 | Plumbing Installations | Dave Brown | In Progress | Medium | 2023-02-21 | 2023-03-07 |  | 6 | Copper Wires | Plot 21, Riverside | 38520.63 | 44384.97 | In progress
C002 | Shopping Complex B | T839 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-01-21 | 2023-02-09 |  | 0 | Rebar | Market Street | 17918.74 | 42827.95 | Not started
C001 | Residential Building A | T431 | Electrical Wiring | Rachel Green | In Progress | High | 2023-08-25 | 2023-09-09 |  | 42 | Copper Wires | Plot 21, Riverside | 15066.17 | 13954.67 | In progress
C004 | Warehouse D | T843 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-04-12 | 2024-04-24 | 2024-04-24 | 100 | Roofing Sheets | Industrial Park | 6414.78 | 6596.54 | No issues
C004 | Warehouse D | T541 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2023-12-14 | 2023-12-27 | 2023-12-27 | 100 | PVC Pipes | Industrial Park | 37439.88 | 39715.81 | No issues
C002 | Shopping Complex B | T615 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-07-07 | 2024-07-25 | 2024-07-25 | 100 | Copper Wires | Market Street | 21153.08 | 41376.61 | No issues
C004 | Warehouse D | T372 | Steel Framework Setup | John Miller | Completed | Low | 2023-08-28 | 2023-09-25 | 2023-09-25 | 100 | PVC Pipes | Industrial Park | 18000.22 | 17865.93 | No issues
C004 | Warehouse D | T107 | Site Survey | Grace Allen | In Progress | Medium | 2024-09-27 | 2024-10-24 |  | 78 | Concrete | Industrial Park | 23940.1 | 18112.7 | In progress
C001 | Residential Building A | T774 | Roofing | Carlos Rivera | Not Started | Low | 2024-01-23 | 2024-01-31 |  | 0 | Paint | Plot 21, Riverside | 24134.33 | 0 | Not started
C001 | Residential Building A | T500 | Steel Framework Setup | Sarah Johnson | Completed | High | 2023-07-21 | 2023-08-05 | 2023-08-05 | 100 | Cement | Plot 21, Riverside | 13970.38 | 8890.83 | No issues
C001 | Residential Building A | T936 | Roofing | Rachel Green | In Progress | Medium | 2023-10-26 | 2023-11-11 |  | 53 | Paint | Plot 21, Riverside | 45205.89 | 52253.9 | In progress
C003 | Office Tower C | T629 | Electrical Wiring | Mike Adams | In Progress | Medium | 2023-12-05 | 2023-12-25 |  | 17 | Cement | Downtown Avenue | 45125.67 | 35792.81 | In progress
C004 | Warehouse D | T678 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2024-09-13 | 2024-09-23 |  | 0 | Concrete | Industrial Park | 18545.79 | 0 | Not started
C004 | Warehouse D | T247 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-12-13 | 2025-01-05 |  | 47 | Copper Wires | Industrial Park | 9104.35 | 7314.6 | In progress
C003 | Office Tower C | T313 | Interior Painting | Mike Adams | Completed | Low | 2023-01-14 | 2023-02-06 | 2023-02-06 | 100 | Steel Beams | Downtown Avenue | 48659.87 | 31208.47 | No issues
C002 | Shopping Complex B | T697 | Steel Framework Setup | Carlos Rivera | Completed | Low | 2023-10-12 | 2023-10-26 | 2023-10-26 | 100 | Concrete | Market Street | 30637.23 | 58069.68 | No issues
C002 | Shopping Complex B | T914 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2024-03-12 | 2024-03-20 | 2024-03-20 | 100 | Roofing Sheets | Market Street | 49700.53 | 77278.44 | No issues
C002 | Shopping Complex B | T514 | Interior Painting | Grace Allen | In Progress | Medium | 2023-06-07 | 2023-06-20 |  | 90 | Copper Wires | Market Street | 46994.99 | 77553.39 | In progress
C004 | Warehouse D | T604 | Foundation Excavation | John Miller | Not Started | Medium | 2024-10-02 | 2024-10-17 |  | 0 | Cement | Industrial Park | 40068.91 | 0 | Not started
C002 | Shopping Complex B | T555 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-11-03 | 2023-11-28 |  | 76 | Concrete | Market Street | 19106.96 | 41297.52 | In progress
C003 | Office Tower C | T354 | Foundation Excavation | Rachel Green | Not Started | Medium | 2024-10-02 | 2024-10-09 |  | 0 | Roofing Sheets | Downtown Avenue | 10255.2 | 0 | Not started
C001 | Residential Building A | T928 | Concrete Pouring | Grace Allen | Not Started | Medium | 2024-06-19 | 2024-07-08 |  | 0 | Steel Beams | Plot 21, Riverside | 47135.77 | 0 | Not started
C002 | Shopping Complex B | T638 | Site Survey | Grace Allen | Not Started | Low | 2023-02-10 | 2023-03-11 |  | 0 | PVC Pipes | Market Street | 12984.25 | 0 | Not started
C004 | Warehouse D | T145 | Site Survey | Dave Brown | Completed | Low | 2024-10-11 | 2024-11-06 | 2024-11-06 | 100 | Copper Wires | Industrial Park | 34592.62 | 28927.02 | No issues
C001 | Residential Building A | T377 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2024-08-10 | 2024-08-31 |  | 0 | PVC Pipes | Plot 21, Riverside | 49163.02 | 0 | Not started
C003 | Office Tower C | T132 | Electrical Wiring | Dave Brown | Blocked | Low | 2023-12-28 | 2024-01-10 |  | 0 | Concrete | Downtown Avenue | 7473.81 | 8948.27 | Not started
C003 | Office Tower C | T844 | Roofing | John Miller | Completed | Medium | 2024-01-16 | 2024-01-24 | 2024-01-24 | 100 | Paint | Downtown Avenue | 33687.52 | 38944.15 | No issues
C002 | Shopping Complex B | T871 | Site Survey | Carlos Rivera | Completed | Medium | 2024-08-14 | 2024-09-13 | 2024-09-13 | 100 | Concrete | Market Street | 32049.85 | 63002.6 | No issues
C003 | Office Tower C | T350 | Plumbing Installations | Dave Brown | Not Started | Low | 2024-05-25 | 2024-06-20 |  | 0 | Rebar | Downtown Avenue | 17239.38 | 0 | Not started
C001 | Residential Building A | T390 | Plumbing Installations | Mike Adams | Completed | Low | 2024-03-08 | 2024-03-29 | 2024-03-29 | 100 | Copper Wires | Plot 21, Riverside | 23178.04 | 14558.2 | No issues
C004 | Warehouse D | T469 | Roofing | Sarah Johnson | In Progress | Medium | 2024-09-10 | 2024-10-04 |  | 56 | Rebar | Industrial Park | 8220.81 | 9501.73 | In progress
C004 | Warehouse D | T753 | Foundation Excavation | John Miller | Not Started | Low | 2024-11-16 | 2024-12-13 |  | 0 | Paint | Industrial Park | 27056.14 | 0 | Not started
C002 | Shopping Complex B | T622 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2023-02-22 | 2023-03-14 |  | 0 | Paint | Market Street | 24496.87 | 48276.96 | Not started
C003 | Office Tower C | T445 | Plumbing Installations | Mike Adams | Not Started | Medium | 2023-10-08 | 2023-10-23 |  | 0 | PVC Pipes | Downtown Avenue | 7924.75 | 0 | Not started
C004 | Warehouse D | T750 | Interior Painting | Sarah Johnson | In Progress | Medium | 2023-11-26 | 2023-12-15 |  | 1 | Copper Wires | Industrial Park | 24160.85 | 26463.16 | In progress
C001 | Residential Building A | T922 | Concrete Pouring | John Miller | Completed | Medium | 2023-11-26 | 2023-12-11 | 2023-12-11 | 100 | Cement | Plot 21, Riverside | 47093.18 | 45259.86 | No issues
C001 | Residential Building A | T783 | Concrete Pouring | Grace Allen | Not Started | High | 2024-04-04 | 2024-04-20 |  | 0 | Copper Wires | Plot 21, Riverside | 20868.54 | 0 | Not started
C001 | Residential Building A | T373 | Electrical Wiring | Mike Adams | Completed | Low | 2024-05-16 | 2024-06-14 | 2024-06-14 | 100 | PVC Pipes | Plot 21, Riverside | 48160.64 | 41507.2 | No issues
C001 | Residential Building A | T110 | Electrical Wiring | Emma White | Blocked | Medium | 2024-06-25 | 2024-07-21 |  | 0 | Roofing Sheets | Plot 21, Riverside | 35487.16 | 26550.88 | Not started
C002 | Shopping Complex B | T315 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-02-23 | 2023-03-25 | 2023-03-25 | 100 | Concrete | Market Street | 46092.89 | 68311.9 | No issues
C004 | Warehouse D | T803 | Site Survey | Rachel Green | In Progress | Low | 2024-01-17 | 2024-02-16 |  | 65 | Rebar | Industrial Park | 12817.26 | 8824.06 | In progress
C001 | Residential Building A | T141 | Steel Framework Setup | Mike Adams | Blocked | High | 2024-09-08 | 2024-09-29 |  | 0 | Steel Beams | Plot 21, Riverside | 12799.25 | 11146.6 | Not started
C002 | Shopping Complex B | T557 | Electrical Wiring | John Miller | Blocked | Low | 2023-11-15 | 2023-11-23 |  | 0 | Paint | Market Street | 27538.07 | 52147.46 | Not started
C002 | Shopping Complex B | T184 | Roofing | John Miller | Blocked | Medium | 2023-12-09 | 2023-12-22 |  | 0 | Copper Wires | Market Street | 19588.74 | 46083.05 | Not started
C001 | Residential Building A | T441 | Electrical Wiring | Rachel Green | In Progress | Low | 2024-03-18 | 2024-04-13 |  | 87 | Concrete | Plot 21, Riverside | 22530.92 | 15403.15 | In progress
C001 | Residential Building A | T703 | Electrical Wiring | Dave Brown | Completed | Medium | 2023-10-21 | 2023-11-18 | 2023-11-18 | 100 | Copper Wires | Plot 21, Riverside | 8952.97 | 6801.11 | No issues
C004 | Warehouse D | T838 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2023-03-14 | 2023-04-02 |  | 0 | Rebar | Industrial Park | 29032.77 | 19082.34 | Not started
C002 | Shopping Complex B | T605 | Steel Framework Setup | Rachel Green | Not Started | Medium | 2024-09-03 | 2024-09-24 |  | 0 | Steel Beams | Market Street | 41179.25 | 0 | Not started
C001 | Residential Building A | T822 | Interior Painting | Sarah Johnson | In Progress | Medium | 2024-03-16 | 2024-03-31 |  | 39 | Steel Beams | Plot 21, Riverside | 46643.29 | 29981.94 | In progress
C004 | Warehouse D | T919 | Interior Painting | John Miller | In Progress | Medium | 2024-11-07 | 2024-12-06 |  | 41 | Cement | Industrial Park | 35542.25 | 39966.05 | In progress
C002 | Shopping Complex B | T336 | Plumbing Installations | Emma White | Blocked | Low | 2024-03-23 | 2024-04-14 |  | 0 | Cement | Market Street | 45876.79 | 70023.73 | Not started
C001 | Residential Building A | T355 | Steel Framework Setup | Dave Brown | Not Started | Medium | 2023-04-03 | 2023-04-19 |  | 0 | Copper Wires | Plot 21, Riverside | 34769.38 | 0 | Not started
C002 | Shopping Complex B | T787 | Concrete Pouring | Dave Brown | Blocked | High | 2023-03-02 | 2023-04-01 |  | 0 | Roofing Sheets | Market Street | 25052.22 | 46107.8 | Not started
C002 | Shopping Complex B | T739 | Interior Painting | Mike Adams | Completed | Medium | 2024-12-01 | 2024-12-25 | 2024-12-25 | 100 | Copper Wires | Market Street | 14261.34 | 36142.51 | No issues
C003 | Office Tower C | T849 | Concrete Pouring | John Miller | Not Started | High | 2023-12-12 | 2024-01-05 |  | 0 | Paint | Downtown Avenue | 39833.34 | 0 | Not started
C002 | Shopping Complex B | T910 | Concrete Pouring | Rachel Green | In Progress | Medium | 2024-02-09 | 2024-03-03 |  | 26 | Concrete | Market Street | 22045.42 | 45191.8 | In progress
C004 | Warehouse D | T622 | Site Survey | Grace Allen | Completed | Low | 2024-05-22 | 2024-06-09 | 2024-06-09 | 100 | Copper Wires | Industrial Park | 15875 | 14377.6 | No issues
C004 | Warehouse D | T733 | Plumbing Installations | Dave Brown | In Progress | High | 2023-03-19 | 2023-03-27 |  | 71 | Rebar | Industrial Park | 26801.45 | 21489.55 | In progress
C001 | Residential Building A | T452 | Roofing | Rachel Green | In Progress | Medium | 2023-10-12 | 2023-11-02 |  | 90 | Roofing Sheets | Plot 21, Riverside | 6212.76 | 7395.35 | In progress
C001 | Residential Building A | T949 | Steel Framework Setup | John Miller | Not Started | High | 2023-09-20 | 2023-09-29 |  | 0 | Steel Beams | Plot 21, Riverside | 17016.96 | 0 | Not started
C003 | Office Tower C | T873 | Foundation Excavation | Dave Brown | Not Started | High | 2024-03-23 | 2024-04-08 |  | 0 | Cement | Downtown Avenue | 33365.92 | 0 | Not started
C004 | Warehouse D | T514 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-12-11 | 2024-01-03 |  | 0 | Copper Wires | Industrial Park | 22248.39 | 0 | Not started
C002 | Shopping Complex B | T166 | Electrical Wiring | Dave Brown | Completed | Low | 2024-06-12 | 2024-06-22 | 2024-06-22 | 100 | Roofing Sheets | Market Street | 22930.65 | 47957.05 | No issues
C002 | Shopping Complex B | T907 | Plumbing Installations | Rachel Green | Completed | Low | 2024-04-28 | 2024-05-17 | 2024-05-17 | 100 | Concrete | Market Street | 42745.91 | 60896.86 | No issues
C004 | Warehouse D | T552 | Foundation Excavation | Sarah Johnson | Not Started | Medium | 2024-10-08 | 2024-10-21 |  | 0 | Concrete | Industrial Park | 32491.01 | 0 | Not started
C001 | Residential Building A | T559 | Interior Painting | John Miller | Blocked | Medium | 2024-04-19 | 2024-04-26 |  | 0 | Paint | Plot 21, Riverside | 49052.3 | 38582.35 | Not started
C002 | Shopping Complex B | T353 | Steel Framework Setup | John Miller | In Progress | Medium | 2023-04-11 | 2023-05-07 |  | 10 | PVC Pipes | Market Street | 23473.85 | 51394.85 | In progress
C001 | Residential Building A | T685 | Electrical Wiring | Mike Adams | Blocked | Medium | 2024-02-22 | 2024-03-04 |  | 0 | Rebar | Plot 21, Riverside | 7682.48 | 4986.17 | Not started
C002 | Shopping Complex B | T111 | Roofing | Grace Allen | Completed | Low | 2024-08-12 | 2024-08-27 | 2024-08-27 | 100 | Steel Beams | Market Street | 20035.89 | 45604.28 | No issues
C002 | Shopping Complex B | T890 | Foundation Excavation | John Miller | In Progress | High | 2023-05-09 | 2023-06-05 |  | 84 | Steel Beams | Market Street | 41015.02 | 52876.78 | In progress
C001 | Residential Building A | T790 | Site Survey | Mike Adams | In Progress | High | 2024-03-13 | 2024-04-08 |  | 55 | Rebar | Plot 21, Riverside | 23560.27 | 22925.98 | In progress
C004 | Warehouse D | T634 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-05-15 | 2024-06-03 |  | 0 | Roofing Sheets | Industrial Park | 25520.83 | 18448.04 | Not started
C002 | Shopping Complex B | T283 | Interior Painting | Rachel Green | Not Started | Low | 2024-11-07 | 2024-12-02 |  | 0 | Cement | Market Street | 32721.1 | 0 | Not started
C002 | Shopping Complex B | T739 | Roofing | John Miller | Not Started | High | 2024-07-23 | 2024-08-06 |  | 0 | Concrete | Market Street | 21948.88 | 0 | Not started
C003 | Office Tower C | T222 | Concrete Pouring | Dave Brown | In Progress | Low | 2023-12-19 | 2024-01-08 |  | 84 | Roofing Sheets | Downtown Avenue | 9259.14 | 7314.95 | In progress
C003 | Office Tower C | T656 | Roofing | Grace Allen | Not Started | Medium | 2024-03-05 | 2024-04-01 |  | 0 | Cement | Downtown Avenue | 47752.33 | 0 | Not started
C001 | Residential Building A | T250 | Site Survey | Dave Brown | Blocked | High | 2024-07-08 | 2024-07-16 |  | 0 | Paint | Plot 21, Riverside | 41784.77 | 48447.04 | Not started
C002 | Shopping Complex B | T837 | Site Survey | Carlos Rivera | In Progress | Low | 2023-02-06 | 2023-02-24 |  | 98 | Roofing Sheets | Market Street | 21007.08 | 38893.56 | In progress
C002 | Shopping Complex B | T853 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-08-05 | 2024-08-22 |  | 0 | Copper Wires | Market Street | 5559.54 | 30804.95 | Not started
C002 | Shopping Complex B | T596 | Roofing | Rachel Green | Blocked | Low | 2023-07-12 | 2023-07-29 |  | 0 | Copper Wires | Market Street | 46570.69 | 69995.43 | Not started
C002 | Shopping Complex B | T811 | Plumbing Installations | Mike Adams | In Progress | High | 2024-10-15 | 2024-10-24 |  | 99 | Paint | Market Street | 16509.56 | 41238.55 | In progress
C003 | Office Tower C | T636 | Foundation Excavation | Emma White | Not Started | Medium | 2024-10-13 | 2024-11-09 |  | 0 | Paint | Downtown Avenue | 34888.32 | 0 | Not started
C003 | Office Tower C | T896 | Steel Framework Setup | Mike Adams | Blocked | Low | 2023-01-13 | 2023-02-05 |  | 0 | Copper Wires | Downtown Avenue | 11262.88 | 6940.28 | Not started
C002 | Shopping Complex B | T328 | Interior Painting | Mike Adams | In Progress | Low | 2023-10-21 | 2023-11-17 |  | 40 | Cement | Market Street | 37821.73 | 52578.12 | In progress
C004 | Warehouse D | T352 | Interior Painting | John Miller | In Progress | Medium | 2023-04-13 | 2023-05-06 |  | 82 | Concrete | Industrial Park | 16495.11 | 19592.67 | In progress
C003 | Office Tower C | T423 | Interior Painting | Grace Allen | Blocked | Low | 2024-08-08 | 2024-08-19 |  | 0 | Cement | Downtown Avenue | 12830.23 | 10233.17 | Not started
C003 | Office Tower C | T955 | Steel Framework Setup | Rachel Green | Not Started | High | 2024-07-12 | 2024-07-24 |  | 0 | Rebar | Downtown Avenue | 5199.31 | 0 | Not started
C004 | Warehouse D | T568 | Steel Framework Setup | Dave Brown | Completed | High | 2024-05-19 | 2024-06-15 | 2024-06-15 | 100 | Rebar | Industrial Park | 20134.19 | 14991.49 | No issues
C003 | Office Tower C | T480 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-08-27 | 2023-09-26 |  | 0 | Cement | Downtown Avenue | 23409.75 | 0 | Not started
C003 | Office Tower C | T742 | Foundation Excavation | Rachel Green | In Progress | High | 2024-05-09 | 2024-05-18 |  | 57 | Cement | Downtown Avenue | 16044.74 | 18436.01 | In progress
C003 | Office Tower C | T358 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2024-01-25 | 2024-02-16 |  | 0 | Paint | Downtown Avenue | 37908.54 | 43167.01 | Not started
C001 | Residential Building A | T352 | Plumbing Installations | Emma White | Not Started | Low | 2024-10-12 | 2024-11-10 |  | 0 | Roofing Sheets | Plot 21, Riverside | 44593.91 | 0 | Not started
C002 | Shopping Complex B | T816 | Roofing | John Miller | Not Started | Medium | 2023-05-11 | 2023-05-24 |  | 0 | Copper Wires | Market Street | 15689.41 | 0 | Not started
C003 | Office Tower C | T911 | Concrete Pouring | Sarah Johnson | Blocked | High | 2023-09-04 | 2023-09-27 |  | 0 | Paint | Downtown Avenue | 15027.66 | 10144.13 | Not started
C002 | Shopping Complex B | T844 | Interior Painting | Dave Brown | Completed | Medium | 2024-10-07 | 2024-11-05 | 2024-11-05 | 100 | Rebar | Market Street | 46697.78 | 64688.97 | No issues
C001 | Residential Building A | T223 | Foundation Excavation | Emma White | Blocked | Medium | 2023-11-06 | 2023-11-16 |  | 0 | Concrete | Plot 21, Riverside | 35820.77 | 28704.82 | Not started
C003 | Office Tower C | T445 | Concrete Pouring | Grace Allen | Blocked | High | 2024-03-15 | 2024-04-05 |  | 0 | PVC Pipes | Downtown Avenue | 21033.51 | 23563.24 | Not started
C003 | Office Tower C | T842 | Roofing | Sarah Johnson | Blocked | High | 2023-06-22 | 2023-07-21 |  | 0 | Copper Wires | Downtown Avenue | 46710.97 | 32086.32 | Not started
C001 | Residential Building A | T103 | Site Survey | Emma White | In Progress | Medium | 2024-03-07 | 2024-03-28 |  | 36 | Concrete | Plot 21, Riverside | 23472.98 | 15586.93 | In progress
C003 | Office Tower C | T900 | Roofing | Grace Allen | Completed | Medium | 2024-05-14 | 2024-06-09 | 2024-06-09 | 100 | Cement | Downtown Avenue | 21574.9 | 24088.74 | No issues
C002 | Shopping Complex B | T419 | Electrical Wiring | Grace Allen | Blocked | High | 2023-12-13 | 2024-01-10 |  | 0 | Steel Beams | Market Street | 44366.91 | 66092.44 | Not started
C002 | Shopping Complex B | T783 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-01-08 | 2023-02-05 |  | 99 | PVC Pipes | Market Street | 23472.26 | 45744.37 | In progress
C003 | Office Tower C | T410 | Electrical Wiring | Sarah Johnson | Blocked | High | 2023-07-09 | 2023-08-06 |  | 0 | Concrete | Downtown Avenue | 36816.77 | 41437.86 | Not started
C001 | Residential Building A | T552 | Site Survey | Grace Allen | Completed | High | 2023-05-06 | 2023-06-04 | 2023-06-04 | 100 | Copper Wires | Plot 21, Riverside | 18169.08 | 19408.87 | No issues
C003 | Office Tower C | T870 | Roofing | Carlos Rivera | Not Started | High | 2023-09-24 | 2023-10-09 |  | 0 | Concrete | Downtown Avenue | 9814.06 | 0 | Not started
C001 | Residential Building A | T911 | Steel Framework Setup | Carlos Rivera | Completed | High | 2024-09-18 | 2024-10-03 | 2024-10-03 | 100 | Cement | Plot 21, Riverside | 24453.72 | 25167.35 | No issues
C001 | Residential Building A | T919 | Electrical Wiring | Mike Adams | Completed | High | 2024-07-02 | 2024-07-24 | 2024-07-24 | 100 | Cement | Plot 21, Riverside | 32385.65 | 21353.78 | No issues
C002 | Shopping Complex B | T386 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2024-08-17 | 2024-08-31 |  | 72 | Concrete | Market Street | 36702.57 | 49162.57 | In progress
C003 | Office Tower C | T194 | Roofing | Rachel Green | Blocked | Medium | 2024-04-22 | 2024-05-16 |  | 0 | Paint | Downtown Avenue | 8821.99 | 8890.45 | Not started
C003 | Office Tower C | T662 | Roofing | Carlos Rivera | Completed | Low | 2023-12-16 | 2024-01-04 | 2024-01-04 | 100 | Concrete | Downtown Avenue | 24395.33 | 19967.56 | No issues
C004 | Warehouse D | T817 | Steel Framework Setup | Rachel Green | In Progress | Medium | 2024-11-24 | 2024-12-15 |  | 53 | Steel Beams | Industrial Park | 26770.2 | 29627.24 | In progress
C002 | Shopping Complex B | T356 | Interior Painting | Dave Brown | In Progress | Medium | 2023-03-16 | 2023-04-07 |  | 67 | Roofing Sheets | Market Street | 6619.75 | 31699.56 | In progress
C003 | Office Tower C | T334 | Foundation Excavation | Sarah Johnson | Blocked | High | 2024-10-05 | 2024-10-17 |  | 0 | Roofing Sheets | Downtown Avenue | 7433.25 | 5461.89 | Not started
C004 | Warehouse D | T733 | Foundation Excavation | Mike Adams | Not Started | High | 2023-06-01 | 2023-06-30 |  | 0 | Steel Beams | Industrial Park | 41913.49 | 0 | Not started
C004 | Warehouse D | T910 | Foundation Excavation | Grace Allen | In Progress | Medium | 2023-02-21 | 2023-03-16 |  | 67 | PVC Pipes | Industrial Park | 7805.47 | 5384.32 | In progress
C002 | Shopping Complex B | T712 | Plumbing Installations | Carlos Rivera | Completed | Low | 2024-10-16 | 2024-11-15 | 2024-11-15 | 100 | Concrete | Market Street | 28575.18 | 53536.04 | No issues
C002 | Shopping Complex B | T908 | Concrete Pouring | Rachel Green | Completed | Low | 2024-11-09 | 2024-11-29 | 2024-11-29 | 100 | Concrete | Market Street | 23957.64 | 42799.24 | No issues
C002 | Shopping Complex B | T249 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-06-15 | 2024-06-25 |  | 0 | Concrete | Market Street | 20204.38 | 48723.02 | Not started
C003 | Office Tower C | T334 | Interior Painting | Carlos Rivera | In Progress | Low | 2024-08-28 | 2024-09-26 |  | 40 | Paint | Downtown Avenue | 47648.39 | 42616.2 | In progress
C003 | Office Tower C | T647 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2023-04-13 | 2023-04-26 | 2023-04-26 | 100 | Roofing Sheets | Downtown Avenue | 14329.23 | 13316.64 | No issues
C001 | Residential Building A | T966 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2023-09-12 | 2023-10-08 |  | 0 | PVC Pipes | Plot 21, Riverside | 10206.87 | 7413.13 | Not started
C001 | Residential Building A | T698 | Electrical Wiring | Carlos Rivera | Not Started | High | 2023-03-22 | 2023-04-03 |  | 0 | Concrete | Plot 21, Riverside | 38993.18 | 0 | Not started
C004 | Warehouse D | T474 | Electrical Wiring | John Miller | Not Started | High | 2023-01-10 | 2023-02-07 |  | 0 | Steel Beams | Industrial Park | 36742.48 | 0 | Not started
C004 | Warehouse D | T377 | Plumbing Installations | Emma White | In Progress | High | 2023-10-16 | 2023-10-28 |  | 47 | Rebar | Industrial Park | 23808.22 | 26650.42 | In progress
C002 | Shopping Complex B | T172 | Plumbing Installations | Carlos Rivera | Blocked | High | 2024-01-10 | 2024-02-09 |  | 0 | Steel Beams | Market Street | 41989.98 | 68118.11 | Not started
C004 | Warehouse D | T961 | Interior Painting | Emma White | Blocked | High | 2023-11-27 | 2023-12-10 |  | 0 | Concrete | Industrial Park | 23924.14 | 17550.89 | Not started
C002 | Shopping Complex B | T229 | Roofing | Dave Brown | Not Started | Low | 2024-10-08 | 2024-10-24 |  | 0 | Copper Wires | Market Street | 21826.64 | 0 | Not started
C001 | Residential Building A | T816 | Electrical Wiring | Mike Adams | Not Started | Medium | 2023-10-15 | 2023-10-30 |  | 0 | Concrete | Plot 21, Riverside | 34407.95 | 0 | Not started
C001 | Residential Building A | T272 | Foundation Excavation | Dave Brown | Completed | Medium | 2023-07-27 | 2023-08-23 | 2023-08-23 | 100 | Roofing Sheets | Plot 21, Riverside | 38316.39 | 25877.88 | No issues
C001 | Residential Building A | T809 | Roofing | John Miller | Blocked | Low | 2023-12-26 | 2024-01-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 44433.51 | 48102.77 | Not started
C003 | Office Tower C | T611 | Site Survey | Dave Brown | In Progress | Medium | 2023-07-18 | 2023-08-02 |  | 14 | Rebar | Downtown Avenue | 46101.84 | 35646.02 | In progress
C001 | Residential Building A | T657 | Plumbing Installations | Carlos Rivera | Completed | High | 2023-01-08 | 2023-01-20 | 2023-01-20 | 100 | Paint | Plot 21, Riverside | 12535.27 | 13450.53 | No issues
C003 | Office Tower C | T440 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2023-07-10 | 2023-07-28 |  | 0 | Rebar | Downtown Avenue | 34645.14 | 0 | Not started
C001 | Residential Building A | T501 | Electrical Wiring | Dave Brown | Blocked | Medium | 2024-04-15 | 2024-04-26 |  | 0 | Paint | Plot 21, Riverside | 42625.02 | 44155.86 | Not started
C003 | Office Tower C | T871 | Site Survey | Grace Allen | Not Started | High | 2024-06-19 | 2024-07-19 |  | 0 | Paint | Downtown Avenue | 30576.94 | 0 | Not started
C004 | Warehouse D | T560 | Electrical Wiring | Carlos Rivera | Completed | High | 2024-09-13 | 2024-10-05 | 2024-10-05 | 100 | Roofing Sheets | Industrial Park | 29989.64 | 28600.21 | No issues
C002 | Shopping Complex B | T340 | Site Survey | Carlos Rivera | In Progress | Medium | 2024-05-19 | 2024-06-01 |  | 81 | PVC Pipes | Market Street | 18216.41 | 44709.77 | In progress
C002 | Shopping Complex B | T464 | Roofing | Dave Brown | Blocked | Low | 2023-11-05 | 2023-11-14 |  | 0 | Concrete | Market Street | 33513.51 | 58043.82 | Not started
C003 | Office Tower C | T307 | Roofing | Emma White | In Progress | Low | 2024-07-04 | 2024-07-18 |  | 84 | PVC Pipes | Downtown Avenue | 38156.29 | 23080.62 | In progress
C002 | Shopping Complex B | T497 | Interior Painting | Carlos Rivera | Not Started | Medium | 2023-06-12 | 2023-07-02 |  | 0 | Cement | Market Street | 12099.84 | 0 | Not started
C001 | Residential Building A | T910 | Steel Framework Setup | Mike Adams | Completed | Low | 2024-06-05 | 2024-06-29 | 2024-06-29 | 100 | Copper Wires | Plot 21, Riverside | 6924.95 | 5638.61 | No issues
C004 | Warehouse D | T882 | Steel Framework Setup | John Miller | Blocked | Medium | 2024-08-17 | 2024-09-02 |  | 0 | Rebar | Industrial Park | 20781.63 | 22205.13 | Not started
C002 | Shopping Complex B | T403 | Foundation Excavation | Grace Allen | Blocked | High | 2023-09-09 | 2023-09-24 |  | 0 | Concrete | Market Street | 44756.09 | 53792.83 | Not started
C003 | Office Tower C | T876 | Site Survey | Carlos Rivera | Completed | Low | 2023-10-24 | 2023-11-16 | 2023-11-16 | 100 | Cement | Downtown Avenue | 36537.91 | 23343.76 | No issues
C003 | Office Tower C | T682 | Foundation Excavation | John Miller | In Progress | Low | 2023-05-19 | 2023-05-26 |  | 24 | Copper Wires | Downtown Avenue | 17284.86 | 14252.29 | In progress
C003 | Office Tower C | T977 | Electrical Wiring | Carlos Rivera | In Progress | High | 2024-01-06 | 2024-01-17 |  | 30 | Roofing Sheets | Downtown Avenue | 49997.22 | 59426.68 | In progress
C003 | Office Tower C | T223 | Site Survey | Dave Brown | Completed | High | 2024-04-05 | 2024-04-13 | 2024-04-13 | 100 | Steel Beams | Downtown Avenue | 47542.55 | 51216.84 | No issues
C002 | Shopping Complex B | T496 | Interior Painting | Rachel Green | Blocked | High | 2023-05-15 | 2023-06-14 |  | 0 | Concrete | Market Street | 7964.31 | 34557.46 | Not started
C004 | Warehouse D | T568 | Site Survey | Emma White | Blocked | Low | 2024-02-26 | 2024-03-26 |  | 0 | Roofing Sheets | Industrial Park | 6981.48 | 6639.38 | Not started
C001 | Residential Building A | T456 | Interior Painting | Mike Adams | In Progress | Medium | 2024-11-20 | 2024-12-14 |  | 88 | Cement | Plot 21, Riverside | 15720.12 | 15922.48 | In progress
C002 | Shopping Complex B | T603 | Interior Painting | Rachel Green | In Progress | Medium | 2024-03-17 | 2024-04-09 |  | 82 | Concrete | Market Street | 36604.67 | 47938.33 | In progress
C001 | Residential Building A | T955 | Electrical Wiring | John Miller | Not Started | High | 2024-03-24 | 2024-04-03 |  | 0 | Copper Wires | Plot 21, Riverside | 21785.07 | 0 | Not started
C003 | Office Tower C | T294 | Interior Painting | John Miller | Completed | Low | 2023-12-18 | 2024-01-14 | 2024-01-14 | 100 | Steel Beams | Downtown Avenue | 12647.93 | 11860.63 | No issues
C004 | Warehouse D | T912 | Concrete Pouring | Mike Adams | Blocked | High | 2024-04-01 | 2024-04-19 |  | 0 | Roofing Sheets | Industrial Park | 25747.93 | 19929.32 | Not started
C002 | Shopping Complex B | T627 | Electrical Wiring | Carlos Rivera | Completed | High | 2023-06-03 | 2023-06-15 | 2023-06-15 | 100 | Copper Wires | Market Street | 10728.46 | 33249.45 | No issues
C004 | Warehouse D | T756 | Site Survey | Rachel Green | Completed | Low | 2023-03-04 | 2023-03-26 | 2023-03-26 | 100 | PVC Pipes | Industrial Park | 33667.22 | 40377.67 | No issues
C002 | Shopping Complex B | T212 | Plumbing Installations | Mike Adams | In Progress | High | 2023-01-14 | 2023-01-23 |  | 60 | Roofing Sheets | Market Street | 48889.43 | 55147.95 | In progress
C001 | Residential Building A | T232 | Concrete Pouring | Rachel Green | Completed | Medium | 2024-04-10 | 2024-05-05 | 2024-05-05 | 100 | Paint | Plot 21, Riverside | 28532.32 | 18224.7 | No issues
C004 | Warehouse D | T149 | Concrete Pouring | John Miller | In Progress | High | 2024-10-27 | 2024-11-13 |  | 4 | Concrete | Industrial Park | 18721.29 | 13370.23 | In progress
C001 | Residential Building A | T328 | Concrete Pouring | Mike Adams | Blocked | Low | 2023-02-05 | 2023-02-19 |  | 0 | PVC Pipes | Plot 21, Riverside | 18921.25 | 22402.27 | Not started
C001 | Residential Building A | T981 | Concrete Pouring | Dave Brown | Completed | High | 2024-10-02 | 2024-10-23 | 2024-10-23 | 100 | Roofing Sheets | Plot 21, Riverside | 41543.14 | 35355.91 | No issues
C003 | Office Tower C | T300 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-03-06 | 2023-03-15 |  | 0 | Cement | Downtown Avenue | 44131.75 | 0 | Not started
C001 | Residential Building A | T817 | Plumbing Installations | John Miller | In Progress | High | 2024-08-01 | 2024-08-17 |  | 18 | Steel Beams | Plot 21, Riverside | 13604.67 | 13828.09 | In progress
C003 | Office Tower C | T657 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2023-01-05 | 2023-01-15 |  | 0 | Paint | Downtown Avenue | 45693.04 | 51811.09 | Not started
C004 | Warehouse D | T251 | Plumbing Installations | Rachel Green | Blocked | Medium | 2023-10-08 | 2023-11-02 |  | 0 | Concrete | Industrial Park | 45194.51 | 47205.29 | Not started
C002 | Shopping Complex B | T924 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2024-06-07 | 2024-06-19 |  | 0 | Roofing Sheets | Market Street | 35391.23 | 0 | Not started
C002 | Shopping Complex B | T709 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-03-03 | 2023-03-20 |  | 0 | Copper Wires | Market Street | 11997.62 | 38983.45 | Not started
C001 | Residential Building A | T642 | Electrical Wiring | John Miller | In Progress | Medium | 2023-09-28 | 2023-10-07 |  | 73 | Rebar | Plot 21, Riverside | 23495.74 | 19666.79 | In progress
C003 | Office Tower C | T521 | Interior Painting | Carlos Rivera | Not Started | High | 2023-06-11 | 2023-06-20 |  | 0 | Concrete | Downtown Avenue | 40429.73 | 0 | Not started
C002 | Shopping Complex B | T421 | Roofing | Rachel Green | In Progress | Medium | 2023-12-22 | 2024-01-18 |  | 68 | Steel Beams | Market Street | 25908.53 | 53547.32 | In progress
C003 | Office Tower C | T555 | Electrical Wiring | Grace Allen | In Progress | High | 2024-12-16 | 2025-01-06 |  | 21 | Steel Beams | Downtown Avenue | 38714.54 | 41525.25 | In progress
C003 | Office Tower C | T485 | Foundation Excavation | Emma White | In Progress | Low | 2023-04-25 | 2023-05-05 |  | 4 | Concrete | Downtown Avenue | 11557.69 | 11967.56 | In progress
C004 | Warehouse D | T972 | Site Survey | Sarah Johnson | Completed | Low | 2024-07-05 | 2024-07-25 | 2024-07-25 | 100 | Copper Wires | Industrial Park | 18568.28 | 11914 | No issues
C004 | Warehouse D | T781 | Interior Painting | Mike Adams | Completed | High | 2023-01-22 | 2023-02-09 | 2023-02-09 | 100 | Rebar | Industrial Park | 31442.71 | 33349.96 | No issues
C004 | Warehouse D | T195 | Concrete Pouring | Emma White | In Progress | High | 2024-04-09 | 2024-04-25 |  | 37 | Steel Beams | Industrial Park | 11597.42 | 9155.78 | In progress
C004 | Warehouse D | T358 | Foundation Excavation | Grace Allen | Completed | Low | 2023-07-06 | 2023-07-29 | 2023-07-29 | 100 | Copper Wires | Industrial Park | 36948.17 | 35839.55 | No issues
C003 | Office Tower C | T387 | Interior Painting | John Miller | In Progress | High | 2024-11-01 | 2024-11-14 |  | 8 | Roofing Sheets | Downtown Avenue | 24920.13 | 28577.71 | In progress
C001 | Residential Building A | T961 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2023-01-15 | 2023-02-06 |  | 0 | Steel Beams | Plot 21, Riverside | 19888.78 | 18219.38 | Not started
C001 | Residential Building A | T229 | Concrete Pouring | Grace Allen | Completed | Medium | 2024-11-26 | 2024-12-24 | 2024-12-24 | 100 | Steel Beams | Plot 21, Riverside | 20108.18 | 20775.48 | No issues
C001 | Residential Building A | T644 | Site Survey | Emma White | Completed | Medium | 2023-11-12 | 2023-11-20 | 2023-11-20 | 100 | Copper Wires | Plot 21, Riverside | 23280 | 22631.16 | No issues
C001 | Residential Building A | T424 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2024-08-14 | 2024-09-06 |  | 80 | Copper Wires | Plot 21, Riverside | 7435.63 | 5722.49 | In progress
C003 | Office Tower C | T379 | Interior Painting | Emma White | Not Started | Medium | 2024-10-08 | 2024-10-27 |  | 0 | Cement | Downtown Avenue | 44540.1 | 0 | Not started
C004 | Warehouse D | T263 | Steel Framework Setup | Dave Brown | Not Started | Low | 2024-06-19 | 2024-07-19 |  | 0 | Roofing Sheets | Industrial Park | 22716.66 | 0 | Not started
C003 | Office Tower C | T529 | Concrete Pouring | Mike Adams | Blocked | High | 2023-02-21 | 2023-03-06 |  | 0 | Steel Beams | Downtown Avenue | 25059.92 | 15486.73 | Not started
C004 | Warehouse D | T559 | Interior Painting | John Miller | In Progress | Low | 2024-01-17 | 2024-01-28 |  | 82 | Roofing Sheets | Industrial Park | 43826.26 | 41970.22 | In progress
C004 | Warehouse D | T673 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-11-07 | 2024-11-27 |  | 0 | Steel Beams | Industrial Park | 17337.65 | 0 | Not started
C001 | Residential Building A | T989 | Interior Painting | Emma White | Not Started | Low | 2023-09-01 | 2023-09-14 |  | 0 | Steel Beams | Plot 21, Riverside | 43970.81 | 0 | Not started
C004 | Warehouse D | T921 | Roofing | Emma White | Not Started | Medium | 2023-10-17 | 2023-11-04 |  | 0 | Concrete | Industrial Park | 29856.44 | 0 | Not started
C004 | Warehouse D | T214 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-03-27 | 2024-04-10 |  | 0 | Roofing Sheets | Industrial Park | 17023.8 | 0 | Not started
C003 | Office Tower C | T385 | Roofing | Sarah Johnson | In Progress | Medium | 2023-12-20 | 2023-12-31 |  | 20 | Steel Beams | Downtown Avenue | 42120.35 | 31098.18 | In progress
C001 | Residential Building A | T714 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2023-07-23 | 2023-08-09 |  | 0 | Copper Wires | Plot 21, Riverside | 15170.87 | 0 | Not started
C001 | Residential Building A | T131 | Site Survey | Rachel Green | Blocked | Medium | 2024-05-28 | 2024-06-12 |  | 0 | Steel Beams | Plot 21, Riverside | 10610.4 | 7374.41 | Not started
C001 | Residential Building A | T657 | Site Survey | Sarah Johnson | Not Started | Medium | 2024-07-27 | 2024-08-06 |  | 0 | Cement | Plot 21, Riverside | 40717.86 | 0 | Not started
C003 | Office Tower C | T743 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2024-04-07 | 2024-05-06 |  | 0 | Copper Wires | Downtown Avenue | 27056.36 | 0 | Not started
C002 | Shopping Complex B | T548 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2024-05-24 | 2024-06-07 |  | 0 | PVC Pipes | Market Street | 43439.82 | 56454.04 | Not started
C001 | Residential Building A | T526 | Site Survey | John Miller | Completed | Low | 2024-07-14 | 2024-07-30 | 2024-07-30 | 100 | Concrete | Plot 21, Riverside | 19566.76 | 20762.96 | No issues
C003 | Office Tower C | T778 | Site Survey | Rachel Green | Not Started | High | 2024-12-03 | 2024-12-24 |  | 0 | Paint | Downtown Avenue | 16407.15 | 0 | Not started
C004 | Warehouse D | T539 | Site Survey | Grace Allen | Not Started | Medium | 2024-11-09 | 2024-12-04 |  | 0 | PVC Pipes | Industrial Park | 47200.88 | 0 | Not started
C004 | Warehouse D | T218 | Foundation Excavation | Mike Adams | In Progress | High | 2024-04-28 | 2024-05-20 |  | 18 | Paint | Industrial Park | 48735.36 | 32829.46 | In progress
C003 | Office Tower C | T641 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2024-08-04 | 2024-08-28 | 2024-08-28 | 100 | PVC Pipes | Downtown Avenue | 15642.72 | 17916.84 | No issues
C003 | Office Tower C | T157 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2024-04-20 | 2024-04-29 |  | 0 | Rebar | Downtown Avenue | 9065.98 | 0 | Not started
C001 | Residential Building A | T911 | Interior Painting | Mike Adams | Completed | High | 2024-01-05 | 2024-01-30 | 2024-01-30 | 100 | Rebar | Plot 21, Riverside | 6775.97 | 5833.95 | No issues
C003 | Office Tower C | T127 | Steel Framework Setup | John Miller | Completed | Low | 2023-02-03 | 2023-02-10 | 2023-02-10 | 100 | Concrete | Downtown Avenue | 22262.48 | 23822.2 | No issues
C003 | Office Tower C | T468 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2023-08-05 | 2023-08-30 |  | 0 | Concrete | Downtown Avenue | 45393.66 | 46095.65 | Not started
C001 | Residential Building A | T996 | Steel Framework Setup | John Miller | Completed | Low | 2023-12-11 | 2024-01-01 | 2024-01-01 | 100 | Concrete | Plot 21, Riverside | 16300.52 | 14833.38 | No issues
C001 | Residential Building A | T921 | Plumbing Installations | John Miller | Blocked | High | 2024-12-07 | 2024-12-27 |  | 0 | Roofing Sheets | Plot 21, Riverside | 12323.32 | 11964.51 | Not started
C002 | Shopping Complex B | T440 | Concrete Pouring | Emma White | Blocked | Medium | 2024-12-07 | 2025-01-06 |  | 0 | Paint | Market Street | 36772.88 | 66715.43 | Not started
C002 | Shopping Complex B | T363 | Interior Painting | Dave Brown | In Progress | Medium | 2023-09-25 | 2023-10-12 |  | 42 | Concrete | Market Street | 25105.14 | 48205.36 | In progress
C001 | Residential Building A | T291 | Concrete Pouring | Emma White | Blocked | High | 2024-02-19 | 2024-03-09 |  | 0 | Steel Beams | Plot 21, Riverside | 37482.77 | 26498.52 | Not started
C002 | Shopping Complex B | T220 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-09-22 | 2023-10-10 | 2023-10-10 | 100 | Cement | Market Street | 40890.24 | 69132.5 | No issues
C003 | Office Tower C | T941 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-01-18 | 2024-02-12 | 2024-02-12 | 100 | Concrete | Downtown Avenue | 35631.01 | 39493.59 | No issues
C003 | Office Tower C | T497 | Roofing | Emma White | Not Started | High | 2023-03-01 | 2023-03-10 |  | 0 | Copper Wires | Downtown Avenue | 36093.74 | 0 | Not started
C001 | Residential Building A | T660 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-09-23 | 2023-10-13 |  | 0 | Steel Beams | Plot 21, Riverside | 13306.75 | 0 | Not started
C004 | Warehouse D | T494 | Foundation Excavation | Rachel Green | In Progress | Low | 2023-02-09 | 2023-02-23 |  | 39 | Steel Beams | Industrial Park | 46098.1 | 35669.55 | In progress
C002 | Shopping Complex B | T364 | Roofing | Rachel Green | Not Started | Low | 2024-06-17 | 2024-06-25 |  | 0 | PVC Pipes | Market Street | 11097.97 | 0 | Not started
C004 | Warehouse D | T906 | Interior Painting | Sarah Johnson | Not Started | High | 2024-02-13 | 2024-03-12 |  | 0 | PVC Pipes | Industrial Park | 24381.38 | 0 | Not started
C002 | Shopping Complex B | T776 | Site Survey | Dave Brown | Completed | High | 2023-04-19 | 2023-05-05 | 2023-05-05 | 100 | Cement | Market Street | 43458.9 | 53648.72 | No issues
C004 | Warehouse D | T524 | Site Survey | Emma White | Completed | Low | 2024-06-26 | 2024-07-13 | 2024-07-13 | 100 | Copper Wires | Industrial Park | 17729.84 | 18840.08 | No issues
C002 | Shopping Complex B | T345 | Roofing | Dave Brown | Not Started | High | 2023-06-06 | 2023-06-28 |  | 0 | Rebar | Market Street | 19444.22 | 0 | Not started
C003 | Office Tower C | T551 | Concrete Pouring | Dave Brown | In Progress | Low | 2023-07-28 | 2023-08-26 |  | 56 | Roofing Sheets | Downtown Avenue | 12767.55 | 13619.01 | In progress
C001 | Residential Building A | T951 | Electrical Wiring | Grace Allen | Completed | Medium | 2023-01-11 | 2023-01-19 | 2023-01-19 | 100 | PVC Pipes | Plot 21, Riverside | 48810.79 | 56979.94 | No issues
C003 | Office Tower C | T945 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2024-03-22 | 2024-04-15 |  | 0 | Copper Wires | Downtown Avenue | 45614.76 | 53488.48 | Not started
C002 | Shopping Complex B | T192 | Concrete Pouring | Grace Allen | In Progress | High | 2023-08-23 | 2023-09-22 |  | 35 | Roofing Sheets | Market Street | 38983.59 | 49580.5 | In progress
C004 | Warehouse D | T770 | Site Survey | Carlos Rivera | In Progress | High | 2024-07-15 | 2024-08-13 |  | 41 | PVC Pipes | Industrial Park | 41367.47 | 41573.86 | In progress
C004 | Warehouse D | T392 | Concrete Pouring | John Miller | In Progress | Low | 2023-10-25 | 2023-11-19 |  | 42 | Rebar | Industrial Park | 15616.24 | 18544.01 | In progress
C001 | Residential Building A | T537 | Concrete Pouring | Grace Allen | Not Started | High | 2024-04-08 | 2024-04-21 |  | 0 | Paint | Plot 21, Riverside | 7839.18 | 0 | Not started
C004 | Warehouse D | T106 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2024-09-16 | 2024-10-04 |  | 0 | Rebar | Industrial Park | 36281.23 | 43307.02 | Not started
C001 | Residential Building A | T650 | Foundation Excavation | Sarah Johnson | Not Started | High | 2023-03-11 | 2023-03-18 |  | 0 | Paint | Plot 21, Riverside | 47632.86 | 0 | Not started
C002 | Shopping Complex B | T387 | Site Survey | Sarah Johnson | Not Started | Low | 2023-02-21 | 2023-03-09 |  | 0 | Cement | Market Street | 11889.2 | 0 | Not started
C004 | Warehouse D | T250 | Roofing | Grace Allen | Completed | High | 2023-10-22 | 2023-11-15 | 2023-11-15 | 100 | Rebar | Industrial Park | 21114.35 | 19597.42 | No issues
C004 | Warehouse D | T341 | Steel Framework Setup | John Miller | In Progress | Medium | 2024-03-27 | 2024-04-25 |  | 72 | Concrete | Industrial Park | 11259.7 | 9468.31 | In progress
C001 | Residential Building A | T569 | Plumbing Installations | Emma White | Completed | High | 2023-07-10 | 2023-07-22 | 2023-07-22 | 100 | Steel Beams | Plot 21, Riverside | 23054.18 | 19569.15 | No issues
C004 | Warehouse D | T469 | Site Survey | Rachel Green | In Progress | Medium | 2023-03-08 | 2023-03-15 |  | 53 | Paint | Industrial Park | 7111.76 | 5911.97 | In progress
C002 | Shopping Complex B | T335 | Foundation Excavation | Dave Brown | Blocked | High | 2023-06-18 | 2023-07-04 |  | 0 | Steel Beams | Market Street | 9229.19 | 31902.12 | Not started
C004 | Warehouse D | T857 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-12-05 | 2025-01-03 | 2025-01-03 | 100 | Paint | Industrial Park | 5847.9 | 5382.85 | No issues
C002 | Shopping Complex B | T198 | Foundation Excavation | Emma White | Completed | Low | 2023-12-16 | 2024-01-02 | 2024-01-02 | 100 | Steel Beams | Market Street | 43997.57 | 69958.3 | No issues
C003 | Office Tower C | T299 | Interior Painting | Sarah Johnson | Completed | Low | 2024-01-13 | 2024-02-08 | 2024-02-08 | 100 | PVC Pipes | Downtown Avenue | 35337.61 | 21310.12 | No issues
C003 | Office Tower C | T936 | Roofing | John Miller | In Progress | Medium | 2024-08-23 | 2024-09-07 |  | 82 | Paint | Downtown Avenue | 11548.76 | 13785.5 | In progress
C001 | Residential Building A | T343 | Interior Painting | Emma White | Completed | Low | 2024-11-02 | 2024-11-19 | 2024-11-19 | 100 | Paint | Plot 21, Riverside | 11465.73 | 13714.7 | No issues
C003 | Office Tower C | T348 | Site Survey | Rachel Green | Completed | Medium | 2024-07-10 | 2024-07-22 | 2024-07-22 | 100 | Cement | Downtown Avenue | 9364.79 | 10506.42 | No issues
C001 | Residential Building A | T613 | Foundation Excavation | Emma White | Blocked | Medium | 2023-01-25 | 2023-02-07 |  | 0 | Steel Beams | Plot 21, Riverside | 48578.84 | 44759 | Not started
C001 | Residential Building A | T190 | Steel Framework Setup | Rachel Green | Completed | Medium | 2023-01-24 | 2023-02-05 | 2023-02-05 | 100 | Rebar | Plot 21, Riverside | 49920.92 | 48873.39 | No issues
C001 | Residential Building A | T435 | Foundation Excavation | Dave Brown | Blocked | Low | 2023-03-12 | 2023-04-04 |  | 0 | Rebar | Plot 21, Riverside | 27188.8 | 24925.73 | Not started
C004 | Warehouse D | T707 | Site Survey | Carlos Rivera | Not Started | Medium | 2023-11-19 | 2023-12-13 |  | 0 | Cement | Industrial Park | 49814.15 | 0 | Not started
C002 | Shopping Complex B | T643 | Interior Painting | Dave Brown | Completed | Medium | 2024-09-26 | 2024-10-07 | 2024-10-07 | 100 | Steel Beams | Market Street | 47780.14 | 81586.93 | No issues
C004 | Warehouse D | T737 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2024-12-10 | 2025-01-02 |  | 88 | Paint | Industrial Park | 14192.68 | 12481.9 | In progress
C004 | Warehouse D | T603 | Electrical Wiring | Dave Brown | Completed | Low | 2023-02-09 | 2023-02-22 | 2023-02-22 | 100 | Steel Beams | Industrial Park | 7404.47 | 5850.89 | No issues
C003 | Office Tower C | T960 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2024-07-28 | 2024-08-21 |  | 0 | Copper Wires | Downtown Avenue | 37904.44 | 28238.19 | Not started
C004 | Warehouse D | T451 | Foundation Excavation | Carlos Rivera | Completed | Low | 2023-03-13 | 2023-03-28 | 2023-03-28 | 100 | Rebar | Industrial Park | 13113.17 | 9178.75 | No issues
C002 | Shopping Complex B | T772 | Plumbing Installations | Sarah Johnson | In Progress | Medium | 2024-07-10 | 2024-07-31 |  | 2 | Rebar | Market Street | 46584.24 | 81041.07 | In progress
C001 | Residential Building A | T703 | Foundation Excavation | Rachel Green | Blocked | High | 2023-04-26 | 2023-05-16 |  | 0 | Copper Wires | Plot 21, Riverside | 7715.8 | 9183.92 | Not started
C003 | Office Tower C | T530 | Roofing | Carlos Rivera | In Progress | Low | 2023-02-24 | 2023-03-22 |  | 57 | Steel Beams | Downtown Avenue | 16014.13 | 11092.97 | In progress
C002 | Shopping Complex B | T758 | Plumbing Installations | Grace Allen | Not Started | Medium | 2024-11-13 | 2024-12-11 |  | 0 | Concrete | Market Street | 11053.11 | 0 | Not started
C002 | Shopping Complex B | T689 | Foundation Excavation | Emma White | Blocked | High | 2024-09-10 | 2024-09-22 |  | 0 | Steel Beams | Market Street | 37604.02 | 49893 | Not started
C003 | Office Tower C | T263 | Site Survey | Rachel Green | Not Started | High | 2024-08-18 | 2024-09-10 |  | 0 | Roofing Sheets | Downtown Avenue | 43863.84 | 0 | Not started
C001 | Residential Building A | T260 | Site Survey | Rachel Green | Blocked | Low | 2023-06-13 | 2023-06-22 |  | 0 | Cement | Plot 21, Riverside | 9704.78 | 11459.58 | Not started
C004 | Warehouse D | T835 | Steel Framework Setup | Emma White | In Progress | Low | 2024-07-12 | 2024-08-02 |  | 85 | Concrete | Industrial Park | 28235.05 | 27674.78 | In progress
C001 | Residential Building A | T238 | Foundation Excavation | Dave Brown | Not Started | Low | 2024-02-14 | 2024-02-27 |  | 0 | PVC Pipes | Plot 21, Riverside | 24391.75 | 0 | Not started
C002 | Shopping Complex B | T536 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-04-13 | 2024-05-02 |  | 0 | Paint | Market Street | 14697.29 | 38626.5 | Not started
C002 | Shopping Complex B | T778 | Plumbing Installations | Rachel Green | Completed | Low | 2023-11-22 | 2023-12-05 | 2023-12-05 | 100 | Paint | Market Street | 41612.9 | 63001.32 | No issues
C002 | Shopping Complex B | T802 | Roofing | Emma White | Blocked | Low | 2024-03-20 | 2024-04-02 |  | 0 | Concrete | Market Street | 15937.12 | 41352.51 | Not started
C003 | Office Tower C | T501 | Concrete Pouring | Mike Adams | Blocked | Medium | 2023-11-23 | 2023-12-05 |  | 0 | Paint | Downtown Avenue | 34137.64 | 27183.91 | Not started
C002 | Shopping Complex B | T532 | Interior Painting | Sarah Johnson | Completed | High | 2023-05-05 | 2023-05-30 | 2023-05-30 | 100 | Copper Wires | Market Street | 36144.51 | 49721.57 | No issues
C001 | Residential Building A | T410 | Interior Painting | Dave Brown | Completed | Medium | 2023-07-11 | 2023-08-07 | 2023-08-07 | 100 | Copper Wires | Plot 21, Riverside | 19490.94 | 22468.59 | No issues
C002 | Shopping Complex B | T339 | Site Survey | Carlos Rivera | Not Started | Medium | 2023-01-06 | 2023-01-25 |  | 0 | Concrete | Market Street | 25562.46 | 0 | Not started
C004 | Warehouse D | T824 | Plumbing Installations | Emma White | Completed | Low | 2023-09-20 | 2023-09-27 | 2023-09-27 | 100 | Paint | Industrial Park | 11856.02 | 8417.5 | No issues
C004 | Warehouse D | T195 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-12-28 | 2025-01-22 |  | 0 | Steel Beams | Industrial Park | 6614.62 | 0 | Not started
C004 | Warehouse D | T465 | Plumbing Installations | Sarah Johnson | Completed | Low | 2024-01-12 | 2024-01-24 | 2024-01-24 | 100 | Concrete | Industrial Park | 26770.68 | 30996.86 | No issues
C002 | Shopping Complex B | T305 | Site Survey | Rachel Green | Not Started | High | 2023-09-15 | 2023-10-03 |  | 0 | Copper Wires | Market Street | 39979.73 | 0 | Not started
C004 | Warehouse D | T139 | Steel Framework Setup | Emma White | Not Started | High | 2024-05-12 | 2024-05-19 |  | 0 | Copper Wires | Industrial Park | 28351.05 | 0 | Not started
C001 | Residential Building A | T803 | Interior Painting | Rachel Green | Blocked | High | 2024-06-27 | 2024-07-27 |  | 0 | Paint | Plot 21, Riverside | 8110.71 | 9149.35 | Not started
C002 | Shopping Complex B | T413 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2023-06-02 | 2023-06-26 |  | 67 | Concrete | Market Street | 49261.77 | 66360.83 | In progress
C003 | Office Tower C | T401 | Interior Painting | Mike Adams | Not Started | Medium | 2024-04-19 | 2024-05-10 |  | 0 | Paint | Downtown Avenue | 7027.45 | 0 | Not started
C003 | Office Tower C | T369 | Steel Framework Setup | Rachel Green | In Progress | Medium | 2024-01-16 | 2024-02-01 |  | 13 | Roofing Sheets | Downtown Avenue | 30872.96 | 19332.72 | In progress
C002 | Shopping Complex B | T297 | Electrical Wiring | Emma White | Completed | High | 2024-07-18 | 2024-08-03 | 2024-08-03 | 100 | Steel Beams | Market Street | 25313.28 | 42779.23 | No issues
C003 | Office Tower C | T284 | Interior Painting | Carlos Rivera | Completed | Low | 2024-03-18 | 2024-04-15 | 2024-04-15 | 100 | Roofing Sheets | Downtown Avenue | 38935.58 | 38899.83 | No issues
C001 | Residential Building A | T855 | Roofing | Sarah Johnson | Not Started | Low | 2023-06-10 | 2023-07-10 |  | 0 | Steel Beams | Plot 21, Riverside | 16412.93 | 0 | Not started
C001 | Residential Building A | T819 | Site Survey | Carlos Rivera | In Progress | High | 2023-05-04 | 2023-05-13 |  | 85 | Roofing Sheets | Plot 21, Riverside | 8673.46 | 9492.07 | In progress
C001 | Residential Building A | T415 | Electrical Wiring | John Miller | Completed | Medium | 2023-05-07 | 2023-05-19 | 2023-05-19 | 100 | Rebar | Plot 21, Riverside | 36652.29 | 38795.43 | No issues
C001 | Residential Building A | T105 | Roofing | Dave Brown | Blocked | Low | 2023-01-10 | 2023-02-07 |  | 0 | PVC Pipes | Plot 21, Riverside | 41664.2 | 36160.75 | Not started
C002 | Shopping Complex B | T989 | Plumbing Installations | Carlos Rivera | Completed | Low | 2023-07-10 | 2023-07-28 | 2023-07-28 | 100 | Paint | Market Street | 19835.08 | 41715.96 | No issues
C002 | Shopping Complex B | T526 | Interior Painting | Sarah Johnson | Blocked | High | 2024-09-15 | 2024-09-25 |  | 0 | Copper Wires | Market Street | 22779.87 | 48759.92 | Not started
C002 | Shopping Complex B | T122 | Site Survey | Sarah Johnson | Blocked | High | 2024-06-19 | 2024-07-04 |  | 0 | Steel Beams | Market Street | 10146.14 | 31885.06 | Not started
C001 | Residential Building A | T589 | Roofing | John Miller | Not Started | High | 2023-07-28 | 2023-08-13 |  | 0 | Paint | Plot 21, Riverside | 47358.76 | 0 | Not started
C003 | Office Tower C | T998 | Site Survey | Dave Brown | In Progress | Medium | 2023-01-07 | 2023-01-14 |  | 92 | Copper Wires | Downtown Avenue | 40119.28 | 29792.67 | In progress
C003 | Office Tower C | T941 | Steel Framework Setup | Grace Allen | Not Started | Low | 2024-11-23 | 2024-12-05 |  | 0 | Rebar | Downtown Avenue | 48609.01 | 0 | Not started
C004 | Warehouse D | T358 | Interior Painting | Grace Allen | Blocked | High | 2023-11-08 | 2023-12-03 |  | 0 | Steel Beams | Industrial Park | 11047.07 | 12911.04 | Not started
C001 | Residential Building A | T678 | Interior Painting | Dave Brown | Not Started | Low | 2024-04-18 | 2024-05-09 |  | 0 | Cement | Plot 21, Riverside | 29305.95 | 0 | Not started
C001 | Residential Building A | T683 | Site Survey | Carlos Rivera | Not Started | High | 2023-02-01 | 2023-02-28 |  | 0 | PVC Pipes | Plot 21, Riverside | 8800.24 | 0 | Not started
C004 | Warehouse D | T171 | Site Survey | Grace Allen | Not Started | Medium | 2023-04-13 | 2023-05-03 |  | 0 | PVC Pipes | Industrial Park | 46393.64 | 0 | Not started
C002 | Shopping Complex B | T567 | Plumbing Installations | John Miller | Blocked | Low | 2024-12-27 | 2025-01-26 |  | 0 | Concrete | Market Street | 32547.9 | 57382.4 | Not started
C003 | Office Tower C | T601 | Plumbing Installations | Grace Allen | Completed | High | 2024-03-12 | 2024-04-02 | 2024-04-02 | 100 | PVC Pipes | Downtown Avenue | 11718.67 | 7875.42 | No issues
C002 | Shopping Complex B | T911 | Site Survey | Carlos Rivera | Completed | High | 2024-01-06 | 2024-02-03 | 2024-02-03 | 100 | Rebar | Market Street | 20488.57 | 49165.56 | No issues
C001 | Residential Building A | T891 | Electrical Wiring | Rachel Green | Completed | Low | 2024-06-19 | 2024-07-05 | 2024-07-05 | 100 | Rebar | Plot 21, Riverside | 27734.49 | 17767.85 | No issues
C001 | Residential Building A | T406 | Site Survey | Rachel Green | Completed | Low | 2023-06-12 | 2023-06-22 | 2023-06-22 | 100 | Cement | Plot 21, Riverside | 13234.27 | 12695.49 | No issues
C003 | Office Tower C | T599 | Electrical Wiring | Emma White | Completed | Medium | 2023-10-07 | 2023-11-05 | 2023-11-05 | 100 | Steel Beams | Downtown Avenue | 9131.05 | 5718.52 | No issues
C001 | Residential Building A | T535 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2024-04-08 | 2024-04-22 |  | 0 | PVC Pipes | Plot 21, Riverside | 38868.71 | 0 | Not started
C001 | Residential Building A | T270 | Interior Painting | Carlos Rivera | Blocked | High | 2023-02-09 | 2023-03-05 |  | 0 | Concrete | Plot 21, Riverside | 8091.37 | 6883.86 | Not started
C002 | Shopping Complex B | T312 | Electrical Wiring | Carlos Rivera | Completed | Low | 2023-08-05 | 2023-09-03 | 2023-09-03 | 100 | Cement | Market Street | 29266.68 | 49205.31 | No issues
C003 | Office Tower C | T664 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-05-23 | 2024-06-12 |  | 0 | Roofing Sheets | Downtown Avenue | 20383.42 | 0 | Not started
C001 | Residential Building A | T441 | Concrete Pouring | Mike Adams | Not Started | Medium | 2024-04-14 | 2024-04-23 |  | 0 | Paint | Plot 21, Riverside | 26970.91 | 0 | Not started
C001 | Residential Building A | T426 | Concrete Pouring | Carlos Rivera | Completed | Low | 2023-08-25 | 2023-09-03 | 2023-09-03 | 100 | PVC Pipes | Plot 21, Riverside | 16318.74 | 16284.88 | No issues
C003 | Office Tower C | T154 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-08-23 | 2024-09-03 |  | 96 | Rebar | Downtown Avenue | 40828.9 | 43315.25 | In progress
C004 | Warehouse D | T698 | Roofing | John Miller | Not Started | High | 2024-03-16 | 2024-03-27 |  | 0 | Copper Wires | Industrial Park | 28915 | 0 | Not started
C004 | Warehouse D | T970 | Concrete Pouring | Carlos Rivera | Not Started | High | 2024-07-01 | 2024-07-12 |  | 0 | Concrete | Industrial Park | 41727.53 | 0 | Not started
C004 | Warehouse D | T803 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2024-03-01 | 2024-03-08 |  | 47 | Copper Wires | Industrial Park | 20634.27 | 23506.29 | In progress
C004 | Warehouse D | T759 | Plumbing Installations | Rachel Green | Not Started | High | 2023-04-05 | 2023-04-15 |  | 0 | Cement | Industrial Park | 27848.88 | 0 | Not started
C003 | Office Tower C | T398 | Electrical Wiring | Carlos Rivera | In Progress | Medium | 2023-06-09 | 2023-06-19 |  | 4 | Rebar | Downtown Avenue | 31967.02 | 25176.77 | In progress
C004 | Warehouse D | T968 | Concrete Pouring | Sarah Johnson | Completed | Low | 2023-05-26 | 2023-06-20 | 2023-06-20 | 100 | Paint | Industrial Park | 40180.85 | 36229.32 | No issues
C003 | Office Tower C | T705 | Plumbing Installations | Carlos Rivera | In Progress | High | 2023-03-24 | 2023-04-22 |  | 48 | Concrete | Downtown Avenue | 16795.59 | 16157.1 | In progress
C004 | Warehouse D | T141 | Interior Painting | Emma White | Blocked | High | 2023-01-10 | 2023-01-31 |  | 0 | Paint | Industrial Park | 37931.03 | 23301.7 | Not started
C001 | Residential Building A | T530 | Interior Painting | John Miller | Completed | High | 2023-11-11 | 2023-12-09 | 2023-12-09 | 100 | Roofing Sheets | Plot 21, Riverside | 21665.07 | 21228.44 | No issues
C003 | Office Tower C | T315 | Roofing | Grace Allen | In Progress | Low | 2023-04-04 | 2023-04-22 |  | 41 | Rebar | Downtown Avenue | 35509.8 | 21444.18 | In progress
C004 | Warehouse D | T578 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-10-18 | 2024-11-11 | 2024-11-11 | 100 | Copper Wires | Industrial Park | 26188.29 | 25945.88 | No issues
C002 | Shopping Complex B | T976 | Steel Framework Setup | Mike Adams | Completed | Low | 2023-05-18 | 2023-06-08 | 2023-06-08 | 100 | Roofing Sheets | Market Street | 29870.84 | 44492.95 | No issues
C001 | Residential Building A | T936 | Interior Painting | Dave Brown | Not Started | High | 2024-10-17 | 2024-10-28 |  | 0 | Concrete | Plot 21, Riverside | 49950.97 | 0 | Not started
C002 | Shopping Complex B | T546 | Site Survey | Emma White | Blocked | High | 2023-03-11 | 2023-04-09 |  | 0 | Copper Wires | Market Street | 13310.12 | 35291.82 | Not started
C002 | Shopping Complex B | T595 | Foundation Excavation | Emma White | Blocked | Low | 2024-03-17 | 2024-04-12 |  | 0 | Concrete | Market Street | 7210 | 31435.07 | Not started
C004 | Warehouse D | T468 | Foundation Excavation | Emma White | Not Started | High | 2023-03-27 | 2023-04-24 |  | 0 | Paint | Industrial Park | 36435.26 | 0 | Not started
C001 | Residential Building A | T340 | Plumbing Installations | Grace Allen | Not Started | Low | 2023-01-08 | 2023-01-30 |  | 0 | Rebar | Plot 21, Riverside | 28755.18 | 0 | Not started
C003 | Office Tower C | T646 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2024-01-12 | 2024-02-08 |  | 0 | Cement | Downtown Avenue | 44970 | 0 | Not started
C001 | Residential Building A | T836 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2023-06-28 | 2023-07-06 |  | 0 | Steel Beams | Plot 21, Riverside | 31521.69 | 0 | Not started
C003 | Office Tower C | T503 | Electrical Wiring | John Miller | Completed | Medium | 2023-05-26 | 2023-06-08 | 2023-06-08 | 100 | PVC Pipes | Downtown Avenue | 9005.24 | 7030.48 | No issues
C004 | Warehouse D | T154 | Concrete Pouring | Mike Adams | Not Started | High | 2023-12-28 | 2024-01-09 |  | 0 | Cement | Industrial Park | 9120.62 | 0 | Not started
C001 | Residential Building A | T113 | Interior Painting | Carlos Rivera | Blocked | High | 2023-05-01 | 2023-05-27 |  | 0 | PVC Pipes | Plot 21, Riverside | 11325.5 | 13578.88 | Not started
C004 | Warehouse D | T956 | Roofing | John Miller | Not Started | Low | 2024-09-27 | 2024-10-19 |  | 0 | Copper Wires | Industrial Park | 28304.08 | 0 | Not started
C003 | Office Tower C | T797 | Plumbing Installations | Emma White | In Progress | High | 2023-01-05 | 2023-01-28 |  | 77 | Rebar | Downtown Avenue | 21309.18 | 17853.02 | In progress
C002 | Shopping Complex B | T988 | Site Survey | Rachel Green | Completed | Low | 2024-09-09 | 2024-10-02 | 2024-10-02 | 100 | Cement | Market Street | 28184.85 | 59242.31 | No issues
C002 | Shopping Complex B | T937 | Steel Framework Setup | Grace Allen | Not Started | High | 2024-02-11 | 2024-03-01 |  | 0 | Roofing Sheets | Market Street | 24350.83 | 0 | Not started
C002 | Shopping Complex B | T207 | Plumbing Installations | Dave Brown | Completed | Medium | 2024-09-25 | 2024-10-07 | 2024-10-07 | 100 | Rebar | Market Street | 5094.91 | 28878.04 | No issues
C004 | Warehouse D | T179 | Plumbing Installations | Emma White | In Progress | Low | 2023-07-10 | 2023-07-28 |  | 12 | Concrete | Industrial Park | 39120.64 | 44185.79 | In progress
C002 | Shopping Complex B | T362 | Roofing | Grace Allen | Blocked | Medium | 2023-01-04 | 2023-01-28 |  | 0 | Cement | Market Street | 36274.39 | 64924.99 | Not started
C001 | Residential Building A | T970 | Site Survey | John Miller | Not Started | Medium | 2023-01-02 | 2023-01-15 |  | 0 | Paint | Plot 21, Riverside | 28295.09 | 0 | Not started
C002 | Shopping Complex B | T960 | Site Survey | Rachel Green | Not Started | Low | 2024-09-06 | 2024-09-20 |  | 0 | Steel Beams | Market Street | 38999.06 | 0 | Not started
C001 | Residential Building A | T406 | Interior Painting | Emma White | Blocked | High | 2024-10-18 | 2024-11-01 |  | 0 | Steel Beams | Plot 21, Riverside | 41998.56 | 43850.13 | Not started
C001 | Residential Building A | T504 | Steel Framework Setup | John Miller | Completed | Low | 2024-05-22 | 2024-06-08 | 2024-06-08 | 100 | Rebar | Plot 21, Riverside | 20565.04 | 21779.32 | No issues
C002 | Shopping Complex B | T373 | Electrical Wiring | Sarah Johnson | In Progress | High | 2024-06-19 | 2024-07-15 |  | 82 | Rebar | Market Street | 29598.03 | 43357.67 | In progress
C001 | Residential Building A | T555 | Foundation Excavation | John Miller | Not Started | High | 2024-07-06 | 2024-07-14 |  | 0 | Paint | Plot 21, Riverside | 18319.36 | 0 | Not started
C003 | Office Tower C | T905 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2023-10-26 | 2023-11-03 | 2023-11-03 | 100 | Roofing Sheets | Downtown Avenue | 28709.09 | 30519.83 | No issues
C003 | Office Tower C | T173 | Roofing | Rachel Green | Blocked | Medium | 2024-03-08 | 2024-03-30 |  | 0 | Roofing Sheets | Downtown Avenue | 48884.66 | 54592.33 | Not started
C003 | Office Tower C | T926 | Concrete Pouring | Rachel Green | In Progress | Low | 2024-02-07 | 2024-02-16 |  | 22 | Rebar | Downtown Avenue | 37812.38 | 31078.22 | In progress
C002 | Shopping Complex B | T699 | Steel Framework Setup | Rachel Green | Completed | Medium | 2023-04-27 | 2023-05-20 | 2023-05-20 | 100 | PVC Pipes | Market Street | 36450.74 | 67937.86 | No issues
C001 | Residential Building A | T358 | Plumbing Installations | Carlos Rivera | Not Started | High | 2023-11-23 | 2023-12-04 |  | 0 | PVC Pipes | Plot 21, Riverside | 18921.25 | 0 | Not started
C004 | Warehouse D | T600 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2023-09-17 | 2023-10-04 |  | 0 | Cement | Industrial Park | 34840.76 | 0 | Not started
C002 | Shopping Complex B | T635 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2023-10-06 | 2023-10-30 |  | 0 | Copper Wires | Market Street | 42682.37 | 58168.42 | Not started
C001 | Residential Building A | T679 | Foundation Excavation | Carlos Rivera | Completed | High | 2023-04-06 | 2023-04-24 | 2023-04-24 | 100 | PVC Pipes | Plot 21, Riverside | 25073.79 | 15982.92 | No issues
C001 | Residential Building A | T854 | Roofing | John Miller | Not Started | High | 2024-08-28 | 2024-09-22 |  | 0 | Roofing Sheets | Plot 21, Riverside | 37447.86 | 0 | Not started
C001 | Residential Building A | T997 | Foundation Excavation | John Miller | In Progress | Low | 2023-01-02 | 2023-01-24 |  | 90 | Rebar | Plot 21, Riverside | 5165.53 | 3424.96 | In progress
C004 | Warehouse D | T763 | Interior Painting | John Miller | Blocked | Medium | 2023-02-10 | 2023-03-05 |  | 0 | Rebar | Industrial Park | 43686.81 | 42793.92 | Not started
C003 | Office Tower C | T620 | Roofing | Sarah Johnson | In Progress | Low | 2024-10-08 | 2024-10-16 |  | 71 | Steel Beams | Downtown Avenue | 25592.4 | 27140.25 | In progress
C002 | Shopping Complex B | T508 | Steel Framework Setup | John Miller | Completed | Low | 2024-07-24 | 2024-08-19 | 2024-08-19 | 100 | PVC Pipes | Market Street | 49684.49 | 66935.7 | No issues
C004 | Warehouse D | T434 | Interior Painting | Emma White | Blocked | High | 2024-08-06 | 2024-09-02 |  | 0 | Roofing Sheets | Industrial Park | 12065.86 | 9081.49 | Not started
C002 | Shopping Complex B | T537 | Interior Painting | Emma White | Not Started | Medium | 2024-09-06 | 2024-09-24 |  | 0 | Rebar | Market Street | 49515.07 | 0 | Not started
C002 | Shopping Complex B | T369 | Concrete Pouring | John Miller | Not Started | High | 2023-05-22 | 2023-05-30 |  | 0 | Paint | Market Street | 49200.83 | 0 | Not started
C003 | Office Tower C | T685 | Electrical Wiring | John Miller | In Progress | Medium | 2023-11-20 | 2023-12-09 |  | 12 | Steel Beams | Downtown Avenue | 16383 | 11841.32 | In progress
C002 | Shopping Complex B | T672 | Site Survey | Carlos Rivera | In Progress | High | 2024-04-01 | 2024-04-10 |  | 46 | Paint | Market Street | 38899.23 | 57827.01 | In progress
C004 | Warehouse D | T434 | Steel Framework Setup | Mike Adams | Completed | Low | 2023-12-25 | 2024-01-17 | 2024-01-17 | 100 | Rebar | Industrial Park | 17750.13 | 17641.31 | No issues
C003 | Office Tower C | T507 | Plumbing Installations | Dave Brown | Completed | Low | 2024-05-14 | 2024-05-21 | 2024-05-21 | 100 | Steel Beams | Downtown Avenue | 25058.28 | 28992.5 | No issues
C003 | Office Tower C | T243 | Steel Framework Setup | Dave Brown | Blocked | Low | 2023-05-17 | 2023-06-07 |  | 0 | Steel Beams | Downtown Avenue | 38602.5 | 28083.71 | Not started
C001 | Residential Building A | T391 | Roofing | John Miller | Completed | Medium | 2023-06-07 | 2023-07-06 | 2023-07-06 | 100 | Roofing Sheets | Plot 21, Riverside | 33454.7 | 35076.16 | No issues
C004 | Warehouse D | T946 | Roofing | Emma White | Blocked | High | 2024-03-14 | 2024-03-24 |  | 0 | Roofing Sheets | Industrial Park | 35292.82 | 26264.96 | Not started
C004 | Warehouse D | T260 | Foundation Excavation | Grace Allen | Completed | Low | 2024-11-17 | 2024-12-08 | 2024-12-08 | 100 | Steel Beams | Industrial Park | 42245.44 | 30731.64 | No issues
C004 | Warehouse D | T445 | Electrical Wiring | Emma White | Blocked | High | 2023-12-26 | 2024-01-25 |  | 0 | Cement | Industrial Park | 19808.01 | 15772.05 | Not started
C001 | Residential Building A | T493 | Interior Painting | Mike Adams | Completed | Medium | 2024-04-17 | 2024-04-30 | 2024-04-30 | 100 | Rebar | Plot 21, Riverside | 23087.62 | 14398.27 | No issues
C003 | Office Tower C | T140 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-06-28 | 2023-07-09 |  | 54 | Cement | Downtown Avenue | 48053.04 | 40741.36 | In progress
C004 | Warehouse D | T965 | Concrete Pouring | Grace Allen | In Progress | High | 2024-03-03 | 2024-03-11 |  | 15 | Concrete | Industrial Park | 34359.46 | 30638.91 | In progress
C002 | Shopping Complex B | T562 | Steel Framework Setup | Dave Brown | Not Started | Low | 2024-08-19 | 2024-09-01 |  | 0 | Steel Beams | Market Street | 33397.63 | 0 | Not started
C002 | Shopping Complex B | T129 | Electrical Wiring | Sarah Johnson | In Progress | High | 2024-06-10 | 2024-06-30 |  | 77 | Copper Wires | Market Street | 45369.85 | 73101.28 | In progress
C004 | Warehouse D | T503 | Steel Framework Setup | John Miller | Completed | Medium | 2024-10-15 | 2024-11-05 | 2024-11-05 | 100 | Rebar | Industrial Park | 28323.78 | 31965.35 | No issues
C003 | Office Tower C | T131 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-05-23 | 2023-06-20 |  | 0 | Paint | Downtown Avenue | 39277.32 | 0 | Not started
C002 | Shopping Complex B | T843 | Site Survey | Mike Adams | Not Started | High | 2023-10-03 | 2023-10-21 |  | 0 | Paint | Market Street | 15937.71 | 0 | Not started
C001 | Residential Building A | T743 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2024-09-06 | 2024-09-27 |  | 0 | Steel Beams | Plot 21, Riverside | 46012.07 | 52500.36 | Not started
C004 | Warehouse D | T360 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2024-12-03 | 2025-01-02 |  | 70 | Cement | Industrial Park | 33918.39 | 26850.56 | In progress
C002 | Shopping Complex B | T786 | Concrete Pouring | John Miller | In Progress | Low | 2024-11-18 | 2024-11-26 |  | 19 | Rebar | Market Street | 31176.83 | 48307.12 | In progress
C003 | Office Tower C | T801 | Steel Framework Setup | Mike Adams | Blocked | Low | 2023-08-20 | 2023-09-18 |  | 0 | Steel Beams | Downtown Avenue | 23712.52 | 15830.12 | Not started
C002 | Shopping Complex B | T194 | Foundation Excavation | John Miller | Not Started | Low | 2024-04-22 | 2024-05-02 |  | 0 | Copper Wires | Market Street | 21374.08 | 0 | Not started
C004 | Warehouse D | T728 | Roofing | Dave Brown | Completed | High | 2023-01-22 | 2023-02-06 | 2023-02-06 | 100 | Paint | Industrial Park | 46016.73 | 38236.83 | No issues
C002 | Shopping Complex B | T259 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-02-14 | 2024-02-24 | 2024-02-24 | 100 | Roofing Sheets | Market Street | 7139.64 | 31948.95 | No issues
C004 | Warehouse D | T737 | Site Survey | Carlos Rivera | Completed | Low | 2023-05-03 | 2023-05-15 | 2023-05-15 | 100 | Roofing Sheets | Industrial Park | 9402.66 | 6689.62 | No issues
C003 | Office Tower C | T480 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-11-11 | 2024-11-24 |  | 0 | Rebar | Downtown Avenue | 23353.47 | 0 | Not started
C004 | Warehouse D | T668 | Concrete Pouring | Carlos Rivera | Completed | High | 2024-03-13 | 2024-04-05 | 2024-04-05 | 100 | Rebar | Industrial Park | 42182.39 | 32542.07 | No issues
C003 | Office Tower C | T970 | Site Survey | Sarah Johnson | Not Started | High | 2024-11-09 | 2024-11-19 |  | 0 | Concrete | Downtown Avenue | 35223.37 | 0 | Not started
C003 | Office Tower C | T219 | Site Survey | Emma White | Completed | High | 2024-02-21 | 2024-03-19 | 2024-03-19 | 100 | Copper Wires | Downtown Avenue | 21425.39 | 21202.17 | No issues
C004 | Warehouse D | T769 | Interior Painting | Mike Adams | Completed | Low | 2023-02-11 | 2023-03-08 | 2023-03-08 | 100 | Paint | Industrial Park | 5825.93 | 5669.11 | No issues
C003 | Office Tower C | T591 | Plumbing Installations | Carlos Rivera | Completed | Low | 2023-12-20 | 2024-01-18 | 2024-01-18 | 100 | Copper Wires | Downtown Avenue | 47758.09 | 52980.39 | No issues
C002 | Shopping Complex B | T885 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2024-12-02 | 2024-12-27 |  | 71 | Rebar | Market Street | 28096.9 | 50768.38 | In progress
C001 | Residential Building A | T603 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-06-19 | 2024-07-07 |  | 0 | Copper Wires | Plot 21, Riverside | 42784.74 | 0 | Not started
C004 | Warehouse D | T659 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-08-13 | 2023-09-02 |  | 67 | Steel Beams | Industrial Park | 11212.56 | 9523.39 | In progress
C004 | Warehouse D | T119 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-01-12 | 2023-01-27 |  | 53 | Rebar | Industrial Park | 45849.34 | 42622.96 | In progress
C003 | Office Tower C | T831 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-10-16 | 2024-10-26 | 2024-10-26 | 100 | Paint | Downtown Avenue | 11264.4 | 11021.28 | No issues
C004 | Warehouse D | T517 | Electrical Wiring | Dave Brown | In Progress | Medium | 2024-02-10 | 2024-02-18 |  | 9 | Copper Wires | Industrial Park | 28172.12 | 19295.96 | In progress
C004 | Warehouse D | T941 | Foundation Excavation | Rachel Green | Blocked | High | 2024-05-26 | 2024-06-14 |  | 0 | Cement | Industrial Park | 29215.44 | 23711.94 | Not started
C001 | Residential Building A | T935 | Plumbing Installations | Mike Adams | Completed | Low | 2024-04-13 | 2024-05-11 | 2024-05-11 | 100 | Copper Wires | Plot 21, Riverside | 35887.84 | 25263.81 | No issues
C002 | Shopping Complex B | T565 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2024-05-01 | 2024-05-25 | 2024-05-25 | 100 | Copper Wires | Market Street | 5394.66 | 29480.29 | No issues
C002 | Shopping Complex B | T105 | Interior Painting | Rachel Green | Not Started | Medium | 2024-02-07 | 2024-02-21 |  | 0 | Paint | Market Street | 14601.5 | 0 | Not started
C003 | Office Tower C | T610 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2024-01-24 | 2024-02-05 |  | 0 | Steel Beams | Downtown Avenue | 19571.26 | 0 | Not started
C002 | Shopping Complex B | T824 | Electrical Wiring | Rachel Green | Completed | High | 2024-09-28 | 2024-10-05 | 2024-10-05 | 100 | Rebar | Market Street | 18397.95 | 45838.24 | No issues
C002 | Shopping Complex B | T218 | Steel Framework Setup | John Miller | Blocked | Low | 2024-12-19 | 2025-01-16 |  | 0 | Roofing Sheets | Market Street | 13606.14 | 40716.81 | Not started
C003 | Office Tower C | T257 | Roofing | Dave Brown | Blocked | Medium | 2023-03-20 | 2023-04-06 |  | 0 | Paint | Downtown Avenue | 49247.57 | 53485.58 | Not started
C003 | Office Tower C | T728 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2024-11-09 | 2024-12-06 |  | 60 | Steel Beams | Downtown Avenue | 6797.59 | 7811.79 | In progress
C002 | Shopping Complex B | T886 | Concrete Pouring | Mike Adams | In Progress | Medium | 2024-08-21 | 2024-09-17 |  | 88 | Concrete | Market Street | 6417.32 | 32159.03 | In progress
C001 | Residential Building A | T319 | Site Survey | John Miller | In Progress | Low | 2023-04-13 | 2023-05-08 |  | 58 | Concrete | Plot 21, Riverside | 7849.47 | 4884.99 | In progress
C004 | Warehouse D | T921 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-06-13 | 2024-06-21 |  | 0 | Paint | Industrial Park | 24405.7 | 24580.64 | Not started
C001 | Residential Building A | T878 | Concrete Pouring | John Miller | Blocked | Medium | 2024-05-06 | 2024-05-31 |  | 0 | Rebar | Plot 21, Riverside | 29760.07 | 31854.59 | Not started
C003 | Office Tower C | T346 | Site Survey | Mike Adams | Blocked | High | 2024-07-28 | 2024-08-23 |  | 0 | Cement | Downtown Avenue | 45102.16 | 28750.53 | Not started
C004 | Warehouse D | T155 | Interior Painting | Dave Brown | In Progress | Medium | 2024-10-04 | 2024-10-11 |  | 49 | Roofing Sheets | Industrial Park | 34744.23 | 22501.92 | In progress
C003 | Office Tower C | T204 | Concrete Pouring | Emma White | Completed | High | 2024-02-07 | 2024-02-26 | 2024-02-26 | 100 | Rebar | Downtown Avenue | 7570.73 | 6898.11 | No issues
C003 | Office Tower C | T486 | Site Survey | Dave Brown | Not Started | Medium | 2024-04-09 | 2024-04-23 |  | 0 | Roofing Sheets | Downtown Avenue | 14358.97 | 0 | Not started
C004 | Warehouse D | T495 | Foundation Excavation | Rachel Green | Not Started | Medium | 2024-01-10 | 2024-01-23 |  | 0 | PVC Pipes | Industrial Park | 45435.25 | 0 | Not started
C004 | Warehouse D | T212 | Plumbing Installations | Grace Allen | In Progress | Medium | 2023-11-20 | 2023-11-28 |  | 38 | Steel Beams | Industrial Park | 30691.28 | 22299.4 | In progress
C001 | Residential Building A | T728 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-01-28 | 2023-02-19 |  | 0 | Rebar | Plot 21, Riverside | 35046.62 | 0 | Not started
C001 | Residential Building A | T392 | Plumbing Installations | Emma White | Not Started | High | 2024-02-02 | 2024-02-23 |  | 0 | PVC Pipes | Plot 21, Riverside | 10248.36 | 0 | Not started
C004 | Warehouse D | T298 | Foundation Excavation | John Miller | Blocked | High | 2023-08-27 | 2023-09-18 |  | 0 | Copper Wires | Industrial Park | 21743.36 | 21711.8 | Not started
C004 | Warehouse D | T292 | Foundation Excavation | Grace Allen | In Progress | Low | 2023-01-06 | 2023-01-20 |  | 36 | Concrete | Industrial Park | 29945.41 | 31346.43 | In progress
C003 | Office Tower C | T330 | Roofing | Emma White | In Progress | Low | 2023-10-16 | 2023-11-02 |  | 32 | PVC Pipes | Downtown Avenue | 19658.85 | 22790.21 | In progress
C003 | Office Tower C | T341 | Plumbing Installations | Emma White | Blocked | Medium | 2024-09-14 | 2024-09-25 |  | 0 | Cement | Downtown Avenue | 8155.16 | 7346.09 | Not started
C002 | Shopping Complex B | T402 | Roofing | Sarah Johnson | Not Started | Medium | 2023-10-18 | 2023-10-29 |  | 0 | PVC Pipes | Market Street | 28868.08 | 0 | Not started
C001 | Residential Building A | T286 | Steel Framework Setup | Emma White | Completed | Low | 2023-12-09 | 2024-01-07 | 2024-01-07 | 100 | Paint | Plot 21, Riverside | 29811.06 | 29797.85 | No issues
C002 | Shopping Complex B | T273 | Roofing | Mike Adams | Blocked | Medium | 2024-01-05 | 2024-01-31 |  | 0 | Steel Beams | Market Street | 27711.33 | 57646.55 | Not started
C003 | Office Tower C | T120 | Interior Painting | John Miller | In Progress | High | 2024-06-05 | 2024-06-17 |  | 81 | PVC Pipes | Downtown Avenue | 30653.42 | 27723.54 | In progress
C003 | Office Tower C | T655 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-01-06 | 2024-02-02 |  | 89 | Paint | Downtown Avenue | 33740.04 | 35808.18 | In progress
C002 | Shopping Complex B | T479 | Site Survey | John Miller | In Progress | High | 2023-07-26 | 2023-08-11 |  | 40 | Copper Wires | Market Street | 36612.25 | 52553.51 | In progress
C001 | Residential Building A | T641 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-10-11 | 2023-10-20 |  | 0 | Cement | Plot 21, Riverside | 14086.42 | 8812.18 | Not started
C004 | Warehouse D | T593 | Electrical Wiring | Sarah Johnson | Completed | High | 2024-06-27 | 2024-07-11 | 2024-07-11 | 100 | Steel Beams | Industrial Park | 34892.9 | 34151.69 | No issues
C004 | Warehouse D | T865 | Concrete Pouring | Mike Adams | Not Started | High | 2023-01-26 | 2023-02-07 |  | 0 | Cement | Industrial Park | 5736.21 | 0 | Not started
C002 | Shopping Complex B | T710 | Roofing | Mike Adams | Completed | High | 2023-06-06 | 2023-06-24 | 2023-06-24 | 100 | Paint | Market Street | 25772.49 | 43461.8 | No issues
C003 | Office Tower C | T784 | Foundation Excavation | John Miller | Blocked | Medium | 2024-07-07 | 2024-07-23 |  | 0 | PVC Pipes | Downtown Avenue | 48012.41 | 32417.15 | Not started
C003 | Office Tower C | T925 | Site Survey | Sarah Johnson | Completed | Medium | 2024-05-05 | 2024-05-31 | 2024-05-31 | 100 | PVC Pipes | Downtown Avenue | 26927.41 | 20187.13 | No issues
C003 | Office Tower C | T127 | Electrical Wiring | Dave Brown | Not Started | High | 2023-03-27 | 2023-04-15 |  | 0 | Roofing Sheets | Downtown Avenue | 23763.4 | 0 | Not started
C003 | Office Tower C | T460 | Foundation Excavation | Grace Allen | Not Started | High | 2024-04-18 | 2024-05-13 |  | 0 | Roofing Sheets | Downtown Avenue | 5125.4 | 0 | Not started
C003 | Office Tower C | T479 | Interior Painting | Emma White | Not Started | Low | 2024-09-11 | 2024-09-24 |  | 0 | Concrete | Downtown Avenue | 5387.13 | 0 | Not started
C003 | Office Tower C | T229 | Interior Painting | Dave Brown | Completed | Low | 2023-09-05 | 2023-09-27 | 2023-09-27 | 100 | Steel Beams | Downtown Avenue | 22938.22 | 19048.42 | No issues
C004 | Warehouse D | T918 | Steel Framework Setup | Emma White | Completed | Medium | 2024-03-24 | 2024-04-10 | 2024-04-10 | 100 | Steel Beams | Industrial Park | 49089.19 | 45174.87 | No issues
C002 | Shopping Complex B | T153 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-11-01 | 2024-11-25 | 2024-11-25 | 100 | Steel Beams | Market Street | 24103.47 | 47519.85 | No issues
C003 | Office Tower C | T932 | Foundation Excavation | Mike Adams | Blocked | High | 2024-11-26 | 2024-12-05 |  | 0 | Roofing Sheets | Downtown Avenue | 19513.18 | 18377.36 | Not started
C002 | Shopping Complex B | T829 | Site Survey | Mike Adams | Blocked | Medium | 2023-06-26 | 2023-07-20 |  | 0 | Cement | Market Street | 43829.47 | 55745.93 | Not started
C003 | Office Tower C | T498 | Site Survey | Grace Allen | Completed | Medium | 2024-04-05 | 2024-04-25 | 2024-04-25 | 100 | Cement | Downtown Avenue | 15910.19 | 15687.82 | No issues
C004 | Warehouse D | T995 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2023-11-17 | 2023-12-13 |  | 42 | Copper Wires | Industrial Park | 38831.61 | 33192.47 | In progress
C003 | Office Tower C | T386 | Roofing | Dave Brown | In Progress | Medium | 2024-09-14 | 2024-10-12 |  | 4 | Cement | Downtown Avenue | 45270.81 | 47323.97 | In progress
C001 | Residential Building A | T720 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-02-28 | 2024-03-11 |  | 0 | Copper Wires | Plot 21, Riverside | 46535.55 | 0 | Not started
C003 | Office Tower C | T523 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2023-05-21 | 2023-05-28 |  | 20 | Cement | Downtown Avenue | 28630.62 | 26604.04 | In progress
C004 | Warehouse D | T100 | Electrical Wiring | Dave Brown | Not Started | High | 2023-07-23 | 2023-08-19 |  | 0 | Copper Wires | Industrial Park | 16017.89 | 0 | Not started
C004 | Warehouse D | T163 | Plumbing Installations | Mike Adams | Blocked | High | 2024-04-07 | 2024-05-07 |  | 0 | Cement | Industrial Park | 38334.05 | 35959.21 | Not started
C001 | Residential Building A | T318 | Site Survey | John Miller | Not Started | Low | 2024-10-09 | 2024-10-17 |  | 0 | Paint | Plot 21, Riverside | 32001.03 | 0 | Not started
C001 | Residential Building A | T763 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2023-01-02 | 2023-01-09 |  | 59 | Rebar | Plot 21, Riverside | 10678.87 | 7186 | In progress
C004 | Warehouse D | T642 | Site Survey | Dave Brown | Not Started | High | 2023-08-08 | 2023-08-23 |  | 0 | Steel Beams | Industrial Park | 9884.84 | 0 | Not started
C003 | Office Tower C | T928 | Plumbing Installations | Grace Allen | In Progress | High | 2023-01-09 | 2023-02-01 |  | 82 | Cement | Downtown Avenue | 20779.95 | 17877.24 | In progress
C004 | Warehouse D | T602 | Steel Framework Setup | John Miller | Blocked | Low | 2024-07-10 | 2024-07-31 |  | 0 | Rebar | Industrial Park | 28589.32 | 19826.3 | Not started
C002 | Shopping Complex B | T969 | Site Survey | Emma White | Completed | Low | 2023-09-12 | 2023-10-02 | 2023-10-02 | 100 | Copper Wires | Market Street | 30356.69 | 55166.08 | No issues
C003 | Office Tower C | T867 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-05-08 | 2024-05-27 |  | 0 | Paint | Downtown Avenue | 16606.18 | 13656.3 | Not started
C003 | Office Tower C | T226 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-06-14 | 2023-06-22 |  | 0 | Copper Wires | Downtown Avenue | 23719.78 | 0 | Not started
C002 | Shopping Complex B | T747 | Roofing | Emma White | In Progress | High | 2024-11-15 | 2024-12-15 |  | 47 | PVC Pipes | Market Street | 22566.86 | 50509.71 | In progress
C003 | Office Tower C | T807 | Foundation Excavation | Grace Allen | Not Started | Low | 2023-06-15 | 2023-06-27 |  | 0 | Copper Wires | Downtown Avenue | 49674.85 | 0 | Not started
C003 | Office Tower C | T684 | Foundation Excavation | Sarah Johnson | Completed | High | 2023-10-14 | 2023-10-30 | 2023-10-30 | 100 | Paint | Downtown Avenue | 21203.02 | 24191.93 | No issues
C002 | Shopping Complex B | T353 | Foundation Excavation | Emma White | Not Started | Low | 2024-11-18 | 2024-11-26 |  | 0 | PVC Pipes | Market Street | 28771.55 | 0 | Not started
C004 | Warehouse D | T848 | Plumbing Installations | John Miller | Blocked | Low | 2023-05-19 | 2023-06-09 |  | 0 | Cement | Industrial Park | 6169.59 | 5230.69 | Not started
C004 | Warehouse D | T366 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2023-01-12 | 2023-01-31 |  | 35 | Roofing Sheets | Industrial Park | 8869.34 | 9660.15 | In progress
C001 | Residential Building A | T783 | Interior Painting | Emma White | In Progress | Low | 2023-03-17 | 2023-04-04 |  | 24 | Concrete | Plot 21, Riverside | 39995.35 | 35383.9 | In progress
C004 | Warehouse D | T590 | Plumbing Installations | Dave Brown | Not Started | Medium | 2024-12-09 | 2024-12-18 |  | 0 | Cement | Industrial Park | 35586.81 | 0 | Not started
C001 | Residential Building A | T992 | Electrical Wiring | Rachel Green | Not Started | Low | 2023-02-19 | 2023-03-03 |  | 0 | Concrete | Plot 21, Riverside | 46313.38 | 0 | Not started
C004 | Warehouse D | T789 | Roofing | Dave Brown | In Progress | Low | 2023-02-21 | 2023-03-17 |  | 87 | Roofing Sheets | Industrial Park | 12795.14 | 10435.03 | In progress
C004 | Warehouse D | T439 | Foundation Excavation | Dave Brown | Completed | Medium | 2024-02-18 | 2024-03-14 | 2024-03-14 | 100 | Roofing Sheets | Industrial Park | 19353.4 | 12446.6 | No issues
C004 | Warehouse D | T106 | Site Survey | John Miller | In Progress | Low | 2023-06-06 | 2023-06-24 |  | 88 | Copper Wires | Industrial Park | 48006.97 | 45254.3 | In progress
C002 | Shopping Complex B | T628 | Roofing | Sarah Johnson | In Progress | Medium | 2023-07-28 | 2023-08-10 |  | 94 | Rebar | Market Street | 35750.72 | 64260.05 | In progress
C004 | Warehouse D | T403 | Roofing | Dave Brown | In Progress | High | 2023-10-24 | 2023-11-06 |  | 77 | Cement | Industrial Park | 5509.67 | 5554.55 | In progress
C001 | Residential Building A | T893 | Steel Framework Setup | Dave Brown | Not Started | Medium | 2024-06-18 | 2024-06-29 |  | 0 | Steel Beams | Plot 21, Riverside | 6893.27 | 0 | Not started
C004 | Warehouse D | T814 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-06-26 | 2024-07-03 |  | 0 | Rebar | Industrial Park | 44017.95 | 0 | Not started
C002 | Shopping Complex B | T341 | Electrical Wiring | Grace Allen | Not Started | High | 2024-04-11 | 2024-04-22 |  | 0 | PVC Pipes | Market Street | 14768.85 | 0 | Not started
C004 | Warehouse D | T435 | Electrical Wiring | Grace Allen | Not Started | Low | 2024-03-04 | 2024-03-28 |  | 0 | Concrete | Industrial Park | 48009.59 | 0 | Not started
C001 | Residential Building A | T311 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-02-25 | 2023-03-07 |  | 0 | PVC Pipes | Plot 21, Riverside | 33523.49 | 0 | Not started
C002 | Shopping Complex B | T325 | Plumbing Installations | Rachel Green | Blocked | Medium | 2024-06-25 | 2024-07-11 |  | 0 | Concrete | Market Street | 37963.21 | 55479.39 | Not started
C001 | Residential Building A | T870 | Plumbing Installations | Grace Allen | Completed | High | 2024-05-18 | 2024-06-16 | 2024-06-16 | 100 | Concrete | Plot 21, Riverside | 43693.06 | 44298.53 | No issues
C003 | Office Tower C | T328 | Plumbing Installations | Rachel Green | In Progress | High | 2023-09-03 | 2023-09-23 |  | 49 | PVC Pipes | Downtown Avenue | 38876.29 | 43306.73 | In progress
C004 | Warehouse D | T638 | Concrete Pouring | Emma White | In Progress | High | 2024-12-25 | 2025-01-09 |  | 71 | Steel Beams | Industrial Park | 37926.43 | 45006.57 | In progress
C004 | Warehouse D | T547 | Interior Painting | Carlos Rivera | Not Started | High | 2024-05-09 | 2024-05-26 |  | 0 | Concrete | Industrial Park | 21668.39 | 0 | Not started
C002 | Shopping Complex B | T276 | Site Survey | Emma White | Not Started | High | 2024-02-08 | 2024-02-17 |  | 0 | PVC Pipes | Market Street | 11621.43 | 0 | Not started
C003 | Office Tower C | T835 | Concrete Pouring | John Miller | Not Started | Low | 2023-09-16 | 2023-10-01 |  | 0 | Concrete | Downtown Avenue | 47774.48 | 0 | Not started
C001 | Residential Building A | T115 | Roofing | Carlos Rivera | Not Started | High | 2024-03-19 | 2024-03-26 |  | 0 | Concrete | Plot 21, Riverside | 21188.63 | 0 | Not started
C003 | Office Tower C | T906 | Concrete Pouring | Carlos Rivera | Not Started | High | 2024-10-26 | 2024-11-20 |  | 0 | Roofing Sheets | Downtown Avenue | 46772.06 | 0 | Not started
C001 | Residential Building A | T854 | Steel Framework Setup | Emma White | In Progress | High | 2023-02-08 | 2023-02-26 |  | 96 | Concrete | Plot 21, Riverside | 23172.88 | 16296.61 | In progress
C003 | Office Tower C | T674 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2024-05-01 | 2024-05-31 |  | 91 | Roofing Sheets | Downtown Avenue | 41389.66 | 37726.65 | In progress
C003 | Office Tower C | T927 | Concrete Pouring | Mike Adams | Not Started | High | 2023-02-15 | 2023-02-23 |  | 0 | Roofing Sheets | Downtown Avenue | 48648.1 | 0 | Not started
C003 | Office Tower C | T537 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-09-12 | 2024-10-05 |  | 0 | Copper Wires | Downtown Avenue | 6968.78 | 0 | Not started
C002 | Shopping Complex B | T646 | Roofing | Sarah Johnson | Blocked | Medium | 2024-10-15 | 2024-11-12 |  | 0 | Concrete | Market Street | 16677.01 | 40465.22 | Not started
C001 | Residential Building A | T740 | Site Survey | John Miller | Not Started | High | 2023-07-27 | 2023-08-20 |  | 0 | Concrete | Plot 21, Riverside | 43952.26 | 0 | Not started
C004 | Warehouse D | T533 | Roofing | Emma White | In Progress | High | 2023-04-01 | 2023-04-14 |  | 71 | Steel Beams | Industrial Park | 27590.55 | 24293.24 | In progress
C004 | Warehouse D | T884 | Concrete Pouring | Emma White | In Progress | Low | 2023-07-14 | 2023-07-28 |  | 54 | Copper Wires | Industrial Park | 47716.61 | 54684.04 | In progress
C004 | Warehouse D | T966 | Roofing | Rachel Green | Completed | Medium | 2023-06-10 | 2023-06-29 | 2023-06-29 | 100 | Roofing Sheets | Industrial Park | 48549.11 | 39273.87 | No issues
C002 | Shopping Complex B | T394 | Concrete Pouring | Carlos Rivera | Completed | Low | 2023-10-11 | 2023-10-29 | 2023-10-29 | 100 | Roofing Sheets | Market Street | 27971.89 | 43133.08 | No issues
C001 | Residential Building A | T727 | Site Survey | Mike Adams | Not Started | High | 2024-08-21 | 2024-09-10 |  | 0 | PVC Pipes | Plot 21, Riverside | 15862.09 | 0 | Not started
C002 | Shopping Complex B | T103 | Foundation Excavation | Emma White | Completed | Low | 2023-06-11 | 2023-07-10 | 2023-07-10 | 100 | Cement | Market Street | 14830.18 | 36153.21 | No issues
C004 | Warehouse D | T274 | Roofing | Rachel Green | Blocked | Low | 2024-08-04 | 2024-08-17 |  | 0 | Steel Beams | Industrial Park | 36551.05 | 30406.92 | Not started
C002 | Shopping Complex B | T718 | Electrical Wiring | John Miller | In Progress | High | 2024-03-14 | 2024-04-11 |  | 22 | PVC Pipes | Market Street | 28576.22 | 51350.72 | In progress
C004 | Warehouse D | T601 | Interior Painting | Emma White | Not Started | Low | 2024-05-01 | 2024-05-30 |  | 0 | PVC Pipes | Industrial Park | 6921.25 | 0 | Not started
C003 | Office Tower C | T398 | Roofing | Sarah Johnson | Completed | Medium | 2024-12-18 | 2025-01-02 | 2025-01-02 | 100 | Roofing Sheets | Downtown Avenue | 29640.33 | 23268.81 | No issues
C003 | Office Tower C | T275 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-05-20 | 2024-06-04 |  | 49 | Roofing Sheets | Downtown Avenue | 41702.89 | 42155.58 | In progress
C004 | Warehouse D | T935 | Foundation Excavation | Dave Brown | Completed | Medium | 2023-06-19 | 2023-07-01 | 2023-07-01 | 100 | Concrete | Industrial Park | 28303.43 | 17806.57 | No issues
C003 | Office Tower C | T794 | Plumbing Installations | Emma White | Not Started | High | 2023-01-25 | 2023-02-01 |  | 0 | Concrete | Downtown Avenue | 32060.5 | 0 | Not started
C001 | Residential Building A | T891 | Foundation Excavation | Rachel Green | In Progress | Medium | 2023-11-25 | 2023-12-23 |  | 52 | PVC Pipes | Plot 21, Riverside | 19670.16 | 17791.26 | In progress
C002 | Shopping Complex B | T866 | Plumbing Installations | Grace Allen | Not Started | Low | 2023-02-10 | 2023-03-09 |  | 0 | PVC Pipes | Market Street | 8709.09 | 0 | Not started
C003 | Office Tower C | T277 | Foundation Excavation | Carlos Rivera | Completed | High | 2024-02-12 | 2024-03-13 | 2024-03-13 | 100 | Copper Wires | Downtown Avenue | 39880.22 | 41589.83 | No issues
C001 | Residential Building A | T199 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2024-03-02 | 2024-03-28 | 2024-03-28 | 100 | PVC Pipes | Plot 21, Riverside | 16891.64 | 12549.65 | No issues
C003 | Office Tower C | T379 | Foundation Excavation | Mike Adams | Blocked | Low | 2024-01-09 | 2024-01-18 |  | 0 | Paint | Downtown Avenue | 23191.09 | 15914.79 | Not started
C002 | Shopping Complex B | T456 | Roofing | Dave Brown | Completed | Low | 2023-11-04 | 2023-11-16 | 2023-11-16 | 100 | Steel Beams | Market Street | 17137.87 | 45255.59 | No issues
C002 | Shopping Complex B | T190 | Steel Framework Setup | Emma White | Not Started | Medium | 2024-12-13 | 2025-01-02 |  | 0 | Roofing Sheets | Market Street | 41491.44 | 0 | Not started
C002 | Shopping Complex B | T408 | Steel Framework Setup | Grace Allen | Completed | Low | 2024-09-11 | 2024-09-24 | 2024-09-24 | 100 | Copper Wires | Market Street | 48095.03 | 72320.82 | No issues
C001 | Residential Building A | T351 | Roofing | Sarah Johnson | Blocked | Low | 2024-02-21 | 2024-03-15 |  | 0 | Rebar | Plot 21, Riverside | 18400.05 | 17418.73 | Not started
C004 | Warehouse D | T220 | Plumbing Installations | Grace Allen | Completed | High | 2024-11-12 | 2024-11-23 | 2024-11-23 | 100 | Copper Wires | Industrial Park | 26532.08 | 30714.5 | No issues
C001 | Residential Building A | T723 | Foundation Excavation | Grace Allen | Completed | Medium | 2024-05-12 | 2024-06-04 | 2024-06-04 | 100 | Copper Wires | Plot 21, Riverside | 15868.51 | 12605.74 | No issues
C002 | Shopping Complex B | T952 | Foundation Excavation | Sarah Johnson | Blocked | Low | 2023-05-07 | 2023-06-02 |  | 0 | Steel Beams | Market Street | 17106.89 | 39765.3 | Not started
C002 | Shopping Complex B | T185 | Steel Framework Setup | Emma White | Completed | Low | 2023-01-13 | 2023-01-22 | 2023-01-22 | 100 | Roofing Sheets | Market Street | 35184.78 | 63378.79 | No issues
C004 | Warehouse D | T237 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2023-01-18 | 2023-02-04 |  | 0 | Roofing Sheets | Industrial Park | 48540.51 | 46659.93 | Not started
C003 | Office Tower C | T315 | Roofing | Rachel Green | Blocked | High | 2023-04-05 | 2023-05-04 |  | 0 | Cement | Downtown Avenue | 22896.38 | 19556.35 | Not started
C002 | Shopping Complex B | T560 | Electrical Wiring | Grace Allen | Not Started | Medium | 2024-05-27 | 2024-06-20 |  | 0 | Copper Wires | Market Street | 25471.11 | 0 | Not started
C001 | Residential Building A | T409 | Concrete Pouring | John Miller | Not Started | Medium | 2023-09-26 | 2023-10-19 |  | 0 | Cement | Plot 21, Riverside | 37565.8 | 0 | Not started
C002 | Shopping Complex B | T914 | Site Survey | Carlos Rivera | In Progress | Low | 2024-05-04 | 2024-05-19 |  | 4 | Rebar | Market Street | 16421.89 | 45166.93 | In progress
C001 | Residential Building A | T411 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2024-03-02 | 2024-03-22 |  | 0 | PVC Pipes | Plot 21, Riverside | 30606.41 | 24945.97 | Not started
C001 | Residential Building A | T617 | Electrical Wiring | Emma White | Completed | High | 2023-10-20 | 2023-11-12 | 2023-11-12 | 100 | Copper Wires | Plot 21, Riverside | 36839.55 | 29828.28 | No issues
C004 | Warehouse D | T820 | Steel Framework Setup | Grace Allen | Not Started | High | 2023-06-17 | 2023-07-12 |  | 0 | Cement | Industrial Park | 41347.62 | 0 | Not started
C004 | Warehouse D | T225 | Electrical Wiring | Grace Allen | In Progress | Low | 2023-02-26 | 2023-03-05 |  | 81 | Steel Beams | Industrial Park | 29647.88 | 24684.83 | In progress
C001 | Residential Building A | T362 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2023-06-25 | 2023-07-15 |  | 22 | Concrete | Plot 21, Riverside | 18343.23 | 21947.17 | In progress
C004 | Warehouse D | T769 | Roofing | Rachel Green | In Progress | High | 2023-07-27 | 2023-08-19 |  | 16 | Concrete | Industrial Park | 12705.31 | 8040.85 | In progress
C002 | Shopping Complex B | T767 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2024-06-25 | 2024-07-15 |  | 0 | Steel Beams | Market Street | 28686.86 | 46101.36 | Not started
C004 | Warehouse D | T499 | Roofing | John Miller | Not Started | Medium | 2024-08-24 | 2024-09-09 |  | 0 | Concrete | Industrial Park | 36468.4 | 0 | Not started
C003 | Office Tower C | T611 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-12-03 | 2023-12-22 | 2023-12-22 | 100 | Copper Wires | Downtown Avenue | 20322.82 | 23779.65 | No issues
C003 | Office Tower C | T196 | Plumbing Installations | Carlos Rivera | In Progress | High | 2024-05-03 | 2024-05-24 |  | 79 | Cement | Downtown Avenue | 32928 | 35650.72 | In progress
C001 | Residential Building A | T693 | Interior Painting | Dave Brown | Not Started | High | 2023-07-17 | 2023-07-29 |  | 0 | Paint | Plot 21, Riverside | 6948.55 | 0 | Not started
C004 | Warehouse D | T106 | Roofing | Sarah Johnson | Blocked | Medium | 2023-07-11 | 2023-08-10 |  | 0 | Rebar | Industrial Park | 45489.25 | 45894.11 | Not started
C003 | Office Tower C | T633 | Plumbing Installations | Dave Brown | Not Started | Medium | 2024-10-01 | 2024-10-13 |  | 0 | Rebar | Downtown Avenue | 31210.13 | 0 | Not started
C002 | Shopping Complex B | T943 | Interior Painting | Dave Brown | Not Started | High | 2024-10-17 | 2024-10-24 |  | 0 | Steel Beams | Market Street | 49975.58 | 0 | Not started
C004 | Warehouse D | T983 | Steel Framework Setup | Rachel Green | Blocked | Low | 2024-02-22 | 2024-03-10 |  | 0 | Roofing Sheets | Industrial Park | 32924.35 | 32150.08 | Not started
C004 | Warehouse D | T248 | Roofing | Grace Allen | Blocked | Low | 2024-05-17 | 2024-06-10 |  | 0 | Steel Beams | Industrial Park | 32140.47 | 30954.82 | Not started
C001 | Residential Building A | T127 | Electrical Wiring | Carlos Rivera | Completed | Low | 2023-06-27 | 2023-07-17 | 2023-07-17 | 100 | Copper Wires | Plot 21, Riverside | 16396.21 | 13821.31 | No issues
C003 | Office Tower C | T545 | Plumbing Installations | Grace Allen | Not Started | Medium | 2023-09-05 | 2023-09-20 |  | 0 | Steel Beams | Downtown Avenue | 6935.53 | 0 | Not started
C003 | Office Tower C | T815 | Concrete Pouring | John Miller | In Progress | Low | 2023-05-18 | 2023-06-03 |  | 21 | Copper Wires | Downtown Avenue | 26900.19 | 30811.8 | In progress
C003 | Office Tower C | T833 | Concrete Pouring | Rachel Green | In Progress | Low | 2024-02-08 | 2024-03-01 |  | 14 | Concrete | Downtown Avenue | 40089.61 | 39403.85 | In progress
C002 | Shopping Complex B | T403 | Concrete Pouring | Grace Allen | In Progress | Low | 2024-10-27 | 2024-11-04 |  | 95 | PVC Pipes | Market Street | 46709.11 | 61302.92 | In progress
C004 | Warehouse D | T410 | Concrete Pouring | Emma White | In Progress | Medium | 2023-05-18 | 2023-06-16 |  | 48 | Rebar | Industrial Park | 6525.05 | 7059.73 | In progress
C003 | Office Tower C | T645 | Concrete Pouring | Mike Adams | Not Started | High | 2024-05-10 | 2024-06-05 |  | 0 | Paint | Downtown Avenue | 9557.91 | 0 | Not started
C003 | Office Tower C | T526 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-12-21 | 2024-01-16 |  | 0 | Rebar | Downtown Avenue | 6797.97 | 4253.42 | Not started
C003 | Office Tower C | T201 | Roofing | Emma White | Blocked | Medium | 2024-08-19 | 2024-09-08 |  | 0 | Roofing Sheets | Downtown Avenue | 23370.59 | 28030.83 | Not started
C003 | Office Tower C | T249 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-09-23 | 2024-10-07 |  | 0 | Cement | Downtown Avenue | 18586.16 | 14273.89 | Not started
C004 | Warehouse D | T918 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2023-03-14 | 2023-03-28 |  | 65 | Copper Wires | Industrial Park | 14177.31 | 10581.59 | In progress
C004 | Warehouse D | T296 | Electrical Wiring | Sarah Johnson | In Progress | High | 2023-10-18 | 2023-11-14 |  | 52 | Cement | Industrial Park | 7727.4 | 7715.5 | In progress
C003 | Office Tower C | T135 | Plumbing Installations | John Miller | Completed | High | 2024-08-25 | 2024-09-04 | 2024-09-04 | 100 | Roofing Sheets | Downtown Avenue | 24251.63 | 24856.6 | No issues
C001 | Residential Building A | T394 | Electrical Wiring | Rachel Green | Not Started | Low | 2023-03-02 | 2023-03-28 |  | 0 | Rebar | Plot 21, Riverside | 40781.2 | 0 | Not started
C001 | Residential Building A | T929 | Roofing | Rachel Green | Blocked | Medium | 2024-11-17 | 2024-12-15 |  | 0 | PVC Pipes | Plot 21, Riverside | 19768.06 | 12140.02 | Not started
C001 | Residential Building A | T932 | Roofing | Sarah Johnson | Blocked | High | 2023-08-17 | 2023-08-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 22642.37 | 14660.12 | Not started
C001 | Residential Building A | T954 | Roofing | Emma White | Blocked | High | 2023-09-21 | 2023-10-08 |  | 0 | Copper Wires | Plot 21, Riverside | 20024.77 | 22744.32 | Not started
C001 | Residential Building A | T857 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2023-06-07 | 2023-06-25 | 2023-06-25 | 100 | Roofing Sheets | Plot 21, Riverside | 48546.77 | 40187.92 | No issues
C001 | Residential Building A | T655 | Concrete Pouring | John Miller | Completed | High | 2024-07-27 | 2024-08-19 | 2024-08-19 | 100 | PVC Pipes | Plot 21, Riverside | 45317.87 | 28324.87 | No issues
C002 | Shopping Complex B | T897 | Roofing | Dave Brown | Completed | Low | 2024-02-21 | 2024-03-02 | 2024-03-02 | 100 | Rebar | Market Street | 30408.61 | 53462.46 | No issues
C003 | Office Tower C | T327 | Interior Painting | Grace Allen | In Progress | Medium | 2024-12-02 | 2024-12-29 |  | 58 | Paint | Downtown Avenue | 48249.08 | 35703.4 | In progress
C001 | Residential Building A | T611 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2024-05-07 | 2024-05-28 | 2024-05-28 | 100 | Cement | Plot 21, Riverside | 23329.68 | 22779.52 | No issues
C002 | Shopping Complex B | T931 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2024-09-18 | 2024-10-09 |  | 0 | Roofing Sheets | Market Street | 5456.26 | 0 | Not started
C001 | Residential Building A | T159 | Concrete Pouring | John Miller | In Progress | Low | 2024-02-28 | 2024-03-27 |  | 77 | Copper Wires | Plot 21, Riverside | 29011.69 | 30018.22 | In progress
C001 | Residential Building A | T992 | Plumbing Installations | Carlos Rivera | Not Started | High | 2024-10-23 | 2024-11-02 |  | 0 | PVC Pipes | Plot 21, Riverside | 16957.88 | 0 | Not started
C003 | Office Tower C | T682 | Foundation Excavation | Grace Allen | Completed | High | 2023-02-22 | 2023-03-07 | 2023-03-07 | 100 | Paint | Downtown Avenue | 9384.76 | 7713.9 | No issues
C004 | Warehouse D | T187 | Concrete Pouring | Grace Allen | In Progress | Low | 2023-04-08 | 2023-04-22 |  | 52 | Roofing Sheets | Industrial Park | 9411.29 | 8305.74 | In progress
C003 | Office Tower C | T543 | Roofing | John Miller | Not Started | High | 2023-06-12 | 2023-06-26 |  | 0 | Paint | Downtown Avenue | 29507.01 | 0 | Not started
C002 | Shopping Complex B | T870 | Interior Painting | John Miller | In Progress | High | 2024-10-20 | 2024-11-07 |  | 62 | Roofing Sheets | Market Street | 16009.92 | 37179.61 | In progress
C002 | Shopping Complex B | T175 | Plumbing Installations | Mike Adams | Completed | High | 2024-06-28 | 2024-07-20 | 2024-07-20 | 100 | Rebar | Market Street | 43847.76 | 65986.92 | No issues
C002 | Shopping Complex B | T610 | Foundation Excavation | Rachel Green | Blocked | Medium | 2023-02-12 | 2023-02-25 |  | 0 | Cement | Market Street | 5727.53 | 29614.44 | Not started
C001 | Residential Building A | T484 | Foundation Excavation | Grace Allen | Completed | High | 2023-12-09 | 2023-12-20 | 2023-12-20 | 100 | Concrete | Plot 21, Riverside | 18541.76 | 11504.38 | No issues
C004 | Warehouse D | T712 | Foundation Excavation | Dave Brown | Not Started | Low | 2023-05-09 | 2023-05-31 |  | 0 | Concrete | Industrial Park | 38774.7 | 0 | Not started
C004 | Warehouse D | T924 | Roofing | Rachel Green | Completed | Low | 2023-05-02 | 2023-05-23 | 2023-05-23 | 100 | Rebar | Industrial Park | 16101.07 | 17736.01 | No issues
C001 | Residential Building A | T848 | Roofing | Sarah Johnson | Completed | Low | 2024-12-18 | 2025-01-05 | 2025-01-05 | 100 | Steel Beams | Plot 21, Riverside | 36062.78 | 27547.1 | No issues
C004 | Warehouse D | T670 | Interior Painting | Mike Adams | In Progress | High | 2024-11-08 | 2024-12-01 |  | 32 | Roofing Sheets | Industrial Park | 18064.69 | 16121.09 | In progress
C004 | Warehouse D | T458 | Steel Framework Setup | Grace Allen | Blocked | Low | 2024-12-03 | 2024-12-18 |  | 0 | PVC Pipes | Industrial Park | 7413.84 | 7463.21 | Not started
C004 | Warehouse D | T466 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-11-06 | 2024-11-15 |  | 0 | Rebar | Industrial Park | 24258.43 | 20033.87 | Not started
C003 | Office Tower C | T962 | Site Survey | John Miller | In Progress | High | 2024-06-27 | 2024-07-19 |  | 12 | Steel Beams | Downtown Avenue | 43011.46 | 42336.23 | In progress
C004 | Warehouse D | T535 | Steel Framework Setup | Dave Brown | Completed | High | 2023-07-27 | 2023-08-16 | 2023-08-16 | 100 | Paint | Industrial Park | 33001.97 | 26356.66 | No issues
C003 | Office Tower C | T829 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2023-10-14 | 2023-11-11 |  | 0 | Concrete | Downtown Avenue | 32174.26 | 25886.7 | Not started
C001 | Residential Building A | T947 | Concrete Pouring | Mike Adams | In Progress | High | 2023-05-09 | 2023-05-26 |  | 7 | Cement | Plot 21, Riverside | 12235.58 | 10109.69 | In progress
C004 | Warehouse D | T347 | Electrical Wiring | Grace Allen | Completed | High | 2024-11-14 | 2024-12-06 | 2024-12-06 | 100 | Rebar | Industrial Park | 7181.78 | 4863.71 | No issues
C004 | Warehouse D | T969 | Interior Painting | Carlos Rivera | Not Started | Medium | 2024-03-25 | 2024-04-24 |  | 0 | Steel Beams | Industrial Park | 36168.05 | 0 | Not started
C002 | Shopping Complex B | T729 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2023-12-28 | 2024-01-18 |  | 0 | Cement | Market Street | 22174.21 | 39582.95 | Not started
C002 | Shopping Complex B | T632 | Interior Painting | Sarah Johnson | Not Started | High | 2024-07-21 | 2024-08-09 |  | 0 | Cement | Market Street | 47165.27 | 0 | Not started
C001 | Residential Building A | T966 | Site Survey | Dave Brown | In Progress | Medium | 2023-07-23 | 2023-08-20 |  | 98 | Rebar | Plot 21, Riverside | 49484.93 | 30537.46 | In progress
C003 | Office Tower C | T899 | Roofing | Sarah Johnson | In Progress | High | 2023-10-10 | 2023-10-19 |  | 42 | Concrete | Downtown Avenue | 13330.09 | 15028.58 | In progress
C001 | Residential Building A | T687 | Site Survey | Dave Brown | In Progress | Low | 2024-01-26 | 2024-02-24 |  | 78 | Rebar | Plot 21, Riverside | 28462.51 | 23703.22 | In progress
C003 | Office Tower C | T912 | Plumbing Installations | Emma White | In Progress | Low | 2024-02-16 | 2024-03-08 |  | 93 | Steel Beams | Downtown Avenue | 6208.41 | 7319.16 | In progress
C001 | Residential Building A | T760 | Roofing | Grace Allen | In Progress | Medium | 2023-07-16 | 2023-08-12 |  | 3 | PVC Pipes | Plot 21, Riverside | 39201.72 | 43842.34 | In progress
C004 | Warehouse D | T711 | Plumbing Installations | Dave Brown | In Progress | Medium | 2024-11-12 | 2024-11-24 |  | 66 | Steel Beams | Industrial Park | 13632.06 | 11584.82 | In progress
C001 | Residential Building A | T190 | Roofing | Dave Brown | Blocked | Low | 2023-10-07 | 2023-11-06 |  | 0 | Rebar | Plot 21, Riverside | 35879.91 | 23589.32 | Not started
C003 | Office Tower C | T696 | Concrete Pouring | Dave Brown | Blocked | Low | 2024-02-15 | 2024-03-09 |  | 0 | Rebar | Downtown Avenue | 6329.11 | 4060.73 | Not started
C004 | Warehouse D | T627 | Plumbing Installations | Emma White | Completed | High | 2024-11-09 | 2024-11-22 | 2024-11-22 | 100 | PVC Pipes | Industrial Park | 27969.83 | 32131.51 | No issues
C004 | Warehouse D | T828 | Plumbing Installations | Grace Allen | Blocked | Low | 2023-07-08 | 2023-07-23 |  | 0 | Concrete | Industrial Park | 12612.97 | 7790.67 | Not started
C004 | Warehouse D | T962 | Concrete Pouring | Dave Brown | Completed | High | 2023-09-26 | 2023-10-10 | 2023-10-10 | 100 | PVC Pipes | Industrial Park | 25959.54 | 23138.68 | No issues
C001 | Residential Building A | T905 | Roofing | Emma White | In Progress | High | 2023-06-09 | 2023-06-25 |  | 80 | Roofing Sheets | Plot 21, Riverside | 39180.56 | 30454.54 | In progress
C001 | Residential Building A | T693 | Interior Painting | Grace Allen | Blocked | Medium | 2024-12-03 | 2024-12-27 |  | 0 | PVC Pipes | Plot 21, Riverside | 47891.6 | 40470.01 | Not started
C001 | Residential Building A | T102 | Steel Framework Setup | Carlos Rivera | In Progress | High | 2024-04-18 | 2024-05-12 |  | 59 | Cement | Plot 21, Riverside | 44775.92 | 47886.57 | In progress
C003 | Office Tower C | T733 | Foundation Excavation | Sarah Johnson | Blocked | High | 2024-01-01 | 2024-01-23 |  | 0 | Steel Beams | Downtown Avenue | 34394.89 | 25929.66 | Not started
C002 | Shopping Complex B | T570 | Interior Painting | Carlos Rivera | In Progress | Low | 2023-06-10 | 2023-06-24 |  | 61 | Paint | Market Street | 43430.67 | 53851.08 | In progress
C004 | Warehouse D | T310 | Steel Framework Setup | Dave Brown | Blocked | High | 2023-11-22 | 2023-12-09 |  | 0 | Concrete | Industrial Park | 17890.78 | 20283.6 | Not started
C004 | Warehouse D | T276 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-11-07 | 2023-11-26 |  | 0 | Concrete | Industrial Park | 29925.64 | 0 | Not started
C002 | Shopping Complex B | T341 | Interior Painting | Dave Brown | Not Started | Medium | 2023-09-16 | 2023-10-03 |  | 0 | PVC Pipes | Market Street | 15364.91 | 0 | Not started
C004 | Warehouse D | T775 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2023-09-21 | 2023-09-29 |  | 0 | Copper Wires | Industrial Park | 49091.62 | 50154.83 | Not started
C003 | Office Tower C | T654 | Foundation Excavation | John Miller | Blocked | High | 2023-05-20 | 2023-06-03 |  | 0 | Copper Wires | Downtown Avenue | 14795.33 | 13388.97 | Not started
C003 | Office Tower C | T776 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2024-09-16 | 2024-10-07 |  | 75 | Concrete | Downtown Avenue | 48655.35 | 31652.76 | In progress
C002 | Shopping Complex B | T192 | Roofing | Emma White | In Progress | Medium | 2024-04-18 | 2024-04-26 |  | 64 | Paint | Market Street | 44587.89 | 64146.77 | In progress
C001 | Residential Building A | T990 | Plumbing Installations | Dave Brown | Blocked | Medium | 2024-12-10 | 2024-12-18 |  | 0 | Paint | Plot 21, Riverside | 34579.04 | 36749.66 | Not started
C001 | Residential Building A | T675 | Foundation Excavation | John Miller | Blocked | Low | 2024-04-14 | 2024-05-05 |  | 0 | Rebar | Plot 21, Riverside | 28242.64 | 30107.1 | Not started
C001 | Residential Building A | T949 | Site Survey | Dave Brown | Not Started | Medium | 2023-01-19 | 2023-01-29 |  | 0 | Rebar | Plot 21, Riverside | 14711.34 | 0 | Not started
C004 | Warehouse D | T280 | Foundation Excavation | Emma White | Blocked | High | 2024-01-27 | 2024-02-14 |  | 0 | Paint | Industrial Park | 40283.25 | 35896.19 | Not started
C004 | Warehouse D | T679 | Site Survey | Rachel Green | Blocked | High | 2023-01-21 | 2023-01-29 |  | 0 | Paint | Industrial Park | 18745.71 | 16547.45 | Not started
C002 | Shopping Complex B | T791 | Site Survey | John Miller | Completed | Medium | 2023-05-21 | 2023-06-04 | 2023-06-04 | 100 | Concrete | Market Street | 18271.83 | 46126.4 | No issues
C002 | Shopping Complex B | T773 | Roofing | Dave Brown | Blocked | High | 2023-04-27 | 2023-05-26 |  | 0 | Cement | Market Street | 35594.84 | 54113.08 | Not started
C004 | Warehouse D | T615 | Site Survey | Carlos Rivera | In Progress | High | 2023-03-06 | 2023-03-24 |  | 25 | Concrete | Industrial Park | 16200.87 | 17430.96 | In progress
C001 | Residential Building A | T134 | Concrete Pouring | Rachel Green | Blocked | Low | 2023-05-27 | 2023-06-19 |  | 0 | Roofing Sheets | Plot 21, Riverside | 15502.9 | 14454.19 | Not started
C003 | Office Tower C | T441 | Plumbing Installations | Sarah Johnson | Not Started | High | 2023-05-23 | 2023-06-09 |  | 0 | Roofing Sheets | Downtown Avenue | 49894.58 | 0 | Not started
C001 | Residential Building A | T314 | Interior Painting | Mike Adams | Blocked | High | 2024-07-15 | 2024-07-29 |  | 0 | Cement | Plot 21, Riverside | 28731.61 | 20934.93 | Not started
C003 | Office Tower C | T459 | Plumbing Installations | Grace Allen | Blocked | Low | 2023-11-17 | 2023-12-11 |  | 0 | Cement | Downtown Avenue | 25252.08 | 24534.04 | Not started
C001 | Residential Building A | T451 | Roofing | Grace Allen | Not Started | High | 2024-07-23 | 2024-07-30 |  | 0 | Copper Wires | Plot 21, Riverside | 49912.32 | 0 | Not started
C002 | Shopping Complex B | T982 | Plumbing Installations | Emma White | In Progress | High | 2024-02-25 | 2024-03-19 |  | 12 | Roofing Sheets | Market Street | 8705.82 | 34073.07 | In progress
C001 | Residential Building A | T297 | Site Survey | Sarah Johnson | In Progress | Low | 2024-11-12 | 2024-11-30 |  | 42 | PVC Pipes | Plot 21, Riverside | 36870.35 | 29392.5 | In progress
C001 | Residential Building A | T213 | Plumbing Installations | John Miller | Not Started | Low | 2023-12-18 | 2024-01-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 5077.61 | 0 | Not started
C002 | Shopping Complex B | T801 | Steel Framework Setup | Dave Brown | In Progress | Low | 2023-02-02 | 2023-02-17 |  | 72 | Concrete | Market Street | 10298.83 | 37044.14 | In progress
C003 | Office Tower C | T444 | Electrical Wiring | John Miller | Completed | Medium | 2024-01-06 | 2024-01-25 | 2024-01-25 | 100 | Cement | Downtown Avenue | 23994.42 | 27149.73 | No issues
C001 | Residential Building A | T570 | Interior Painting | Grace Allen | In Progress | Medium | 2023-10-16 | 2023-11-11 |  | 50 | Copper Wires | Plot 21, Riverside | 14399.34 | 13096.44 | In progress
C004 | Warehouse D | T800 | Foundation Excavation | Dave Brown | In Progress | Medium | 2024-04-10 | 2024-04-18 |  | 89 | Roofing Sheets | Industrial Park | 42926.33 | 27299.2 | In progress
C002 | Shopping Complex B | T856 | Foundation Excavation | Emma White | Completed | Low | 2024-01-03 | 2024-01-14 | 2024-01-14 | 100 | Rebar | Market Street | 20497.06 | 45440.85 | No issues
C001 | Residential Building A | T712 | Site Survey | Emma White | Not Started | High | 2024-09-18 | 2024-10-05 |  | 0 | Copper Wires | Plot 21, Riverside | 7079.7 | 0 | Not started
C002 | Shopping Complex B | T120 | Plumbing Installations | Mike Adams | Completed | High | 2024-07-24 | 2024-08-19 | 2024-08-19 | 100 | Rebar | Market Street | 5995.61 | 30470.97 | No issues
C003 | Office Tower C | T322 | Concrete Pouring | John Miller | Blocked | High | 2023-05-02 | 2023-05-21 |  | 0 | Roofing Sheets | Downtown Avenue | 28985.07 | 28055.67 | Not started
C003 | Office Tower C | T978 | Roofing | Sarah Johnson | In Progress | Medium | 2024-04-08 | 2024-04-22 |  | 2 | Rebar | Downtown Avenue | 17132.48 | 12954.23 | In progress
C004 | Warehouse D | T512 | Site Survey | Dave Brown | In Progress | Medium | 2023-07-03 | 2023-08-02 |  | 35 | Rebar | Industrial Park | 25373.83 | 17416.67 | In progress
C001 | Residential Building A | T817 | Concrete Pouring | Rachel Green | Blocked | Low | 2023-07-01 | 2023-07-10 |  | 0 | Steel Beams | Plot 21, Riverside | 5015.36 | 3304.31 | Not started
C002 | Shopping Complex B | T202 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2023-04-26 | 2023-05-21 |  | 0 | Rebar | Market Street | 32594.03 | 53468.44 | Not started
C003 | Office Tower C | T556 | Concrete Pouring | Grace Allen | Not Started | Low | 2023-08-22 | 2023-08-29 |  | 0 | Concrete | Downtown Avenue | 6413.58 | 0 | Not started
C003 | Office Tower C | T136 | Concrete Pouring | John Miller | Blocked | Low | 2024-06-10 | 2024-07-08 |  | 0 | Paint | Downtown Avenue | 18015.34 | 16578.16 | Not started
C003 | Office Tower C | T995 | Site Survey | Dave Brown | Blocked | High | 2023-08-14 | 2023-09-02 |  | 0 | Concrete | Downtown Avenue | 10337.87 | 11204.61 | Not started
C003 | Office Tower C | T303 | Foundation Excavation | Emma White | Completed | Medium | 2023-12-24 | 2024-01-19 | 2024-01-19 | 100 | Copper Wires | Downtown Avenue | 44396.53 | 45061.03 | No issues
C003 | Office Tower C | T267 | Site Survey | Sarah Johnson | Not Started | Low | 2024-08-20 | 2024-09-05 |  | 0 | PVC Pipes | Downtown Avenue | 24974.6 | 0 | Not started
C001 | Residential Building A | T542 | Steel Framework Setup | John Miller | Not Started | High | 2024-11-20 | 2024-12-12 |  | 0 | Concrete | Plot 21, Riverside | 24918.11 | 0 | Not started
C004 | Warehouse D | T632 | Foundation Excavation | Rachel Green | Not Started | Low | 2023-02-22 | 2023-03-11 |  | 0 | Steel Beams | Industrial Park | 13864.53 | 0 | Not started
C002 | Shopping Complex B | T862 | Concrete Pouring | John Miller | Completed | Medium | 2023-12-22 | 2024-01-18 | 2024-01-18 | 100 | Rebar | Market Street | 35509.6 | 54592.14 | No issues
C004 | Warehouse D | T350 | Roofing | John Miller | Completed | High | 2024-01-01 | 2024-01-24 | 2024-01-24 | 100 | Rebar | Industrial Park | 37650.59 | 31501 | No issues
C002 | Shopping Complex B | T953 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-08-21 | 2023-09-13 |  | 4 | Concrete | Market Street | 15367.42 | 38650.22 | In progress
C003 | Office Tower C | T512 | Site Survey | Emma White | Not Started | Medium | 2023-09-18 | 2023-10-01 |  | 0 | Rebar | Downtown Avenue | 9525.9 | 0 | Not started
C001 | Residential Building A | T641 | Concrete Pouring | Dave Brown | In Progress | Medium | 2024-01-10 | 2024-02-02 |  | 50 | Cement | Plot 21, Riverside | 39060.76 | 44367.35 | In progress
C003 | Office Tower C | T352 | Site Survey | Dave Brown | In Progress | Low | 2024-06-11 | 2024-06-28 |  | 30 | Cement | Downtown Avenue | 24453.27 | 20079.25 | In progress
C003 | Office Tower C | T768 | Concrete Pouring | Dave Brown | Blocked | High | 2024-02-25 | 2024-03-11 |  | 0 | Cement | Downtown Avenue | 36073.49 | 24663.24 | Not started
C004 | Warehouse D | T293 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2024-06-26 | 2024-07-12 |  | 0 | Roofing Sheets | Industrial Park | 38293.87 | 0 | Not started
C001 | Residential Building A | T807 | Interior Painting | Mike Adams | Blocked | High | 2023-11-25 | 2023-12-19 |  | 0 | Rebar | Plot 21, Riverside | 30416.03 | 32671.59 | Not started
C001 | Residential Building A | T980 | Plumbing Installations | Emma White | In Progress | Low | 2024-12-16 | 2025-01-15 |  | 95 | PVC Pipes | Plot 21, Riverside | 30610.67 | 26845.66 | In progress
C004 | Warehouse D | T747 | Roofing | Carlos Rivera | Blocked | Medium | 2024-11-06 | 2024-11-25 |  | 0 | PVC Pipes | Industrial Park | 23700.47 | 21960.1 | Not started
C002 | Shopping Complex B | T727 | Steel Framework Setup | Rachel Green | In Progress | Medium | 2024-02-24 | 2024-03-22 |  | 1 | Paint | Market Street | 16635.59 | 36664.03 | In progress
C003 | Office Tower C | T181 | Steel Framework Setup | Grace Allen | Not Started | High | 2023-07-02 | 2023-07-26 |  | 0 | PVC Pipes | Downtown Avenue | 47401.11 | 0 | Not started
C003 | Office Tower C | T901 | Roofing | Emma White | Completed | Low | 2023-08-09 | 2023-09-07 | 2023-09-07 | 100 | Concrete | Downtown Avenue | 22378.83 | 24263.81 | No issues
C001 | Residential Building A | T997 | Roofing | Sarah Johnson | Completed | Low | 2024-07-23 | 2024-08-14 | 2024-08-14 | 100 | Concrete | Plot 21, Riverside | 34523.08 | 27851.08 | No issues
C003 | Office Tower C | T970 | Steel Framework Setup | Mike Adams | Completed | High | 2024-01-16 | 2024-02-13 | 2024-02-13 | 100 | Cement | Downtown Avenue | 17373.41 | 11309.98 | No issues
C004 | Warehouse D | T757 | Plumbing Installations | Grace Allen | Blocked | High | 2024-06-07 | 2024-06-30 |  | 0 | PVC Pipes | Industrial Park | 47264.78 | 41796.41 | Not started
C001 | Residential Building A | T394 | Electrical Wiring | Mike Adams | In Progress | High | 2023-01-14 | 2023-02-09 |  | 0 | Roofing Sheets | Plot 21, Riverside | 18749.25 | 18100.17 | In progress
C001 | Residential Building A | T543 | Site Survey | Sarah Johnson | Not Started | Low | 2023-04-28 | 2023-05-24 |  | 0 | Cement | Plot 21, Riverside | 17017.66 | 0 | Not started
C003 | Office Tower C | T961 | Interior Painting | Sarah Johnson | Blocked | Medium | 2024-01-22 | 2024-02-05 |  | 0 | Roofing Sheets | Downtown Avenue | 36384.62 | 39365.99 | Not started
C001 | Residential Building A | T966 | Electrical Wiring | Dave Brown | Not Started | Low | 2024-08-18 | 2024-09-16 |  | 0 | Copper Wires | Plot 21, Riverside | 10256.48 | 0 | Not started
C004 | Warehouse D | T226 | Electrical Wiring | Dave Brown | Completed | Medium | 2024-10-17 | 2024-10-27 | 2024-10-27 | 100 | Cement | Industrial Park | 39567.24 | 44052.65 | No issues
C004 | Warehouse D | T377 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-06-22 | 2023-07-18 |  | 88 | Steel Beams | Industrial Park | 11779.73 | 7557.33 | In progress
C001 | Residential Building A | T204 | Roofing | Mike Adams | Completed | Low | 2023-06-20 | 2023-07-17 | 2023-07-17 | 100 | Cement | Plot 21, Riverside | 38478.18 | 27235.32 | No issues
C001 | Residential Building A | T329 | Plumbing Installations | Grace Allen | Completed | Low | 2024-03-27 | 2024-04-12 | 2024-04-12 | 100 | PVC Pipes | Plot 21, Riverside | 18697.43 | 14045.14 | No issues
C003 | Office Tower C | T811 | Foundation Excavation | Emma White | Completed | Low | 2024-01-15 | 2024-01-31 | 2024-01-31 | 100 | Paint | Downtown Avenue | 49202.28 | 44775.12 | No issues
C003 | Office Tower C | T248 | Concrete Pouring | Dave Brown | Completed | High | 2024-11-03 | 2024-11-24 | 2024-11-24 | 100 | Cement | Downtown Avenue | 16073.31 | 13584.92 | No issues
C001 | Residential Building A | T564 | Interior Painting | Rachel Green | Completed | High | 2024-02-09 | 2024-03-06 | 2024-03-06 | 100 | Roofing Sheets | Plot 21, Riverside | 33222.94 | 22723.1 | No issues
C003 | Office Tower C | T920 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2024-03-20 | 2024-04-10 |  | 0 | PVC Pipes | Downtown Avenue | 41364.53 | 36188.34 | Not started
C004 | Warehouse D | T214 | Foundation Excavation | Mike Adams | Completed | High | 2024-02-28 | 2024-03-08 | 2024-03-08 | 100 | Rebar | Industrial Park | 46972.83 | 46916.82 | No issues
C001 | Residential Building A | T567 | Plumbing Installations | Emma White | Completed | Medium | 2023-11-20 | 2023-11-29 | 2023-11-29 | 100 | Rebar | Plot 21, Riverside | 30724.32 | 24633.09 | No issues
C001 | Residential Building A | T561 | Roofing | Carlos Rivera | Blocked | Low | 2024-10-25 | 2024-11-13 |  | 0 | Cement | Plot 21, Riverside | 47794.9 | 37121.84 | Not started
C002 | Shopping Complex B | T184 | Plumbing Installations | John Miller | Not Started | Medium | 2023-08-13 | 2023-09-11 |  | 0 | Roofing Sheets | Market Street | 12448.54 | 0 | Not started
C004 | Warehouse D | T882 | Steel Framework Setup | Rachel Green | Completed | High | 2023-08-26 | 2023-09-04 | 2023-09-04 | 100 | Cement | Industrial Park | 48192.97 | 51435.72 | No issues
C002 | Shopping Complex B | T948 | Foundation Excavation | Emma White | Completed | High | 2024-07-17 | 2024-07-30 | 2024-07-30 | 100 | Rebar | Market Street | 37999.89 | 56086.23 | No issues
C003 | Office Tower C | T161 | Electrical Wiring | Mike Adams | In Progress | High | 2023-02-16 | 2023-03-17 |  | 54 | Concrete | Downtown Avenue | 21711.28 | 15407.06 | In progress
C001 | Residential Building A | T614 | Site Survey | Grace Allen | Not Started | Low | 2024-04-22 | 2024-05-22 |  | 0 | Roofing Sheets | Plot 21, Riverside | 20741 | 0 | Not started
C003 | Office Tower C | T805 | Roofing | Emma White | Completed | Low | 2024-01-17 | 2024-01-30 | 2024-01-30 | 100 | Cement | Downtown Avenue | 33321.3 | 35686.26 | No issues
C002 | Shopping Complex B | T438 | Concrete Pouring | Emma White | Not Started | Low | 2024-02-15 | 2024-02-24 |  | 0 | Steel Beams | Market Street | 8052.5 | 0 | Not started
C001 | Residential Building A | T653 | Foundation Excavation | Dave Brown | Not Started | Medium | 2024-10-26 | 2024-11-11 |  | 0 | Paint | Plot 21, Riverside | 35392.28 | 0 | Not started
C002 | Shopping Complex B | T433 | Plumbing Installations | Rachel Green | Completed | Low | 2024-11-14 | 2024-11-24 | 2024-11-24 | 100 | Copper Wires | Market Street | 41608.02 | 73769.41 | No issues
C002 | Shopping Complex B | T948 | Site Survey | Sarah Johnson | Blocked | Low | 2024-06-05 | 2024-06-24 |  | 0 | Paint | Market Street | 30572.3 | 59899.37 | Not started
C003 | Office Tower C | T183 | Site Survey | Carlos Rivera | In Progress | Medium | 2023-08-05 | 2023-08-23 |  | 62 | Roofing Sheets | Downtown Avenue | 42294.98 | 27436.68 | In progress
C003 | Office Tower C | T308 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2023-04-11 | 2023-05-10 |  | 6 | Roofing Sheets | Downtown Avenue | 34601.43 | 37786.27 | In progress
C002 | Shopping Complex B | T751 | Roofing | Rachel Green | In Progress | Low | 2024-02-01 | 2024-02-22 |  | 45 | Roofing Sheets | Market Street | 44114.81 | 56078.22 | In progress
C003 | Office Tower C | T477 | Interior Painting | Mike Adams | Completed | High | 2024-05-26 | 2024-06-10 | 2024-06-10 | 100 | Copper Wires | Downtown Avenue | 39484.38 | 39325.6 | No issues
C001 | Residential Building A | T364 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-10-13 | 2024-10-28 |  | 0 | Copper Wires | Plot 21, Riverside | 10608.47 | 0 | Not started
C004 | Warehouse D | T524 | Site Survey | Carlos Rivera | Blocked | Medium | 2024-03-14 | 2024-03-26 |  | 0 | Concrete | Industrial Park | 21923.81 | 16031.09 | Not started
C001 | Residential Building A | T718 | Interior Painting | Mike Adams | Completed | High | 2024-03-14 | 2024-04-06 | 2024-04-06 | 100 | Paint | Plot 21, Riverside | 20431.66 | 22540.43 | No issues
C004 | Warehouse D | T858 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-07-08 | 2023-08-06 |  | 0 | Paint | Industrial Park | 12465.37 | 0 | Not started
C001 | Residential Building A | T353 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-10-25 | 2023-11-18 |  | 67 | Steel Beams | Plot 21, Riverside | 26954.65 | 23178.86 | In progress
C004 | Warehouse D | T984 | Electrical Wiring | Sarah Johnson | Completed | High | 2024-11-22 | 2024-12-20 | 2024-12-20 | 100 | Concrete | Industrial Park | 36866.79 | 29354.03 | No issues
C001 | Residential Building A | T387 | Interior Painting | Emma White | Blocked | High | 2024-07-21 | 2024-08-07 |  | 0 | Rebar | Plot 21, Riverside | 41829.4 | 37721.96 | Not started
C001 | Residential Building A | T226 | Site Survey | John Miller | Blocked | Medium | 2024-09-06 | 2024-09-21 |  | 0 | Copper Wires | Plot 21, Riverside | 21206.23 | 20627.33 | Not started
C002 | Shopping Complex B | T909 | Foundation Excavation | Emma White | In Progress | High | 2024-11-26 | 2024-12-23 |  | 24 | Paint | Market Street | 18723.17 | 45443.35 | In progress
C001 | Residential Building A | T215 | Plumbing Installations | John Miller | Blocked | Low | 2023-01-01 | 2023-01-09 |  | 0 | Copper Wires | Plot 21, Riverside | 25065.41 | 29076.65 | Not started
C004 | Warehouse D | T611 | Plumbing Installations | John Miller | Not Started | Low | 2024-03-08 | 2024-04-06 |  | 0 | Rebar | Industrial Park | 11363.22 | 0 | Not started
C004 | Warehouse D | T396 | Electrical Wiring | Grace Allen | In Progress | Low | 2023-01-01 | 2023-01-25 |  | 77 | Concrete | Industrial Park | 41282.88 | 36001.44 | In progress
C004 | Warehouse D | T258 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-08-17 | 2023-09-10 | 2023-09-10 | 100 | PVC Pipes | Industrial Park | 27038.25 | 19138.45 | No issues
C003 | Office Tower C | T289 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-01-17 | 2023-01-31 |  | 36 | PVC Pipes | Downtown Avenue | 35095.11 | 40360.45 | In progress
C003 | Office Tower C | T786 | Electrical Wiring | Rachel Green | Blocked | High | 2024-10-01 | 2024-10-08 |  | 0 | Cement | Downtown Avenue | 21619.27 | 23037.03 | Not started
C002 | Shopping Complex B | T184 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-01-23 | 2023-02-07 |  | 31 | Roofing Sheets | Market Street | 30895.22 | 59188.41 | In progress
C002 | Shopping Complex B | T997 | Interior Painting | Carlos Rivera | Not Started | High | 2024-12-08 | 2024-12-30 |  | 0 | Concrete | Market Street | 14234.33 | 0 | Not started
C004 | Warehouse D | T873 | Site Survey | Rachel Green | Completed | Medium | 2024-12-21 | 2025-01-12 | 2025-01-12 | 100 | Cement | Industrial Park | 44821.3 | 32944.29 | No issues
C004 | Warehouse D | T394 | Site Survey | Dave Brown | Not Started | High | 2024-11-20 | 2024-11-27 |  | 0 | Concrete | Industrial Park | 34468.02 | 0 | Not started
C004 | Warehouse D | T278 | Roofing | Rachel Green | Completed | Medium | 2024-04-28 | 2024-05-14 | 2024-05-14 | 100 | Paint | Industrial Park | 23011.1 | 26080.52 | No issues
C001 | Residential Building A | T410 | Site Survey | Sarah Johnson | Not Started | Medium | 2023-10-17 | 2023-11-06 |  | 0 | Roofing Sheets | Plot 21, Riverside | 49117.37 | 0 | Not started
C002 | Shopping Complex B | T155 | Concrete Pouring | John Miller | Blocked | Medium | 2024-03-23 | 2024-04-15 |  | 0 | Copper Wires | Market Street | 7144.84 | 34066.63 | Not started
C003 | Office Tower C | T385 | Concrete Pouring | Mike Adams | Blocked | Medium | 2023-08-08 | 2023-08-16 |  | 0 | Paint | Downtown Avenue | 6300.3 | 4655.05 | Not started
C001 | Residential Building A | T960 | Concrete Pouring | Emma White | Not Started | High | 2023-03-14 | 2023-04-10 |  | 0 | Concrete | Plot 21, Riverside | 46338.24 | 0 | Not started
C003 | Office Tower C | T324 | Interior Painting | Sarah Johnson | Blocked | Low | 2024-07-04 | 2024-07-24 |  | 0 | Steel Beams | Downtown Avenue | 28049.65 | 17503.33 | Not started
C001 | Residential Building A | T903 | Roofing | Mike Adams | Completed | High | 2024-07-16 | 2024-08-14 | 2024-08-14 | 100 | Rebar | Plot 21, Riverside | 25323.37 | 21516.59 | No issues
C003 | Office Tower C | T248 | Interior Painting | John Miller | Completed | Low | 2024-01-16 | 2024-01-25 | 2024-01-25 | 100 | Concrete | Downtown Avenue | 5773.59 | 5138.16 | No issues
C001 | Residential Building A | T164 | Site Survey | John Miller | Blocked | High | 2023-04-18 | 2023-05-08 |  | 0 | Concrete | Plot 21, Riverside | 48265.7 | 30134.4 | Not started
C004 | Warehouse D | T444 | Interior Painting | John Miller | In Progress | High | 2024-11-18 | 2024-12-03 |  | 54 | PVC Pipes | Industrial Park | 40626.5 | 43920.47 | In progress
C001 | Residential Building A | T381 | Plumbing Installations | Emma White | Completed | High | 2024-03-20 | 2024-03-29 | 2024-03-29 | 100 | Rebar | Plot 21, Riverside | 40829.16 | 33564.73 | No issues
C001 | Residential Building A | T222 | Foundation Excavation | Sarah Johnson | Blocked | Low | 2024-12-22 | 2025-01-20 |  | 0 | PVC Pipes | Plot 21, Riverside | 27783.6 | 26662.26 | Not started
C002 | Shopping Complex B | T415 | Interior Painting | Mike Adams | Completed | Medium | 2023-11-23 | 2023-12-17 | 2023-12-17 | 100 | Paint | Market Street | 24530.87 | 44055.26 | No issues
C002 | Shopping Complex B | T100 | Steel Framework Setup | Emma White | Blocked | Medium | 2023-02-02 | 2023-02-11 |  | 0 | Concrete | Market Street | 33331.22 | 64612.33 | Not started
C004 | Warehouse D | T210 | Plumbing Installations | John Miller | Blocked | Low | 2023-07-15 | 2023-07-30 |  | 0 | Cement | Industrial Park | 24998.65 | 28173.32 | Not started
C002 | Shopping Complex B | T224 | Plumbing Installations | Rachel Green | In Progress | High | 2023-12-08 | 2023-12-29 |  | 69 | Roofing Sheets | Market Street | 33160.88 | 46753.89 | In progress
C001 | Residential Building A | T686 | Electrical Wiring | Emma White | In Progress | High | 2023-11-16 | 2023-11-29 |  | 29 | Concrete | Plot 21, Riverside | 38593.46 | 29477.33 | In progress
C004 | Warehouse D | T635 | Plumbing Installations | Emma White | Blocked | Medium | 2023-08-07 | 2023-08-23 |  | 0 | Roofing Sheets | Industrial Park | 8422.82 | 8355.34 | Not started
C001 | Residential Building A | T953 | Roofing | Dave Brown | In Progress | Low | 2023-09-06 | 2023-09-23 |  | 19 | Steel Beams | Plot 21, Riverside | 48128.57 | 29406.53 | In progress
C002 | Shopping Complex B | T168 | Interior Painting | Mike Adams | Completed | Medium | 2023-01-28 | 2023-02-15 | 2023-02-15 | 100 | Roofing Sheets | Market Street | 16827.12 | 44492.23 | No issues
C001 | Residential Building A | T269 | Foundation Excavation | Grace Allen | Not Started | High | 2024-11-24 | 2024-12-06 |  | 0 | PVC Pipes | Plot 21, Riverside | 20865.63 | 0 | Not started
C003 | Office Tower C | T534 | Interior Painting | John Miller | Blocked | Medium | 2023-09-12 | 2023-10-07 |  | 0 | Roofing Sheets | Downtown Avenue | 10646.07 | 11798.82 | Not started
C004 | Warehouse D | T571 | Steel Framework Setup | John Miller | Completed | Low | 2023-09-11 | 2023-09-25 | 2023-09-25 | 100 | Cement | Industrial Park | 32333.51 | 26764.38 | No issues
C002 | Shopping Complex B | T895 | Site Survey | Grace Allen | In Progress | Low | 2023-11-16 | 2023-12-05 |  | 62 | Copper Wires | Market Street | 43611 | 53261.28 | In progress
C001 | Residential Building A | T611 | Plumbing Installations | Rachel Green | Blocked | High | 2024-09-23 | 2024-10-03 |  | 0 | Roofing Sheets | Plot 21, Riverside | 12031.82 | 11918.82 | Not started
C001 | Residential Building A | T273 | Interior Painting | John Miller | Blocked | Medium | 2023-05-10 | 2023-05-26 |  | 0 | Paint | Plot 21, Riverside | 11570.67 | 7711.78 | Not started
C002 | Shopping Complex B | T674 | Roofing | Emma White | In Progress | High | 2023-02-28 | 2023-03-26 |  | 8 | Paint | Market Street | 28249.63 | 58293.62 | In progress
C001 | Residential Building A | T216 | Plumbing Installations | Mike Adams | Blocked | Low | 2024-06-20 | 2024-07-04 |  | 0 | Paint | Plot 21, Riverside | 10879.2 | 6597.41 | Not started
C003 | Office Tower C | T808 | Steel Framework Setup | John Miller | Completed | Medium | 2023-03-13 | 2023-04-10 | 2023-04-10 | 100 | PVC Pipes | Downtown Avenue | 40109.79 | 27899.34 | No issues
C003 | Office Tower C | T520 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-11-07 | 2024-11-18 |  | 0 | Cement | Downtown Avenue | 23252.93 | 27137.55 | Not started
C002 | Shopping Complex B | T240 | Concrete Pouring | Emma White | Completed | High | 2023-06-01 | 2023-06-22 | 2023-06-22 | 100 | Rebar | Market Street | 47929.51 | 68234.37 | No issues
C004 | Warehouse D | T554 | Electrical Wiring | Carlos Rivera | Not Started | High | 2024-01-16 | 2024-02-02 |  | 0 | Concrete | Industrial Park | 7544.33 | 0 | Not started
C002 | Shopping Complex B | T601 | Plumbing Installations | John Miller | Not Started | High | 2024-10-10 | 2024-11-04 |  | 0 | Cement | Market Street | 18560.71 | 0 | Not started
C004 | Warehouse D | T842 | Roofing | Dave Brown | Completed | High | 2023-03-21 | 2023-03-28 | 2023-03-28 | 100 | Roofing Sheets | Industrial Park | 47159.86 | 46288.54 | No issues
C003 | Office Tower C | T399 | Roofing | Rachel Green | Blocked | High | 2024-04-26 | 2024-05-06 |  | 0 | Paint | Downtown Avenue | 19488.42 | 15226.31 | Not started
C004 | Warehouse D | T358 | Site Survey | Dave Brown | Blocked | Low | 2024-12-22 | 2025-01-10 |  | 0 | Steel Beams | Industrial Park | 9570.86 | 11453.15 | Not started
C003 | Office Tower C | T939 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-03-01 | 2023-03-08 | 2023-03-08 | 100 | Steel Beams | Downtown Avenue | 30362.67 | 28287.67 | No issues
C004 | Warehouse D | T126 | Site Survey | Sarah Johnson | Not Started | Low | 2023-09-17 | 2023-10-14 |  | 0 | Cement | Industrial Park | 35244.39 | 0 | Not started
C001 | Residential Building A | T623 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-10-22 | 2023-10-29 |  | 94 | Paint | Plot 21, Riverside | 24950.5 | 27571.89 | In progress
C001 | Residential Building A | T644 | Foundation Excavation | Rachel Green | In Progress | Medium | 2024-04-02 | 2024-04-14 |  | 17 | Roofing Sheets | Plot 21, Riverside | 6901.27 | 7445.85 | In progress
C004 | Warehouse D | T907 | Interior Painting | Grace Allen | Not Started | High | 2024-09-12 | 2024-10-07 |  | 0 | PVC Pipes | Industrial Park | 19595.55 | 0 | Not started
C001 | Residential Building A | T550 | Concrete Pouring | Dave Brown | Blocked | Low | 2023-11-26 | 2023-12-09 |  | 0 | Paint | Plot 21, Riverside | 16652.44 | 18216.59 | Not started
C002 | Shopping Complex B | T929 | Roofing | Dave Brown | Not Started | Medium | 2024-05-09 | 2024-05-16 |  | 0 | Steel Beams | Market Street | 38757.61 | 0 | Not started
C003 | Office Tower C | T486 | Foundation Excavation | Dave Brown | Not Started | Low | 2023-02-05 | 2023-03-06 |  | 0 | Roofing Sheets | Downtown Avenue | 13428.73 | 0 | Not started
C001 | Residential Building A | T574 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-11-06 | 2023-12-01 |  | 0 | Copper Wires | Plot 21, Riverside | 34776.25 | 0 | Not started
C001 | Residential Building A | T592 | Plumbing Installations | Mike Adams | Not Started | High | 2023-02-21 | 2023-03-03 |  | 0 | Rebar | Plot 21, Riverside | 30177.15 | 0 | Not started
C001 | Residential Building A | T377 | Electrical Wiring | Grace Allen | Blocked | Low | 2023-07-23 | 2023-08-17 |  | 0 | Steel Beams | Plot 21, Riverside | 25453.98 | 17870.91 | Not started
C001 | Residential Building A | T398 | Roofing | Sarah Johnson | Completed | Medium | 2024-09-25 | 2024-10-07 | 2024-10-07 | 100 | Cement | Plot 21, Riverside | 35126.32 | 30755.19 | No issues
C002 | Shopping Complex B | T510 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-07-01 | 2024-07-26 |  | 16 | PVC Pipes | Market Street | 35571.12 | 51756.15 | In progress
C003 | Office Tower C | T407 | Electrical Wiring | Mike Adams | Blocked | Medium | 2024-06-26 | 2024-07-10 |  | 0 | Roofing Sheets | Downtown Avenue | 46933.4 | 33883.47 | Not started
C003 | Office Tower C | T705 | Site Survey | Dave Brown | Not Started | Medium | 2023-12-21 | 2024-01-04 |  | 0 | Cement | Downtown Avenue | 34349.42 | 0 | Not started
C001 | Residential Building A | T281 | Site Survey | Grace Allen | In Progress | Medium | 2024-09-02 | 2024-09-13 |  | 4 | Rebar | Plot 21, Riverside | 26108.57 | 29285.1 | In progress
C004 | Warehouse D | T492 | Roofing | Mike Adams | Completed | High | 2024-03-27 | 2024-04-13 | 2024-04-13 | 100 | Copper Wires | Industrial Park | 47262.11 | 49821.12 | No issues
C003 | Office Tower C | T497 | Electrical Wiring | Dave Brown | In Progress | Medium | 2024-02-20 | 2024-02-28 |  | 12 | Concrete | Downtown Avenue | 9677.29 | 7725.33 | In progress
C003 | Office Tower C | T509 | Plumbing Installations | Carlos Rivera | Blocked | High | 2024-03-06 | 2024-03-17 |  | 0 | Cement | Downtown Avenue | 41537.29 | 37772.44 | Not started
C004 | Warehouse D | T732 | Roofing | Rachel Green | Blocked | High | 2024-09-15 | 2024-09-29 |  | 0 | Roofing Sheets | Industrial Park | 13551.61 | 13568.47 | Not started
C003 | Office Tower C | T493 | Concrete Pouring | Grace Allen | Blocked | High | 2023-01-15 | 2023-02-09 |  | 0 | PVC Pipes | Downtown Avenue | 35435.57 | 39049.3 | Not started
C004 | Warehouse D | T297 | Plumbing Installations | Mike Adams | Not Started | High | 2023-08-25 | 2023-09-18 |  | 0 | Roofing Sheets | Industrial Park | 45512.02 | 0 | Not started
C002 | Shopping Complex B | T474 | Plumbing Installations | Grace Allen | Not Started | High | 2023-05-01 | 2023-05-20 |  | 0 | Concrete | Market Street | 11612.65 | 0 | Not started
C002 | Shopping Complex B | T178 | Interior Painting | Rachel Green | Completed | Low | 2024-01-21 | 2024-02-11 | 2024-02-11 | 100 | Cement | Market Street | 29776.64 | 51582.18 | No issues
C002 | Shopping Complex B | T109 | Interior Painting | Dave Brown | Completed | High | 2024-01-07 | 2024-01-21 | 2024-01-21 | 100 | Steel Beams | Market Street | 18407.7 | 37151.17 | No issues
C004 | Warehouse D | T637 | Interior Painting | John Miller | In Progress | Medium | 2024-09-02 | 2024-09-11 |  | 39 | Rebar | Industrial Park | 43364.48 | 32046.38 | In progress
C004 | Warehouse D | T679 | Interior Painting | Carlos Rivera | Not Started | High | 2024-05-28 | 2024-06-27 |  | 0 | Concrete | Industrial Park | 7768.53 | 0 | Not started
C004 | Warehouse D | T216 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-03-21 | 2023-04-07 |  | 0 | Paint | Industrial Park | 42967.86 | 0 | Not started
C001 | Residential Building A | T867 | Electrical Wiring | Sarah Johnson | In Progress | High | 2024-10-17 | 2024-11-04 |  | 8 | Concrete | Plot 21, Riverside | 20360.71 | 19638.65 | In progress
C004 | Warehouse D | T573 | Electrical Wiring | Rachel Green | Completed | High | 2024-01-04 | 2024-02-03 | 2024-02-03 | 100 | Cement | Industrial Park | 48326.71 | 29488.02 | No issues
C001 | Residential Building A | T461 | Roofing | Emma White | In Progress | Low | 2024-12-07 | 2024-12-24 |  | 38 | PVC Pipes | Plot 21, Riverside | 43575.83 | 38641.71 | In progress
C003 | Office Tower C | T678 | Site Survey | Emma White | Completed | Low | 2024-10-21 | 2024-11-20 | 2024-11-20 | 100 | Concrete | Downtown Avenue | 10989.46 | 10130.54 | No issues
C004 | Warehouse D | T318 | Site Survey | Grace Allen | In Progress | High | 2024-08-02 | 2024-08-31 |  | 41 | Paint | Industrial Park | 15792.24 | 13171.25 | In progress
C001 | Residential Building A | T596 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-09-10 | 2024-09-19 |  | 0 | Paint | Plot 21, Riverside | 35034.71 | 0 | Not started
C001 | Residential Building A | T659 | Interior Painting | Emma White | In Progress | Low | 2024-10-01 | 2024-10-08 |  | 34 | Roofing Sheets | Plot 21, Riverside | 23685.72 | 22170.21 | In progress
C003 | Office Tower C | T913 | Interior Painting | Mike Adams | Not Started | Medium | 2024-05-27 | 2024-06-17 |  | 0 | Rebar | Downtown Avenue | 19626.85 | 0 | Not started
C002 | Shopping Complex B | T702 | Foundation Excavation | Carlos Rivera | Completed | High | 2023-10-05 | 2023-10-18 | 2023-10-18 | 100 | Copper Wires | Market Street | 45114.33 | 77601.73 | No issues
C002 | Shopping Complex B | T110 | Concrete Pouring | John Miller | In Progress | Low | 2023-09-18 | 2023-10-13 |  | 25 | Cement | Market Street | 19740.29 | 45521.52 | In progress
C004 | Warehouse D | T261 | Foundation Excavation | Grace Allen | Not Started | Medium | 2024-06-13 | 2024-06-26 |  | 0 | Concrete | Industrial Park | 45783.97 | 0 | Not started
C002 | Shopping Complex B | T274 | Concrete Pouring | Mike Adams | In Progress | Medium | 2024-10-14 | 2024-11-12 |  | 27 | Steel Beams | Market Street | 43323.63 | 60750.63 | In progress
C002 | Shopping Complex B | T583 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-02-03 | 2023-03-01 |  | 0 | Steel Beams | Market Street | 49199.8 | 74848.06 | Not started
C003 | Office Tower C | T747 | Steel Framework Setup | Emma White | Completed | Low | 2023-04-17 | 2023-05-08 | 2023-05-08 | 100 | Cement | Downtown Avenue | 27939.47 | 19772.05 | No issues
C002 | Shopping Complex B | T919 | Roofing | John Miller | Blocked | High | 2023-06-26 | 2023-07-26 |  | 0 | Paint | Market Street | 49779.29 | 56354.02 | Not started
C004 | Warehouse D | T190 | Interior Painting | Grace Allen | In Progress | Low | 2024-07-11 | 2024-08-01 |  | 25 | Concrete | Industrial Park | 23494.91 | 24514.03 | In progress
C002 | Shopping Complex B | T886 | Foundation Excavation | John Miller | Blocked | Medium | 2024-11-22 | 2024-12-19 |  | 0 | Copper Wires | Market Street | 22397.26 | 44885.38 | Not started
C003 | Office Tower C | T597 | Plumbing Installations | Dave Brown | Completed | Medium | 2023-04-11 | 2023-05-01 | 2023-05-01 | 100 | Roofing Sheets | Downtown Avenue | 16035.17 | 10747.72 | No issues
C004 | Warehouse D | T345 | Concrete Pouring | John Miller | Completed | Low | 2024-12-11 | 2024-12-21 | 2024-12-21 | 100 | Copper Wires | Industrial Park | 24589.99 | 20624.42 | No issues
C001 | Residential Building A | T639 | Roofing | Dave Brown | Not Started | Low | 2023-07-06 | 2023-07-24 |  | 0 | Copper Wires | Plot 21, Riverside | 33513.74 | 0 | Not started
C001 | Residential Building A | T736 | Steel Framework Setup | John Miller | In Progress | Low | 2023-10-04 | 2023-11-02 |  | 78 | Steel Beams | Plot 21, Riverside | 7737.93 | 7928.71 | In progress
C003 | Office Tower C | T819 | Foundation Excavation | Mike Adams | Completed | Low | 2024-06-16 | 2024-07-15 | 2024-07-15 | 100 | Paint | Downtown Avenue | 31968.61 | 24012.1 | No issues
C002 | Shopping Complex B | T889 | Electrical Wiring | Dave Brown | Completed | Medium | 2024-01-03 | 2024-01-20 | 2024-01-20 | 100 | Steel Beams | Market Street | 48338.65 | 62260.17 | No issues
C004 | Warehouse D | T800 | Plumbing Installations | Mike Adams | In Progress | Medium | 2024-07-09 | 2024-07-25 |  | 80 | Steel Beams | Industrial Park | 15498.77 | 17839.34 | In progress
C003 | Office Tower C | T506 | Foundation Excavation | Sarah Johnson | Completed | Low | 2023-09-05 | 2023-10-02 | 2023-10-02 | 100 | Copper Wires | Downtown Avenue | 40103.89 | 42837.45 | No issues
C004 | Warehouse D | T991 | Site Survey | Dave Brown | In Progress | High | 2023-11-23 | 2023-12-13 |  | 68 | Rebar | Industrial Park | 26830.16 | 28462.2 | In progress
C003 | Office Tower C | T699 | Steel Framework Setup | Dave Brown | In Progress | Low | 2024-03-19 | 2024-04-16 |  | 69 | Rebar | Downtown Avenue | 7900.88 | 5514.13 | In progress
C001 | Residential Building A | T667 | Roofing | Rachel Green | Completed | High | 2024-09-26 | 2024-10-09 | 2024-10-09 | 100 | Roofing Sheets | Plot 21, Riverside | 32839.95 | 22967.1 | No issues
C002 | Shopping Complex B | T978 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-10-03 | 2024-10-31 |  | 0 | Copper Wires | Market Street | 41129.42 | 0 | Not started
C003 | Office Tower C | T172 | Plumbing Installations | Emma White | Blocked | Low | 2024-11-01 | 2024-11-08 |  | 0 | Paint | Downtown Avenue | 39841.43 | 42982.58 | Not started
C003 | Office Tower C | T474 | Concrete Pouring | Grace Allen | Completed | Low | 2024-08-22 | 2024-09-05 | 2024-09-05 | 100 | Cement | Downtown Avenue | 36147.05 | 30629.04 | No issues
C003 | Office Tower C | T989 | Site Survey | Carlos Rivera | Blocked | Medium | 2024-07-10 | 2024-08-06 |  | 0 | Cement | Downtown Avenue | 46071.27 | 46502.79 | Not started
C004 | Warehouse D | T350 | Concrete Pouring | Dave Brown | Not Started | Low | 2023-06-12 | 2023-07-06 |  | 0 | Paint | Industrial Park | 48352.83 | 0 | Not started
C002 | Shopping Complex B | T177 | Roofing | Mike Adams | Blocked | High | 2024-08-15 | 2024-08-27 |  | 0 | Rebar | Market Street | 45378.34 | 55088.8 | Not started
C004 | Warehouse D | T564 | Site Survey | Mike Adams | Blocked | Low | 2024-05-27 | 2024-06-09 |  | 0 | Cement | Industrial Park | 41866.17 | 38373.7 | Not started
C001 | Residential Building A | T968 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-08-25 | 2024-09-09 |  | 0 | Copper Wires | Plot 21, Riverside | 20462.23 | 13542.5 | Not started
C004 | Warehouse D | T630 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2023-11-10 | 2023-11-21 |  | 88 | Roofing Sheets | Industrial Park | 45623.89 | 52997.74 | In progress
C001 | Residential Building A | T427 | Electrical Wiring | Emma White | Blocked | Medium | 2023-03-08 | 2023-04-05 |  | 0 | Cement | Plot 21, Riverside | 41153.02 | 45372.02 | Not started
C002 | Shopping Complex B | T926 | Electrical Wiring | Rachel Green | In Progress | Low | 2024-12-19 | 2025-01-14 |  | 97 | Cement | Market Street | 49016.5 | 60920.88 | In progress
C003 | Office Tower C | T944 | Site Survey | Rachel Green | In Progress | High | 2023-10-06 | 2023-10-15 |  | 93 | Cement | Downtown Avenue | 26927.67 | 27955.6 | In progress
C003 | Office Tower C | T150 | Roofing | Carlos Rivera | Blocked | Medium | 2023-12-04 | 2023-12-28 |  | 0 | Rebar | Downtown Avenue | 27337.15 | 18520.25 | Not started
C001 | Residential Building A | T149 | Interior Painting | Grace Allen | Not Started | High | 2023-07-10 | 2023-08-09 |  | 0 | Steel Beams | Plot 21, Riverside | 43573.6 | 0 | Not started
C004 | Warehouse D | T608 | Steel Framework Setup | Dave Brown | Completed | Medium | 2023-10-01 | 2023-10-15 | 2023-10-15 | 100 | Concrete | Industrial Park | 43187.93 | 30260.89 | No issues
C003 | Office Tower C | T748 | Steel Framework Setup | Emma White | Completed | High | 2024-05-06 | 2024-05-15 | 2024-05-15 | 100 | Paint | Downtown Avenue | 24770.2 | 19588.01 | No issues
C004 | Warehouse D | T122 | Concrete Pouring | Rachel Green | In Progress | Medium | 2024-07-15 | 2024-08-02 |  | 82 | Steel Beams | Industrial Park | 6710.66 | 5236.72 | In progress
C002 | Shopping Complex B | T917 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-08-25 | 2023-09-13 |  | 48 | Paint | Market Street | 17940.64 | 40570.95 | In progress
C002 | Shopping Complex B | T399 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2024-01-10 | 2024-01-23 |  | 97 | PVC Pipes | Market Street | 11664.66 | 33107.01 | In progress
C001 | Residential Building A | T625 | Concrete Pouring | Rachel Green | Completed | Medium | 2024-06-24 | 2024-07-07 | 2024-07-07 | 100 | Concrete | Plot 21, Riverside | 33080.44 | 27339.51 | No issues
C001 | Residential Building A | T289 | Site Survey | Mike Adams | Blocked | High | 2023-11-19 | 2023-12-15 |  | 0 | Roofing Sheets | Plot 21, Riverside | 46947.02 | 41610.77 | Not started
C004 | Warehouse D | T121 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2023-05-23 | 2023-06-03 |  | 0 | Steel Beams | Industrial Park | 27907.79 | 31809.47 | Not started
C002 | Shopping Complex B | T225 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2023-04-13 | 2023-05-07 |  | 0 | Copper Wires | Market Street | 6928.08 | 30873.25 | Not started
C002 | Shopping Complex B | T374 | Foundation Excavation | Dave Brown | Not Started | High | 2023-06-10 | 2023-07-08 |  | 0 | Concrete | Market Street | 17099.04 | 0 | Not started
C003 | Office Tower C | T649 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2023-07-19 | 2023-07-30 |  | 79 | Copper Wires | Downtown Avenue | 12799.39 | 8988.55 | In progress
C001 | Residential Building A | T432 | Electrical Wiring | John Miller | In Progress | Low | 2024-02-27 | 2024-03-18 |  | 30 | Rebar | Plot 21, Riverside | 13518.43 | 10222.96 | In progress
C001 | Residential Building A | T409 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-12-16 | 2024-01-03 |  | 71 | Cement | Plot 21, Riverside | 49941.48 | 32223.75 | In progress
C004 | Warehouse D | T763 | Electrical Wiring | Mike Adams | Blocked | High | 2023-01-17 | 2023-02-02 |  | 0 | Cement | Industrial Park | 28429.28 | 19497.46 | Not started
C002 | Shopping Complex B | T591 | Roofing | Emma White | Completed | High | 2023-03-21 | 2023-04-16 | 2023-04-16 | 100 | PVC Pipes | Market Street | 49596.34 | 66289.7 | No issues
C002 | Shopping Complex B | T673 | Interior Painting | Grace Allen | Not Started | Medium | 2023-05-21 | 2023-06-11 |  | 0 | Copper Wires | Market Street | 30955.18 | 0 | Not started
C004 | Warehouse D | T705 | Foundation Excavation | Dave Brown | Not Started | Low | 2024-04-04 | 2024-04-23 |  | 0 | Cement | Industrial Park | 39200.01 | 0 | Not started
C004 | Warehouse D | T359 | Foundation Excavation | Rachel Green | In Progress | High | 2024-06-20 | 2024-07-13 |  | 14 | Cement | Industrial Park | 12940.19 | 7945.78 | In progress
C004 | Warehouse D | T828 | Plumbing Installations | Rachel Green | Not Started | High | 2023-12-20 | 2024-01-11 |  | 0 | Concrete | Industrial Park | 10437.67 | 0 | Not started
C002 | Shopping Complex B | T218 | Plumbing Installations | Dave Brown | Blocked | High | 2024-08-09 | 2024-08-27 |  | 0 | Steel Beams | Market Street | 32461.64 | 46179.28 | Not started
C002 | Shopping Complex B | T477 | Foundation Excavation | Mike Adams | Not Started | Low | 2023-12-15 | 2023-12-27 |  | 0 | Steel Beams | Market Street | 25101.55 | 0 | Not started
C002 | Shopping Complex B | T515 | Plumbing Installations | John Miller | Not Started | Medium | 2023-01-16 | 2023-01-27 |  | 0 | Concrete | Market Street | 42686.28 | 0 | Not started
C002 | Shopping Complex B | T680 | Foundation Excavation | Dave Brown | Not Started | Medium | 2024-04-12 | 2024-04-30 |  | 0 | Roofing Sheets | Market Street | 22467.49 | 0 | Not started
C003 | Office Tower C | T856 | Electrical Wiring | Mike Adams | Completed | Low | 2024-10-10 | 2024-10-29 | 2024-10-29 | 100 | Rebar | Downtown Avenue | 49353.09 | 40449.71 | No issues
C002 | Shopping Complex B | T578 | Electrical Wiring | Mike Adams | Blocked | Low | 2024-07-04 | 2024-08-01 |  | 0 | Paint | Market Street | 30189.29 | 50663.89 | Not started
C001 | Residential Building A | T658 | Interior Painting | Dave Brown | Blocked | Medium | 2024-07-11 | 2024-07-29 |  | 0 | Cement | Plot 21, Riverside | 44390.59 | 37317.58 | Not started
C004 | Warehouse D | T312 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2023-01-17 | 2023-01-28 |  | 61 | Steel Beams | Industrial Park | 6813.33 | 5573.98 | In progress
C002 | Shopping Complex B | T209 | Plumbing Installations | Dave Brown | In Progress | Low | 2023-09-16 | 2023-10-09 |  | 78 | Copper Wires | Market Street | 38191.06 | 54397.3 | In progress
C002 | Shopping Complex B | T617 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2024-09-21 | 2024-10-21 |  | 0 | Cement | Market Street | 36134.32 | 63196.29 | Not started
C002 | Shopping Complex B | T301 | Roofing | Sarah Johnson | Not Started | Low | 2024-11-17 | 2024-12-15 |  | 0 | Roofing Sheets | Market Street | 8694.01 | 0 | Not started
C004 | Warehouse D | T570 | Interior Painting | Grace Allen | Completed | Medium | 2024-11-03 | 2024-12-03 | 2024-12-03 | 100 | Cement | Industrial Park | 25320.17 | 27004.62 | No issues
C003 | Office Tower C | T975 | Interior Painting | Rachel Green | In Progress | High | 2024-12-24 | 2025-01-02 |  | 10 | PVC Pipes | Downtown Avenue | 20021.39 | 16122.42 | In progress
C001 | Residential Building A | T869 | Interior Painting | Dave Brown | In Progress | High | 2024-08-08 | 2024-08-17 |  | 21 | Roofing Sheets | Plot 21, Riverside | 44602.3 | 33239.91 | In progress
C002 | Shopping Complex B | T159 | Site Survey | John Miller | In Progress | Low | 2024-08-28 | 2024-09-20 |  | 52 | Rebar | Market Street | 9937.78 | 32177.98 | In progress
C003 | Office Tower C | T600 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-01-12 | 2024-01-30 |  | 0 | Rebar | Downtown Avenue | 42465.53 | 0 | Not started
C003 | Office Tower C | T575 | Steel Framework Setup | Grace Allen | Completed | High | 2024-10-28 | 2024-11-21 | 2024-11-21 | 100 | PVC Pipes | Downtown Avenue | 49312.52 | 49216.82 | No issues
C001 | Residential Building A | T224 | Roofing | Rachel Green | Not Started | Medium | 2024-07-25 | 2024-08-05 |  | 0 | Paint | Plot 21, Riverside | 31048.55 | 0 | Not started
C003 | Office Tower C | T235 | Plumbing Installations | Rachel Green | In Progress | Medium | 2023-08-14 | 2023-08-28 |  | 44 | Steel Beams | Downtown Avenue | 23428.79 | 14955.19 | In progress
C001 | Residential Building A | T515 | Foundation Excavation | Dave Brown | Completed | High | 2023-08-22 | 2023-09-18 | 2023-09-18 | 100 | Steel Beams | Plot 21, Riverside | 42308.71 | 33773.26 | No issues
C004 | Warehouse D | T840 | Roofing | Emma White | In Progress | Medium | 2024-09-28 | 2024-10-27 |  | 69 | Cement | Industrial Park | 16939.02 | 12741.82 | In progress
C001 | Residential Building A | T654 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2024-01-24 | 2024-02-04 |  | 0 | Concrete | Plot 21, Riverside | 20882.06 | 24140.67 | Not started
C004 | Warehouse D | T655 | Roofing | Emma White | Completed | Medium | 2023-11-08 | 2023-11-18 | 2023-11-18 | 100 | Cement | Industrial Park | 10449.61 | 7990.94 | No issues
C003 | Office Tower C | T458 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-04-26 | 2023-05-12 |  | 0 | Roofing Sheets | Downtown Avenue | 17337.24 | 10948.71 | Not started
C004 | Warehouse D | T808 | Roofing | Emma White | Blocked | Medium | 2024-05-08 | 2024-05-15 |  | 0 | Steel Beams | Industrial Park | 48234.5 | 51093.07 | Not started
C004 | Warehouse D | T586 | Interior Painting | Rachel Green | Completed | Low | 2023-08-04 | 2023-08-19 | 2023-08-19 | 100 | Cement | Industrial Park | 23693.42 | 28322.45 | No issues
C003 | Office Tower C | T964 | Concrete Pouring | John Miller | Completed | Low | 2023-08-08 | 2023-08-29 | 2023-08-29 | 100 | Concrete | Downtown Avenue | 32184.8 | 34767.71 | No issues
C003 | Office Tower C | T112 | Steel Framework Setup | Dave Brown | Completed | Medium | 2023-11-25 | 2023-12-09 | 2023-12-09 | 100 | PVC Pipes | Downtown Avenue | 43366.47 | 47852.95 | No issues
C002 | Shopping Complex B | T560 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-12-15 | 2025-01-05 |  | 0 | PVC Pipes | Market Street | 15734.28 | 42736.85 | Not started
C001 | Residential Building A | T375 | Electrical Wiring | Mike Adams | Not Started | High | 2024-09-06 | 2024-09-30 |  | 0 | Cement | Plot 21, Riverside | 38268.19 | 0 | Not started
C001 | Residential Building A | T838 | Steel Framework Setup | Dave Brown | Blocked | Low | 2023-08-22 | 2023-09-15 |  | 0 | PVC Pipes | Plot 21, Riverside | 18879.91 | 11333.32 | Not started
C002 | Shopping Complex B | T675 | Plumbing Installations | Mike Adams | In Progress | High | 2024-09-22 | 2024-10-01 |  | 72 | Copper Wires | Market Street | 19840.52 | 41053.14 | In progress
C003 | Office Tower C | T793 | Steel Framework Setup | John Miller | Not Started | High | 2023-09-17 | 2023-10-10 |  | 0 | Steel Beams | Downtown Avenue | 6745.86 | 0 | Not started
C001 | Residential Building A | T553 | Roofing | Carlos Rivera | In Progress | Medium | 2024-12-05 | 2024-12-29 |  | 18 | Steel Beams | Plot 21, Riverside | 49576.81 | 46684.89 | In progress
C002 | Shopping Complex B | T347 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-04-18 | 2023-05-10 |  | 59 | Roofing Sheets | Market Street | 47122.89 | 62075.89 | In progress
C004 | Warehouse D | T233 | Interior Painting | Rachel Green | Completed | High | 2023-09-27 | 2023-10-06 | 2023-10-06 | 100 | PVC Pipes | Industrial Park | 42191.3 | 40540.19 | No issues
C002 | Shopping Complex B | T779 | Concrete Pouring | Rachel Green | Not Started | High | 2024-10-15 | 2024-10-26 |  | 0 | Steel Beams | Market Street | 7188.08 | 0 | Not started
C002 | Shopping Complex B | T851 | Roofing | John Miller | Completed | Low | 2024-07-11 | 2024-08-05 | 2024-08-05 | 100 | Steel Beams | Market Street | 12039.63 | 36640.37 | No issues
C003 | Office Tower C | T997 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2023-05-21 | 2023-06-05 |  | 0 | Steel Beams | Downtown Avenue | 10254.76 | 0 | Not started
C003 | Office Tower C | T120 | Steel Framework Setup | Rachel Green | Not Started | Low | 2024-06-09 | 2024-07-04 |  | 0 | Rebar | Downtown Avenue | 18905.68 | 0 | Not started
C003 | Office Tower C | T187 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2024-07-15 | 2024-08-07 |  | 22 | Cement | Downtown Avenue | 31516.99 | 33057.3 | In progress
C001 | Residential Building A | T986 | Concrete Pouring | Grace Allen | Not Started | High | 2024-06-02 | 2024-06-14 |  | 0 | Cement | Plot 21, Riverside | 6195.41 | 0 | Not started
C001 | Residential Building A | T621 | Concrete Pouring | Rachel Green | Not Started | High | 2023-08-19 | 2023-09-15 |  | 0 | Roofing Sheets | Plot 21, Riverside | 9888.86 | 0 | Not started
C002 | Shopping Complex B | T503 | Site Survey | Carlos Rivera | Completed | Medium | 2024-04-06 | 2024-04-27 | 2024-04-27 | 100 | Roofing Sheets | Market Street | 10129 | 32066.7 | No issues
C003 | Office Tower C | T384 | Foundation Excavation | Grace Allen | In Progress | High | 2023-11-06 | 2023-12-06 |  | 38 | Rebar | Downtown Avenue | 8014.43 | 9344.65 | In progress
C003 | Office Tower C | T587 | Steel Framework Setup | Mike Adams | Not Started | Medium | 2023-11-22 | 2023-12-21 |  | 0 | Steel Beams | Downtown Avenue | 14057.79 | 0 | Not started
C003 | Office Tower C | T317 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-11-24 | 2024-12-23 |  | 0 | Paint | Downtown Avenue | 39024.25 | 31378.25 | Not started
C002 | Shopping Complex B | T652 | Roofing | Sarah Johnson | In Progress | Low | 2024-08-28 | 2024-09-20 |  | 75 | Copper Wires | Market Street | 19356.49 | 46479.01 | In progress
C002 | Shopping Complex B | T365 | Roofing | Carlos Rivera | Blocked | Medium | 2024-08-03 | 2024-08-25 |  | 0 | Cement | Market Street | 9574.61 | 31822.25 | Not started
C001 | Residential Building A | T500 | Site Survey | Carlos Rivera | Not Started | Low | 2024-10-25 | 2024-11-08 |  | 0 | Rebar | Plot 21, Riverside | 45316.38 | 0 | Not started
C002 | Shopping Complex B | T167 | Steel Framework Setup | Mike Adams | Blocked | High | 2024-07-06 | 2024-07-25 |  | 0 | Rebar | Market Street | 44812.27 | 54255.86 | Not started
C002 | Shopping Complex B | T115 | Plumbing Installations | John Miller | In Progress | Medium | 2024-09-28 | 2024-10-06 |  | 9 | Steel Beams | Market Street | 12258.32 | 35376.69 | In progress
C002 | Shopping Complex B | T530 | Steel Framework Setup | Emma White | Blocked | Medium | 2023-04-27 | 2023-05-22 |  | 0 | Paint | Market Street | 45942.43 | 55560.47 | Not started
C003 | Office Tower C | T970 | Site Survey | Sarah Johnson | Not Started | Medium | 2024-07-27 | 2024-08-12 |  | 0 | Paint | Downtown Avenue | 30669.14 | 0 | Not started
C001 | Residential Building A | T838 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2024-01-08 | 2024-01-29 | 2024-01-29 | 100 | Roofing Sheets | Plot 21, Riverside | 46455.44 | 50644.64 | No issues
C003 | Office Tower C | T221 | Plumbing Installations | Grace Allen | Blocked | Medium | 2024-01-26 | 2024-02-22 |  | 0 | Steel Beams | Downtown Avenue | 18165.49 | 16701.31 | Not started
C004 | Warehouse D | T204 | Interior Painting | Sarah Johnson | In Progress | Low | 2023-08-09 | 2023-08-20 |  | 97 | Steel Beams | Industrial Park | 36747.28 | 38304.68 | In progress
C002 | Shopping Complex B | T150 | Site Survey | Rachel Green | Completed | High | 2023-09-08 | 2023-09-23 | 2023-09-23 | 100 | Roofing Sheets | Market Street | 35895.93 | 56440.39 | No issues
C004 | Warehouse D | T801 | Roofing | Rachel Green | In Progress | High | 2023-04-22 | 2023-05-06 |  | 0 | Paint | Industrial Park | 12221.2 | 8897.48 | In progress
C002 | Shopping Complex B | T563 | Concrete Pouring | Dave Brown | Completed | High | 2024-04-16 | 2024-05-09 | 2024-05-09 | 100 | Roofing Sheets | Market Street | 49404.1 | 78458.65 | No issues
C001 | Residential Building A | T704 | Concrete Pouring | Dave Brown | Completed | Low | 2024-04-16 | 2024-05-11 | 2024-05-11 | 100 | PVC Pipes | Plot 21, Riverside | 27083.92 | 20789.8 | No issues
C001 | Residential Building A | T989 | Steel Framework Setup | Dave Brown | Blocked | Low | 2023-08-11 | 2023-08-24 |  | 0 | PVC Pipes | Plot 21, Riverside | 45142.84 | 51154.52 | Not started
C004 | Warehouse D | T162 | Concrete Pouring | Rachel Green | In Progress | High | 2023-09-28 | 2023-10-09 |  | 72 | Roofing Sheets | Industrial Park | 14450.3 | 15227.23 | In progress
C002 | Shopping Complex B | T971 | Foundation Excavation | Mike Adams | Blocked | High | 2024-12-01 | 2024-12-23 |  | 0 | Cement | Market Street | 29704.19 | 47529.83 | Not started
C004 | Warehouse D | T310 | Electrical Wiring | Grace Allen | Blocked | Low | 2023-09-02 | 2023-10-02 |  | 0 | Rebar | Industrial Park | 13781.52 | 12146.88 | Not started
C001 | Residential Building A | T120 | Roofing | Rachel Green | Blocked | High | 2024-12-16 | 2025-01-04 |  | 0 | Concrete | Plot 21, Riverside | 29816.03 | 34392.1 | Not started
C002 | Shopping Complex B | T964 | Steel Framework Setup | Sarah Johnson | Completed | Low | 2024-07-06 | 2024-07-21 | 2024-07-21 | 100 | Copper Wires | Market Street | 35681.74 | 66404.9 | No issues
C001 | Residential Building A | T520 | Foundation Excavation | Grace Allen | Not Started | High | 2024-03-24 | 2024-04-07 |  | 0 | Cement | Plot 21, Riverside | 13395.89 | 0 | Not started
C001 | Residential Building A | T731 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2023-08-22 | 2023-09-09 |  | 60 | PVC Pipes | Plot 21, Riverside | 28725.7 | 30761.05 | In progress
C004 | Warehouse D | T358 | Site Survey | Grace Allen | Blocked | Medium | 2023-06-10 | 2023-06-25 |  | 0 | Copper Wires | Industrial Park | 29760.99 | 19518.84 | Not started
C004 | Warehouse D | T755 | Steel Framework Setup | Mike Adams | Blocked | High | 2024-04-18 | 2024-05-06 |  | 0 | Paint | Industrial Park | 45525.47 | 35405.64 | Not started
C002 | Shopping Complex B | T851 | Electrical Wiring | Rachel Green | In Progress | Medium | 2024-11-21 | 2024-12-16 |  | 4 | PVC Pipes | Market Street | 7788.21 | 31369.72 | In progress
C001 | Residential Building A | T874 | Roofing | Rachel Green | In Progress | Low | 2024-05-18 | 2024-06-15 |  | 33 | Roofing Sheets | Plot 21, Riverside | 18562.84 | 12207.56 | In progress
C003 | Office Tower C | T182 | Interior Painting | Emma White | Not Started | High | 2023-07-07 | 2023-08-01 |  | 0 | Steel Beams | Downtown Avenue | 24925.63 | 0 | Not started
C003 | Office Tower C | T741 | Concrete Pouring | Grace Allen | Completed | Low | 2024-07-13 | 2024-07-31 | 2024-07-31 | 100 | Roofing Sheets | Downtown Avenue | 32881.06 | 32366.86 | No issues
C001 | Residential Building A | T888 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2024-02-03 | 2024-02-24 |  | 74 | Paint | Plot 21, Riverside | 18179.71 | 15485.4 | In progress
C004 | Warehouse D | T797 | Concrete Pouring | Dave Brown | Not Started | Medium | 2024-03-01 | 2024-03-13 |  | 0 | Copper Wires | Industrial Park | 33375 | 0 | Not started
C002 | Shopping Complex B | T905 | Foundation Excavation | Rachel Green | In Progress | High | 2023-04-05 | 2023-04-19 |  | 78 | PVC Pipes | Market Street | 19886 | 39948.27 | In progress
C001 | Residential Building A | T417 | Roofing | Carlos Rivera | Not Started | Medium | 2024-08-28 | 2024-09-09 |  | 0 | Concrete | Plot 21, Riverside | 29882.44 | 0 | Not started
C004 | Warehouse D | T939 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-11-08 | 2023-11-29 |  | 87 | Copper Wires | Industrial Park | 16556.95 | 10844.83 | In progress
C001 | Residential Building A | T256 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-01-24 | 2023-02-11 |  | 57 | Rebar | Plot 21, Riverside | 24669.94 | 20493.51 | In progress
C002 | Shopping Complex B | T133 | Site Survey | Grace Allen | Completed | Low | 2024-03-02 | 2024-03-16 | 2024-03-16 | 100 | Cement | Market Street | 43904.96 | 62926.07 | No issues
C001 | Residential Building A | T878 | Interior Painting | Sarah Johnson | Completed | High | 2023-05-10 | 2023-06-06 | 2023-06-06 | 100 | Cement | Plot 21, Riverside | 32106.2 | 23415.49 | No issues
C003 | Office Tower C | T713 | Plumbing Installations | Carlos Rivera | Completed | Low | 2023-02-13 | 2023-02-21 | 2023-02-21 | 100 | PVC Pipes | Downtown Avenue | 42873.77 | 31241.64 | No issues
C004 | Warehouse D | T309 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2024-02-13 | 2024-03-04 |  | 0 | Paint | Industrial Park | 32146.85 | 35499.35 | Not started
C001 | Residential Building A | T818 | Concrete Pouring | Grace Allen | Blocked | High | 2024-07-09 | 2024-07-29 |  | 0 | Roofing Sheets | Plot 21, Riverside | 28025.41 | 24692.6 | Not started
C002 | Shopping Complex B | T282 | Site Survey | Emma White | Not Started | High | 2023-03-06 | 2023-03-16 |  | 0 | Paint | Market Street | 40490.51 | 0 | Not started
C001 | Residential Building A | T528 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2024-01-26 | 2024-02-12 |  | 0 | PVC Pipes | Plot 21, Riverside | 11402.55 | 0 | Not started
C002 | Shopping Complex B | T899 | Plumbing Installations | Mike Adams | Completed | High | 2023-07-03 | 2023-07-21 | 2023-07-21 | 100 | Steel Beams | Market Street | 20850.88 | 43902.75 | No issues
C002 | Shopping Complex B | T671 | Plumbing Installations | Emma White | Not Started | Low | 2024-11-16 | 2024-11-27 |  | 0 | Concrete | Market Street | 8768.48 | 0 | Not started
C002 | Shopping Complex B | T351 | Site Survey | Emma White | Completed | Medium | 2024-04-19 | 2024-05-09 | 2024-05-09 | 100 | Rebar | Market Street | 31995.28 | 52714.08 | No issues
C002 | Shopping Complex B | T327 | Concrete Pouring | Emma White | Completed | Medium | 2024-12-23 | 2025-01-01 | 2025-01-01 | 100 | Copper Wires | Market Street | 31012.85 | 58999.36 | No issues
C001 | Residential Building A | T134 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-01-10 | 2023-01-20 |  | 88 | Paint | Plot 21, Riverside | 31307.78 | 19217.86 | In progress
C002 | Shopping Complex B | T625 | Roofing | Emma White | In Progress | High | 2024-01-17 | 2024-02-02 |  | 52 | Concrete | Market Street | 49354.25 | 66354.89 | In progress
C001 | Residential Building A | T295 | Plumbing Installations | Grace Allen | Blocked | Medium | 2023-09-07 | 2023-09-24 |  | 0 | Concrete | Plot 21, Riverside | 38960.89 | 33647.32 | Not started
C002 | Shopping Complex B | T732 | Steel Framework Setup | Dave Brown | In Progress | High | 2024-04-19 | 2024-05-06 |  | 92 | Rebar | Market Street | 17303.33 | 44307.53 | In progress
C002 | Shopping Complex B | T480 | Plumbing Installations | Grace Allen | Not Started | Medium | 2024-06-15 | 2024-06-28 |  | 0 | Copper Wires | Market Street | 43661.02 | 0 | Not started
C003 | Office Tower C | T402 | Electrical Wiring | Mike Adams | Completed | High | 2024-10-19 | 2024-10-30 | 2024-10-30 | 100 | Rebar | Downtown Avenue | 24245.52 | 28202.29 | No issues
C003 | Office Tower C | T251 | Interior Painting | Grace Allen | In Progress | Medium | 2024-03-27 | 2024-04-17 |  | 34 | Steel Beams | Downtown Avenue | 34006.68 | 37809.65 | In progress
C003 | Office Tower C | T429 | Interior Painting | John Miller | Completed | Low | 2023-10-24 | 2023-11-12 | 2023-11-12 | 100 | Concrete | Downtown Avenue | 29729.16 | 27123.96 | No issues
C002 | Shopping Complex B | T209 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2023-03-12 | 2023-03-29 |  | 0 | Roofing Sheets | Market Street | 16452.88 | 0 | Not started
C002 | Shopping Complex B | T765 | Foundation Excavation | Grace Allen | In Progress | Low | 2023-11-28 | 2023-12-18 |  | 7 | Roofing Sheets | Market Street | 36696.17 | 55714.06 | In progress
C003 | Office Tower C | T319 | Foundation Excavation | Dave Brown | In Progress | Low | 2024-04-03 | 2024-04-25 |  | 64 | Copper Wires | Downtown Avenue | 27177.02 | 22278.6 | In progress
C004 | Warehouse D | T766 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-07-09 | 2023-08-02 |  | 0 | Roofing Sheets | Industrial Park | 20500.57 | 19381.97 | Not started
C002 | Shopping Complex B | T839 | Steel Framework Setup | Emma White | Blocked | High | 2024-06-23 | 2024-07-08 |  | 0 | Cement | Market Street | 43077.72 | 71082.28 | Not started
C002 | Shopping Complex B | T503 | Foundation Excavation | Emma White | Not Started | Low | 2023-03-16 | 2023-04-07 |  | 0 | Concrete | Market Street | 45044.32 | 0 | Not started
C002 | Shopping Complex B | T124 | Site Survey | Sarah Johnson | In Progress | Low | 2024-06-13 | 2024-07-10 |  | 29 | Roofing Sheets | Market Street | 26716.34 | 44599.05 | In progress
C003 | Office Tower C | T941 | Interior Painting | Mike Adams | Blocked | High | 2024-07-06 | 2024-07-21 |  | 0 | Roofing Sheets | Downtown Avenue | 38337.82 | 40077.74 | Not started
C003 | Office Tower C | T708 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2023-09-10 | 2023-10-03 |  | 34 | PVC Pipes | Downtown Avenue | 36837.42 | 24181.97 | In progress
C001 | Residential Building A | T965 | Interior Painting | Mike Adams | Not Started | Medium | 2024-07-21 | 2024-08-11 |  | 0 | Concrete | Plot 21, Riverside | 49694.68 | 0 | Not started
C004 | Warehouse D | T518 | Interior Painting | Dave Brown | Blocked | Low | 2024-10-03 | 2024-10-18 |  | 0 | Cement | Industrial Park | 21491.83 | 14171.89 | Not started
C003 | Office Tower C | T785 | Concrete Pouring | Grace Allen | Completed | Medium | 2023-09-14 | 2023-09-25 | 2023-09-25 | 100 | Concrete | Downtown Avenue | 32898.28 | 29658.26 | No issues
C002 | Shopping Complex B | T496 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-03-09 | 2023-04-04 |  | 23 | Rebar | Market Street | 45308 | 64785.45 | In progress
C004 | Warehouse D | T654 | Interior Painting | Mike Adams | Completed | High | 2023-12-21 | 2024-01-02 | 2024-01-02 | 100 | PVC Pipes | Industrial Park | 26662.25 | 31601.2 | No issues
C003 | Office Tower C | T151 | Plumbing Installations | Mike Adams | Completed | High | 2024-04-24 | 2024-05-01 | 2024-05-01 | 100 | Cement | Downtown Avenue | 10586.58 | 10114.24 | No issues
C003 | Office Tower C | T290 | Interior Painting | Emma White | Completed | High | 2023-01-24 | 2023-02-22 | 2023-02-22 | 100 | Copper Wires | Downtown Avenue | 41608.56 | 25810.09 | No issues
C004 | Warehouse D | T269 | Concrete Pouring | Grace Allen | Completed | Low | 2023-04-08 | 2023-04-20 | 2023-04-20 | 100 | Rebar | Industrial Park | 14206.5 | 10841.41 | No issues
C002 | Shopping Complex B | T517 | Concrete Pouring | Carlos Rivera | Completed | High | 2024-10-18 | 2024-11-14 | 2024-11-14 | 100 | Paint | Market Street | 18250.94 | 45543.84 | No issues
C004 | Warehouse D | T111 | Concrete Pouring | John Miller | Not Started | Low | 2024-07-03 | 2024-07-30 |  | 0 | Steel Beams | Industrial Park | 45307.58 | 0 | Not started
C001 | Residential Building A | T388 | Site Survey | John Miller | Not Started | Medium | 2024-01-25 | 2024-02-08 |  | 0 | Concrete | Plot 21, Riverside | 34879.78 | 0 | Not started
C001 | Residential Building A | T766 | Concrete Pouring | John Miller | Blocked | High | 2024-10-19 | 2024-11-12 |  | 0 | Concrete | Plot 21, Riverside | 38719.76 | 34682.32 | Not started
C002 | Shopping Complex B | T617 | Foundation Excavation | Dave Brown | In Progress | Medium | 2023-03-27 | 2023-04-17 |  | 70 | Steel Beams | Market Street | 39609.8 | 66736.28 | In progress
C004 | Warehouse D | T908 | Interior Painting | Mike Adams | Completed | Medium | 2024-06-10 | 2024-06-25 | 2024-06-25 | 100 | Roofing Sheets | Industrial Park | 14336.65 | 14986.26 | No issues
C002 | Shopping Complex B | T772 | Interior Painting | Grace Allen | Not Started | High | 2023-02-24 | 2023-03-14 |  | 0 | Copper Wires | Market Street | 42773.52 | 0 | Not started
C001 | Residential Building A | T546 | Plumbing Installations | Emma White | Not Started | Medium | 2023-07-13 | 2023-08-09 |  | 0 | Concrete | Plot 21, Riverside | 14595.27 | 0 | Not started
C001 | Residential Building A | T167 | Roofing | Dave Brown | Blocked | Low | 2023-12-11 | 2024-01-01 |  | 0 | Rebar | Plot 21, Riverside | 19143.85 | 12814.86 | Not started
C004 | Warehouse D | T614 | Site Survey | Rachel Green | Completed | Low | 2024-04-21 | 2024-05-17 | 2024-05-17 | 100 | Roofing Sheets | Industrial Park | 21846.6 | 17696.61 | No issues
C004 | Warehouse D | T424 | Roofing | Grace Allen | Blocked | High | 2024-04-06 | 2024-04-14 |  | 0 | Concrete | Industrial Park | 29031.12 | 29991.28 | Not started
C003 | Office Tower C | T713 | Site Survey | Grace Allen | Not Started | Low | 2023-04-05 | 2023-04-13 |  | 0 | Paint | Downtown Avenue | 25704.79 | 0 | Not started
C001 | Residential Building A | T314 | Steel Framework Setup | Carlos Rivera | Not Started | High | 2023-02-18 | 2023-03-13 |  | 0 | Steel Beams | Plot 21, Riverside | 31180.47 | 0 | Not started
C003 | Office Tower C | T499 | Plumbing Installations | Grace Allen | Blocked | Medium | 2023-07-19 | 2023-08-12 |  | 0 | Roofing Sheets | Downtown Avenue | 36851.12 | 37260.9 | Not started
C003 | Office Tower C | T255 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2024-09-15 | 2024-10-01 |  | 0 | Copper Wires | Downtown Avenue | 13282.55 | 0 | Not started
C003 | Office Tower C | T632 | Roofing | Sarah Johnson | In Progress | High | 2023-01-22 | 2023-02-03 |  | 21 | PVC Pipes | Downtown Avenue | 17064.64 | 16712.81 | In progress
C002 | Shopping Complex B | T254 | Steel Framework Setup | Dave Brown | Completed | Low | 2023-07-21 | 2023-08-04 | 2023-08-04 | 100 | Steel Beams | Market Street | 48912.15 | 72248.52 | No issues
C001 | Residential Building A | T366 | Roofing | Sarah Johnson | Completed | Medium | 2024-07-06 | 2024-07-28 | 2024-07-28 | 100 | Roofing Sheets | Plot 21, Riverside | 33792.41 | 24383.26 | No issues
C003 | Office Tower C | T307 | Site Survey | Rachel Green | In Progress | High | 2024-10-23 | 2024-11-08 |  | 19 | Paint | Downtown Avenue | 49172.54 | 51967.32 | In progress
C003 | Office Tower C | T282 | Interior Painting | Sarah Johnson | In Progress | Low | 2024-08-24 | 2024-09-11 |  | 56 | Rebar | Downtown Avenue | 40662.01 | 30877.86 | In progress
C001 | Residential Building A | T987 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-11-21 | 2024-12-06 |  | 28 | Paint | Plot 21, Riverside | 25110.8 | 15581.13 | In progress
C004 | Warehouse D | T833 | Roofing | Mike Adams | In Progress | High | 2023-02-16 | 2023-03-10 |  | 69 | Steel Beams | Industrial Park | 24695.22 | 18589.28 | In progress
C002 | Shopping Complex B | T581 | Site Survey | Dave Brown | Completed | Low | 2023-06-10 | 2023-06-19 | 2023-06-19 | 100 | PVC Pipes | Market Street | 46693.53 | 81471.46 | No issues
C002 | Shopping Complex B | T275 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2024-05-22 | 2024-05-29 |  | 96 | Rebar | Market Street | 15518.3 | 36694.07 | In progress
C001 | Residential Building A | T114 | Interior Painting | Carlos Rivera | Completed | High | 2024-04-11 | 2024-04-30 | 2024-04-30 | 100 | Copper Wires | Plot 21, Riverside | 49318.39 | 31615.49 | No issues
C003 | Office Tower C | T659 | Foundation Excavation | Grace Allen | Not Started | Medium | 2023-05-05 | 2023-05-14 |  | 0 | PVC Pipes | Downtown Avenue | 48705.05 | 0 | Not started
C001 | Residential Building A | T292 | Steel Framework Setup | John Miller | Not Started | Low | 2024-03-07 | 2024-03-16 |  | 0 | Cement | Plot 21, Riverside | 23778.66 | 0 | Not started
C002 | Shopping Complex B | T982 | Steel Framework Setup | John Miller | Not Started | Low | 2023-12-07 | 2023-12-14 |  | 0 | Cement | Market Street | 43829.04 | 0 | Not started
C002 | Shopping Complex B | T593 | Steel Framework Setup | Carlos Rivera | Completed | High | 2023-05-24 | 2023-06-12 | 2023-06-12 | 100 | Rebar | Market Street | 44477.37 | 64749.1 | No issues
C002 | Shopping Complex B | T236 | Electrical Wiring | John Miller | Blocked | Low | 2024-09-06 | 2024-09-28 |  | 0 | Cement | Market Street | 39058.19 | 54075.53 | Not started
C001 | Residential Building A | T729 | Foundation Excavation | Sarah Johnson | Not Started | Medium | 2024-09-22 | 2024-09-29 |  | 0 | Paint | Plot 21, Riverside | 24841.88 | 0 | Not started
C004 | Warehouse D | T599 | Roofing | Grace Allen | Completed | Medium | 2023-06-15 | 2023-06-26 | 2023-06-26 | 100 | Steel Beams | Industrial Park | 7989.35 | 9261.58 | No issues
C001 | Residential Building A | T106 | Interior Painting | John Miller | Blocked | Low | 2023-08-15 | 2023-08-22 |  | 0 | Rebar | Plot 21, Riverside | 37016.44 | 28727.74 | Not started
C003 | Office Tower C | T781 | Plumbing Installations | Sarah Johnson | Blocked | High | 2024-07-10 | 2024-08-09 |  | 0 | Copper Wires | Downtown Avenue | 43615.36 | 28184.96 | Not started
C002 | Shopping Complex B | T510 | Site Survey | Emma White | Completed | Low | 2023-02-02 | 2023-02-18 | 2023-02-18 | 100 | Roofing Sheets | Market Street | 28242.73 | 45462.09 | No issues
C004 | Warehouse D | T664 | Foundation Excavation | John Miller | In Progress | Medium | 2024-10-16 | 2024-10-24 |  | 62 | Rebar | Industrial Park | 13583.85 | 11860.38 | In progress
C002 | Shopping Complex B | T182 | Electrical Wiring | Carlos Rivera | Completed | High | 2023-07-05 | 2023-08-04 | 2023-08-04 | 100 | Roofing Sheets | Market Street | 18934.77 | 37274.51 | No issues
C001 | Residential Building A | T771 | Plumbing Installations | Mike Adams | Completed | High | 2023-04-06 | 2023-04-27 | 2023-04-27 | 100 | PVC Pipes | Plot 21, Riverside | 37832.82 | 37369.95 | No issues
C001 | Residential Building A | T271 | Roofing | Carlos Rivera | Not Started | Medium | 2023-02-05 | 2023-02-23 |  | 0 | Paint | Plot 21, Riverside | 13500.6 | 0 | Not started
C002 | Shopping Complex B | T239 | Foundation Excavation | Dave Brown | Completed | Low | 2023-01-03 | 2023-01-11 | 2023-01-11 | 100 | Paint | Market Street | 6269.28 | 30089.78 | No issues
C004 | Warehouse D | T623 | Concrete Pouring | Emma White | Not Started | High | 2024-05-20 | 2024-06-16 |  | 0 | Steel Beams | Industrial Park | 35732.08 | 0 | Not started
C001 | Residential Building A | T964 | Electrical Wiring | John Miller | Completed | Medium | 2024-09-10 | 2024-10-01 | 2024-10-01 | 100 | Cement | Plot 21, Riverside | 48838.15 | 53147.4 | No issues
C004 | Warehouse D | T218 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-07-06 | 2023-07-19 |  | 0 | PVC Pipes | Industrial Park | 10850.9 | 10405.46 | Not started
C001 | Residential Building A | T834 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2024-06-03 | 2024-06-17 |  | 0 | Concrete | Plot 21, Riverside | 11055.2 | 0 | Not started
C002 | Shopping Complex B | T189 | Concrete Pouring | Dave Brown | Completed | Medium | 2024-11-17 | 2024-11-24 | 2024-11-24 | 100 | Concrete | Market Street | 46418.89 | 77152.6 | No issues
C004 | Warehouse D | T771 | Plumbing Installations | Dave Brown | Not Started | Medium | 2024-08-24 | 2024-09-02 |  | 0 | Copper Wires | Industrial Park | 13547.18 | 0 | Not started
C001 | Residential Building A | T434 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2024-08-18 | 2024-09-02 |  | 0 | Copper Wires | Plot 21, Riverside | 34515.62 | 35218.84 | Not started
C002 | Shopping Complex B | T612 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2024-04-26 | 2024-05-06 |  | 39 | PVC Pipes | Market Street | 40410.59 | 69247.78 | In progress
C004 | Warehouse D | T360 | Foundation Excavation | Grace Allen | Completed | Medium | 2024-10-21 | 2024-11-15 | 2024-11-15 | 100 | Steel Beams | Industrial Park | 43609.08 | 32678.84 | No issues
C002 | Shopping Complex B | T151 | Foundation Excavation | Mike Adams | Blocked | High | 2023-02-10 | 2023-03-02 |  | 0 | Paint | Market Street | 41063.91 | 63470.23 | Not started
C004 | Warehouse D | T529 | Concrete Pouring | Dave Brown | Blocked | Low | 2023-08-15 | 2023-08-23 |  | 0 | Concrete | Industrial Park | 47904.34 | 55058.33 | Not started
C004 | Warehouse D | T605 | Concrete Pouring | Rachel Green | Blocked | Medium | 2023-04-05 | 2023-04-21 |  | 0 | Roofing Sheets | Industrial Park | 5922.91 | 4697.98 | Not started
C002 | Shopping Complex B | T351 | Foundation Excavation | Carlos Rivera | Not Started | High | 2024-01-07 | 2024-01-14 |  | 0 | Steel Beams | Market Street | 19811.79 | 0 | Not started
C004 | Warehouse D | T706 | Site Survey | Mike Adams | Completed | High | 2024-05-28 | 2024-06-26 | 2024-06-26 | 100 | Rebar | Industrial Park | 40063.6 | 37057.47 | No issues
C001 | Residential Building A | T343 | Site Survey | Sarah Johnson | Completed | Low | 2023-09-28 | 2023-10-19 | 2023-10-19 | 100 | Cement | Plot 21, Riverside | 44999.55 | 51891.02 | No issues
C004 | Warehouse D | T788 | Foundation Excavation | Mike Adams | Not Started | Medium | 2023-07-08 | 2023-07-25 |  | 0 | Concrete | Industrial Park | 25898.97 | 0 | Not started
C002 | Shopping Complex B | T145 | Roofing | Rachel Green | Completed | Low | 2023-11-14 | 2023-12-10 | 2023-12-10 | 100 | Paint | Market Street | 48777.99 | 78675.32 | No issues
C001 | Residential Building A | T115 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-01-03 | 2023-01-11 |  | 0 | Copper Wires | Plot 21, Riverside | 17551.7 | 0 | Not started
C002 | Shopping Complex B | T405 | Electrical Wiring | Rachel Green | Blocked | High | 2024-10-20 | 2024-10-28 |  | 0 | Rebar | Market Street | 14462.06 | 38962.18 | Not started
C004 | Warehouse D | T243 | Roofing | Dave Brown | In Progress | High | 2023-06-11 | 2023-07-03 |  | 8 | Steel Beams | Industrial Park | 37097.3 | 25715.78 | In progress
C002 | Shopping Complex B | T638 | Foundation Excavation | Emma White | Blocked | Low | 2023-07-16 | 2023-08-13 |  | 0 | Copper Wires | Market Street | 7250.59 | 33732.41 | Not started
C004 | Warehouse D | T211 | Plumbing Installations | Dave Brown | In Progress | Medium | 2023-03-15 | 2023-03-24 |  | 11 | Rebar | Industrial Park | 41172.03 | 34472.82 | In progress
C004 | Warehouse D | T496 | Electrical Wiring | Emma White | Blocked | High | 2024-11-20 | 2024-12-15 |  | 0 | Paint | Industrial Park | 32703.4 | 31053.64 | Not started
C003 | Office Tower C | T741 | Interior Painting | Sarah Johnson | Not Started | Low | 2024-03-07 | 2024-03-19 |  | 0 | Cement | Downtown Avenue | 35139.11 | 0 | Not started
C003 | Office Tower C | T182 | Site Survey | Grace Allen | Completed | Low | 2024-02-17 | 2024-03-13 | 2024-03-13 | 100 | Cement | Downtown Avenue | 16817.58 | 14838.62 | No issues
C003 | Office Tower C | T413 | Steel Framework Setup | Grace Allen | In Progress | Low | 2024-04-07 | 2024-04-30 |  | 9 | PVC Pipes | Downtown Avenue | 13576.72 | 15050.23 | In progress
C002 | Shopping Complex B | T599 | Plumbing Installations | Sarah Johnson | In Progress | Medium | 2024-02-19 | 2024-03-19 |  | 30 | Steel Beams | Market Street | 42331.16 | 73957.99 | In progress
C001 | Residential Building A | T266 | Plumbing Installations | Dave Brown | Completed | Low | 2024-09-12 | 2024-10-07 | 2024-10-07 | 100 | Rebar | Plot 21, Riverside | 24890.19 | 24896.04 | No issues
C003 | Office Tower C | T572 | Foundation Excavation | John Miller | Not Started | High | 2024-01-15 | 2024-02-05 |  | 0 | Roofing Sheets | Downtown Avenue | 10642.48 | 0 | Not started
C003 | Office Tower C | T835 | Plumbing Installations | John Miller | In Progress | Medium | 2023-05-26 | 2023-06-19 |  | 68 | Roofing Sheets | Downtown Avenue | 43724.51 | 36901.1 | In progress
C003 | Office Tower C | T878 | Interior Painting | Mike Adams | Blocked | Low | 2023-09-23 | 2023-10-18 |  | 0 | Paint | Downtown Avenue | 7327.13 | 8544.65 | Not started
C001 | Residential Building A | T587 | Roofing | Carlos Rivera | Completed | High | 2024-12-13 | 2025-01-07 | 2025-01-07 | 100 | Roofing Sheets | Plot 21, Riverside | 49984.57 | 41486.22 | No issues
C004 | Warehouse D | T985 | Electrical Wiring | Mike Adams | Completed | Medium | 2024-06-14 | 2024-07-05 | 2024-07-05 | 100 | Rebar | Industrial Park | 5891.7 | 3951.32 | No issues
C004 | Warehouse D | T246 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-12-19 | 2025-01-18 |  | 80 | PVC Pipes | Industrial Park | 21466.12 | 19612.9 | In progress
C002 | Shopping Complex B | T775 | Roofing | John Miller | Blocked | Medium | 2024-05-20 | 2024-06-18 |  | 0 | Concrete | Market Street | 28625.53 | 46701.1 | Not started
C004 | Warehouse D | T668 | Plumbing Installations | Rachel Green | Blocked | Low | 2024-11-13 | 2024-12-10 |  | 0 | Concrete | Industrial Park | 38547.07 | 42979.86 | Not started
C002 | Shopping Complex B | T954 | Roofing | Mike Adams | Not Started | High | 2023-10-16 | 2023-10-24 |  | 0 | Paint | Market Street | 32102.58 | 0 | Not started
C003 | Office Tower C | T465 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2024-05-25 | 2024-06-04 |  | 0 | Roofing Sheets | Downtown Avenue | 44256.6 | 42838.13 | Not started
C003 | Office Tower C | T714 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-02-03 | 2023-02-14 |  | 0 | Rebar | Downtown Avenue | 25399.51 | 23947.46 | Not started
C003 | Office Tower C | T451 | Plumbing Installations | Mike Adams | Completed | High | 2024-08-19 | 2024-09-18 | 2024-09-18 | 100 | Cement | Downtown Avenue | 34020.13 | 28159.7 | No issues
C001 | Residential Building A | T746 | Roofing | Mike Adams | Completed | High | 2023-05-13 | 2023-05-20 | 2023-05-20 | 100 | Steel Beams | Plot 21, Riverside | 20928.32 | 20998.75 | No issues
C002 | Shopping Complex B | T937 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-03-01 | 2023-03-21 |  | 0 | Copper Wires | Market Street | 39629.7 | 0 | Not started
C004 | Warehouse D | T878 | Site Survey | Emma White | Not Started | High | 2023-05-16 | 2023-05-25 |  | 0 | Rebar | Industrial Park | 27908.32 | 0 | Not started
C004 | Warehouse D | T437 | Steel Framework Setup | John Miller | Not Started | Low | 2023-05-12 | 2023-05-23 |  | 0 | Copper Wires | Industrial Park | 7606.76 | 0 | Not started
C004 | Warehouse D | T244 | Interior Painting | Emma White | Blocked | Medium | 2023-08-15 | 2023-09-07 |  | 0 | Steel Beams | Industrial Park | 25059.29 | 25480.43 | Not started
C002 | Shopping Complex B | T851 | Site Survey | Grace Allen | Completed | Medium | 2023-10-12 | 2023-10-24 | 2023-10-24 | 100 | Steel Beams | Market Street | 27919.99 | 52523.47 | No issues
C004 | Warehouse D | T830 | Site Survey | John Miller | In Progress | Low | 2023-09-06 | 2023-09-21 |  | 36 | Copper Wires | Industrial Park | 9117.54 | 5534.22 | In progress
C001 | Residential Building A | T721 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2024-10-08 | 2024-10-20 |  | 0 | Copper Wires | Plot 21, Riverside | 10850.74 | 8466.74 | Not started
C004 | Warehouse D | T807 | Concrete Pouring | Dave Brown | In Progress | Medium | 2024-08-17 | 2024-09-02 |  | 35 | Concrete | Industrial Park | 34148.36 | 21849.52 | In progress
C004 | Warehouse D | T602 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-03-04 | 2024-04-03 | 2024-04-03 | 100 | Concrete | Industrial Park | 49564.18 | 59439.64 | No issues
C004 | Warehouse D | T603 | Plumbing Installations | Rachel Green | In Progress | Medium | 2023-03-21 | 2023-04-18 |  | 65 | Paint | Industrial Park | 27999.46 | 33201.69 | In progress
C002 | Shopping Complex B | T663 | Interior Painting | John Miller | Not Started | Medium | 2023-07-23 | 2023-08-21 |  | 0 | Copper Wires | Market Street | 45718.95 | 0 | Not started
C003 | Office Tower C | T338 | Plumbing Installations | Grace Allen | Blocked | High | 2024-12-12 | 2024-12-29 |  | 0 | Steel Beams | Downtown Avenue | 46783.61 | 35381.61 | Not started
C003 | Office Tower C | T737 | Steel Framework Setup | Emma White | Not Started | High | 2024-11-10 | 2024-12-09 |  | 0 | PVC Pipes | Downtown Avenue | 39439.43 | 0 | Not started
C001 | Residential Building A | T811 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2024-09-17 | 2024-09-24 |  | 72 | Paint | Plot 21, Riverside | 13594.34 | 12406.42 | In progress
C004 | Warehouse D | T449 | Roofing | Emma White | Not Started | Low | 2024-01-26 | 2024-02-22 |  | 0 | Copper Wires | Industrial Park | 43789.2 | 0 | Not started
C004 | Warehouse D | T458 | Concrete Pouring | Grace Allen | Not Started | Low | 2023-12-23 | 2024-01-18 |  | 0 | Rebar | Industrial Park | 27406.64 | 0 | Not started
C004 | Warehouse D | T597 | Interior Painting | Sarah Johnson | Not Started | High | 2023-06-07 | 2023-07-04 |  | 0 | Rebar | Industrial Park | 48611.57 | 0 | Not started
C001 | Residential Building A | T754 | Site Survey | John Miller | Completed | High | 2024-11-06 | 2024-11-30 | 2024-11-30 | 100 | Steel Beams | Plot 21, Riverside | 39811.08 | 36334.55 | No issues
C002 | Shopping Complex B | T601 | Site Survey | Mike Adams | Not Started | Medium | 2024-09-17 | 2024-10-16 |  | 0 | Roofing Sheets | Market Street | 13820.01 | 0 | Not started
C002 | Shopping Complex B | T659 | Electrical Wiring | Grace Allen | Completed | High | 2023-04-19 | 2023-05-15 | 2023-05-15 | 100 | Roofing Sheets | Market Street | 32196.47 | 61245.46 | No issues
C004 | Warehouse D | T138 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2023-02-15 | 2023-03-08 |  | 0 | PVC Pipes | Industrial Park | 27071.3 | 0 | Not started
C004 | Warehouse D | T706 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2024-12-06 | 2024-12-24 |  | 0 | Concrete | Industrial Park | 35231.1 | 34970.24 | Not started
C001 | Residential Building A | T531 | Steel Framework Setup | Mike Adams | In Progress | Low | 2024-08-26 | 2024-09-14 |  | 23 | Paint | Plot 21, Riverside | 17369.42 | 13836.22 | In progress
C002 | Shopping Complex B | T530 | Site Survey | Emma White | Not Started | High | 2023-09-17 | 2023-09-24 |  | 0 | Copper Wires | Market Street | 31763.89 | 0 | Not started
C003 | Office Tower C | T505 | Plumbing Installations | Rachel Green | Completed | Low | 2024-09-18 | 2024-10-05 | 2024-10-05 | 100 | PVC Pipes | Downtown Avenue | 37462.76 | 42429.41 | No issues
C002 | Shopping Complex B | T465 | Steel Framework Setup | Carlos Rivera | Completed | High | 2023-12-05 | 2023-12-30 | 2023-12-30 | 100 | Copper Wires | Market Street | 46619.12 | 76347.58 | No issues
C001 | Residential Building A | T410 | Site Survey | Carlos Rivera | In Progress | Medium | 2024-04-10 | 2024-05-09 |  | 76 | Concrete | Plot 21, Riverside | 43929.77 | 27043.15 | In progress
C004 | Warehouse D | T481 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-05-15 | 2024-06-03 |  | 0 | Paint | Industrial Park | 45249.81 | 0 | Not started
C003 | Office Tower C | T989 | Concrete Pouring | Carlos Rivera | Completed | High | 2023-10-05 | 2023-10-15 | 2023-10-15 | 100 | Roofing Sheets | Downtown Avenue | 38353.14 | 27507.2 | No issues
C003 | Office Tower C | T515 | Foundation Excavation | Rachel Green | Completed | High | 2024-01-09 | 2024-02-07 | 2024-02-07 | 100 | Rebar | Downtown Avenue | 25970.14 | 22036.02 | No issues
C001 | Residential Building A | T929 | Electrical Wiring | Emma White | In Progress | High | 2024-04-26 | 2024-05-21 |  | 2 | Paint | Plot 21, Riverside | 23821.83 | 14881.23 | In progress
C003 | Office Tower C | T216 | Concrete Pouring | Emma White | Completed | Medium | 2024-04-08 | 2024-04-17 | 2024-04-17 | 100 | Rebar | Downtown Avenue | 46032.13 | 32538.22 | No issues
C002 | Shopping Complex B | T510 | Site Survey | Dave Brown | In Progress | Medium | 2024-01-02 | 2024-01-31 |  | 18 | Cement | Market Street | 8225.09 | 34383.87 | In progress
C002 | Shopping Complex B | T209 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-07-01 | 2024-07-18 |  | 24 | Roofing Sheets | Market Street | 12850.71 | 35625.79 | In progress
C001 | Residential Building A | T913 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2024-04-26 | 2024-05-03 |  | 0 | Paint | Plot 21, Riverside | 29788.61 | 18351.42 | Not started
C003 | Office Tower C | T186 | Site Survey | Emma White | Not Started | Low | 2023-04-09 | 2023-05-02 |  | 0 | Roofing Sheets | Downtown Avenue | 10004.55 | 0 | Not started
C003 | Office Tower C | T814 | Site Survey | Rachel Green | In Progress | High | 2023-06-02 | 2023-06-27 |  | 29 | Copper Wires | Downtown Avenue | 24904.88 | 28115.5 | In progress
C003 | Office Tower C | T283 | Foundation Excavation | Carlos Rivera | Completed | Medium | 2023-06-15 | 2023-06-27 | 2023-06-27 | 100 | Copper Wires | Downtown Avenue | 48465.41 | 35736.69 | No issues
C004 | Warehouse D | T330 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-02-05 | 2023-03-05 |  | 0 | Roofing Sheets | Industrial Park | 44812.41 | 0 | Not started
C004 | Warehouse D | T859 | Site Survey | Emma White | Not Started | Medium | 2023-03-12 | 2023-04-05 |  | 0 | Concrete | Industrial Park | 16506.09 | 0 | Not started
C001 | Residential Building A | T227 | Roofing | Sarah Johnson | Blocked | High | 2024-10-08 | 2024-11-04 |  | 0 | PVC Pipes | Plot 21, Riverside | 10473.24 | 7156.19 | Not started
C001 | Residential Building A | T612 | Site Survey | Grace Allen | Completed | High | 2024-09-17 | 2024-10-17 | 2024-10-17 | 100 | Rebar | Plot 21, Riverside | 22895.98 | 24161.84 | No issues
C001 | Residential Building A | T743 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2023-01-10 | 2023-01-25 |  | 0 | Copper Wires | Plot 21, Riverside | 49106.08 | 55685.29 | Not started
C002 | Shopping Complex B | T589 | Interior Painting | Dave Brown | Completed | High | 2023-12-06 | 2023-12-28 | 2023-12-28 | 100 | PVC Pipes | Market Street | 45333.4 | 78880.69 | No issues
C002 | Shopping Complex B | T126 | Steel Framework Setup | Grace Allen | Completed | High | 2024-03-17 | 2024-04-16 | 2024-04-16 | 100 | PVC Pipes | Market Street | 20865.83 | 47513.24 | No issues
C002 | Shopping Complex B | T558 | Site Survey | Sarah Johnson | Not Started | Low | 2024-04-13 | 2024-05-09 |  | 0 | Paint | Market Street | 37586.66 | 0 | Not started
C004 | Warehouse D | T436 | Concrete Pouring | Sarah Johnson | In Progress | High | 2024-01-04 | 2024-01-24 |  | 87 | Concrete | Industrial Park | 5455.85 | 4795.94 | In progress
C002 | Shopping Complex B | T506 | Plumbing Installations | Emma White | Blocked | Medium | 2024-07-05 | 2024-07-29 |  | 0 | Cement | Market Street | 35863.77 | 53494.74 | Not started
C001 | Residential Building A | T258 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2024-06-04 | 2024-06-24 |  | 3 | Steel Beams | Plot 21, Riverside | 23925.75 | 28292.78 | In progress
C002 | Shopping Complex B | T162 | Site Survey | Emma White | Completed | Low | 2023-11-20 | 2023-11-29 | 2023-11-29 | 100 | Rebar | Market Street | 22935.08 | 43959.57 | No issues
C002 | Shopping Complex B | T133 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2024-11-15 | 2024-12-15 |  | 87 | Roofing Sheets | Market Street | 44217.06 | 61133.68 | In progress
C002 | Shopping Complex B | T643 | Foundation Excavation | Mike Adams | Blocked | High | 2024-06-10 | 2024-06-26 |  | 0 | PVC Pipes | Market Street | 6515.14 | 29679.71 | Not started
C003 | Office Tower C | T403 | Site Survey | Carlos Rivera | Blocked | Medium | 2023-11-09 | 2023-11-22 |  | 0 | PVC Pipes | Downtown Avenue | 5147.07 | 4984.88 | Not started
C003 | Office Tower C | T203 | Electrical Wiring | Emma White | Blocked | Medium | 2024-05-04 | 2024-05-29 |  | 0 | Paint | Downtown Avenue | 23962.29 | 14916.51 | Not started
C001 | Residential Building A | T420 | Steel Framework Setup | Mike Adams | Not Started | Low | 2023-10-04 | 2023-10-18 |  | 0 | Rebar | Plot 21, Riverside | 41885.14 | 0 | Not started
C001 | Residential Building A | T968 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2023-11-24 | 2023-12-08 |  | 0 | Rebar | Plot 21, Riverside | 25857.3 | 0 | Not started
C004 | Warehouse D | T433 | Interior Painting | John Miller | Not Started | Low | 2023-11-26 | 2023-12-25 |  | 0 | Copper Wires | Industrial Park | 42455.98 | 0 | Not started
C002 | Shopping Complex B | T160 | Site Survey | Dave Brown | Completed | Low | 2024-12-27 | 2025-01-26 | 2025-01-26 | 100 | Cement | Market Street | 43493.37 | 54067.64 | No issues
C004 | Warehouse D | T634 | Concrete Pouring | Dave Brown | Not Started | Medium | 2024-09-24 | 2024-10-08 |  | 0 | Steel Beams | Industrial Park | 19456.76 | 0 | Not started
C003 | Office Tower C | T698 | Electrical Wiring | Rachel Green | Blocked | High | 2023-07-28 | 2023-08-26 |  | 0 | PVC Pipes | Downtown Avenue | 40511.34 | 42662.1 | Not started
C003 | Office Tower C | T374 | Foundation Excavation | Emma White | Blocked | High | 2024-08-04 | 2024-08-26 |  | 0 | PVC Pipes | Downtown Avenue | 26465.03 | 21459.95 | Not started
C004 | Warehouse D | T900 | Roofing | Rachel Green | Blocked | Low | 2024-06-13 | 2024-07-03 |  | 0 | Copper Wires | Industrial Park | 44714.23 | 40542.7 | Not started
C003 | Office Tower C | T860 | Steel Framework Setup | Emma White | Completed | Medium | 2024-03-10 | 2024-03-25 | 2024-03-25 | 100 | Roofing Sheets | Downtown Avenue | 45053.01 | 30150.73 | No issues
C003 | Office Tower C | T244 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-04-16 | 2023-04-28 | 2023-04-28 | 100 | Roofing Sheets | Downtown Avenue | 28844.33 | 23730.66 | No issues
C003 | Office Tower C | T338 | Foundation Excavation | John Miller | Completed | Medium | 2024-05-10 | 2024-06-04 | 2024-06-04 | 100 | Copper Wires | Downtown Avenue | 47513.17 | 31213.96 | No issues
C001 | Residential Building A | T488 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-11-14 | 2024-11-21 |  | 0 | Roofing Sheets | Plot 21, Riverside | 45902.56 | 30360.05 | Not started
C001 | Residential Building A | T248 | Interior Painting | Emma White | In Progress | Medium | 2024-07-06 | 2024-07-20 |  | 84 | Copper Wires | Plot 21, Riverside | 29974.12 | 29547.24 | In progress
C002 | Shopping Complex B | T882 | Foundation Excavation | Emma White | In Progress | Low | 2024-06-19 | 2024-07-07 |  | 9 | Copper Wires | Market Street | 44136.73 | 73646.24 | In progress
C004 | Warehouse D | T772 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2023-02-26 | 2023-03-14 |  | 12 | Copper Wires | Industrial Park | 45238.33 | 32169.68 | In progress
C001 | Residential Building A | T916 | Interior Painting | Emma White | In Progress | High | 2024-12-18 | 2025-01-13 |  | 77 | Rebar | Plot 21, Riverside | 13970.81 | 16645.02 | In progress
C004 | Warehouse D | T847 | Electrical Wiring | Sarah Johnson | Blocked | High | 2023-12-17 | 2023-12-30 |  | 0 | Copper Wires | Industrial Park | 8087.92 | 7898.39 | Not started
C004 | Warehouse D | T884 | Interior Painting | Sarah Johnson | Blocked | Medium | 2023-06-08 | 2023-06-29 |  | 0 | Steel Beams | Industrial Park | 22794.68 | 20784.7 | Not started
C004 | Warehouse D | T925 | Concrete Pouring | Emma White | Not Started | Low | 2024-07-02 | 2024-07-22 |  | 0 | Copper Wires | Industrial Park | 15849.43 | 0 | Not started
C003 | Office Tower C | T537 | Roofing | Dave Brown | Blocked | High | 2024-04-28 | 2024-05-28 |  | 0 | Steel Beams | Downtown Avenue | 36037.37 | 28176.07 | Not started
C002 | Shopping Complex B | T976 | Electrical Wiring | John Miller | In Progress | Low | 2023-11-14 | 2023-12-11 |  | 2 | Cement | Market Street | 17356.05 | 45645.57 | In progress
C002 | Shopping Complex B | T234 | Interior Painting | Sarah Johnson | Not Started | High | 2024-08-14 | 2024-08-22 |  | 0 | Cement | Market Street | 39771.6 | 0 | Not started
C002 | Shopping Complex B | T876 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-06-26 | 2023-07-13 |  | 0 | Steel Beams | Market Street | 42574.31 | 0 | Not started
C001 | Residential Building A | T396 | Steel Framework Setup | Rachel Green | Blocked | Low | 2024-11-13 | 2024-12-07 |  | 0 | PVC Pipes | Plot 21, Riverside | 44067.95 | 41736.22 | Not started
C003 | Office Tower C | T369 | Electrical Wiring | Rachel Green | Completed | Low | 2023-10-07 | 2023-10-23 | 2023-10-23 | 100 | Copper Wires | Downtown Avenue | 18736.28 | 21706.49 | No issues
C003 | Office Tower C | T619 | Electrical Wiring | Rachel Green | In Progress | High | 2023-10-12 | 2023-11-10 |  | 40 | PVC Pipes | Downtown Avenue | 19217.53 | 12166.87 | In progress
C003 | Office Tower C | T731 | Plumbing Installations | Emma White | Completed | Medium | 2024-12-15 | 2024-12-31 | 2024-12-31 | 100 | Steel Beams | Downtown Avenue | 48323.39 | 44751.18 | No issues
C004 | Warehouse D | T110 | Interior Painting | John Miller | In Progress | Low | 2023-05-27 | 2023-06-08 |  | 61 | Rebar | Industrial Park | 29595.83 | 31470.28 | In progress
C003 | Office Tower C | T160 | Plumbing Installations | Grace Allen | In Progress | High | 2023-01-11 | 2023-01-18 |  | 22 | Copper Wires | Downtown Avenue | 33169.66 | 36002.77 | In progress
C002 | Shopping Complex B | T426 | Concrete Pouring | Dave Brown | In Progress | Medium | 2024-11-10 | 2024-11-28 |  | 58 | PVC Pipes | Market Street | 40889.31 | 64028.45 | In progress
C004 | Warehouse D | T913 | Site Survey | John Miller | Not Started | High | 2024-03-28 | 2024-04-10 |  | 0 | Concrete | Industrial Park | 26825.89 | 0 | Not started
C002 | Shopping Complex B | T985 | Site Survey | John Miller | Blocked | Low | 2023-04-11 | 2023-04-28 |  | 0 | PVC Pipes | Market Street | 19407.26 | 38244.46 | Not started
C003 | Office Tower C | T574 | Foundation Excavation | Emma White | Completed | Low | 2023-04-26 | 2023-05-08 | 2023-05-08 | 100 | Cement | Downtown Avenue | 36200.63 | 41315.6 | No issues
C001 | Residential Building A | T437 | Foundation Excavation | Rachel Green | Blocked | Medium | 2023-10-08 | 2023-11-01 |  | 0 | Roofing Sheets | Plot 21, Riverside | 14636.58 | 16094.42 | Not started
C002 | Shopping Complex B | T494 | Plumbing Installations | Grace Allen | Blocked | Medium | 2024-02-16 | 2024-02-28 |  | 0 | Steel Beams | Market Street | 47580.23 | 62932.8 | Not started
C004 | Warehouse D | T757 | Roofing | Carlos Rivera | In Progress | Low | 2024-02-01 | 2024-02-17 |  | 86 | Paint | Industrial Park | 20532.21 | 18928.12 | In progress
C002 | Shopping Complex B | T489 | Roofing | Mike Adams | Completed | Medium | 2024-12-09 | 2025-01-03 | 2025-01-03 | 100 | Copper Wires | Market Street | 48637.9 | 63235.25 | No issues
C001 | Residential Building A | T135 | Site Survey | Carlos Rivera | Completed | Medium | 2023-09-10 | 2023-09-25 | 2023-09-25 | 100 | Steel Beams | Plot 21, Riverside | 41466.77 | 36320.23 | No issues
C003 | Office Tower C | T677 | Interior Painting | Rachel Green | Completed | Medium | 2024-02-03 | 2024-02-29 | 2024-02-29 | 100 | Copper Wires | Downtown Avenue | 41599.61 | 49520.28 | No issues
C002 | Shopping Complex B | T943 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-06-22 | 2024-07-14 |  | 99 | Paint | Market Street | 42573.16 | 60813.11 | In progress
C003 | Office Tower C | T829 | Steel Framework Setup | John Miller | Completed | Medium | 2024-01-19 | 2024-01-30 | 2024-01-30 | 100 | Concrete | Downtown Avenue | 32672.86 | 21304.73 | No issues
C004 | Warehouse D | T287 | Roofing | John Miller | In Progress | High | 2023-07-24 | 2023-08-15 |  | 33 | Roofing Sheets | Industrial Park | 33291.47 | 20138.27 | In progress
C002 | Shopping Complex B | T477 | Concrete Pouring | Emma White | Completed | Low | 2024-12-18 | 2024-12-29 | 2024-12-29 | 100 | Copper Wires | Market Street | 15270.22 | 36047.12 | No issues
C003 | Office Tower C | T777 | Electrical Wiring | Mike Adams | Blocked | High | 2023-01-21 | 2023-02-18 |  | 0 | PVC Pipes | Downtown Avenue | 44654.94 | 47937.16 | Not started
C002 | Shopping Complex B | T670 | Plumbing Installations | John Miller | In Progress | Medium | 2023-05-16 | 2023-06-04 |  | 29 | Paint | Market Street | 12710.68 | 36365.91 | In progress
C003 | Office Tower C | T289 | Interior Painting | Dave Brown | Not Started | Medium | 2024-01-06 | 2024-01-16 |  | 0 | Rebar | Downtown Avenue | 39667.77 | 0 | Not started
C003 | Office Tower C | T484 | Steel Framework Setup | Emma White | Completed | Medium | 2024-12-28 | 2025-01-22 | 2025-01-22 | 100 | PVC Pipes | Downtown Avenue | 5652.05 | 5606.56 | No issues
C002 | Shopping Complex B | T227 | Foundation Excavation | Dave Brown | Completed | High | 2024-04-17 | 2024-04-30 | 2024-04-30 | 100 | Steel Beams | Market Street | 37160.22 | 50839.09 | No issues
C004 | Warehouse D | T243 | Concrete Pouring | John Miller | Blocked | High | 2024-05-19 | 2024-06-03 |  | 0 | Rebar | Industrial Park | 32785.47 | 30924.5 | Not started
C001 | Residential Building A | T163 | Plumbing Installations | Emma White | Blocked | Medium | 2024-08-24 | 2024-09-16 |  | 0 | Roofing Sheets | Plot 21, Riverside | 34377.54 | 38338.9 | Not started
C002 | Shopping Complex B | T249 | Roofing | Rachel Green | Not Started | Medium | 2023-07-06 | 2023-08-04 |  | 0 | Rebar | Market Street | 45894.04 | 0 | Not started
C004 | Warehouse D | T649 | Roofing | Rachel Green | Not Started | High | 2024-07-19 | 2024-08-18 |  | 0 | Cement | Industrial Park | 43949.63 | 0 | Not started
C001 | Residential Building A | T882 | Roofing | Rachel Green | In Progress | Low | 2024-01-05 | 2024-01-24 |  | 89 | Cement | Plot 21, Riverside | 29570.79 | 31508.28 | In progress
C001 | Residential Building A | T906 | Interior Painting | Emma White | Completed | High | 2024-10-09 | 2024-10-26 | 2024-10-26 | 100 | Roofing Sheets | Plot 21, Riverside | 23296.77 | 15862.03 | No issues
C001 | Residential Building A | T650 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2024-08-13 | 2024-08-26 | 2024-08-26 | 100 | Roofing Sheets | Plot 21, Riverside | 25720.81 | 27254.3 | No issues
C002 | Shopping Complex B | T798 | Concrete Pouring | John Miller | Not Started | Medium | 2024-05-08 | 2024-05-20 |  | 0 | Roofing Sheets | Market Street | 47200.19 | 0 | Not started
C003 | Office Tower C | T799 | Steel Framework Setup | Grace Allen | Completed | Medium | 2024-02-02 | 2024-02-11 | 2024-02-11 | 100 | Concrete | Downtown Avenue | 34989.3 | 26876.19 | No issues
C002 | Shopping Complex B | T440 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2024-02-04 | 2024-02-11 |  | 0 | Copper Wires | Market Street | 39575.2 | 56205.22 | Not started
C002 | Shopping Complex B | T136 | Concrete Pouring | Dave Brown | Completed | Medium | 2024-08-18 | 2024-09-11 | 2024-09-11 | 100 | Rebar | Market Street | 5559.94 | 31621.41 | No issues
C001 | Residential Building A | T538 | Site Survey | John Miller | Blocked | Medium | 2023-09-24 | 2023-10-04 |  | 0 | Cement | Plot 21, Riverside | 41251.91 | 28652.73 | Not started
C004 | Warehouse D | T474 | Roofing | Sarah Johnson | Completed | High | 2023-09-13 | 2023-10-10 | 2023-10-10 | 100 | Concrete | Industrial Park | 45777.18 | 48881.32 | No issues
C004 | Warehouse D | T379 | Electrical Wiring | Emma White | Blocked | Low | 2023-02-06 | 2023-02-18 |  | 0 | Steel Beams | Industrial Park | 22644.44 | 22576.52 | Not started
C001 | Residential Building A | T513 | Concrete Pouring | Grace Allen | In Progress | High | 2023-05-12 | 2023-06-09 |  | 9 | Paint | Plot 21, Riverside | 26940.5 | 18111.23 | In progress
C002 | Shopping Complex B | T683 | Steel Framework Setup | Mike Adams | Blocked | High | 2023-02-17 | 2023-03-11 |  | 0 | Steel Beams | Market Street | 35946.05 | 48283.36 | Not started
C004 | Warehouse D | T532 | Plumbing Installations | Sarah Johnson | In Progress | High | 2024-11-10 | 2024-11-19 |  | 42 | Concrete | Industrial Park | 47449.57 | 53689.21 | In progress
C004 | Warehouse D | T946 | Concrete Pouring | Mike Adams | Completed | High | 2023-08-05 | 2023-09-03 | 2023-09-03 | 100 | Rebar | Industrial Park | 27269.74 | 24624.82 | No issues
C004 | Warehouse D | T814 | Interior Painting | Dave Brown | In Progress | High | 2023-01-18 | 2023-02-04 |  | 54 | Roofing Sheets | Industrial Park | 20743.44 | 18005.8 | In progress
C001 | Residential Building A | T364 | Roofing | Carlos Rivera | In Progress | High | 2023-03-11 | 2023-04-03 |  | 62 | Steel Beams | Plot 21, Riverside | 19769.93 | 17439.96 | In progress
C002 | Shopping Complex B | T637 | Roofing | Mike Adams | In Progress | Medium | 2023-06-28 | 2023-07-06 |  | 19 | Concrete | Market Street | 32716.18 | 59925.03 | In progress
C004 | Warehouse D | T554 | Plumbing Installations | Mike Adams | Not Started | Low | 2024-02-14 | 2024-03-12 |  | 0 | Rebar | Industrial Park | 47447.06 | 0 | Not started
C001 | Residential Building A | T526 | Plumbing Installations | Dave Brown | Blocked | High | 2024-07-02 | 2024-07-23 |  | 0 | PVC Pipes | Plot 21, Riverside | 13767.76 | 12803.72 | Not started
C002 | Shopping Complex B | T432 | Interior Painting | Dave Brown | Not Started | Low | 2023-03-16 | 2023-04-12 |  | 0 | Roofing Sheets | Market Street | 6897.13 | 0 | Not started
C004 | Warehouse D | T449 | Plumbing Installations | Emma White | In Progress | Low | 2023-04-20 | 2023-05-05 |  | 85 | Roofing Sheets | Industrial Park | 48287.76 | 38475.4 | In progress
C003 | Office Tower C | T831 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-12-16 | 2023-12-28 |  | 0 | Roofing Sheets | Downtown Avenue | 46788.44 | 0 | Not started
C001 | Residential Building A | T808 | Interior Painting | Grace Allen | Blocked | High | 2023-03-27 | 2023-04-07 |  | 0 | Copper Wires | Plot 21, Riverside | 15424.28 | 10028.14 | Not started
C004 | Warehouse D | T722 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2024-12-04 | 2024-12-27 |  | 0 | Concrete | Industrial Park | 18631.28 | 16860.5 | Not started
C004 | Warehouse D | T685 | Site Survey | Mike Adams | Blocked | Medium | 2024-07-12 | 2024-07-25 |  | 0 | PVC Pipes | Industrial Park | 11927.55 | 7631.94 | Not started
C002 | Shopping Complex B | T657 | Steel Framework Setup | Mike Adams | Completed | High | 2024-04-05 | 2024-05-05 | 2024-05-05 | 100 | Roofing Sheets | Market Street | 43618.96 | 54294.37 | No issues
C001 | Residential Building A | T772 | Roofing | Grace Allen | Blocked | Medium | 2023-07-07 | 2023-08-04 |  | 0 | Copper Wires | Plot 21, Riverside | 47871.37 | 46333.71 | Not started
C001 | Residential Building A | T229 | Steel Framework Setup | Dave Brown | Not Started | Low | 2024-11-18 | 2024-12-05 |  | 0 | Paint | Plot 21, Riverside | 11080.54 | 0 | Not started
C003 | Office Tower C | T767 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-08-17 | 2024-09-05 | 2024-09-05 | 100 | Cement | Downtown Avenue | 42367.19 | 42990.01 | No issues
C002 | Shopping Complex B | T114 | Site Survey | Rachel Green | Blocked | Medium | 2023-05-04 | 2023-05-21 |  | 0 | Paint | Market Street | 27186.25 | 51238.79 | Not started
C001 | Residential Building A | T457 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-01-12 | 2023-02-07 |  | 58 | Steel Beams | Plot 21, Riverside | 22507.63 | 23238.15 | In progress
C003 | Office Tower C | T915 | Roofing | John Miller | Completed | Low | 2023-09-24 | 2023-10-11 | 2023-10-11 | 100 | Cement | Downtown Avenue | 23543.16 | 15265.17 | No issues
C001 | Residential Building A | T334 | Steel Framework Setup | Grace Allen | In Progress | Low | 2023-10-08 | 2023-10-17 |  | 21 | Rebar | Plot 21, Riverside | 26667.63 | 28976.2 | In progress
C002 | Shopping Complex B | T243 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-11-14 | 2023-12-04 |  | 77 | Steel Beams | Market Street | 27569.02 | 53208.04 | In progress
C002 | Shopping Complex B | T414 | Foundation Excavation | Emma White | Completed | High | 2024-10-07 | 2024-10-27 | 2024-10-27 | 100 | Concrete | Market Street | 6132.25 | 31797.08 | No issues
C003 | Office Tower C | T421 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-05-03 | 2023-05-31 |  | 0 | Concrete | Downtown Avenue | 30119.43 | 0 | Not started
C004 | Warehouse D | T403 | Concrete Pouring | Dave Brown | Not Started | High | 2024-08-26 | 2024-09-16 |  | 0 | PVC Pipes | Industrial Park | 5624.32 | 0 | Not started
C001 | Residential Building A | T373 | Plumbing Installations | Dave Brown | In Progress | Low | 2023-06-07 | 2023-06-25 |  | 15 | Copper Wires | Plot 21, Riverside | 13179.3 | 10705.29 | In progress
C003 | Office Tower C | T921 | Foundation Excavation | Mike Adams | In Progress | Medium | 2023-02-24 | 2023-03-06 |  | 20 | Concrete | Downtown Avenue | 18725.84 | 22459.08 | In progress
C002 | Shopping Complex B | T681 | Electrical Wiring | John Miller | Not Started | High | 2023-06-05 | 2023-06-14 |  | 0 | Steel Beams | Market Street | 13655.85 | 0 | Not started
C001 | Residential Building A | T984 | Concrete Pouring | Grace Allen | In Progress | High | 2024-06-27 | 2024-07-21 |  | 43 | Roofing Sheets | Plot 21, Riverside | 7770.48 | 9143.13 | In progress
C001 | Residential Building A | T291 | Roofing | Dave Brown | In Progress | Low | 2024-11-22 | 2024-12-16 |  | 25 | Cement | Plot 21, Riverside | 38188.01 | 42387.76 | In progress
C004 | Warehouse D | T734 | Concrete Pouring | Grace Allen | Not Started | High | 2023-06-23 | 2023-07-04 |  | 0 | Cement | Industrial Park | 24355.9 | 0 | Not started
C004 | Warehouse D | T399 | Foundation Excavation | Grace Allen | Completed | Medium | 2023-06-03 | 2023-06-20 | 2023-06-20 | 100 | Paint | Industrial Park | 31175.61 | 29401.63 | No issues
C002 | Shopping Complex B | T490 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-02-22 | 2024-03-06 |  | 0 | Cement | Market Street | 8172.05 | 32963.23 | Not started
C003 | Office Tower C | T184 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-05-18 | 2024-06-06 |  | 0 | PVC Pipes | Downtown Avenue | 36505.69 | 26768.35 | Not started
C003 | Office Tower C | T648 | Foundation Excavation | John Miller | Completed | High | 2023-05-24 | 2023-06-22 | 2023-06-22 | 100 | Concrete | Downtown Avenue | 32880.58 | 23704.49 | No issues
C003 | Office Tower C | T281 | Interior Painting | Rachel Green | In Progress | Low | 2023-10-26 | 2023-11-13 |  | 94 | Concrete | Downtown Avenue | 16468.71 | 19374.4 | In progress
C004 | Warehouse D | T215 | Roofing | Rachel Green | Blocked | Low | 2024-12-15 | 2024-12-23 |  | 0 | Cement | Industrial Park | 7818.92 | 8164.62 | Not started
C003 | Office Tower C | T315 | Concrete Pouring | Rachel Green | Completed | Low | 2023-08-23 | 2023-09-05 | 2023-09-05 | 100 | Copper Wires | Downtown Avenue | 6373.3 | 6889.28 | No issues
C003 | Office Tower C | T534 | Plumbing Installations | Rachel Green | Blocked | Low | 2023-04-24 | 2023-05-07 |  | 0 | Cement | Downtown Avenue | 19053.79 | 11793.18 | Not started
C002 | Shopping Complex B | T243 | Foundation Excavation | Dave Brown | Completed | High | 2023-09-19 | 2023-10-02 | 2023-10-02 | 100 | PVC Pipes | Market Street | 20853.87 | 42467.09 | No issues
C004 | Warehouse D | T823 | Concrete Pouring | Mike Adams | Not Started | High | 2023-04-27 | 2023-05-23 |  | 0 | Steel Beams | Industrial Park | 45050.43 | 0 | Not started
C004 | Warehouse D | T561 | Concrete Pouring | Grace Allen | In Progress | High | 2024-10-23 | 2024-11-05 |  | 64 | Concrete | Industrial Park | 46489.2 | 49507.22 | In progress
C001 | Residential Building A | T787 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-05-04 | 2024-05-25 | 2024-05-25 | 100 | Cement | Plot 21, Riverside | 48311.38 | 55056.4 | No issues
C001 | Residential Building A | T218 | Electrical Wiring | Mike Adams | In Progress | Low | 2024-12-15 | 2024-12-24 |  | 83 | Concrete | Plot 21, Riverside | 13703.5 | 12495.27 | In progress
C002 | Shopping Complex B | T418 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2024-11-14 | 2024-12-13 |  | 0 | Copper Wires | Market Street | 9589.55 | 0 | Not started
C004 | Warehouse D | T129 | Steel Framework Setup | Rachel Green | Completed | Medium | 2024-08-22 | 2024-09-01 | 2024-09-01 | 100 | Copper Wires | Industrial Park | 23732.2 | 20622.8 | No issues
C002 | Shopping Complex B | T295 | Steel Framework Setup | Rachel Green | In Progress | High | 2023-07-08 | 2023-08-03 |  | 80 | Cement | Market Street | 14509.77 | 39000.72 | In progress
C001 | Residential Building A | T888 | Electrical Wiring | John Miller | Completed | Low | 2023-03-17 | 2023-04-16 | 2023-04-16 | 100 | PVC Pipes | Plot 21, Riverside | 40633.13 | 40502.39 | No issues
C003 | Office Tower C | T616 | Concrete Pouring | Dave Brown | In Progress | Low | 2023-01-27 | 2023-02-14 |  | 53 | Copper Wires | Downtown Avenue | 39498.15 | 24686.74 | In progress
C002 | Shopping Complex B | T800 | Interior Painting | Sarah Johnson | Blocked | Medium | 2024-09-13 | 2024-09-29 |  | 0 | Copper Wires | Market Street | 6344.02 | 30209.73 | Not started
C003 | Office Tower C | T816 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-07-21 | 2023-08-12 | 2023-08-12 | 100 | Roofing Sheets | Downtown Avenue | 37991.58 | 24740.78 | No issues
C003 | Office Tower C | T863 | Roofing | Emma White | Not Started | Medium | 2023-08-13 | 2023-08-27 |  | 0 | Cement | Downtown Avenue | 7170.08 | 0 | Not started
C004 | Warehouse D | T260 | Interior Painting | Dave Brown | Not Started | Low | 2024-03-28 | 2024-04-20 |  | 0 | Rebar | Industrial Park | 14913.49 | 0 | Not started
C002 | Shopping Complex B | T292 | Roofing | John Miller | Blocked | High | 2023-03-11 | 2023-04-04 |  | 0 | Cement | Market Street | 45033.88 | 71477.22 | Not started
C003 | Office Tower C | T632 | Foundation Excavation | Grace Allen | Completed | Medium | 2024-02-26 | 2024-03-24 | 2024-03-24 | 100 | Steel Beams | Downtown Avenue | 28891.02 | 18691.37 | No issues
C004 | Warehouse D | T819 | Site Survey | Rachel Green | In Progress | High | 2023-02-27 | 2023-03-16 |  | 24 | Cement | Industrial Park | 44302.16 | 46591.43 | In progress
C001 | Residential Building A | T148 | Steel Framework Setup | John Miller | Not Started | Medium | 2023-02-16 | 2023-03-07 |  | 0 | PVC Pipes | Plot 21, Riverside | 32675.09 | 0 | Not started
C001 | Residential Building A | T631 | Steel Framework Setup | Sarah Johnson | Completed | High | 2024-08-12 | 2024-09-07 | 2024-09-07 | 100 | Paint | Plot 21, Riverside | 49828.89 | 45088.13 | No issues
C003 | Office Tower C | T957 | Electrical Wiring | Sarah Johnson | Completed | High | 2024-11-22 | 2024-12-06 | 2024-12-06 | 100 | Copper Wires | Downtown Avenue | 47217.35 | 43793.97 | No issues
C001 | Residential Building A | T457 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2024-05-07 | 2024-05-26 |  | 0 | Roofing Sheets | Plot 21, Riverside | 19637.44 | 12634.58 | Not started
C003 | Office Tower C | T111 | Interior Painting | Dave Brown | Not Started | High | 2023-03-26 | 2023-04-16 |  | 0 | Concrete | Downtown Avenue | 12340.12 | 0 | Not started
C002 | Shopping Complex B | T957 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-04-03 | 2024-05-02 |  | 0 | Steel Beams | Market Street | 39281.25 | 0 | Not started
C001 | Residential Building A | T391 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-08-03 | 2024-09-02 | 2024-09-02 | 100 | Rebar | Plot 21, Riverside | 17287.05 | 18068.35 | No issues
C004 | Warehouse D | T497 | Site Survey | Mike Adams | Completed | Medium | 2024-02-09 | 2024-02-27 | 2024-02-27 | 100 | Roofing Sheets | Industrial Park | 34731.42 | 34310.43 | No issues
C002 | Shopping Complex B | T106 | Interior Painting | Emma White | Blocked | Medium | 2023-01-16 | 2023-01-31 |  | 0 | Concrete | Market Street | 11691.03 | 32956.2 | Not started
C001 | Residential Building A | T959 | Interior Painting | Dave Brown | In Progress | Medium | 2024-03-25 | 2024-04-05 |  | 56 | PVC Pipes | Plot 21, Riverside | 10262.64 | 6173.35 | In progress
C001 | Residential Building A | T221 | Plumbing Installations | Mike Adams | Completed | High | 2023-07-26 | 2023-08-22 | 2023-08-22 | 100 | Cement | Plot 21, Riverside | 44412.89 | 44201.96 | No issues
C001 | Residential Building A | T900 | Electrical Wiring | Mike Adams | Completed | High | 2023-04-21 | 2023-05-10 | 2023-05-10 | 100 | Copper Wires | Plot 21, Riverside | 20157.81 | 17316.75 | No issues
C001 | Residential Building A | T226 | Foundation Excavation | Carlos Rivera | Completed | Medium | 2024-12-09 | 2024-12-17 | 2024-12-17 | 100 | Cement | Plot 21, Riverside | 41105.39 | 35391.52 | No issues
C001 | Residential Building A | T781 | Plumbing Installations | Dave Brown | In Progress | High | 2023-09-11 | 2023-09-23 |  | 96 | Copper Wires | Plot 21, Riverside | 25007.48 | 26003.44 | In progress
C002 | Shopping Complex B | T724 | Steel Framework Setup | Dave Brown | In Progress | Low | 2024-10-01 | 2024-10-15 |  | 68 | Copper Wires | Market Street | 47740.9 | 71227.14 | In progress
C001 | Residential Building A | T298 | Foundation Excavation | Emma White | Not Started | High | 2023-09-05 | 2023-09-25 |  | 0 | Paint | Plot 21, Riverside | 39376.82 | 0 | Not started
C001 | Residential Building A | T634 | Concrete Pouring | Dave Brown | Blocked | Low | 2024-08-14 | 2024-09-03 |  | 0 | Steel Beams | Plot 21, Riverside | 44733.35 | 50436.91 | Not started
C001 | Residential Building A | T531 | Plumbing Installations | Sarah Johnson | Completed | Low | 2023-10-13 | 2023-10-22 | 2023-10-22 | 100 | Concrete | Plot 21, Riverside | 32204.99 | 33723.77 | No issues
C003 | Office Tower C | T440 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2023-04-04 | 2023-04-20 |  | 4 | Roofing Sheets | Downtown Avenue | 32477.35 | 30358.56 | In progress
C001 | Residential Building A | T579 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-01-09 | 2024-01-29 |  | 0 | Copper Wires | Plot 21, Riverside | 41665.39 | 0 | Not started
C001 | Residential Building A | T755 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-04-25 | 2023-05-13 |  | 0 | Steel Beams | Plot 21, Riverside | 11326.49 | 0 | Not started
C004 | Warehouse D | T970 | Steel Framework Setup | Sarah Johnson | Blocked | High | 2023-12-03 | 2023-12-22 |  | 0 | PVC Pipes | Industrial Park | 38092.44 | 24392.38 | Not started
C001 | Residential Building A | T534 | Interior Painting | Grace Allen | Blocked | Medium | 2023-11-23 | 2023-12-17 |  | 0 | Paint | Plot 21, Riverside | 23867.31 | 26777.54 | Not started
C002 | Shopping Complex B | T342 | Plumbing Installations | Grace Allen | Completed | Low | 2023-01-26 | 2023-02-14 | 2023-02-14 | 100 | Cement | Market Street | 16965.33 | 36609.13 | No issues
C004 | Warehouse D | T218 | Plumbing Installations | Mike Adams | Completed | Low | 2023-01-25 | 2023-02-08 | 2023-02-08 | 100 | Concrete | Industrial Park | 47437.48 | 48416.34 | No issues
C001 | Residential Building A | T314 | Electrical Wiring | Mike Adams | Not Started | High | 2024-04-17 | 2024-04-29 |  | 0 | Paint | Plot 21, Riverside | 29540.54 | 0 | Not started
C001 | Residential Building A | T399 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2024-09-17 | 2024-10-05 |  | 0 | Concrete | Plot 21, Riverside | 40455.81 | 0 | Not started
C002 | Shopping Complex B | T940 | Steel Framework Setup | Emma White | Completed | Low | 2023-06-26 | 2023-07-12 | 2023-07-12 | 100 | Rebar | Market Street | 10968.78 | 37534.53 | No issues
C004 | Warehouse D | T621 | Foundation Excavation | John Miller | Completed | Medium | 2024-10-15 | 2024-11-07 | 2024-11-07 | 100 | PVC Pipes | Industrial Park | 11875.25 | 10027.3 | No issues
C003 | Office Tower C | T136 | Site Survey | Carlos Rivera | Not Started | High | 2023-12-09 | 2024-01-01 |  | 0 | Concrete | Downtown Avenue | 36860.96 | 0 | Not started
C002 | Shopping Complex B | T773 | Plumbing Installations | Emma White | Completed | Low | 2024-07-04 | 2024-07-22 | 2024-07-22 | 100 | Rebar | Market Street | 20235.17 | 38849.83 | No issues
C001 | Residential Building A | T877 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-07-17 | 2023-08-15 |  | 0 | Roofing Sheets | Plot 21, Riverside | 32013.47 | 31159.46 | Not started
C004 | Warehouse D | T481 | Site Survey | Sarah Johnson | Blocked | Low | 2023-07-12 | 2023-07-21 |  | 0 | Concrete | Industrial Park | 43026.12 | 43663.05 | Not started
C002 | Shopping Complex B | T745 | Steel Framework Setup | Carlos Rivera | Completed | High | 2024-07-14 | 2024-07-23 | 2024-07-23 | 100 | Copper Wires | Market Street | 21511.49 | 43235.18 | No issues
C003 | Office Tower C | T597 | Plumbing Installations | Rachel Green | Blocked | High | 2023-01-18 | 2023-01-26 |  | 0 | PVC Pipes | Downtown Avenue | 27845.39 | 25404.81 | Not started
C001 | Residential Building A | T495 | Plumbing Installations | Dave Brown | Not Started | High | 2023-02-13 | 2023-03-03 |  | 0 | Roofing Sheets | Plot 21, Riverside | 36177.14 | 0 | Not started
C004 | Warehouse D | T307 | Electrical Wiring | Rachel Green | Completed | High | 2024-05-27 | 2024-06-16 | 2024-06-16 | 100 | Cement | Industrial Park | 11933.59 | 9397.58 | No issues
C004 | Warehouse D | T382 | Plumbing Installations | Dave Brown | Not Started | Medium | 2023-12-25 | 2024-01-13 |  | 0 | Concrete | Industrial Park | 8714.58 | 0 | Not started
C003 | Office Tower C | T346 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2023-05-28 | 2023-06-14 |  | 0 | Steel Beams | Downtown Avenue | 29294.05 | 0 | Not started
C002 | Shopping Complex B | T397 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2023-02-27 | 2023-03-17 |  | 0 | Copper Wires | Market Street | 46584.91 | 60853.64 | Not started
C003 | Office Tower C | T238 | Site Survey | Sarah Johnson | Not Started | Low | 2023-01-28 | 2023-02-13 |  | 0 | Rebar | Downtown Avenue | 11585.96 | 0 | Not started
C001 | Residential Building A | T310 | Steel Framework Setup | John Miller | In Progress | High | 2024-04-17 | 2024-05-15 |  | 71 | Roofing Sheets | Plot 21, Riverside | 14770.86 | 14440.51 | In progress
C003 | Office Tower C | T423 | Electrical Wiring | John Miller | Not Started | Low | 2023-04-09 | 2023-05-01 |  | 0 | Copper Wires | Downtown Avenue | 33470.83 | 0 | Not started
C003 | Office Tower C | T738 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-08-25 | 2024-09-16 | 2024-09-16 | 100 | Roofing Sheets | Downtown Avenue | 28609.28 | 29790.93 | No issues
C001 | Residential Building A | T670 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-08-19 | 2024-09-18 | 2024-09-18 | 100 | Cement | Plot 21, Riverside | 40186.2 | 42769.62 | No issues
C004 | Warehouse D | T307 | Interior Painting | Dave Brown | In Progress | Medium | 2024-10-25 | 2024-11-02 |  | 2 | Copper Wires | Industrial Park | 23848.52 | 20091.65 | In progress
C004 | Warehouse D | T558 | Foundation Excavation | Grace Allen | Not Started | High | 2024-10-08 | 2024-11-02 |  | 0 | Rebar | Industrial Park | 5091.81 | 0 | Not started
C002 | Shopping Complex B | T152 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2023-10-17 | 2023-11-03 |  | 0 | PVC Pipes | Market Street | 42214.36 | 54305 | Not started
C004 | Warehouse D | T972 | Interior Painting | Dave Brown | Blocked | High | 2024-11-14 | 2024-12-11 |  | 0 | Cement | Industrial Park | 43702 | 40287.14 | Not started
C004 | Warehouse D | T267 | Foundation Excavation | Emma White | Completed | Low | 2024-11-01 | 2024-11-09 | 2024-11-09 | 100 | Copper Wires | Industrial Park | 49223.49 | 37308.27 | No issues
C001 | Residential Building A | T246 | Concrete Pouring | Emma White | In Progress | Low | 2023-10-02 | 2023-10-31 |  | 44 | Steel Beams | Plot 21, Riverside | 46913.68 | 51542.42 | In progress
C003 | Office Tower C | T223 | Electrical Wiring | Grace Allen | In Progress | Medium | 2024-09-22 | 2024-10-16 |  | 19 | Cement | Downtown Avenue | 8175.38 | 7379.12 | In progress
C004 | Warehouse D | T608 | Electrical Wiring | Dave Brown | In Progress | High | 2023-04-21 | 2023-05-07 |  | 88 | Concrete | Industrial Park | 39243.05 | 34767.35 | In progress
C001 | Residential Building A | T988 | Site Survey | Emma White | Blocked | High | 2024-03-02 | 2024-03-13 |  | 0 | Paint | Plot 21, Riverside | 46819.25 | 53828.62 | Not started
C002 | Shopping Complex B | T420 | Electrical Wiring | Mike Adams | Not Started | High | 2024-01-17 | 2024-02-10 |  | 0 | Steel Beams | Market Street | 44521.34 | 0 | Not started
C001 | Residential Building A | T630 | Interior Painting | Grace Allen | Not Started | Low | 2024-11-19 | 2024-12-02 |  | 0 | Copper Wires | Plot 21, Riverside | 31607.39 | 0 | Not started
C004 | Warehouse D | T696 | Foundation Excavation | Dave Brown | Completed | High | 2023-03-05 | 2023-03-17 | 2023-03-17 | 100 | Roofing Sheets | Industrial Park | 45567.51 | 28001.29 | No issues
C004 | Warehouse D | T291 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-03-19 | 2024-04-05 |  | 0 | Concrete | Industrial Park | 21103.79 | 18169.6 | Not started
C004 | Warehouse D | T924 | Electrical Wiring | Rachel Green | Blocked | Medium | 2023-04-24 | 2023-05-20 |  | 0 | Rebar | Industrial Park | 27121.04 | 22238.97 | Not started
C004 | Warehouse D | T585 | Plumbing Installations | Mike Adams | Completed | High | 2024-03-05 | 2024-03-12 | 2024-03-12 | 100 | Steel Beams | Industrial Park | 30795.07 | 27328.85 | No issues
C002 | Shopping Complex B | T294 | Electrical Wiring | Rachel Green | Completed | Low | 2023-11-21 | 2023-12-07 | 2023-12-07 | 100 | Copper Wires | Market Street | 44716.52 | 56061.91 | No issues
C002 | Shopping Complex B | T434 | Roofing | John Miller | In Progress | Low | 2023-11-19 | 2023-12-08 |  | 32 | Paint | Market Street | 44975.43 | 73228.21 | In progress
C004 | Warehouse D | T781 | Concrete Pouring | Rachel Green | In Progress | High | 2024-07-18 | 2024-07-30 |  | 74 | Cement | Industrial Park | 38526.25 | 40228.49 | In progress
C001 | Residential Building A | T372 | Site Survey | Rachel Green | Not Started | Medium | 2024-07-15 | 2024-08-01 |  | 0 | Steel Beams | Plot 21, Riverside | 28614.94 | 0 | Not started
C002 | Shopping Complex B | T893 | Site Survey | Dave Brown | Completed | Low | 2023-09-25 | 2023-10-25 | 2023-10-25 | 100 | Paint | Market Street | 32607.82 | 55132.63 | No issues
C002 | Shopping Complex B | T622 | Foundation Excavation | Emma White | Completed | Low | 2024-07-14 | 2024-08-05 | 2024-08-05 | 100 | PVC Pipes | Market Street | 15472.64 | 40278.05 | No issues
C001 | Residential Building A | T756 | Roofing | Carlos Rivera | Blocked | Medium | 2024-08-22 | 2024-09-15 |  | 0 | Concrete | Plot 21, Riverside | 8006.53 | 9329.5 | Not started
C002 | Shopping Complex B | T335 | Electrical Wiring | Grace Allen | Completed | Medium | 2023-07-10 | 2023-07-23 | 2023-07-23 | 100 | Rebar | Market Street | 44003.63 | 64678.84 | No issues
C001 | Residential Building A | T694 | Steel Framework Setup | John Miller | In Progress | High | 2023-03-05 | 2023-03-30 |  | 0 | Rebar | Plot 21, Riverside | 8908.04 | 10155.81 | In progress
C003 | Office Tower C | T615 | Concrete Pouring | Grace Allen | Not Started | Medium | 2024-08-21 | 2024-09-12 |  | 0 | Rebar | Downtown Avenue | 18412.17 | 0 | Not started
C002 | Shopping Complex B | T541 | Roofing | Dave Brown | Not Started | High | 2024-06-26 | 2024-07-20 |  | 0 | Cement | Market Street | 29060.11 | 0 | Not started
C003 | Office Tower C | T593 | Foundation Excavation | Rachel Green | Not Started | High | 2024-01-13 | 2024-02-11 |  | 0 | Cement | Downtown Avenue | 27528.62 | 0 | Not started
C001 | Residential Building A | T377 | Interior Painting | Carlos Rivera | Not Started | High | 2024-11-01 | 2024-11-29 |  | 0 | Rebar | Plot 21, Riverside | 8259.17 | 0 | Not started
C002 | Shopping Complex B | T358 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-07-01 | 2024-07-22 |  | 24 | Copper Wires | Market Street | 15416.97 | 39336.1 | In progress
C003 | Office Tower C | T924 | Foundation Excavation | Sarah Johnson | Not Started | High | 2024-12-13 | 2025-01-04 |  | 0 | Copper Wires | Downtown Avenue | 43069.75 | 0 | Not started
C001 | Residential Building A | T841 | Plumbing Installations | Mike Adams | Not Started | Medium | 2023-06-06 | 2023-07-06 |  | 0 | Cement | Plot 21, Riverside | 18252.46 | 0 | Not started
C001 | Residential Building A | T975 | Electrical Wiring | Carlos Rivera | In Progress | Medium | 2024-12-05 | 2024-12-19 |  | 49 | Steel Beams | Plot 21, Riverside | 30532.04 | 32969.98 | In progress
C002 | Shopping Complex B | T343 | Concrete Pouring | Rachel Green | Blocked | High | 2024-07-01 | 2024-07-31 |  | 0 | Cement | Market Street | 26872.09 | 46641.95 | Not started
C003 | Office Tower C | T619 | Concrete Pouring | John Miller | Blocked | Medium | 2023-03-15 | 2023-04-13 |  | 0 | PVC Pipes | Downtown Avenue | 12171.21 | 10036.69 | Not started
C004 | Warehouse D | T439 | Concrete Pouring | Mike Adams | Completed | High | 2024-02-19 | 2024-03-17 | 2024-03-17 | 100 | Roofing Sheets | Industrial Park | 24467.77 | 24277.53 | No issues
C003 | Office Tower C | T944 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2024-10-10 | 2024-10-17 |  | 0 | Roofing Sheets | Downtown Avenue | 22507.5 | 17035.24 | Not started
C003 | Office Tower C | T642 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-07-03 | 2023-07-19 |  | 91 | Rebar | Downtown Avenue | 14053.47 | 15695.55 | In progress
C004 | Warehouse D | T117 | Roofing | Emma White | Completed | Medium | 2024-03-06 | 2024-03-19 | 2024-03-19 | 100 | Paint | Industrial Park | 11733.76 | 9932.87 | No issues
C002 | Shopping Complex B | T231 | Foundation Excavation | John Miller | In Progress | High | 2023-08-26 | 2023-09-24 |  | 22 | Paint | Market Street | 36538.56 | 60724.72 | In progress
C002 | Shopping Complex B | T292 | Concrete Pouring | John Miller | Not Started | Low | 2024-10-12 | 2024-10-20 |  | 0 | Copper Wires | Market Street | 45614.66 | 0 | Not started
C001 | Residential Building A | T945 | Steel Framework Setup | Grace Allen | Blocked | Low | 2023-09-11 | 2023-10-08 |  | 0 | Paint | Plot 21, Riverside | 42750.71 | 44525.12 | Not started
C003 | Office Tower C | T570 | Roofing | Grace Allen | Not Started | Medium | 2024-05-26 | 2024-06-04 |  | 0 | Cement | Downtown Avenue | 41900.86 | 0 | Not started
C001 | Residential Building A | T558 | Concrete Pouring | Sarah Johnson | Completed | High | 2024-08-13 | 2024-08-31 | 2024-08-31 | 100 | Steel Beams | Plot 21, Riverside | 43924.03 | 45679.37 | No issues
C002 | Shopping Complex B | T314 | Foundation Excavation | Sarah Johnson | In Progress | High | 2024-08-14 | 2024-08-22 |  | 19 | Steel Beams | Market Street | 42782.31 | 69364.51 | In progress
C001 | Residential Building A | T950 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2024-01-26 | 2024-02-19 |  | 96 | Cement | Plot 21, Riverside | 12914.55 | 12529.71 | In progress
C001 | Residential Building A | T238 | Foundation Excavation | Carlos Rivera | Not Started | High | 2024-03-07 | 2024-04-02 |  | 0 | Paint | Plot 21, Riverside | 10093.3 | 0 | Not started
C004 | Warehouse D | T156 | Interior Painting | Emma White | Not Started | Medium | 2024-09-08 | 2024-09-23 |  | 0 | Paint | Industrial Park | 8682.55 | 0 | Not started
C003 | Office Tower C | T965 | Plumbing Installations | Emma White | Completed | High | 2023-06-20 | 2023-07-15 | 2023-07-15 | 100 | PVC Pipes | Downtown Avenue | 30638.64 | 29816.89 | No issues
C002 | Shopping Complex B | T796 | Steel Framework Setup | Emma White | Not Started | Low | 2023-01-05 | 2023-01-27 |  | 0 | Concrete | Market Street | 11054.21 | 0 | Not started
C001 | Residential Building A | T472 | Electrical Wiring | Grace Allen | Not Started | Low | 2023-01-10 | 2023-02-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 40820.7 | 0 | Not started
C002 | Shopping Complex B | T503 | Steel Framework Setup | Emma White | Completed | High | 2024-02-21 | 2024-03-19 | 2024-03-19 | 100 | Roofing Sheets | Market Street | 42444.5 | 62778.55 | No issues
C004 | Warehouse D | T939 | Interior Painting | Emma White | Blocked | Low | 2024-07-15 | 2024-08-14 |  | 0 | Cement | Industrial Park | 17122.42 | 16926.26 | Not started
C004 | Warehouse D | T689 | Roofing | Dave Brown | In Progress | Low | 2024-08-24 | 2024-09-18 |  | 1 | Roofing Sheets | Industrial Park | 48058.27 | 39209.2 | In progress
C003 | Office Tower C | T889 | Interior Painting | Rachel Green | In Progress | Medium | 2023-05-18 | 2023-06-03 |  | 42 | Paint | Downtown Avenue | 35556.74 | 22897.74 | In progress
C003 | Office Tower C | T485 | Site Survey | Sarah Johnson | Completed | High | 2024-07-11 | 2024-08-02 | 2024-08-02 | 100 | Roofing Sheets | Downtown Avenue | 18300.06 | 21243.93 | No issues
C003 | Office Tower C | T625 | Foundation Excavation | Grace Allen | Not Started | High | 2023-12-25 | 2024-01-19 |  | 0 | Steel Beams | Downtown Avenue | 25287.86 | 0 | Not started
C001 | Residential Building A | T332 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-07-15 | 2024-08-08 |  | 0 | Steel Beams | Plot 21, Riverside | 32317.34 | 0 | Not started
C001 | Residential Building A | T658 | Foundation Excavation | Carlos Rivera | Blocked | High | 2024-07-21 | 2024-08-19 |  | 0 | Steel Beams | Plot 21, Riverside | 38402.88 | 39431.14 | Not started
C002 | Shopping Complex B | T659 | Steel Framework Setup | Dave Brown | Not Started | Medium | 2024-07-07 | 2024-08-05 |  | 0 | Paint | Market Street | 22567.65 | 0 | Not started
C003 | Office Tower C | T188 | Concrete Pouring | Sarah Johnson | Blocked | High | 2024-12-21 | 2025-01-06 |  | 0 | Concrete | Downtown Avenue | 14522.92 | 17331.65 | Not started
C003 | Office Tower C | T173 | Roofing | Rachel Green | Completed | High | 2024-05-16 | 2024-06-06 | 2024-06-06 | 100 | Paint | Downtown Avenue | 13670.04 | 15317.51 | No issues
C003 | Office Tower C | T224 | Roofing | Dave Brown | Not Started | Low | 2023-08-01 | 2023-08-08 |  | 0 | Cement | Downtown Avenue | 34364.61 | 0 | Not started
C004 | Warehouse D | T187 | Site Survey | Dave Brown | Blocked | Low | 2024-05-07 | 2024-06-04 |  | 0 | Concrete | Industrial Park | 19060.65 | 13844.49 | Not started
C001 | Residential Building A | T406 | Electrical Wiring | John Miller | Completed | Medium | 2024-11-23 | 2024-12-21 | 2024-12-21 | 100 | Copper Wires | Plot 21, Riverside | 30089.21 | 21463.35 | No issues
C003 | Office Tower C | T125 | Interior Painting | Emma White | In Progress | Medium | 2023-09-23 | 2023-10-15 |  | 87 | PVC Pipes | Downtown Avenue | 36891.82 | 40943.03 | In progress
C003 | Office Tower C | T927 | Steel Framework Setup | Emma White | Completed | Medium | 2023-03-12 | 2023-03-27 | 2023-03-27 | 100 | PVC Pipes | Downtown Avenue | 17893.87 | 19014.49 | No issues
C004 | Warehouse D | T403 | Electrical Wiring | Mike Adams | Not Started | High | 2024-10-13 | 2024-10-30 |  | 0 | Roofing Sheets | Industrial Park | 32914.86 | 0 | Not started
C004 | Warehouse D | T977 | Site Survey | John Miller | In Progress | Medium | 2024-01-02 | 2024-01-18 |  | 47 | Rebar | Industrial Park | 37365.66 | 26666.91 | In progress
C001 | Residential Building A | T103 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-06-09 | 2024-07-08 |  | 0 | Concrete | Plot 21, Riverside | 28328.13 | 24246.83 | Not started
C002 | Shopping Complex B | T228 | Roofing | Dave Brown | Blocked | Medium | 2024-11-12 | 2024-12-09 |  | 0 | Cement | Market Street | 28985.45 | 58537.59 | Not started
C001 | Residential Building A | T254 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2023-11-26 | 2023-12-25 |  | 0 | Rebar | Plot 21, Riverside | 33597.49 | 0 | Not started
C002 | Shopping Complex B | T144 | Plumbing Installations | Mike Adams | Not Started | High | 2023-10-26 | 2023-11-25 |  | 0 | Paint | Market Street | 27731.24 | 0 | Not started
C002 | Shopping Complex B | T310 | Foundation Excavation | Carlos Rivera | Blocked | Low | 2024-12-07 | 2024-12-16 |  | 0 | Copper Wires | Market Street | 26434.64 | 56396.22 | Not started
C002 | Shopping Complex B | T748 | Site Survey | Sarah Johnson | Not Started | Medium | 2023-07-08 | 2023-07-22 |  | 0 | Paint | Market Street | 32664.48 | 0 | Not started
C002 | Shopping Complex B | T852 | Roofing | Mike Adams | In Progress | Low | 2023-09-17 | 2023-10-05 |  | 61 | Rebar | Market Street | 7055.08 | 30427.89 | In progress
C004 | Warehouse D | T893 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2023-01-10 | 2023-01-29 |  | 0 | Paint | Industrial Park | 46091.77 | 52352.96 | Not started
C002 | Shopping Complex B | T827 | Electrical Wiring | John Miller | In Progress | Low | 2024-12-08 | 2024-12-27 |  | 88 | Cement | Market Street | 25919.02 | 41261.74 | In progress
C003 | Office Tower C | T385 | Concrete Pouring | Grace Allen | In Progress | Low | 2023-08-13 | 2023-09-04 |  | 90 | PVC Pipes | Downtown Avenue | 42072.85 | 48868.47 | In progress
C003 | Office Tower C | T455 | Steel Framework Setup | Grace Allen | Not Started | Low | 2024-02-05 | 2024-02-17 |  | 0 | PVC Pipes | Downtown Avenue | 23621.3 | 0 | Not started
C003 | Office Tower C | T970 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2024-07-09 | 2024-07-22 |  | 53 | Roofing Sheets | Downtown Avenue | 18508.8 | 19054.28 | In progress
C003 | Office Tower C | T132 | Plumbing Installations | Mike Adams | Blocked | High | 2024-01-02 | 2024-01-13 |  | 0 | Copper Wires | Downtown Avenue | 22218.63 | 18996.78 | Not started
C001 | Residential Building A | T295 | Foundation Excavation | Rachel Green | Completed | Low | 2023-01-01 | 2023-01-28 | 2023-01-28 | 100 | Rebar | Plot 21, Riverside | 47154.82 | 41917.13 | No issues
C003 | Office Tower C | T558 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-09-05 | 2024-09-29 |  | 0 | Paint | Downtown Avenue | 48315.67 | 49220.98 | Not started
C001 | Residential Building A | T468 | Electrical Wiring | John Miller | Completed | Medium | 2024-06-17 | 2024-07-01 | 2024-07-01 | 100 | Concrete | Plot 21, Riverside | 49783.65 | 58438.12 | No issues
C002 | Shopping Complex B | T470 | Roofing | Dave Brown | Not Started | Medium | 2024-06-13 | 2024-07-02 |  | 0 | Cement | Market Street | 36234.39 | 0 | Not started
C003 | Office Tower C | T808 | Site Survey | Rachel Green | Completed | High | 2024-07-14 | 2024-07-21 | 2024-07-21 | 100 | Steel Beams | Downtown Avenue | 24666.62 | 19064.91 | No issues
C002 | Shopping Complex B | T859 | Foundation Excavation | Carlos Rivera | Blocked | High | 2023-09-04 | 2023-09-21 |  | 0 | Cement | Market Street | 22643.52 | 41050.47 | Not started
C003 | Office Tower C | T803 | Electrical Wiring | Emma White | In Progress | Low | 2023-01-21 | 2023-02-20 |  | 47 | Copper Wires | Downtown Avenue | 8454.86 | 9270.75 | In progress
C002 | Shopping Complex B | T746 | Roofing | Carlos Rivera | In Progress | Low | 2023-04-19 | 2023-05-01 |  | 65 | Roofing Sheets | Market Street | 13297.94 | 34454.2 | In progress
C001 | Residential Building A | T727 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2024-01-24 | 2024-02-19 |  | 73 | Roofing Sheets | Plot 21, Riverside | 36327.96 | 31265.22 | In progress
C004 | Warehouse D | T662 | Interior Painting | Rachel Green | Completed | Low | 2024-05-10 | 2024-06-06 | 2024-06-06 | 100 | Rebar | Industrial Park | 41692.29 | 39960.94 | No issues
C001 | Residential Building A | T735 | Roofing | Dave Brown | Blocked | Low | 2024-07-01 | 2024-07-29 |  | 0 | Concrete | Plot 21, Riverside | 45970.17 | 42198.72 | Not started
C004 | Warehouse D | T775 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-01-07 | 2024-01-27 |  | 0 | Paint | Industrial Park | 31218.11 | 29758.03 | Not started
C004 | Warehouse D | T774 | Concrete Pouring | Mike Adams | In Progress | Low | 2024-04-01 | 2024-04-28 |  | 59 | Paint | Industrial Park | 32619.84 | 19770.2 | In progress
C003 | Office Tower C | T750 | Plumbing Installations | Dave Brown | Completed | Medium | 2023-05-10 | 2023-05-31 | 2023-05-31 | 100 | Rebar | Downtown Avenue | 45043.06 | 42792.58 | No issues
C001 | Residential Building A | T248 | Foundation Excavation | Rachel Green | Not Started | High | 2023-06-20 | 2023-07-09 |  | 0 | Rebar | Plot 21, Riverside | 5202.21 | 0 | Not started
C003 | Office Tower C | T701 | Site Survey | Grace Allen | Not Started | Medium | 2024-04-27 | 2024-05-13 |  | 0 | Copper Wires | Downtown Avenue | 8557.15 | 0 | Not started
C003 | Office Tower C | T595 | Interior Painting | Mike Adams | Not Started | Low | 2024-10-15 | 2024-10-25 |  | 0 | Steel Beams | Downtown Avenue | 45409.72 | 0 | Not started
C002 | Shopping Complex B | T921 | Electrical Wiring | Emma White | Completed | Low | 2024-09-02 | 2024-09-29 | 2024-09-29 | 100 | Cement | Market Street | 10722.59 | 34631.17 | No issues
C003 | Office Tower C | T607 | Plumbing Installations | Sarah Johnson | Not Started | High | 2024-12-12 | 2024-12-28 |  | 0 | Copper Wires | Downtown Avenue | 25527.6 | 0 | Not started
C003 | Office Tower C | T781 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2024-08-27 | 2024-09-14 |  | 79 | PVC Pipes | Downtown Avenue | 9210.62 | 9267.73 | In progress
C004 | Warehouse D | T872 | Foundation Excavation | Dave Brown | Not Started | Low | 2023-06-24 | 2023-07-20 |  | 0 | Roofing Sheets | Industrial Park | 42205.77 | 0 | Not started
C003 | Office Tower C | T485 | Electrical Wiring | Emma White | Not Started | Medium | 2023-04-09 | 2023-04-25 |  | 0 | Steel Beams | Downtown Avenue | 8424.14 | 0 | Not started
C002 | Shopping Complex B | T293 | Plumbing Installations | Rachel Green | In Progress | Medium | 2024-10-10 | 2024-10-18 |  | 90 | Concrete | Market Street | 15241.35 | 42413.35 | In progress
C004 | Warehouse D | T974 | Steel Framework Setup | Emma White | Blocked | Low | 2024-06-14 | 2024-07-04 |  | 0 | Steel Beams | Industrial Park | 41721.97 | 28954.88 | Not started
C001 | Residential Building A | T187 | Roofing | Grace Allen | Not Started | Medium | 2024-05-13 | 2024-05-28 |  | 0 | Rebar | Plot 21, Riverside | 34977.21 | 0 | Not started
C004 | Warehouse D | T622 | Foundation Excavation | Dave Brown | Blocked | Medium | 2023-10-10 | 2023-10-25 |  | 0 | Rebar | Industrial Park | 26162.37 | 25203.6 | Not started
C002 | Shopping Complex B | T513 | Electrical Wiring | Rachel Green | Not Started | High | 2023-02-27 | 2023-03-27 |  | 0 | Roofing Sheets | Market Street | 16003.83 | 0 | Not started
C001 | Residential Building A | T603 | Plumbing Installations | Emma White | Blocked | Medium | 2024-01-02 | 2024-01-22 |  | 0 | PVC Pipes | Plot 21, Riverside | 5226.55 | 4531.44 | Not started
C003 | Office Tower C | T165 | Interior Painting | Grace Allen | In Progress | Medium | 2024-04-17 | 2024-05-10 |  | 65 | Steel Beams | Downtown Avenue | 14668.87 | 17304.64 | In progress
C002 | Shopping Complex B | T452 | Roofing | Emma White | Completed | Medium | 2023-04-06 | 2023-05-01 | 2023-05-01 | 100 | Concrete | Market Street | 38206.8 | 58199.24 | No issues
C001 | Residential Building A | T226 | Site Survey | Emma White | Blocked | Medium | 2023-12-19 | 2024-01-03 |  | 0 | Copper Wires | Plot 21, Riverside | 45519.64 | 35994.88 | Not started
C002 | Shopping Complex B | T460 | Electrical Wiring | Dave Brown | Not Started | High | 2024-04-14 | 2024-05-05 |  | 0 | PVC Pipes | Market Street | 10745.2 | 0 | Not started
C002 | Shopping Complex B | T579 | Roofing | Emma White | Not Started | Low | 2024-08-07 | 2024-08-31 |  | 0 | Rebar | Market Street | 49858.11 | 0 | Not started
C001 | Residential Building A | T167 | Plumbing Installations | Rachel Green | In Progress | Low | 2024-06-15 | 2024-06-24 |  | 75 | Cement | Plot 21, Riverside | 5845.91 | 5484.82 | In progress
C001 | Residential Building A | T569 | Foundation Excavation | Rachel Green | In Progress | High | 2023-03-25 | 2023-04-13 |  | 9 | Steel Beams | Plot 21, Riverside | 46327.23 | 54868.55 | In progress
C001 | Residential Building A | T914 | Electrical Wiring | Emma White | Not Started | High | 2023-09-27 | 2023-10-26 |  | 0 | Cement | Plot 21, Riverside | 46235.9 | 0 | Not started
C002 | Shopping Complex B | T242 | Interior Painting | Sarah Johnson | In Progress | Low | 2023-12-27 | 2024-01-10 |  | 40 | Rebar | Market Street | 28382.23 | 42657.55 | In progress
C003 | Office Tower C | T193 | Site Survey | Grace Allen | Blocked | High | 2023-04-07 | 2023-04-23 |  | 0 | Concrete | Downtown Avenue | 9381.02 | 8220.34 | Not started
C002 | Shopping Complex B | T711 | Steel Framework Setup | Mike Adams | Blocked | High | 2023-06-02 | 2023-06-09 |  | 0 | Steel Beams | Market Street | 34337.98 | 57099.6 | Not started
C001 | Residential Building A | T759 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2024-08-03 | 2024-08-22 | 2024-08-22 | 100 | Copper Wires | Plot 21, Riverside | 42392.69 | 45837.75 | No issues
C001 | Residential Building A | T305 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2024-11-25 | 2024-12-02 |  | 76 | Steel Beams | Plot 21, Riverside | 43763.73 | 48872.35 | In progress
C001 | Residential Building A | T824 | Interior Painting | Rachel Green | Blocked | High | 2023-11-05 | 2023-11-19 |  | 0 | Roofing Sheets | Plot 21, Riverside | 17276.37 | 14382.05 | Not started
C001 | Residential Building A | T797 | Roofing | Dave Brown | Not Started | Low | 2023-02-21 | 2023-03-15 |  | 0 | Copper Wires | Plot 21, Riverside | 5007.53 | 0 | Not started
C003 | Office Tower C | T522 | Concrete Pouring | Rachel Green | Not Started | Low | 2024-07-19 | 2024-08-08 |  | 0 | PVC Pipes | Downtown Avenue | 30085.8 | 0 | Not started
C001 | Residential Building A | T430 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2024-07-06 | 2024-08-05 |  | 0 | Concrete | Plot 21, Riverside | 22510.99 | 22620.17 | Not started
C004 | Warehouse D | T282 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-07-07 | 2023-08-02 |  | 0 | Concrete | Industrial Park | 23250.57 | 0 | Not started
C004 | Warehouse D | T228 | Interior Painting | Sarah Johnson | Blocked | Low | 2023-12-19 | 2024-01-06 |  | 0 | Concrete | Industrial Park | 26532.66 | 25502.84 | Not started
C001 | Residential Building A | T765 | Concrete Pouring | Emma White | Completed | Medium | 2023-06-03 | 2023-06-19 | 2023-06-19 | 100 | Roofing Sheets | Plot 21, Riverside | 44903.44 | 33517.76 | No issues
C002 | Shopping Complex B | T901 | Site Survey | Carlos Rivera | Completed | High | 2024-11-23 | 2024-12-22 | 2024-12-22 | 100 | Paint | Market Street | 34996.28 | 55091.86 | No issues
C002 | Shopping Complex B | T207 | Site Survey | Sarah Johnson | In Progress | Low | 2024-11-06 | 2024-11-20 |  | 37 | Roofing Sheets | Market Street | 21579.83 | 50574.69 | In progress
C002 | Shopping Complex B | T390 | Roofing | Dave Brown | Not Started | Medium | 2023-10-05 | 2023-10-20 |  | 0 | PVC Pipes | Market Street | 36896.12 | 0 | Not started
C004 | Warehouse D | T984 | Site Survey | Emma White | Not Started | Low | 2024-05-11 | 2024-05-23 |  | 0 | Rebar | Industrial Park | 34082.24 | 0 | Not started
C001 | Residential Building A | T791 | Roofing | Sarah Johnson | Not Started | High | 2023-07-07 | 2023-07-24 |  | 0 | Steel Beams | Plot 21, Riverside | 36720.14 | 0 | Not started
C002 | Shopping Complex B | T211 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-10-06 | 2024-10-24 | 2024-10-24 | 100 | Copper Wires | Market Street | 45580.07 | 69816.52 | No issues
C001 | Residential Building A | T720 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-08-17 | 2024-08-29 | 2024-08-29 | 100 | Rebar | Plot 21, Riverside | 34207.25 | 25739.39 | No issues
C001 | Residential Building A | T641 | Plumbing Installations | John Miller | Not Started | Low | 2023-10-18 | 2023-11-02 |  | 0 | Concrete | Plot 21, Riverside | 27085.03 | 0 | Not started
C003 | Office Tower C | T272 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-09-12 | 2024-09-29 |  | 0 | Rebar | Downtown Avenue | 42239.36 | 0 | Not started
C004 | Warehouse D | T566 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-09-11 | 2024-09-21 |  | 89 | Rebar | Industrial Park | 42524.87 | 37658.18 | In progress
C002 | Shopping Complex B | T255 | Plumbing Installations | Rachel Green | In Progress | Low | 2024-07-26 | 2024-08-20 |  | 23 | Concrete | Market Street | 26612.29 | 46597.01 | In progress
C002 | Shopping Complex B | T409 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2023-12-25 | 2024-01-24 |  | 0 | Rebar | Market Street | 42918.03 | 0 | Not started
C002 | Shopping Complex B | T911 | Foundation Excavation | John Miller | Not Started | Low | 2024-10-22 | 2024-11-15 |  | 0 | Copper Wires | Market Street | 33279.51 | 0 | Not started
C001 | Residential Building A | T689 | Concrete Pouring | John Miller | In Progress | Medium | 2024-01-10 | 2024-01-20 |  | 15 | Roofing Sheets | Plot 21, Riverside | 35751.87 | 33365.65 | In progress
C002 | Shopping Complex B | T420 | Plumbing Installations | Emma White | Blocked | Medium | 2024-10-01 | 2024-10-16 |  | 0 | Concrete | Market Street | 29413.14 | 51121.45 | Not started
C003 | Office Tower C | T420 | Steel Framework Setup | John Miller | Blocked | Low | 2024-08-24 | 2024-09-11 |  | 0 | Rebar | Downtown Avenue | 9551.89 | 9553.87 | Not started
C001 | Residential Building A | T887 | Roofing | John Miller | Not Started | Low | 2023-07-28 | 2023-08-08 |  | 0 | Roofing Sheets | Plot 21, Riverside | 25747.4 | 0 | Not started
C004 | Warehouse D | T644 | Electrical Wiring | Mike Adams | Blocked | Medium | 2024-10-19 | 2024-10-28 |  | 0 | Rebar | Industrial Park | 18852.08 | 20505.81 | Not started
C002 | Shopping Complex B | T417 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-10-23 | 2023-11-14 |  | 0 | Steel Beams | Market Street | 34754.62 | 0 | Not started
C001 | Residential Building A | T612 | Electrical Wiring | John Miller | In Progress | High | 2023-04-13 | 2023-04-27 |  | 97 | Rebar | Plot 21, Riverside | 8723.17 | 6252.7 | In progress
C004 | Warehouse D | T136 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2024-03-15 | 2024-03-23 |  | 25 | Cement | Industrial Park | 36958.49 | 27100.04 | In progress
C001 | Residential Building A | T263 | Steel Framework Setup | Dave Brown | Completed | Low | 2023-02-23 | 2023-03-10 | 2023-03-10 | 100 | Steel Beams | Plot 21, Riverside | 5536.1 | 5485.28 | No issues
C001 | Residential Building A | T346 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-12-15 | 2025-01-05 |  | 0 | Steel Beams | Plot 21, Riverside | 33200.98 | 20830.74 | Not started
C001 | Residential Building A | T295 | Site Survey | Grace Allen | Not Started | High | 2023-04-04 | 2023-04-20 |  | 0 | Paint | Plot 21, Riverside | 34112.22 | 0 | Not started
C004 | Warehouse D | T608 | Concrete Pouring | John Miller | Blocked | Medium | 2024-04-19 | 2024-05-02 |  | 0 | PVC Pipes | Industrial Park | 21362.82 | 15249.75 | Not started
C004 | Warehouse D | T634 | Concrete Pouring | John Miller | In Progress | High | 2023-08-21 | 2023-09-09 |  | 43 | Roofing Sheets | Industrial Park | 44745.78 | 36440.77 | In progress
C002 | Shopping Complex B | T117 | Concrete Pouring | Grace Allen | In Progress | Low | 2023-05-06 | 2023-05-27 |  | 86 | Rebar | Market Street | 13922.56 | 41451.91 | In progress
C001 | Residential Building A | T249 | Site Survey | Grace Allen | Not Started | High | 2024-06-18 | 2024-06-30 |  | 0 | Rebar | Plot 21, Riverside | 25079.43 | 0 | Not started
C001 | Residential Building A | T313 | Site Survey | Carlos Rivera | Completed | Medium | 2023-02-27 | 2023-03-14 | 2023-03-14 | 100 | Roofing Sheets | Plot 21, Riverside | 48783.79 | 33633.73 | No issues
C001 | Residential Building A | T499 | Site Survey | Grace Allen | Completed | Medium | 2023-03-20 | 2023-03-28 | 2023-03-28 | 100 | Copper Wires | Plot 21, Riverside | 23777.95 | 23985.61 | No issues
C003 | Office Tower C | T698 | Foundation Excavation | Emma White | Completed | High | 2024-05-26 | 2024-06-04 | 2024-06-04 | 100 | Paint | Downtown Avenue | 11718.36 | 9671.22 | No issues
C001 | Residential Building A | T807 | Site Survey | Grace Allen | Completed | Medium | 2024-11-02 | 2024-11-11 | 2024-11-11 | 100 | Steel Beams | Plot 21, Riverside | 45484.15 | 31392.24 | No issues
C001 | Residential Building A | T836 | Interior Painting | Mike Adams | In Progress | Medium | 2024-05-14 | 2024-05-29 |  | 30 | Copper Wires | Plot 21, Riverside | 13422.47 | 14446.45 | In progress
C003 | Office Tower C | T752 | Foundation Excavation | Dave Brown | Not Started | Medium | 2024-06-19 | 2024-07-07 |  | 0 | Steel Beams | Downtown Avenue | 12681.54 | 0 | Not started
C001 | Residential Building A | T118 | Steel Framework Setup | Sarah Johnson | Completed | High | 2023-06-02 | 2023-06-27 | 2023-06-27 | 100 | Concrete | Plot 21, Riverside | 28467.58 | 25715.09 | No issues
C002 | Shopping Complex B | T849 | Foundation Excavation | Mike Adams | Not Started | Medium | 2023-01-07 | 2023-02-01 |  | 0 | Roofing Sheets | Market Street | 25502.62 | 0 | Not started
C003 | Office Tower C | T710 | Electrical Wiring | Rachel Green | In Progress | High | 2024-12-14 | 2025-01-06 |  | 62 | Steel Beams | Downtown Avenue | 20870.56 | 16287.66 | In progress
C004 | Warehouse D | T357 | Concrete Pouring | Grace Allen | Completed | Low | 2024-10-09 | 2024-10-27 | 2024-10-27 | 100 | Concrete | Industrial Park | 45194.89 | 32217.11 | No issues
C003 | Office Tower C | T544 | Steel Framework Setup | John Miller | Not Started | Medium | 2024-05-17 | 2024-05-27 |  | 0 | PVC Pipes | Downtown Avenue | 48191.92 | 0 | Not started
C002 | Shopping Complex B | T123 | Steel Framework Setup | Emma White | Not Started | High | 2023-04-15 | 2023-05-11 |  | 0 | Paint | Market Street | 41818.43 | 0 | Not started
C001 | Residential Building A | T779 | Roofing | Rachel Green | Blocked | High | 2024-07-16 | 2024-08-11 |  | 0 | Copper Wires | Plot 21, Riverside | 6186.37 | 4927.84 | Not started
C001 | Residential Building A | T889 | Plumbing Installations | Grace Allen | In Progress | Medium | 2023-07-03 | 2023-07-28 |  | 50 | Steel Beams | Plot 21, Riverside | 5163.16 | 4008.08 | In progress
C002 | Shopping Complex B | T507 | Concrete Pouring | Mike Adams | Completed | Low | 2023-12-05 | 2023-12-13 | 2023-12-13 | 100 | Roofing Sheets | Market Street | 45722.62 | 78916.97 | No issues
C001 | Residential Building A | T960 | Interior Painting | Mike Adams | Completed | Medium | 2023-07-25 | 2023-08-19 | 2023-08-19 | 100 | Steel Beams | Plot 21, Riverside | 34742.49 | 32973.62 | No issues
C003 | Office Tower C | T158 | Site Survey | Dave Brown | Blocked | Low | 2023-12-08 | 2024-01-05 |  | 0 | Concrete | Downtown Avenue | 19329.24 | 13598.94 | Not started
C001 | Residential Building A | T159 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-03-14 | 2024-04-03 |  | 0 | Steel Beams | Plot 21, Riverside | 31014.75 | 0 | Not started
C002 | Shopping Complex B | T344 | Concrete Pouring | Rachel Green | Not Started | Low | 2023-07-11 | 2023-07-25 |  | 0 | Paint | Market Street | 36733.38 | 0 | Not started
C001 | Residential Building A | T774 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2023-03-16 | 2023-04-11 |  | 0 | Rebar | Plot 21, Riverside | 15009.36 | 0 | Not started
C004 | Warehouse D | T536 | Plumbing Installations | Sarah Johnson | Not Started | High | 2024-03-18 | 2024-04-04 |  | 0 | Cement | Industrial Park | 40396.55 | 0 | Not started
C003 | Office Tower C | T291 | Concrete Pouring | Dave Brown | Not Started | High | 2024-01-15 | 2024-02-13 |  | 0 | Rebar | Downtown Avenue | 19726.51 | 0 | Not started
C001 | Residential Building A | T586 | Foundation Excavation | Sarah Johnson | Completed | High | 2024-02-01 | 2024-02-10 | 2024-02-10 | 100 | Rebar | Plot 21, Riverside | 30103.73 | 23966.4 | No issues
C002 | Shopping Complex B | T466 | Plumbing Installations | Grace Allen | Blocked | High | 2024-11-01 | 2024-11-13 |  | 0 | Cement | Market Street | 6139.26 | 29320.38 | Not started
C004 | Warehouse D | T634 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2024-07-04 | 2024-07-13 |  | 0 | Concrete | Industrial Park | 25845.8 | 27435.6 | Not started
C004 | Warehouse D | T996 | Steel Framework Setup | Carlos Rivera | Completed | High | 2024-10-06 | 2024-11-01 | 2024-11-01 | 100 | Steel Beams | Industrial Park | 25892.86 | 19961.05 | No issues
C004 | Warehouse D | T868 | Site Survey | Emma White | Completed | High | 2023-07-24 | 2023-08-09 | 2023-08-09 | 100 | Steel Beams | Industrial Park | 39733.84 | 43343.95 | No issues
C004 | Warehouse D | T298 | Foundation Excavation | Sarah Johnson | Blocked | Low | 2024-09-01 | 2024-09-27 |  | 0 | Concrete | Industrial Park | 21932.37 | 21520.5 | Not started
C003 | Office Tower C | T688 | Electrical Wiring | Grace Allen | Not Started | Medium | 2023-10-04 | 2023-10-22 |  | 0 | Rebar | Downtown Avenue | 20480.59 | 0 | Not started
C004 | Warehouse D | T971 | Steel Framework Setup | Emma White | Completed | High | 2024-10-26 | 2024-11-10 | 2024-11-10 | 100 | Roofing Sheets | Industrial Park | 12773.4 | 10447.76 | No issues
C004 | Warehouse D | T190 | Interior Painting | Mike Adams | In Progress | Medium | 2024-11-25 | 2024-12-11 |  | 35 | Copper Wires | Industrial Park | 23077.05 | 14249.57 | In progress
C003 | Office Tower C | T848 | Interior Painting | John Miller | Completed | High | 2024-11-17 | 2024-12-15 | 2024-12-15 | 100 | Paint | Downtown Avenue | 45309.93 | 28722.64 | No issues
C003 | Office Tower C | T258 | Interior Painting | John Miller | In Progress | Low | 2023-06-22 | 2023-07-05 |  | 86 | Paint | Downtown Avenue | 35160.51 | 41244.55 | In progress
C001 | Residential Building A | T241 | Steel Framework Setup | Dave Brown | In Progress | Low | 2024-04-11 | 2024-04-22 |  | 14 | Concrete | Plot 21, Riverside | 7602.17 | 5962.4 | In progress
C004 | Warehouse D | T324 | Plumbing Installations | Dave Brown | Completed | Medium | 2023-05-06 | 2023-06-04 | 2023-06-04 | 100 | Concrete | Industrial Park | 31926.86 | 21026.49 | No issues
C002 | Shopping Complex B | T299 | Site Survey | Sarah Johnson | Completed | Medium | 2024-12-14 | 2025-01-10 | 2025-01-10 | 100 | Rebar | Market Street | 35531.67 | 62567.8 | No issues
C002 | Shopping Complex B | T817 | Interior Painting | Grace Allen | Not Started | Low | 2024-04-07 | 2024-04-27 |  | 0 | Steel Beams | Market Street | 8502.69 | 0 | Not started
C002 | Shopping Complex B | T550 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-06-27 | 2023-07-04 |  | 0 | Copper Wires | Market Street | 19058.44 | 0 | Not started
C001 | Residential Building A | T998 | Site Survey | Emma White | Not Started | High | 2023-07-23 | 2023-07-30 |  | 0 | Copper Wires | Plot 21, Riverside | 13631.5 | 0 | Not started
C002 | Shopping Complex B | T754 | Interior Painting | Emma White | In Progress | Medium | 2024-05-12 | 2024-05-20 |  | 8 | Copper Wires | Market Street | 43308.31 | 59607.82 | In progress
C002 | Shopping Complex B | T918 | Interior Painting | Grace Allen | Not Started | High | 2023-12-20 | 2024-01-18 |  | 0 | PVC Pipes | Market Street | 38066.42 | 0 | Not started
C002 | Shopping Complex B | T579 | Roofing | Carlos Rivera | In Progress | Medium | 2024-05-12 | 2024-05-26 |  | 88 | PVC Pipes | Market Street | 41119.5 | 53796.54 | In progress
C001 | Residential Building A | T102 | Electrical Wiring | Grace Allen | Not Started | High | 2023-08-28 | 2023-09-15 |  | 0 | Concrete | Plot 21, Riverside | 43796.26 | 0 | Not started
C003 | Office Tower C | T954 | Plumbing Installations | Rachel Green | Not Started | Low | 2023-11-18 | 2023-12-15 |  | 0 | Copper Wires | Downtown Avenue | 19210 | 0 | Not started
C002 | Shopping Complex B | T135 | Plumbing Installations | Mike Adams | In Progress | Low | 2023-01-20 | 2023-02-18 |  | 80 | Steel Beams | Market Street | 14984.41 | 37415.19 | In progress
C003 | Office Tower C | T217 | Steel Framework Setup | Mike Adams | Not Started | High | 2023-11-03 | 2023-11-30 |  | 0 | Copper Wires | Downtown Avenue | 12721.09 | 0 | Not started
C003 | Office Tower C | T196 | Interior Painting | Emma White | Blocked | High | 2024-09-28 | 2024-10-10 |  | 0 | Roofing Sheets | Downtown Avenue | 32151.76 | 30073.8 | Not started
C001 | Residential Building A | T151 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2024-11-26 | 2024-12-05 |  | 92 | Roofing Sheets | Plot 21, Riverside | 42625.64 | 36370.12 | In progress
C002 | Shopping Complex B | T961 | Roofing | Emma White | Not Started | High | 2024-10-14 | 2024-11-08 |  | 0 | Steel Beams | Market Street | 42202.52 | 0 | Not started
C002 | Shopping Complex B | T151 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2024-06-25 | 2024-07-23 |  | 0 | Concrete | Market Street | 19947.27 | 0 | Not started
C004 | Warehouse D | T746 | Foundation Excavation | Rachel Green | Blocked | Low | 2024-02-08 | 2024-03-01 |  | 0 | Concrete | Industrial Park | 17767.65 | 21038.26 | Not started
C002 | Shopping Complex B | T315 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2024-11-06 | 2024-11-16 |  | 0 | Paint | Market Street | 37215.75 | 0 | Not started
C001 | Residential Building A | T428 | Steel Framework Setup | John Miller | Blocked | Medium | 2024-11-05 | 2024-11-18 |  | 0 | Copper Wires | Plot 21, Riverside | 29195.47 | 33504.27 | Not started
C002 | Shopping Complex B | T461 | Roofing | Dave Brown | In Progress | High | 2023-04-07 | 2023-04-16 |  | 90 | Copper Wires | Market Street | 30454.29 | 56277.65 | In progress
C002 | Shopping Complex B | T471 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-01-06 | 2024-02-03 |  | 0 | Steel Beams | Market Street | 27525.14 | 0 | Not started
C001 | Residential Building A | T530 | Roofing | John Miller | In Progress | Medium | 2024-06-10 | 2024-06-29 |  | 34 | Rebar | Plot 21, Riverside | 33009.5 | 28867.98 | In progress
C004 | Warehouse D | T276 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-04-18 | 2023-05-13 | 2023-05-13 | 100 | Cement | Industrial Park | 12586.42 | 13494.01 | No issues
C004 | Warehouse D | T845 | Roofing | Sarah Johnson | Completed | High | 2023-02-28 | 2023-03-30 | 2023-03-30 | 100 | Rebar | Industrial Park | 21969.04 | 20173.77 | No issues
C003 | Office Tower C | T232 | Electrical Wiring | Rachel Green | Blocked | High | 2024-09-02 | 2024-09-09 |  | 0 | Steel Beams | Downtown Avenue | 28459.57 | 21886.67 | Not started
C003 | Office Tower C | T388 | Roofing | Rachel Green | Not Started | Medium | 2024-05-19 | 2024-06-09 |  | 0 | Roofing Sheets | Downtown Avenue | 30746.03 | 0 | Not started
C004 | Warehouse D | T670 | Roofing | Mike Adams | In Progress | Low | 2023-11-16 | 2023-12-02 |  | 32 | Cement | Industrial Park | 33739.17 | 22741.37 | In progress
C004 | Warehouse D | T953 | Interior Painting | Carlos Rivera | Completed | Medium | 2023-07-02 | 2023-07-17 | 2023-07-17 | 100 | Paint | Industrial Park | 19300.27 | 14151.42 | No issues
C004 | Warehouse D | T127 | Roofing | John Miller | Completed | Medium | 2023-01-06 | 2023-01-21 | 2023-01-21 | 100 | Rebar | Industrial Park | 41963.63 | 45114.55 | No issues
C004 | Warehouse D | T901 | Foundation Excavation | Grace Allen | Completed | Medium | 2023-11-14 | 2023-12-03 | 2023-12-03 | 100 | Rebar | Industrial Park | 20768.24 | 20157.25 | No issues
C004 | Warehouse D | T669 | Roofing | Emma White | Completed | High | 2023-09-10 | 2023-10-07 | 2023-10-07 | 100 | Concrete | Industrial Park | 44114.38 | 42979.12 | No issues
C003 | Office Tower C | T536 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2023-09-07 | 2023-09-18 |  | 0 | Concrete | Downtown Avenue | 24312.09 | 0 | Not started
C003 | Office Tower C | T166 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-05-03 | 2023-05-29 | 2023-05-29 | 100 | Paint | Downtown Avenue | 23723.99 | 23183.52 | No issues
C003 | Office Tower C | T446 | Concrete Pouring | Rachel Green | Not Started | Medium | 2023-04-20 | 2023-05-12 |  | 0 | Cement | Downtown Avenue | 30865.19 | 0 | Not started
C003 | Office Tower C | T748 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-02-13 | 2024-03-03 |  | 0 | Cement | Downtown Avenue | 16897.78 | 0 | Not started
C003 | Office Tower C | T837 | Interior Painting | Sarah Johnson | In Progress | High | 2023-02-15 | 2023-03-01 |  | 54 | Paint | Downtown Avenue | 41446.26 | 38712.24 | In progress
C003 | Office Tower C | T864 | Concrete Pouring | Emma White | Blocked | High | 2023-01-10 | 2023-01-19 |  | 0 | Roofing Sheets | Downtown Avenue | 11221.56 | 10589.42 | Not started
C001 | Residential Building A | T362 | Plumbing Installations | John Miller | Not Started | Low | 2024-09-06 | 2024-09-19 |  | 0 | Concrete | Plot 21, Riverside | 24313.93 | 0 | Not started
C004 | Warehouse D | T366 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-08-12 | 2024-09-05 |  | 0 | Concrete | Industrial Park | 30623.21 | 23917.14 | Not started
C001 | Residential Building A | T302 | Electrical Wiring | Mike Adams | Not Started | Medium | 2023-08-18 | 2023-08-26 |  | 0 | Rebar | Plot 21, Riverside | 29481.38 | 0 | Not started
C002 | Shopping Complex B | T112 | Electrical Wiring | Carlos Rivera | In Progress | Medium | 2023-10-26 | 2023-11-07 |  | 98 | Rebar | Market Street | 20590.49 | 47610.64 | In progress
C004 | Warehouse D | T748 | Plumbing Installations | Sarah Johnson | Completed | High | 2023-08-28 | 2023-09-04 | 2023-09-04 | 100 | Cement | Industrial Park | 31641.56 | 24894.11 | No issues
C003 | Office Tower C | T207 | Steel Framework Setup | Mike Adams | Blocked | High | 2024-09-09 | 2024-09-23 |  | 0 | Roofing Sheets | Downtown Avenue | 31543.09 | 23788.73 | Not started
C002 | Shopping Complex B | T165 | Plumbing Installations | Grace Allen | Completed | Low | 2024-08-01 | 2024-08-17 | 2024-08-17 | 100 | Paint | Market Street | 8365.02 | 30953.63 | No issues
C001 | Residential Building A | T455 | Roofing | Emma White | Completed | Low | 2024-01-20 | 2024-02-02 | 2024-02-02 | 100 | Steel Beams | Plot 21, Riverside | 32389.86 | 23929.88 | No issues
C004 | Warehouse D | T561 | Roofing | Emma White | Completed | High | 2024-05-18 | 2024-06-02 | 2024-06-02 | 100 | Paint | Industrial Park | 41112.72 | 35767.21 | No issues
C003 | Office Tower C | T579 | Electrical Wiring | Grace Allen | Not Started | High | 2024-03-23 | 2024-03-30 |  | 0 | Cement | Downtown Avenue | 22802.43 | 0 | Not started
C002 | Shopping Complex B | T583 | Concrete Pouring | Dave Brown | Completed | High | 2023-03-19 | 2023-03-26 | 2023-03-26 | 100 | PVC Pipes | Market Street | 11893.71 | 36545.25 | No issues
C004 | Warehouse D | T360 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2023-04-24 | 2023-05-16 |  | 29 | Cement | Industrial Park | 14266.38 | 11028.35 | In progress
C001 | Residential Building A | T418 | Roofing | Rachel Green | Blocked | Medium | 2024-03-24 | 2024-04-07 |  | 0 | Steel Beams | Plot 21, Riverside | 9111.59 | 6092.81 | Not started
C003 | Office Tower C | T367 | Concrete Pouring | Carlos Rivera | Completed | High | 2024-11-08 | 2024-12-04 | 2024-12-04 | 100 | Paint | Downtown Avenue | 18230.99 | 14473.1 | No issues
C001 | Residential Building A | T656 | Foundation Excavation | Grace Allen | Completed | Low | 2024-02-13 | 2024-03-12 | 2024-03-12 | 100 | Paint | Plot 21, Riverside | 21939.02 | 20055.29 | No issues
C002 | Shopping Complex B | T685 | Steel Framework Setup | Emma White | Blocked | High | 2024-06-17 | 2024-06-27 |  | 0 | Steel Beams | Market Street | 19566.46 | 42418.31 | Not started
C001 | Residential Building A | T880 | Steel Framework Setup | Mike Adams | Completed | High | 2023-01-16 | 2023-01-26 | 2023-01-26 | 100 | Rebar | Plot 21, Riverside | 28793.9 | 33926.73 | No issues
C003 | Office Tower C | T118 | Roofing | Grace Allen | Blocked | Medium | 2023-01-20 | 2023-01-31 |  | 0 | Rebar | Downtown Avenue | 20778.58 | 19272.48 | Not started
C002 | Shopping Complex B | T407 | Foundation Excavation | Emma White | Completed | Medium | 2024-11-20 | 2024-12-02 | 2024-12-02 | 100 | Steel Beams | Market Street | 11175.27 | 35192.64 | No issues
C003 | Office Tower C | T532 | Site Survey | Mike Adams | Not Started | Medium | 2023-04-14 | 2023-04-23 |  | 0 | Steel Beams | Downtown Avenue | 5204.83 | 0 | Not started
C001 | Residential Building A | T384 | Site Survey | Emma White | Blocked | Low | 2024-03-21 | 2024-04-02 |  | 0 | Cement | Plot 21, Riverside | 5065.83 | 5297.95 | Not started
C001 | Residential Building A | T261 | Site Survey | John Miller | Completed | Medium | 2023-05-20 | 2023-06-08 | 2023-06-08 | 100 | Copper Wires | Plot 21, Riverside | 49382.3 | 51360.13 | No issues
C002 | Shopping Complex B | T439 | Foundation Excavation | Emma White | Blocked | Low | 2023-11-06 | 2023-11-28 |  | 0 | Paint | Market Street | 30330.74 | 53711.79 | Not started
C004 | Warehouse D | T454 | Roofing | Dave Brown | Completed | High | 2023-08-02 | 2023-08-23 | 2023-08-23 | 100 | Cement | Industrial Park | 17852.1 | 13175.38 | No issues
C002 | Shopping Complex B | T182 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2024-02-04 | 2024-02-26 |  | 0 | Copper Wires | Market Street | 31574.98 | 0 | Not started
C001 | Residential Building A | T195 | Concrete Pouring | Mike Adams | Completed | Medium | 2023-08-16 | 2023-08-31 | 2023-08-31 | 100 | Cement | Plot 21, Riverside | 40731.53 | 29688.25 | No issues
C003 | Office Tower C | T192 | Interior Painting | Mike Adams | Completed | Low | 2024-08-05 | 2024-08-30 | 2024-08-30 | 100 | Paint | Downtown Avenue | 13630.92 | 12635.97 | No issues
C001 | Residential Building A | T884 | Interior Painting | Carlos Rivera | Completed | Medium | 2023-07-24 | 2023-08-09 | 2023-08-09 | 100 | Cement | Plot 21, Riverside | 22099.69 | 18649 | No issues
C003 | Office Tower C | T910 | Concrete Pouring | Emma White | Not Started | Low | 2023-07-15 | 2023-07-25 |  | 0 | Copper Wires | Downtown Avenue | 12104.22 | 0 | Not started
C003 | Office Tower C | T631 | Roofing | Carlos Rivera | Completed | Low | 2023-12-13 | 2023-12-28 | 2023-12-28 | 100 | Concrete | Downtown Avenue | 17014.06 | 18842.2 | No issues
C003 | Office Tower C | T713 | Site Survey | Emma White | Blocked | High | 2024-12-16 | 2024-12-29 |  | 0 | PVC Pipes | Downtown Avenue | 5653.08 | 3685.23 | Not started
C002 | Shopping Complex B | T569 | Roofing | Carlos Rivera | Not Started | High | 2024-08-26 | 2024-09-09 |  | 0 | Rebar | Market Street | 49564.13 | 0 | Not started
C002 | Shopping Complex B | T261 | Foundation Excavation | Dave Brown | Not Started | Medium | 2023-03-25 | 2023-04-12 |  | 0 | Roofing Sheets | Market Street | 25641.24 | 0 | Not started
C003 | Office Tower C | T608 | Foundation Excavation | Grace Allen | Blocked | High | 2023-03-02 | 2023-03-16 |  | 0 | PVC Pipes | Downtown Avenue | 22402.34 | 18464.1 | Not started
C002 | Shopping Complex B | T114 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-11-05 | 2023-11-17 |  | 33 | Steel Beams | Market Street | 38104.51 | 48495.31 | In progress
C003 | Office Tower C | T969 | Electrical Wiring | Rachel Green | Completed | High | 2024-08-05 | 2024-08-21 | 2024-08-21 | 100 | Roofing Sheets | Downtown Avenue | 14290.39 | 9545.79 | No issues
C004 | Warehouse D | T133 | Interior Painting | John Miller | Not Started | Low | 2023-12-13 | 2024-01-06 |  | 0 | Concrete | Industrial Park | 22278.37 | 0 | Not started
C002 | Shopping Complex B | T495 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2024-07-09 | 2024-07-31 |  | 7 | Paint | Market Street | 44460.27 | 69246.3 | In progress
C002 | Shopping Complex B | T348 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2023-10-28 | 2023-11-08 | 2023-11-08 | 100 | Concrete | Market Street | 41793.58 | 70129.14 | No issues
C001 | Residential Building A | T784 | Steel Framework Setup | Rachel Green | Not Started | Low | 2024-06-07 | 2024-07-05 |  | 0 | Concrete | Plot 21, Riverside | 27678.16 | 0 | Not started
C003 | Office Tower C | T502 | Concrete Pouring | Emma White | In Progress | Medium | 2023-02-16 | 2023-02-25 |  | 20 | Cement | Downtown Avenue | 46119.27 | 50725.16 | In progress
C003 | Office Tower C | T853 | Site Survey | Carlos Rivera | Completed | Low | 2023-10-15 | 2023-10-22 | 2023-10-22 | 100 | Cement | Downtown Avenue | 33968.97 | 22978.82 | No issues
C001 | Residential Building A | T589 | Foundation Excavation | Mike Adams | Blocked | Medium | 2023-07-13 | 2023-07-29 |  | 0 | Concrete | Plot 21, Riverside | 29694.32 | 25084.75 | Not started
C003 | Office Tower C | T136 | Concrete Pouring | John Miller | Blocked | Medium | 2023-07-21 | 2023-08-04 |  | 0 | Cement | Downtown Avenue | 31395.99 | 29280 | Not started
C002 | Shopping Complex B | T527 | Electrical Wiring | Mike Adams | Completed | Medium | 2024-03-08 | 2024-03-23 | 2024-03-23 | 100 | Concrete | Market Street | 49048.88 | 75679.37 | No issues
C002 | Shopping Complex B | T661 | Plumbing Installations | Grace Allen | In Progress | High | 2023-08-26 | 2023-09-17 |  | 26 | Concrete | Market Street | 35392.35 | 62345.84 | In progress
C001 | Residential Building A | T460 | Steel Framework Setup | Mike Adams | In Progress | High | 2023-12-26 | 2024-01-19 |  | 92 | Copper Wires | Plot 21, Riverside | 44914.29 | 49567.65 | In progress
C004 | Warehouse D | T319 | Steel Framework Setup | Carlos Rivera | Completed | Low | 2024-06-23 | 2024-07-22 | 2024-07-22 | 100 | Concrete | Industrial Park | 15591.54 | 17064.84 | No issues
C001 | Residential Building A | T201 | Concrete Pouring | John Miller | Blocked | Low | 2024-02-03 | 2024-02-15 |  | 0 | Cement | Plot 21, Riverside | 28743.38 | 29405.37 | Not started
C004 | Warehouse D | T107 | Steel Framework Setup | Grace Allen | In Progress | High | 2023-06-12 | 2023-07-07 |  | 9 | Steel Beams | Industrial Park | 43457.98 | 35928.96 | In progress
C003 | Office Tower C | T297 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-07-15 | 2024-07-22 | 2024-07-22 | 100 | Paint | Downtown Avenue | 33981.86 | 23686.91 | No issues
C004 | Warehouse D | T401 | Interior Painting | Carlos Rivera | Blocked | Medium | 2023-10-19 | 2023-10-31 |  | 0 | Roofing Sheets | Industrial Park | 17729.66 | 13628.69 | Not started
C003 | Office Tower C | T280 | Electrical Wiring | Dave Brown | In Progress | Low | 2024-07-10 | 2024-07-31 |  | 22 | Steel Beams | Downtown Avenue | 24638.28 | 26169.62 | In progress
C001 | Residential Building A | T788 | Steel Framework Setup | Dave Brown | Blocked | Low | 2023-02-26 | 2023-03-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 49739.7 | 56102.5 | Not started
C004 | Warehouse D | T658 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2024-02-27 | 2024-03-20 |  | 0 | Copper Wires | Industrial Park | 32140.43 | 35308.19 | Not started
C002 | Shopping Complex B | T133 | Steel Framework Setup | Rachel Green | Not Started | Low | 2024-09-15 | 2024-10-06 |  | 0 | Copper Wires | Market Street | 23201.72 | 0 | Not started
C003 | Office Tower C | T668 | Site Survey | Dave Brown | Not Started | High | 2023-07-14 | 2023-07-30 |  | 0 | Cement | Downtown Avenue | 39043.8 | 0 | Not started
C004 | Warehouse D | T797 | Plumbing Installations | Carlos Rivera | In Progress | High | 2023-11-03 | 2023-11-15 |  | 72 | Copper Wires | Industrial Park | 32479.82 | 36746.74 | In progress
C004 | Warehouse D | T357 | Steel Framework Setup | Emma White | Completed | Medium | 2024-01-14 | 2024-01-21 | 2024-01-21 | 100 | Paint | Industrial Park | 35644.57 | 26977.07 | No issues
C004 | Warehouse D | T397 | Foundation Excavation | Rachel Green | Blocked | Low | 2024-05-27 | 2024-06-04 |  | 0 | Cement | Industrial Park | 10701.28 | 6983.39 | Not started
C001 | Residential Building A | T829 | Plumbing Installations | Sarah Johnson | In Progress | Medium | 2024-01-11 | 2024-01-24 |  | 57 | Concrete | Plot 21, Riverside | 37392.94 | 24436.13 | In progress
C004 | Warehouse D | T527 | Electrical Wiring | Dave Brown | In Progress | High | 2023-12-03 | 2023-12-16 |  | 35 | Cement | Industrial Park | 21300.28 | 13557.5 | In progress
C004 | Warehouse D | T764 | Roofing | Mike Adams | Completed | High | 2023-12-01 | 2023-12-09 | 2023-12-09 | 100 | Cement | Industrial Park | 44915.89 | 34775.04 | No issues
C002 | Shopping Complex B | T100 | Concrete Pouring | John Miller | Not Started | High | 2024-06-19 | 2024-06-26 |  | 0 | Roofing Sheets | Market Street | 45725.79 | 0 | Not started
C004 | Warehouse D | T743 | Site Survey | Carlos Rivera | In Progress | High | 2024-09-02 | 2024-09-16 |  | 46 | PVC Pipes | Industrial Park | 36783.9 | 34684.28 | In progress
C003 | Office Tower C | T507 | Site Survey | Emma White | Not Started | High | 2024-03-18 | 2024-04-14 |  | 0 | Steel Beams | Downtown Avenue | 12162.51 | 0 | Not started
C002 | Shopping Complex B | T386 | Roofing | Rachel Green | Not Started | Low | 2023-05-20 | 2023-06-15 |  | 0 | Roofing Sheets | Market Street | 31732.19 | 0 | Not started
C001 | Residential Building A | T424 | Site Survey | Mike Adams | Completed | Medium | 2023-11-05 | 2023-11-20 | 2023-11-20 | 100 | Steel Beams | Plot 21, Riverside | 44473.73 | 52315.97 | No issues
C004 | Warehouse D | T815 | Site Survey | Mike Adams | Not Started | High | 2023-07-22 | 2023-08-20 |  | 0 | PVC Pipes | Industrial Park | 5947.27 | 0 | Not started
C003 | Office Tower C | T751 | Interior Painting | Sarah Johnson | Not Started | High | 2024-02-07 | 2024-02-19 |  | 0 | Roofing Sheets | Downtown Avenue | 23722.86 | 0 | Not started
C002 | Shopping Complex B | T584 | Roofing | Carlos Rivera | In Progress | High | 2023-04-03 | 2023-04-30 |  | 49 | Steel Beams | Market Street | 41468.71 | 66136.92 | In progress
C004 | Warehouse D | T788 | Concrete Pouring | Mike Adams | In Progress | Low | 2024-10-18 | 2024-11-14 |  | 32 | Steel Beams | Industrial Park | 26120.88 | 30232.86 | In progress
C002 | Shopping Complex B | T115 | Site Survey | Mike Adams | In Progress | Medium | 2024-04-12 | 2024-05-10 |  | 87 | PVC Pipes | Market Street | 44631.87 | 57657.5 | In progress
C001 | Residential Building A | T491 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2024-01-23 | 2024-02-03 |  | 71 | Copper Wires | Plot 21, Riverside | 26965.63 | 29422.89 | In progress
C001 | Residential Building A | T734 | Electrical Wiring | John Miller | In Progress | High | 2024-03-09 | 2024-03-25 |  | 59 | Cement | Plot 21, Riverside | 37260.43 | 25216.51 | In progress
C004 | Warehouse D | T439 | Roofing | Carlos Rivera | Not Started | Low | 2024-04-18 | 2024-05-10 |  | 0 | PVC Pipes | Industrial Park | 14092.05 | 0 | Not started
C004 | Warehouse D | T477 | Interior Painting | Dave Brown | Completed | Low | 2024-03-07 | 2024-04-03 | 2024-04-03 | 100 | Steel Beams | Industrial Park | 41688.82 | 33364.05 | No issues
C002 | Shopping Complex B | T921 | Electrical Wiring | John Miller | In Progress | High | 2024-03-24 | 2024-03-31 |  | 53 | Copper Wires | Market Street | 8372.78 | 34047.12 | In progress
C001 | Residential Building A | T898 | Site Survey | Mike Adams | Not Started | High | 2023-02-05 | 2023-03-02 |  | 0 | Rebar | Plot 21, Riverside | 25129.34 | 0 | Not started
C001 | Residential Building A | T652 | Steel Framework Setup | Emma White | In Progress | Medium | 2023-08-18 | 2023-09-16 |  | 68 | Steel Beams | Plot 21, Riverside | 44616.59 | 38630.42 | In progress
C003 | Office Tower C | T250 | Foundation Excavation | Dave Brown | Completed | Medium | 2023-03-01 | 2023-03-22 | 2023-03-22 | 100 | Roofing Sheets | Downtown Avenue | 26697.09 | 29453.98 | No issues
C003 | Office Tower C | T477 | Interior Painting | Emma White | Blocked | Medium | 2023-08-15 | 2023-09-05 |  | 0 | Concrete | Downtown Avenue | 34610.8 | 30567.28 | Not started
C001 | Residential Building A | T962 | Steel Framework Setup | Mike Adams | Not Started | High | 2024-02-05 | 2024-03-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 9577.82 | 0 | Not started
C004 | Warehouse D | T147 | Steel Framework Setup | Grace Allen | Completed | High | 2024-01-02 | 2024-01-29 | 2024-01-29 | 100 | Rebar | Industrial Park | 26334.16 | 30624.01 | No issues
C002 | Shopping Complex B | T872 | Steel Framework Setup | Sarah Johnson | Completed | High | 2023-03-08 | 2023-03-29 | 2023-03-29 | 100 | Rebar | Market Street | 38035.85 | 54675.05 | No issues
C001 | Residential Building A | T889 | Concrete Pouring | Dave Brown | Blocked | High | 2024-09-05 | 2024-09-20 |  | 0 | PVC Pipes | Plot 21, Riverside | 34044.59 | 35946.94 | Not started
C003 | Office Tower C | T142 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2023-03-07 | 2023-04-01 |  | 0 | Cement | Downtown Avenue | 24215.37 | 0 | Not started
C004 | Warehouse D | T986 | Concrete Pouring | Dave Brown | Blocked | High | 2023-02-14 | 2023-03-04 |  | 0 | Cement | Industrial Park | 37183.71 | 36624.89 | Not started
C001 | Residential Building A | T226 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-06-23 | 2024-07-05 |  | 18 | Copper Wires | Plot 21, Riverside | 47659.98 | 32553.76 | In progress
C002 | Shopping Complex B | T719 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-12-24 | 2024-01-07 | 2024-01-07 | 100 | Roofing Sheets | Market Street | 34843.67 | 67128.08 | No issues
C002 | Shopping Complex B | T426 | Foundation Excavation | Rachel Green | Not Started | Low | 2023-06-25 | 2023-07-22 |  | 0 | Roofing Sheets | Market Street | 9156.31 | 0 | Not started
C002 | Shopping Complex B | T785 | Site Survey | John Miller | Blocked | Low | 2023-01-25 | 2023-02-09 |  | 0 | Steel Beams | Market Street | 44561.29 | 54977.26 | Not started
C003 | Office Tower C | T586 | Roofing | Grace Allen | Blocked | Low | 2024-04-26 | 2024-05-13 |  | 0 | Rebar | Downtown Avenue | 17420.02 | 17860.62 | Not started
C003 | Office Tower C | T830 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2023-11-07 | 2023-12-02 |  | 0 | Copper Wires | Downtown Avenue | 17486.6 | 0 | Not started
C002 | Shopping Complex B | T299 | Electrical Wiring | John Miller | In Progress | High | 2024-06-27 | 2024-07-27 |  | 11 | Roofing Sheets | Market Street | 44453.52 | 59218.43 | In progress
C003 | Office Tower C | T676 | Site Survey | Grace Allen | In Progress | Medium | 2023-08-25 | 2023-09-17 |  | 72 | Roofing Sheets | Downtown Avenue | 44700.23 | 45612.54 | In progress
C003 | Office Tower C | T640 | Roofing | Dave Brown | Not Started | High | 2024-01-17 | 2024-02-14 |  | 0 | PVC Pipes | Downtown Avenue | 8639.91 | 0 | Not started
C002 | Shopping Complex B | T983 | Concrete Pouring | John Miller | In Progress | High | 2023-09-05 | 2023-09-19 |  | 71 | Copper Wires | Market Street | 37456.8 | 56186.41 | In progress
C002 | Shopping Complex B | T772 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2024-12-09 | 2024-12-19 |  | 0 | Paint | Market Street | 31904.43 | 53023.84 | Not started
C004 | Warehouse D | T537 | Steel Framework Setup | Sarah Johnson | Completed | High | 2024-04-21 | 2024-05-01 | 2024-05-01 | 100 | Paint | Industrial Park | 14422 | 10372.66 | No issues
C001 | Residential Building A | T929 | Site Survey | Mike Adams | Not Started | Medium | 2024-08-07 | 2024-08-19 |  | 0 | Cement | Plot 21, Riverside | 36458.11 | 0 | Not started
C004 | Warehouse D | T931 | Concrete Pouring | John Miller | In Progress | Medium | 2024-07-23 | 2024-08-16 |  | 25 | Cement | Industrial Park | 14390.61 | 11726.11 | In progress
C002 | Shopping Complex B | T513 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2023-01-22 | 2023-02-19 | 2023-02-19 | 100 | Roofing Sheets | Market Street | 32309.83 | 50407.94 | No issues
C002 | Shopping Complex B | T544 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-04-06 | 2024-04-21 | 2024-04-21 | 100 | Copper Wires | Market Street | 27497.25 | 47616.24 | No issues
C004 | Warehouse D | T777 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-04-18 | 2023-05-02 |  | 0 | Steel Beams | Industrial Park | 27438.57 | 28870.41 | In progress
C003 | Office Tower C | T806 | Plumbing Installations | Emma White | In Progress | High | 2023-11-11 | 2023-12-01 |  | 26 | Steel Beams | Downtown Avenue | 43124.39 | 34376.08 | In progress
C002 | Shopping Complex B | T544 | Interior Painting | Emma White | In Progress | High | 2023-01-08 | 2023-01-24 |  | 46 | Cement | Market Street | 39922.85 | 60481.62 | In progress
C002 | Shopping Complex B | T220 | Electrical Wiring | Dave Brown | Completed | Medium | 2023-06-24 | 2023-07-04 | 2023-07-04 | 100 | PVC Pipes | Market Street | 12423.92 | 38303.9 | No issues
C004 | Warehouse D | T333 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2024-06-19 | 2024-07-02 |  | 0 | Steel Beams | Industrial Park | 11964.99 | 14176.74 | Not started
C003 | Office Tower C | T850 | Foundation Excavation | John Miller | Blocked | High | 2023-08-09 | 2023-09-06 |  | 0 | Paint | Downtown Avenue | 17414.48 | 12192.62 | Not started
C002 | Shopping Complex B | T414 | Site Survey | John Miller | Completed | Low | 2023-09-19 | 2023-10-12 | 2023-10-12 | 100 | Concrete | Market Street | 22343.1 | 43486.35 | No issues
C003 | Office Tower C | T611 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2023-04-07 | 2023-05-04 |  | 0 | PVC Pipes | Downtown Avenue | 19958.27 | 14610.23 | Not started
C004 | Warehouse D | T681 | Interior Painting | Rachel Green | Not Started | Low | 2023-05-28 | 2023-06-16 |  | 0 | Copper Wires | Industrial Park | 48170.74 | 0 | Not started
C004 | Warehouse D | T161 | Concrete Pouring | John Miller | Not Started | Low | 2023-01-26 | 2023-02-02 |  | 0 | PVC Pipes | Industrial Park | 37360.27 | 0 | Not started
C003 | Office Tower C | T226 | Interior Painting | Carlos Rivera | In Progress | Low | 2023-12-20 | 2024-01-13 |  | 88 | Cement | Downtown Avenue | 5115.49 | 5066.02 | In progress
C003 | Office Tower C | T150 | Electrical Wiring | Sarah Johnson | In Progress | High | 2023-05-22 | 2023-06-12 |  | 63 | Roofing Sheets | Downtown Avenue | 30100.54 | 19326.68 | In progress
C001 | Residential Building A | T887 | Roofing | Dave Brown | Blocked | High | 2023-11-26 | 2023-12-24 |  | 0 | Cement | Plot 21, Riverside | 20552.93 | 13881.72 | Not started
C003 | Office Tower C | T763 | Interior Painting | Mike Adams | In Progress | Low | 2024-02-15 | 2024-03-12 |  | 42 | Steel Beams | Downtown Avenue | 43305.98 | 50665.29 | In progress
C004 | Warehouse D | T427 | Interior Painting | Dave Brown | Not Started | High | 2024-08-11 | 2024-09-06 |  | 0 | Copper Wires | Industrial Park | 24812.15 | 0 | Not started
C002 | Shopping Complex B | T680 | Site Survey | Carlos Rivera | Blocked | Medium | 2023-08-25 | 2023-09-18 |  | 0 | Roofing Sheets | Market Street | 46899.66 | 61094.84 | Not started
C004 | Warehouse D | T219 | Foundation Excavation | Rachel Green | In Progress | High | 2023-04-13 | 2023-05-07 |  | 11 | PVC Pipes | Industrial Park | 8046.27 | 8659.65 | In progress
C003 | Office Tower C | T633 | Roofing | Grace Allen | Completed | Low | 2024-12-20 | 2025-01-04 | 2025-01-04 | 100 | Copper Wires | Downtown Avenue | 17681.8 | 10875.59 | No issues
C001 | Residential Building A | T166 | Foundation Excavation | Sarah Johnson | Blocked | Low | 2023-11-24 | 2023-12-07 |  | 0 | Rebar | Plot 21, Riverside | 12006.02 | 7500.07 | Not started
C004 | Warehouse D | T194 | Site Survey | Sarah Johnson | Completed | Low | 2023-04-13 | 2023-04-22 | 2023-04-22 | 100 | Paint | Industrial Park | 31774.04 | 30336.12 | No issues
C002 | Shopping Complex B | T186 | Roofing | Mike Adams | In Progress | High | 2024-05-07 | 2024-06-02 |  | 36 | PVC Pipes | Market Street | 11136.72 | 36363.37 | In progress
C002 | Shopping Complex B | T465 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-07-07 | 2023-08-05 |  | 0 | Copper Wires | Market Street | 23480.5 | 48625.6 | Not started
C002 | Shopping Complex B | T597 | Concrete Pouring | Mike Adams | Not Started | High | 2023-11-14 | 2023-11-24 |  | 0 | Roofing Sheets | Market Street | 6192.27 | 0 | Not started
C004 | Warehouse D | T654 | Site Survey | Emma White | Not Started | Medium | 2023-06-12 | 2023-07-01 |  | 0 | Steel Beams | Industrial Park | 22607.37 | 0 | Not started
C004 | Warehouse D | T868 | Site Survey | Dave Brown | In Progress | Low | 2023-07-21 | 2023-08-19 |  | 39 | Cement | Industrial Park | 44211.71 | 46995.45 | In progress
C003 | Office Tower C | T306 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2024-06-03 | 2024-06-15 | 2024-06-15 | 100 | Paint | Downtown Avenue | 20193.64 | 17984.25 | No issues
C002 | Shopping Complex B | T170 | Steel Framework Setup | Sarah Johnson | Completed | High | 2023-10-28 | 2023-11-07 | 2023-11-07 | 100 | Rebar | Market Street | 25841.34 | 48960.12 | No issues
C002 | Shopping Complex B | T868 | Steel Framework Setup | Emma White | In Progress | Low | 2024-11-26 | 2024-12-23 |  | 62 | Copper Wires | Market Street | 41040.65 | 51019.54 | In progress
C003 | Office Tower C | T424 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2024-07-01 | 2024-07-08 |  | 41 | Roofing Sheets | Downtown Avenue | 13786.72 | 11470.01 | In progress
C002 | Shopping Complex B | T587 | Concrete Pouring | Rachel Green | Blocked | Medium | 2023-08-16 | 2023-09-06 |  | 0 | Cement | Market Street | 16780.94 | 40520.08 | Not started
C003 | Office Tower C | T124 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2024-05-07 | 2024-05-25 |  | 0 | Rebar | Downtown Avenue | 16347.23 | 0 | Not started
C003 | Office Tower C | T795 | Plumbing Installations | Emma White | Not Started | Low | 2023-04-28 | 2023-05-26 |  | 0 | Paint | Downtown Avenue | 41689.28 | 0 | Not started
C001 | Residential Building A | T137 | Concrete Pouring | John Miller | Blocked | Low | 2023-04-22 | 2023-04-30 |  | 0 | PVC Pipes | Plot 21, Riverside | 9909.92 | 7971.36 | Not started
C003 | Office Tower C | T527 | Roofing | Sarah Johnson | Completed | Low | 2023-01-13 | 2023-01-30 | 2023-01-30 | 100 | Cement | Downtown Avenue | 47941.32 | 36905.74 | No issues
C001 | Residential Building A | T745 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-01-15 | 2023-01-24 |  | 34 | Rebar | Plot 21, Riverside | 46015.8 | 47850.69 | In progress
C004 | Warehouse D | T978 | Foundation Excavation | John Miller | Blocked | Medium | 2024-12-02 | 2024-12-10 |  | 0 | Copper Wires | Industrial Park | 34554.63 | 30449.49 | Not started
C003 | Office Tower C | T920 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-09-27 | 2024-10-12 |  | 0 | PVC Pipes | Downtown Avenue | 49126.6 | 37264.52 | Not started
C002 | Shopping Complex B | T278 | Foundation Excavation | John Miller | Completed | Medium | 2023-08-01 | 2023-08-23 | 2023-08-23 | 100 | Concrete | Market Street | 23755 | 43707.86 | No issues
C002 | Shopping Complex B | T942 | Foundation Excavation | Emma White | In Progress | Low | 2024-06-23 | 2024-07-02 |  | 99 | Paint | Market Street | 41962.88 | 68374.38 | In progress
C002 | Shopping Complex B | T504 | Plumbing Installations | Dave Brown | Blocked | Medium | 2024-06-08 | 2024-07-07 |  | 0 | Steel Beams | Market Street | 40650.65 | 56194.65 | Not started
C001 | Residential Building A | T667 | Site Survey | Grace Allen | Not Started | Medium | 2023-03-08 | 2023-03-20 |  | 0 | Cement | Plot 21, Riverside | 44985.67 | 0 | Not started
C001 | Residential Building A | T937 | Roofing | Dave Brown | Not Started | Medium | 2023-02-08 | 2023-02-17 |  | 0 | Steel Beams | Plot 21, Riverside | 28910.51 | 0 | Not started
C001 | Residential Building A | T525 | Interior Painting | Dave Brown | Not Started | Low | 2024-03-10 | 2024-04-01 |  | 0 | Paint | Plot 21, Riverside | 30657.1 | 0 | Not started
C002 | Shopping Complex B | T692 | Electrical Wiring | John Miller | In Progress | High | 2023-01-04 | 2023-01-16 |  | 99 | Cement | Market Street | 31555.16 | 46986.8 | In progress
C003 | Office Tower C | T451 | Site Survey | Emma White | In Progress | High | 2023-01-01 | 2023-01-27 |  | 44 | Concrete | Downtown Avenue | 40281.55 | 41660.08 | In progress
C001 | Residential Building A | T955 | Steel Framework Setup | Carlos Rivera | Not Started | High | 2024-05-16 | 2024-05-27 |  | 0 | Steel Beams | Plot 21, Riverside | 6708.1 | 0 | Not started
C004 | Warehouse D | T397 | Concrete Pouring | Dave Brown | Completed | Low | 2023-05-08 | 2023-05-21 | 2023-05-21 | 100 | Steel Beams | Industrial Park | 22520.92 | 19955.66 | No issues
C003 | Office Tower C | T415 | Interior Painting | Carlos Rivera | Blocked | Low | 2023-12-07 | 2023-12-22 |  | 0 | Rebar | Downtown Avenue | 13503.72 | 11004.86 | Not started
C002 | Shopping Complex B | T449 | Site Survey | Dave Brown | Completed | High | 2023-11-28 | 2023-12-21 | 2023-12-21 | 100 | Roofing Sheets | Market Street | 43802.07 | 59463.86 | No issues
C004 | Warehouse D | T840 | Interior Painting | Emma White | Blocked | Low | 2023-01-10 | 2023-01-29 |  | 0 | Rebar | Industrial Park | 43107.9 | 31704.56 | Not started
C004 | Warehouse D | T786 | Roofing | Emma White | Completed | Medium | 2024-11-08 | 2024-11-16 | 2024-11-16 | 100 | Concrete | Industrial Park | 43055.01 | 42980.25 | No issues
C003 | Office Tower C | T280 | Foundation Excavation | Dave Brown | Completed | High | 2024-02-22 | 2024-03-23 | 2024-03-23 | 100 | Copper Wires | Downtown Avenue | 20111.66 | 22385.1 | No issues
C001 | Residential Building A | T215 | Steel Framework Setup | John Miller | Not Started | Low | 2023-06-22 | 2023-07-04 |  | 0 | Steel Beams | Plot 21, Riverside | 16674.33 | 0 | Not started
C003 | Office Tower C | T627 | Interior Painting | Mike Adams | In Progress | Low | 2024-07-19 | 2024-08-07 |  | 17 | PVC Pipes | Downtown Avenue | 49408.44 | 40290.95 | In progress
C001 | Residential Building A | T334 | Roofing | Emma White | Completed | Low | 2024-10-14 | 2024-11-02 | 2024-11-02 | 100 | Rebar | Plot 21, Riverside | 10993.46 | 11676.55 | No issues
C003 | Office Tower C | T809 | Interior Painting | Mike Adams | Blocked | High | 2024-04-24 | 2024-05-16 |  | 0 | PVC Pipes | Downtown Avenue | 24115.47 | 24382 | Not started
C002 | Shopping Complex B | T596 | Plumbing Installations | John Miller | In Progress | Low | 2024-11-22 | 2024-12-04 |  | 59 | Rebar | Market Street | 31542.63 | 62456.43 | In progress
C003 | Office Tower C | T505 | Roofing | Sarah Johnson | In Progress | Medium | 2023-11-22 | 2023-12-15 |  | 20 | Cement | Downtown Avenue | 30623.19 | 32386.96 | In progress
C002 | Shopping Complex B | T888 | Site Survey | Mike Adams | Not Started | Low | 2024-03-10 | 2024-03-24 |  | 0 | PVC Pipes | Market Street | 40606.24 | 0 | Not started
C003 | Office Tower C | T542 | Site Survey | Carlos Rivera | Blocked | Medium | 2023-06-12 | 2023-06-20 |  | 0 | Cement | Downtown Avenue | 44792.37 | 32444.22 | Not started
C003 | Office Tower C | T202 | Interior Painting | Sarah Johnson | Completed | High | 2023-01-18 | 2023-01-29 | 2023-01-29 | 100 | Rebar | Downtown Avenue | 49741.28 | 33029.57 | No issues
C003 | Office Tower C | T853 | Steel Framework Setup | Grace Allen | In Progress | High | 2024-08-14 | 2024-08-31 |  | 20 | Concrete | Downtown Avenue | 36841.86 | 35397.38 | In progress
C004 | Warehouse D | T136 | Plumbing Installations | John Miller | Completed | Low | 2023-12-24 | 2024-01-23 | 2024-01-23 | 100 | Cement | Industrial Park | 26443.05 | 28738.66 | No issues
C004 | Warehouse D | T241 | Roofing | Mike Adams | Not Started | High | 2023-12-04 | 2023-12-21 |  | 0 | Rebar | Industrial Park | 12464.76 | 0 | Not started
C004 | Warehouse D | T457 | Site Survey | John Miller | Not Started | Medium | 2024-04-28 | 2024-05-08 |  | 0 | Copper Wires | Industrial Park | 47018.83 | 0 | Not started
C004 | Warehouse D | T913 | Steel Framework Setup | Mike Adams | Completed | Low | 2024-08-18 | 2024-09-12 | 2024-09-12 | 100 | Concrete | Industrial Park | 29638.11 | 19216.39 | No issues
C004 | Warehouse D | T231 | Steel Framework Setup | Dave Brown | Not Started | Low | 2023-12-23 | 2024-01-11 |  | 0 | PVC Pipes | Industrial Park | 27191.6 | 0 | Not started
C004 | Warehouse D | T283 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2023-12-27 | 2024-01-15 |  | 40 | PVC Pipes | Industrial Park | 20845.65 | 22564.2 | In progress
C002 | Shopping Complex B | T638 | Site Survey | Sarah Johnson | Not Started | Low | 2024-04-23 | 2024-05-11 |  | 0 | Paint | Market Street | 37521.02 | 0 | Not started
C002 | Shopping Complex B | T652 | Concrete Pouring | Emma White | In Progress | Low | 2023-12-01 | 2023-12-13 |  | 27 | Paint | Market Street | 43972.19 | 63578.03 | In progress
C001 | Residential Building A | T229 | Site Survey | Grace Allen | Not Started | Low | 2024-02-06 | 2024-02-19 |  | 0 | Cement | Plot 21, Riverside | 34055.64 | 0 | Not started
C004 | Warehouse D | T904 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2024-04-23 | 2024-05-18 | 2024-05-18 | 100 | Copper Wires | Industrial Park | 20682.47 | 19937.44 | No issues
C001 | Residential Building A | T502 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2024-04-15 | 2024-05-05 |  | 0 | Roofing Sheets | Plot 21, Riverside | 38838.16 | 0 | Not started
C004 | Warehouse D | T807 | Roofing | Emma White | In Progress | High | 2024-07-19 | 2024-08-10 |  | 4 | Paint | Industrial Park | 42963.36 | 30198.04 | In progress
C003 | Office Tower C | T720 | Concrete Pouring | John Miller | Not Started | Low | 2024-05-11 | 2024-05-23 |  | 0 | PVC Pipes | Downtown Avenue | 35364.22 | 0 | Not started
C002 | Shopping Complex B | T499 | Plumbing Installations | Carlos Rivera | In Progress | High | 2023-11-07 | 2023-11-17 |  | 79 | PVC Pipes | Market Street | 28530.76 | 55202.8 | In progress
C003 | Office Tower C | T514 | Foundation Excavation | Carlos Rivera | Blocked | High | 2024-05-07 | 2024-06-02 |  | 0 | Concrete | Downtown Avenue | 47526.94 | 53238.74 | Not started
C002 | Shopping Complex B | T532 | Plumbing Installations | Mike Adams | Not Started | High | 2024-12-24 | 2025-01-14 |  | 0 | Concrete | Market Street | 16943.31 | 0 | Not started
C003 | Office Tower C | T615 | Plumbing Installations | Grace Allen | Completed | Low | 2023-06-15 | 2023-06-26 | 2023-06-26 | 100 | PVC Pipes | Downtown Avenue | 45003.62 | 48947.13 | No issues
C003 | Office Tower C | T837 | Plumbing Installations | Dave Brown | In Progress | High | 2024-01-08 | 2024-02-04 |  | 44 | Roofing Sheets | Downtown Avenue | 29439.9 | 34313.09 | In progress
C003 | Office Tower C | T830 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-01-08 | 2023-02-06 |  | 0 | Steel Beams | Downtown Avenue | 33381.22 | 34695.15 | Not started
C004 | Warehouse D | T851 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-07-12 | 2024-07-21 |  | 0 | Steel Beams | Industrial Park | 25214.91 | 20295.23 | Not started
C004 | Warehouse D | T798 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-10-18 | 2024-10-31 |  | 0 | Copper Wires | Industrial Park | 19875.93 | 12870.86 | Not started
C002 | Shopping Complex B | T975 | Concrete Pouring | Mike Adams | Not Started | Medium | 2024-07-01 | 2024-07-08 |  | 0 | Paint | Market Street | 29728.42 | 0 | Not started
C002 | Shopping Complex B | T253 | Foundation Excavation | Rachel Green | In Progress | High | 2023-06-24 | 2023-07-09 |  | 94 | Paint | Market Street | 16678.27 | 41389.92 | In progress
C003 | Office Tower C | T917 | Foundation Excavation | Dave Brown | In Progress | Medium | 2024-02-26 | 2024-03-21 |  | 21 | Cement | Downtown Avenue | 48271.75 | 46722.92 | In progress
C001 | Residential Building A | T824 | Interior Painting | Mike Adams | In Progress | Low | 2024-10-28 | 2024-11-04 |  | 1 | Steel Beams | Plot 21, Riverside | 48516.23 | 48810.13 | In progress
C001 | Residential Building A | T113 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2024-01-12 | 2024-02-03 |  | 0 | Paint | Plot 21, Riverside | 13812.42 | 15277.8 | Not started
C002 | Shopping Complex B | T982 | Interior Painting | John Miller | Not Started | Medium | 2024-12-28 | 2025-01-10 |  | 0 | Cement | Market Street | 34528.65 | 0 | Not started
C001 | Residential Building A | T310 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2024-06-23 | 2024-07-16 |  | 0 | Cement | Plot 21, Riverside | 41121.57 | 0 | Not started
C002 | Shopping Complex B | T523 | Roofing | Sarah Johnson | Blocked | High | 2023-06-25 | 2023-07-07 |  | 0 | PVC Pipes | Market Street | 46542.6 | 74491.16 | Not started
C002 | Shopping Complex B | T283 | Site Survey | Carlos Rivera | Not Started | High | 2023-07-25 | 2023-08-24 |  | 0 | Copper Wires | Market Street | 17042.9 | 0 | Not started
C003 | Office Tower C | T163 | Interior Painting | Mike Adams | Completed | Medium | 2023-02-09 | 2023-02-28 | 2023-02-28 | 100 | Copper Wires | Downtown Avenue | 6885.31 | 7558.98 | No issues
C003 | Office Tower C | T304 | Foundation Excavation | Sarah Johnson | Completed | Low | 2024-02-28 | 2024-03-14 | 2024-03-14 | 100 | Cement | Downtown Avenue | 13408.82 | 8798.94 | No issues
C004 | Warehouse D | T914 | Site Survey | Grace Allen | Blocked | Low | 2023-08-06 | 2023-08-16 |  | 0 | Roofing Sheets | Industrial Park | 9078.16 | 5926.08 | Not started
C001 | Residential Building A | T914 | Steel Framework Setup | Emma White | Completed | Medium | 2024-04-06 | 2024-04-22 | 2024-04-22 | 100 | Steel Beams | Plot 21, Riverside | 27190.09 | 27325.7 | No issues
C001 | Residential Building A | T798 | Site Survey | Emma White | Not Started | High | 2023-12-03 | 2023-12-24 |  | 0 | Paint | Plot 21, Riverside | 42409.83 | 0 | Not started
C001 | Residential Building A | T576 | Site Survey | Dave Brown | Blocked | Medium | 2024-01-19 | 2024-02-12 |  | 0 | Paint | Plot 21, Riverside | 40172.35 | 35775.92 | Not started
C003 | Office Tower C | T999 | Foundation Excavation | Dave Brown | Blocked | High | 2023-02-02 | 2023-02-13 |  | 0 | PVC Pipes | Downtown Avenue | 11578.45 | 12922.36 | Not started
C004 | Warehouse D | T979 | Roofing | Emma White | In Progress | High | 2024-10-23 | 2024-11-03 |  | 89 | Copper Wires | Industrial Park | 25496.48 | 16343.58 | In progress
C001 | Residential Building A | T502 | Concrete Pouring | Mike Adams | Completed | High | 2023-07-25 | 2023-08-20 | 2023-08-20 | 100 | Rebar | Plot 21, Riverside | 47708.82 | 47828.35 | No issues
C001 | Residential Building A | T707 | Roofing | Mike Adams | Blocked | Medium | 2023-08-04 | 2023-08-20 |  | 0 | PVC Pipes | Plot 21, Riverside | 11035.55 | 8204.6 | Not started
C003 | Office Tower C | T207 | Interior Painting | Grace Allen | In Progress | Low | 2023-06-12 | 2023-07-08 |  | 62 | Cement | Downtown Avenue | 8350.13 | 6736.52 | In progress
C003 | Office Tower C | T913 | Roofing | Mike Adams | Completed | Medium | 2024-04-11 | 2024-04-23 | 2024-04-23 | 100 | Roofing Sheets | Downtown Avenue | 16695.08 | 10260.87 | No issues
C004 | Warehouse D | T158 | Site Survey | Sarah Johnson | Not Started | High | 2024-01-09 | 2024-01-30 |  | 0 | Cement | Industrial Park | 40749.41 | 0 | Not started
C004 | Warehouse D | T543 | Roofing | Carlos Rivera | In Progress | Medium | 2023-02-17 | 2023-03-11 |  | 37 | Concrete | Industrial Park | 5030.78 | 4675.69 | In progress
C001 | Residential Building A | T450 | Roofing | John Miller | Not Started | Low | 2023-10-20 | 2023-11-06 |  | 0 | Rebar | Plot 21, Riverside | 17320.4 | 0 | Not started
C003 | Office Tower C | T596 | Roofing | Dave Brown | In Progress | Medium | 2023-11-14 | 2023-11-27 |  | 66 | Concrete | Downtown Avenue | 29750.87 | 29714.69 | In progress
C002 | Shopping Complex B | T634 | Electrical Wiring | Emma White | Blocked | High | 2023-03-08 | 2023-03-23 |  | 0 | Roofing Sheets | Market Street | 29068.12 | 51583.22 | Not started
C002 | Shopping Complex B | T309 | Interior Painting | Emma White | Completed | Medium | 2024-03-13 | 2024-04-10 | 2024-04-10 | 100 | Steel Beams | Market Street | 30975.44 | 57656.34 | No issues
C004 | Warehouse D | T667 | Electrical Wiring | John Miller | Not Started | Medium | 2023-08-05 | 2023-09-03 |  | 0 | Copper Wires | Industrial Park | 27976.96 | 0 | Not started
C004 | Warehouse D | T950 | Foundation Excavation | Sarah Johnson | Completed | Low | 2023-03-15 | 2023-03-29 | 2023-03-29 | 100 | Rebar | Industrial Park | 30930.96 | 23678.14 | No issues
C003 | Office Tower C | T504 | Interior Painting | Carlos Rivera | In Progress | Low | 2024-01-08 | 2024-01-17 |  | 40 | Concrete | Downtown Avenue | 36263.41 | 33267.57 | In progress
C001 | Residential Building A | T419 | Roofing | Rachel Green | In Progress | High | 2024-12-21 | 2025-01-06 |  | 77 | Rebar | Plot 21, Riverside | 11562.16 | 8856.42 | In progress
C002 | Shopping Complex B | T144 | Concrete Pouring | Emma White | Not Started | Low | 2024-05-19 | 2024-06-05 |  | 0 | Rebar | Market Street | 15427.39 | 0 | Not started
C004 | Warehouse D | T757 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-09-05 | 2024-09-19 |  | 0 | Concrete | Industrial Park | 9744.76 | 0 | Not started
C003 | Office Tower C | T940 | Foundation Excavation | Carlos Rivera | Completed | Medium | 2023-11-05 | 2023-12-01 | 2023-12-01 | 100 | Concrete | Downtown Avenue | 7362.12 | 7853.67 | No issues
C004 | Warehouse D | T817 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-05-01 | 2023-05-18 |  | 0 | PVC Pipes | Industrial Park | 30667.83 | 31082.59 | Not started
C002 | Shopping Complex B | T399 | Concrete Pouring | Emma White | Completed | High | 2023-10-03 | 2023-10-29 | 2023-10-29 | 100 | Roofing Sheets | Market Street | 41692.16 | 72566.91 | No issues
C003 | Office Tower C | T409 | Roofing | John Miller | Completed | Low | 2023-05-24 | 2023-06-18 | 2023-06-18 | 100 | Cement | Downtown Avenue | 36490.01 | 28187.49 | No issues
C002 | Shopping Complex B | T982 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2024-08-28 | 2024-09-16 |  | 22 | PVC Pipes | Market Street | 38542.07 | 50089.43 | In progress
C004 | Warehouse D | T531 | Roofing | Carlos Rivera | Completed | High | 2023-01-05 | 2023-01-19 | 2023-01-19 | 100 | Roofing Sheets | Industrial Park | 13784.99 | 14170.13 | No issues
C002 | Shopping Complex B | T326 | Roofing | Sarah Johnson | In Progress | High | 2023-05-15 | 2023-05-22 |  | 14 | Rebar | Market Street | 26596.19 | 44524.71 | In progress
C002 | Shopping Complex B | T651 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-04-07 | 2023-05-02 |  | 0 | Steel Beams | Market Street | 34125.58 | 55192.16 | Not started
C001 | Residential Building A | T988 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2024-07-23 | 2024-08-12 |  | 0 | Rebar | Plot 21, Riverside | 26674 | 27736.67 | Not started
C003 | Office Tower C | T676 | Foundation Excavation | Emma White | In Progress | Medium | 2023-04-20 | 2023-05-14 |  | 0 | Paint | Downtown Avenue | 5584.22 | 3822 | In progress
C003 | Office Tower C | T685 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2024-02-10 | 2024-03-04 |  | 0 | Paint | Downtown Avenue | 13076.11 | 0 | Not started
C002 | Shopping Complex B | T276 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2024-11-20 | 2024-12-19 |  | 0 | Cement | Market Street | 7046.14 | 33158.32 | Not started
C003 | Office Tower C | T204 | Roofing | Dave Brown | In Progress | High | 2023-05-17 | 2023-06-01 |  | 2 | Copper Wires | Downtown Avenue | 41525.65 | 31377.18 | In progress
C004 | Warehouse D | T175 | Site Survey | Dave Brown | In Progress | High | 2023-11-03 | 2023-11-14 |  | 27 | Cement | Industrial Park | 35071.91 | 38040.49 | In progress
C001 | Residential Building A | T593 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2023-08-14 | 2023-09-07 |  | 0 | PVC Pipes | Plot 21, Riverside | 23285.36 | 0 | Not started
C003 | Office Tower C | T966 | Steel Framework Setup | Mike Adams | Blocked | High | 2024-12-09 | 2025-01-06 |  | 0 | Rebar | Downtown Avenue | 19239.76 | 15132.79 | Not started
C003 | Office Tower C | T356 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-11-14 | 2024-11-26 | 2024-11-26 | 100 | Rebar | Downtown Avenue | 8099.03 | 7672.34 | No issues
C004 | Warehouse D | T264 | Roofing | John Miller | Completed | Medium | 2023-03-14 | 2023-04-08 | 2023-04-08 | 100 | PVC Pipes | Industrial Park | 16812.37 | 10876.48 | No issues
C003 | Office Tower C | T655 | Concrete Pouring | Emma White | In Progress | Low | 2024-11-16 | 2024-12-16 |  | 37 | Paint | Downtown Avenue | 13513.16 | 9538.09 | In progress
C001 | Residential Building A | T300 | Plumbing Installations | John Miller | Not Started | High | 2024-09-06 | 2024-09-29 |  | 0 | Copper Wires | Plot 21, Riverside | 12893.58 | 0 | Not started
C002 | Shopping Complex B | T243 | Interior Painting | Dave Brown | Blocked | Medium | 2023-04-22 | 2023-05-06 |  | 0 | Roofing Sheets | Market Street | 26620.82 | 54382.51 | Not started
C004 | Warehouse D | T469 | Steel Framework Setup | Emma White | Blocked | High | 2024-02-12 | 2024-02-20 |  | 0 | PVC Pipes | Industrial Park | 33046.02 | 24116.13 | Not started
C004 | Warehouse D | T317 | Foundation Excavation | Emma White | Blocked | Medium | 2023-10-09 | 2023-10-25 |  | 0 | Paint | Industrial Park | 40734.56 | 36215.43 | Not started
C004 | Warehouse D | T899 | Interior Painting | Dave Brown | Completed | Medium | 2023-07-13 | 2023-07-27 | 2023-07-27 | 100 | Cement | Industrial Park | 36566.64 | 36744.34 | No issues
C004 | Warehouse D | T568 | Electrical Wiring | Rachel Green | Blocked | Medium | 2024-01-14 | 2024-02-02 |  | 0 | Roofing Sheets | Industrial Park | 29064.43 | 31208.56 | Not started
C004 | Warehouse D | T760 | Concrete Pouring | John Miller | In Progress | Medium | 2024-08-27 | 2024-09-14 |  | 2 | Copper Wires | Industrial Park | 19276.94 | 20868.11 | In progress
C001 | Residential Building A | T476 | Interior Painting | John Miller | Not Started | High | 2024-08-23 | 2024-09-18 |  | 0 | Paint | Plot 21, Riverside | 30905.86 | 0 | Not started
C004 | Warehouse D | T142 | Concrete Pouring | John Miller | Not Started | Medium | 2024-08-28 | 2024-09-11 |  | 0 | Roofing Sheets | Industrial Park | 27823.97 | 0 | Not started
C001 | Residential Building A | T254 | Site Survey | Emma White | Completed | High | 2024-11-18 | 2024-12-05 | 2024-12-05 | 100 | Roofing Sheets | Plot 21, Riverside | 28860.56 | 33122.07 | No issues
C004 | Warehouse D | T353 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2024-04-11 | 2024-04-18 |  | 0 | Rebar | Industrial Park | 8688.61 | 0 | Not started
C004 | Warehouse D | T747 | Site Survey | Dave Brown | In Progress | Low | 2023-08-25 | 2023-09-14 |  | 48 | Cement | Industrial Park | 40208.97 | 28567.49 | In progress
C002 | Shopping Complex B | T481 | Site Survey | John Miller | Blocked | High | 2023-12-27 | 2024-01-11 |  | 0 | Steel Beams | Market Street | 47226.61 | 78050.94 | Not started
C003 | Office Tower C | T178 | Foundation Excavation | Mike Adams | Blocked | Medium | 2023-07-12 | 2023-07-20 |  | 0 | Concrete | Downtown Avenue | 13361.88 | 14865.86 | Not started
C004 | Warehouse D | T558 | Plumbing Installations | Dave Brown | In Progress | Low | 2023-01-21 | 2023-02-17 |  | 51 | Rebar | Industrial Park | 42665.58 | 50876.91 | In progress
C001 | Residential Building A | T603 | Plumbing Installations | Grace Allen | Not Started | Low | 2024-09-01 | 2024-09-17 |  | 0 | Copper Wires | Plot 21, Riverside | 44998.13 | 0 | Not started
C002 | Shopping Complex B | T246 | Interior Painting | Mike Adams | In Progress | High | 2024-12-16 | 2025-01-03 |  | 50 | Cement | Market Street | 42686.05 | 68648.77 | In progress
C001 | Residential Building A | T136 | Site Survey | Dave Brown | In Progress | High | 2024-11-16 | 2024-11-30 |  | 38 | Paint | Plot 21, Riverside | 42549.88 | 39146.12 | In progress
C002 | Shopping Complex B | T702 | Foundation Excavation | Mike Adams | Not Started | High | 2023-11-12 | 2023-12-06 |  | 0 | Rebar | Market Street | 42882.48 | 0 | Not started
C001 | Residential Building A | T503 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-06-07 | 2023-07-04 |  | 35 | Concrete | Plot 21, Riverside | 5261.52 | 4762.14 | In progress
C002 | Shopping Complex B | T438 | Steel Framework Setup | Rachel Green | Completed | Medium | 2024-04-17 | 2024-05-14 | 2024-05-14 | 100 | Cement | Market Street | 49529.42 | 65476.88 | No issues
C001 | Residential Building A | T686 | Concrete Pouring | Grace Allen | Completed | High | 2024-06-16 | 2024-06-24 | 2024-06-24 | 100 | Rebar | Plot 21, Riverside | 17897.6 | 11536.57 | No issues
C001 | Residential Building A | T526 | Steel Framework Setup | Grace Allen | Blocked | High | 2023-05-05 | 2023-05-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 17542.19 | 17783.73 | Not started
C003 | Office Tower C | T958 | Foundation Excavation | Rachel Green | Completed | High | 2023-02-27 | 2023-03-22 | 2023-03-22 | 100 | Paint | Downtown Avenue | 38693.81 | 31585.11 | No issues
C003 | Office Tower C | T949 | Site Survey | Sarah Johnson | Not Started | High | 2023-01-25 | 2023-02-17 |  | 0 | Concrete | Downtown Avenue | 49162.13 | 0 | Not started
C001 | Residential Building A | T227 | Steel Framework Setup | Emma White | Blocked | Low | 2023-02-13 | 2023-03-14 |  | 0 | PVC Pipes | Plot 21, Riverside | 42579.02 | 47228.7 | Not started
C002 | Shopping Complex B | T305 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2023-03-06 | 2023-03-31 |  | 0 | Cement | Market Street | 43880.29 | 0 | Not started
C004 | Warehouse D | T386 | Site Survey | Sarah Johnson | Not Started | High | 2024-04-12 | 2024-04-23 |  | 0 | Paint | Industrial Park | 30310.42 | 0 | Not started
C003 | Office Tower C | T883 | Electrical Wiring | Rachel Green | Blocked | Low | 2023-12-01 | 2023-12-16 |  | 0 | Steel Beams | Downtown Avenue | 34487.14 | 24018.62 | Not started
C003 | Office Tower C | T586 | Roofing | Emma White | Completed | Low | 2024-11-15 | 2024-11-30 | 2024-11-30 | 100 | Paint | Downtown Avenue | 29247.13 | 22962.28 | No issues
C002 | Shopping Complex B | T826 | Concrete Pouring | Rachel Green | Not Started | High | 2024-02-11 | 2024-03-10 |  | 0 | PVC Pipes | Market Street | 40696.93 | 0 | Not started
C002 | Shopping Complex B | T216 | Roofing | Carlos Rivera | Blocked | High | 2023-07-27 | 2023-08-15 |  | 0 | Steel Beams | Market Street | 32676.6 | 63915.83 | Not started
C003 | Office Tower C | T893 | Interior Painting | Sarah Johnson | Not Started | High | 2023-12-28 | 2024-01-22 |  | 0 | Paint | Downtown Avenue | 46860.95 | 0 | Not started
C002 | Shopping Complex B | T639 | Foundation Excavation | Emma White | Not Started | Medium | 2024-10-21 | 2024-10-31 |  | 0 | Rebar | Market Street | 39537.25 | 0 | Not started
C001 | Residential Building A | T370 | Electrical Wiring | Emma White | Not Started | High | 2023-12-21 | 2024-01-10 |  | 0 | Cement | Plot 21, Riverside | 6692.66 | 0 | Not started
C003 | Office Tower C | T248 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2024-07-08 | 2024-08-07 |  | 83 | PVC Pipes | Downtown Avenue | 39246.63 | 32886.06 | In progress
C004 | Warehouse D | T759 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-01-22 | 2024-02-21 |  | 0 | Paint | Industrial Park | 24564.57 | 21809.34 | Not started
C003 | Office Tower C | T975 | Roofing | Carlos Rivera | Not Started | High | 2024-04-03 | 2024-04-29 |  | 0 | Concrete | Downtown Avenue | 17477.49 | 0 | Not started
C001 | Residential Building A | T479 | Site Survey | Emma White | Blocked | Low | 2023-11-01 | 2023-11-25 |  | 0 | Steel Beams | Plot 21, Riverside | 47883.76 | 47811.95 | Not started
C004 | Warehouse D | T757 | Plumbing Installations | Dave Brown | In Progress | Medium | 2024-09-13 | 2024-09-26 |  | 57 | Rebar | Industrial Park | 42677.09 | 26325.94 | In progress
C001 | Residential Building A | T380 | Concrete Pouring | Sarah Johnson | Blocked | High | 2023-05-17 | 2023-06-16 |  | 0 | PVC Pipes | Plot 21, Riverside | 7604.32 | 8466.32 | Not started
C003 | Office Tower C | T980 | Foundation Excavation | Grace Allen | Not Started | High | 2023-01-12 | 2023-01-29 |  | 0 | Cement | Downtown Avenue | 44776.43 | 0 | Not started
C001 | Residential Building A | T134 | Steel Framework Setup | John Miller | Blocked | High | 2024-03-06 | 2024-03-27 |  | 0 | Steel Beams | Plot 21, Riverside | 35940.1 | 41733.47 | Not started
C001 | Residential Building A | T638 | Steel Framework Setup | Mike Adams | In Progress | High | 2023-05-27 | 2023-06-20 |  | 3 | Steel Beams | Plot 21, Riverside | 20987.77 | 21670 | In progress
C003 | Office Tower C | T571 | Electrical Wiring | Carlos Rivera | Not Started | High | 2023-01-13 | 2023-02-07 |  | 0 | Paint | Downtown Avenue | 11088.9 | 0 | Not started
C003 | Office Tower C | T658 | Concrete Pouring | Carlos Rivera | Blocked | High | 2024-02-05 | 2024-02-14 |  | 0 | Rebar | Downtown Avenue | 23512.47 | 26381.84 | Not started
C003 | Office Tower C | T898 | Plumbing Installations | John Miller | Completed | Medium | 2023-12-11 | 2024-01-07 | 2024-01-07 | 100 | Cement | Downtown Avenue | 45523.76 | 32127.9 | No issues
C001 | Residential Building A | T764 | Interior Painting | Emma White | In Progress | High | 2024-01-07 | 2024-02-04 |  | 72 | PVC Pipes | Plot 21, Riverside | 43791.53 | 52482.82 | In progress
C004 | Warehouse D | T389 | Steel Framework Setup | Rachel Green | Not Started | Medium | 2024-03-20 | 2024-04-04 |  | 0 | Rebar | Industrial Park | 45731.21 | 0 | Not started
C004 | Warehouse D | T399 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-09-16 | 2023-10-14 |  | 0 | PVC Pipes | Industrial Park | 5297.41 | 0 | Not started
C004 | Warehouse D | T928 | Roofing | Rachel Green | Completed | Medium | 2023-09-02 | 2023-09-15 | 2023-09-15 | 100 | Paint | Industrial Park | 33232.5 | 27548.76 | No issues
C004 | Warehouse D | T992 | Foundation Excavation | Emma White | Not Started | Medium | 2023-03-05 | 2023-03-28 |  | 0 | Steel Beams | Industrial Park | 35003.84 | 0 | Not started
C002 | Shopping Complex B | T446 | Electrical Wiring | Dave Brown | Blocked | Medium | 2024-10-02 | 2024-10-13 |  | 0 | Concrete | Market Street | 36362.52 | 56554.78 | Not started
C004 | Warehouse D | T180 | Electrical Wiring | Rachel Green | Completed | Low | 2024-04-08 | 2024-04-28 | 2024-04-28 | 100 | PVC Pipes | Industrial Park | 11291.03 | 7265.38 | No issues
C003 | Office Tower C | T258 | Roofing | Grace Allen | Blocked | Medium | 2023-04-23 | 2023-05-13 |  | 0 | Roofing Sheets | Downtown Avenue | 5623.6 | 4393.04 | Not started
C002 | Shopping Complex B | T257 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2023-04-06 | 2023-04-16 |  | 0 | Concrete | Market Street | 40195.73 | 0 | Not started
C002 | Shopping Complex B | T418 | Interior Painting | Emma White | Completed | High | 2023-02-04 | 2023-03-04 | 2023-03-04 | 100 | Roofing Sheets | Market Street | 27071.89 | 48763.2 | No issues
C002 | Shopping Complex B | T146 | Site Survey | John Miller | Not Started | Low | 2024-08-24 | 2024-09-02 |  | 0 | Copper Wires | Market Street | 20724.89 | 0 | Not started
C003 | Office Tower C | T976 | Interior Painting | Grace Allen | Completed | Medium | 2023-12-12 | 2023-12-26 | 2023-12-26 | 100 | PVC Pipes | Downtown Avenue | 30488.17 | 36536.47 | No issues
C001 | Residential Building A | T385 | Site Survey | Grace Allen | Not Started | High | 2023-11-03 | 2023-11-10 |  | 0 | Cement | Plot 21, Riverside | 28127.28 | 0 | Not started
C001 | Residential Building A | T362 | Electrical Wiring | John Miller | Not Started | Medium | 2023-09-24 | 2023-10-14 |  | 0 | Rebar | Plot 21, Riverside | 37226.85 | 0 | Not started
C001 | Residential Building A | T917 | Electrical Wiring | Grace Allen | Blocked | High | 2023-02-27 | 2023-03-20 |  | 0 | Steel Beams | Plot 21, Riverside | 28460.62 | 18501.7 | Not started
C001 | Residential Building A | T843 | Roofing | Rachel Green | In Progress | High | 2024-10-13 | 2024-10-26 |  | 89 | Copper Wires | Plot 21, Riverside | 17837.47 | 16140.04 | In progress
C004 | Warehouse D | T572 | Interior Painting | Grace Allen | Not Started | Medium | 2024-12-17 | 2024-12-25 |  | 0 | Cement | Industrial Park | 10417.76 | 0 | Not started
C002 | Shopping Complex B | T499 | Foundation Excavation | Carlos Rivera | Completed | High | 2023-08-06 | 2023-08-19 | 2023-08-19 | 100 | Paint | Market Street | 46218.67 | 72296.71 | No issues
C001 | Residential Building A | T385 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2024-03-02 | 2024-03-30 |  | 0 | Copper Wires | Plot 21, Riverside | 25508.27 | 29424 | Not started
C003 | Office Tower C | T394 | Electrical Wiring | Grace Allen | In Progress | Low | 2023-09-27 | 2023-10-22 |  | 67 | Rebar | Downtown Avenue | 9826.22 | 10987.08 | In progress
C002 | Shopping Complex B | T730 | Plumbing Installations | John Miller | Blocked | Medium | 2023-02-14 | 2023-02-27 |  | 0 | Cement | Market Street | 24814.57 | 40730.06 | Not started
C003 | Office Tower C | T551 | Foundation Excavation | John Miller | In Progress | Low | 2024-04-26 | 2024-05-21 |  | 97 | Steel Beams | Downtown Avenue | 17272.56 | 20550.17 | In progress
C003 | Office Tower C | T301 | Interior Painting | Dave Brown | Blocked | High | 2024-04-17 | 2024-05-01 |  | 0 | Cement | Downtown Avenue | 7330.98 | 5869.79 | Not started
C001 | Residential Building A | T340 | Electrical Wiring | Rachel Green | In Progress | Medium | 2024-10-11 | 2024-10-23 |  | 10 | Copper Wires | Plot 21, Riverside | 26463.31 | 30653.98 | In progress
C001 | Residential Building A | T120 | Roofing | Rachel Green | Completed | Low | 2023-10-19 | 2023-11-08 | 2023-11-08 | 100 | PVC Pipes | Plot 21, Riverside | 14700.57 | 13991.21 | No issues
C004 | Warehouse D | T136 | Site Survey | Carlos Rivera | Completed | Low | 2024-10-11 | 2024-11-08 | 2024-11-08 | 100 | Roofing Sheets | Industrial Park | 6172.31 | 5198.52 | No issues
C002 | Shopping Complex B | T157 | Plumbing Installations | Mike Adams | Completed | Low | 2024-06-06 | 2024-06-21 | 2024-06-21 | 100 | Paint | Market Street | 19609.69 | 39691.95 | No issues
C001 | Residential Building A | T573 | Site Survey | Dave Brown | Blocked | High | 2023-05-28 | 2023-06-04 |  | 0 | Cement | Plot 21, Riverside | 39816.78 | 29795.97 | Not started
C003 | Office Tower C | T797 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-12-14 | 2025-01-05 |  | 0 | Cement | Downtown Avenue | 8962.37 | 5731.74 | Not started
C002 | Shopping Complex B | T825 | Steel Framework Setup | Emma White | Not Started | Low | 2024-01-08 | 2024-02-02 |  | 0 | Copper Wires | Market Street | 47194.23 | 0 | Not started
C004 | Warehouse D | T976 | Site Survey | Dave Brown | Not Started | Medium | 2023-05-06 | 2023-05-14 |  | 0 | Concrete | Industrial Park | 43653.89 | 0 | Not started
C004 | Warehouse D | T913 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2024-08-25 | 2024-09-22 |  | 28 | Roofing Sheets | Industrial Park | 41791.61 | 43088.17 | In progress
C004 | Warehouse D | T806 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-09-28 | 2024-10-10 | 2024-10-10 | 100 | PVC Pipes | Industrial Park | 39540.83 | 44874.22 | No issues
C003 | Office Tower C | T973 | Plumbing Installations | Dave Brown | Blocked | Medium | 2024-03-24 | 2024-04-13 |  | 0 | Rebar | Downtown Avenue | 7018.76 | 4697.55 | Not started
C002 | Shopping Complex B | T307 | Roofing | Grace Allen | Blocked | Medium | 2024-01-18 | 2024-02-14 |  | 0 | Steel Beams | Market Street | 37690.4 | 56430.32 | Not started
C002 | Shopping Complex B | T967 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-04-04 | 2023-04-20 |  | 66 | Rebar | Market Street | 6734.09 | 31730.69 | In progress
C002 | Shopping Complex B | T902 | Steel Framework Setup | John Miller | Not Started | High | 2023-10-22 | 2023-11-13 |  | 0 | Paint | Market Street | 9006.18 | 0 | Not started
C001 | Residential Building A | T772 | Plumbing Installations | Carlos Rivera | In Progress | High | 2023-10-28 | 2023-11-23 |  | 17 | Cement | Plot 21, Riverside | 13674.97 | 15718.96 | In progress
C003 | Office Tower C | T232 | Plumbing Installations | Emma White | Not Started | High | 2024-06-02 | 2024-06-29 |  | 0 | PVC Pipes | Downtown Avenue | 37102.71 | 0 | Not started
C001 | Residential Building A | T748 | Electrical Wiring | Rachel Green | Blocked | Low | 2023-08-18 | 2023-08-29 |  | 0 | Paint | Plot 21, Riverside | 21684.43 | 21740.84 | Not started
C001 | Residential Building A | T290 | Steel Framework Setup | Emma White | Not Started | Low | 2023-09-03 | 2023-09-10 |  | 0 | Copper Wires | Plot 21, Riverside | 44618.42 | 0 | Not started
C003 | Office Tower C | T407 | Electrical Wiring | Emma White | Blocked | High | 2024-06-06 | 2024-06-16 |  | 0 | Paint | Downtown Avenue | 25599.83 | 23436.58 | Not started
C001 | Residential Building A | T656 | Roofing | Sarah Johnson | In Progress | Low | 2024-10-14 | 2024-11-05 |  | 58 | Steel Beams | Plot 21, Riverside | 49171.8 | 43956.1 | In progress
C003 | Office Tower C | T430 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-03-10 | 2024-03-19 | 2024-03-19 | 100 | PVC Pipes | Downtown Avenue | 49739.89 | 44277.24 | No issues
C002 | Shopping Complex B | T795 | Roofing | Emma White | Completed | Medium | 2023-01-18 | 2023-02-09 | 2023-02-09 | 100 | Cement | Market Street | 9598.56 | 35976.62 | No issues
C001 | Residential Building A | T456 | Site Survey | Dave Brown | In Progress | Medium | 2024-06-11 | 2024-06-21 |  | 3 | Copper Wires | Plot 21, Riverside | 14448.19 | 12529.96 | In progress
C002 | Shopping Complex B | T943 | Concrete Pouring | Grace Allen | Completed | Low | 2023-10-03 | 2023-10-21 | 2023-10-21 | 100 | PVC Pipes | Market Street | 14856.64 | 35516.54 | No issues
C001 | Residential Building A | T785 | Roofing | Dave Brown | Blocked | High | 2023-10-27 | 2023-11-13 |  | 0 | Rebar | Plot 21, Riverside | 47327.47 | 40392.51 | Not started
C004 | Warehouse D | T205 | Electrical Wiring | Rachel Green | In Progress | High | 2023-02-14 | 2023-03-09 |  | 85 | Rebar | Industrial Park | 28998.24 | 31221.79 | In progress
C002 | Shopping Complex B | T387 | Electrical Wiring | Rachel Green | In Progress | Low | 2024-11-16 | 2024-11-28 |  | 7 | Rebar | Market Street | 7454.82 | 33911.13 | In progress
C002 | Shopping Complex B | T159 | Electrical Wiring | John Miller | Completed | Low | 2023-05-13 | 2023-06-11 | 2023-06-11 | 100 | Rebar | Market Street | 13836.92 | 40889.75 | No issues
C001 | Residential Building A | T653 | Electrical Wiring | Carlos Rivera | In Progress | Medium | 2023-10-22 | 2023-11-16 |  | 4 | Steel Beams | Plot 21, Riverside | 49581.79 | 45608.47 | In progress
C001 | Residential Building A | T659 | Plumbing Installations | Grace Allen | In Progress | Medium | 2024-01-13 | 2024-01-25 |  | 81 | Paint | Plot 21, Riverside | 44129.73 | 36343.16 | In progress
C004 | Warehouse D | T518 | Electrical Wiring | Carlos Rivera | In Progress | High | 2024-07-09 | 2024-07-31 |  | 84 | Cement | Industrial Park | 13050.81 | 8975.08 | In progress
C004 | Warehouse D | T179 | Site Survey | Dave Brown | Not Started | Medium | 2023-05-17 | 2023-06-05 |  | 0 | Cement | Industrial Park | 49721.17 | 0 | Not started
C001 | Residential Building A | T580 | Roofing | Carlos Rivera | Not Started | Low | 2023-11-26 | 2023-12-17 |  | 0 | Cement | Plot 21, Riverside | 16235.66 | 0 | Not started
C002 | Shopping Complex B | T216 | Foundation Excavation | Carlos Rivera | Completed | High | 2023-05-12 | 2023-06-10 | 2023-06-10 | 100 | Roofing Sheets | Market Street | 42766.07 | 58450.45 | No issues
C003 | Office Tower C | T439 | Steel Framework Setup | John Miller | Not Started | Low | 2023-08-20 | 2023-09-01 |  | 0 | Paint | Downtown Avenue | 29220.89 | 0 | Not started
C004 | Warehouse D | T944 | Interior Painting | Sarah Johnson | In Progress | High | 2024-07-07 | 2024-07-28 |  | 81 | PVC Pipes | Industrial Park | 30948.46 | 26042.76 | In progress
C001 | Residential Building A | T655 | Steel Framework Setup | Grace Allen | Not Started | High | 2023-06-21 | 2023-07-20 |  | 0 | Paint | Plot 21, Riverside | 39156.78 | 0 | Not started
C001 | Residential Building A | T901 | Concrete Pouring | Dave Brown | Blocked | Low | 2024-12-14 | 2024-12-30 |  | 0 | Copper Wires | Plot 21, Riverside | 30808.43 | 32746.92 | Not started
C001 | Residential Building A | T781 | Site Survey | John Miller | Completed | Medium | 2023-06-02 | 2023-06-21 | 2023-06-21 | 100 | PVC Pipes | Plot 21, Riverside | 32016.55 | 31370.56 | No issues
C002 | Shopping Complex B | T539 | Concrete Pouring | Rachel Green | Blocked | High | 2024-09-14 | 2024-09-21 |  | 0 | Roofing Sheets | Market Street | 32663.33 | 45585.92 | Not started
C004 | Warehouse D | T948 | Concrete Pouring | John Miller | In Progress | Low | 2024-07-06 | 2024-07-16 |  | 34 | Rebar | Industrial Park | 41886.25 | 42473.63 | In progress
C001 | Residential Building A | T427 | Interior Painting | Mike Adams | In Progress | High | 2023-09-27 | 2023-10-27 |  | 93 | Cement | Plot 21, Riverside | 49386.87 | 33015.22 | In progress
C001 | Residential Building A | T659 | Steel Framework Setup | Emma White | Completed | High | 2023-02-02 | 2023-02-09 | 2023-02-09 | 100 | Steel Beams | Plot 21, Riverside | 32042.5 | 37127.08 | No issues
C002 | Shopping Complex B | T683 | Steel Framework Setup | Emma White | Completed | Medium | 2023-04-16 | 2023-05-04 | 2023-05-04 | 100 | Roofing Sheets | Market Street | 31627.35 | 44634.04 | No issues
C002 | Shopping Complex B | T820 | Interior Painting | Grace Allen | Blocked | Low | 2023-05-21 | 2023-06-19 |  | 0 | Copper Wires | Market Street | 17300.04 | 44399.18 | Not started
C002 | Shopping Complex B | T134 | Steel Framework Setup | Emma White | In Progress | Medium | 2024-01-26 | 2024-02-14 |  | 11 | Rebar | Market Street | 40599.75 | 65037.23 | In progress
C001 | Residential Building A | T826 | Steel Framework Setup | Dave Brown | Blocked | Low | 2024-01-23 | 2024-02-07 |  | 0 | Steel Beams | Plot 21, Riverside | 31639.27 | 23786.77 | Not started
C004 | Warehouse D | T973 | Steel Framework Setup | Emma White | In Progress | Low | 2024-02-21 | 2024-03-09 |  | 69 | Steel Beams | Industrial Park | 35567.62 | 38209.98 | In progress
C001 | Residential Building A | T692 | Plumbing Installations | Carlos Rivera | Completed | High | 2023-10-27 | 2023-11-07 | 2023-11-07 | 100 | Concrete | Plot 21, Riverside | 39351.12 | 29978.16 | No issues
C001 | Residential Building A | T712 | Interior Painting | John Miller | Completed | Low | 2024-05-04 | 2024-05-28 | 2024-05-28 | 100 | PVC Pipes | Plot 21, Riverside | 5581.34 | 5969.22 | No issues
C001 | Residential Building A | T516 | Foundation Excavation | Emma White | Completed | Medium | 2024-06-05 | 2024-06-17 | 2024-06-17 | 100 | Roofing Sheets | Plot 21, Riverside | 31349.89 | 36338.78 | No issues
C002 | Shopping Complex B | T123 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-08-27 | 2023-09-14 |  | 44 | Cement | Market Street | 38367.77 | 59736.8 | In progress
C002 | Shopping Complex B | T318 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2023-02-08 | 2023-02-21 |  | 38 | Copper Wires | Market Street | 28704.95 | 47168.1 | In progress
C002 | Shopping Complex B | T723 | Site Survey | Sarah Johnson | Not Started | Low | 2024-10-12 | 2024-11-05 |  | 0 | Roofing Sheets | Market Street | 32580.78 | 0 | Not started
C004 | Warehouse D | T140 | Plumbing Installations | John Miller | In Progress | Low | 2024-06-10 | 2024-07-02 |  | 60 | Concrete | Industrial Park | 31168.18 | 33641.41 | In progress
C001 | Residential Building A | T815 | Steel Framework Setup | Mike Adams | Completed | Low | 2024-03-07 | 2024-03-26 | 2024-03-26 | 100 | Steel Beams | Plot 21, Riverside | 21437.89 | 15205.68 | No issues
C002 | Shopping Complex B | T193 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-07-21 | 2024-08-16 |  | 0 | Cement | Market Street | 46392.72 | 75873.45 | Not started
C004 | Warehouse D | T683 | Concrete Pouring | Mike Adams | Not Started | Medium | 2023-07-05 | 2023-07-16 |  | 0 | Cement | Industrial Park | 10188.12 | 0 | Not started
C002 | Shopping Complex B | T877 | Electrical Wiring | Dave Brown | Not Started | Medium | 2023-11-08 | 2023-11-16 |  | 0 | PVC Pipes | Market Street | 10834.22 | 0 | Not started
C003 | Office Tower C | T859 | Steel Framework Setup | Emma White | Completed | Medium | 2024-09-01 | 2024-09-13 | 2024-09-13 | 100 | Roofing Sheets | Downtown Avenue | 37492.69 | 27505.73 | No issues
C004 | Warehouse D | T138 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-10-24 | 2023-11-15 |  | 82 | PVC Pipes | Industrial Park | 27135.86 | 23946.95 | In progress
C002 | Shopping Complex B | T392 | Steel Framework Setup | Grace Allen | Completed | High | 2024-06-14 | 2024-06-23 | 2024-06-23 | 100 | PVC Pipes | Market Street | 16460.84 | 41966.19 | No issues
C004 | Warehouse D | T103 | Interior Painting | John Miller | In Progress | Medium | 2024-11-14 | 2024-12-01 |  | 2 | Roofing Sheets | Industrial Park | 42977.86 | 26977.64 | In progress
C001 | Residential Building A | T624 | Electrical Wiring | Carlos Rivera | Completed | High | 2023-04-21 | 2023-05-10 | 2023-05-10 | 100 | Copper Wires | Plot 21, Riverside | 5565.58 | 6577.4 | No issues
C001 | Residential Building A | T884 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2023-12-02 | 2023-12-23 | 2023-12-23 | 100 | Paint | Plot 21, Riverside | 12693.83 | 14746.38 | No issues
C003 | Office Tower C | T403 | Concrete Pouring | Sarah Johnson | Blocked | High | 2024-02-16 | 2024-03-08 |  | 0 | Paint | Downtown Avenue | 6207.93 | 5151.33 | Not started
C002 | Shopping Complex B | T645 | Interior Painting | Rachel Green | Blocked | Medium | 2024-05-28 | 2024-06-24 |  | 0 | PVC Pipes | Market Street | 6318.32 | 32182.46 | Not started
C002 | Shopping Complex B | T806 | Concrete Pouring | Dave Brown | In Progress | Medium | 2024-10-04 | 2024-10-17 |  | 81 | PVC Pipes | Market Street | 24254.57 | 43252.27 | In progress
C003 | Office Tower C | T709 | Interior Painting | Sarah Johnson | In Progress | Low | 2024-04-24 | 2024-05-23 |  | 91 | Steel Beams | Downtown Avenue | 42091.51 | 33567.58 | In progress
C004 | Warehouse D | T514 | Foundation Excavation | Sarah Johnson | Not Started | High | 2023-01-09 | 2023-01-28 |  | 0 | Roofing Sheets | Industrial Park | 19387.52 | 0 | Not started
C003 | Office Tower C | T455 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-04-07 | 2023-05-01 | 2023-05-01 | 100 | Roofing Sheets | Downtown Avenue | 45748.28 | 34098.91 | No issues
C001 | Residential Building A | T497 | Electrical Wiring | John Miller | In Progress | Medium | 2023-12-10 | 2023-12-21 |  | 39 | Concrete | Plot 21, Riverside | 24470.07 | 19668.59 | In progress
C001 | Residential Building A | T747 | Steel Framework Setup | Dave Brown | Blocked | Low | 2024-10-01 | 2024-10-29 |  | 0 | Roofing Sheets | Plot 21, Riverside | 38664.8 | 38104.31 | Not started
C003 | Office Tower C | T144 | Interior Painting | Dave Brown | Blocked | Medium | 2024-05-09 | 2024-05-18 |  | 0 | Concrete | Downtown Avenue | 16132.21 | 10102.73 | Not started
C001 | Residential Building A | T549 | Plumbing Installations | Rachel Green | Completed | Medium | 2024-11-18 | 2024-12-05 | 2024-12-05 | 100 | Steel Beams | Plot 21, Riverside | 30263.11 | 18504.64 | No issues
C003 | Office Tower C | T568 | Foundation Excavation | Mike Adams | In Progress | Low | 2023-07-06 | 2023-07-14 |  | 7 | Cement | Downtown Avenue | 36431.2 | 24876.34 | In progress
C001 | Residential Building A | T737 | Interior Painting | Mike Adams | Not Started | High | 2023-05-19 | 2023-06-06 |  | 0 | Steel Beams | Plot 21, Riverside | 11620.33 | 0 | Not started
C002 | Shopping Complex B | T340 | Roofing | Mike Adams | In Progress | Medium | 2024-08-01 | 2024-08-23 |  | 0 | Concrete | Market Street | 10605.96 | 35829.1 | In progress
C002 | Shopping Complex B | T804 | Site Survey | Grace Allen | In Progress | Medium | 2023-11-12 | 2023-11-24 |  | 56 | PVC Pipes | Market Street | 19665.55 | 43448.18 | In progress
C002 | Shopping Complex B | T181 | Roofing | Emma White | Completed | Medium | 2023-03-27 | 2023-04-05 | 2023-04-05 | 100 | PVC Pipes | Market Street | 25868.95 | 53942.57 | No issues
C004 | Warehouse D | T869 | Electrical Wiring | Dave Brown | In Progress | Low | 2023-04-24 | 2023-05-09 |  | 34 | Cement | Industrial Park | 16187.45 | 18518.35 | In progress
C004 | Warehouse D | T924 | Plumbing Installations | Sarah Johnson | Completed | Low | 2024-08-08 | 2024-09-05 | 2024-09-05 | 100 | Copper Wires | Industrial Park | 39265.03 | 38910.59 | No issues
C004 | Warehouse D | T900 | Interior Painting | Carlos Rivera | Completed | High | 2023-10-25 | 2023-11-02 | 2023-11-02 | 100 | Copper Wires | Industrial Park | 46022.76 | 30891.41 | No issues
C002 | Shopping Complex B | T282 | Interior Painting | Grace Allen | Not Started | High | 2023-09-06 | 2023-09-13 |  | 0 | Concrete | Market Street | 24837.72 | 0 | Not started
C003 | Office Tower C | T314 | Interior Painting | Dave Brown | In Progress | Medium | 2024-02-12 | 2024-02-24 |  | 99 | Rebar | Downtown Avenue | 10026.62 | 9808.55 | In progress
C001 | Residential Building A | T722 | Plumbing Installations | Sarah Johnson | Blocked | High | 2023-11-16 | 2023-11-24 |  | 0 | Steel Beams | Plot 21, Riverside | 24751.17 | 24260.36 | Not started
C004 | Warehouse D | T578 | Site Survey | Rachel Green | In Progress | High | 2023-02-22 | 2023-03-10 |  | 52 | Steel Beams | Industrial Park | 35340.06 | 33930.84 | In progress
C003 | Office Tower C | T357 | Site Survey | Dave Brown | In Progress | Low | 2024-02-15 | 2024-03-13 |  | 26 | Roofing Sheets | Downtown Avenue | 8287.37 | 9459.87 | In progress
C001 | Residential Building A | T276 | Interior Painting | John Miller | Blocked | Medium | 2023-04-08 | 2023-04-25 |  | 0 | Rebar | Plot 21, Riverside | 40650.24 | 31917.19 | Not started
C004 | Warehouse D | T318 | Foundation Excavation | Emma White | Blocked | Medium | 2023-08-27 | 2023-09-13 |  | 0 | Paint | Industrial Park | 29386.79 | 31245.05 | Not started
C001 | Residential Building A | T186 | Foundation Excavation | John Miller | In Progress | Medium | 2023-02-17 | 2023-03-10 |  | 38 | Paint | Plot 21, Riverside | 16881.05 | 11303.73 | In progress
C004 | Warehouse D | T543 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-02-12 | 2024-03-05 |  | 0 | PVC Pipes | Industrial Park | 28391.94 | 29128.68 | Not started
C002 | Shopping Complex B | T691 | Site Survey | Sarah Johnson | Blocked | High | 2024-05-20 | 2024-06-08 |  | 0 | Cement | Market Street | 26838.43 | 52362.55 | Not started
C001 | Residential Building A | T420 | Concrete Pouring | John Miller | In Progress | High | 2023-04-24 | 2023-05-05 |  | 85 | Rebar | Plot 21, Riverside | 40491 | 46997.42 | In progress
C001 | Residential Building A | T283 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2023-11-17 | 2023-11-24 |  | 0 | Steel Beams | Plot 21, Riverside | 33859.32 | 26840.92 | Not started
C001 | Residential Building A | T466 | Roofing | Sarah Johnson | In Progress | High | 2023-01-28 | 2023-02-18 |  | 50 | Rebar | Plot 21, Riverside | 19672.59 | 16147.94 | In progress
C004 | Warehouse D | T583 | Interior Painting | Rachel Green | In Progress | Medium | 2023-09-04 | 2023-09-14 |  | 43 | Rebar | Industrial Park | 32634.68 | 22241.57 | In progress
C001 | Residential Building A | T375 | Interior Painting | Grace Allen | Not Started | Medium | 2024-06-02 | 2024-06-30 |  | 0 | Steel Beams | Plot 21, Riverside | 16009.39 | 0 | Not started
C003 | Office Tower C | T341 | Foundation Excavation | John Miller | Not Started | Medium | 2023-03-01 | 2023-03-14 |  | 0 | Paint | Downtown Avenue | 44632.09 | 0 | Not started
C002 | Shopping Complex B | T993 | Site Survey | John Miller | In Progress | Medium | 2024-08-05 | 2024-08-29 |  | 8 | Concrete | Market Street | 13012.58 | 33722.62 | In progress
C001 | Residential Building A | T205 | Plumbing Installations | Rachel Green | Blocked | Low | 2024-02-04 | 2024-03-05 |  | 0 | Rebar | Plot 21, Riverside | 28949.6 | 23106.15 | Not started
C004 | Warehouse D | T195 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-03-06 | 2024-03-21 | 2024-03-21 | 100 | Paint | Industrial Park | 31675.1 | 19550.72 | No issues
C001 | Residential Building A | T124 | Roofing | Dave Brown | Blocked | High | 2024-03-23 | 2024-04-14 |  | 0 | Roofing Sheets | Plot 21, Riverside | 45898.19 | 28832.85 | Not started
C004 | Warehouse D | T329 | Roofing | Rachel Green | In Progress | Medium | 2024-08-03 | 2024-08-25 |  | 2 | Rebar | Industrial Park | 21246.04 | 16438.47 | In progress
C002 | Shopping Complex B | T851 | Roofing | John Miller | Blocked | High | 2024-03-05 | 2024-03-25 |  | 0 | Steel Beams | Market Street | 16779.09 | 45005.44 | Not started
C003 | Office Tower C | T163 | Foundation Excavation | Mike Adams | In Progress | High | 2024-11-21 | 2024-12-07 |  | 5 | PVC Pipes | Downtown Avenue | 44389.07 | 36222.63 | In progress
C001 | Residential Building A | T136 | Concrete Pouring | Dave Brown | Not Started | High | 2024-08-14 | 2024-09-12 |  | 0 | Paint | Plot 21, Riverside | 34546.28 | 0 | Not started
C003 | Office Tower C | T251 | Roofing | Grace Allen | Completed | Low | 2023-01-17 | 2023-01-29 | 2023-01-29 | 100 | PVC Pipes | Downtown Avenue | 22240.23 | 13507.12 | No issues
C004 | Warehouse D | T982 | Site Survey | Mike Adams | In Progress | High | 2023-05-07 | 2023-05-16 |  | 79 | Roofing Sheets | Industrial Park | 32903.96 | 31266.74 | In progress
C002 | Shopping Complex B | T424 | Site Survey | Grace Allen | In Progress | Low | 2024-12-03 | 2024-12-23 |  | 25 | Cement | Market Street | 35767.78 | 53910.58 | In progress
C002 | Shopping Complex B | T588 | Site Survey | Rachel Green | In Progress | Medium | 2024-07-26 | 2024-08-12 |  | 30 | PVC Pipes | Market Street | 39178.55 | 53494.45 | In progress
C001 | Residential Building A | T891 | Plumbing Installations | Mike Adams | Completed | Low | 2023-03-23 | 2023-04-18 | 2023-04-18 | 100 | Copper Wires | Plot 21, Riverside | 38184.41 | 37706.18 | No issues
C004 | Warehouse D | T790 | Site Survey | Sarah Johnson | Blocked | Low | 2023-12-12 | 2023-12-31 |  | 0 | Paint | Industrial Park | 16373.14 | 16243.67 | Not started
C003 | Office Tower C | T150 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2024-01-13 | 2024-02-12 |  | 0 | Copper Wires | Downtown Avenue | 40894.61 | 30015.69 | Not started
C002 | Shopping Complex B | T543 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-01-23 | 2023-02-10 |  | 44 | Cement | Market Street | 14530.97 | 41277.4 | In progress
C001 | Residential Building A | T817 | Foundation Excavation | Grace Allen | Blocked | High | 2024-05-18 | 2024-06-05 |  | 0 | Roofing Sheets | Plot 21, Riverside | 20375.94 | 22165.64 | Not started
C003 | Office Tower C | T166 | Foundation Excavation | Emma White | Blocked | Low | 2024-12-18 | 2025-01-05 |  | 0 | Concrete | Downtown Avenue | 48645.11 | 46937.92 | Not started
C002 | Shopping Complex B | T740 | Roofing | Dave Brown | Not Started | Low | 2024-06-20 | 2024-07-03 |  | 0 | Copper Wires | Market Street | 34231.26 | 0 | Not started
C001 | Residential Building A | T936 | Interior Painting | John Miller | Not Started | Medium | 2024-10-14 | 2024-11-09 |  | 0 | Paint | Plot 21, Riverside | 38961.32 | 0 | Not started
C003 | Office Tower C | T210 | Concrete Pouring | Grace Allen | Completed | Low | 2023-06-24 | 2023-07-22 | 2023-07-22 | 100 | Concrete | Downtown Avenue | 18671.04 | 16916.74 | No issues
C001 | Residential Building A | T277 | Plumbing Installations | Mike Adams | Blocked | Low | 2023-05-17 | 2023-05-31 |  | 0 | Copper Wires | Plot 21, Riverside | 24404.69 | 26287.59 | Not started
C002 | Shopping Complex B | T725 | Site Survey | Sarah Johnson | Blocked | Low | 2024-12-19 | 2024-12-31 |  | 0 | Roofing Sheets | Market Street | 29658.71 | 53088.94 | Not started
C002 | Shopping Complex B | T635 | Site Survey | John Miller | Not Started | Medium | 2023-11-11 | 2023-11-20 |  | 0 | Rebar | Market Street | 49532.51 | 0 | Not started
C004 | Warehouse D | T883 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2023-05-03 | 2023-05-29 |  | 0 | Concrete | Industrial Park | 16006.2 | 0 | Not started
C004 | Warehouse D | T138 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2023-11-28 | 2023-12-11 | 2023-12-11 | 100 | Rebar | Industrial Park | 23586.12 | 25586.17 | No issues
C003 | Office Tower C | T524 | Foundation Excavation | Grace Allen | In Progress | High | 2023-01-28 | 2023-02-18 |  | 74 | Roofing Sheets | Downtown Avenue | 41023.03 | 43808.69 | In progress
C002 | Shopping Complex B | T270 | Plumbing Installations | Rachel Green | Blocked | High | 2024-08-10 | 2024-08-30 |  | 0 | Concrete | Market Street | 5217.09 | 31257.67 | Not started
C003 | Office Tower C | T424 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-03-13 | 2023-04-05 |  | 66 | Steel Beams | Downtown Avenue | 33247.34 | 32021.67 | In progress
C002 | Shopping Complex B | T985 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-10-23 | 2024-11-03 |  | 0 | Copper Wires | Market Street | 34041.98 | 0 | Not started
C003 | Office Tower C | T887 | Site Survey | Carlos Rivera | In Progress | Low | 2024-05-21 | 2024-06-01 |  | 35 | Steel Beams | Downtown Avenue | 35810.03 | 24059.28 | In progress
C001 | Residential Building A | T980 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-04-09 | 2024-05-06 |  | 0 | Steel Beams | Plot 21, Riverside | 17156.64 | 0 | Not started
C002 | Shopping Complex B | T816 | Site Survey | Sarah Johnson | Completed | High | 2023-03-18 | 2023-04-07 | 2023-04-07 | 100 | Roofing Sheets | Market Street | 45487.93 | 69108.2 | No issues
C004 | Warehouse D | T478 | Steel Framework Setup | Emma White | Completed | High | 2023-08-21 | 2023-09-09 | 2023-09-09 | 100 | Steel Beams | Industrial Park | 13199.25 | 11814.82 | No issues
C002 | Shopping Complex B | T735 | Site Survey | Grace Allen | Blocked | High | 2023-06-06 | 2023-06-25 |  | 0 | Copper Wires | Market Street | 25922.03 | 41126.3 | Not started
C004 | Warehouse D | T574 | Electrical Wiring | Emma White | In Progress | Medium | 2023-02-11 | 2023-02-21 |  | 73 | Roofing Sheets | Industrial Park | 10460 | 8301.51 | In progress
C002 | Shopping Complex B | T735 | Site Survey | Rachel Green | Completed | Low | 2023-08-03 | 2023-08-31 | 2023-08-31 | 100 | PVC Pipes | Market Street | 43558.33 | 69855.88 | No issues
C004 | Warehouse D | T821 | Steel Framework Setup | Rachel Green | Blocked | Low | 2024-03-20 | 2024-04-13 |  | 0 | Cement | Industrial Park | 46970.25 | 29605.27 | Not started
C003 | Office Tower C | T882 | Roofing | Sarah Johnson | Not Started | Medium | 2023-01-13 | 2023-02-04 |  | 0 | PVC Pipes | Downtown Avenue | 39560.72 | 0 | Not started
C002 | Shopping Complex B | T424 | Electrical Wiring | John Miller | Completed | Medium | 2024-08-27 | 2024-09-18 | 2024-09-18 | 100 | Cement | Market Street | 39818.32 | 50508.18 | No issues
C002 | Shopping Complex B | T734 | Concrete Pouring | John Miller | In Progress | High | 2023-10-22 | 2023-11-13 |  | 34 | Rebar | Market Street | 40318.99 | 63584.63 | In progress
C003 | Office Tower C | T913 | Interior Painting | John Miller | Not Started | High | 2024-04-25 | 2024-05-14 |  | 0 | Cement | Downtown Avenue | 33844.43 | 0 | Not started
C003 | Office Tower C | T609 | Plumbing Installations | Carlos Rivera | Completed | High | 2024-05-17 | 2024-05-28 | 2024-05-28 | 100 | Steel Beams | Downtown Avenue | 29679.71 | 20996.68 | No issues
C003 | Office Tower C | T475 | Electrical Wiring | John Miller | Blocked | High | 2024-09-26 | 2024-10-13 |  | 0 | Roofing Sheets | Downtown Avenue | 28178.71 | 21059.11 | Not started
C003 | Office Tower C | T204 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-03-04 | 2024-03-19 |  | 0 | Steel Beams | Downtown Avenue | 26206.08 | 29781.33 | Not started
C004 | Warehouse D | T731 | Electrical Wiring | Dave Brown | Not Started | High | 2024-08-21 | 2024-09-15 |  | 0 | Roofing Sheets | Industrial Park | 14448.47 | 0 | Not started
C002 | Shopping Complex B | T587 | Site Survey | Dave Brown | Blocked | High | 2023-03-19 | 2023-04-02 |  | 0 | Steel Beams | Market Street | 48383.64 | 80957.71 | Not started
C004 | Warehouse D | T820 | Steel Framework Setup | Emma White | In Progress | Low | 2023-02-05 | 2023-03-07 |  | 60 | Steel Beams | Industrial Park | 47787.9 | 55976.69 | In progress
C002 | Shopping Complex B | T399 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2023-03-14 | 2023-03-24 |  | 0 | Cement | Market Street | 46663.47 | 56106.63 | Not started
C002 | Shopping Complex B | T148 | Plumbing Installations | Rachel Green | Not Started | Low | 2024-05-27 | 2024-06-16 |  | 0 | Cement | Market Street | 33514.47 | 0 | Not started
C002 | Shopping Complex B | T256 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2024-09-19 | 2024-10-10 |  | 0 | PVC Pipes | Market Street | 26914.25 | 0 | Not started
C002 | Shopping Complex B | T732 | Plumbing Installations | Carlos Rivera | Blocked | High | 2024-02-26 | 2024-03-08 |  | 0 | Copper Wires | Market Street | 43206.78 | 57693.04 | Not started
C002 | Shopping Complex B | T240 | Site Survey | Grace Allen | Blocked | Low | 2023-06-07 | 2023-06-15 |  | 0 | Paint | Market Street | 18813.92 | 42784.54 | Not started
C002 | Shopping Complex B | T933 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-09-03 | 2023-09-17 |  | 29 | Roofing Sheets | Market Street | 22689.51 | 52289.58 | In progress
C003 | Office Tower C | T956 | Steel Framework Setup | Mike Adams | Not Started | High | 2023-06-15 | 2023-07-02 |  | 0 | Concrete | Downtown Avenue | 43080 | 0 | Not started
C003 | Office Tower C | T686 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2023-11-05 | 2023-12-04 |  | 0 | Cement | Downtown Avenue | 12203.15 | 11927.63 | Not started
C002 | Shopping Complex B | T683 | Concrete Pouring | Mike Adams | Completed | High | 2023-01-13 | 2023-01-26 | 2023-01-26 | 100 | Cement | Market Street | 14827.63 | 35392.44 | No issues
C001 | Residential Building A | T865 | Plumbing Installations | Emma White | Not Started | High | 2024-11-06 | 2024-11-28 |  | 0 | Cement | Plot 21, Riverside | 46330.62 | 0 | Not started
C004 | Warehouse D | T305 | Roofing | Sarah Johnson | Not Started | Medium | 2024-04-18 | 2024-05-07 |  | 0 | Copper Wires | Industrial Park | 22487.09 | 0 | Not started
C001 | Residential Building A | T428 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-01-11 | 2024-02-05 |  | 0 | Concrete | Plot 21, Riverside | 30926.68 | 0 | Not started
C004 | Warehouse D | T806 | Roofing | Emma White | Completed | Medium | 2024-12-19 | 2025-01-13 | 2025-01-13 | 100 | Concrete | Industrial Park | 11296.5 | 10407.35 | No issues
C001 | Residential Building A | T515 | Electrical Wiring | John Miller | In Progress | Medium | 2023-09-06 | 2023-09-16 |  | 38 | Paint | Plot 21, Riverside | 29477.19 | 18498.06 | In progress
C004 | Warehouse D | T120 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2024-08-05 | 2024-08-14 |  | 0 | Paint | Industrial Park | 10564.5 | 10295.45 | Not started
C001 | Residential Building A | T860 | Concrete Pouring | Mike Adams | Completed | Low | 2024-12-17 | 2025-01-05 | 2025-01-05 | 100 | PVC Pipes | Plot 21, Riverside | 35746.64 | 21752.75 | No issues
C004 | Warehouse D | T452 | Interior Painting | Mike Adams | Completed | Medium | 2024-01-23 | 2024-02-19 | 2024-02-19 | 100 | Steel Beams | Industrial Park | 23645.88 | 19576.71 | No issues
C004 | Warehouse D | T528 | Roofing | Dave Brown | In Progress | Medium | 2024-08-26 | 2024-09-04 |  | 48 | Cement | Industrial Park | 42415.37 | 28580.61 | In progress
C001 | Residential Building A | T182 | Site Survey | Rachel Green | Not Started | Medium | 2023-11-22 | 2023-12-14 |  | 0 | Roofing Sheets | Plot 21, Riverside | 8945.49 | 0 | Not started
C002 | Shopping Complex B | T403 | Roofing | Sarah Johnson | Not Started | Low | 2023-12-08 | 2023-12-20 |  | 0 | Roofing Sheets | Market Street | 29456.42 | 0 | Not started
C001 | Residential Building A | T115 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-10-28 | 2024-11-26 |  | 0 | Rebar | Plot 21, Riverside | 13058.59 | 12970.51 | Not started
C001 | Residential Building A | T642 | Roofing | Rachel Green | Not Started | High | 2023-07-23 | 2023-08-08 |  | 0 | Paint | Plot 21, Riverside | 45508.27 | 0 | Not started
C001 | Residential Building A | T125 | Foundation Excavation | Grace Allen | Blocked | High | 2024-07-26 | 2024-08-02 |  | 0 | Paint | Plot 21, Riverside | 37209.88 | 42745.51 | Not started
C001 | Residential Building A | T321 | Site Survey | Grace Allen | Completed | Medium | 2023-01-24 | 2023-02-12 | 2023-02-12 | 100 | Cement | Plot 21, Riverside | 38722.36 | 41759.65 | No issues
C003 | Office Tower C | T470 | Foundation Excavation | Emma White | Blocked | Medium | 2023-03-19 | 2023-04-11 |  | 0 | Rebar | Downtown Avenue | 10329.77 | 9094.01 | Not started
C001 | Residential Building A | T626 | Electrical Wiring | Dave Brown | In Progress | Low | 2023-11-23 | 2023-12-13 |  | 0 | Cement | Plot 21, Riverside | 10717.16 | 11805.6 | In progress
C002 | Shopping Complex B | T122 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-09-26 | 2024-10-09 |  | 0 | Concrete | Market Street | 26582.88 | 0 | Not started
C001 | Residential Building A | T388 | Interior Painting | John Miller | Not Started | Low | 2024-07-15 | 2024-08-04 |  | 0 | Concrete | Plot 21, Riverside | 43209.86 | 0 | Not started
C002 | Shopping Complex B | T863 | Foundation Excavation | John Miller | Not Started | Medium | 2023-05-14 | 2023-06-01 |  | 0 | Copper Wires | Market Street | 39651.6 | 0 | Not started
C003 | Office Tower C | T900 | Interior Painting | John Miller | Completed | Medium | 2023-07-19 | 2023-08-08 | 2023-08-08 | 100 | Cement | Downtown Avenue | 23566.8 | 14631.02 | No issues
C001 | Residential Building A | T238 | Foundation Excavation | Rachel Green | In Progress | Medium | 2023-03-07 | 2023-03-17 |  | 19 | PVC Pipes | Plot 21, Riverside | 8695.39 | 10075.79 | In progress
C004 | Warehouse D | T610 | Plumbing Installations | Grace Allen | Completed | Low | 2023-03-19 | 2023-04-14 | 2023-04-14 | 100 | Copper Wires | Industrial Park | 45835.25 | 30457.07 | No issues
C002 | Shopping Complex B | T479 | Concrete Pouring | Emma White | Not Started | Medium | 2024-11-16 | 2024-11-27 |  | 0 | Copper Wires | Market Street | 49610.31 | 0 | Not started
C001 | Residential Building A | T588 | Concrete Pouring | Dave Brown | Not Started | Low | 2024-05-04 | 2024-05-29 |  | 0 | Steel Beams | Plot 21, Riverside | 49897.2 | 0 | Not started
C002 | Shopping Complex B | T144 | Site Survey | Mike Adams | Completed | High | 2023-11-12 | 2023-11-26 | 2023-11-26 | 100 | Rebar | Market Street | 11544.56 | 37048.95 | No issues
C002 | Shopping Complex B | T574 | Electrical Wiring | Dave Brown | In Progress | High | 2023-08-15 | 2023-09-09 |  | 49 | Cement | Market Street | 33364.83 | 61559.28 | In progress
C002 | Shopping Complex B | T207 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2024-12-15 | 2024-12-22 |  | 0 | Copper Wires | Market Street | 16623.95 | 0 | Not started
C002 | Shopping Complex B | T131 | Electrical Wiring | Mike Adams | Not Started | High | 2023-08-08 | 2023-08-17 |  | 0 | Paint | Market Street | 11223.68 | 0 | Not started
C001 | Residential Building A | T959 | Site Survey | Dave Brown | In Progress | Medium | 2024-10-24 | 2024-11-22 |  | 84 | Rebar | Plot 21, Riverside | 22612.86 | 18286.58 | In progress
C001 | Residential Building A | T385 | Interior Painting | Rachel Green | In Progress | High | 2023-06-23 | 2023-07-23 |  | 88 | Paint | Plot 21, Riverside | 17348.15 | 13999.37 | In progress
C002 | Shopping Complex B | T507 | Concrete Pouring | Dave Brown | Completed | High | 2024-12-18 | 2025-01-03 | 2025-01-03 | 100 | Paint | Market Street | 38244.63 | 55766.37 | No issues
C001 | Residential Building A | T722 | Foundation Excavation | Dave Brown | Not Started | High | 2024-12-02 | 2024-12-12 |  | 0 | Steel Beams | Plot 21, Riverside | 23582.96 | 0 | Not started
C001 | Residential Building A | T517 | Site Survey | Sarah Johnson | Completed | Medium | 2023-09-07 | 2023-09-18 | 2023-09-18 | 100 | Copper Wires | Plot 21, Riverside | 16825.33 | 13301.31 | No issues
C001 | Residential Building A | T266 | Interior Painting | Carlos Rivera | Not Started | Low | 2024-08-19 | 2024-08-26 |  | 0 | PVC Pipes | Plot 21, Riverside | 11451.17 | 0 | Not started
C001 | Residential Building A | T694 | Concrete Pouring | Emma White | In Progress | Low | 2024-10-16 | 2024-11-05 |  | 59 | Rebar | Plot 21, Riverside | 24378.27 | 14879.99 | In progress
C004 | Warehouse D | T759 | Site Survey | Emma White | In Progress | Medium | 2024-03-18 | 2024-04-09 |  | 47 | Rebar | Industrial Park | 24639.14 | 21680.31 | In progress
C001 | Residential Building A | T203 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2023-04-26 | 2023-05-10 |  | 50 | PVC Pipes | Plot 21, Riverside | 37008.66 | 29461.21 | In progress
C004 | Warehouse D | T827 | Concrete Pouring | Sarah Johnson | Completed | Low | 2024-03-24 | 2024-04-21 | 2024-04-21 | 100 | Concrete | Industrial Park | 43555.81 | 42277.94 | No issues
C004 | Warehouse D | T101 | Foundation Excavation | Dave Brown | Blocked | Low | 2023-02-04 | 2023-02-16 |  | 0 | PVC Pipes | Industrial Park | 44519.57 | 39302.56 | Not started
C003 | Office Tower C | T169 | Roofing | John Miller | Completed | Medium | 2023-10-12 | 2023-10-20 | 2023-10-20 | 100 | Copper Wires | Downtown Avenue | 34975.67 | 25392.73 | No issues
C001 | Residential Building A | T591 | Plumbing Installations | John Miller | Completed | Low | 2023-06-13 | 2023-07-04 | 2023-07-04 | 100 | Paint | Plot 21, Riverside | 37071.96 | 23430.53 | No issues
C002 | Shopping Complex B | T642 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-12-04 | 2024-12-23 |  | 59 | Rebar | Market Street | 38591.04 | 65805.7 | In progress
C001 | Residential Building A | T665 | Steel Framework Setup | John Miller | Blocked | Low | 2024-07-23 | 2024-08-07 |  | 0 | Paint | Plot 21, Riverside | 34340.79 | 39820.17 | Not started
C001 | Residential Building A | T238 | Plumbing Installations | Sarah Johnson | Blocked | High | 2024-08-14 | 2024-09-04 |  | 0 | Concrete | Plot 21, Riverside | 30911.46 | 19224.27 | Not started
C002 | Shopping Complex B | T315 | Roofing | Dave Brown | Not Started | High | 2024-05-23 | 2024-06-02 |  | 0 | Rebar | Market Street | 10942.52 | 0 | Not started
C002 | Shopping Complex B | T767 | Interior Painting | Emma White | Blocked | High | 2023-11-24 | 2023-12-21 |  | 0 | Cement | Market Street | 28327.16 | 58942.8 | Not started
C004 | Warehouse D | T187 | Site Survey | Carlos Rivera | In Progress | High | 2024-06-23 | 2024-07-12 |  | 55 | Copper Wires | Industrial Park | 32400.08 | 26705.39 | In progress
C001 | Residential Building A | T310 | Electrical Wiring | Grace Allen | In Progress | High | 2024-09-04 | 2024-09-25 |  | 48 | Roofing Sheets | Plot 21, Riverside | 22800.31 | 26279.56 | In progress
C001 | Residential Building A | T414 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-05-20 | 2024-05-27 |  | 0 | Concrete | Plot 21, Riverside | 30448.81 | 24398.5 | Not started
C001 | Residential Building A | T824 | Electrical Wiring | John Miller | Completed | High | 2023-07-11 | 2023-08-08 | 2023-08-08 | 100 | PVC Pipes | Plot 21, Riverside | 43925.66 | 46860.66 | No issues
C001 | Residential Building A | T663 | Interior Painting | Mike Adams | Completed | Medium | 2023-04-08 | 2023-04-18 | 2023-04-18 | 100 | Steel Beams | Plot 21, Riverside | 41468.72 | 27316.21 | No issues
C001 | Residential Building A | T128 | Electrical Wiring | Emma White | Completed | Medium | 2023-07-04 | 2023-07-27 | 2023-07-27 | 100 | Rebar | Plot 21, Riverside | 46240.21 | 55048.95 | No issues
C001 | Residential Building A | T629 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-07-25 | 2023-08-03 |  | 0 | Concrete | Plot 21, Riverside | 18528.04 | 0 | Not started
C003 | Office Tower C | T451 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-04-15 | 2023-05-08 |  | 0 | Steel Beams | Downtown Avenue | 12610.89 | 0 | Not started
C002 | Shopping Complex B | T494 | Foundation Excavation | Emma White | Blocked | Low | 2023-08-14 | 2023-08-28 |  | 0 | Copper Wires | Market Street | 26213.71 | 48657.79 | Not started
C001 | Residential Building A | T275 | Roofing | Sarah Johnson | Blocked | High | 2023-01-11 | 2023-02-05 |  | 0 | Paint | Plot 21, Riverside | 33639.63 | 27018.86 | Not started
C003 | Office Tower C | T799 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-10-07 | 2023-10-18 |  | 58 | PVC Pipes | Downtown Avenue | 43929.7 | 26663.77 | In progress
C001 | Residential Building A | T704 | Plumbing Installations | Emma White | Blocked | Medium | 2024-10-09 | 2024-11-06 |  | 0 | PVC Pipes | Plot 21, Riverside | 20081.53 | 12170.23 | Not started
C001 | Residential Building A | T372 | Foundation Excavation | Mike Adams | In Progress | Medium | 2023-12-17 | 2024-01-09 |  | 8 | Roofing Sheets | Plot 21, Riverside | 27705.03 | 22609.72 | In progress
C004 | Warehouse D | T537 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-10-04 | 2024-10-24 |  | 0 | PVC Pipes | Industrial Park | 18991.13 | 11951.53 | Not started
C004 | Warehouse D | T393 | Site Survey | Emma White | Not Started | Low | 2023-08-02 | 2023-09-01 |  | 0 | Steel Beams | Industrial Park | 7486.53 | 0 | Not started
C003 | Office Tower C | T751 | Site Survey | Dave Brown | Not Started | High | 2023-06-24 | 2023-07-13 |  | 0 | Cement | Downtown Avenue | 24377.31 | 0 | Not started
C001 | Residential Building A | T989 | Steel Framework Setup | Grace Allen | In Progress | High | 2024-08-27 | 2024-09-21 |  | 58 | Rebar | Plot 21, Riverside | 32701.49 | 21055.95 | In progress
C002 | Shopping Complex B | T174 | Interior Painting | Dave Brown | Not Started | Low | 2023-02-26 | 2023-03-13 |  | 0 | Rebar | Market Street | 29201.07 | 0 | Not started
C003 | Office Tower C | T546 | Plumbing Installations | Emma White | Completed | Low | 2024-08-12 | 2024-09-01 | 2024-09-01 | 100 | Copper Wires | Downtown Avenue | 25955.08 | 15994.8 | No issues
C004 | Warehouse D | T822 | Interior Painting | Rachel Green | In Progress | Low | 2023-02-11 | 2023-02-22 |  | 5 | Roofing Sheets | Industrial Park | 44339.27 | 29148.4 | In progress
C001 | Residential Building A | T782 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2024-06-21 | 2024-07-17 |  | 0 | Steel Beams | Plot 21, Riverside | 39981.4 | 38630.88 | Not started
C001 | Residential Building A | T409 | Site Survey | Emma White | In Progress | High | 2023-11-02 | 2023-11-25 |  | 34 | Rebar | Plot 21, Riverside | 37672.07 | 33281.86 | In progress
C004 | Warehouse D | T246 | Interior Painting | Emma White | Not Started | Low | 2023-05-02 | 2023-05-13 |  | 0 | Roofing Sheets | Industrial Park | 15931.02 | 0 | Not started
C002 | Shopping Complex B | T823 | Plumbing Installations | Grace Allen | In Progress | High | 2024-10-15 | 2024-11-06 |  | 29 | Rebar | Market Street | 47690.21 | 79791.74 | In progress
C002 | Shopping Complex B | T633 | Plumbing Installations | Emma White | Not Started | Medium | 2024-02-03 | 2024-02-19 |  | 0 | PVC Pipes | Market Street | 24562.88 | 0 | Not started
C004 | Warehouse D | T976 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2023-04-20 | 2023-05-12 |  | 0 | Concrete | Industrial Park | 30460.17 | 0 | Not started
C003 | Office Tower C | T683 | Roofing | Rachel Green | In Progress | Medium | 2023-08-18 | 2023-09-01 |  | 21 | Rebar | Downtown Avenue | 18541.39 | 12125.6 | In progress
C002 | Shopping Complex B | T376 | Steel Framework Setup | John Miller | In Progress | High | 2023-01-28 | 2023-02-08 |  | 44 | Concrete | Market Street | 13004.2 | 33972.93 | In progress
C001 | Residential Building A | T878 | Interior Painting | John Miller | Blocked | High | 2023-05-20 | 2023-06-19 |  | 0 | Copper Wires | Plot 21, Riverside | 35639.15 | 33523.58 | Not started
C001 | Residential Building A | T237 | Concrete Pouring | Mike Adams | Completed | High | 2024-01-27 | 2024-02-24 | 2024-02-24 | 100 | Rebar | Plot 21, Riverside | 6455.46 | 6343.53 | No issues
C003 | Office Tower C | T419 | Plumbing Installations | Emma White | Blocked | Low | 2024-03-23 | 2024-04-14 |  | 0 | Copper Wires | Downtown Avenue | 42021.2 | 30196.76 | Not started
C004 | Warehouse D | T613 | Roofing | Carlos Rivera | In Progress | Medium | 2024-05-27 | 2024-06-14 |  | 29 | Rebar | Industrial Park | 37403.95 | 28588.37 | In progress
C001 | Residential Building A | T766 | Interior Painting | Dave Brown | Blocked | High | 2023-10-06 | 2023-10-17 |  | 0 | Roofing Sheets | Plot 21, Riverside | 12785.03 | 9803.83 | Not started
C004 | Warehouse D | T324 | Site Survey | Carlos Rivera | Completed | High | 2024-03-09 | 2024-03-25 | 2024-03-25 | 100 | Paint | Industrial Park | 10452.03 | 7470.15 | No issues
C002 | Shopping Complex B | T677 | Roofing | Dave Brown | Completed | Low | 2023-11-03 | 2023-11-14 | 2023-11-14 | 100 | Paint | Market Street | 29940.78 | 54564.08 | No issues
C001 | Residential Building A | T677 | Roofing | Rachel Green | Not Started | High | 2023-09-20 | 2023-10-13 |  | 0 | Paint | Plot 21, Riverside | 45247.65 | 0 | Not started
C001 | Residential Building A | T328 | Roofing | Sarah Johnson | Blocked | Low | 2024-05-18 | 2024-06-15 |  | 0 | Roofing Sheets | Plot 21, Riverside | 21620.51 | 25053.11 | Not started
C001 | Residential Building A | T283 | Electrical Wiring | Emma White | Not Started | Medium | 2023-10-24 | 2023-11-14 |  | 0 | Rebar | Plot 21, Riverside | 24188.93 | 0 | Not started
C002 | Shopping Complex B | T320 | Roofing | Carlos Rivera | Completed | Medium | 2023-03-02 | 2023-03-27 | 2023-03-27 | 100 | Paint | Market Street | 17612.79 | 37091.97 | No issues
C001 | Residential Building A | T729 | Interior Painting | Mike Adams | Not Started | High | 2024-06-06 | 2024-06-22 |  | 0 | Copper Wires | Plot 21, Riverside | 46506.41 | 0 | Not started
C004 | Warehouse D | T413 | Site Survey | Emma White | In Progress | Medium | 2024-07-19 | 2024-08-02 |  | 40 | Concrete | Industrial Park | 46618.82 | 41700.33 | In progress
C002 | Shopping Complex B | T931 | Roofing | Carlos Rivera | Blocked | Medium | 2024-03-21 | 2024-04-07 |  | 0 | Roofing Sheets | Market Street | 33337.18 | 56306.32 | Not started
C002 | Shopping Complex B | T613 | Interior Painting | Grace Allen | In Progress | Low | 2024-05-23 | 2024-06-02 |  | 75 | Steel Beams | Market Street | 10563.55 | 32418.78 | In progress
C003 | Office Tower C | T918 | Foundation Excavation | Rachel Green | Blocked | High | 2023-10-07 | 2023-10-19 |  | 0 | Roofing Sheets | Downtown Avenue | 11615.31 | 11009.97 | Not started
C001 | Residential Building A | T860 | Electrical Wiring | Dave Brown | Not Started | Medium | 2024-02-15 | 2024-02-22 |  | 0 | Rebar | Plot 21, Riverside | 19380.91 | 0 | Not started
C003 | Office Tower C | T632 | Site Survey | Emma White | In Progress | Medium | 2024-10-13 | 2024-11-09 |  | 2 | Cement | Downtown Avenue | 5023.64 | 3609.59 | In progress
C001 | Residential Building A | T885 | Roofing | Mike Adams | Blocked | Low | 2024-07-02 | 2024-07-29 |  | 0 | Cement | Plot 21, Riverside | 5022.27 | 3439.03 | Not started
C001 | Residential Building A | T384 | Electrical Wiring | Grace Allen | Not Started | High | 2024-10-14 | 2024-11-07 |  | 0 | Cement | Plot 21, Riverside | 25043.48 | 0 | Not started
C004 | Warehouse D | T909 | Interior Painting | Carlos Rivera | In Progress | Low | 2023-07-10 | 2023-07-31 |  | 79 | Concrete | Industrial Park | 44858.14 | 49781.19 | In progress
C003 | Office Tower C | T747 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2023-12-18 | 2024-01-12 | 2024-01-12 | 100 | Concrete | Downtown Avenue | 35400.49 | 40140.66 | No issues
C002 | Shopping Complex B | T781 | Interior Painting | Rachel Green | Blocked | Low | 2023-08-24 | 2023-08-31 |  | 0 | PVC Pipes | Market Street | 5531.75 | 28945.83 | Not started
C001 | Residential Building A | T838 | Steel Framework Setup | Mike Adams | In Progress | High | 2023-02-05 | 2023-02-19 |  | 73 | PVC Pipes | Plot 21, Riverside | 18634.14 | 21183.03 | In progress
C003 | Office Tower C | T535 | Foundation Excavation | Sarah Johnson | Completed | Low | 2024-12-04 | 2024-12-17 | 2024-12-17 | 100 | Paint | Downtown Avenue | 39742.49 | 39882.11 | No issues
C003 | Office Tower C | T490 | Foundation Excavation | Emma White | Not Started | Low | 2023-02-07 | 2023-02-19 |  | 0 | Paint | Downtown Avenue | 20448.11 | 0 | Not started
C002 | Shopping Complex B | T900 | Roofing | Rachel Green | Blocked | High | 2024-02-15 | 2024-03-02 |  | 0 | Rebar | Market Street | 37549.3 | 51749.68 | Not started
C002 | Shopping Complex B | T109 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-09-14 | 2023-09-27 |  | 0 | Rebar | Market Street | 33840.82 | 62330.72 | Not started
C003 | Office Tower C | T520 | Plumbing Installations | Grace Allen | Blocked | High | 2023-07-13 | 2023-08-02 |  | 0 | Cement | Downtown Avenue | 13702.63 | 15933.44 | Not started
C003 | Office Tower C | T489 | Foundation Excavation | Rachel Green | Blocked | Low | 2023-09-04 | 2023-09-24 |  | 0 | PVC Pipes | Downtown Avenue | 26783.45 | 19436.08 | Not started
C002 | Shopping Complex B | T668 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2024-06-12 | 2024-07-12 | 2024-07-12 | 100 | Steel Beams | Market Street | 18822.42 | 45694.4 | No issues
C003 | Office Tower C | T704 | Roofing | Rachel Green | Completed | High | 2023-11-12 | 2023-11-26 | 2023-11-26 | 100 | Cement | Downtown Avenue | 40284.59 | 38720.45 | No issues
C001 | Residential Building A | T445 | Roofing | Dave Brown | Blocked | High | 2023-06-05 | 2023-06-27 |  | 0 | Steel Beams | Plot 21, Riverside | 32683.23 | 33117.09 | Not started
C002 | Shopping Complex B | T330 | Interior Painting | Mike Adams | Completed | Low | 2024-05-15 | 2024-06-08 | 2024-06-08 | 100 | PVC Pipes | Market Street | 11499.57 | 38217.65 | No issues
C003 | Office Tower C | T452 | Steel Framework Setup | Emma White | Blocked | High | 2024-04-28 | 2024-05-07 |  | 0 | Rebar | Downtown Avenue | 22250.46 | 24635.14 | Not started
C002 | Shopping Complex B | T126 | Site Survey | Dave Brown | Completed | High | 2023-11-13 | 2023-12-08 | 2023-12-08 | 100 | Rebar | Market Street | 27546.18 | 42812.96 | No issues
C002 | Shopping Complex B | T163 | Electrical Wiring | Grace Allen | Completed | Low | 2024-01-21 | 2024-02-02 | 2024-02-02 | 100 | Copper Wires | Market Street | 44922.08 | 62112.03 | No issues
C002 | Shopping Complex B | T777 | Electrical Wiring | Grace Allen | In Progress | Low | 2023-05-09 | 2023-06-02 |  | 17 | Copper Wires | Market Street | 43987.33 | 74216.55 | In progress
C002 | Shopping Complex B | T766 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2023-08-18 | 2023-09-17 |  | 0 | Roofing Sheets | Market Street | 33406.77 | 0 | Not started
C002 | Shopping Complex B | T650 | Roofing | Sarah Johnson | Completed | High | 2023-10-27 | 2023-11-13 | 2023-11-13 | 100 | Roofing Sheets | Market Street | 32849.96 | 60579.05 | No issues
C001 | Residential Building A | T354 | Site Survey | Mike Adams | In Progress | High | 2023-02-10 | 2023-02-24 |  | 58 | Roofing Sheets | Plot 21, Riverside | 46354.41 | 32265.54 | In progress
C001 | Residential Building A | T813 | Foundation Excavation | Grace Allen | Completed | Low | 2024-04-10 | 2024-05-08 | 2024-05-08 | 100 | Cement | Plot 21, Riverside | 37786.1 | 39647.29 | No issues
C004 | Warehouse D | T222 | Interior Painting | Mike Adams | Blocked | High | 2024-04-05 | 2024-04-24 |  | 0 | Rebar | Industrial Park | 42335.62 | 48237.71 | Not started
C001 | Residential Building A | T614 | Concrete Pouring | Rachel Green | Not Started | Low | 2024-06-25 | 2024-07-09 |  | 0 | Copper Wires | Plot 21, Riverside | 42039.92 | 0 | Not started
C004 | Warehouse D | T705 | Foundation Excavation | Emma White | Not Started | Medium | 2024-11-27 | 2024-12-19 |  | 0 | Paint | Industrial Park | 8484.2 | 0 | Not started
C001 | Residential Building A | T846 | Site Survey | Grace Allen | Completed | Medium | 2023-09-16 | 2023-09-29 | 2023-09-29 | 100 | PVC Pipes | Plot 21, Riverside | 21986.81 | 14269.94 | No issues
C001 | Residential Building A | T530 | Plumbing Installations | Emma White | Completed | Medium | 2024-07-11 | 2024-08-09 | 2024-08-09 | 100 | PVC Pipes | Plot 21, Riverside | 9535.51 | 8918.87 | No issues
C004 | Warehouse D | T420 | Roofing | Mike Adams | Completed | Medium | 2024-09-15 | 2024-10-03 | 2024-10-03 | 100 | Rebar | Industrial Park | 9895.71 | 6476.36 | No issues
C004 | Warehouse D | T646 | Roofing | Dave Brown | Not Started | High | 2023-11-14 | 2023-12-05 |  | 0 | Steel Beams | Industrial Park | 42280.72 | 0 | Not started
C002 | Shopping Complex B | T474 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-07-04 | 2024-08-01 |  | 0 | PVC Pipes | Market Street | 19202.53 | 45586.06 | Not started
C002 | Shopping Complex B | T416 | Roofing | Grace Allen | Blocked | High | 2024-04-27 | 2024-05-09 |  | 0 | PVC Pipes | Market Street | 27241.06 | 49008.9 | Not started
C001 | Residential Building A | T444 | Roofing | Sarah Johnson | Not Started | High | 2024-05-15 | 2024-05-22 |  | 0 | Roofing Sheets | Plot 21, Riverside | 21856.61 | 0 | Not started
C003 | Office Tower C | T397 | Plumbing Installations | Carlos Rivera | Blocked | High | 2024-11-05 | 2024-12-02 |  | 0 | Concrete | Downtown Avenue | 38539.22 | 45859.8 | Not started
C003 | Office Tower C | T421 | Roofing | Rachel Green | Blocked | High | 2024-09-16 | 2024-09-24 |  | 0 | Steel Beams | Downtown Avenue | 33274.94 | 29028.54 | Not started
C004 | Warehouse D | T468 | Plumbing Installations | Carlos Rivera | Completed | High | 2024-02-25 | 2024-03-17 | 2024-03-17 | 100 | Cement | Industrial Park | 37598.56 | 31650.17 | No issues
C004 | Warehouse D | T428 | Electrical Wiring | Sarah Johnson | Not Started | High | 2024-09-21 | 2024-09-29 |  | 0 | Roofing Sheets | Industrial Park | 14009.32 | 0 | Not started
C001 | Residential Building A | T214 | Steel Framework Setup | Dave Brown | Completed | Medium | 2024-10-01 | 2024-10-24 | 2024-10-24 | 100 | PVC Pipes | Plot 21, Riverside | 10780.87 | 8029.12 | No issues
C004 | Warehouse D | T657 | Interior Painting | Mike Adams | Blocked | Low | 2023-08-05 | 2023-08-12 |  | 0 | Rebar | Industrial Park | 24788.24 | 19504.87 | Not started
C001 | Residential Building A | T956 | Steel Framework Setup | Emma White | Completed | Medium | 2024-01-16 | 2024-02-05 | 2024-02-05 | 100 | Copper Wires | Plot 21, Riverside | 29067.85 | 24173.01 | No issues
C001 | Residential Building A | T936 | Concrete Pouring | Dave Brown | Completed | High | 2023-07-27 | 2023-08-21 | 2023-08-21 | 100 | Copper Wires | Plot 21, Riverside | 20266.18 | 20600.37 | No issues
C004 | Warehouse D | T224 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2023-03-19 | 2023-04-10 |  | 0 | Copper Wires | Industrial Park | 16435.87 | 14465.77 | Not started
C004 | Warehouse D | T884 | Steel Framework Setup | Dave Brown | In Progress | Low | 2023-09-01 | 2023-09-14 |  | 76 | Roofing Sheets | Industrial Park | 47391.09 | 34904.53 | In progress
C003 | Office Tower C | T344 | Electrical Wiring | Emma White | In Progress | Medium | 2024-07-19 | 2024-08-04 |  | 68 | Roofing Sheets | Downtown Avenue | 28306.04 | 30192.06 | In progress
C002 | Shopping Complex B | T366 | Interior Painting | John Miller | Not Started | Low | 2023-02-11 | 2023-03-06 |  | 0 | Rebar | Market Street | 48229.03 | 0 | Not started
C002 | Shopping Complex B | T128 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2024-02-17 | 2024-03-17 |  | 0 | Copper Wires | Market Street | 46031.58 | 0 | Not started
C004 | Warehouse D | T994 | Site Survey | Carlos Rivera | Blocked | High | 2023-03-01 | 2023-03-31 |  | 0 | Cement | Industrial Park | 24182.04 | 19647.13 | Not started
C003 | Office Tower C | T372 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2024-10-14 | 2024-10-21 | 2024-10-21 | 100 | Rebar | Downtown Avenue | 11727.36 | 11923.26 | No issues
C004 | Warehouse D | T685 | Site Survey | Rachel Green | Blocked | Medium | 2024-05-09 | 2024-06-03 |  | 0 | Copper Wires | Industrial Park | 6040.8 | 6485.91 | Not started
C003 | Office Tower C | T587 | Concrete Pouring | Dave Brown | Not Started | Low | 2024-08-23 | 2024-09-13 |  | 0 | Copper Wires | Downtown Avenue | 33672.35 | 0 | Not started
C004 | Warehouse D | T671 | Electrical Wiring | Rachel Green | Blocked | High | 2024-12-22 | 2025-01-13 |  | 0 | Roofing Sheets | Industrial Park | 36067.09 | 31779.77 | Not started
C003 | Office Tower C | T111 | Plumbing Installations | Rachel Green | In Progress | Medium | 2024-02-09 | 2024-02-27 |  | 47 | Cement | Downtown Avenue | 49000.69 | 49580.28 | In progress
C004 | Warehouse D | T246 | Electrical Wiring | Emma White | In Progress | Medium | 2024-04-16 | 2024-05-16 |  | 72 | Steel Beams | Industrial Park | 23523.51 | 18791.61 | In progress
C004 | Warehouse D | T921 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2024-03-22 | 2024-04-02 | 2024-04-02 | 100 | Copper Wires | Industrial Park | 35404.62 | 26009.85 | No issues
C003 | Office Tower C | T249 | Concrete Pouring | Rachel Green | Completed | Medium | 2024-08-27 | 2024-09-14 | 2024-09-14 | 100 | Concrete | Downtown Avenue | 35237.34 | 35059.06 | No issues
C004 | Warehouse D | T254 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-08-04 | 2024-08-12 |  | 22 | Rebar | Industrial Park | 43462.46 | 30691.37 | In progress
C001 | Residential Building A | T208 | Interior Painting | Carlos Rivera | Not Started | Medium | 2023-06-28 | 2023-07-26 |  | 0 | Rebar | Plot 21, Riverside | 5651.99 | 0 | Not started
C002 | Shopping Complex B | T768 | Concrete Pouring | Dave Brown | In Progress | Medium | 2024-07-13 | 2024-07-31 |  | 14 | Copper Wires | Market Street | 32622.78 | 60972.87 | In progress
C003 | Office Tower C | T755 | Site Survey | Carlos Rivera | In Progress | Medium | 2023-04-22 | 2023-05-09 |  | 39 | Copper Wires | Downtown Avenue | 10083.38 | 9635.75 | In progress
C004 | Warehouse D | T454 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2024-09-04 | 2024-09-28 |  | 0 | Copper Wires | Industrial Park | 19540.88 | 19512.72 | Not started
C001 | Residential Building A | T665 | Plumbing Installations | Emma White | In Progress | Medium | 2024-10-07 | 2024-11-06 |  | 29 | Concrete | Plot 21, Riverside | 20027.41 | 12127.05 | In progress
C001 | Residential Building A | T334 | Steel Framework Setup | Dave Brown | Not Started | Medium | 2024-02-12 | 2024-03-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 32657.88 | 0 | Not started
C003 | Office Tower C | T675 | Roofing | John Miller | Blocked | Medium | 2023-08-16 | 2023-09-14 |  | 0 | Roofing Sheets | Downtown Avenue | 42602.61 | 47549.74 | Not started
C004 | Warehouse D | T726 | Plumbing Installations | Grace Allen | Blocked | High | 2024-06-13 | 2024-06-24 |  | 0 | Rebar | Industrial Park | 15126.24 | 14708.86 | Not started
C002 | Shopping Complex B | T999 | Foundation Excavation | Rachel Green | Completed | High | 2024-12-02 | 2024-12-31 | 2024-12-31 | 100 | Cement | Market Street | 30895.73 | 61835.54 | No issues
C002 | Shopping Complex B | T298 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2023-02-18 | 2023-03-10 |  | 73 | Concrete | Market Street | 26370.44 | 54214.92 | In progress
C002 | Shopping Complex B | T949 | Roofing | Carlos Rivera | Blocked | Medium | 2023-08-06 | 2023-08-13 |  | 0 | Concrete | Market Street | 7957.31 | 32191.18 | Not started
C003 | Office Tower C | T728 | Roofing | Grace Allen | Completed | Low | 2023-02-07 | 2023-03-05 | 2023-03-05 | 100 | Steel Beams | Downtown Avenue | 16195.92 | 13411.47 | No issues
C004 | Warehouse D | T255 | Interior Painting | Sarah Johnson | Completed | Medium | 2023-03-11 | 2023-04-09 | 2023-04-09 | 100 | Cement | Industrial Park | 15215.27 | 12398.45 | No issues
C002 | Shopping Complex B | T901 | Plumbing Installations | Dave Brown | In Progress | Medium | 2023-02-06 | 2023-02-20 |  | 74 | Concrete | Market Street | 30505.4 | 51422.33 | In progress
C004 | Warehouse D | T806 | Site Survey | John Miller | Completed | Medium | 2024-12-17 | 2024-12-31 | 2024-12-31 | 100 | Steel Beams | Industrial Park | 24244.84 | 18561.53 | No issues
C002 | Shopping Complex B | T630 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2024-07-22 | 2024-08-01 |  | 0 | Cement | Market Street | 45820.75 | 0 | Not started
C002 | Shopping Complex B | T957 | Foundation Excavation | Dave Brown | Completed | High | 2023-08-23 | 2023-09-17 | 2023-09-17 | 100 | Roofing Sheets | Market Street | 13155.44 | 36444.63 | No issues
C004 | Warehouse D | T275 | Foundation Excavation | Rachel Green | Completed | High | 2023-11-08 | 2023-11-20 | 2023-11-20 | 100 | Rebar | Industrial Park | 17951.14 | 17243.8 | No issues
C001 | Residential Building A | T833 | Site Survey | Dave Brown | Completed | High | 2023-01-08 | 2023-01-24 | 2023-01-24 | 100 | Cement | Plot 21, Riverside | 22383.3 | 21036.65 | No issues
C003 | Office Tower C | T121 | Foundation Excavation | Grace Allen | Not Started | Low | 2023-11-03 | 2023-11-27 |  | 0 | PVC Pipes | Downtown Avenue | 33021.02 | 0 | Not started
C004 | Warehouse D | T838 | Plumbing Installations | Dave Brown | In Progress | Medium | 2024-05-14 | 2024-06-10 |  | 32 | Rebar | Industrial Park | 19321.31 | 13927.28 | In progress
C002 | Shopping Complex B | T599 | Concrete Pouring | Grace Allen | Not Started | Medium | 2024-04-19 | 2024-04-30 |  | 0 | Roofing Sheets | Market Street | 5140.01 | 0 | Not started
C002 | Shopping Complex B | T399 | Interior Painting | Grace Allen | Blocked | Medium | 2024-10-22 | 2024-11-06 |  | 0 | Steel Beams | Market Street | 17758.5 | 37152.83 | Not started
C004 | Warehouse D | T238 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2023-05-25 | 2023-06-11 |  | 41 | Cement | Industrial Park | 36677.91 | 39577.26 | In progress
C002 | Shopping Complex B | T865 | Foundation Excavation | Emma White | Not Started | High | 2023-04-15 | 2023-04-26 |  | 0 | Copper Wires | Market Street | 13603.45 | 0 | Not started
C003 | Office Tower C | T951 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-06-11 | 2024-06-27 |  | 36 | Paint | Downtown Avenue | 45867.98 | 48227.92 | In progress
C004 | Warehouse D | T122 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2024-03-22 | 2024-04-18 |  | 0 | Paint | Industrial Park | 22079.83 | 16644.38 | Not started
C001 | Residential Building A | T234 | Site Survey | Emma White | In Progress | Medium | 2023-12-05 | 2023-12-12 |  | 10 | Steel Beams | Plot 21, Riverside | 45044.28 | 46962.15 | In progress
C002 | Shopping Complex B | T898 | Plumbing Installations | John Miller | In Progress | High | 2024-04-18 | 2024-05-18 |  | 53 | Paint | Market Street | 14316.18 | 37341.61 | In progress
C001 | Residential Building A | T280 | Interior Painting | Rachel Green | Completed | Medium | 2024-05-24 | 2024-06-19 | 2024-06-19 | 100 | Paint | Plot 21, Riverside | 31876.65 | 38104.27 | No issues
C001 | Residential Building A | T445 | Concrete Pouring | Carlos Rivera | Completed | High | 2024-05-27 | 2024-06-10 | 2024-06-10 | 100 | Roofing Sheets | Plot 21, Riverside | 9334.39 | 9027.75 | No issues
C003 | Office Tower C | T661 | Site Survey | Sarah Johnson | In Progress | Medium | 2024-11-13 | 2024-12-13 |  | 48 | Copper Wires | Downtown Avenue | 32323.99 | 31221.68 | In progress
C004 | Warehouse D | T329 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-07-27 | 2024-08-18 |  | 0 | Roofing Sheets | Industrial Park | 10405.16 | 0 | Not started
C004 | Warehouse D | T245 | Foundation Excavation | John Miller | Completed | High | 2024-04-26 | 2024-05-23 | 2024-05-23 | 100 | PVC Pipes | Industrial Park | 8527.11 | 7485.81 | No issues
C001 | Residential Building A | T484 | Concrete Pouring | Rachel Green | In Progress | High | 2024-12-26 | 2025-01-12 |  | 40 | Steel Beams | Plot 21, Riverside | 7723.08 | 8051.62 | In progress
C004 | Warehouse D | T254 | Concrete Pouring | Dave Brown | Not Started | High | 2024-03-19 | 2024-04-17 |  | 0 | Copper Wires | Industrial Park | 41281.33 | 0 | Not started
C001 | Residential Building A | T368 | Plumbing Installations | Mike Adams | Completed | Low | 2024-03-18 | 2024-04-06 | 2024-04-06 | 100 | Paint | Plot 21, Riverside | 8396.16 | 7140.28 | No issues
C001 | Residential Building A | T209 | Plumbing Installations | Sarah Johnson | Not Started | High | 2024-12-14 | 2025-01-12 |  | 0 | Steel Beams | Plot 21, Riverside | 14115.94 | 0 | Not started
C001 | Residential Building A | T749 | Concrete Pouring | Rachel Green | In Progress | Low | 2024-03-12 | 2024-03-22 |  | 85 | Concrete | Plot 21, Riverside | 22321.38 | 21325.59 | In progress
C004 | Warehouse D | T139 | Roofing | John Miller | Not Started | High | 2023-07-12 | 2023-08-10 |  | 0 | Steel Beams | Industrial Park | 40906.31 | 0 | Not started
C002 | Shopping Complex B | T613 | Roofing | Dave Brown | Blocked | Low | 2024-04-10 | 2024-04-18 |  | 0 | Copper Wires | Market Street | 38320.85 | 50962.04 | Not started
C003 | Office Tower C | T850 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2023-03-02 | 2023-03-22 |  | 0 | Paint | Downtown Avenue | 13643.15 | 12929.79 | Not started
C001 | Residential Building A | T125 | Interior Painting | John Miller | Not Started | High | 2024-11-17 | 2024-12-07 |  | 0 | Steel Beams | Plot 21, Riverside | 43481.7 | 0 | Not started
C003 | Office Tower C | T756 | Electrical Wiring | Emma White | In Progress | Medium | 2023-10-03 | 2023-10-23 |  | 63 | Rebar | Downtown Avenue | 47432.51 | 32594.11 | In progress
C001 | Residential Building A | T634 | Concrete Pouring | John Miller | Not Started | Medium | 2024-06-02 | 2024-06-22 |  | 0 | Copper Wires | Plot 21, Riverside | 38904.31 | 0 | Not started
C002 | Shopping Complex B | T228 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2023-10-17 | 2023-11-13 |  | 0 | Concrete | Market Street | 25454.22 | 0 | Not started
C001 | Residential Building A | T908 | Roofing | Rachel Green | In Progress | High | 2024-08-15 | 2024-08-22 |  | 12 | Cement | Plot 21, Riverside | 42256.62 | 26736.44 | In progress
C001 | Residential Building A | T312 | Plumbing Installations | Grace Allen | Completed | Medium | 2023-12-03 | 2023-12-14 | 2023-12-14 | 100 | Roofing Sheets | Plot 21, Riverside | 12523.06 | 14350.58 | No issues
C002 | Shopping Complex B | T960 | Site Survey | Rachel Green | Completed | Medium | 2024-06-12 | 2024-07-07 | 2024-07-07 | 100 | Paint | Market Street | 9958.69 | 37298.57 | No issues
C001 | Residential Building A | T935 | Site Survey | Grace Allen | Completed | High | 2023-11-18 | 2023-11-26 | 2023-11-26 | 100 | Steel Beams | Plot 21, Riverside | 27705.51 | 18278.81 | No issues
C003 | Office Tower C | T226 | Site Survey | Sarah Johnson | Completed | High | 2024-10-02 | 2024-10-17 | 2024-10-17 | 100 | Paint | Downtown Avenue | 49960.63 | 49714.31 | No issues
C004 | Warehouse D | T771 | Site Survey | Sarah Johnson | Blocked | Low | 2023-03-21 | 2023-04-11 |  | 0 | Roofing Sheets | Industrial Park | 6809.37 | 6501.45 | Not started
C003 | Office Tower C | T576 | Electrical Wiring | Sarah Johnson | Completed | High | 2024-04-05 | 2024-04-22 | 2024-04-22 | 100 | Paint | Downtown Avenue | 32124.55 | 22828.81 | No issues
C001 | Residential Building A | T676 | Concrete Pouring | Mike Adams | Completed | Medium | 2024-01-26 | 2024-02-08 | 2024-02-08 | 100 | PVC Pipes | Plot 21, Riverside | 24362.13 | 20753.6 | No issues
C001 | Residential Building A | T658 | Site Survey | Carlos Rivera | Not Started | Low | 2023-07-20 | 2023-08-09 |  | 0 | Cement | Plot 21, Riverside | 28831.86 | 0 | Not started
C003 | Office Tower C | T312 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-10-17 | 2023-11-13 |  | 0 | Concrete | Downtown Avenue | 13016.39 | 0 | Not started
C004 | Warehouse D | T203 | Foundation Excavation | John Miller | Blocked | Low | 2024-06-19 | 2024-07-06 |  | 0 | Paint | Industrial Park | 37498.94 | 32700.95 | Not started
C002 | Shopping Complex B | T281 | Foundation Excavation | Carlos Rivera | Blocked | Low | 2024-07-04 | 2024-07-24 |  | 0 | PVC Pipes | Market Street | 23219.18 | 44018.89 | Not started
C002 | Shopping Complex B | T400 | Interior Painting | Mike Adams | Completed | Low | 2023-10-04 | 2023-10-28 | 2023-10-28 | 100 | Rebar | Market Street | 23794.29 | 40535.39 | No issues
C001 | Residential Building A | T621 | Interior Painting | Emma White | In Progress | Low | 2023-04-24 | 2023-05-20 |  | 36 | Rebar | Plot 21, Riverside | 18570.95 | 11496.53 | In progress
C004 | Warehouse D | T802 | Site Survey | Mike Adams | Not Started | High | 2024-03-04 | 2024-03-25 |  | 0 | Rebar | Industrial Park | 42976.8 | 0 | Not started
C004 | Warehouse D | T398 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-08-23 | 2024-09-18 | 2024-09-18 | 100 | PVC Pipes | Industrial Park | 29273.56 | 30067.83 | No issues
C004 | Warehouse D | T103 | Interior Painting | Mike Adams | Blocked | Low | 2024-08-15 | 2024-08-29 |  | 0 | Concrete | Industrial Park | 30641.85 | 18393.91 | Not started
C002 | Shopping Complex B | T899 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2023-09-01 | 2023-09-21 |  | 55 | Roofing Sheets | Market Street | 12707.87 | 38294.44 | In progress
C003 | Office Tower C | T673 | Plumbing Installations | Mike Adams | Not Started | High | 2024-07-24 | 2024-08-14 |  | 0 | Cement | Downtown Avenue | 43401.69 | 0 | Not started
C004 | Warehouse D | T525 | Concrete Pouring | Emma White | Blocked | Medium | 2023-09-21 | 2023-10-04 |  | 0 | Roofing Sheets | Industrial Park | 8218.79 | 5027.75 | Not started
C001 | Residential Building A | T329 | Site Survey | Dave Brown | Not Started | High | 2023-03-13 | 2023-04-11 |  | 0 | Concrete | Plot 21, Riverside | 36104.18 | 0 | Not started
C002 | Shopping Complex B | T646 | Concrete Pouring | Grace Allen | Not Started | Low | 2024-10-25 | 2024-11-20 |  | 0 | Rebar | Market Street | 20911.61 | 0 | Not started
C001 | Residential Building A | T107 | Plumbing Installations | Grace Allen | Completed | Medium | 2024-12-28 | 2025-01-11 | 2025-01-11 | 100 | Rebar | Plot 21, Riverside | 40579.44 | 32462.5 | No issues
C003 | Office Tower C | T313 | Steel Framework Setup | Emma White | Blocked | Medium | 2024-05-27 | 2024-06-08 |  | 0 | Paint | Downtown Avenue | 12601.47 | 12149.09 | Not started
C001 | Residential Building A | T974 | Roofing | Rachel Green | Completed | High | 2024-11-22 | 2024-12-09 | 2024-12-09 | 100 | Concrete | Plot 21, Riverside | 36021.02 | 27598.57 | No issues
C003 | Office Tower C | T550 | Site Survey | Rachel Green | Completed | Low | 2024-09-05 | 2024-09-14 | 2024-09-14 | 100 | Cement | Downtown Avenue | 5754.52 | 3991.22 | No issues
C003 | Office Tower C | T995 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-08-15 | 2024-08-28 | 2024-08-28 | 100 | Cement | Downtown Avenue | 45341.22 | 45738.9 | No issues
C004 | Warehouse D | T155 | Foundation Excavation | Grace Allen | Blocked | Medium | 2024-08-15 | 2024-08-22 |  | 0 | Paint | Industrial Park | 47514.45 | 42258.21 | Not started
C001 | Residential Building A | T940 | Roofing | Dave Brown | Completed | Low | 2023-03-07 | 2023-03-24 | 2023-03-24 | 100 | Copper Wires | Plot 21, Riverside | 42983.84 | 32221.95 | No issues
C004 | Warehouse D | T479 | Concrete Pouring | Dave Brown | Blocked | Medium | 2023-03-26 | 2023-04-08 |  | 0 | Roofing Sheets | Industrial Park | 14845.98 | 16261.37 | Not started
C001 | Residential Building A | T391 | Steel Framework Setup | Mike Adams | Blocked | Low | 2024-06-13 | 2024-06-23 |  | 0 | PVC Pipes | Plot 21, Riverside | 19531.01 | 14323.9 | Not started
C002 | Shopping Complex B | T612 | Steel Framework Setup | Dave Brown | Completed | Medium | 2024-05-07 | 2024-05-22 | 2024-05-22 | 100 | Steel Beams | Market Street | 35576.98 | 52099.79 | No issues
C002 | Shopping Complex B | T522 | Site Survey | Emma White | Not Started | Low | 2024-12-05 | 2024-12-20 |  | 0 | Concrete | Market Street | 9593.69 | 0 | Not started
C001 | Residential Building A | T419 | Interior Painting | John Miller | In Progress | High | 2024-03-07 | 2024-03-21 |  | 26 | Roofing Sheets | Plot 21, Riverside | 36597.53 | 22165.64 | In progress
C002 | Shopping Complex B | T173 | Steel Framework Setup | Dave Brown | Not Started | Medium | 2023-05-03 | 2023-06-02 |  | 0 | Paint | Market Street | 5930.79 | 0 | Not started
C003 | Office Tower C | T829 | Roofing | Emma White | Completed | High | 2024-02-07 | 2024-03-06 | 2024-03-06 | 100 | PVC Pipes | Downtown Avenue | 13703.71 | 8702.48 | No issues
C001 | Residential Building A | T905 | Foundation Excavation | Dave Brown | Not Started | Medium | 2023-10-18 | 2023-10-31 |  | 0 | Copper Wires | Plot 21, Riverside | 21311.33 | 0 | Not started
C004 | Warehouse D | T286 | Roofing | Rachel Green | In Progress | Medium | 2023-12-27 | 2024-01-18 |  | 21 | Cement | Industrial Park | 43299.05 | 44309.98 | In progress
C002 | Shopping Complex B | T501 | Plumbing Installations | Emma White | In Progress | Low | 2024-03-06 | 2024-03-14 |  | 53 | Concrete | Market Street | 12036.55 | 35649.07 | In progress
C001 | Residential Building A | T856 | Steel Framework Setup | John Miller | Blocked | High | 2023-09-28 | 2023-10-27 |  | 0 | Copper Wires | Plot 21, Riverside | 31820.26 | 37716.9 | Not started
C001 | Residential Building A | T885 | Electrical Wiring | John Miller | Not Started | Low | 2024-11-24 | 2024-12-23 |  | 0 | Copper Wires | Plot 21, Riverside | 21030.25 | 0 | Not started
C002 | Shopping Complex B | T238 | Electrical Wiring | John Miller | Not Started | Low | 2023-07-23 | 2023-08-04 |  | 0 | Copper Wires | Market Street | 9547.53 | 0 | Not started
C004 | Warehouse D | T214 | Roofing | Emma White | Blocked | High | 2024-07-06 | 2024-07-27 |  | 0 | Paint | Industrial Park | 22632.12 | 19947.16 | Not started
C004 | Warehouse D | T268 | Steel Framework Setup | Grace Allen | Not Started | High | 2024-12-10 | 2024-12-19 |  | 0 | Roofing Sheets | Industrial Park | 11679.7 | 0 | Not started
C004 | Warehouse D | T736 | Concrete Pouring | Carlos Rivera | Completed | Low | 2023-08-01 | 2023-08-29 | 2023-08-29 | 100 | Paint | Industrial Park | 35660.57 | 31052.39 | No issues
C003 | Office Tower C | T505 | Electrical Wiring | Rachel Green | Blocked | Medium | 2024-07-28 | 2024-08-07 |  | 0 | Paint | Downtown Avenue | 29099.45 | 19583.98 | Not started
C004 | Warehouse D | T919 | Concrete Pouring | Grace Allen | Blocked | High | 2024-11-16 | 2024-12-09 |  | 0 | Cement | Industrial Park | 37510.11 | 28105.9 | Not started
C002 | Shopping Complex B | T488 | Interior Painting | Emma White | Not Started | Low | 2023-11-05 | 2023-11-15 |  | 0 | Paint | Market Street | 39428.16 | 0 | Not started
C002 | Shopping Complex B | T768 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-11-10 | 2024-11-29 |  | 0 | Roofing Sheets | Market Street | 42111.22 | 66505.58 | Not started
C001 | Residential Building A | T977 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-03-21 | 2023-04-15 | 2023-04-15 | 100 | Rebar | Plot 21, Riverside | 11012.58 | 7365.75 | No issues
C004 | Warehouse D | T259 | Site Survey | John Miller | Blocked | High | 2023-01-14 | 2023-01-26 |  | 0 | Steel Beams | Industrial Park | 28385.45 | 24509.49 | Not started
C002 | Shopping Complex B | T725 | Interior Painting | Emma White | In Progress | High | 2024-02-03 | 2024-02-14 |  | 45 | Paint | Market Street | 40314.17 | 56954.09 | In progress
C003 | Office Tower C | T329 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-02-26 | 2024-03-08 |  | 0 | Rebar | Downtown Avenue | 16843.98 | 16845.71 | Not started
C004 | Warehouse D | T853 | Plumbing Installations | Rachel Green | Not Started | Low | 2023-09-26 | 2023-10-18 |  | 0 | Roofing Sheets | Industrial Park | 47806.74 | 0 | Not started
C004 | Warehouse D | T953 | Roofing | Sarah Johnson | Not Started | Low | 2023-01-11 | 2023-02-07 |  | 0 | PVC Pipes | Industrial Park | 38369.21 | 0 | Not started
C004 | Warehouse D | T703 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-06-28 | 2023-07-23 |  | 0 | Copper Wires | Industrial Park | 28438.2 | 0 | Not started
C001 | Residential Building A | T628 | Interior Painting | John Miller | Blocked | Low | 2024-07-28 | 2024-08-07 |  | 0 | PVC Pipes | Plot 21, Riverside | 23561.11 | 20037.79 | Not started
C004 | Warehouse D | T540 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-08-05 | 2024-08-24 |  | 0 | Cement | Industrial Park | 29038.12 | 0 | Not started
C002 | Shopping Complex B | T793 | Steel Framework Setup | Grace Allen | Blocked | High | 2023-05-16 | 2023-06-08 |  | 0 | Steel Beams | Market Street | 12907.07 | 35936.83 | Not started
C001 | Residential Building A | T485 | Electrical Wiring | Dave Brown | Not Started | Medium | 2023-09-06 | 2023-09-27 |  | 0 | Copper Wires | Plot 21, Riverside | 34199.78 | 0 | Not started
C002 | Shopping Complex B | T587 | Plumbing Installations | John Miller | In Progress | High | 2024-03-02 | 2024-03-23 |  | 14 | Roofing Sheets | Market Street | 33884.94 | 58646.41 | In progress
C003 | Office Tower C | T674 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-10-09 | 2023-11-05 |  | 1 | Rebar | Downtown Avenue | 26581.18 | 29213.3 | In progress
C004 | Warehouse D | T605 | Interior Painting | Grace Allen | Not Started | High | 2023-09-25 | 2023-10-11 |  | 0 | Paint | Industrial Park | 33003.57 | 0 | Not started
C001 | Residential Building A | T733 | Interior Painting | Carlos Rivera | Blocked | High | 2024-03-25 | 2024-04-22 |  | 0 | Paint | Plot 21, Riverside | 47287.63 | 46385.83 | Not started
C002 | Shopping Complex B | T763 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2024-02-18 | 2024-03-08 |  | 0 | Steel Beams | Market Street | 25003.59 | 0 | Not started
C002 | Shopping Complex B | T201 | Interior Painting | John Miller | Blocked | Low | 2024-10-05 | 2024-10-29 |  | 0 | Copper Wires | Market Street | 38943.82 | 54426.47 | Not started
C002 | Shopping Complex B | T453 | Interior Painting | Rachel Green | Not Started | Low | 2023-02-15 | 2023-03-12 |  | 0 | Cement | Market Street | 33879.13 | 0 | Not started
C002 | Shopping Complex B | T552 | Roofing | Rachel Green | In Progress | High | 2023-01-28 | 2023-02-04 |  | 8 | Steel Beams | Market Street | 10694.85 | 36185.68 | In progress
C001 | Residential Building A | T227 | Concrete Pouring | Rachel Green | Not Started | Low | 2023-02-13 | 2023-03-12 |  | 0 | Concrete | Plot 21, Riverside | 40985.64 | 0 | Not started
C002 | Shopping Complex B | T738 | Concrete Pouring | Grace Allen | Completed | Medium | 2023-04-01 | 2023-04-12 | 2023-04-12 | 100 | Rebar | Market Street | 32168.27 | 56446.78 | No issues
C001 | Residential Building A | T527 | Roofing | Grace Allen | Blocked | Medium | 2024-01-14 | 2024-01-27 |  | 0 | Roofing Sheets | Plot 21, Riverside | 25830.32 | 22207.85 | Not started
C002 | Shopping Complex B | T377 | Interior Painting | Carlos Rivera | Not Started | High | 2023-06-10 | 2023-07-09 |  | 0 | Roofing Sheets | Market Street | 26071.26 | 0 | Not started
C001 | Residential Building A | T936 | Interior Painting | Grace Allen | Not Started | Medium | 2023-03-13 | 2023-03-20 |  | 0 | Cement | Plot 21, Riverside | 40026.64 | 0 | Not started
C001 | Residential Building A | T697 | Electrical Wiring | John Miller | In Progress | Low | 2024-11-17 | 2024-12-03 |  | 21 | Rebar | Plot 21, Riverside | 28271.03 | 32336.9 | In progress
C001 | Residential Building A | T501 | Roofing | Carlos Rivera | In Progress | Low | 2024-01-18 | 2024-02-08 |  | 48 | Roofing Sheets | Plot 21, Riverside | 11415.8 | 6928.45 | In progress
C003 | Office Tower C | T826 | Roofing | Carlos Rivera | In Progress | Low | 2024-11-13 | 2024-11-30 |  | 85 | Steel Beams | Downtown Avenue | 28095.44 | 23967.12 | In progress
C002 | Shopping Complex B | T486 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-05-08 | 2023-06-05 |  | 0 | Rebar | Market Street | 45246.81 | 0 | Not started
C003 | Office Tower C | T338 | Site Survey | Mike Adams | In Progress | High | 2024-12-08 | 2024-12-31 |  | 35 | PVC Pipes | Downtown Avenue | 6112.71 | 4255.29 | In progress
C001 | Residential Building A | T134 | Plumbing Installations | John Miller | Completed | High | 2023-06-02 | 2023-06-24 | 2023-06-24 | 100 | Cement | Plot 21, Riverside | 36457.6 | 28225.78 | No issues
C001 | Residential Building A | T242 | Roofing | Dave Brown | Not Started | Medium | 2024-05-23 | 2024-06-07 |  | 0 | Paint | Plot 21, Riverside | 24297.21 | 0 | Not started
C002 | Shopping Complex B | T448 | Electrical Wiring | Grace Allen | Not Started | High | 2024-07-13 | 2024-07-20 |  | 0 | Roofing Sheets | Market Street | 24801.42 | 0 | Not started
C002 | Shopping Complex B | T980 | Electrical Wiring | Grace Allen | In Progress | High | 2024-05-02 | 2024-05-09 |  | 52 | Paint | Market Street | 40022.46 | 73368.99 | In progress
C001 | Residential Building A | T445 | Roofing | Rachel Green | Not Started | High | 2024-09-04 | 2024-09-29 |  | 0 | Rebar | Plot 21, Riverside | 32860.89 | 0 | Not started
C004 | Warehouse D | T861 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2024-08-15 | 2024-09-04 |  | 0 | Steel Beams | Industrial Park | 14975.14 | 10430.08 | Not started
C004 | Warehouse D | T186 | Interior Painting | Emma White | Not Started | Low | 2024-05-25 | 2024-06-06 |  | 0 | Paint | Industrial Park | 11128.4 | 0 | Not started
C004 | Warehouse D | T334 | Roofing | Emma White | Not Started | High | 2023-01-02 | 2023-01-13 |  | 0 | Rebar | Industrial Park | 42153.03 | 0 | Not started
C003 | Office Tower C | T836 | Plumbing Installations | Grace Allen | In Progress | Low | 2023-10-13 | 2023-11-09 |  | 80 | Roofing Sheets | Downtown Avenue | 42676.92 | 44371.36 | In progress
C004 | Warehouse D | T284 | Roofing | Grace Allen | In Progress | High | 2023-12-12 | 2023-12-31 |  | 0 | Roofing Sheets | Industrial Park | 34026.66 | 35801.48 | In progress
C002 | Shopping Complex B | T840 | Concrete Pouring | Grace Allen | Blocked | High | 2024-12-24 | 2025-01-11 |  | 0 | Concrete | Market Street | 5441.45 | 28808.2 | Not started
C004 | Warehouse D | T761 | Plumbing Installations | Dave Brown | Completed | High | 2023-05-09 | 2023-05-21 | 2023-05-21 | 100 | PVC Pipes | Industrial Park | 11473.88 | 7801.95 | No issues
C001 | Residential Building A | T682 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-11-10 | 2023-12-06 |  | 28 | Concrete | Plot 21, Riverside | 46026.72 | 28647.5 | In progress
C002 | Shopping Complex B | T376 | Electrical Wiring | Emma White | Blocked | Low | 2024-02-16 | 2024-03-02 |  | 0 | Steel Beams | Market Street | 31157.13 | 54529.57 | Not started
C004 | Warehouse D | T521 | Interior Painting | Carlos Rivera | In Progress | Low | 2023-09-01 | 2023-09-12 |  | 33 | Steel Beams | Industrial Park | 30166.55 | 34223.34 | In progress
C003 | Office Tower C | T203 | Foundation Excavation | Sarah Johnson | Completed | High | 2024-11-24 | 2024-12-24 | 2024-12-24 | 100 | Paint | Downtown Avenue | 10317.58 | 11105.23 | No issues
C002 | Shopping Complex B | T607 | Concrete Pouring | Rachel Green | Blocked | Medium | 2024-09-15 | 2024-09-26 |  | 0 | Steel Beams | Market Street | 43371.25 | 63064.57 | Not started
C002 | Shopping Complex B | T596 | Roofing | Emma White | In Progress | Medium | 2024-09-03 | 2024-09-12 |  | 86 | Concrete | Market Street | 26094 | 53097.66 | In progress
C003 | Office Tower C | T340 | Plumbing Installations | Mike Adams | In Progress | Medium | 2024-11-27 | 2024-12-26 |  | 62 | Copper Wires | Downtown Avenue | 14391.79 | 10745.86 | In progress
C004 | Warehouse D | T218 | Site Survey | Emma White | In Progress | High | 2024-06-18 | 2024-07-02 |  | 76 | Copper Wires | Industrial Park | 6974.53 | 8129.7 | In progress
C003 | Office Tower C | T836 | Interior Painting | John Miller | Completed | Medium | 2023-11-28 | 2023-12-20 | 2023-12-20 | 100 | Roofing Sheets | Downtown Avenue | 10084.04 | 8955.26 | No issues
C002 | Shopping Complex B | T206 | Plumbing Installations | Mike Adams | Completed | Low | 2023-01-21 | 2023-02-19 | 2023-02-19 | 100 | PVC Pipes | Market Street | 23553.05 | 51896 | No issues
C001 | Residential Building A | T384 | Plumbing Installations | Carlos Rivera | Not Started | Medium | 2024-08-03 | 2024-08-20 |  | 0 | PVC Pipes | Plot 21, Riverside | 47125.23 | 0 | Not started
C003 | Office Tower C | T437 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2023-10-12 | 2023-11-10 |  | 16 | Steel Beams | Downtown Avenue | 5923.22 | 4065.02 | In progress
C004 | Warehouse D | T527 | Concrete Pouring | Emma White | In Progress | Low | 2024-11-27 | 2024-12-23 |  | 95 | PVC Pipes | Industrial Park | 25103.3 | 16614.87 | In progress
C001 | Residential Building A | T507 | Interior Painting | Emma White | In Progress | Medium | 2023-06-20 | 2023-07-11 |  | 18 | Rebar | Plot 21, Riverside | 44210.25 | 50547 | In progress
C001 | Residential Building A | T840 | Roofing | Rachel Green | Not Started | Medium | 2023-01-19 | 2023-02-14 |  | 0 | Paint | Plot 21, Riverside | 16884.38 | 0 | Not started
C003 | Office Tower C | T591 | Foundation Excavation | Rachel Green | Blocked | Medium | 2024-04-04 | 2024-04-16 |  | 0 | Concrete | Downtown Avenue | 40390.02 | 44292.61 | Not started
C004 | Warehouse D | T366 | Foundation Excavation | Sarah Johnson | Not Started | Medium | 2024-08-03 | 2024-08-18 |  | 0 | Copper Wires | Industrial Park | 30934.6 | 0 | Not started
C002 | Shopping Complex B | T311 | Site Survey | John Miller | In Progress | Low | 2023-02-18 | 2023-02-27 |  | 18 | Rebar | Market Street | 20003.18 | 47210.72 | In progress
C004 | Warehouse D | T991 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2024-08-10 | 2024-08-25 |  | 0 | PVC Pipes | Industrial Park | 15486.06 | 14340.75 | Not started
C001 | Residential Building A | T956 | Concrete Pouring | Grace Allen | In Progress | High | 2023-02-08 | 2023-02-21 |  | 51 | PVC Pipes | Plot 21, Riverside | 21184.01 | 18163.85 | In progress
C004 | Warehouse D | T663 | Site Survey | Grace Allen | Not Started | Medium | 2024-12-20 | 2025-01-03 |  | 0 | PVC Pipes | Industrial Park | 46718.4 | 0 | Not started
C001 | Residential Building A | T333 | Foundation Excavation | Dave Brown | In Progress | High | 2023-04-23 | 2023-05-15 |  | 17 | Concrete | Plot 21, Riverside | 16407.84 | 16686.51 | In progress
C004 | Warehouse D | T542 | Foundation Excavation | John Miller | Completed | High | 2024-05-15 | 2024-06-04 | 2024-06-04 | 100 | Copper Wires | Industrial Park | 39043.56 | 36887 | No issues
C003 | Office Tower C | T810 | Electrical Wiring | Grace Allen | Not Started | High | 2024-02-25 | 2024-03-25 |  | 0 | Steel Beams | Downtown Avenue | 33537.73 | 0 | Not started
C002 | Shopping Complex B | T933 | Concrete Pouring | Emma White | Completed | Medium | 2024-01-20 | 2024-02-10 | 2024-02-10 | 100 | PVC Pipes | Market Street | 28980.47 | 52602.48 | No issues
C001 | Residential Building A | T890 | Foundation Excavation | John Miller | Completed | Low | 2024-12-13 | 2024-12-26 | 2024-12-26 | 100 | Copper Wires | Plot 21, Riverside | 42719.32 | 40646.67 | No issues
C004 | Warehouse D | T108 | Site Survey | Emma White | Blocked | Low | 2023-05-28 | 2023-06-05 |  | 0 | Paint | Industrial Park | 44564.58 | 36351.62 | Not started
C002 | Shopping Complex B | T742 | Steel Framework Setup | Rachel Green | In Progress | Low | 2023-02-09 | 2023-02-18 |  | 62 | Copper Wires | Market Street | 43361.21 | 57352.1 | In progress
C001 | Residential Building A | T714 | Foundation Excavation | Rachel Green | Completed | Medium | 2024-05-06 | 2024-05-21 | 2024-05-21 | 100 | Cement | Plot 21, Riverside | 22548.23 | 24028.17 | No issues
C002 | Shopping Complex B | T693 | Plumbing Installations | Grace Allen | Completed | High | 2024-08-09 | 2024-08-19 | 2024-08-19 | 100 | Roofing Sheets | Market Street | 8918.46 | 34742.58 | No issues
C003 | Office Tower C | T156 | Interior Painting | Emma White | In Progress | High | 2023-06-22 | 2023-07-12 |  | 14 | Concrete | Downtown Avenue | 13538.36 | 14468.38 | In progress
C004 | Warehouse D | T770 | Electrical Wiring | Emma White | Blocked | High | 2024-07-21 | 2024-08-20 |  | 0 | Paint | Industrial Park | 33527.63 | 33392.51 | Not started
C002 | Shopping Complex B | T491 | Concrete Pouring | Emma White | In Progress | High | 2024-05-05 | 2024-05-21 |  | 12 | PVC Pipes | Market Street | 10120.88 | 33798.07 | In progress
C003 | Office Tower C | T508 | Concrete Pouring | Grace Allen | Not Started | Low | 2023-08-07 | 2023-09-01 |  | 0 | Concrete | Downtown Avenue | 24861.83 | 0 | Not started
C003 | Office Tower C | T739 | Site Survey | Emma White | Blocked | Low | 2024-11-02 | 2024-11-30 |  | 0 | Cement | Downtown Avenue | 17738.78 | 11231.8 | Not started
C002 | Shopping Complex B | T678 | Electrical Wiring | Emma White | Blocked | Low | 2024-04-18 | 2024-05-13 |  | 0 | Roofing Sheets | Market Street | 47254.88 | 65361.93 | Not started
C004 | Warehouse D | T788 | Site Survey | Mike Adams | Not Started | High | 2024-05-08 | 2024-05-24 |  | 0 | Roofing Sheets | Industrial Park | 22017.49 | 0 | Not started
C001 | Residential Building A | T524 | Concrete Pouring | Dave Brown | In Progress | Medium | 2023-12-17 | 2024-01-05 |  | 87 | Concrete | Plot 21, Riverside | 36443.79 | 24945.22 | In progress
C001 | Residential Building A | T504 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-06-17 | 2023-07-02 |  | 55 | Roofing Sheets | Plot 21, Riverside | 19688.12 | 11856.17 | In progress
C001 | Residential Building A | T840 | Foundation Excavation | Rachel Green | Completed | High | 2023-12-17 | 2023-12-28 | 2023-12-28 | 100 | Paint | Plot 21, Riverside | 41469.53 | 29166 | No issues
C003 | Office Tower C | T741 | Roofing | Rachel Green | Blocked | High | 2024-06-05 | 2024-06-26 |  | 0 | Steel Beams | Downtown Avenue | 14536.02 | 14441.9 | Not started
C002 | Shopping Complex B | T835 | Roofing | Carlos Rivera | Completed | Low | 2024-04-23 | 2024-05-20 | 2024-05-20 | 100 | Rebar | Market Street | 27657.49 | 44244.22 | No issues
C003 | Office Tower C | T827 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2024-07-04 | 2024-08-03 |  | 0 | PVC Pipes | Downtown Avenue | 35694.56 | 37180.08 | Not started
C003 | Office Tower C | T255 | Site Survey | Grace Allen | Completed | Low | 2023-06-16 | 2023-07-03 | 2023-07-03 | 100 | Paint | Downtown Avenue | 48431.9 | 32777.22 | No issues
C004 | Warehouse D | T247 | Steel Framework Setup | John Miller | Blocked | High | 2024-02-06 | 2024-03-05 |  | 0 | Copper Wires | Industrial Park | 28664.95 | 28047.18 | Not started
C004 | Warehouse D | T284 | Plumbing Installations | Sarah Johnson | Blocked | Low | 2023-01-21 | 2023-02-05 |  | 0 | PVC Pipes | Industrial Park | 39169.29 | 31483.66 | Not started
C003 | Office Tower C | T524 | Roofing | Dave Brown | Not Started | Medium | 2023-04-10 | 2023-04-19 |  | 0 | PVC Pipes | Downtown Avenue | 5218.86 | 0 | Not started
C004 | Warehouse D | T512 | Concrete Pouring | Emma White | Blocked | High | 2023-01-20 | 2023-02-16 |  | 0 | Steel Beams | Industrial Park | 12693.1 | 14523.21 | Not started
C003 | Office Tower C | T574 | Plumbing Installations | Grace Allen | Completed | High | 2023-05-17 | 2023-06-12 | 2023-06-12 | 100 | Concrete | Downtown Avenue | 26568.78 | 16497.87 | No issues
C004 | Warehouse D | T231 | Concrete Pouring | John Miller | In Progress | High | 2024-04-17 | 2024-05-01 |  | 36 | Copper Wires | Industrial Park | 14154.7 | 10975.93 | In progress
C003 | Office Tower C | T186 | Site Survey | Grace Allen | Not Started | Low | 2023-09-20 | 2023-10-10 |  | 0 | PVC Pipes | Downtown Avenue | 14642.95 | 0 | Not started
C002 | Shopping Complex B | T950 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-05-12 | 2024-06-03 |  | 0 | Paint | Market Street | 10158.34 | 36929.54 | Not started
C002 | Shopping Complex B | T351 | Roofing | Emma White | Blocked | High | 2023-06-04 | 2023-06-16 |  | 0 | Rebar | Market Street | 14295.7 | 42626.19 | Not started
C002 | Shopping Complex B | T307 | Concrete Pouring | Mike Adams | In Progress | Low | 2024-06-15 | 2024-07-07 |  | 3 | Copper Wires | Market Street | 18089.24 | 36811.36 | In progress
C003 | Office Tower C | T706 | Interior Painting | John Miller | Not Started | Low | 2023-03-28 | 2023-04-20 |  | 0 | PVC Pipes | Downtown Avenue | 29560.3 | 0 | Not started
C002 | Shopping Complex B | T171 | Steel Framework Setup | Carlos Rivera | Completed | Low | 2024-05-09 | 2024-06-02 | 2024-06-02 | 100 | Copper Wires | Market Street | 26259.05 | 56115.76 | No issues
C003 | Office Tower C | T587 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-04-15 | 2023-05-06 |  | 50 | Cement | Downtown Avenue | 5450.99 | 5223.1 | In progress
C004 | Warehouse D | T838 | Site Survey | Dave Brown | In Progress | Medium | 2023-08-26 | 2023-09-15 |  | 47 | Roofing Sheets | Industrial Park | 43837.59 | 28856.02 | In progress
C003 | Office Tower C | T580 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-04-11 | 2024-04-19 |  | 65 | Paint | Downtown Avenue | 38043.54 | 34553.97 | In progress
C001 | Residential Building A | T162 | Concrete Pouring | Mike Adams | Completed | High | 2023-07-26 | 2023-08-09 | 2023-08-09 | 100 | PVC Pipes | Plot 21, Riverside | 17613.36 | 13671.68 | No issues
C003 | Office Tower C | T809 | Foundation Excavation | Sarah Johnson | Completed | High | 2023-04-21 | 2023-05-21 | 2023-05-21 | 100 | Paint | Downtown Avenue | 41475.75 | 27373.57 | No issues
C003 | Office Tower C | T759 | Concrete Pouring | Grace Allen | In Progress | Medium | 2024-12-03 | 2024-12-15 |  | 54 | Rebar | Downtown Avenue | 28700.02 | 20581.16 | In progress
C001 | Residential Building A | T778 | Electrical Wiring | John Miller | Completed | Medium | 2024-03-18 | 2024-04-14 | 2024-04-14 | 100 | Concrete | Plot 21, Riverside | 45511.01 | 50951.18 | No issues
C001 | Residential Building A | T263 | Electrical Wiring | John Miller | Not Started | High | 2024-09-21 | 2024-10-02 |  | 0 | Concrete | Plot 21, Riverside | 15729.11 | 0 | Not started
C004 | Warehouse D | T736 | Roofing | Emma White | In Progress | Medium | 2023-06-12 | 2023-06-27 |  | 24 | Concrete | Industrial Park | 6540.35 | 7229.8 | In progress
C004 | Warehouse D | T879 | Electrical Wiring | Dave Brown | Completed | Medium | 2023-03-04 | 2023-03-11 | 2023-03-11 | 100 | Paint | Industrial Park | 12926.68 | 14686.33 | No issues
C003 | Office Tower C | T588 | Electrical Wiring | Carlos Rivera | Completed | Low | 2023-11-09 | 2023-11-19 | 2023-11-19 | 100 | Rebar | Downtown Avenue | 5683.93 | 6638.97 | No issues
C002 | Shopping Complex B | T418 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-05-03 | 2023-05-24 |  | 0 | Paint | Market Street | 5277.52 | 31774.65 | Not started
C003 | Office Tower C | T542 | Concrete Pouring | Sarah Johnson | Blocked | High | 2024-12-01 | 2024-12-25 |  | 0 | Cement | Downtown Avenue | 43705.47 | 46485.72 | Not started
C004 | Warehouse D | T413 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2024-08-13 | 2024-08-24 | 2024-08-24 | 100 | PVC Pipes | Industrial Park | 34819.22 | 32007.46 | No issues
C003 | Office Tower C | T910 | Interior Painting | Emma White | In Progress | Medium | 2024-08-17 | 2024-09-03 |  | 58 | Rebar | Downtown Avenue | 35192.34 | 39371.9 | In progress
C003 | Office Tower C | T625 | Roofing | Emma White | Not Started | Medium | 2024-09-25 | 2024-10-09 |  | 0 | PVC Pipes | Downtown Avenue | 16205.33 | 0 | Not started
C003 | Office Tower C | T886 | Roofing | John Miller | Blocked | Medium | 2024-10-14 | 2024-10-23 |  | 0 | PVC Pipes | Downtown Avenue | 21305.09 | 24666.53 | Not started
C003 | Office Tower C | T569 | Electrical Wiring | Rachel Green | In Progress | High | 2024-07-21 | 2024-08-01 |  | 29 | PVC Pipes | Downtown Avenue | 16350.8 | 10524.12 | In progress
C001 | Residential Building A | T718 | Plumbing Installations | John Miller | In Progress | High | 2024-12-27 | 2025-01-23 |  | 59 | Paint | Plot 21, Riverside | 13645.2 | 13992.11 | In progress
C001 | Residential Building A | T199 | Roofing | Sarah Johnson | In Progress | Medium | 2023-09-28 | 2023-10-15 |  | 62 | PVC Pipes | Plot 21, Riverside | 21564.66 | 19070.56 | In progress
C004 | Warehouse D | T297 | Roofing | Emma White | Blocked | Low | 2023-06-14 | 2023-07-05 |  | 0 | Paint | Industrial Park | 11759.55 | 8115.18 | Not started
C004 | Warehouse D | T657 | Roofing | Grace Allen | In Progress | Medium | 2023-01-04 | 2023-01-17 |  | 30 | Concrete | Industrial Park | 25597.16 | 19807.89 | In progress
C001 | Residential Building A | T277 | Site Survey | Mike Adams | Blocked | Low | 2023-01-24 | 2023-02-06 |  | 0 | Steel Beams | Plot 21, Riverside | 13155.61 | 10331.9 | Not started
C002 | Shopping Complex B | T144 | Electrical Wiring | Carlos Rivera | Blocked | Low | 2024-04-01 | 2024-04-10 |  | 0 | Rebar | Market Street | 13163.37 | 40362.57 | Not started
C002 | Shopping Complex B | T149 | Roofing | Grace Allen | Not Started | High | 2023-07-25 | 2023-08-15 |  | 0 | PVC Pipes | Market Street | 5595.4 | 0 | Not started
C003 | Office Tower C | T341 | Site Survey | Mike Adams | Blocked | High | 2023-10-06 | 2023-10-31 |  | 0 | Steel Beams | Downtown Avenue | 48389.4 | 47909.73 | Not started
C002 | Shopping Complex B | T950 | Concrete Pouring | John Miller | Blocked | Medium | 2024-01-08 | 2024-02-01 |  | 0 | Roofing Sheets | Market Street | 24999.59 | 52597.95 | Not started
C002 | Shopping Complex B | T525 | Site Survey | Grace Allen | Not Started | Low | 2023-09-09 | 2023-09-18 |  | 0 | Rebar | Market Street | 22122.44 | 0 | Not started
C004 | Warehouse D | T849 | Interior Painting | Mike Adams | Not Started | Low | 2024-11-11 | 2024-12-07 |  | 0 | Cement | Industrial Park | 43337.12 | 0 | Not started
C001 | Residential Building A | T985 | Interior Painting | Carlos Rivera | In Progress | High | 2023-09-17 | 2023-10-06 |  | 72 | Rebar | Plot 21, Riverside | 42244.47 | 36858.37 | In progress
C002 | Shopping Complex B | T603 | Plumbing Installations | Sarah Johnson | Blocked | High | 2023-03-25 | 2023-04-02 |  | 0 | Paint | Market Street | 19420.26 | 45315.94 | Not started
C004 | Warehouse D | T605 | Foundation Excavation | Emma White | Blocked | Medium | 2023-10-01 | 2023-10-27 |  | 0 | Steel Beams | Industrial Park | 26658.92 | 16700.14 | Not started
C004 | Warehouse D | T490 | Site Survey | Rachel Green | Completed | High | 2024-03-20 | 2024-04-07 | 2024-04-07 | 100 | Cement | Industrial Park | 32657.31 | 35840.07 | No issues
C001 | Residential Building A | T557 | Roofing | John Miller | Not Started | Low | 2023-02-13 | 2023-03-01 |  | 0 | Copper Wires | Plot 21, Riverside | 8941.19 | 0 | Not started
C003 | Office Tower C | T418 | Foundation Excavation | Mike Adams | Completed | Medium | 2023-02-24 | 2023-03-05 | 2023-03-05 | 100 | Cement | Downtown Avenue | 7739.24 | 6973.23 | No issues
C004 | Warehouse D | T257 | Site Survey | Emma White | In Progress | Medium | 2024-06-05 | 2024-06-12 |  | 14 | Concrete | Industrial Park | 42296.97 | 46316.33 | In progress
C003 | Office Tower C | T310 | Electrical Wiring | Dave Brown | Blocked | High | 2024-08-21 | 2024-09-16 |  | 0 | Concrete | Downtown Avenue | 12753.11 | 13706.61 | Not started
C002 | Shopping Complex B | T235 | Foundation Excavation | Grace Allen | Not Started | High | 2024-11-26 | 2024-12-11 |  | 0 | Roofing Sheets | Market Street | 20191.76 | 0 | Not started
C003 | Office Tower C | T984 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-03-10 | 2023-03-29 |  | 97 | Rebar | Downtown Avenue | 36502.28 | 39382.15 | In progress
C002 | Shopping Complex B | T784 | Plumbing Installations | Rachel Green | Blocked | High | 2023-07-02 | 2023-07-12 |  | 0 | Paint | Market Street | 37070.11 | 60213.15 | Not started
C003 | Office Tower C | T689 | Concrete Pouring | Carlos Rivera | Completed | Low | 2024-02-10 | 2024-02-18 | 2024-02-18 | 100 | Copper Wires | Downtown Avenue | 38464.8 | 44604.03 | No issues
C002 | Shopping Complex B | T854 | Steel Framework Setup | Carlos Rivera | Not Started | High | 2023-07-24 | 2023-08-17 |  | 0 | Concrete | Market Street | 44106.41 | 0 | Not started
C003 | Office Tower C | T336 | Interior Painting | Carlos Rivera | Not Started | Medium | 2024-01-25 | 2024-02-23 |  | 0 | Copper Wires | Downtown Avenue | 39108.17 | 0 | Not started
C001 | Residential Building A | T236 | Electrical Wiring | Grace Allen | Blocked | High | 2023-10-10 | 2023-11-06 |  | 0 | Concrete | Plot 21, Riverside | 16556.29 | 10975.49 | Not started
C003 | Office Tower C | T323 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-09-15 | 2023-10-03 |  | 0 | Cement | Downtown Avenue | 42610.57 | 0 | Not started
C003 | Office Tower C | T518 | Roofing | John Miller | Blocked | Medium | 2023-02-10 | 2023-02-25 |  | 0 | Cement | Downtown Avenue | 9179.8 | 10676.34 | Not started
C002 | Shopping Complex B | T337 | Site Survey | Dave Brown | Completed | Medium | 2023-07-10 | 2023-08-06 | 2023-08-06 | 100 | Concrete | Market Street | 23877.55 | 46787.05 | No issues
C001 | Residential Building A | T375 | Interior Painting | Sarah Johnson | In Progress | Low | 2024-06-16 | 2024-07-10 |  | 35 | PVC Pipes | Plot 21, Riverside | 37757.48 | 34509.09 | In progress
C001 | Residential Building A | T196 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2023-06-16 | 2023-06-23 |  | 0 | Roofing Sheets | Plot 21, Riverside | 36970.13 | 36175.27 | Not started
C001 | Residential Building A | T671 | Site Survey | John Miller | Not Started | High | 2023-05-11 | 2023-06-09 |  | 0 | Cement | Plot 21, Riverside | 45815.54 | 0 | Not started
C002 | Shopping Complex B | T222 | Foundation Excavation | John Miller | In Progress | Low | 2023-02-08 | 2023-03-06 |  | 82 | Copper Wires | Market Street | 27633.84 | 56256.17 | In progress
C003 | Office Tower C | T762 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2024-10-19 | 2024-11-14 |  | 0 | Steel Beams | Downtown Avenue | 49295.37 | 0 | Not started
C003 | Office Tower C | T674 | Electrical Wiring | Grace Allen | Blocked | High | 2024-03-28 | 2024-04-20 |  | 0 | Steel Beams | Downtown Avenue | 6766.12 | 7463.71 | Not started
C003 | Office Tower C | T877 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-01-19 | 2023-02-01 |  | 0 | Steel Beams | Downtown Avenue | 37800.55 | 0 | Not started
C002 | Shopping Complex B | T665 | Concrete Pouring | Mike Adams | Completed | High | 2024-09-02 | 2024-09-30 | 2024-09-30 | 100 | Cement | Market Street | 20560.8 | 44143.47 | No issues
C001 | Residential Building A | T895 | Site Survey | Sarah Johnson | Not Started | Medium | 2024-04-22 | 2024-05-20 |  | 0 | Steel Beams | Plot 21, Riverside | 46302.71 | 0 | Not started
C001 | Residential Building A | T660 | Interior Painting | Carlos Rivera | Blocked | Medium | 2023-07-19 | 2023-07-27 |  | 0 | Copper Wires | Plot 21, Riverside | 19102.42 | 17769.62 | Not started
C003 | Office Tower C | T166 | Site Survey | Grace Allen | Blocked | Low | 2024-02-18 | 2024-03-08 |  | 0 | Rebar | Downtown Avenue | 23485.1 | 15673.82 | Not started
C003 | Office Tower C | T698 | Interior Painting | Sarah Johnson | Blocked | High | 2024-03-08 | 2024-03-16 |  | 0 | Concrete | Downtown Avenue | 29974.08 | 31339.69 | Not started
C002 | Shopping Complex B | T884 | Plumbing Installations | John Miller | Blocked | Low | 2023-10-09 | 2023-10-21 |  | 0 | Copper Wires | Market Street | 43608.59 | 71135.58 | Not started
C002 | Shopping Complex B | T378 | Foundation Excavation | Grace Allen | Completed | High | 2024-12-12 | 2024-12-31 | 2024-12-31 | 100 | Cement | Market Street | 20584.53 | 47385.53 | No issues
C001 | Residential Building A | T118 | Site Survey | Rachel Green | Not Started | High | 2024-11-08 | 2024-11-20 |  | 0 | Steel Beams | Plot 21, Riverside | 23198.11 | 0 | Not started
C002 | Shopping Complex B | T626 | Concrete Pouring | Dave Brown | Completed | High | 2024-06-17 | 2024-07-01 | 2024-07-01 | 100 | Roofing Sheets | Market Street | 26676.12 | 46274.78 | No issues
C003 | Office Tower C | T684 | Plumbing Installations | Grace Allen | Not Started | Low | 2024-11-07 | 2024-12-05 |  | 0 | Roofing Sheets | Downtown Avenue | 43713.09 | 0 | Not started
C003 | Office Tower C | T925 | Concrete Pouring | Grace Allen | Not Started | Low | 2023-06-03 | 2023-06-11 |  | 0 | Roofing Sheets | Downtown Avenue | 45656.96 | 0 | Not started
C004 | Warehouse D | T332 | Roofing | Rachel Green | In Progress | High | 2023-04-06 | 2023-04-29 |  | 49 | Steel Beams | Industrial Park | 15970.21 | 15526.1 | In progress
C001 | Residential Building A | T210 | Concrete Pouring | John Miller | Blocked | Low | 2024-05-03 | 2024-06-01 |  | 0 | Concrete | Plot 21, Riverside | 30812.61 | 35879.25 | Not started
C002 | Shopping Complex B | T214 | Roofing | Grace Allen | Blocked | High | 2023-05-11 | 2023-05-18 |  | 0 | Concrete | Market Street | 39461.46 | 54761.41 | Not started
C001 | Residential Building A | T606 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-06-01 | 2023-06-09 |  | 0 | Rebar | Plot 21, Riverside | 35024.47 | 31330.41 | Not started
C003 | Office Tower C | T500 | Interior Painting | Sarah Johnson | Completed | High | 2023-06-06 | 2023-07-02 | 2023-07-02 | 100 | Cement | Downtown Avenue | 15199.15 | 14408.03 | No issues
C002 | Shopping Complex B | T554 | Roofing | Mike Adams | Completed | Low | 2024-07-26 | 2024-08-25 | 2024-08-25 | 100 | Roofing Sheets | Market Street | 6958.3 | 30351.38 | No issues
C003 | Office Tower C | T645 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-07-23 | 2024-08-22 |  | 75 | Concrete | Downtown Avenue | 26661.94 | 20632.99 | In progress
C002 | Shopping Complex B | T276 | Plumbing Installations | John Miller | Blocked | Medium | 2024-04-02 | 2024-04-11 |  | 0 | Rebar | Market Street | 7727.9 | 31502.21 | Not started
C003 | Office Tower C | T990 | Interior Painting | Carlos Rivera | Not Started | High | 2024-04-15 | 2024-04-26 |  | 0 | Roofing Sheets | Downtown Avenue | 35252.99 | 0 | Not started
C001 | Residential Building A | T675 | Interior Painting | Dave Brown | Completed | Low | 2024-04-23 | 2024-05-07 | 2024-05-07 | 100 | Steel Beams | Plot 21, Riverside | 41879.32 | 39915.92 | No issues
C004 | Warehouse D | T538 | Concrete Pouring | Emma White | Blocked | Low | 2024-06-01 | 2024-06-26 |  | 0 | Rebar | Industrial Park | 29545.52 | 21128.37 | Not started
C003 | Office Tower C | T366 | Site Survey | Rachel Green | Not Started | High | 2023-09-16 | 2023-10-16 |  | 0 | Paint | Downtown Avenue | 19854.95 | 0 | Not started
C003 | Office Tower C | T185 | Interior Painting | Grace Allen | In Progress | Medium | 2023-01-28 | 2023-02-24 |  | 20 | Concrete | Downtown Avenue | 31103.3 | 26911.61 | In progress
C002 | Shopping Complex B | T433 | Site Survey | John Miller | Not Started | Low | 2024-10-07 | 2024-10-25 |  | 0 | PVC Pipes | Market Street | 18130.74 | 0 | Not started
C001 | Residential Building A | T321 | Site Survey | Carlos Rivera | In Progress | Medium | 2023-10-22 | 2023-11-17 |  | 18 | Rebar | Plot 21, Riverside | 31772 | 29155.25 | In progress
C002 | Shopping Complex B | T311 | Electrical Wiring | Mike Adams | Completed | Low | 2023-03-01 | 2023-03-16 | 2023-03-16 | 100 | Copper Wires | Market Street | 18870.75 | 45587.64 | No issues
C004 | Warehouse D | T140 | Electrical Wiring | John Miller | Not Started | Low | 2024-03-15 | 2024-04-02 |  | 0 | Copper Wires | Industrial Park | 44545.91 | 0 | Not started
C001 | Residential Building A | T249 | Site Survey | Mike Adams | Completed | Low | 2024-08-20 | 2024-09-19 | 2024-09-19 | 100 | Concrete | Plot 21, Riverside | 41596.26 | 39125.04 | No issues
C001 | Residential Building A | T757 | Roofing | Mike Adams | Completed | Low | 2023-03-08 | 2023-03-31 | 2023-03-31 | 100 | Paint | Plot 21, Riverside | 16876.34 | 10416.56 | No issues
C001 | Residential Building A | T404 | Interior Painting | Emma White | Completed | High | 2023-05-22 | 2023-06-20 | 2023-06-20 | 100 | PVC Pipes | Plot 21, Riverside | 8704.75 | 5437.25 | No issues
C003 | Office Tower C | T180 | Electrical Wiring | Grace Allen | Completed | High | 2023-04-25 | 2023-05-07 | 2023-05-07 | 100 | Paint | Downtown Avenue | 19394.77 | 14703.22 | No issues
C004 | Warehouse D | T862 | Site Survey | Grace Allen | In Progress | Low | 2023-12-09 | 2024-01-08 |  | 29 | Concrete | Industrial Park | 27261.29 | 24120.63 | In progress
C003 | Office Tower C | T977 | Interior Painting | Dave Brown | Completed | High | 2024-08-13 | 2024-08-23 | 2024-08-23 | 100 | Steel Beams | Downtown Avenue | 43982.29 | 52157.76 | No issues
C002 | Shopping Complex B | T144 | Electrical Wiring | Dave Brown | In Progress | High | 2023-05-11 | 2023-05-27 |  | 63 | Paint | Market Street | 35552.89 | 48937.94 | In progress
C003 | Office Tower C | T712 | Electrical Wiring | Grace Allen | Completed | High | 2024-01-18 | 2024-01-25 | 2024-01-25 | 100 | Steel Beams | Downtown Avenue | 8059.19 | 8126.69 | No issues
C003 | Office Tower C | T243 | Electrical Wiring | Carlos Rivera | Completed | Low | 2024-07-21 | 2024-08-10 | 2024-08-10 | 100 | Rebar | Downtown Avenue | 13716.39 | 10876.33 | No issues
C002 | Shopping Complex B | T963 | Foundation Excavation | John Miller | Completed | Low | 2023-10-10 | 2023-11-04 | 2023-11-04 | 100 | PVC Pipes | Market Street | 26077.96 | 45303.08 | No issues
C001 | Residential Building A | T754 | Electrical Wiring | Grace Allen | In Progress | Medium | 2023-02-22 | 2023-03-17 |  | 86 | Rebar | Plot 21, Riverside | 6201.16 | 4304.77 | In progress
C003 | Office Tower C | T102 | Plumbing Installations | John Miller | Not Started | Low | 2023-07-23 | 2023-08-07 |  | 0 | Roofing Sheets | Downtown Avenue | 45461.01 | 0 | Not started
C003 | Office Tower C | T432 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2023-10-22 | 2023-11-14 |  | 0 | Concrete | Downtown Avenue | 11536.76 | 0 | Not started
C001 | Residential Building A | T222 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2024-03-07 | 2024-04-03 |  | 0 | PVC Pipes | Plot 21, Riverside | 44907.84 | 30897.34 | Not started
C002 | Shopping Complex B | T228 | Site Survey | Carlos Rivera | Not Started | High | 2023-07-07 | 2023-08-03 |  | 0 | Concrete | Market Street | 5744.8 | 0 | Not started
C002 | Shopping Complex B | T523 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2023-03-08 | 2023-03-31 |  | 82 | Concrete | Market Street | 6442.86 | 31099.04 | In progress
C001 | Residential Building A | T409 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2024-12-23 | 2025-01-17 |  | 0 | Steel Beams | Plot 21, Riverside | 22122.04 | 0 | Not started
C003 | Office Tower C | T877 | Plumbing Installations | Grace Allen | Completed | Medium | 2023-10-12 | 2023-11-06 | 2023-11-06 | 100 | Copper Wires | Downtown Avenue | 30575.5 | 23984.08 | No issues
C002 | Shopping Complex B | T663 | Electrical Wiring | Rachel Green | Completed | High | 2023-05-04 | 2023-05-28 | 2023-05-28 | 100 | Copper Wires | Market Street | 14539.89 | 39780.51 | No issues
C003 | Office Tower C | T231 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2023-11-28 | 2023-12-15 |  | 92 | Roofing Sheets | Downtown Avenue | 46945.15 | 30141.55 | In progress
C001 | Residential Building A | T251 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2023-10-28 | 2023-11-05 |  | 0 | Concrete | Plot 21, Riverside | 36712.67 | 37759.23 | Not started
C001 | Residential Building A | T238 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2024-12-06 | 2024-12-27 |  | 0 | Roofing Sheets | Plot 21, Riverside | 38774.09 | 39612.33 | Not started
C003 | Office Tower C | T941 | Steel Framework Setup | John Miller | Completed | Low | 2023-05-02 | 2023-05-31 | 2023-05-31 | 100 | Roofing Sheets | Downtown Avenue | 27141.48 | 17466.66 | No issues
C001 | Residential Building A | T293 | Foundation Excavation | Dave Brown | Blocked | Medium | 2023-05-04 | 2023-05-13 |  | 0 | Steel Beams | Plot 21, Riverside | 31236.25 | 24783.74 | Not started
C002 | Shopping Complex B | T248 | Foundation Excavation | Dave Brown | Not Started | Medium | 2024-11-06 | 2024-11-23 |  | 0 | Roofing Sheets | Market Street | 14066.03 | 0 | Not started
C001 | Residential Building A | T666 | Concrete Pouring | Grace Allen | Completed | Medium | 2024-02-10 | 2024-03-01 | 2024-03-01 | 100 | Roofing Sheets | Plot 21, Riverside | 13765.54 | 14581.98 | No issues
C002 | Shopping Complex B | T454 | Roofing | Grace Allen | Completed | Medium | 2024-11-22 | 2024-12-16 | 2024-12-16 | 100 | Roofing Sheets | Market Street | 11321.42 | 32590.52 | No issues
C003 | Office Tower C | T308 | Site Survey | Carlos Rivera | Not Started | Low | 2024-04-01 | 2024-04-09 |  | 0 | Cement | Downtown Avenue | 25538.66 | 0 | Not started
C002 | Shopping Complex B | T491 | Roofing | Sarah Johnson | In Progress | Medium | 2023-12-28 | 2024-01-21 |  | 1 | Cement | Market Street | 17208.23 | 40994.3 | In progress
C004 | Warehouse D | T636 | Roofing | Sarah Johnson | Completed | Medium | 2023-12-11 | 2023-12-19 | 2023-12-19 | 100 | PVC Pipes | Industrial Park | 33882.07 | 37499.44 | No issues
C002 | Shopping Complex B | T211 | Site Survey | Grace Allen | Blocked | Medium | 2023-01-26 | 2023-02-05 |  | 0 | PVC Pipes | Market Street | 48810.51 | 58851.18 | Not started
C001 | Residential Building A | T791 | Electrical Wiring | Rachel Green | Not Started | Medium | 2024-09-17 | 2024-09-24 |  | 0 | Paint | Plot 21, Riverside | 8982.07 | 0 | Not started
C002 | Shopping Complex B | T974 | Roofing | John Miller | Completed | Low | 2023-07-27 | 2023-08-17 | 2023-08-17 | 100 | PVC Pipes | Market Street | 24298.23 | 51325.63 | No issues
C002 | Shopping Complex B | T161 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-06-15 | 2024-07-08 |  | 0 | Copper Wires | Market Street | 47936.78 | 62636.06 | Not started
C004 | Warehouse D | T180 | Electrical Wiring | Dave Brown | Not Started | High | 2023-02-27 | 2023-03-21 |  | 0 | Rebar | Industrial Park | 28507.21 | 0 | Not started
C002 | Shopping Complex B | T498 | Site Survey | Carlos Rivera | Completed | High | 2024-04-22 | 2024-05-09 | 2024-05-09 | 100 | Cement | Market Street | 40222.23 | 65054.19 | No issues
C003 | Office Tower C | T271 | Concrete Pouring | Mike Adams | Completed | High | 2024-08-04 | 2024-08-24 | 2024-08-24 | 100 | Paint | Downtown Avenue | 13605.23 | 10395.97 | No issues
C001 | Residential Building A | T636 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-02-16 | 2024-03-12 |  | 0 | Copper Wires | Plot 21, Riverside | 15661.85 | 0 | Not started
C004 | Warehouse D | T555 | Electrical Wiring | Rachel Green | Blocked | Low | 2023-08-16 | 2023-09-13 |  | 0 | Roofing Sheets | Industrial Park | 9454.9 | 9619.71 | Not started
C003 | Office Tower C | T197 | Foundation Excavation | Sarah Johnson | Completed | Low | 2023-11-06 | 2023-12-03 | 2023-12-03 | 100 | Roofing Sheets | Downtown Avenue | 13279.38 | 15581.1 | No issues
C002 | Shopping Complex B | T100 | Foundation Excavation | Dave Brown | In Progress | Low | 2023-11-10 | 2023-11-19 |  | 82 | Copper Wires | Market Street | 11662.71 | 35265.11 | In progress
C001 | Residential Building A | T652 | Interior Painting | Carlos Rivera | Blocked | High | 2024-08-05 | 2024-08-29 |  | 0 | Steel Beams | Plot 21, Riverside | 43311.23 | 31776.1 | Not started
C001 | Residential Building A | T514 | Roofing | Mike Adams | In Progress | Low | 2023-06-28 | 2023-07-26 |  | 76 | Paint | Plot 21, Riverside | 7035.18 | 7197.91 | In progress
C003 | Office Tower C | T751 | Interior Painting | Rachel Green | In Progress | Low | 2024-09-14 | 2024-10-11 |  | 9 | Cement | Downtown Avenue | 47539.26 | 37766.63 | In progress
C002 | Shopping Complex B | T481 | Electrical Wiring | Sarah Johnson | Completed | High | 2024-04-11 | 2024-05-09 | 2024-05-09 | 100 | Concrete | Market Street | 6762.81 | 32480.22 | No issues
C004 | Warehouse D | T467 | Interior Painting | Grace Allen | In Progress | Low | 2023-02-24 | 2023-03-13 |  | 20 | Concrete | Industrial Park | 20650.2 | 17607.27 | In progress
C002 | Shopping Complex B | T603 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2023-02-14 | 2023-03-16 |  | 0 | Concrete | Market Street | 43336.72 | 0 | Not started
C004 | Warehouse D | T785 | Steel Framework Setup | Emma White | Blocked | Low | 2024-01-12 | 2024-01-29 |  | 0 | Steel Beams | Industrial Park | 12891.03 | 11092.86 | Not started
C002 | Shopping Complex B | T943 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-01-11 | 2024-02-07 |  | 27 | Paint | Market Street | 49385.47 | 80505.22 | In progress
C004 | Warehouse D | T928 | Roofing | Dave Brown | Not Started | Low | 2024-04-02 | 2024-04-23 |  | 0 | Cement | Industrial Park | 27730.05 | 0 | Not started
C004 | Warehouse D | T706 | Site Survey | Emma White | In Progress | Medium | 2024-08-25 | 2024-09-03 |  | 75 | PVC Pipes | Industrial Park | 37897.66 | 23164.21 | In progress
C004 | Warehouse D | T766 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-01-06 | 2023-02-01 |  | 0 | Copper Wires | Industrial Park | 35218.85 | 0 | Not started
C004 | Warehouse D | T611 | Concrete Pouring | Dave Brown | Not Started | High | 2024-11-05 | 2024-11-28 |  | 0 | Concrete | Industrial Park | 38971.55 | 0 | Not started
C004 | Warehouse D | T338 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2024-08-10 | 2024-08-23 |  | 0 | Steel Beams | Industrial Park | 6151.83 | 6278.3 | Not started
C004 | Warehouse D | T990 | Foundation Excavation | Mike Adams | Completed | Medium | 2023-02-05 | 2023-02-13 | 2023-02-13 | 100 | Rebar | Industrial Park | 49759.65 | 42711.89 | No issues
C002 | Shopping Complex B | T959 | Plumbing Installations | Sarah Johnson | In Progress | High | 2023-08-14 | 2023-08-26 |  | 95 | Roofing Sheets | Market Street | 27333.18 | 43328.78 | In progress
C002 | Shopping Complex B | T541 | Foundation Excavation | Carlos Rivera | Not Started | High | 2024-03-09 | 2024-03-20 |  | 0 | Roofing Sheets | Market Street | 45120.03 | 0 | Not started
C001 | Residential Building A | T288 | Plumbing Installations | Emma White | In Progress | Medium | 2024-09-13 | 2024-09-25 |  | 36 | Roofing Sheets | Plot 21, Riverside | 20044.58 | 15483.12 | In progress
C001 | Residential Building A | T664 | Foundation Excavation | Mike Adams | Not Started | Low | 2023-02-17 | 2023-03-03 |  | 0 | Rebar | Plot 21, Riverside | 31826.67 | 0 | Not started
C002 | Shopping Complex B | T560 | Plumbing Installations | Emma White | Completed | Low | 2024-01-15 | 2024-02-13 | 2024-02-13 | 100 | Concrete | Market Street | 10260.39 | 33726.96 | No issues
C004 | Warehouse D | T397 | Concrete Pouring | Dave Brown | Completed | High | 2023-11-18 | 2023-12-03 | 2023-12-03 | 100 | PVC Pipes | Industrial Park | 23324.81 | 24535.55 | No issues
C003 | Office Tower C | T215 | Electrical Wiring | Rachel Green | Blocked | High | 2023-06-17 | 2023-07-13 |  | 0 | Copper Wires | Downtown Avenue | 43646.3 | 39974.26 | Not started
C004 | Warehouse D | T509 | Plumbing Installations | Mike Adams | In Progress | High | 2023-08-07 | 2023-09-06 |  | 5 | Steel Beams | Industrial Park | 17018.87 | 14487.36 | In progress
C002 | Shopping Complex B | T635 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-10-26 | 2024-11-16 |  | 0 | Copper Wires | Market Street | 41012 | 73537.71 | Not started
C004 | Warehouse D | T755 | Roofing | John Miller | Not Started | High | 2023-11-20 | 2023-12-05 |  | 0 | Cement | Industrial Park | 14607.76 | 0 | Not started
C004 | Warehouse D | T745 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-02-17 | 2024-03-12 |  | 77 | Copper Wires | Industrial Park | 30219.49 | 25515.36 | In progress
C001 | Residential Building A | T104 | Roofing | Dave Brown | Completed | High | 2023-10-17 | 2023-11-09 | 2023-11-09 | 100 | PVC Pipes | Plot 21, Riverside | 40950.12 | 33259.43 | No issues
C003 | Office Tower C | T916 | Interior Painting | Emma White | Not Started | Medium | 2023-02-20 | 2023-02-28 |  | 0 | PVC Pipes | Downtown Avenue | 28226.31 | 0 | Not started
C003 | Office Tower C | T538 | Interior Painting | Emma White | Completed | Medium | 2024-05-15 | 2024-06-05 | 2024-06-05 | 100 | Roofing Sheets | Downtown Avenue | 46930.29 | 45149.73 | No issues
C003 | Office Tower C | T596 | Foundation Excavation | Sarah Johnson | Not Started | High | 2024-09-08 | 2024-09-18 |  | 0 | Rebar | Downtown Avenue | 39393.33 | 0 | Not started
C001 | Residential Building A | T738 | Site Survey | Mike Adams | Completed | Medium | 2024-04-13 | 2024-05-06 | 2024-05-06 | 100 | Cement | Plot 21, Riverside | 9520.67 | 11190.87 | No issues
C002 | Shopping Complex B | T187 | Concrete Pouring | Grace Allen | Not Started | High | 2023-09-27 | 2023-10-05 |  | 0 | Paint | Market Street | 13933.6 | 0 | Not started
C002 | Shopping Complex B | T397 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-05-19 | 2024-06-02 |  | 0 | Steel Beams | Market Street | 24922.22 | 49513.76 | Not started
C003 | Office Tower C | T284 | Concrete Pouring | Sarah Johnson | In Progress | High | 2023-08-17 | 2023-09-06 |  | 58 | Steel Beams | Downtown Avenue | 12958.67 | 11507.61 | In progress
C003 | Office Tower C | T458 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2023-05-09 | 2023-05-30 | 2023-05-30 | 100 | Rebar | Downtown Avenue | 45666.42 | 50414.57 | No issues
C001 | Residential Building A | T697 | Electrical Wiring | Carlos Rivera | Completed | Low | 2024-06-02 | 2024-06-09 | 2024-06-09 | 100 | Concrete | Plot 21, Riverside | 33067.41 | 31756.81 | No issues
C003 | Office Tower C | T373 | Foundation Excavation | John Miller | Blocked | Low | 2024-08-26 | 2024-09-15 |  | 0 | Rebar | Downtown Avenue | 33629.55 | 37921.06 | Not started
C001 | Residential Building A | T119 | Interior Painting | Carlos Rivera | Not Started | Medium | 2024-11-09 | 2024-11-30 |  | 0 | Paint | Plot 21, Riverside | 44467.63 | 0 | Not started
C004 | Warehouse D | T853 | Foundation Excavation | Sarah Johnson | Not Started | High | 2024-12-27 | 2025-01-11 |  | 0 | Rebar | Industrial Park | 49005.57 | 0 | Not started
C004 | Warehouse D | T610 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2023-08-15 | 2023-08-31 |  | 0 | Steel Beams | Industrial Park | 18926.42 | 20071.34 | Not started
C002 | Shopping Complex B | T504 | Site Survey | Emma White | Blocked | High | 2024-05-01 | 2024-05-21 |  | 0 | PVC Pipes | Market Street | 49984.36 | 84996.18 | Not started
C002 | Shopping Complex B | T736 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-02-28 | 2023-03-23 | 2023-03-23 | 100 | Paint | Market Street | 9178.34 | 32332.86 | No issues
C003 | Office Tower C | T834 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-10-24 | 2023-11-08 | 2023-11-08 | 100 | Paint | Downtown Avenue | 28900.87 | 19615.58 | No issues
C002 | Shopping Complex B | T861 | Site Survey | Emma White | Blocked | High | 2023-10-16 | 2023-11-07 |  | 0 | Paint | Market Street | 5670.17 | 30727.86 | Not started
C001 | Residential Building A | T237 | Interior Painting | John Miller | In Progress | High | 2024-03-03 | 2024-03-26 |  | 23 | Cement | Plot 21, Riverside | 49935.05 | 50192.35 | In progress
C002 | Shopping Complex B | T456 | Concrete Pouring | Emma White | Completed | Low | 2024-03-19 | 2024-04-05 | 2024-04-05 | 100 | Rebar | Market Street | 8151.35 | 32985.04 | No issues
C003 | Office Tower C | T262 | Interior Painting | Mike Adams | In Progress | Medium | 2023-03-17 | 2023-03-28 |  | 67 | Paint | Downtown Avenue | 25022.56 | 23982.17 | In progress
C003 | Office Tower C | T299 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2023-02-25 | 2023-03-18 |  | 0 | Copper Wires | Downtown Avenue | 39752.17 | 0 | Not started
C002 | Shopping Complex B | T921 | Site Survey | John Miller | Completed | Medium | 2024-02-24 | 2024-03-06 | 2024-03-06 | 100 | Rebar | Market Street | 43717.27 | 67361.44 | No issues
C003 | Office Tower C | T499 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2023-11-11 | 2023-12-04 |  | 0 | Roofing Sheets | Downtown Avenue | 16523.31 | 0 | Not started
C002 | Shopping Complex B | T338 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-05-25 | 2023-06-20 |  | 0 | Rebar | Market Street | 47345.37 | 80259.27 | Not started
C002 | Shopping Complex B | T684 | Foundation Excavation | Grace Allen | Not Started | Low | 2023-10-27 | 2023-11-04 |  | 0 | Copper Wires | Market Street | 47625.57 | 0 | Not started
C002 | Shopping Complex B | T897 | Electrical Wiring | Carlos Rivera | In Progress | Medium | 2024-10-17 | 2024-10-26 |  | 40 | Concrete | Market Street | 5849.05 | 30073.04 | In progress
C004 | Warehouse D | T469 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-12-03 | 2024-12-29 |  | 0 | PVC Pipes | Industrial Park | 20353.78 | 0 | Not started
C001 | Residential Building A | T266 | Interior Painting | Grace Allen | Blocked | Medium | 2023-03-02 | 2023-03-24 |  | 0 | Cement | Plot 21, Riverside | 31514.31 | 35310.58 | Not started
C001 | Residential Building A | T527 | Site Survey | Mike Adams | In Progress | High | 2024-08-18 | 2024-09-10 |  | 19 | PVC Pipes | Plot 21, Riverside | 18745.15 | 16209.34 | In progress
C004 | Warehouse D | T345 | Plumbing Installations | John Miller | In Progress | Low | 2023-12-19 | 2024-01-04 |  | 40 | Copper Wires | Industrial Park | 31675.95 | 31032.33 | In progress
C002 | Shopping Complex B | T912 | Roofing | Carlos Rivera | In Progress | Low | 2023-01-21 | 2023-02-16 |  | 28 | Paint | Market Street | 16509.94 | 37358.16 | In progress
C004 | Warehouse D | T814 | Foundation Excavation | Rachel Green | Completed | Medium | 2023-04-15 | 2023-05-01 | 2023-05-01 | 100 | Copper Wires | Industrial Park | 26371.3 | 24733.56 | No issues
C003 | Office Tower C | T992 | Concrete Pouring | Carlos Rivera | Blocked | High | 2023-03-01 | 2023-03-15 |  | 0 | Steel Beams | Downtown Avenue | 11205.41 | 7335.85 | Not started
C001 | Residential Building A | T416 | Foundation Excavation | Rachel Green | Not Started | Medium | 2024-10-06 | 2024-10-16 |  | 0 | Paint | Plot 21, Riverside | 34997.7 | 0 | Not started
C002 | Shopping Complex B | T710 | Plumbing Installations | John Miller | Not Started | High | 2024-05-25 | 2024-06-20 |  | 0 | Concrete | Market Street | 27820.42 | 0 | Not started
C004 | Warehouse D | T932 | Steel Framework Setup | Rachel Green | In Progress | Medium | 2023-04-03 | 2023-04-15 |  | 28 | Steel Beams | Industrial Park | 32200.44 | 21426.15 | In progress
C001 | Residential Building A | T395 | Site Survey | Carlos Rivera | Not Started | Medium | 2024-06-21 | 2024-07-11 |  | 0 | Paint | Plot 21, Riverside | 44573.04 | 0 | Not started
C002 | Shopping Complex B | T380 | Site Survey | Carlos Rivera | Blocked | Low | 2024-11-22 | 2024-12-03 |  | 0 | Copper Wires | Market Street | 8167.74 | 30444.97 | Not started
C004 | Warehouse D | T282 | Interior Painting | Dave Brown | Blocked | Medium | 2023-01-28 | 2023-02-05 |  | 0 | Cement | Industrial Park | 44682.61 | 42271.74 | Not started
C001 | Residential Building A | T215 | Plumbing Installations | Carlos Rivera | Completed | High | 2024-10-15 | 2024-10-30 | 2024-10-30 | 100 | Steel Beams | Plot 21, Riverside | 28685.83 | 19864.98 | No issues
C002 | Shopping Complex B | T877 | Roofing | Sarah Johnson | Not Started | Medium | 2024-08-20 | 2024-08-30 |  | 0 | Roofing Sheets | Market Street | 12347.13 | 0 | Not started
C004 | Warehouse D | T109 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2024-12-20 | 2025-01-07 |  | 0 | Paint | Industrial Park | 34223.82 | 29362.45 | Not started
C002 | Shopping Complex B | T847 | Electrical Wiring | Rachel Green | Completed | Medium | 2023-02-06 | 2023-02-21 | 2023-02-21 | 100 | Steel Beams | Market Street | 38037.56 | 53537.54 | No issues
C002 | Shopping Complex B | T960 | Plumbing Installations | Emma White | In Progress | High | 2024-05-26 | 2024-06-17 |  | 81 | Copper Wires | Market Street | 20525.15 | 47735.48 | In progress
C004 | Warehouse D | T975 | Steel Framework Setup | Grace Allen | Not Started | Low | 2023-08-17 | 2023-08-27 |  | 0 | PVC Pipes | Industrial Park | 39511.02 | 0 | Not started
C001 | Residential Building A | T913 | Electrical Wiring | Dave Brown | Completed | Low | 2023-11-10 | 2023-12-04 | 2023-12-04 | 100 | PVC Pipes | Plot 21, Riverside | 45300.91 | 31075.37 | No issues
C003 | Office Tower C | T472 | Roofing | Grace Allen | Not Started | High | 2023-05-25 | 2023-06-17 |  | 0 | PVC Pipes | Downtown Avenue | 39612.39 | 0 | Not started
C004 | Warehouse D | T924 | Concrete Pouring | John Miller | Completed | Low | 2023-04-15 | 2023-05-08 | 2023-05-08 | 100 | Rebar | Industrial Park | 12400.62 | 13154.3 | No issues
C003 | Office Tower C | T780 | Electrical Wiring | Mike Adams | Completed | Low | 2024-01-16 | 2024-02-05 | 2024-02-05 | 100 | Copper Wires | Downtown Avenue | 31352.97 | 37267.81 | No issues
C003 | Office Tower C | T556 | Roofing | Dave Brown | Completed | Low | 2024-02-10 | 2024-03-10 | 2024-03-10 | 100 | Rebar | Downtown Avenue | 42938.35 | 36969.19 | No issues
C003 | Office Tower C | T512 | Electrical Wiring | Rachel Green | Completed | High | 2024-06-28 | 2024-07-14 | 2024-07-14 | 100 | Concrete | Downtown Avenue | 42301.31 | 40342.81 | No issues
C004 | Warehouse D | T528 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-04-07 | 2024-04-20 | 2024-04-20 | 100 | Rebar | Industrial Park | 20952.07 | 14637.82 | No issues
C002 | Shopping Complex B | T184 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-11-22 | 2023-12-14 |  | 76 | Concrete | Market Street | 25663.74 | 54986.79 | In progress
C003 | Office Tower C | T103 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-12-15 | 2023-12-25 |  | 0 | Cement | Downtown Avenue | 14135.98 | 14056.33 | Not started
C002 | Shopping Complex B | T488 | Foundation Excavation | Emma White | In Progress | Low | 2024-10-28 | 2024-11-22 |  | 93 | Roofing Sheets | Market Street | 35584.38 | 47221.27 | In progress
C002 | Shopping Complex B | T903 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2024-01-17 | 2024-02-10 | 2024-02-10 | 100 | Cement | Market Street | 16611.74 | 42020.86 | No issues
C004 | Warehouse D | T380 | Interior Painting | Sarah Johnson | Blocked | Medium | 2024-01-14 | 2024-01-21 |  | 0 | Cement | Industrial Park | 32386.54 | 37453.36 | Not started
C004 | Warehouse D | T135 | Electrical Wiring | Emma White | Completed | Low | 2023-03-21 | 2023-04-16 | 2023-04-16 | 100 | Steel Beams | Industrial Park | 13013.89 | 13047.14 | No issues
C001 | Residential Building A | T546 | Site Survey | Rachel Green | In Progress | Medium | 2024-04-10 | 2024-04-20 |  | 98 | Concrete | Plot 21, Riverside | 43242.63 | 45374 | In progress
C002 | Shopping Complex B | T317 | Plumbing Installations | Dave Brown | Completed | Medium | 2023-09-20 | 2023-10-09 | 2023-10-09 | 100 | Paint | Market Street | 24980.81 | 43049.7 | No issues
C001 | Residential Building A | T621 | Interior Painting | Sarah Johnson | Completed | Medium | 2024-06-02 | 2024-06-18 | 2024-06-18 | 100 | Steel Beams | Plot 21, Riverside | 27516.09 | 32137.78 | No issues
C003 | Office Tower C | T270 | Site Survey | John Miller | Completed | Low | 2023-11-25 | 2023-12-22 | 2023-12-22 | 100 | Roofing Sheets | Downtown Avenue | 44094.35 | 39566.07 | No issues
C004 | Warehouse D | T293 | Concrete Pouring | Mike Adams | In Progress | Low | 2024-08-08 | 2024-09-05 |  | 25 | Concrete | Industrial Park | 46289.59 | 53214.86 | In progress
C001 | Residential Building A | T332 | Interior Painting | Grace Allen | In Progress | Medium | 2023-10-07 | 2023-10-29 |  | 97 | Paint | Plot 21, Riverside | 43743.79 | 30439.55 | In progress
C002 | Shopping Complex B | T216 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2024-11-25 | 2024-12-23 |  | 0 | Paint | Market Street | 17189.95 | 41924.83 | In progress
C004 | Warehouse D | T667 | Plumbing Installations | Emma White | In Progress | Low | 2023-10-27 | 2023-11-23 |  | 27 | Paint | Industrial Park | 48967.89 | 54862.53 | In progress
C003 | Office Tower C | T173 | Interior Painting | John Miller | Not Started | Medium | 2023-07-13 | 2023-08-02 |  | 0 | Concrete | Downtown Avenue | 11489.26 | 0 | Not started
C003 | Office Tower C | T350 | Concrete Pouring | John Miller | Completed | Low | 2023-03-08 | 2023-03-19 | 2023-03-19 | 100 | Concrete | Downtown Avenue | 44817.45 | 49407.58 | No issues
C003 | Office Tower C | T906 | Plumbing Installations | Dave Brown | Not Started | Low | 2023-10-13 | 2023-10-21 |  | 0 | Paint | Downtown Avenue | 13748.13 | 0 | Not started
C004 | Warehouse D | T959 | Plumbing Installations | Grace Allen | Not Started | High | 2023-01-25 | 2023-02-24 |  | 0 | Rebar | Industrial Park | 38434.94 | 0 | Not started
C004 | Warehouse D | T241 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-05-01 | 2023-05-11 |  | 0 | Steel Beams | Industrial Park | 7227.5 | 6327.31 | Not started
C002 | Shopping Complex B | T612 | Plumbing Installations | Rachel Green | Completed | Low | 2023-05-08 | 2023-05-15 | 2023-05-15 | 100 | Copper Wires | Market Street | 30662.23 | 44333.95 | No issues
C003 | Office Tower C | T261 | Interior Painting | John Miller | Blocked | Low | 2024-05-07 | 2024-05-16 |  | 0 | PVC Pipes | Downtown Avenue | 45939.86 | 33776.98 | Not started
C002 | Shopping Complex B | T267 | Concrete Pouring | Dave Brown | Blocked | Low | 2023-12-24 | 2024-01-17 |  | 0 | Steel Beams | Market Street | 11411.29 | 37509.34 | Not started
C003 | Office Tower C | T467 | Plumbing Installations | Rachel Green | In Progress | Low | 2024-04-06 | 2024-04-14 |  | 19 | Copper Wires | Downtown Avenue | 22991.86 | 22211.88 | In progress
C003 | Office Tower C | T985 | Foundation Excavation | Rachel Green | Completed | High | 2023-06-03 | 2023-06-29 | 2023-06-29 | 100 | Rebar | Downtown Avenue | 16639.09 | 16328.71 | No issues
C004 | Warehouse D | T429 | Electrical Wiring | John Miller | Blocked | High | 2024-04-09 | 2024-05-04 |  | 0 | PVC Pipes | Industrial Park | 16972.36 | 19296.8 | Not started
C003 | Office Tower C | T505 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2023-11-19 | 2023-12-02 | 2023-12-02 | 100 | Steel Beams | Downtown Avenue | 47511.11 | 30870.31 | No issues
C002 | Shopping Complex B | T389 | Concrete Pouring | Emma White | Blocked | Medium | 2023-11-26 | 2023-12-19 |  | 0 | PVC Pipes | Market Street | 46469.01 | 63740.78 | Not started
C003 | Office Tower C | T543 | Interior Painting | John Miller | Blocked | Low | 2024-06-21 | 2024-06-28 |  | 0 | PVC Pipes | Downtown Avenue | 21533.9 | 24170.7 | Not started
C001 | Residential Building A | T516 | Concrete Pouring | Dave Brown | Completed | Low | 2023-11-23 | 2023-12-08 | 2023-12-08 | 100 | Steel Beams | Plot 21, Riverside | 34545.49 | 28383.19 | No issues
C001 | Residential Building A | T582 | Plumbing Installations | Dave Brown | Not Started | Medium | 2024-03-08 | 2024-03-29 |  | 0 | Roofing Sheets | Plot 21, Riverside | 36972.55 | 0 | Not started
C001 | Residential Building A | T695 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-04-16 | 2023-04-30 |  | 0 | Paint | Plot 21, Riverside | 36451.41 | 27263.99 | Not started
C002 | Shopping Complex B | T769 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2024-10-16 | 2024-11-02 |  | 0 | Roofing Sheets | Market Street | 48606.92 | 0 | Not started
C004 | Warehouse D | T677 | Interior Painting | Carlos Rivera | Completed | High | 2024-06-10 | 2024-07-07 | 2024-07-07 | 100 | Concrete | Industrial Park | 32636 | 28313.53 | No issues
C004 | Warehouse D | T601 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-05-15 | 2024-06-07 |  | 0 | Roofing Sheets | Industrial Park | 43761.67 | 0 | Not started
C002 | Shopping Complex B | T392 | Foundation Excavation | Emma White | In Progress | High | 2023-02-28 | 2023-03-25 |  | 42 | Paint | Market Street | 38207.03 | 55483.29 | In progress
C004 | Warehouse D | T881 | Concrete Pouring | Mike Adams | Not Started | Medium | 2023-09-27 | 2023-10-07 |  | 0 | Cement | Industrial Park | 7333.53 | 0 | Not started
C004 | Warehouse D | T172 | Electrical Wiring | Mike Adams | Not Started | High | 2023-01-03 | 2023-02-01 |  | 0 | Roofing Sheets | Industrial Park | 48332.17 | 0 | Not started
C002 | Shopping Complex B | T788 | Plumbing Installations | Mike Adams | In Progress | High | 2024-06-04 | 2024-06-14 |  | 98 | Concrete | Market Street | 32776.01 | 58835.82 | In progress
C001 | Residential Building A | T667 | Plumbing Installations | John Miller | In Progress | Low | 2024-01-25 | 2024-02-21 |  | 59 | Cement | Plot 21, Riverside | 19180.99 | 13960.63 | In progress
C002 | Shopping Complex B | T197 | Site Survey | Rachel Green | In Progress | High | 2023-12-08 | 2023-12-20 |  | 25 | Cement | Market Street | 33877.31 | 63026.75 | In progress
C002 | Shopping Complex B | T499 | Site Survey | Carlos Rivera | Completed | High | 2023-09-04 | 2023-09-24 | 2023-09-24 | 100 | Copper Wires | Market Street | 20659.74 | 40847.64 | No issues
C003 | Office Tower C | T953 | Steel Framework Setup | John Miller | In Progress | High | 2024-11-24 | 2024-12-15 |  | 51 | Cement | Downtown Avenue | 13896.91 | 13497.66 | In progress
C002 | Shopping Complex B | T217 | Plumbing Installations | Emma White | Blocked | High | 2024-07-06 | 2024-07-14 |  | 0 | Concrete | Market Street | 6153.09 | 32785.82 | Not started
C004 | Warehouse D | T299 | Steel Framework Setup | Sarah Johnson | Completed | High | 2024-11-28 | 2024-12-08 | 2024-12-08 | 100 | Concrete | Industrial Park | 30344.84 | 33108.37 | No issues
C002 | Shopping Complex B | T979 | Plumbing Installations | Emma White | Not Started | Medium | 2023-04-16 | 2023-05-02 |  | 0 | PVC Pipes | Market Street | 10309.72 | 0 | Not started
C003 | Office Tower C | T544 | Foundation Excavation | Dave Brown | In Progress | High | 2024-04-22 | 2024-05-12 |  | 36 | Paint | Downtown Avenue | 13672.6 | 11267.02 | In progress
C003 | Office Tower C | T741 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2024-05-25 | 2024-06-20 | 2024-06-20 | 100 | PVC Pipes | Downtown Avenue | 5455.89 | 4016.76 | No issues
C001 | Residential Building A | T339 | Concrete Pouring | Emma White | Blocked | Medium | 2023-03-24 | 2023-04-05 |  | 0 | Copper Wires | Plot 21, Riverside | 35053.37 | 28042.08 | Not started
C002 | Shopping Complex B | T642 | Plumbing Installations | Grace Allen | Not Started | High | 2024-11-26 | 2024-12-13 |  | 0 | Roofing Sheets | Market Street | 48952.62 | 0 | Not started
C001 | Residential Building A | T720 | Concrete Pouring | Dave Brown | In Progress | Medium | 2023-07-02 | 2023-07-12 |  | 30 | Cement | Plot 21, Riverside | 45254.46 | 51178.73 | In progress
C001 | Residential Building A | T870 | Steel Framework Setup | Rachel Green | Not Started | High | 2023-05-17 | 2023-05-30 |  | 0 | Cement | Plot 21, Riverside | 5400.82 | 0 | Not started
C004 | Warehouse D | T951 | Roofing | Rachel Green | Completed | Medium | 2024-04-07 | 2024-04-20 | 2024-04-20 | 100 | Rebar | Industrial Park | 47771.74 | 35808.43 | No issues
C001 | Residential Building A | T165 | Electrical Wiring | Mike Adams | Not Started | Low | 2023-12-08 | 2023-12-28 |  | 0 | Rebar | Plot 21, Riverside | 17429.26 | 0 | Not started
C004 | Warehouse D | T112 | Electrical Wiring | Emma White | Not Started | High | 2024-06-03 | 2024-06-25 |  | 0 | Rebar | Industrial Park | 46641.42 | 0 | Not started
C002 | Shopping Complex B | T749 | Roofing | Dave Brown | Not Started | Low | 2023-06-23 | 2023-07-20 |  | 0 | PVC Pipes | Market Street | 25182.27 | 0 | Not started
C001 | Residential Building A | T948 | Foundation Excavation | Mike Adams | Not Started | Medium | 2024-11-17 | 2024-11-30 |  | 0 | PVC Pipes | Plot 21, Riverside | 39047.68 | 0 | Not started
C003 | Office Tower C | T456 | Foundation Excavation | Emma White | Completed | High | 2024-06-17 | 2024-06-30 | 2024-06-30 | 100 | PVC Pipes | Downtown Avenue | 16955.18 | 17021.11 | No issues
C002 | Shopping Complex B | T182 | Site Survey | Rachel Green | Blocked | Medium | 2023-08-05 | 2023-08-18 |  | 0 | Steel Beams | Market Street | 44886.32 | 56571.87 | Not started
C001 | Residential Building A | T481 | Site Survey | Dave Brown | Blocked | Medium | 2023-07-23 | 2023-07-30 |  | 0 | Cement | Plot 21, Riverside | 24943.3 | 27840.46 | Not started
C001 | Residential Building A | T789 | Steel Framework Setup | Rachel Green | In Progress | Low | 2023-12-13 | 2023-12-30 |  | 5 | PVC Pipes | Plot 21, Riverside | 34478.65 | 28441.82 | In progress
C002 | Shopping Complex B | T973 | Foundation Excavation | Grace Allen | Completed | Medium | 2024-10-21 | 2024-10-30 | 2024-10-30 | 100 | Copper Wires | Market Street | 7522.79 | 30200.72 | No issues
C003 | Office Tower C | T885 | Site Survey | Rachel Green | Blocked | Medium | 2023-06-20 | 2023-07-07 |  | 0 | Copper Wires | Downtown Avenue | 38574.66 | 25291.71 | Not started
C004 | Warehouse D | T603 | Electrical Wiring | Grace Allen | Not Started | High | 2023-07-10 | 2023-07-18 |  | 0 | Paint | Industrial Park | 38028.35 | 0 | Not started
C002 | Shopping Complex B | T560 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2023-11-20 | 2023-12-05 |  | 0 | Paint | Market Street | 34194.61 | 0 | Not started
C002 | Shopping Complex B | T740 | Interior Painting | Sarah Johnson | Not Started | Low | 2023-11-14 | 2023-12-01 |  | 0 | PVC Pipes | Market Street | 26168.77 | 0 | Not started
C001 | Residential Building A | T529 | Foundation Excavation | John Miller | Completed | High | 2023-08-07 | 2023-08-19 | 2023-08-19 | 100 | Copper Wires | Plot 21, Riverside | 8168.83 | 8702.78 | No issues
C003 | Office Tower C | T657 | Interior Painting | Rachel Green | Completed | Medium | 2023-06-02 | 2023-06-14 | 2023-06-14 | 100 | PVC Pipes | Downtown Avenue | 27052.51 | 29153.29 | No issues
C004 | Warehouse D | T826 | Foundation Excavation | Rachel Green | Blocked | Low | 2024-07-07 | 2024-08-04 |  | 0 | Concrete | Industrial Park | 42720.74 | 36674.94 | Not started
C004 | Warehouse D | T201 | Site Survey | Carlos Rivera | Not Started | Low | 2023-03-16 | 2023-04-06 |  | 0 | Cement | Industrial Park | 31120.65 | 0 | Not started
C003 | Office Tower C | T507 | Electrical Wiring | Dave Brown | Completed | Low | 2024-04-24 | 2024-05-13 | 2024-05-13 | 100 | Steel Beams | Downtown Avenue | 46685.87 | 42624.61 | No issues
C002 | Shopping Complex B | T886 | Foundation Excavation | Rachel Green | Not Started | Medium | 2024-08-13 | 2024-08-24 |  | 0 | Copper Wires | Market Street | 11048.97 | 0 | Not started
C001 | Residential Building A | T653 | Interior Painting | Carlos Rivera | In Progress | Medium | 2024-08-18 | 2024-09-17 |  | 48 | Rebar | Plot 21, Riverside | 47758.9 | 30020.16 | In progress
C002 | Shopping Complex B | T403 | Concrete Pouring | Emma White | In Progress | High | 2023-02-04 | 2023-02-13 |  | 2 | Rebar | Market Street | 34244.63 | 53671.52 | In progress
C004 | Warehouse D | T810 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-02-14 | 2024-03-02 |  | 59 | Copper Wires | Industrial Park | 32312.16 | 20575.91 | In progress
C002 | Shopping Complex B | T218 | Concrete Pouring | Grace Allen | Blocked | High | 2024-06-27 | 2024-07-14 |  | 0 | Cement | Market Street | 49786.46 | 63528.78 | Not started
C001 | Residential Building A | T219 | Interior Painting | Mike Adams | Not Started | Low | 2024-06-18 | 2024-07-09 |  | 0 | Rebar | Plot 21, Riverside | 43864.26 | 0 | Not started
C001 | Residential Building A | T758 | Electrical Wiring | Emma White | Completed | High | 2023-08-12 | 2023-09-08 | 2023-09-08 | 100 | Cement | Plot 21, Riverside | 13738.43 | 16298.58 | No issues
C004 | Warehouse D | T857 | Plumbing Installations | Carlos Rivera | In Progress | High | 2023-08-12 | 2023-09-04 |  | 56 | Paint | Industrial Park | 11064.93 | 7933.87 | In progress
C003 | Office Tower C | T449 | Concrete Pouring | Emma White | In Progress | High | 2023-04-26 | 2023-05-05 |  | 72 | Concrete | Downtown Avenue | 36918.59 | 33749.7 | In progress
C003 | Office Tower C | T211 | Roofing | John Miller | Not Started | High | 2024-10-15 | 2024-10-25 |  | 0 | Steel Beams | Downtown Avenue | 32178.24 | 0 | Not started
C003 | Office Tower C | T448 | Roofing | Emma White | In Progress | High | 2023-07-01 | 2023-07-09 |  | 73 | Paint | Downtown Avenue | 29924.37 | 21577.66 | In progress
C002 | Shopping Complex B | T566 | Plumbing Installations | Dave Brown | Not Started | High | 2023-01-10 | 2023-02-09 |  | 0 | Copper Wires | Market Street | 25119.87 | 0 | Not started
C004 | Warehouse D | T455 | Interior Painting | Dave Brown | Not Started | Medium | 2024-02-01 | 2024-02-08 |  | 0 | Paint | Industrial Park | 6086.81 | 0 | Not started
C004 | Warehouse D | T696 | Plumbing Installations | John Miller | In Progress | Medium | 2023-10-24 | 2023-11-18 |  | 92 | Roofing Sheets | Industrial Park | 44338.88 | 33051.64 | In progress
C003 | Office Tower C | T143 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-03-22 | 2024-04-19 |  | 73 | Copper Wires | Downtown Avenue | 31708.85 | 32659.04 | In progress
C002 | Shopping Complex B | T970 | Roofing | Rachel Green | In Progress | Medium | 2023-12-12 | 2023-12-24 |  | 23 | Copper Wires | Market Street | 13796.95 | 38531.46 | In progress
C002 | Shopping Complex B | T408 | Foundation Excavation | Rachel Green | Not Started | Low | 2023-12-15 | 2024-01-05 |  | 0 | Cement | Market Street | 39233.92 | 0 | Not started
C004 | Warehouse D | T397 | Plumbing Installations | Rachel Green | Not Started | Low | 2024-03-04 | 2024-03-24 |  | 0 | Steel Beams | Industrial Park | 25284.72 | 0 | Not started
C004 | Warehouse D | T118 | Interior Painting | John Miller | In Progress | High | 2023-04-12 | 2023-04-25 |  | 69 | Paint | Industrial Park | 48883.34 | 56813.66 | In progress
C002 | Shopping Complex B | T680 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2024-09-12 | 2024-10-04 |  | 7 | PVC Pipes | Market Street | 25090.81 | 43341.81 | In progress
C001 | Residential Building A | T444 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2023-12-21 | 2024-01-10 |  | 0 | Paint | Plot 21, Riverside | 48238.31 | 0 | Not started
C001 | Residential Building A | T140 | Site Survey | Grace Allen | Completed | High | 2023-01-27 | 2023-02-05 | 2023-02-05 | 100 | Copper Wires | Plot 21, Riverside | 42681.56 | 49538.04 | No issues
C001 | Residential Building A | T512 | Roofing | Rachel Green | Completed | Low | 2023-08-15 | 2023-09-14 | 2023-09-14 | 100 | Copper Wires | Plot 21, Riverside | 8840.48 | 9150.53 | No issues
C002 | Shopping Complex B | T643 | Electrical Wiring | Dave Brown | Blocked | High | 2024-04-06 | 2024-04-13 |  | 0 | Copper Wires | Market Street | 44878.02 | 54278.6 | Not started
C002 | Shopping Complex B | T662 | Site Survey | Dave Brown | Not Started | Medium | 2024-12-16 | 2024-12-31 |  | 0 | Roofing Sheets | Market Street | 21950.5 | 0 | Not started
C001 | Residential Building A | T782 | Plumbing Installations | Mike Adams | Not Started | Low | 2024-02-22 | 2024-03-20 |  | 0 | Roofing Sheets | Plot 21, Riverside | 24566.68 | 0 | Not started
C004 | Warehouse D | T864 | Interior Painting | Dave Brown | Not Started | Medium | 2023-12-09 | 2023-12-16 |  | 0 | PVC Pipes | Industrial Park | 15072.96 | 0 | Not started
C003 | Office Tower C | T688 | Interior Painting | Grace Allen | Completed | Medium | 2023-11-01 | 2023-11-30 | 2023-11-30 | 100 | PVC Pipes | Downtown Avenue | 6023.32 | 4794.4 | No issues
C004 | Warehouse D | T637 | Interior Painting | Grace Allen | Not Started | Low | 2023-02-26 | 2023-03-28 |  | 0 | Rebar | Industrial Park | 7359.39 | 0 | Not started
C001 | Residential Building A | T280 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-04-14 | 2024-05-13 |  | 8 | Roofing Sheets | Plot 21, Riverside | 35739.9 | 32656.41 | In progress
C003 | Office Tower C | T455 | Site Survey | John Miller | In Progress | Low | 2023-09-17 | 2023-10-09 |  | 66 | PVC Pipes | Downtown Avenue | 46741.51 | 44688.74 | In progress
C003 | Office Tower C | T478 | Interior Painting | Mike Adams | Blocked | Low | 2023-07-27 | 2023-08-04 |  | 0 | Concrete | Downtown Avenue | 43138.77 | 42112.59 | Not started
C002 | Shopping Complex B | T989 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2023-01-06 | 2023-01-13 |  | 56 | Cement | Market Street | 33750.28 | 62728.14 | In progress
C003 | Office Tower C | T347 | Steel Framework Setup | Mike Adams | Blocked | Low | 2024-08-08 | 2024-08-30 |  | 0 | Rebar | Downtown Avenue | 41729.37 | 33057.91 | Not started
C001 | Residential Building A | T581 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2023-09-21 | 2023-10-15 |  | 0 | Concrete | Plot 21, Riverside | 42270.9 | 45994.99 | Not started
C003 | Office Tower C | T339 | Concrete Pouring | Mike Adams | In Progress | Medium | 2024-10-09 | 2024-10-21 |  | 91 | Concrete | Downtown Avenue | 23014.17 | 16434.51 | In progress
C003 | Office Tower C | T917 | Interior Painting | Rachel Green | In Progress | Medium | 2024-10-12 | 2024-10-31 |  | 27 | Steel Beams | Downtown Avenue | 33287.76 | 38935.48 | In progress
C001 | Residential Building A | T225 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2024-06-22 | 2024-07-14 | 2024-07-14 | 100 | Roofing Sheets | Plot 21, Riverside | 39132.54 | 33413.73 | No issues
C004 | Warehouse D | T576 | Interior Painting | John Miller | Not Started | Medium | 2024-06-21 | 2024-07-20 |  | 0 | PVC Pipes | Industrial Park | 36942.43 | 0 | Not started
C002 | Shopping Complex B | T810 | Roofing | Mike Adams | Blocked | Low | 2024-10-08 | 2024-11-05 |  | 0 | Steel Beams | Market Street | 10778.67 | 37848.25 | Not started
C004 | Warehouse D | T430 | Plumbing Installations | Grace Allen | Blocked | Low | 2023-03-05 | 2023-03-31 |  | 0 | Cement | Industrial Park | 23266.5 | 27263.56 | Not started
C003 | Office Tower C | T561 | Roofing | Carlos Rivera | Blocked | High | 2023-05-05 | 2023-05-22 |  | 0 | Roofing Sheets | Downtown Avenue | 12905.77 | 9684.85 | Not started
C001 | Residential Building A | T710 | Roofing | Carlos Rivera | Not Started | Medium | 2023-03-09 | 2023-03-29 |  | 0 | Rebar | Plot 21, Riverside | 10769.59 | 0 | Not started
C003 | Office Tower C | T182 | Foundation Excavation | Rachel Green | Blocked | High | 2023-02-14 | 2023-03-13 |  | 0 | Copper Wires | Downtown Avenue | 21140.44 | 13774.21 | Not started
C003 | Office Tower C | T627 | Site Survey | Sarah Johnson | Blocked | High | 2023-12-10 | 2023-12-29 |  | 0 | Rebar | Downtown Avenue | 12295.01 | 9147.53 | Not started
C001 | Residential Building A | T353 | Electrical Wiring | Grace Allen | Completed | High | 2024-11-18 | 2024-11-28 | 2024-11-28 | 100 | Steel Beams | Plot 21, Riverside | 24415.69 | 20484.37 | No issues
C003 | Office Tower C | T938 | Interior Painting | Mike Adams | Completed | Medium | 2023-08-01 | 2023-08-30 | 2023-08-30 | 100 | PVC Pipes | Downtown Avenue | 24581.56 | 20542.04 | No issues
C004 | Warehouse D | T918 | Site Survey | Carlos Rivera | In Progress | High | 2023-01-01 | 2023-01-26 |  | 70 | Steel Beams | Industrial Park | 19204.84 | 19656.99 | In progress
C002 | Shopping Complex B | T937 | Concrete Pouring | Grace Allen | Blocked | Low | 2023-08-11 | 2023-08-18 |  | 0 | Rebar | Market Street | 12180.61 | 32930.91 | Not started
C001 | Residential Building A | T294 | Foundation Excavation | Grace Allen | Blocked | Medium | 2023-03-06 | 2023-03-14 |  | 0 | Roofing Sheets | Plot 21, Riverside | 27540.61 | 29457.27 | Not started
C001 | Residential Building A | T955 | Site Survey | John Miller | In Progress | Medium | 2024-08-13 | 2024-08-25 |  | 5 | PVC Pipes | Plot 21, Riverside | 49643.74 | 53617.72 | In progress
C002 | Shopping Complex B | T506 | Interior Painting | John Miller | In Progress | Low | 2023-06-10 | 2023-07-05 |  | 27 | PVC Pipes | Market Street | 25256.13 | 55023.53 | In progress
C002 | Shopping Complex B | T685 | Plumbing Installations | Emma White | Blocked | High | 2023-12-10 | 2023-12-30 |  | 0 | Copper Wires | Market Street | 33253.19 | 45560.6 | Not started
C002 | Shopping Complex B | T562 | Plumbing Installations | Grace Allen | Completed | Low | 2024-09-14 | 2024-09-24 | 2024-09-24 | 100 | Paint | Market Street | 8522.07 | 32223.31 | No issues
C001 | Residential Building A | T233 | Steel Framework Setup | Mike Adams | Completed | Medium | 2023-02-01 | 2023-02-28 | 2023-02-28 | 100 | Copper Wires | Plot 21, Riverside | 34574.36 | 29840.46 | No issues
C004 | Warehouse D | T409 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-10-10 | 2024-10-22 | 2024-10-22 | 100 | Roofing Sheets | Industrial Park | 20701.18 | 22485.83 | No issues
C001 | Residential Building A | T405 | Site Survey | Carlos Rivera | In Progress | High | 2024-03-27 | 2024-04-26 |  | 19 | Rebar | Plot 21, Riverside | 14392.16 | 8698.51 | In progress
C002 | Shopping Complex B | T512 | Interior Painting | Mike Adams | Completed | Medium | 2024-02-27 | 2024-03-13 | 2024-03-13 | 100 | Paint | Market Street | 23160.33 | 50724.85 | No issues
C002 | Shopping Complex B | T222 | Electrical Wiring | Mike Adams | In Progress | High | 2024-11-18 | 2024-12-05 |  | 82 | Roofing Sheets | Market Street | 14691.78 | 37315.26 | In progress
C001 | Residential Building A | T660 | Foundation Excavation | Dave Brown | Blocked | Medium | 2023-08-03 | 2023-08-21 |  | 0 | Steel Beams | Plot 21, Riverside | 11410.18 | 11780 | Not started
C001 | Residential Building A | T483 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2023-11-17 | 2023-12-07 |  | 0 | Copper Wires | Plot 21, Riverside | 43110.9 | 28417.79 | Not started
C002 | Shopping Complex B | T268 | Plumbing Installations | Rachel Green | Completed | Medium | 2024-09-04 | 2024-09-16 | 2024-09-16 | 100 | PVC Pipes | Market Street | 42463.57 | 61210.82 | No issues
C004 | Warehouse D | T754 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2023-08-05 | 2023-08-25 |  | 0 | Steel Beams | Industrial Park | 22353.68 | 0 | Not started
C004 | Warehouse D | T836 | Interior Painting | Carlos Rivera | Blocked | Medium | 2024-03-12 | 2024-03-28 |  | 0 | Copper Wires | Industrial Park | 25978.23 | 27449.5 | Not started
C003 | Office Tower C | T939 | Roofing | Mike Adams | Not Started | Medium | 2024-04-23 | 2024-05-18 |  | 0 | PVC Pipes | Downtown Avenue | 43323.81 | 0 | Not started
C001 | Residential Building A | T955 | Interior Painting | Mike Adams | Completed | Low | 2023-11-02 | 2023-11-22 | 2023-11-22 | 100 | Copper Wires | Plot 21, Riverside | 8562.98 | 7251.16 | No issues
C002 | Shopping Complex B | T283 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-08-20 | 2024-08-31 |  | 0 | Copper Wires | Market Street | 13106.74 | 38558.32 | Not started
C004 | Warehouse D | T473 | Electrical Wiring | Emma White | Not Started | Medium | 2024-03-25 | 2024-04-23 |  | 0 | Steel Beams | Industrial Park | 9043.77 | 0 | Not started
C001 | Residential Building A | T774 | Plumbing Installations | Emma White | In Progress | High | 2024-01-27 | 2024-02-15 |  | 76 | Copper Wires | Plot 21, Riverside | 16356.9 | 17101.01 | In progress
C004 | Warehouse D | T718 | Plumbing Installations | Rachel Green | Blocked | High | 2024-05-07 | 2024-05-19 |  | 0 | Roofing Sheets | Industrial Park | 26554.97 | 22669.68 | Not started
C004 | Warehouse D | T168 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-05-22 | 2024-06-05 |  | 0 | Concrete | Industrial Park | 36463.19 | 0 | Not started
C003 | Office Tower C | T942 | Site Survey | Rachel Green | Not Started | Low | 2024-05-04 | 2024-06-01 |  | 0 | PVC Pipes | Downtown Avenue | 45991.19 | 0 | Not started
C002 | Shopping Complex B | T240 | Concrete Pouring | Dave Brown | Blocked | Medium | 2024-04-11 | 2024-04-20 |  | 0 | Paint | Market Street | 34915.62 | 66216.59 | Not started
C002 | Shopping Complex B | T904 | Steel Framework Setup | Sarah Johnson | Completed | High | 2023-09-18 | 2023-10-09 | 2023-10-09 | 100 | Roofing Sheets | Market Street | 20331.01 | 49821.39 | No issues
C001 | Residential Building A | T645 | Foundation Excavation | Grace Allen | In Progress | Low | 2023-06-01 | 2023-06-12 |  | 51 | Rebar | Plot 21, Riverside | 26639.99 | 31329.09 | In progress
C003 | Office Tower C | T375 | Plumbing Installations | Grace Allen | Not Started | Medium | 2024-09-28 | 2024-10-25 |  | 0 | Roofing Sheets | Downtown Avenue | 29375.93 | 0 | Not started
C003 | Office Tower C | T743 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2023-09-04 | 2023-09-14 | 2023-09-14 | 100 | Concrete | Downtown Avenue | 24196.88 | 26552.33 | No issues
C003 | Office Tower C | T741 | Steel Framework Setup | Grace Allen | Completed | Low | 2024-05-10 | 2024-06-07 | 2024-06-07 | 100 | Paint | Downtown Avenue | 38165.8 | 34846.95 | No issues
C004 | Warehouse D | T363 | Plumbing Installations | Dave Brown | In Progress | Low | 2023-07-10 | 2023-08-06 |  | 62 | Concrete | Industrial Park | 27998.06 | 23810.31 | In progress
C001 | Residential Building A | T670 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-06-28 | 2023-07-11 | 2023-07-11 | 100 | PVC Pipes | Plot 21, Riverside | 42245.66 | 38440.68 | No issues
C001 | Residential Building A | T363 | Steel Framework Setup | Rachel Green | Completed | Medium | 2024-04-26 | 2024-05-26 | 2024-05-26 | 100 | Rebar | Plot 21, Riverside | 21311.94 | 20704.63 | No issues
C003 | Office Tower C | T277 | Roofing | Grace Allen | In Progress | High | 2024-04-05 | 2024-04-28 |  | 48 | Rebar | Downtown Avenue | 39151.8 | 38223.45 | In progress
C003 | Office Tower C | T957 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2024-11-10 | 2024-12-06 |  | 0 | Rebar | Downtown Avenue | 47331.98 | 0 | Not started
C003 | Office Tower C | T145 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2023-10-28 | 2023-11-27 |  | 50 | Steel Beams | Downtown Avenue | 38764.47 | 40315.26 | In progress
C003 | Office Tower C | T292 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2023-08-28 | 2023-09-21 |  | 0 | Copper Wires | Downtown Avenue | 11728.87 | 0 | Not started
C002 | Shopping Complex B | T722 | Electrical Wiring | Emma White | Blocked | High | 2024-01-15 | 2024-01-30 |  | 0 | Steel Beams | Market Street | 13149.82 | 39478.09 | Not started
C001 | Residential Building A | T137 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2023-07-22 | 2023-08-11 |  | 0 | Steel Beams | Plot 21, Riverside | 39989.61 | 44539.19 | Not started
C004 | Warehouse D | T802 | Roofing | Dave Brown | Completed | Low | 2024-02-28 | 2024-03-15 | 2024-03-15 | 100 | Roofing Sheets | Industrial Park | 8657.7 | 5254.58 | No issues
C001 | Residential Building A | T899 | Foundation Excavation | Grace Allen | Completed | High | 2024-11-07 | 2024-12-02 | 2024-12-02 | 100 | PVC Pipes | Plot 21, Riverside | 27107.67 | 18945.76 | No issues
C004 | Warehouse D | T140 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-05-09 | 2023-05-29 |  | 83 | Rebar | Industrial Park | 23040.24 | 21321.43 | In progress
C003 | Office Tower C | T739 | Interior Painting | Rachel Green | Completed | Low | 2024-10-13 | 2024-10-20 | 2024-10-20 | 100 | Copper Wires | Downtown Avenue | 23791.34 | 20582.29 | No issues
C001 | Residential Building A | T325 | Site Survey | Grace Allen | Completed | High | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100 | Paint | Plot 21, Riverside | 26918.82 | 24438.89 | No issues
C003 | Office Tower C | T993 | Plumbing Installations | Carlos Rivera | In Progress | High | 2024-04-07 | 2024-04-28 |  | 87 | Copper Wires | Downtown Avenue | 31660.3 | 21320.97 | In progress
C003 | Office Tower C | T518 | Concrete Pouring | Emma White | Blocked | Medium | 2024-01-02 | 2024-01-29 |  | 0 | Rebar | Downtown Avenue | 32159.62 | 22487.71 | Not started
C002 | Shopping Complex B | T531 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-12-09 | 2023-12-17 |  | 16 | Paint | Market Street | 12858.69 | 38538.38 | In progress
C001 | Residential Building A | T455 | Roofing | Carlos Rivera | Not Started | Low | 2023-05-24 | 2023-06-19 |  | 0 | Copper Wires | Plot 21, Riverside | 35253.26 | 0 | Not started
C002 | Shopping Complex B | T116 | Roofing | Emma White | Completed | Low | 2023-12-27 | 2024-01-09 | 2024-01-09 | 100 | PVC Pipes | Market Street | 42705.07 | 75129.14 | No issues
C004 | Warehouse D | T551 | Steel Framework Setup | Emma White | In Progress | Low | 2023-03-18 | 2023-03-27 |  | 12 | Copper Wires | Industrial Park | 46360.94 | 54742.07 | In progress
C003 | Office Tower C | T369 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2024-08-24 | 2024-09-05 |  | 0 | Paint | Downtown Avenue | 18957.7 | 22454.3 | Not started
C004 | Warehouse D | T824 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2024-08-28 | 2024-09-16 |  | 0 | Roofing Sheets | Industrial Park | 40828.81 | 0 | Not started
C001 | Residential Building A | T574 | Foundation Excavation | Sarah Johnson | Not Started | Low | 2023-09-09 | 2023-09-25 |  | 0 | Paint | Plot 21, Riverside | 5752.71 | 0 | Not started
C002 | Shopping Complex B | T541 | Plumbing Installations | Mike Adams | Blocked | High | 2024-04-22 | 2024-04-30 |  | 0 | PVC Pipes | Market Street | 11888.23 | 38295.35 | Not started
C001 | Residential Building A | T565 | Electrical Wiring | Grace Allen | Not Started | Low | 2023-05-08 | 2023-05-31 |  | 0 | Cement | Plot 21, Riverside | 49313.66 | 0 | Not started
C003 | Office Tower C | T124 | Concrete Pouring | Emma White | Completed | Medium | 2023-04-20 | 2023-05-17 | 2023-05-17 | 100 | Cement | Downtown Avenue | 39790.04 | 28320.69 | No issues
C002 | Shopping Complex B | T668 | Steel Framework Setup | Emma White | Blocked | Medium | 2023-09-16 | 2023-10-14 |  | 0 | Paint | Market Street | 5096.1 | 29107.96 | Not started
C004 | Warehouse D | T168 | Concrete Pouring | John Miller | Blocked | High | 2023-09-14 | 2023-10-02 |  | 0 | PVC Pipes | Industrial Park | 14201.24 | 10106.46 | Not started
C003 | Office Tower C | T734 | Site Survey | Mike Adams | Completed | Medium | 2023-04-04 | 2023-05-02 | 2023-05-02 | 100 | Cement | Downtown Avenue | 10423.86 | 7111.97 | No issues
C001 | Residential Building A | T929 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2024-11-28 | 2024-12-07 |  | 0 | Steel Beams | Plot 21, Riverside | 42222.75 | 0 | Not started
C002 | Shopping Complex B | T360 | Foundation Excavation | Dave Brown | In Progress | Low | 2023-10-24 | 2023-11-12 |  | 48 | Rebar | Market Street | 47948.86 | 79889.87 | In progress
C004 | Warehouse D | T770 | Interior Painting | Carlos Rivera | Not Started | Medium | 2024-02-10 | 2024-03-03 |  | 0 | Roofing Sheets | Industrial Park | 15863.54 | 0 | Not started
C002 | Shopping Complex B | T508 | Steel Framework Setup | Rachel Green | Blocked | Low | 2023-01-10 | 2023-01-31 |  | 0 | Roofing Sheets | Market Street | 16308.79 | 42866.99 | Not started
C001 | Residential Building A | T627 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-06-11 | 2023-07-09 | 2023-07-09 | 100 | Copper Wires | Plot 21, Riverside | 26135.65 | 22647.37 | No issues
C001 | Residential Building A | T358 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2024-02-21 | 2024-02-28 |  | 0 | Copper Wires | Plot 21, Riverside | 36258.15 | 39612.05 | Not started
C002 | Shopping Complex B | T496 | Steel Framework Setup | Emma White | In Progress | Low | 2024-04-06 | 2024-04-13 |  | 74 | Steel Beams | Market Street | 40064.81 | 57654.9 | In progress
C002 | Shopping Complex B | T846 | Roofing | Grace Allen | In Progress | High | 2024-10-21 | 2024-11-02 |  | 8 | Steel Beams | Market Street | 11940.12 | 34200.97 | In progress
C002 | Shopping Complex B | T419 | Steel Framework Setup | Emma White | Blocked | Low | 2024-01-20 | 2024-01-31 |  | 0 | Paint | Market Street | 46279.04 | 61958.55 | Not started
C004 | Warehouse D | T326 | Concrete Pouring | Mike Adams | Completed | Medium | 2024-09-21 | 2024-10-02 | 2024-10-02 | 100 | Steel Beams | Industrial Park | 17889 | 15056.78 | No issues
C001 | Residential Building A | T650 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2023-05-03 | 2023-05-30 |  | 0 | Concrete | Plot 21, Riverside | 38363.05 | 0 | Not started
C003 | Office Tower C | T950 | Foundation Excavation | Sarah Johnson | Blocked | Low | 2023-11-01 | 2023-11-08 |  | 0 | Rebar | Downtown Avenue | 34063.66 | 38335.52 | Not started
C004 | Warehouse D | T164 | Foundation Excavation | Carlos Rivera | Blocked | High | 2023-06-13 | 2023-07-02 |  | 0 | PVC Pipes | Industrial Park | 45028.02 | 33975.11 | Not started
C002 | Shopping Complex B | T205 | Site Survey | Grace Allen | Not Started | Low | 2023-07-26 | 2023-08-16 |  | 0 | Cement | Market Street | 21516.75 | 0 | Not started
C003 | Office Tower C | T133 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-10-11 | 2024-10-27 |  | 0 | PVC Pipes | Downtown Avenue | 32943.48 | 24292.9 | Not started
C004 | Warehouse D | T330 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2023-03-16 | 2023-04-10 |  | 0 | Concrete | Industrial Park | 40018.76 | 0 | Not started
C002 | Shopping Complex B | T426 | Concrete Pouring | Grace Allen | Completed | High | 2023-05-13 | 2023-06-04 | 2023-06-04 | 100 | Steel Beams | Market Street | 18770.81 | 45557.85 | No issues
C001 | Residential Building A | T465 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-04-06 | 2023-04-20 |  | 0 | Paint | Plot 21, Riverside | 37500.04 | 0 | Not started
C003 | Office Tower C | T468 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-05-12 | 2023-05-28 |  | 0 | Steel Beams | Downtown Avenue | 17874.44 | 20926.62 | Not started
C004 | Warehouse D | T632 | Plumbing Installations | Dave Brown | Completed | Low | 2024-02-25 | 2024-03-10 | 2024-03-10 | 100 | PVC Pipes | Industrial Park | 9139.26 | 7699.1 | No issues
C001 | Residential Building A | T926 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2023-07-07 | 2023-07-18 |  | 0 | Concrete | Plot 21, Riverside | 28423.57 | 0 | Not started
C004 | Warehouse D | T679 | Concrete Pouring | Mike Adams | In Progress | Low | 2024-09-23 | 2024-10-13 |  | 24 | Cement | Industrial Park | 27832.87 | 23103.18 | In progress
C004 | Warehouse D | T900 | Steel Framework Setup | Mike Adams | In Progress | High | 2024-04-26 | 2024-05-03 |  | 17 | Steel Beams | Industrial Park | 28968.97 | 34605.92 | In progress
C004 | Warehouse D | T840 | Steel Framework Setup | Grace Allen | Completed | High | 2023-02-12 | 2023-03-12 | 2023-03-12 | 100 | Rebar | Industrial Park | 20843.5 | 21175.54 | No issues
C004 | Warehouse D | T877 | Site Survey | John Miller | Completed | Medium | 2023-04-24 | 2023-05-24 | 2023-05-24 | 100 | Rebar | Industrial Park | 15157.37 | 12219.53 | No issues
C003 | Office Tower C | T428 | Site Survey | John Miller | Blocked | High | 2024-05-01 | 2024-05-28 |  | 0 | Rebar | Downtown Avenue | 38539.95 | 31290.98 | Not started
C002 | Shopping Complex B | T712 | Concrete Pouring | Sarah Johnson | Completed | Low | 2023-12-08 | 2023-12-15 | 2023-12-15 | 100 | PVC Pipes | Market Street | 23690.52 | 50995.58 | No issues
C004 | Warehouse D | T572 | Foundation Excavation | Emma White | In Progress | Low | 2023-06-06 | 2023-06-14 |  | 30 | Copper Wires | Industrial Park | 28641.6 | 25541.19 | In progress
C002 | Shopping Complex B | T851 | Foundation Excavation | Rachel Green | Not Started | High | 2024-03-04 | 2024-03-18 |  | 0 | Steel Beams | Market Street | 34405.71 | 0 | Not started
C002 | Shopping Complex B | T510 | Steel Framework Setup | Emma White | Blocked | High | 2023-07-08 | 2023-07-27 |  | 0 | Copper Wires | Market Street | 30107.13 | 59928.29 | Not started
C003 | Office Tower C | T435 | Site Survey | Dave Brown | In Progress | High | 2024-09-27 | 2024-10-09 |  | 72 | Copper Wires | Downtown Avenue | 18618.47 | 21952.44 | In progress
C004 | Warehouse D | T728 | Interior Painting | Dave Brown | Completed | Low | 2023-05-02 | 2023-05-17 | 2023-05-17 | 100 | Rebar | Industrial Park | 7234.48 | 7686.91 | No issues
C001 | Residential Building A | T732 | Concrete Pouring | Dave Brown | Blocked | High | 2023-04-25 | 2023-05-18 |  | 0 | Steel Beams | Plot 21, Riverside | 13482.67 | 10682.28 | Not started
C004 | Warehouse D | T959 | Steel Framework Setup | Rachel Green | Completed | High | 2024-06-10 | 2024-07-06 | 2024-07-06 | 100 | Copper Wires | Industrial Park | 10969.03 | 12250.47 | No issues
C001 | Residential Building A | T781 | Interior Painting | Carlos Rivera | Not Started | High | 2024-12-02 | 2024-12-10 |  | 0 | Paint | Plot 21, Riverside | 14497.74 | 0 | Not started
C003 | Office Tower C | T355 | Electrical Wiring | Carlos Rivera | Completed | Low | 2023-10-08 | 2023-10-21 | 2023-10-21 | 100 | Concrete | Downtown Avenue | 29943.17 | 29210.01 | No issues
C001 | Residential Building A | T306 | Roofing | Dave Brown | Blocked | High | 2023-01-15 | 2023-01-24 |  | 0 | Rebar | Plot 21, Riverside | 48828.99 | 53163.74 | Not started
C004 | Warehouse D | T295 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2023-11-07 | 2023-11-27 | 2023-11-27 | 100 | Cement | Industrial Park | 39170.84 | 31543.03 | No issues
C001 | Residential Building A | T803 | Electrical Wiring | Mike Adams | Blocked | Medium | 2024-05-09 | 2024-05-16 |  | 0 | PVC Pipes | Plot 21, Riverside | 41332.09 | 32056.35 | Not started
C001 | Residential Building A | T304 | Roofing | Sarah Johnson | Completed | High | 2024-02-21 | 2024-03-04 | 2024-03-04 | 100 | Paint | Plot 21, Riverside | 14039.61 | 9997.38 | No issues
C003 | Office Tower C | T897 | Concrete Pouring | Mike Adams | In Progress | Medium | 2024-01-01 | 2024-01-29 |  | 58 | Rebar | Downtown Avenue | 22302.65 | 23963.46 | In progress
C003 | Office Tower C | T190 | Roofing | Mike Adams | Not Started | High | 2023-01-26 | 2023-02-21 |  | 0 | Rebar | Downtown Avenue | 16603.62 | 0 | Not started
C004 | Warehouse D | T912 | Site Survey | Rachel Green | Not Started | High | 2023-02-18 | 2023-03-17 |  | 0 | Steel Beams | Industrial Park | 7938.41 | 0 | Not started
C003 | Office Tower C | T400 | Site Survey | Dave Brown | Not Started | Medium | 2024-12-04 | 2025-01-02 |  | 0 | Paint | Downtown Avenue | 45322.58 | 0 | Not started
C003 | Office Tower C | T888 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2024-11-28 | 2024-12-23 |  | 0 | Steel Beams | Downtown Avenue | 11176.63 | 10547.7 | Not started
C004 | Warehouse D | T636 | Concrete Pouring | John Miller | Not Started | Medium | 2023-11-21 | 2023-12-14 |  | 0 | Rebar | Industrial Park | 39966.82 | 0 | Not started
C002 | Shopping Complex B | T341 | Foundation Excavation | Grace Allen | Blocked | High | 2023-01-25 | 2023-02-14 |  | 0 | Roofing Sheets | Market Street | 7437.31 | 33155.4 | Not started
C003 | Office Tower C | T173 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-04-27 | 2024-05-16 |  | 0 | Paint | Downtown Avenue | 47351.36 | 0 | Not started
C003 | Office Tower C | T913 | Roofing | Emma White | In Progress | Medium | 2023-09-13 | 2023-09-23 |  | 21 | Rebar | Downtown Avenue | 20213.22 | 14914.56 | In progress
C002 | Shopping Complex B | T828 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2023-01-14 | 2023-02-10 |  | 37 | PVC Pipes | Market Street | 32063.37 | 47419.2 | In progress
C002 | Shopping Complex B | T267 | Concrete Pouring | John Miller | Not Started | Medium | 2023-09-18 | 2023-10-15 |  | 0 | Concrete | Market Street | 8258.22 | 0 | Not started
C001 | Residential Building A | T991 | Steel Framework Setup | Dave Brown | Not Started | Low | 2024-10-06 | 2024-10-21 |  | 0 | Paint | Plot 21, Riverside | 46414.23 | 0 | Not started
C004 | Warehouse D | T396 | Concrete Pouring | Mike Adams | Completed | Medium | 2024-12-28 | 2025-01-09 | 2025-01-09 | 100 | PVC Pipes | Industrial Park | 14061.74 | 13719.69 | No issues
C004 | Warehouse D | T359 | Plumbing Installations | Dave Brown | Completed | High | 2023-04-14 | 2023-04-26 | 2023-04-26 | 100 | Copper Wires | Industrial Park | 31341.47 | 20300.43 | No issues
C001 | Residential Building A | T454 | Site Survey | Rachel Green | Not Started | Low | 2023-09-28 | 2023-10-12 |  | 0 | Paint | Plot 21, Riverside | 30086.83 | 0 | Not started
C003 | Office Tower C | T838 | Site Survey | Rachel Green | Completed | Low | 2023-05-25 | 2023-06-08 | 2023-06-08 | 100 | Cement | Downtown Avenue | 7889.51 | 5370.94 | No issues
C001 | Residential Building A | T955 | Roofing | Dave Brown | Completed | High | 2024-01-25 | 2024-02-20 | 2024-02-20 | 100 | PVC Pipes | Plot 21, Riverside | 23695.91 | 22200.81 | No issues
C003 | Office Tower C | T457 | Interior Painting | Rachel Green | Blocked | Medium | 2023-10-28 | 2023-11-22 |  | 0 | Copper Wires | Downtown Avenue | 23603.99 | 21218.25 | Not started
C003 | Office Tower C | T718 | Interior Painting | Mike Adams | Blocked | High | 2024-07-16 | 2024-08-01 |  | 0 | Cement | Downtown Avenue | 37282.35 | 38348.31 | Not started
C004 | Warehouse D | T830 | Site Survey | Dave Brown | Not Started | Medium | 2024-08-19 | 2024-08-28 |  | 0 | Roofing Sheets | Industrial Park | 39453.71 | 0 | Not started
C004 | Warehouse D | T139 | Electrical Wiring | Emma White | In Progress | Low | 2023-04-12 | 2023-04-22 |  | 48 | PVC Pipes | Industrial Park | 45625.5 | 40862.85 | In progress
C002 | Shopping Complex B | T746 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-10-26 | 2023-11-04 |  | 0 | Paint | Market Street | 34852.47 | 0 | Not started
C002 | Shopping Complex B | T838 | Site Survey | Mike Adams | Blocked | High | 2024-03-24 | 2024-04-18 |  | 0 | Steel Beams | Market Street | 6353.89 | 31477.66 | Not started
C002 | Shopping Complex B | T150 | Electrical Wiring | John Miller | Blocked | High | 2023-08-18 | 2023-09-16 |  | 0 | Paint | Market Street | 34273.31 | 55165.04 | Not started
C003 | Office Tower C | T944 | Steel Framework Setup | Emma White | Not Started | High | 2024-06-05 | 2024-06-12 |  | 0 | Concrete | Downtown Avenue | 17757.03 | 0 | Not started
C003 | Office Tower C | T101 | Roofing | John Miller | Not Started | High | 2024-01-03 | 2024-01-25 |  | 0 | Roofing Sheets | Downtown Avenue | 13545.74 | 0 | Not started
C001 | Residential Building A | T441 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2023-11-20 | 2023-11-30 |  | 0 | Concrete | Plot 21, Riverside | 21261.67 | 21933.71 | Not started
C004 | Warehouse D | T433 | Plumbing Installations | Emma White | Completed | Medium | 2024-01-15 | 2024-02-07 | 2024-02-07 | 100 | Rebar | Industrial Park | 5802.63 | 4263.47 | No issues
C001 | Residential Building A | T781 | Interior Painting | Dave Brown | Not Started | High | 2023-07-09 | 2023-07-16 |  | 0 | Concrete | Plot 21, Riverside | 11965.61 | 0 | Not started
C004 | Warehouse D | T739 | Roofing | John Miller | Not Started | Low | 2024-04-25 | 2024-05-15 |  | 0 | Steel Beams | Industrial Park | 23334.38 | 0 | Not started
C004 | Warehouse D | T536 | Concrete Pouring | Emma White | In Progress | High | 2023-06-26 | 2023-07-21 |  | 0 | Rebar | Industrial Park | 41371.25 | 46719.87 | In progress
C003 | Office Tower C | T372 | Site Survey | Dave Brown | Blocked | Medium | 2024-05-26 | 2024-06-22 |  | 0 | Copper Wires | Downtown Avenue | 12513.28 | 9789.7 | Not started
C003 | Office Tower C | T992 | Interior Painting | Mike Adams | Blocked | High | 2023-11-28 | 2023-12-10 |  | 0 | Rebar | Downtown Avenue | 35955.89 | 25702.11 | Not started
C003 | Office Tower C | T723 | Electrical Wiring | Rachel Green | In Progress | Medium | 2023-11-13 | 2023-11-26 |  | 56 | Copper Wires | Downtown Avenue | 6665.74 | 6967.05 | In progress
C002 | Shopping Complex B | T952 | Plumbing Installations | Dave Brown | Blocked | High | 2024-02-19 | 2024-02-27 |  | 0 | Roofing Sheets | Market Street | 48439.86 | 70831.11 | Not started
C003 | Office Tower C | T131 | Steel Framework Setup | Grace Allen | Not Started | High | 2023-08-22 | 2023-08-30 |  | 0 | Concrete | Downtown Avenue | 18086.38 | 0 | Not started
C002 | Shopping Complex B | T134 | Site Survey | Rachel Green | Not Started | Low | 2023-12-16 | 2024-01-05 |  | 0 | Steel Beams | Market Street | 44563.9 | 0 | Not started
C001 | Residential Building A | T578 | Foundation Excavation | John Miller | Blocked | Medium | 2023-11-26 | 2023-12-26 |  | 0 | Steel Beams | Plot 21, Riverside | 25610.3 | 25614.05 | Not started
C001 | Residential Building A | T986 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-05-10 | 2024-05-31 | 2024-05-31 | 100 | Rebar | Plot 21, Riverside | 18352.19 | 21932.51 | No issues
C001 | Residential Building A | T417 | Plumbing Installations | Dave Brown | In Progress | High | 2023-05-08 | 2023-05-23 |  | 57 | Paint | Plot 21, Riverside | 39175.52 | 27613.6 | In progress
C004 | Warehouse D | T641 | Plumbing Installations | John Miller | In Progress | High | 2024-10-20 | 2024-11-06 |  | 92 | Roofing Sheets | Industrial Park | 32331.21 | 34769.28 | In progress
C002 | Shopping Complex B | T517 | Foundation Excavation | Rachel Green | Blocked | High | 2024-06-08 | 2024-06-29 |  | 0 | Paint | Market Street | 47735.01 | 74886.33 | Not started
C002 | Shopping Complex B | T138 | Roofing | Rachel Green | Completed | Medium | 2024-03-07 | 2024-03-21 | 2024-03-21 | 100 | PVC Pipes | Market Street | 6424.64 | 32507.45 | No issues
C001 | Residential Building A | T674 | Concrete Pouring | John Miller | Completed | High | 2023-07-18 | 2023-08-07 | 2023-08-07 | 100 | PVC Pipes | Plot 21, Riverside | 46619.39 | 37009.77 | No issues
C002 | Shopping Complex B | T546 | Plumbing Installations | John Miller | Not Started | High | 2024-09-10 | 2024-10-06 |  | 0 | Cement | Market Street | 16038.75 | 0 | Not started
C004 | Warehouse D | T836 | Site Survey | Sarah Johnson | Completed | Low | 2023-05-20 | 2023-05-30 | 2023-05-30 | 100 | Paint | Industrial Park | 17305.65 | 16164.47 | No issues
C002 | Shopping Complex B | T752 | Steel Framework Setup | Emma White | Not Started | Medium | 2023-09-26 | 2023-10-15 |  | 0 | Roofing Sheets | Market Street | 47582.79 | 0 | Not started
C001 | Residential Building A | T463 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-09-13 | 2024-09-25 |  | 0 | Copper Wires | Plot 21, Riverside | 43153.16 | 46196.1 | Not started
C002 | Shopping Complex B | T982 | Concrete Pouring | Emma White | Not Started | Medium | 2023-05-22 | 2023-05-31 |  | 0 | Concrete | Market Street | 17308.14 | 0 | Not started
C001 | Residential Building A | T810 | Roofing | Mike Adams | Blocked | Low | 2024-02-01 | 2024-02-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 34367.59 | 38405.21 | Not started
C003 | Office Tower C | T826 | Foundation Excavation | Grace Allen | Blocked | Medium | 2023-07-01 | 2023-07-28 |  | 0 | Copper Wires | Downtown Avenue | 43487 | 29348.39 | Not started
C002 | Shopping Complex B | T374 | Concrete Pouring | Dave Brown | Completed | Medium | 2024-03-12 | 2024-03-23 | 2024-03-23 | 100 | PVC Pipes | Market Street | 46028.96 | 80656.67 | No issues
C003 | Office Tower C | T837 | Steel Framework Setup | Mike Adams | In Progress | High | 2024-10-26 | 2024-11-10 |  | 68 | PVC Pipes | Downtown Avenue | 39314.95 | 26697.62 | In progress
C001 | Residential Building A | T719 | Site Survey | Dave Brown | Blocked | Medium | 2023-07-26 | 2023-08-07 |  | 0 | Rebar | Plot 21, Riverside | 7872.32 | 8498.56 | Not started
C004 | Warehouse D | T280 | Site Survey | Rachel Green | In Progress | Medium | 2024-05-18 | 2024-06-07 |  | 10 | Roofing Sheets | Industrial Park | 14178.32 | 14491.8 | In progress
C001 | Residential Building A | T657 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2024-05-20 | 2024-06-18 |  | 0 | Cement | Plot 21, Riverside | 25183.74 | 24817.53 | Not started
C004 | Warehouse D | T607 | Plumbing Installations | Rachel Green | In Progress | High | 2024-11-14 | 2024-12-10 |  | 97 | Roofing Sheets | Industrial Park | 47854.38 | 55917.39 | In progress
C002 | Shopping Complex B | T333 | Site Survey | Dave Brown | Completed | Low | 2023-02-25 | 2023-03-27 | 2023-03-27 | 100 | Steel Beams | Market Street | 19179.99 | 40483.56 | No issues
C004 | Warehouse D | T893 | Electrical Wiring | Emma White | Blocked | Medium | 2023-10-27 | 2023-11-09 |  | 0 | Copper Wires | Industrial Park | 29625.91 | 22595.18 | Not started
C003 | Office Tower C | T628 | Foundation Excavation | Grace Allen | Blocked | Medium | 2024-01-17 | 2024-02-08 |  | 0 | Roofing Sheets | Downtown Avenue | 14120.71 | 14812.22 | Not started
C002 | Shopping Complex B | T168 | Electrical Wiring | Carlos Rivera | In Progress | High | 2023-01-09 | 2023-01-17 |  | 14 | Copper Wires | Market Street | 15450.67 | 34897.62 | In progress
C001 | Residential Building A | T765 | Steel Framework Setup | Emma White | Not Started | Low | 2024-05-26 | 2024-06-02 |  | 0 | Cement | Plot 21, Riverside | 13073.23 | 0 | Not started
C003 | Office Tower C | T389 | Electrical Wiring | Emma White | In Progress | High | 2023-05-18 | 2023-06-03 |  | 4 | Rebar | Downtown Avenue | 11050.1 | 13141.78 | In progress
C004 | Warehouse D | T973 | Plumbing Installations | Dave Brown | Completed | High | 2024-07-11 | 2024-07-21 | 2024-07-21 | 100 | Rebar | Industrial Park | 5113.49 | 6117.66 | No issues
C004 | Warehouse D | T308 | Steel Framework Setup | Mike Adams | In Progress | High | 2023-07-06 | 2023-07-26 |  | 16 | Cement | Industrial Park | 14398.19 | 13669.61 | In progress
C002 | Shopping Complex B | T793 | Plumbing Installations | Emma White | In Progress | Medium | 2024-12-05 | 2024-12-15 |  | 15 | Rebar | Market Street | 14678.28 | 35549.53 | In progress
C003 | Office Tower C | T613 | Foundation Excavation | Rachel Green | In Progress | High | 2024-11-14 | 2024-12-01 |  | 12 | Rebar | Downtown Avenue | 37982.66 | 39164.57 | In progress
C003 | Office Tower C | T972 | Interior Painting | Grace Allen | Completed | Medium | 2024-03-26 | 2024-04-06 | 2024-04-06 | 100 | Copper Wires | Downtown Avenue | 15874.93 | 12509.54 | No issues
C002 | Shopping Complex B | T742 | Steel Framework Setup | Mike Adams | Completed | Medium | 2023-12-11 | 2023-12-26 | 2023-12-26 | 100 | Concrete | Market Street | 23569.4 | 47603.27 | No issues
C004 | Warehouse D | T372 | Roofing | Sarah Johnson | In Progress | Medium | 2024-04-27 | 2024-05-25 |  | 86 | Concrete | Industrial Park | 33174.42 | 28693.49 | In progress
C001 | Residential Building A | T988 | Electrical Wiring | Sarah Johnson | Not Started | High | 2024-02-16 | 2024-03-11 |  | 0 | Cement | Plot 21, Riverside | 9070.05 | 0 | Not started
C004 | Warehouse D | T310 | Site Survey | Rachel Green | Blocked | High | 2023-09-13 | 2023-10-04 |  | 0 | Concrete | Industrial Park | 42011.31 | 45258.89 | Not started
C002 | Shopping Complex B | T621 | Roofing | Carlos Rivera | Completed | Low | 2023-01-16 | 2023-01-29 | 2023-01-29 | 100 | Cement | Market Street | 27790.39 | 50256.04 | No issues
C001 | Residential Building A | T505 | Foundation Excavation | John Miller | Not Started | Low | 2023-12-04 | 2023-12-31 |  | 0 | Paint | Plot 21, Riverside | 7858.33 | 0 | Not started
C001 | Residential Building A | T928 | Plumbing Installations | Grace Allen | In Progress | Low | 2023-05-15 | 2023-05-27 |  | 34 | Paint | Plot 21, Riverside | 25446.43 | 26124.13 | In progress
C003 | Office Tower C | T348 | Site Survey | Emma White | In Progress | Medium | 2023-07-14 | 2023-07-31 |  | 80 | Cement | Downtown Avenue | 33057.62 | 32436.08 | In progress
C001 | Residential Building A | T257 | Site Survey | Mike Adams | Not Started | High | 2024-03-17 | 2024-03-25 |  | 0 | Copper Wires | Plot 21, Riverside | 31004.75 | 0 | Not started
C002 | Shopping Complex B | T758 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2023-08-02 | 2023-08-09 |  | 60 | Cement | Market Street | 29387.68 | 50860.13 | In progress
C003 | Office Tower C | T508 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2024-06-25 | 2024-07-10 |  | 66 | Paint | Downtown Avenue | 5119.26 | 5851.65 | In progress
C004 | Warehouse D | T630 | Foundation Excavation | John Miller | Completed | Medium | 2024-07-18 | 2024-07-28 | 2024-07-28 | 100 | PVC Pipes | Industrial Park | 46064.06 | 45070.05 | No issues
C004 | Warehouse D | T814 | Steel Framework Setup | Grace Allen | In Progress | High | 2023-03-11 | 2023-04-03 |  | 45 | Steel Beams | Industrial Park | 14544.01 | 13841.7 | In progress
C001 | Residential Building A | T814 | Electrical Wiring | John Miller | Blocked | Medium | 2023-01-16 | 2023-01-29 |  | 0 | Copper Wires | Plot 21, Riverside | 14336.57 | 14636.74 | Not started
C004 | Warehouse D | T345 | Plumbing Installations | Rachel Green | In Progress | Medium | 2024-05-16 | 2024-06-06 |  | 95 | Roofing Sheets | Industrial Park | 33853.85 | 32922.88 | In progress
C003 | Office Tower C | T834 | Concrete Pouring | Grace Allen | Not Started | High | 2023-01-26 | 2023-02-23 |  | 0 | Paint | Downtown Avenue | 6216.46 | 0 | Not started
C003 | Office Tower C | T909 | Interior Painting | Rachel Green | Blocked | Medium | 2023-12-19 | 2024-01-18 |  | 0 | Cement | Downtown Avenue | 20793.7 | 16564.86 | Not started
C002 | Shopping Complex B | T529 | Foundation Excavation | Rachel Green | Completed | High | 2023-09-21 | 2023-10-12 | 2023-10-12 | 100 | Steel Beams | Market Street | 32894.71 | 53226.67 | No issues
C004 | Warehouse D | T349 | Interior Painting | Sarah Johnson | Completed | Low | 2024-07-03 | 2024-08-02 | 2024-08-02 | 100 | Rebar | Industrial Park | 30943.49 | 30097.72 | No issues
C001 | Residential Building A | T809 | Roofing | Emma White | Blocked | Low | 2024-08-21 | 2024-08-31 |  | 0 | Copper Wires | Plot 21, Riverside | 16370.69 | 19038.16 | Not started
C001 | Residential Building A | T153 | Plumbing Installations | Grace Allen | In Progress | Medium | 2024-10-04 | 2024-10-23 |  | 48 | Paint | Plot 21, Riverside | 43796.57 | 43234.19 | In progress
C003 | Office Tower C | T524 | Plumbing Installations | Grace Allen | In Progress | High | 2024-11-05 | 2024-12-01 |  | 18 | Rebar | Downtown Avenue | 43097.47 | 50441.29 | In progress
C002 | Shopping Complex B | T948 | Roofing | Dave Brown | Blocked | Low | 2024-05-27 | 2024-06-17 |  | 0 | PVC Pipes | Market Street | 47954.59 | 56636.19 | Not started
C002 | Shopping Complex B | T945 | Interior Painting | Grace Allen | Completed | Low | 2023-09-05 | 2023-09-19 | 2023-09-19 | 100 | Concrete | Market Street | 20495.22 | 41027.03 | No issues
C003 | Office Tower C | T234 | Site Survey | John Miller | Completed | Medium | 2024-04-15 | 2024-04-29 | 2024-04-29 | 100 | Steel Beams | Downtown Avenue | 31610.31 | 21575.24 | No issues
C002 | Shopping Complex B | T381 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2023-09-22 | 2023-10-15 | 2023-10-15 | 100 | Cement | Market Street | 35867.59 | 68472.41 | No issues
C001 | Residential Building A | T936 | Foundation Excavation | Carlos Rivera | Completed | Low | 2023-12-21 | 2024-01-01 | 2024-01-01 | 100 | Steel Beams | Plot 21, Riverside | 41186.77 | 49384.71 | No issues
C004 | Warehouse D | T176 | Roofing | Grace Allen | Not Started | High | 2023-02-22 | 2023-03-09 |  | 0 | Steel Beams | Industrial Park | 41149.41 | 0 | Not started
C003 | Office Tower C | T855 | Foundation Excavation | Mike Adams | Not Started | High | 2023-10-14 | 2023-11-10 |  | 0 | Rebar | Downtown Avenue | 41470.95 | 0 | Not started
C004 | Warehouse D | T345 | Interior Painting | Grace Allen | Not Started | Medium | 2023-05-19 | 2023-06-03 |  | 0 | Rebar | Industrial Park | 28003.22 | 0 | Not started
C004 | Warehouse D | T898 | Concrete Pouring | Mike Adams | Blocked | Low | 2023-09-25 | 2023-10-23 |  | 0 | Roofing Sheets | Industrial Park | 18984.15 | 20198.31 | Not started
C003 | Office Tower C | T509 | Interior Painting | Mike Adams | Blocked | High | 2024-05-19 | 2024-05-30 |  | 0 | PVC Pipes | Downtown Avenue | 41609.08 | 46438.83 | Not started
C002 | Shopping Complex B | T476 | Steel Framework Setup | Emma White | Blocked | Medium | 2024-09-27 | 2024-10-22 |  | 0 | Copper Wires | Market Street | 21552.61 | 45375.94 | Not started
C003 | Office Tower C | T467 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-10-02 | 2023-10-27 |  | 0 | Cement | Downtown Avenue | 29643.11 | 0 | Not started
C002 | Shopping Complex B | T265 | Roofing | Dave Brown | Blocked | Low | 2023-06-20 | 2023-07-11 |  | 0 | PVC Pipes | Market Street | 23356.3 | 39686.42 | Not started
C001 | Residential Building A | T813 | Foundation Excavation | Mike Adams | Completed | Medium | 2024-10-03 | 2024-10-13 | 2024-10-13 | 100 | Roofing Sheets | Plot 21, Riverside | 43848.61 | 42460.59 | No issues
C002 | Shopping Complex B | T772 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-10-06 | 2024-10-30 | 2024-10-30 | 100 | Roofing Sheets | Market Street | 30802.6 | 52173.95 | No issues
C004 | Warehouse D | T953 | Steel Framework Setup | Grace Allen | In Progress | High | 2023-02-04 | 2023-02-27 |  | 48 | Concrete | Industrial Park | 5074.09 | 5823.8 | In progress
C001 | Residential Building A | T685 | Electrical Wiring | Carlos Rivera | Blocked | High | 2023-01-05 | 2023-01-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 19536.6 | 13123.12 | Not started
C003 | Office Tower C | T451 | Electrical Wiring | Dave Brown | In Progress | High | 2023-01-04 | 2023-01-18 |  | 85 | Roofing Sheets | Downtown Avenue | 38812.77 | 42130.56 | In progress
C004 | Warehouse D | T627 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-05-23 | 2024-06-02 |  | 0 | Roofing Sheets | Industrial Park | 32572.37 | 25031.94 | Not started
C002 | Shopping Complex B | T979 | Roofing | Emma White | In Progress | Medium | 2024-07-17 | 2024-07-26 |  | 50 | Rebar | Market Street | 39134.04 | 65856.95 | In progress
C004 | Warehouse D | T197 | Electrical Wiring | Mike Adams | Blocked | High | 2023-10-09 | 2023-10-17 |  | 0 | Cement | Industrial Park | 10009.77 | 10357.86 | Not started
C003 | Office Tower C | T537 | Site Survey | Carlos Rivera | Completed | Medium | 2023-04-27 | 2023-05-24 | 2023-05-24 | 100 | Copper Wires | Downtown Avenue | 8313.95 | 5514.12 | No issues
C002 | Shopping Complex B | T193 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-01-12 | 2024-02-06 |  | 0 | Rebar | Market Street | 46039.14 | 0 | Not started
C002 | Shopping Complex B | T499 | Concrete Pouring | Grace Allen | Not Started | Low | 2023-03-15 | 2023-03-25 |  | 0 | PVC Pipes | Market Street | 38218.4 | 0 | Not started
C002 | Shopping Complex B | T145 | Steel Framework Setup | Dave Brown | In Progress | Low | 2023-06-05 | 2023-06-30 |  | 35 | Concrete | Market Street | 47958.49 | 61381.95 | In progress
C003 | Office Tower C | T580 | Roofing | Mike Adams | Not Started | Medium | 2023-11-22 | 2023-12-11 |  | 0 | Cement | Downtown Avenue | 29887.54 | 0 | Not started
C004 | Warehouse D | T118 | Electrical Wiring | Grace Allen | In Progress | Medium | 2024-07-26 | 2024-08-13 |  | 39 | Copper Wires | Industrial Park | 22805.16 | 19097.01 | In progress
C004 | Warehouse D | T857 | Interior Painting | Dave Brown | Not Started | Medium | 2024-12-16 | 2024-12-23 |  | 0 | Roofing Sheets | Industrial Park | 9806.02 | 0 | Not started
C002 | Shopping Complex B | T934 | Interior Painting | Sarah Johnson | Blocked | High | 2024-12-02 | 2024-12-25 |  | 0 | Rebar | Market Street | 26709.89 | 55303.9 | Not started
C001 | Residential Building A | T843 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-02-26 | 2024-03-13 |  | 44 | Paint | Plot 21, Riverside | 44685.63 | 50174.49 | In progress
C001 | Residential Building A | T987 | Steel Framework Setup | Mike Adams | Not Started | Medium | 2023-02-09 | 2023-03-09 |  | 0 | Paint | Plot 21, Riverside | 9544.91 | 0 | Not started
C001 | Residential Building A | T427 | Interior Painting | Dave Brown | Not Started | Low | 2023-08-03 | 2023-08-11 |  | 0 | Steel Beams | Plot 21, Riverside | 7258.1 | 0 | Not started
C003 | Office Tower C | T371 | Plumbing Installations | Grace Allen | Blocked | Low | 2024-12-16 | 2025-01-06 |  | 0 | Paint | Downtown Avenue | 24884.66 | 25449.43 | Not started
C004 | Warehouse D | T285 | Interior Painting | Carlos Rivera | Blocked | Low | 2023-09-18 | 2023-09-30 |  | 0 | PVC Pipes | Industrial Park | 29709.53 | 25281.96 | Not started
C004 | Warehouse D | T882 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2023-02-14 | 2023-03-08 |  | 18 | Copper Wires | Industrial Park | 6608.47 | 4681.42 | In progress
C002 | Shopping Complex B | T627 | Interior Painting | John Miller | Not Started | Medium | 2024-05-16 | 2024-05-24 |  | 0 | Copper Wires | Market Street | 42289.67 | 0 | Not started
C003 | Office Tower C | T749 | Steel Framework Setup | Dave Brown | In Progress | Low | 2023-08-03 | 2023-08-23 |  | 36 | Concrete | Downtown Avenue | 13510.51 | 15151.6 | In progress
C004 | Warehouse D | T569 | Electrical Wiring | Emma White | Blocked | High | 2024-01-21 | 2024-02-05 |  | 0 | Cement | Industrial Park | 7110.48 | 6002.05 | Not started
C003 | Office Tower C | T753 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2024-05-18 | 2024-05-25 |  | 0 | Cement | Downtown Avenue | 46994.61 | 46478.5 | Not started
C003 | Office Tower C | T651 | Roofing | Rachel Green | Not Started | Low | 2023-11-16 | 2023-11-24 |  | 0 | Concrete | Downtown Avenue | 35817.46 | 0 | Not started
C004 | Warehouse D | T667 | Foundation Excavation | John Miller | Not Started | Medium | 2023-04-04 | 2023-05-04 |  | 0 | Roofing Sheets | Industrial Park | 5833.38 | 0 | Not started
C003 | Office Tower C | T701 | Site Survey | Dave Brown | Not Started | Medium | 2023-01-21 | 2023-02-03 |  | 0 | Steel Beams | Downtown Avenue | 37257.41 | 0 | Not started
C003 | Office Tower C | T834 | Roofing | Sarah Johnson | In Progress | Low | 2024-04-20 | 2024-05-19 |  | 78 | Roofing Sheets | Downtown Avenue | 26196.25 | 17214.49 | In progress
C002 | Shopping Complex B | T470 | Roofing | Sarah Johnson | Blocked | High | 2024-09-07 | 2024-09-18 |  | 0 | Cement | Market Street | 41386.61 | 60094.22 | Not started
C003 | Office Tower C | T740 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2024-05-01 | 2024-05-23 |  | 44 | Roofing Sheets | Downtown Avenue | 11861.79 | 12740.94 | In progress
C001 | Residential Building A | T409 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-11-11 | 2024-12-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 29854.15 | 23335.71 | Not started
C003 | Office Tower C | T681 | Plumbing Installations | Emma White | Blocked | Low | 2023-09-22 | 2023-10-16 |  | 0 | Paint | Downtown Avenue | 48602.6 | 41274.13 | Not started
C004 | Warehouse D | T160 | Interior Painting | Mike Adams | Completed | Medium | 2024-10-07 | 2024-11-04 | 2024-11-04 | 100 | PVC Pipes | Industrial Park | 7333.44 | 7313.67 | No issues
C003 | Office Tower C | T208 | Electrical Wiring | Dave Brown | In Progress | High | 2023-02-16 | 2023-03-13 |  | 93 | Roofing Sheets | Downtown Avenue | 29138.15 | 34275.36 | In progress
C001 | Residential Building A | T455 | Interior Painting | Dave Brown | In Progress | Low | 2023-11-24 | 2023-12-22 |  | 75 | Concrete | Plot 21, Riverside | 6044.97 | 5768.29 | In progress
C003 | Office Tower C | T937 | Interior Painting | John Miller | In Progress | High | 2023-11-19 | 2023-12-02 |  | 43 | Copper Wires | Downtown Avenue | 35885.14 | 35029.16 | In progress
C004 | Warehouse D | T513 | Concrete Pouring | Emma White | Completed | Low | 2023-08-06 | 2023-08-13 | 2023-08-13 | 100 | PVC Pipes | Industrial Park | 29262.34 | 29352.56 | No issues
C004 | Warehouse D | T359 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2024-03-25 | 2024-04-21 |  | 22 | Steel Beams | Industrial Park | 7183.3 | 6394.38 | In progress
C004 | Warehouse D | T328 | Foundation Excavation | Rachel Green | In Progress | High | 2024-09-21 | 2024-10-02 |  | 5 | Concrete | Industrial Park | 42618.44 | 31146.03 | In progress
C004 | Warehouse D | T340 | Concrete Pouring | Emma White | Completed | Medium | 2024-11-05 | 2024-11-28 | 2024-11-28 | 100 | Concrete | Industrial Park | 30245.92 | 26398.1 | No issues
C001 | Residential Building A | T768 | Roofing | Mike Adams | In Progress | Low | 2023-07-01 | 2023-07-23 |  | 14 | PVC Pipes | Plot 21, Riverside | 26642.52 | 30650.06 | In progress
C002 | Shopping Complex B | T189 | Interior Painting | John Miller | In Progress | Medium | 2023-03-14 | 2023-04-02 |  | 93 | PVC Pipes | Market Street | 45846.98 | 74555.86 | In progress
C001 | Residential Building A | T336 | Plumbing Installations | Carlos Rivera | Completed | High | 2024-12-24 | 2025-01-11 | 2025-01-11 | 100 | Roofing Sheets | Plot 21, Riverside | 32364.22 | 37773.12 | No issues
C001 | Residential Building A | T609 | Plumbing Installations | Sarah Johnson | Completed | Low | 2023-11-10 | 2023-11-19 | 2023-11-19 | 100 | Paint | Plot 21, Riverside | 39209.61 | 33949.65 | No issues
C001 | Residential Building A | T483 | Plumbing Installations | Mike Adams | In Progress | High | 2023-03-28 | 2023-04-18 |  | 24 | Copper Wires | Plot 21, Riverside | 21764.99 | 23697.71 | In progress
C004 | Warehouse D | T929 | Roofing | Carlos Rivera | Not Started | Low | 2023-10-18 | 2023-11-03 |  | 0 | Steel Beams | Industrial Park | 21142.71 | 0 | Not started
C004 | Warehouse D | T603 | Electrical Wiring | Dave Brown | Completed | Low | 2024-05-21 | 2024-05-28 | 2024-05-28 | 100 | Paint | Industrial Park | 49815.65 | 56491.25 | No issues
C001 | Residential Building A | T395 | Plumbing Installations | Dave Brown | In Progress | High | 2024-10-08 | 2024-11-02 |  | 79 | Concrete | Plot 21, Riverside | 40158.07 | 46696.47 | In progress
C003 | Office Tower C | T586 | Concrete Pouring | Rachel Green | Completed | Low | 2024-06-09 | 2024-07-02 | 2024-07-02 | 100 | Paint | Downtown Avenue | 46543.23 | 48219.11 | No issues
C004 | Warehouse D | T531 | Roofing | Emma White | In Progress | High | 2023-01-23 | 2023-02-15 |  | 18 | PVC Pipes | Industrial Park | 36097.59 | 23564.96 | In progress
C002 | Shopping Complex B | T856 | Site Survey | Sarah Johnson | Not Started | Medium | 2024-04-07 | 2024-04-30 |  | 0 | Copper Wires | Market Street | 16941.03 | 0 | Not started
C002 | Shopping Complex B | T522 | Foundation Excavation | Dave Brown | Not Started | Medium | 2023-06-26 | 2023-07-19 |  | 0 | Copper Wires | Market Street | 31106.54 | 0 | Not started
C001 | Residential Building A | T797 | Site Survey | Sarah Johnson | Completed | Medium | 2023-12-13 | 2024-01-07 | 2024-01-07 | 100 | Roofing Sheets | Plot 21, Riverside | 6116.9 | 5947.63 | No issues
C004 | Warehouse D | T989 | Plumbing Installations | Sarah Johnson | In Progress | Medium | 2024-05-04 | 2024-05-23 |  | 42 | Cement | Industrial Park | 37893.12 | 24289.25 | In progress
C003 | Office Tower C | T287 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-10-08 | 2023-11-06 | 2023-11-06 | 100 | Paint | Downtown Avenue | 11575.98 | 10692.72 | No issues
C003 | Office Tower C | T216 | Electrical Wiring | Rachel Green | Blocked | Medium | 2023-10-13 | 2023-11-04 |  | 0 | Roofing Sheets | Downtown Avenue | 41095.75 | 49078.75 | Not started
C001 | Residential Building A | T232 | Plumbing Installations | Dave Brown | Not Started | Medium | 2023-03-07 | 2023-03-20 |  | 0 | Copper Wires | Plot 21, Riverside | 47834.04 | 0 | Not started
C004 | Warehouse D | T448 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2023-05-09 | 2023-05-23 | 2023-05-23 | 100 | Rebar | Industrial Park | 7395.67 | 6478.92 | No issues
C004 | Warehouse D | T740 | Roofing | Dave Brown | Blocked | Medium | 2023-08-05 | 2023-08-19 |  | 0 | Copper Wires | Industrial Park | 10149.37 | 10389.27 | Not started
C004 | Warehouse D | T986 | Plumbing Installations | Grace Allen | Not Started | High | 2023-11-13 | 2023-11-26 |  | 0 | Steel Beams | Industrial Park | 25547.59 | 0 | Not started
C001 | Residential Building A | T687 | Foundation Excavation | John Miller | Completed | Medium | 2024-01-25 | 2024-02-03 | 2024-02-03 | 100 | Rebar | Plot 21, Riverside | 5293.94 | 6102.67 | No issues
C002 | Shopping Complex B | T897 | Concrete Pouring | Grace Allen | Blocked | Low | 2023-07-06 | 2023-07-20 |  | 0 | Roofing Sheets | Market Street | 10106.88 | 34411.83 | Not started
C003 | Office Tower C | T903 | Interior Painting | Grace Allen | In Progress | Low | 2024-02-28 | 2024-03-25 |  | 56 | Concrete | Downtown Avenue | 15287.95 | 12122.06 | In progress
C002 | Shopping Complex B | T914 | Electrical Wiring | Emma White | Blocked | Low | 2023-07-26 | 2023-08-02 |  | 0 | Roofing Sheets | Market Street | 39315.23 | 68724.22 | Not started
C002 | Shopping Complex B | T858 | Plumbing Installations | Rachel Green | Blocked | High | 2023-10-02 | 2023-10-20 |  | 0 | Copper Wires | Market Street | 12463.69 | 39194.99 | Not started
C004 | Warehouse D | T790 | Interior Painting | Dave Brown | Not Started | High | 2023-08-07 | 2023-09-03 |  | 0 | Roofing Sheets | Industrial Park | 6349.54 | 0 | Not started
C003 | Office Tower C | T149 | Roofing | Mike Adams | Completed | Low | 2024-04-23 | 2024-05-04 | 2024-05-04 | 100 | Paint | Downtown Avenue | 11663.7 | 8205.8 | No issues
C002 | Shopping Complex B | T900 | Foundation Excavation | Grace Allen | Not Started | Low | 2024-12-23 | 2024-12-31 |  | 0 | Rebar | Market Street | 31582.99 | 0 | Not started
C003 | Office Tower C | T993 | Foundation Excavation | John Miller | Not Started | Medium | 2024-08-13 | 2024-09-10 |  | 0 | PVC Pipes | Downtown Avenue | 29934.54 | 0 | Not started
C001 | Residential Building A | T443 | Concrete Pouring | Rachel Green | Completed | Low | 2024-11-17 | 2024-12-07 | 2024-12-07 | 100 | Concrete | Plot 21, Riverside | 47536.01 | 34181.99 | No issues
C002 | Shopping Complex B | T212 | Roofing | Emma White | Not Started | Medium | 2023-09-17 | 2023-10-04 |  | 0 | Concrete | Market Street | 28385.12 | 0 | Not started
C003 | Office Tower C | T539 | Concrete Pouring | John Miller | Completed | Medium | 2024-02-08 | 2024-02-19 | 2024-02-19 | 100 | Copper Wires | Downtown Avenue | 45002.65 | 44201.62 | No issues
C004 | Warehouse D | T504 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-05-14 | 2024-05-21 | 2024-05-21 | 100 | Roofing Sheets | Industrial Park | 9423.02 | 6712.64 | No issues
C003 | Office Tower C | T175 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-05-13 | 2024-05-28 |  | 0 | Rebar | Downtown Avenue | 46549.98 | 0 | Not started
C002 | Shopping Complex B | T945 | Plumbing Installations | Grace Allen | Not Started | Medium | 2023-09-12 | 2023-09-30 |  | 0 | Steel Beams | Market Street | 47756.37 | 0 | Not started
C004 | Warehouse D | T488 | Site Survey | John Miller | Not Started | High | 2024-12-25 | 2025-01-03 |  | 0 | Paint | Industrial Park | 40646.09 | 0 | Not started
C002 | Shopping Complex B | T868 | Plumbing Installations | Dave Brown | Not Started | Low | 2023-02-27 | 2023-03-22 |  | 0 | Copper Wires | Market Street | 10688.24 | 0 | Not started
C003 | Office Tower C | T625 | Concrete Pouring | Grace Allen | Blocked | High | 2023-08-26 | 2023-09-17 |  | 0 | Roofing Sheets | Downtown Avenue | 48777.34 | 31845.21 | Not started
C002 | Shopping Complex B | T637 | Interior Painting | Carlos Rivera | Blocked | High | 2023-12-06 | 2023-12-26 |  | 0 | Rebar | Market Street | 36182.66 | 54757.31 | Not started
C002 | Shopping Complex B | T183 | Concrete Pouring | John Miller | Not Started | Low | 2023-09-09 | 2023-09-25 |  | 0 | Copper Wires | Market Street | 44576.44 | 0 | Not started
C002 | Shopping Complex B | T631 | Electrical Wiring | John Miller | Blocked | High | 2023-09-17 | 2023-10-17 |  | 0 | Cement | Market Street | 15938.94 | 43446.2 | Not started
C003 | Office Tower C | T868 | Electrical Wiring | Emma White | Completed | Medium | 2023-11-03 | 2023-11-26 | 2023-11-26 | 100 | PVC Pipes | Downtown Avenue | 25193.97 | 24372.38 | No issues
C002 | Shopping Complex B | T330 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2024-03-12 | 2024-04-10 | 2024-04-10 | 100 | PVC Pipes | Market Street | 48037.98 | 74592.27 | No issues
C001 | Residential Building A | T867 | Site Survey | Emma White | In Progress | Low | 2023-02-07 | 2023-03-08 |  | 58 | Paint | Plot 21, Riverside | 42396.99 | 40799.33 | In progress
C004 | Warehouse D | T959 | Foundation Excavation | Sarah Johnson | Blocked | High | 2024-04-18 | 2024-05-18 |  | 0 | PVC Pipes | Industrial Park | 16618.11 | 18504.6 | Not started
C004 | Warehouse D | T223 | Foundation Excavation | Dave Brown | Not Started | High | 2023-09-27 | 2023-10-16 |  | 0 | Rebar | Industrial Park | 29982.05 | 0 | Not started
C002 | Shopping Complex B | T706 | Site Survey | Carlos Rivera | Not Started | Medium | 2024-11-11 | 2024-12-10 |  | 0 | Roofing Sheets | Market Street | 42866.81 | 0 | Not started
C002 | Shopping Complex B | T369 | Steel Framework Setup | Rachel Green | Not Started | High | 2023-11-02 | 2023-11-16 |  | 0 | Rebar | Market Street | 44245.2 | 0 | Not started
C004 | Warehouse D | T703 | Interior Painting | Emma White | Completed | Medium | 2024-10-16 | 2024-10-28 | 2024-10-28 | 100 | Copper Wires | Industrial Park | 38353.29 | 33643.84 | No issues
C001 | Residential Building A | T608 | Concrete Pouring | Emma White | Not Started | Low | 2023-12-05 | 2023-12-15 |  | 0 | Rebar | Plot 21, Riverside | 48420.97 | 0 | Not started
C004 | Warehouse D | T396 | Site Survey | Emma White | In Progress | Low | 2024-09-19 | 2024-10-11 |  | 8 | PVC Pipes | Industrial Park | 15239.5 | 15174.24 | In progress
C002 | Shopping Complex B | T430 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-09-23 | 2023-10-18 |  | 40 | Roofing Sheets | Market Street | 17599.53 | 43586.76 | In progress
C003 | Office Tower C | T169 | Roofing | Carlos Rivera | Not Started | Medium | 2024-01-28 | 2024-02-10 |  | 0 | Steel Beams | Downtown Avenue | 37638.78 | 0 | Not started
C004 | Warehouse D | T469 | Interior Painting | Carlos Rivera | In Progress | Medium | 2024-07-16 | 2024-08-01 |  | 95 | Paint | Industrial Park | 9922.47 | 8336.02 | In progress
C002 | Shopping Complex B | T831 | Site Survey | Grace Allen | Completed | Medium | 2024-10-14 | 2024-11-03 | 2024-11-03 | 100 | Paint | Market Street | 32339.78 | 51968.32 | No issues
C001 | Residential Building A | T166 | Foundation Excavation | John Miller | Completed | High | 2023-08-26 | 2023-09-15 | 2023-09-15 | 100 | Rebar | Plot 21, Riverside | 27993.07 | 19034.97 | No issues
C001 | Residential Building A | T979 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2024-12-03 | 2024-12-13 |  | 14 | Paint | Plot 21, Riverside | 47302.69 | 49488.93 | In progress
C003 | Office Tower C | T981 | Electrical Wiring | Grace Allen | In Progress | Low | 2024-03-08 | 2024-04-07 |  | 63 | Concrete | Downtown Avenue | 5985.77 | 5475.34 | In progress
C004 | Warehouse D | T278 | Concrete Pouring | Rachel Green | Not Started | Medium | 2023-04-20 | 2023-05-15 |  | 0 | Paint | Industrial Park | 9528.49 | 0 | Not started
C002 | Shopping Complex B | T434 | Concrete Pouring | Emma White | Not Started | High | 2023-11-14 | 2023-11-26 |  | 0 | Copper Wires | Market Street | 49543.07 | 0 | Not started
C003 | Office Tower C | T472 | Roofing | Carlos Rivera | Completed | Low | 2024-01-11 | 2024-01-20 | 2024-01-20 | 100 | Roofing Sheets | Downtown Avenue | 34899.2 | 38015.08 | No issues
C001 | Residential Building A | T860 | Interior Painting | Dave Brown | Not Started | High | 2024-02-18 | 2024-03-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 21420.72 | 0 | Not started
C003 | Office Tower C | T121 | Concrete Pouring | Mike Adams | Blocked | Medium | 2023-07-03 | 2023-07-22 |  | 0 | Rebar | Downtown Avenue | 7084.87 | 6324.37 | Not started
C003 | Office Tower C | T437 | Concrete Pouring | Grace Allen | Completed | Low | 2023-04-19 | 2023-04-28 | 2023-04-28 | 100 | Roofing Sheets | Downtown Avenue | 12625.99 | 8252.45 | No issues
C004 | Warehouse D | T655 | Interior Painting | Sarah Johnson | Completed | High | 2024-11-16 | 2024-12-07 | 2024-12-07 | 100 | Paint | Industrial Park | 23186.73 | 26847.55 | No issues
C002 | Shopping Complex B | T302 | Interior Painting | Rachel Green | In Progress | High | 2023-05-08 | 2023-05-19 |  | 45 | Cement | Market Street | 20812.33 | 44291.5 | In progress
C002 | Shopping Complex B | T494 | Plumbing Installations | Dave Brown | Blocked | Medium | 2024-01-21 | 2024-01-28 |  | 0 | Rebar | Market Street | 15730.68 | 38518.52 | Not started
C004 | Warehouse D | T744 | Site Survey | John Miller | Blocked | High | 2023-08-23 | 2023-09-02 |  | 0 | Copper Wires | Industrial Park | 18330.22 | 14571.19 | Not started
C004 | Warehouse D | T297 | Plumbing Installations | Emma White | Completed | Medium | 2023-01-07 | 2023-01-18 | 2023-01-18 | 100 | Concrete | Industrial Park | 23974.81 | 20630.65 | No issues
C004 | Warehouse D | T680 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2024-09-12 | 2024-10-02 |  | 39 | Roofing Sheets | Industrial Park | 28796.66 | 29663.08 | In progress
C004 | Warehouse D | T768 | Concrete Pouring | Rachel Green | Completed | Medium | 2024-12-06 | 2025-01-01 | 2025-01-01 | 100 | Paint | Industrial Park | 20159.57 | 22224.46 | No issues
C002 | Shopping Complex B | T624 | Plumbing Installations | Mike Adams | Blocked | Medium | 2023-04-23 | 2023-05-11 |  | 0 | PVC Pipes | Market Street | 43686.85 | 64227.83 | Not started
C001 | Residential Building A | T748 | Roofing | Carlos Rivera | Blocked | Low | 2023-10-27 | 2023-11-03 |  | 0 | Rebar | Plot 21, Riverside | 43170.63 | 47465.54 | Not started
C004 | Warehouse D | T497 | Plumbing Installations | Grace Allen | Blocked | Low | 2024-09-25 | 2024-10-24 |  | 0 | Steel Beams | Industrial Park | 12126.19 | 13608.9 | Not started
C002 | Shopping Complex B | T638 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2023-01-23 | 2023-02-04 |  | 51 | Steel Beams | Market Street | 44144.8 | 66318.16 | In progress
C004 | Warehouse D | T514 | Electrical Wiring | Mike Adams | Completed | High | 2024-05-01 | 2024-05-26 | 2024-05-26 | 100 | PVC Pipes | Industrial Park | 38432.27 | 38288.03 | No issues
C004 | Warehouse D | T403 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2024-05-26 | 2024-06-22 |  | 0 | Roofing Sheets | Industrial Park | 49446.22 | 39340.64 | Not started
C004 | Warehouse D | T181 | Electrical Wiring | Grace Allen | In Progress | High | 2023-04-07 | 2023-04-21 |  | 46 | Steel Beams | Industrial Park | 41342.68 | 45872.64 | In progress
C001 | Residential Building A | T669 | Roofing | Emma White | Not Started | Medium | 2024-12-10 | 2024-12-26 |  | 0 | Paint | Plot 21, Riverside | 25061.14 | 0 | Not started
C002 | Shopping Complex B | T531 | Concrete Pouring | John Miller | Not Started | Low | 2024-11-02 | 2024-11-29 |  | 0 | Rebar | Market Street | 48161.11 | 0 | Not started
C001 | Residential Building A | T925 | Foundation Excavation | John Miller | In Progress | Medium | 2024-06-19 | 2024-07-02 |  | 14 | Steel Beams | Plot 21, Riverside | 47403.15 | 51008.29 | In progress
C004 | Warehouse D | T403 | Plumbing Installations | Rachel Green | Completed | High | 2024-08-27 | 2024-09-03 | 2024-09-03 | 100 | PVC Pipes | Industrial Park | 7618.34 | 8401.44 | No issues
C001 | Residential Building A | T942 | Plumbing Installations | Carlos Rivera | Not Started | High | 2023-09-21 | 2023-10-11 |  | 0 | Cement | Plot 21, Riverside | 17921.14 | 0 | Not started
C003 | Office Tower C | T696 | Interior Painting | Emma White | In Progress | Low | 2023-02-14 | 2023-03-09 |  | 57 | Roofing Sheets | Downtown Avenue | 18239.63 | 14369.55 | In progress
C003 | Office Tower C | T661 | Concrete Pouring | Grace Allen | Not Started | High | 2024-04-24 | 2024-05-12 |  | 0 | Roofing Sheets | Downtown Avenue | 14664.71 | 0 | Not started
C002 | Shopping Complex B | T402 | Roofing | Sarah Johnson | Not Started | Low | 2023-07-23 | 2023-08-10 |  | 0 | Steel Beams | Market Street | 10227.32 | 0 | Not started
C001 | Residential Building A | T249 | Foundation Excavation | Grace Allen | In Progress | High | 2023-09-06 | 2023-10-06 |  | 20 | Steel Beams | Plot 21, Riverside | 22949.07 | 20922.8 | In progress
C004 | Warehouse D | T480 | Interior Painting | Grace Allen | Completed | Medium | 2024-06-10 | 2024-06-25 | 2024-06-25 | 100 | Steel Beams | Industrial Park | 32405.75 | 37595.97 | No issues
C002 | Shopping Complex B | T207 | Site Survey | Sarah Johnson | In Progress | Low | 2023-04-22 | 2023-05-22 |  | 60 | Roofing Sheets | Market Street | 8518.65 | 35254.49 | In progress
C002 | Shopping Complex B | T546 | Electrical Wiring | Grace Allen | Not Started | High | 2024-08-25 | 2024-09-14 |  | 0 | Roofing Sheets | Market Street | 5379.86 | 0 | Not started
C003 | Office Tower C | T533 | Roofing | Sarah Johnson | Completed | Medium | 2024-05-07 | 2024-05-20 | 2024-05-20 | 100 | Rebar | Downtown Avenue | 34739.27 | 30382.6 | No issues
C003 | Office Tower C | T831 | Site Survey | Carlos Rivera | Blocked | Low | 2023-02-18 | 2023-02-28 |  | 0 | Copper Wires | Downtown Avenue | 23088.96 | 20830.29 | Not started
C003 | Office Tower C | T694 | Electrical Wiring | Grace Allen | Not Started | High | 2024-12-05 | 2024-12-24 |  | 0 | Cement | Downtown Avenue | 29161.65 | 0 | Not started
C003 | Office Tower C | T696 | Interior Painting | Emma White | Not Started | High | 2024-06-19 | 2024-07-10 |  | 0 | Copper Wires | Downtown Avenue | 25078.01 | 0 | Not started
C002 | Shopping Complex B | T714 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2024-08-08 | 2024-08-15 |  | 0 | PVC Pipes | Market Street | 9127.68 | 0 | Not started
C002 | Shopping Complex B | T552 | Steel Framework Setup | Carlos Rivera | Not Started | High | 2023-07-06 | 2023-07-16 |  | 0 | Copper Wires | Market Street | 11703.93 | 0 | Not started
C003 | Office Tower C | T782 | Interior Painting | Emma White | In Progress | Medium | 2024-11-15 | 2024-11-25 |  | 98 | Rebar | Downtown Avenue | 16199.76 | 16029.89 | In progress
C002 | Shopping Complex B | T966 | Roofing | Rachel Green | Not Started | Low | 2023-12-08 | 2024-01-06 |  | 0 | Copper Wires | Market Street | 35003.75 | 0 | Not started
C001 | Residential Building A | T977 | Site Survey | Grace Allen | Blocked | High | 2024-04-25 | 2024-05-23 |  | 0 | Copper Wires | Plot 21, Riverside | 38763.5 | 25633.99 | Not started
C004 | Warehouse D | T624 | Site Survey | Emma White | Completed | High | 2024-06-14 | 2024-07-09 | 2024-07-09 | 100 | Cement | Industrial Park | 36056.75 | 34310.55 | No issues
C004 | Warehouse D | T260 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2024-02-06 | 2024-02-20 |  | 0 | Paint | Industrial Park | 11577.64 | 11501.61 | Not started
C004 | Warehouse D | T256 | Roofing | Carlos Rivera | Not Started | High | 2024-08-10 | 2024-08-29 |  | 0 | Paint | Industrial Park | 29283.79 | 0 | Not started
C004 | Warehouse D | T945 | Concrete Pouring | Rachel Green | Blocked | Medium | 2024-09-27 | 2024-10-23 |  | 0 | Steel Beams | Industrial Park | 45844.14 | 36370.67 | Not started
C004 | Warehouse D | T838 | Foundation Excavation | Rachel Green | Completed | High | 2024-11-01 | 2024-11-21 | 2024-11-21 | 100 | Rebar | Industrial Park | 41038.31 | 36621.44 | No issues
C002 | Shopping Complex B | T647 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-07-18 | 2024-08-05 |  | 0 | Paint | Market Street | 11105.54 | 34024.03 | Not started
C003 | Office Tower C | T292 | Foundation Excavation | Emma White | In Progress | Low | 2024-10-24 | 2024-11-02 |  | 18 | Copper Wires | Downtown Avenue | 42003.44 | 46239.83 | In progress
C003 | Office Tower C | T669 | Steel Framework Setup | Sarah Johnson | Blocked | High | 2023-03-11 | 2023-04-03 |  | 0 | PVC Pipes | Downtown Avenue | 30811.04 | 25598.08 | Not started
C003 | Office Tower C | T884 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2024-06-15 | 2024-07-12 |  | 0 | Concrete | Downtown Avenue | 32952.15 | 0 | Not started
C001 | Residential Building A | T387 | Roofing | Rachel Green | Blocked | High | 2024-03-01 | 2024-03-26 |  | 0 | Paint | Plot 21, Riverside | 36954.35 | 36598.58 | Not started
C004 | Warehouse D | T498 | Interior Painting | Rachel Green | Blocked | High | 2023-08-04 | 2023-08-25 |  | 0 | Steel Beams | Industrial Park | 6475.47 | 4372.89 | Not started
C001 | Residential Building A | T617 | Concrete Pouring | Grace Allen | Completed | Low | 2023-03-05 | 2023-03-22 | 2023-03-22 | 100 | Copper Wires | Plot 21, Riverside | 43713.84 | 48300.64 | No issues
C003 | Office Tower C | T456 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-06-13 | 2023-07-06 |  | 0 | Steel Beams | Downtown Avenue | 41696.19 | 0 | Not started
C002 | Shopping Complex B | T640 | Roofing | Sarah Johnson | Completed | Medium | 2023-10-11 | 2023-11-10 | 2023-11-10 | 100 | Steel Beams | Market Street | 49427.19 | 79152.83 | No issues
C004 | Warehouse D | T389 | Site Survey | Dave Brown | Completed | Low | 2024-07-15 | 2024-08-09 | 2024-08-09 | 100 | Steel Beams | Industrial Park | 28712.01 | 27586.6 | No issues
C002 | Shopping Complex B | T927 | Roofing | Grace Allen | Not Started | Low | 2024-11-28 | 2024-12-08 |  | 0 | Copper Wires | Market Street | 32650.49 | 0 | Not started
C004 | Warehouse D | T456 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-05-10 | 2023-06-03 |  | 0 | PVC Pipes | Industrial Park | 31329.62 | 0 | Not started
C002 | Shopping Complex B | T574 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-07-18 | 2024-08-15 | 2024-08-15 | 100 | PVC Pipes | Market Street | 19491.35 | 40156.92 | No issues
C002 | Shopping Complex B | T207 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2023-05-24 | 2023-06-19 |  | 0 | Steel Beams | Market Street | 23663.27 | 0 | Not started
C003 | Office Tower C | T991 | Site Survey | John Miller | Completed | Low | 2024-02-27 | 2024-03-21 | 2024-03-21 | 100 | Roofing Sheets | Downtown Avenue | 18898.15 | 12691.27 | No issues
C002 | Shopping Complex B | T952 | Interior Painting | Emma White | Not Started | Medium | 2023-11-27 | 2023-12-11 |  | 0 | Concrete | Market Street | 48917.45 | 0 | Not started
C003 | Office Tower C | T182 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2023-03-21 | 2023-04-05 | 2023-04-05 | 100 | Cement | Downtown Avenue | 18748.6 | 21170.87 | No issues
C003 | Office Tower C | T692 | Foundation Excavation | Mike Adams | In Progress | Low | 2024-02-07 | 2024-02-27 |  | 44 | Rebar | Downtown Avenue | 32552.72 | 36157.02 | In progress
C001 | Residential Building A | T766 | Interior Painting | John Miller | Completed | High | 2024-02-23 | 2024-03-11 | 2024-03-11 | 100 | Roofing Sheets | Plot 21, Riverside | 16365.05 | 12914.63 | No issues
C004 | Warehouse D | T411 | Roofing | Carlos Rivera | Not Started | Medium | 2023-02-01 | 2023-02-17 |  | 0 | Steel Beams | Industrial Park | 47715.38 | 0 | Not started
C002 | Shopping Complex B | T377 | Plumbing Installations | Grace Allen | Blocked | Low | 2023-07-11 | 2023-07-23 |  | 0 | Cement | Market Street | 47905.68 | 70112.01 | Not started
C002 | Shopping Complex B | T357 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-09-04 | 2023-09-12 |  | 0 | PVC Pipes | Market Street | 25678.28 | 0 | Not started
C003 | Office Tower C | T253 | Foundation Excavation | Sarah Johnson | Completed | High | 2023-11-25 | 2023-12-09 | 2023-12-09 | 100 | Paint | Downtown Avenue | 42423.14 | 34301.59 | No issues
C002 | Shopping Complex B | T363 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-09-03 | 2023-09-21 |  | 0 | Concrete | Market Street | 23216.35 | 0 | Not started
C002 | Shopping Complex B | T145 | Plumbing Installations | Dave Brown | Completed | High | 2024-03-10 | 2024-03-21 | 2024-03-21 | 100 | Concrete | Market Street | 14122 | 36348.82 | No issues
C001 | Residential Building A | T388 | Electrical Wiring | Dave Brown | Not Started | Medium | 2024-11-12 | 2024-12-11 |  | 0 | Steel Beams | Plot 21, Riverside | 48869.81 | 0 | Not started
C003 | Office Tower C | T987 | Steel Framework Setup | Emma White | Completed | Medium | 2024-06-08 | 2024-06-22 | 2024-06-22 | 100 | Cement | Downtown Avenue | 20293.04 | 14547.6 | No issues
C003 | Office Tower C | T691 | Roofing | Rachel Green | In Progress | High | 2023-03-18 | 2023-04-11 |  | 76 | Copper Wires | Downtown Avenue | 13616.73 | 10562.91 | In progress
C002 | Shopping Complex B | T624 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2024-09-23 | 2024-10-04 |  | 0 | Paint | Market Street | 40598.74 | 0 | Not started
C001 | Residential Building A | T370 | Foundation Excavation | Mike Adams | In Progress | Low | 2024-10-11 | 2024-11-06 |  | 90 | Roofing Sheets | Plot 21, Riverside | 47486.72 | 35721.5 | In progress
C003 | Office Tower C | T898 | Site Survey | Mike Adams | Not Started | Medium | 2023-02-22 | 2023-03-11 |  | 0 | Roofing Sheets | Downtown Avenue | 32795.12 | 0 | Not started
C004 | Warehouse D | T917 | Plumbing Installations | Rachel Green | Completed | Low | 2024-12-04 | 2024-12-12 | 2024-12-12 | 100 | Concrete | Industrial Park | 37974.28 | 36227.4 | No issues
C002 | Shopping Complex B | T255 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-07-26 | 2023-08-25 | 2023-08-25 | 100 | Cement | Market Street | 10720.54 | 36233.92 | No issues
C001 | Residential Building A | T265 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2024-04-25 | 2024-05-02 |  | 0 | Concrete | Plot 21, Riverside | 46522.12 | 51497.99 | Not started
C004 | Warehouse D | T877 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2024-06-03 | 2024-06-11 |  | 0 | Paint | Industrial Park | 31716.36 | 34614.19 | Not started
C001 | Residential Building A | T220 | Electrical Wiring | Grace Allen | Blocked | Medium | 2024-01-10 | 2024-02-05 |  | 0 | Steel Beams | Plot 21, Riverside | 26315.22 | 26151.26 | Not started
C001 | Residential Building A | T457 | Site Survey | Rachel Green | Not Started | Low | 2023-02-22 | 2023-03-06 |  | 0 | PVC Pipes | Plot 21, Riverside | 41590.14 | 0 | Not started
C004 | Warehouse D | T292 | Plumbing Installations | John Miller | Completed | Medium | 2023-03-21 | 2023-04-14 | 2023-04-14 | 100 | Paint | Industrial Park | 23509.25 | 23765 | No issues
C004 | Warehouse D | T304 | Interior Painting | Dave Brown | Not Started | High | 2024-09-28 | 2024-10-21 |  | 0 | Concrete | Industrial Park | 13719.2 | 0 | Not started
C002 | Shopping Complex B | T770 | Electrical Wiring | John Miller | Blocked | Low | 2024-10-12 | 2024-10-21 |  | 0 | Copper Wires | Market Street | 35583.52 | 61040.82 | Not started
C003 | Office Tower C | T247 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-03-22 | 2023-04-15 |  | 37 | Copper Wires | Downtown Avenue | 43026.24 | 43017.5 | In progress
C004 | Warehouse D | T958 | Steel Framework Setup | Rachel Green | In Progress | High | 2023-10-05 | 2023-10-16 |  | 86 | Rebar | Industrial Park | 46023.97 | 42119.72 | In progress
C003 | Office Tower C | T974 | Interior Painting | Rachel Green | Not Started | Low | 2023-07-21 | 2023-08-07 |  | 0 | Rebar | Downtown Avenue | 28370.3 | 0 | Not started
C001 | Residential Building A | T421 | Foundation Excavation | Rachel Green | In Progress | High | 2023-09-09 | 2023-09-25 |  | 21 | Steel Beams | Plot 21, Riverside | 48418.94 | 47123.94 | In progress
C003 | Office Tower C | T851 | Foundation Excavation | Emma White | Completed | Low | 2024-07-17 | 2024-08-02 | 2024-08-02 | 100 | Paint | Downtown Avenue | 46826.79 | 50649.9 | No issues
C004 | Warehouse D | T123 | Plumbing Installations | John Miller | Completed | High | 2024-06-27 | 2024-07-11 | 2024-07-11 | 100 | PVC Pipes | Industrial Park | 36874.1 | 27017.72 | No issues
C004 | Warehouse D | T787 | Foundation Excavation | Mike Adams | Completed | High | 2023-02-13 | 2023-03-01 | 2023-03-01 | 100 | Concrete | Industrial Park | 21647.82 | 25804.01 | No issues
C004 | Warehouse D | T370 | Site Survey | Mike Adams | Not Started | Low | 2023-02-27 | 2023-03-12 |  | 0 | Cement | Industrial Park | 34576.66 | 0 | Not started
C003 | Office Tower C | T641 | Roofing | Mike Adams | Not Started | Medium | 2024-05-11 | 2024-06-10 |  | 0 | Copper Wires | Downtown Avenue | 34791.18 | 0 | Not started
C004 | Warehouse D | T630 | Electrical Wiring | Dave Brown | Not Started | Medium | 2023-04-24 | 2023-05-18 |  | 0 | Roofing Sheets | Industrial Park | 34330.82 | 0 | Not started
C002 | Shopping Complex B | T649 | Roofing | Sarah Johnson | In Progress | Medium | 2024-11-09 | 2024-12-04 |  | 25 | Concrete | Market Street | 19608.75 | 46781.93 | In progress
C001 | Residential Building A | T614 | Site Survey | John Miller | Completed | Low | 2024-07-26 | 2024-08-20 | 2024-08-20 | 100 | Steel Beams | Plot 21, Riverside | 6098.74 | 4985.16 | No issues
C001 | Residential Building A | T677 | Roofing | Carlos Rivera | Not Started | Medium | 2024-06-25 | 2024-07-23 |  | 0 | Concrete | Plot 21, Riverside | 38327.82 | 0 | Not started
C002 | Shopping Complex B | T722 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-09-18 | 2023-09-30 |  | 0 | Cement | Market Street | 21580.3 | 45655.11 | Not started
C004 | Warehouse D | T918 | Roofing | Sarah Johnson | Completed | High | 2024-11-01 | 2024-11-15 | 2024-11-15 | 100 | Roofing Sheets | Industrial Park | 18383.07 | 17271.05 | No issues
C003 | Office Tower C | T605 | Steel Framework Setup | Emma White | Blocked | High | 2024-05-17 | 2024-06-09 |  | 0 | Cement | Downtown Avenue | 43792.73 | 31341.28 | Not started
C004 | Warehouse D | T171 | Roofing | John Miller | Not Started | Low | 2024-01-07 | 2024-01-29 |  | 0 | Copper Wires | Industrial Park | 42804.44 | 0 | Not started
C003 | Office Tower C | T370 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2024-04-02 | 2024-04-20 |  | 0 | Rebar | Downtown Avenue | 42563.6 | 48108.02 | Not started
C003 | Office Tower C | T348 | Site Survey | Emma White | Completed | Low | 2024-01-20 | 2024-02-02 | 2024-02-02 | 100 | Steel Beams | Downtown Avenue | 31999.21 | 33386.62 | No issues
C002 | Shopping Complex B | T649 | Steel Framework Setup | Dave Brown | Completed | High | 2023-09-07 | 2023-10-02 | 2023-10-02 | 100 | Roofing Sheets | Market Street | 33943.13 | 51976.46 | No issues
C004 | Warehouse D | T573 | Interior Painting | Mike Adams | Blocked | Low | 2023-01-04 | 2023-01-13 |  | 0 | Concrete | Industrial Park | 20504.45 | 14640.4 | Not started
C003 | Office Tower C | T200 | Steel Framework Setup | John Miller | In Progress | Medium | 2023-01-14 | 2023-01-28 |  | 19 | Rebar | Downtown Avenue | 31977.37 | 32851.52 | In progress
C001 | Residential Building A | T869 | Plumbing Installations | Mike Adams | Completed | High | 2023-04-24 | 2023-05-02 | 2023-05-02 | 100 | Concrete | Plot 21, Riverside | 21852.98 | 18278.04 | No issues
C003 | Office Tower C | T392 | Roofing | Dave Brown | Completed | High | 2024-03-14 | 2024-03-30 | 2024-03-30 | 100 | Rebar | Downtown Avenue | 30481.98 | 21352.71 | No issues
C003 | Office Tower C | T580 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-11-27 | 2023-12-17 |  | 0 | PVC Pipes | Downtown Avenue | 45639.42 | 35964.98 | Not started
C003 | Office Tower C | T541 | Electrical Wiring | Emma White | Completed | Low | 2024-12-06 | 2025-01-03 | 2025-01-03 | 100 | Rebar | Downtown Avenue | 46255.72 | 38519.21 | No issues
C002 | Shopping Complex B | T224 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2023-03-24 | 2023-03-31 |  | 0 | PVC Pipes | Market Street | 10229.01 | 0 | Not started
C002 | Shopping Complex B | T721 | Roofing | Carlos Rivera | Completed | Medium | 2023-05-23 | 2023-06-18 | 2023-06-18 | 100 | Rebar | Market Street | 18123.08 | 46691.45 | No issues
C002 | Shopping Complex B | T882 | Plumbing Installations | Grace Allen | Not Started | Medium | 2024-05-12 | 2024-05-26 |  | 0 | PVC Pipes | Market Street | 42590.39 | 0 | Not started
C003 | Office Tower C | T889 | Site Survey | Dave Brown | In Progress | Medium | 2024-02-11 | 2024-02-25 |  | 87 | PVC Pipes | Downtown Avenue | 12603.92 | 9049.32 | In progress
C002 | Shopping Complex B | T760 | Steel Framework Setup | Dave Brown | Completed | Low | 2023-04-28 | 2023-05-25 | 2023-05-25 | 100 | Steel Beams | Market Street | 22341.98 | 41998.96 | No issues
C001 | Residential Building A | T419 | Electrical Wiring | Mike Adams | In Progress | High | 2024-09-12 | 2024-10-11 |  | 1 | Rebar | Plot 21, Riverside | 49206.6 | 54039.21 | In progress
C003 | Office Tower C | T684 | Interior Painting | Emma White | Blocked | Low | 2023-10-10 | 2023-10-26 |  | 0 | Cement | Downtown Avenue | 31971.89 | 19549.56 | Not started
C001 | Residential Building A | T192 | Interior Painting | John Miller | Completed | Medium | 2023-12-03 | 2023-12-22 | 2023-12-22 | 100 | Steel Beams | Plot 21, Riverside | 14296.89 | 13428.44 | No issues
C003 | Office Tower C | T453 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-12-19 | 2025-01-13 |  | 0 | Paint | Downtown Avenue | 28358.36 | 0 | Not started
C001 | Residential Building A | T131 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2023-01-01 | 2023-01-20 |  | 0 | PVC Pipes | Plot 21, Riverside | 49769.89 | 37978.41 | Not started
C003 | Office Tower C | T211 | Steel Framework Setup | Emma White | Blocked | Low | 2024-10-25 | 2024-11-13 |  | 0 | Roofing Sheets | Downtown Avenue | 19720.37 | 18100.11 | Not started
C001 | Residential Building A | T958 | Roofing | Grace Allen | Not Started | Low | 2024-05-04 | 2024-05-14 |  | 0 | Rebar | Plot 21, Riverside | 24857.61 | 0 | Not started
C004 | Warehouse D | T237 | Electrical Wiring | John Miller | Not Started | High | 2023-10-24 | 2023-11-09 |  | 0 | Paint | Industrial Park | 42555.94 | 0 | Not started
C001 | Residential Building A | T636 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-06-19 | 2024-07-05 |  | 0 | Roofing Sheets | Plot 21, Riverside | 20040.16 | 18366.52 | Not started
C004 | Warehouse D | T167 | Foundation Excavation | Mike Adams | Blocked | Low | 2024-08-21 | 2024-09-14 |  | 0 | Cement | Industrial Park | 23456.73 | 23265.85 | Not started
C004 | Warehouse D | T322 | Concrete Pouring | Mike Adams | In Progress | Low | 2024-02-26 | 2024-03-19 |  | 26 | Cement | Industrial Park | 23632.55 | 15715.39 | In progress
C004 | Warehouse D | T997 | Plumbing Installations | John Miller | Blocked | Medium | 2023-07-28 | 2023-08-05 |  | 0 | PVC Pipes | Industrial Park | 24699.29 | 27719.7 | Not started
C002 | Shopping Complex B | T618 | Site Survey | Carlos Rivera | In Progress | Low | 2024-04-24 | 2024-05-13 |  | 80 | Roofing Sheets | Market Street | 42166.79 | 52057.13 | In progress
C002 | Shopping Complex B | T425 | Steel Framework Setup | Rachel Green | Not Started | High | 2023-03-13 | 2023-04-04 |  | 0 | Rebar | Market Street | 11001.94 | 0 | Not started
C004 | Warehouse D | T570 | Electrical Wiring | Grace Allen | Completed | High | 2024-07-25 | 2024-08-13 | 2024-08-13 | 100 | Roofing Sheets | Industrial Park | 11296.82 | 12092.58 | No issues
C001 | Residential Building A | T733 | Roofing | Grace Allen | Not Started | High | 2023-05-17 | 2023-06-10 |  | 0 | Rebar | Plot 21, Riverside | 8068.27 | 0 | Not started
C003 | Office Tower C | T573 | Concrete Pouring | Dave Brown | Not Started | High | 2023-05-12 | 2023-06-08 |  | 0 | Copper Wires | Downtown Avenue | 17453.57 | 0 | Not started
C002 | Shopping Complex B | T223 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-04-28 | 2024-05-07 |  | 0 | Paint | Market Street | 21596.36 | 43716.18 | Not started
C003 | Office Tower C | T901 | Roofing | John Miller | Blocked | Medium | 2023-06-24 | 2023-07-06 |  | 0 | Concrete | Downtown Avenue | 41699.15 | 28600 | Not started
C003 | Office Tower C | T392 | Electrical Wiring | Mike Adams | Blocked | Low | 2023-08-07 | 2023-08-22 |  | 0 | Cement | Downtown Avenue | 14834.07 | 10768.57 | Not started
C001 | Residential Building A | T578 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-01-16 | 2024-01-31 |  | 2 | Concrete | Plot 21, Riverside | 23922.85 | 18218.89 | In progress
C002 | Shopping Complex B | T177 | Roofing | John Miller | Not Started | Low | 2023-05-28 | 2023-06-18 |  | 0 | Roofing Sheets | Market Street | 26678.2 | 0 | Not started
C004 | Warehouse D | T940 | Roofing | John Miller | Completed | Low | 2024-06-01 | 2024-06-20 | 2024-06-20 | 100 | Rebar | Industrial Park | 41716.99 | 33789 | No issues
C001 | Residential Building A | T207 | Foundation Excavation | John Miller | Not Started | High | 2024-10-17 | 2024-10-31 |  | 0 | Steel Beams | Plot 21, Riverside | 35813.89 | 0 | Not started
C002 | Shopping Complex B | T696 | Site Survey | Sarah Johnson | Completed | High | 2024-12-20 | 2024-12-28 | 2024-12-28 | 100 | Steel Beams | Market Street | 11598.67 | 34487.71 | No issues
C004 | Warehouse D | T840 | Concrete Pouring | Grace Allen | Blocked | High | 2023-07-15 | 2023-08-06 |  | 0 | Steel Beams | Industrial Park | 42222.7 | 46647.26 | Not started
C004 | Warehouse D | T857 | Interior Painting | Carlos Rivera | Blocked | High | 2024-05-03 | 2024-06-01 |  | 0 | Steel Beams | Industrial Park | 23463.55 | 23924.32 | Not started
C001 | Residential Building A | T856 | Plumbing Installations | John Miller | Blocked | Medium | 2024-03-20 | 2024-03-31 |  | 0 | Paint | Plot 21, Riverside | 27637.84 | 28538.93 | Not started
C002 | Shopping Complex B | T748 | Plumbing Installations | Sarah Johnson | Completed | Low | 2023-04-05 | 2023-04-20 | 2023-04-20 | 100 | Cement | Market Street | 45222.93 | 70089.96 | No issues
C003 | Office Tower C | T360 | Plumbing Installations | John Miller | In Progress | Low | 2024-04-23 | 2024-05-01 |  | 52 | Cement | Downtown Avenue | 22986.4 | 23169.12 | In progress
C003 | Office Tower C | T308 | Roofing | Rachel Green | In Progress | Medium | 2023-06-23 | 2023-07-21 |  | 71 | Concrete | Downtown Avenue | 41793.43 | 29957.18 | In progress
C004 | Warehouse D | T593 | Roofing | John Miller | Completed | Medium | 2024-01-02 | 2024-01-24 | 2024-01-24 | 100 | Concrete | Industrial Park | 24470.45 | 15579.85 | No issues
C004 | Warehouse D | T491 | Site Survey | Mike Adams | Blocked | High | 2024-04-22 | 2024-05-20 |  | 0 | Rebar | Industrial Park | 21814.83 | 14037.83 | Not started
C001 | Residential Building A | T532 | Foundation Excavation | Emma White | In Progress | Low | 2024-11-05 | 2024-11-17 |  | 46 | Copper Wires | Plot 21, Riverside | 33174.44 | 22429.36 | In progress
C001 | Residential Building A | T439 | Interior Painting | Dave Brown | Completed | Low | 2023-04-25 | 2023-05-05 | 2023-05-05 | 100 | Cement | Plot 21, Riverside | 47379.86 | 36880.83 | No issues
C003 | Office Tower C | T495 | Roofing | Emma White | Blocked | Low | 2023-07-18 | 2023-08-07 |  | 0 | Copper Wires | Downtown Avenue | 39775.03 | 25676.3 | Not started
C002 | Shopping Complex B | T387 | Site Survey | John Miller | Not Started | Low | 2023-04-24 | 2023-05-04 |  | 0 | PVC Pipes | Market Street | 49739.34 | 0 | Not started
C003 | Office Tower C | T449 | Roofing | Emma White | Completed | High | 2024-12-16 | 2025-01-07 | 2025-01-07 | 100 | PVC Pipes | Downtown Avenue | 23303.93 | 27526.72 | No issues
C003 | Office Tower C | T108 | Interior Painting | Rachel Green | Completed | Medium | 2024-01-13 | 2024-02-02 | 2024-02-02 | 100 | Paint | Downtown Avenue | 40432.08 | 31103.61 | No issues
C003 | Office Tower C | T441 | Site Survey | John Miller | Blocked | Medium | 2024-11-11 | 2024-11-25 |  | 0 | PVC Pipes | Downtown Avenue | 35384.33 | 22169 | Not started
C001 | Residential Building A | T160 | Concrete Pouring | John Miller | Blocked | Low | 2024-08-07 | 2024-09-02 |  | 0 | PVC Pipes | Plot 21, Riverside | 40029.23 | 27308.82 | Not started
C001 | Residential Building A | T918 | Electrical Wiring | Mike Adams | Completed | Low | 2024-10-26 | 2024-11-10 | 2024-11-10 | 100 | Roofing Sheets | Plot 21, Riverside | 14691.88 | 17292.22 | No issues
C004 | Warehouse D | T311 | Plumbing Installations | Mike Adams | Blocked | Low | 2024-05-05 | 2024-05-27 |  | 0 | Paint | Industrial Park | 34171.68 | 28559.8 | Not started
C002 | Shopping Complex B | T552 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-12-21 | 2024-01-01 |  | 46 | Rebar | Market Street | 41509.56 | 72907.15 | In progress
C001 | Residential Building A | T894 | Interior Painting | Mike Adams | Blocked | Medium | 2024-02-06 | 2024-02-25 |  | 0 | Copper Wires | Plot 21, Riverside | 12565.82 | 11641.25 | Not started
C001 | Residential Building A | T532 | Steel Framework Setup | Dave Brown | In Progress | High | 2024-05-08 | 2024-06-06 |  | 43 | Cement | Plot 21, Riverside | 37869.85 | 24455.52 | In progress
C003 | Office Tower C | T284 | Interior Painting | Mike Adams | Completed | Low | 2023-06-15 | 2023-07-14 | 2023-07-14 | 100 | PVC Pipes | Downtown Avenue | 28690.36 | 22969.29 | No issues
C003 | Office Tower C | T919 | Interior Painting | Emma White | Completed | High | 2024-03-09 | 2024-03-25 | 2024-03-25 | 100 | Copper Wires | Downtown Avenue | 20994.95 | 23026.4 | No issues
C003 | Office Tower C | T435 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2023-10-02 | 2023-10-30 |  | 0 | Paint | Downtown Avenue | 44837.53 | 28453.41 | In progress
C004 | Warehouse D | T136 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2024-02-24 | 2024-03-08 |  | 0 | Cement | Industrial Park | 44212.82 | 44951.26 | Not started
C002 | Shopping Complex B | T805 | Interior Painting | Dave Brown | Not Started | Low | 2023-01-02 | 2023-01-16 |  | 0 | Copper Wires | Market Street | 40058.21 | 0 | Not started
C002 | Shopping Complex B | T299 | Site Survey | Mike Adams | Blocked | Low | 2023-03-22 | 2023-04-11 |  | 0 | Paint | Market Street | 49376.08 | 64466.09 | Not started
C004 | Warehouse D | T576 | Roofing | Rachel Green | Blocked | Low | 2024-03-05 | 2024-03-22 |  | 0 | Steel Beams | Industrial Park | 25224.27 | 29232.88 | Not started
C004 | Warehouse D | T724 | Concrete Pouring | John Miller | Completed | High | 2024-03-17 | 2024-04-07 | 2024-04-07 | 100 | PVC Pipes | Industrial Park | 22858.39 | 21923.64 | No issues
C001 | Residential Building A | T180 | Electrical Wiring | Emma White | Not Started | Medium | 2023-03-11 | 2023-04-10 |  | 0 | Roofing Sheets | Plot 21, Riverside | 32258.94 | 0 | Not started
C003 | Office Tower C | T750 | Concrete Pouring | Emma White | In Progress | Low | 2024-04-12 | 2024-04-19 |  | 42 | Steel Beams | Downtown Avenue | 37380.69 | 44147.67 | In progress
C003 | Office Tower C | T713 | Site Survey | Grace Allen | In Progress | Low | 2024-09-25 | 2024-10-08 |  | 23 | Rebar | Downtown Avenue | 9501.03 | 7821.23 | In progress
C004 | Warehouse D | T814 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2024-04-08 | 2024-04-21 |  | 0 | Roofing Sheets | Industrial Park | 15119.71 | 10292.12 | Not started
C003 | Office Tower C | T834 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2023-01-13 | 2023-01-28 |  | 0 | Roofing Sheets | Downtown Avenue | 39109.94 | 0 | Not started
C003 | Office Tower C | T684 | Roofing | Mike Adams | In Progress | High | 2024-11-13 | 2024-11-20 |  | 44 | Concrete | Downtown Avenue | 33354.04 | 26028.22 | In progress
C002 | Shopping Complex B | T937 | Electrical Wiring | Grace Allen | Blocked | Low | 2023-10-10 | 2023-10-20 |  | 0 | Paint | Market Street | 47179.28 | 62662.9 | Not started
C002 | Shopping Complex B | T390 | Plumbing Installations | Dave Brown | Blocked | High | 2024-02-02 | 2024-02-16 |  | 0 | Roofing Sheets | Market Street | 18022.59 | 42261.16 | Not started
C002 | Shopping Complex B | T291 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2024-07-13 | 2024-08-02 |  | 33 | PVC Pipes | Market Street | 20736.02 | 46348.22 | In progress
C002 | Shopping Complex B | T293 | Concrete Pouring | Carlos Rivera | Blocked | High | 2024-02-28 | 2024-03-25 |  | 0 | Copper Wires | Market Street | 37476.69 | 61649.88 | Not started
C002 | Shopping Complex B | T977 | Roofing | Dave Brown | Not Started | High | 2024-05-09 | 2024-06-01 |  | 0 | Steel Beams | Market Street | 44161.28 | 0 | Not started
C002 | Shopping Complex B | T538 | Site Survey | Mike Adams | Completed | Low | 2023-04-27 | 2023-05-18 | 2023-05-18 | 100 | Steel Beams | Market Street | 29846.95 | 56978.32 | No issues
C002 | Shopping Complex B | T796 | Foundation Excavation | Grace Allen | Blocked | Medium | 2024-01-25 | 2024-02-18 |  | 0 | Copper Wires | Market Street | 15751.53 | 36898.78 | Not started
C004 | Warehouse D | T896 | Steel Framework Setup | Grace Allen | Completed | Low | 2023-09-07 | 2023-09-24 | 2023-09-24 | 100 | Copper Wires | Industrial Park | 22680.3 | 23250.82 | No issues
C002 | Shopping Complex B | T272 | Plumbing Installations | Emma White | Completed | Medium | 2024-12-13 | 2025-01-01 | 2025-01-01 | 100 | Rebar | Market Street | 22484.92 | 42972.28 | No issues
C003 | Office Tower C | T154 | Roofing | Mike Adams | In Progress | Low | 2023-12-11 | 2024-01-03 |  | 62 | Copper Wires | Downtown Avenue | 40577.32 | 36113.71 | In progress
C001 | Residential Building A | T109 | Foundation Excavation | Emma White | Completed | Medium | 2024-05-28 | 2024-06-18 | 2024-06-18 | 100 | PVC Pipes | Plot 21, Riverside | 42688.67 | 25990.08 | No issues
C004 | Warehouse D | T221 | Site Survey | Mike Adams | Blocked | Low | 2023-03-05 | 2023-03-21 |  | 0 | Steel Beams | Industrial Park | 29474.79 | 25000.82 | Not started
C003 | Office Tower C | T347 | Foundation Excavation | Carlos Rivera | Blocked | High | 2023-02-06 | 2023-03-07 |  | 0 | Roofing Sheets | Downtown Avenue | 28062.45 | 17293.99 | Not started
C004 | Warehouse D | T828 | Concrete Pouring | Grace Allen | Blocked | High | 2024-01-24 | 2024-02-01 |  | 0 | Roofing Sheets | Industrial Park | 40946.62 | 34725 | Not started
C001 | Residential Building A | T798 | Roofing | Emma White | Blocked | Medium | 2023-04-21 | 2023-05-06 |  | 0 | Concrete | Plot 21, Riverside | 27841.31 | 31959.95 | Not started
C001 | Residential Building A | T903 | Site Survey | Grace Allen | Not Started | Medium | 2023-02-04 | 2023-03-05 |  | 0 | Paint | Plot 21, Riverside | 35622.19 | 0 | Not started
C003 | Office Tower C | T590 | Roofing | Rachel Green | Blocked | Low | 2023-04-24 | 2023-05-16 |  | 0 | Concrete | Downtown Avenue | 6194.91 | 5336.4 | Not started
C003 | Office Tower C | T566 | Site Survey | Grace Allen | Completed | Medium | 2024-04-28 | 2024-05-27 | 2024-05-27 | 100 | Cement | Downtown Avenue | 28544.56 | 19156.44 | No issues
C003 | Office Tower C | T298 | Roofing | Grace Allen | Completed | Low | 2024-08-13 | 2024-09-03 | 2024-09-03 | 100 | PVC Pipes | Downtown Avenue | 10806.69 | 7006.19 | No issues
C003 | Office Tower C | T792 | Concrete Pouring | Dave Brown | Not Started | Low | 2023-04-10 | 2023-04-26 |  | 0 | PVC Pipes | Downtown Avenue | 30442.52 | 0 | Not started
C004 | Warehouse D | T637 | Plumbing Installations | Grace Allen | Completed | Medium | 2023-12-14 | 2024-01-06 | 2024-01-06 | 100 | Rebar | Industrial Park | 35415.02 | 36971.67 | No issues
C001 | Residential Building A | T164 | Plumbing Installations | Sarah Johnson | Blocked | High | 2023-10-07 | 2023-10-30 |  | 0 | Roofing Sheets | Plot 21, Riverside | 33892.49 | 32363.96 | Not started
C001 | Residential Building A | T449 | Steel Framework Setup | Rachel Green | Blocked | High | 2024-10-21 | 2024-11-17 |  | 0 | Rebar | Plot 21, Riverside | 13661.21 | 9713.76 | Not started
C002 | Shopping Complex B | T599 | Electrical Wiring | Emma White | Blocked | Low | 2023-07-08 | 2023-07-28 |  | 0 | Steel Beams | Market Street | 11902.07 | 36570.58 | Not started
C002 | Shopping Complex B | T449 | Foundation Excavation | John Miller | Not Started | Low | 2024-05-04 | 2024-05-13 |  | 0 | PVC Pipes | Market Street | 29462.49 | 0 | Not started
C002 | Shopping Complex B | T779 | Roofing | Rachel Green | Completed | Medium | 2024-09-18 | 2024-10-08 | 2024-10-08 | 100 | Cement | Market Street | 18582.59 | 40805.03 | No issues
C003 | Office Tower C | T177 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2024-07-02 | 2024-07-09 |  | 0 | PVC Pipes | Downtown Avenue | 27157.74 | 0 | Not started
C004 | Warehouse D | T487 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-11-13 | 2024-12-02 |  | 67 | Rebar | Industrial Park | 49995 | 39084.29 | In progress
C004 | Warehouse D | T718 | Site Survey | Carlos Rivera | Not Started | High | 2023-02-26 | 2023-03-06 |  | 0 | Copper Wires | Industrial Park | 7660.21 | 0 | Not started
C003 | Office Tower C | T401 | Interior Painting | Rachel Green | Completed | Low | 2023-12-14 | 2024-01-13 | 2024-01-13 | 100 | Steel Beams | Downtown Avenue | 7796.66 | 8266 | No issues
C004 | Warehouse D | T654 | Concrete Pouring | John Miller | Blocked | High | 2024-08-15 | 2024-08-31 |  | 0 | Rebar | Industrial Park | 8867.38 | 5587.43 | Not started
C002 | Shopping Complex B | T608 | Interior Painting | Emma White | Blocked | Medium | 2023-01-22 | 2023-02-03 |  | 0 | Paint | Market Street | 7654.04 | 31767.29 | Not started
C001 | Residential Building A | T209 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-04-13 | 2024-05-02 | 2024-05-02 | 100 | Concrete | Plot 21, Riverside | 15152.97 | 13335.42 | No issues
C004 | Warehouse D | T946 | Interior Painting | Grace Allen | Not Started | Low | 2023-08-16 | 2023-08-30 |  | 0 | Copper Wires | Industrial Park | 14498.05 | 0 | Not started
C003 | Office Tower C | T207 | Electrical Wiring | Mike Adams | Blocked | Low | 2023-07-26 | 2023-08-21 |  | 0 | Cement | Downtown Avenue | 39513.17 | 30358.18 | Not started
C002 | Shopping Complex B | T960 | Site Survey | Mike Adams | Not Started | Low | 2023-03-10 | 2023-04-07 |  | 0 | PVC Pipes | Market Street | 18615.66 | 0 | Not started
C002 | Shopping Complex B | T285 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2024-04-22 | 2024-05-01 |  | 0 | Steel Beams | Market Street | 32780.66 | 0 | Not started
C002 | Shopping Complex B | T386 | Electrical Wiring | Mike Adams | Not Started | High | 2024-05-22 | 2024-06-14 |  | 0 | Cement | Market Street | 11482.01 | 0 | Not started
C001 | Residential Building A | T996 | Foundation Excavation | Dave Brown | Not Started | Medium | 2023-01-03 | 2023-01-10 |  | 0 | Steel Beams | Plot 21, Riverside | 37471.37 | 0 | Not started
C003 | Office Tower C | T573 | Site Survey | Mike Adams | Not Started | Low | 2024-09-09 | 2024-09-17 |  | 0 | Paint | Downtown Avenue | 5333.29 | 0 | Not started
C002 | Shopping Complex B | T428 | Site Survey | Carlos Rivera | Not Started | High | 2023-07-08 | 2023-07-17 |  | 0 | Copper Wires | Market Street | 15140.04 | 0 | Not started
C002 | Shopping Complex B | T167 | Site Survey | Dave Brown | In Progress | High | 2024-07-19 | 2024-07-26 |  | 98 | Copper Wires | Market Street | 27334.62 | 43257.09 | In progress
C001 | Residential Building A | T153 | Site Survey | Dave Brown | In Progress | High | 2023-08-10 | 2023-08-25 |  | 3 | PVC Pipes | Plot 21, Riverside | 12639.56 | 10251.87 | In progress
C002 | Shopping Complex B | T521 | Foundation Excavation | Emma White | Not Started | Medium | 2023-05-02 | 2023-06-01 |  | 0 | Rebar | Market Street | 9716.49 | 0 | Not started
C001 | Residential Building A | T741 | Steel Framework Setup | Rachel Green | Completed | Low | 2024-12-17 | 2025-01-11 | 2025-01-11 | 100 | Roofing Sheets | Plot 21, Riverside | 42946.04 | 25816.93 | No issues
C002 | Shopping Complex B | T857 | Roofing | John Miller | In Progress | Medium | 2023-08-28 | 2023-09-24 |  | 4 | Roofing Sheets | Market Street | 12049.19 | 33464.56 | In progress
C003 | Office Tower C | T185 | Interior Painting | Grace Allen | In Progress | Medium | 2023-01-18 | 2023-01-30 |  | 0 | Paint | Downtown Avenue | 20622.69 | 22157.97 | In progress
C004 | Warehouse D | T902 | Concrete Pouring | Sarah Johnson | In Progress | High | 2024-11-04 | 2024-11-17 |  | 59 | Paint | Industrial Park | 15737.08 | 11464.08 | In progress
C004 | Warehouse D | T984 | Foundation Excavation | Sarah Johnson | Not Started | Medium | 2024-02-28 | 2024-03-26 |  | 0 | Paint | Industrial Park | 37971.55 | 0 | Not started
C001 | Residential Building A | T346 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2023-05-27 | 2023-06-06 |  | 0 | Cement | Plot 21, Riverside | 44144.14 | 0 | Not started
C002 | Shopping Complex B | T378 | Steel Framework Setup | Grace Allen | Completed | Medium | 2023-01-10 | 2023-01-24 | 2023-01-24 | 100 | Copper Wires | Market Street | 6945.48 | 32148.12 | No issues
C004 | Warehouse D | T645 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2024-11-28 | 2024-12-26 | 2024-12-26 | 100 | PVC Pipes | Industrial Park | 26584.18 | 27555.82 | No issues
C001 | Residential Building A | T624 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2024-07-26 | 2024-08-24 |  | 0 | Roofing Sheets | Plot 21, Riverside | 39092.19 | 44792.58 | Not started
C003 | Office Tower C | T737 | Plumbing Installations | Emma White | In Progress | High | 2023-01-08 | 2023-02-03 |  | 43 | PVC Pipes | Downtown Avenue | 20030.86 | 16817.99 | In progress
C003 | Office Tower C | T142 | Concrete Pouring | Grace Allen | Completed | High | 2023-06-03 | 2023-06-11 | 2023-06-11 | 100 | Paint | Downtown Avenue | 46918.69 | 38699.38 | No issues
C001 | Residential Building A | T165 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2024-08-16 | 2024-08-27 |  | 0 | PVC Pipes | Plot 21, Riverside | 8933.13 | 5517.98 | Not started
C003 | Office Tower C | T562 | Electrical Wiring | Mike Adams | Completed | Low | 2023-03-08 | 2023-03-21 | 2023-03-21 | 100 | Paint | Downtown Avenue | 35666.41 | 39814.31 | No issues
C002 | Shopping Complex B | T543 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2023-04-15 | 2023-05-03 |  | 0 | Cement | Market Street | 34248.23 | 0 | Not started
C001 | Residential Building A | T949 | Site Survey | Emma White | Not Started | High | 2023-06-09 | 2023-07-09 |  | 0 | Cement | Plot 21, Riverside | 38157.22 | 0 | Not started
C002 | Shopping Complex B | T633 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2023-06-01 | 2023-06-21 |  | 0 | Paint | Market Street | 16951.59 | 42938.56 | Not started
C004 | Warehouse D | T163 | Concrete Pouring | Dave Brown | Blocked | Medium | 2024-12-14 | 2025-01-12 |  | 0 | Rebar | Industrial Park | 38105.4 | 41652.66 | Not started
C001 | Residential Building A | T134 | Foundation Excavation | Grace Allen | In Progress | Low | 2024-04-04 | 2024-04-16 |  | 28 | PVC Pipes | Plot 21, Riverside | 44359.63 | 48194.05 | In progress
C003 | Office Tower C | T762 | Roofing | Mike Adams | In Progress | High | 2023-06-26 | 2023-07-07 |  | 97 | Roofing Sheets | Downtown Avenue | 49792.32 | 54246.99 | In progress
C004 | Warehouse D | T326 | Foundation Excavation | Dave Brown | In Progress | High | 2023-06-27 | 2023-07-25 |  | 17 | Roofing Sheets | Industrial Park | 17982.67 | 21249.24 | In progress
C004 | Warehouse D | T899 | Steel Framework Setup | Rachel Green | Blocked | High | 2023-03-22 | 2023-04-08 |  | 0 | Copper Wires | Industrial Park | 47012.91 | 41498.69 | Not started
C003 | Office Tower C | T988 | Foundation Excavation | Grace Allen | Not Started | Medium | 2024-04-26 | 2024-05-08 |  | 0 | Concrete | Downtown Avenue | 44615.74 | 0 | Not started
C004 | Warehouse D | T272 | Roofing | Rachel Green | In Progress | Medium | 2023-09-25 | 2023-10-19 |  | 20 | Paint | Industrial Park | 27692.44 | 32797.68 | In progress
C001 | Residential Building A | T496 | Electrical Wiring | Rachel Green | Not Started | High | 2023-09-16 | 2023-10-13 |  | 0 | Paint | Plot 21, Riverside | 43946.83 | 0 | Not started
C004 | Warehouse D | T331 | Plumbing Installations | Grace Allen | In Progress | Medium | 2023-10-20 | 2023-10-30 |  | 23 | PVC Pipes | Industrial Park | 6780.03 | 5134.86 | In progress
C003 | Office Tower C | T483 | Concrete Pouring | Mike Adams | Completed | Low | 2023-06-21 | 2023-07-17 | 2023-07-17 | 100 | Cement | Downtown Avenue | 46363.67 | 40161.68 | No issues
C003 | Office Tower C | T252 | Concrete Pouring | John Miller | Not Started | Medium | 2023-04-20 | 2023-05-20 |  | 0 | Roofing Sheets | Downtown Avenue | 22362.33 | 0 | Not started
C001 | Residential Building A | T375 | Roofing | Dave Brown | In Progress | Low | 2024-07-01 | 2024-07-27 |  | 93 | Roofing Sheets | Plot 21, Riverside | 18817.86 | 12246.72 | In progress
C003 | Office Tower C | T249 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-02-26 | 2023-03-22 |  | 0 | Cement | Downtown Avenue | 28288.36 | 0 | Not started
C003 | Office Tower C | T981 | Site Survey | Sarah Johnson | Not Started | Low | 2024-08-20 | 2024-09-11 |  | 0 | Roofing Sheets | Downtown Avenue | 47652.2 | 0 | Not started
C001 | Residential Building A | T162 | Electrical Wiring | John Miller | Blocked | High | 2023-10-26 | 2023-11-04 |  | 0 | Roofing Sheets | Plot 21, Riverside | 10467.85 | 10610.05 | Not started
C004 | Warehouse D | T828 | Foundation Excavation | Grace Allen | In Progress | High | 2024-07-12 | 2024-07-27 |  | 53 | PVC Pipes | Industrial Park | 45689.42 | 32438.29 | In progress
C001 | Residential Building A | T876 | Foundation Excavation | Sarah Johnson | Completed | High | 2023-07-28 | 2023-08-05 | 2023-08-05 | 100 | PVC Pipes | Plot 21, Riverside | 30270.69 | 27891.04 | No issues
C001 | Residential Building A | T946 | Roofing | John Miller | Blocked | Medium | 2024-04-01 | 2024-04-24 |  | 0 | PVC Pipes | Plot 21, Riverside | 45001.33 | 45616.95 | Not started
C004 | Warehouse D | T374 | Roofing | Carlos Rivera | Not Started | Medium | 2023-09-04 | 2023-09-19 |  | 0 | Copper Wires | Industrial Park | 30169.3 | 0 | Not started
C003 | Office Tower C | T682 | Interior Painting | Grace Allen | Not Started | Medium | 2024-07-10 | 2024-07-20 |  | 0 | Rebar | Downtown Avenue | 28184.43 | 0 | Not started
C001 | Residential Building A | T588 | Concrete Pouring | Mike Adams | Not Started | High | 2024-03-15 | 2024-03-25 |  | 0 | Cement | Plot 21, Riverside | 25148.37 | 0 | Not started
C004 | Warehouse D | T770 | Interior Painting | Grace Allen | Completed | High | 2023-06-07 | 2023-06-29 | 2023-06-29 | 100 | Rebar | Industrial Park | 38464.65 | 42931.76 | No issues
C002 | Shopping Complex B | T789 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2023-06-06 | 2023-06-24 | 2023-06-24 | 100 | Paint | Market Street | 38025.14 | 66062.68 | No issues
C004 | Warehouse D | T848 | Plumbing Installations | John Miller | Completed | Low | 2023-01-25 | 2023-02-07 | 2023-02-07 | 100 | PVC Pipes | Industrial Park | 38600.36 | 27929.13 | No issues
C004 | Warehouse D | T277 | Foundation Excavation | Dave Brown | Blocked | Low | 2023-10-27 | 2023-11-23 |  | 0 | Roofing Sheets | Industrial Park | 24166.31 | 24605.12 | Not started
C004 | Warehouse D | T158 | Roofing | Rachel Green | Completed | Medium | 2024-02-10 | 2024-02-29 | 2024-02-29 | 100 | Paint | Industrial Park | 35305.75 | 41985.96 | No issues
C002 | Shopping Complex B | T353 | Roofing | Sarah Johnson | Blocked | High | 2023-01-16 | 2023-02-02 |  | 0 | Cement | Market Street | 44855.44 | 54481.61 | Not started
C001 | Residential Building A | T324 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2023-11-05 | 2023-11-20 |  | 1 | Rebar | Plot 21, Riverside | 17295.52 | 13994.99 | In progress
C004 | Warehouse D | T634 | Steel Framework Setup | Rachel Green | Completed | Medium | 2024-06-11 | 2024-07-09 | 2024-07-09 | 100 | Paint | Industrial Park | 30592.19 | 19793.59 | No issues
C003 | Office Tower C | T753 | Concrete Pouring | John Miller | In Progress | Low | 2024-08-25 | 2024-09-16 |  | 10 | Rebar | Downtown Avenue | 9652.68 | 7409.63 | In progress
C002 | Shopping Complex B | T100 | Concrete Pouring | Mike Adams | Completed | Low | 2023-06-23 | 2023-07-18 | 2023-07-18 | 100 | Paint | Market Street | 16993.71 | 41581.59 | No issues
C004 | Warehouse D | T696 | Roofing | Carlos Rivera | In Progress | Medium | 2023-09-16 | 2023-10-12 |  | 21 | PVC Pipes | Industrial Park | 9976.29 | 8148.17 | In progress
C002 | Shopping Complex B | T241 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-08-05 | 2024-08-15 |  | 25 | PVC Pipes | Market Street | 10015.06 | 36167.6 | In progress
C001 | Residential Building A | T513 | Plumbing Installations | Sarah Johnson | Not Started | High | 2024-04-14 | 2024-05-01 |  | 0 | Paint | Plot 21, Riverside | 35584.99 | 0 | Not started
C002 | Shopping Complex B | T674 | Steel Framework Setup | Emma White | Completed | Medium | 2023-07-07 | 2023-07-30 | 2023-07-30 | 100 | Steel Beams | Market Street | 30383.69 | 47676.4 | No issues
C003 | Office Tower C | T652 | Site Survey | John Miller | Completed | Medium | 2023-10-23 | 2023-11-09 | 2023-11-09 | 100 | Steel Beams | Downtown Avenue | 10199.8 | 7977.18 | No issues
C003 | Office Tower C | T767 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-09-28 | 2023-10-09 | 2023-10-09 | 100 | Cement | Downtown Avenue | 15605.8 | 14191.05 | No issues
C003 | Office Tower C | T313 | Electrical Wiring | Carlos Rivera | Not Started | High | 2024-04-06 | 2024-04-24 |  | 0 | Copper Wires | Downtown Avenue | 15679.78 | 0 | Not started
C004 | Warehouse D | T638 | Interior Painting | Rachel Green | Not Started | High | 2023-02-03 | 2023-02-22 |  | 0 | Cement | Industrial Park | 30807.41 | 0 | Not started
C002 | Shopping Complex B | T665 | Plumbing Installations | John Miller | Not Started | Low | 2024-12-25 | 2025-01-02 |  | 0 | Copper Wires | Market Street | 35016.13 | 0 | Not started
C004 | Warehouse D | T155 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-02-17 | 2023-03-14 |  | 30 | Rebar | Industrial Park | 44331.87 | 40852.68 | In progress
C004 | Warehouse D | T679 | Site Survey | Carlos Rivera | Completed | High | 2023-04-24 | 2023-05-03 | 2023-05-03 | 100 | Rebar | Industrial Park | 17091.3 | 12799.33 | No issues
C004 | Warehouse D | T396 | Site Survey | Emma White | In Progress | Medium | 2024-05-04 | 2024-05-25 |  | 19 | Roofing Sheets | Industrial Park | 17294.91 | 15626.53 | In progress
C003 | Office Tower C | T797 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2024-09-09 | 2024-09-24 |  | 0 | Concrete | Downtown Avenue | 27059.09 | 0 | Not started
C001 | Residential Building A | T705 | Electrical Wiring | Sarah Johnson | Not Started | High | 2023-06-26 | 2023-07-04 |  | 0 | Concrete | Plot 21, Riverside | 40498.17 | 0 | Not started
C002 | Shopping Complex B | T457 | Plumbing Installations | Mike Adams | Not Started | High | 2024-09-21 | 2024-10-18 |  | 0 | Steel Beams | Market Street | 32726.84 | 0 | Not started
C004 | Warehouse D | T609 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2023-10-16 | 2023-10-25 |  | 0 | Concrete | Industrial Park | 41402.96 | 27173.09 | Not started
C004 | Warehouse D | T291 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2024-04-08 | 2024-04-23 |  | 0 | Steel Beams | Industrial Park | 5148 | 5625.78 | Not started
C001 | Residential Building A | T637 | Roofing | Mike Adams | Completed | Medium | 2024-06-11 | 2024-07-08 | 2024-07-08 | 100 | Copper Wires | Plot 21, Riverside | 30676.27 | 26369.32 | No issues
C001 | Residential Building A | T728 | Roofing | Dave Brown | Blocked | High | 2023-11-16 | 2023-12-13 |  | 0 | Paint | Plot 21, Riverside | 19035.44 | 14277.71 | Not started
C004 | Warehouse D | T248 | Roofing | Rachel Green | Completed | Medium | 2023-07-24 | 2023-08-11 | 2023-08-11 | 100 | Roofing Sheets | Industrial Park | 37334.87 | 29675.09 | No issues
C003 | Office Tower C | T342 | Plumbing Installations | Mike Adams | Not Started | Low | 2024-06-23 | 2024-07-10 |  | 0 | Concrete | Downtown Avenue | 40816.85 | 0 | Not started
C003 | Office Tower C | T628 | Plumbing Installations | Grace Allen | In Progress | Low | 2023-07-01 | 2023-07-21 |  | 74 | Steel Beams | Downtown Avenue | 44733.2 | 46177.1 | In progress
C002 | Shopping Complex B | T265 | Plumbing Installations | Sarah Johnson | Blocked | Low | 2023-03-14 | 2023-04-10 |  | 0 | PVC Pipes | Market Street | 14153.22 | 34437.79 | Not started
C002 | Shopping Complex B | T557 | Site Survey | Carlos Rivera | Not Started | Medium | 2023-08-10 | 2023-08-17 |  | 0 | PVC Pipes | Market Street | 31488.13 | 0 | Not started
C003 | Office Tower C | T390 | Interior Painting | Mike Adams | Completed | Medium | 2024-06-22 | 2024-07-08 | 2024-07-08 | 100 | Roofing Sheets | Downtown Avenue | 29885.76 | 27027.06 | No issues
C004 | Warehouse D | T337 | Steel Framework Setup | John Miller | Completed | Low | 2024-09-09 | 2024-10-01 | 2024-10-01 | 100 | Roofing Sheets | Industrial Park | 35668.43 | 34817.64 | No issues
C001 | Residential Building A | T623 | Interior Painting | Mike Adams | Blocked | Low | 2024-09-14 | 2024-10-01 |  | 0 | Copper Wires | Plot 21, Riverside | 13859.18 | 9215.3 | Not started
C004 | Warehouse D | T987 | Electrical Wiring | John Miller | In Progress | Medium | 2024-03-18 | 2024-04-09 |  | 12 | Steel Beams | Industrial Park | 36788.93 | 22356.56 | In progress
C001 | Residential Building A | T776 | Concrete Pouring | Sarah Johnson | Blocked | High | 2024-08-06 | 2024-08-23 |  | 0 | Copper Wires | Plot 21, Riverside | 13359.47 | 14810.65 | Not started
C004 | Warehouse D | T895 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-03-09 | 2024-03-26 |  | 63 | PVC Pipes | Industrial Park | 45972.66 | 36335.98 | In progress
C001 | Residential Building A | T607 | Plumbing Installations | Mike Adams | Not Started | Medium | 2023-10-26 | 2023-11-17 |  | 0 | Copper Wires | Plot 21, Riverside | 18913.64 | 0 | Not started
C004 | Warehouse D | T219 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-11-09 | 2024-11-21 |  | 3 | Steel Beams | Industrial Park | 26371.87 | 29854.88 | In progress
C004 | Warehouse D | T400 | Site Survey | Emma White | In Progress | Low | 2023-09-17 | 2023-10-12 |  | 16 | PVC Pipes | Industrial Park | 28698.76 | 33442.04 | In progress
C003 | Office Tower C | T422 | Electrical Wiring | John Miller | Not Started | Medium | 2023-03-22 | 2023-04-21 |  | 0 | Roofing Sheets | Downtown Avenue | 26444.4 | 0 | Not started
C001 | Residential Building A | T360 | Roofing | Dave Brown | Not Started | Low | 2023-02-03 | 2023-02-11 |  | 0 | Copper Wires | Plot 21, Riverside | 14801.49 | 0 | Not started
C001 | Residential Building A | T732 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-11-07 | 2024-12-06 |  | 10 | Steel Beams | Plot 21, Riverside | 29623.47 | 27505.74 | In progress
C004 | Warehouse D | T808 | Site Survey | John Miller | Completed | Medium | 2023-07-06 | 2023-07-19 | 2023-07-19 | 100 | PVC Pipes | Industrial Park | 24962.86 | 29337.61 | No issues
C002 | Shopping Complex B | T643 | Interior Painting | Rachel Green | Not Started | Low | 2024-12-28 | 2025-01-09 |  | 0 | Copper Wires | Market Street | 26492.97 | 0 | Not started
C003 | Office Tower C | T540 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-04-22 | 2024-05-10 |  | 0 | Roofing Sheets | Downtown Avenue | 45508.99 | 38715.85 | Not started
C003 | Office Tower C | T313 | Roofing | Dave Brown | Blocked | Medium | 2023-10-04 | 2023-10-23 |  | 0 | Steel Beams | Downtown Avenue | 24462.12 | 27861.56 | Not started
C003 | Office Tower C | T712 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2024-03-03 | 2024-03-31 |  | 94 | Paint | Downtown Avenue | 31847.05 | 26232.13 | In progress
C002 | Shopping Complex B | T450 | Concrete Pouring | Emma White | Completed | Medium | 2024-03-06 | 2024-03-16 | 2024-03-16 | 100 | PVC Pipes | Market Street | 25091.62 | 49670.37 | No issues
C001 | Residential Building A | T824 | Steel Framework Setup | Carlos Rivera | In Progress | High | 2023-03-21 | 2023-04-01 |  | 47 | Copper Wires | Plot 21, Riverside | 28395 | 26855.46 | In progress
C002 | Shopping Complex B | T897 | Site Survey | Mike Adams | Completed | High | 2024-09-10 | 2024-09-18 | 2024-09-18 | 100 | Copper Wires | Market Street | 25536.73 | 48314.69 | No issues
C003 | Office Tower C | T972 | Electrical Wiring | Dave Brown | Completed | Low | 2024-02-02 | 2024-02-15 | 2024-02-15 | 100 | Paint | Downtown Avenue | 17245.54 | 15004.48 | No issues
C004 | Warehouse D | T294 | Roofing | Carlos Rivera | In Progress | Medium | 2024-05-22 | 2024-06-08 |  | 79 | Roofing Sheets | Industrial Park | 21107.67 | 24519.88 | In progress
C001 | Residential Building A | T486 | Roofing | Grace Allen | Not Started | Low | 2023-11-19 | 2023-12-04 |  | 0 | Concrete | Plot 21, Riverside | 5933.01 | 0 | Not started
C003 | Office Tower C | T644 | Roofing | Emma White | Blocked | Low | 2023-10-11 | 2023-10-22 |  | 0 | Steel Beams | Downtown Avenue | 45453.65 | 40745.64 | Not started
C004 | Warehouse D | T916 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-03-18 | 2024-04-02 |  | 0 | Steel Beams | Industrial Park | 27218.45 | 25953.92 | Not started
C002 | Shopping Complex B | T297 | Interior Painting | Carlos Rivera | In Progress | Low | 2023-05-24 | 2023-06-01 |  | 56 | Roofing Sheets | Market Street | 40712.44 | 62968.49 | In progress
C001 | Residential Building A | T344 | Concrete Pouring | John Miller | Blocked | Medium | 2023-03-28 | 2023-04-27 |  | 0 | Concrete | Plot 21, Riverside | 31835.49 | 37694.59 | Not started
C004 | Warehouse D | T992 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-01-01 | 2023-01-24 |  | 0 | Roofing Sheets | Industrial Park | 27833.66 | 31588.27 | Not started
C002 | Shopping Complex B | T472 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-04-09 | 2023-05-06 |  | 0 | PVC Pipes | Market Street | 39165.48 | 56128.95 | Not started
C003 | Office Tower C | T788 | Foundation Excavation | Mike Adams | Blocked | High | 2023-09-25 | 2023-10-09 |  | 0 | Steel Beams | Downtown Avenue | 13931.19 | 9936.42 | Not started
C004 | Warehouse D | T525 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-06-25 | 2024-07-25 |  | 0 | Paint | Industrial Park | 11792.59 | 0 | Not started
C003 | Office Tower C | T522 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-11-14 | 2024-12-01 | 2024-12-01 | 100 | Rebar | Downtown Avenue | 23953.16 | 21421.24 | No issues
C003 | Office Tower C | T746 | Electrical Wiring | Rachel Green | Not Started | High | 2024-05-01 | 2024-05-29 |  | 0 | Copper Wires | Downtown Avenue | 22247.26 | 0 | Not started
C003 | Office Tower C | T229 | Roofing | John Miller | Blocked | Medium | 2024-07-05 | 2024-07-29 |  | 0 | Copper Wires | Downtown Avenue | 16194.06 | 19413.1 | Not started
C001 | Residential Building A | T341 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2023-03-23 | 2023-04-22 |  | 0 | PVC Pipes | Plot 21, Riverside | 18626.03 | 16076.81 | Not started
C004 | Warehouse D | T837 | Interior Painting | Carlos Rivera | Blocked | Low | 2024-10-10 | 2024-11-08 |  | 0 | Roofing Sheets | Industrial Park | 31965.41 | 20737.35 | Not started
C001 | Residential Building A | T732 | Site Survey | Carlos Rivera | Completed | High | 2024-04-20 | 2024-05-17 | 2024-05-17 | 100 | Cement | Plot 21, Riverside | 8250.74 | 9622.34 | No issues
C004 | Warehouse D | T598 | Foundation Excavation | Emma White | Not Started | Medium | 2023-09-19 | 2023-10-05 |  | 0 | Concrete | Industrial Park | 32183.24 | 0 | Not started
C003 | Office Tower C | T964 | Foundation Excavation | Grace Allen | In Progress | Low | 2024-03-02 | 2024-03-29 |  | 72 | Cement | Downtown Avenue | 40794.92 | 26739.55 | In progress
C004 | Warehouse D | T810 | Roofing | Rachel Green | In Progress | Low | 2023-06-12 | 2023-07-03 |  | 14 | Concrete | Industrial Park | 7388.94 | 8617.11 | In progress
C001 | Residential Building A | T488 | Site Survey | John Miller | Blocked | High | 2024-10-10 | 2024-10-24 |  | 0 | PVC Pipes | Plot 21, Riverside | 49082.85 | 38651.96 | Not started
C003 | Office Tower C | T426 | Site Survey | Rachel Green | Completed | Medium | 2023-01-22 | 2023-02-20 | 2023-02-20 | 100 | PVC Pipes | Downtown Avenue | 23635.89 | 17458.51 | No issues
C004 | Warehouse D | T558 | Steel Framework Setup | John Miller | Not Started | High | 2023-01-24 | 2023-02-12 |  | 0 | Rebar | Industrial Park | 13765.2 | 0 | Not started
C003 | Office Tower C | T680 | Concrete Pouring | John Miller | Blocked | Medium | 2023-07-17 | 2023-08-04 |  | 0 | Copper Wires | Downtown Avenue | 9918.14 | 7214.41 | Not started
C001 | Residential Building A | T530 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-09-02 | 2024-09-29 |  | 0 | Copper Wires | Plot 21, Riverside | 29672.72 | 31135.39 | Not started
C004 | Warehouse D | T772 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2024-07-22 | 2024-08-15 |  | 0 | Roofing Sheets | Industrial Park | 25695.59 | 0 | Not started
C002 | Shopping Complex B | T552 | Steel Framework Setup | John Miller | Blocked | High | 2023-06-10 | 2023-06-18 |  | 0 | Roofing Sheets | Market Street | 19547.53 | 45337.36 | Not started
C002 | Shopping Complex B | T483 | Foundation Excavation | Dave Brown | Not Started | Low | 2024-01-10 | 2024-01-25 |  | 0 | Rebar | Market Street | 22718.28 | 0 | Not started
C002 | Shopping Complex B | T165 | Foundation Excavation | Sarah Johnson | Blocked | High | 2024-01-02 | 2024-01-22 |  | 0 | Roofing Sheets | Market Street | 27418.87 | 48155.94 | Not started
C003 | Office Tower C | T791 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-05-26 | 2024-06-13 |  | 0 | PVC Pipes | Downtown Avenue | 44306 | 0 | Not started
C004 | Warehouse D | T372 | Interior Painting | Mike Adams | Not Started | Low | 2024-12-27 | 2025-01-23 |  | 0 | Rebar | Industrial Park | 12768.21 | 0 | Not started
C003 | Office Tower C | T910 | Site Survey | Sarah Johnson | In Progress | Low | 2024-02-08 | 2024-02-26 |  | 64 | PVC Pipes | Downtown Avenue | 24749.56 | 16793.3 | In progress
C001 | Residential Building A | T615 | Steel Framework Setup | Mike Adams | In Progress | High | 2024-12-12 | 2024-12-24 |  | 50 | Concrete | Plot 21, Riverside | 32566.55 | 31239.1 | In progress
C004 | Warehouse D | T608 | Roofing | Emma White | Blocked | Low | 2023-09-04 | 2023-09-14 |  | 0 | Steel Beams | Industrial Park | 42652.24 | 35328.64 | Not started
C001 | Residential Building A | T199 | Site Survey | Sarah Johnson | Not Started | Medium | 2024-02-13 | 2024-03-10 |  | 0 | Paint | Plot 21, Riverside | 21770.45 | 0 | Not started
C004 | Warehouse D | T769 | Electrical Wiring | John Miller | Blocked | High | 2024-10-28 | 2024-11-17 |  | 0 | Concrete | Industrial Park | 9999.45 | 11022.54 | Not started
C001 | Residential Building A | T843 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2024-11-28 | 2024-12-11 |  | 42 | Steel Beams | Plot 21, Riverside | 48317.6 | 42854.12 | In progress
C004 | Warehouse D | T178 | Concrete Pouring | Mike Adams | Completed | Low | 2024-04-20 | 2024-05-10 | 2024-05-10 | 100 | Roofing Sheets | Industrial Park | 27867.94 | 17766.48 | No issues
C003 | Office Tower C | T710 | Foundation Excavation | Dave Brown | In Progress | Medium | 2023-01-24 | 2023-02-01 |  | 85 | Rebar | Downtown Avenue | 22647.51 | 16836.34 | In progress
C004 | Warehouse D | T796 | Site Survey | Grace Allen | Blocked | Medium | 2024-09-08 | 2024-09-23 |  | 0 | Copper Wires | Industrial Park | 9027.15 | 6203.73 | Not started
C004 | Warehouse D | T868 | Foundation Excavation | Carlos Rivera | Completed | Low | 2023-06-10 | 2023-06-27 | 2023-06-27 | 100 | Cement | Industrial Park | 9505.08 | 6865.05 | No issues
C002 | Shopping Complex B | T482 | Interior Painting | Grace Allen | Not Started | Low | 2024-03-16 | 2024-04-13 |  | 0 | Cement | Market Street | 46783.56 | 0 | Not started
C003 | Office Tower C | T122 | Site Survey | Rachel Green | Completed | High | 2024-06-10 | 2024-06-25 | 2024-06-25 | 100 | Steel Beams | Downtown Avenue | 6832.34 | 5605.31 | No issues
C004 | Warehouse D | T574 | Roofing | Carlos Rivera | Not Started | High | 2023-03-08 | 2023-04-04 |  | 0 | Rebar | Industrial Park | 39091.56 | 0 | Not started
C003 | Office Tower C | T738 | Plumbing Installations | Emma White | Blocked | Medium | 2023-04-22 | 2023-05-16 |  | 0 | Steel Beams | Downtown Avenue | 30850.45 | 36085.89 | Not started
C002 | Shopping Complex B | T792 | Interior Painting | Mike Adams | Completed | Low | 2023-03-17 | 2023-03-27 | 2023-03-27 | 100 | Copper Wires | Market Street | 23352.58 | 44947.02 | No issues
C002 | Shopping Complex B | T570 | Plumbing Installations | Sarah Johnson | Not Started | High | 2023-12-04 | 2023-12-12 |  | 0 | Paint | Market Street | 40812.11 | 0 | Not started
C003 | Office Tower C | T933 | Roofing | Mike Adams | Not Started | High | 2024-04-03 | 2024-04-22 |  | 0 | PVC Pipes | Downtown Avenue | 36229.65 | 0 | Not started
C004 | Warehouse D | T483 | Electrical Wiring | John Miller | Completed | Low | 2023-04-19 | 2023-05-07 | 2023-05-07 | 100 | Concrete | Industrial Park | 15226.62 | 15988.29 | No issues
C001 | Residential Building A | T647 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2023-04-25 | 2023-05-12 |  | 0 | PVC Pipes | Plot 21, Riverside | 15026.69 | 17405.31 | Not started
C002 | Shopping Complex B | T268 | Roofing | Grace Allen | In Progress | High | 2024-07-02 | 2024-07-15 |  | 37 | Cement | Market Street | 39533.04 | 61760.6 | In progress
C004 | Warehouse D | T229 | Site Survey | Carlos Rivera | Blocked | Medium | 2023-10-01 | 2023-10-24 |  | 0 | Paint | Industrial Park | 24223.3 | 14637.53 | Not started
C002 | Shopping Complex B | T885 | Concrete Pouring | Mike Adams | Not Started | Medium | 2023-08-17 | 2023-09-02 |  | 0 | Copper Wires | Market Street | 35595.59 | 0 | Not started
C003 | Office Tower C | T198 | Interior Painting | Carlos Rivera | Not Started | Medium | 2023-02-10 | 2023-02-24 |  | 0 | PVC Pipes | Downtown Avenue | 14079.11 | 0 | Not started
C002 | Shopping Complex B | T978 | Concrete Pouring | John Miller | Completed | Medium | 2023-02-20 | 2023-03-11 | 2023-03-11 | 100 | Steel Beams | Market Street | 38261.77 | 52138.27 | No issues
C003 | Office Tower C | T555 | Interior Painting | John Miller | Blocked | High | 2024-06-18 | 2024-07-05 |  | 0 | PVC Pipes | Downtown Avenue | 41578.78 | 43386.55 | Not started
C001 | Residential Building A | T503 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2023-12-06 | 2023-12-15 |  | 0 | Concrete | Plot 21, Riverside | 41217.1 | 39935.63 | Not started
C004 | Warehouse D | T841 | Foundation Excavation | Dave Brown | In Progress | High | 2023-02-12 | 2023-02-23 |  | 44 | Steel Beams | Industrial Park | 31299.48 | 20596.87 | In progress
C001 | Residential Building A | T161 | Electrical Wiring | Rachel Green | Completed | Medium | 2024-05-25 | 2024-06-10 | 2024-06-10 | 100 | Cement | Plot 21, Riverside | 20822.97 | 15623.46 | No issues
C002 | Shopping Complex B | T180 | Electrical Wiring | Emma White | Not Started | Low | 2024-09-28 | 2024-10-15 |  | 0 | Copper Wires | Market Street | 48443.52 | 0 | Not started
C002 | Shopping Complex B | T859 | Electrical Wiring | Emma White | Completed | Low | 2023-12-19 | 2024-01-03 | 2024-01-03 | 100 | Steel Beams | Market Street | 49826.7 | 82749.37 | No issues
C001 | Residential Building A | T577 | Roofing | Emma White | In Progress | High | 2023-09-27 | 2023-10-05 |  | 42 | Copper Wires | Plot 21, Riverside | 10226.57 | 6995.25 | In progress
C004 | Warehouse D | T462 | Concrete Pouring | Dave Brown | Completed | High | 2023-12-27 | 2024-01-03 | 2024-01-03 | 100 | Cement | Industrial Park | 17954.53 | 11946.35 | No issues
C004 | Warehouse D | T142 | Concrete Pouring | John Miller | Blocked | Medium | 2024-05-24 | 2024-06-22 |  | 0 | Cement | Industrial Park | 37669.49 | 33569.03 | Not started
C001 | Residential Building A | T619 | Plumbing Installations | Sarah Johnson | Completed | High | 2024-01-15 | 2024-01-26 | 2024-01-26 | 100 | Paint | Plot 21, Riverside | 33048.13 | 35593.11 | No issues
C003 | Office Tower C | T192 | Plumbing Installations | Dave Brown | Not Started | Low | 2024-10-24 | 2024-11-17 |  | 0 | Roofing Sheets | Downtown Avenue | 10164.55 | 0 | Not started
C003 | Office Tower C | T904 | Interior Painting | Emma White | Blocked | High | 2024-07-05 | 2024-08-01 |  | 0 | Concrete | Downtown Avenue | 42346.05 | 32026.56 | Not started
C004 | Warehouse D | T952 | Steel Framework Setup | Emma White | In Progress | Medium | 2023-02-25 | 2023-03-23 |  | 68 | Steel Beams | Industrial Park | 40441.2 | 30489.65 | In progress
C002 | Shopping Complex B | T232 | Concrete Pouring | Carlos Rivera | Not Started | High | 2024-04-14 | 2024-04-29 |  | 0 | Paint | Market Street | 10128.05 | 0 | Not started
C003 | Office Tower C | T186 | Plumbing Installations | John Miller | In Progress | Medium | 2023-03-20 | 2023-03-27 |  | 90 | Rebar | Downtown Avenue | 16801.23 | 14444.73 | In progress
C004 | Warehouse D | T421 | Concrete Pouring | Emma White | Completed | Medium | 2023-05-12 | 2023-06-07 | 2023-06-07 | 100 | Copper Wires | Industrial Park | 32923.05 | 38247.31 | No issues
C002 | Shopping Complex B | T312 | Plumbing Installations | Rachel Green | Blocked | Medium | 2024-12-08 | 2024-12-23 |  | 0 | Rebar | Market Street | 5611.55 | 31281.3 | Not started
C002 | Shopping Complex B | T400 | Electrical Wiring | Dave Brown | Completed | High | 2023-02-23 | 2023-03-05 | 2023-03-05 | 100 | Copper Wires | Market Street | 29142.91 | 53195.17 | No issues
C003 | Office Tower C | T394 | Roofing | John Miller | Completed | Medium | 2023-08-01 | 2023-08-10 | 2023-08-10 | 100 | Paint | Downtown Avenue | 18327.39 | 20036.48 | No issues
C003 | Office Tower C | T305 | Foundation Excavation | Dave Brown | Blocked | Medium | 2023-02-20 | 2023-03-04 |  | 0 | Concrete | Downtown Avenue | 34572.86 | 27878.56 | Not started
C001 | Residential Building A | T927 | Plumbing Installations | John Miller | In Progress | Low | 2024-03-18 | 2024-04-07 |  | 93 | PVC Pipes | Plot 21, Riverside | 19227.8 | 16201.36 | In progress
C001 | Residential Building A | T347 | Site Survey | Sarah Johnson | In Progress | High | 2024-02-05 | 2024-03-01 |  | 20 | Steel Beams | Plot 21, Riverside | 43903.74 | 48992.53 | In progress
C003 | Office Tower C | T813 | Site Survey | Carlos Rivera | Completed | Low | 2023-09-15 | 2023-09-29 | 2023-09-29 | 100 | Steel Beams | Downtown Avenue | 47745.39 | 33919.98 | No issues
C003 | Office Tower C | T351 | Foundation Excavation | Emma White | In Progress | High | 2023-07-04 | 2023-07-12 |  | 26 | Cement | Downtown Avenue | 39275.74 | 27612.19 | In progress
C003 | Office Tower C | T449 | Steel Framework Setup | Grace Allen | In Progress | Low | 2024-04-06 | 2024-04-18 |  | 80 | Roofing Sheets | Downtown Avenue | 11208.9 | 7351.64 | In progress
C004 | Warehouse D | T469 | Steel Framework Setup | Emma White | Blocked | High | 2023-04-28 | 2023-05-17 |  | 0 | Roofing Sheets | Industrial Park | 22956.74 | 15060.32 | Not started
C001 | Residential Building A | T700 | Electrical Wiring | Mike Adams | Not Started | High | 2023-01-25 | 2023-02-03 |  | 0 | Concrete | Plot 21, Riverside | 6756.67 | 0 | Not started
C002 | Shopping Complex B | T262 | Roofing | Grace Allen | Blocked | Low | 2023-03-22 | 2023-04-20 |  | 0 | Cement | Market Street | 43644.87 | 57402.09 | Not started
C003 | Office Tower C | T507 | Steel Framework Setup | Emma White | Completed | Low | 2023-07-28 | 2023-08-04 | 2023-08-04 | 100 | Roofing Sheets | Downtown Avenue | 48008.37 | 52807.11 | No issues
C004 | Warehouse D | T927 | Interior Painting | Dave Brown | Completed | Medium | 2023-10-08 | 2023-10-24 | 2023-10-24 | 100 | Steel Beams | Industrial Park | 42355.02 | 47816.52 | No issues
C001 | Residential Building A | T133 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2023-07-11 | 2023-07-24 | 2023-07-24 | 100 | Steel Beams | Plot 21, Riverside | 42223.66 | 31227.77 | No issues
C002 | Shopping Complex B | T100 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-12-12 | 2024-01-02 |  | 0 | Steel Beams | Market Street | 47361.44 | 61295.44 | Not started
C002 | Shopping Complex B | T105 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-03-13 | 2023-03-25 |  | 20 | Copper Wires | Market Street | 9458.21 | 34455.87 | In progress
C001 | Residential Building A | T667 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2024-11-27 | 2024-12-14 | 2024-12-14 | 100 | Steel Beams | Plot 21, Riverside | 23842.89 | 19190.57 | No issues
C001 | Residential Building A | T377 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2024-10-24 | 2024-11-19 | 2024-11-19 | 100 | Paint | Plot 21, Riverside | 13910.25 | 15831.22 | No issues
C003 | Office Tower C | T564 | Foundation Excavation | Carlos Rivera | Completed | Low | 2023-11-11 | 2023-12-05 | 2023-12-05 | 100 | Paint | Downtown Avenue | 7205.79 | 7768.86 | No issues
C004 | Warehouse D | T844 | Electrical Wiring | Mike Adams | Completed | Medium | 2024-03-27 | 2024-04-25 | 2024-04-25 | 100 | Roofing Sheets | Industrial Park | 45980.7 | 49542.41 | No issues
C004 | Warehouse D | T424 | Foundation Excavation | Grace Allen | Not Started | Low | 2023-05-09 | 2023-05-21 |  | 0 | Copper Wires | Industrial Park | 28981.1 | 0 | Not started
C003 | Office Tower C | T111 | Concrete Pouring | Dave Brown | In Progress | Medium | 2023-12-19 | 2024-01-17 |  | 28 | Steel Beams | Downtown Avenue | 16264.27 | 10554.31 | In progress
C001 | Residential Building A | T676 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2023-06-24 | 2023-07-06 | 2023-07-06 | 100 | Paint | Plot 21, Riverside | 35511.79 | 32055.43 | No issues
C001 | Residential Building A | T218 | Electrical Wiring | Grace Allen | Completed | High | 2024-02-01 | 2024-02-24 | 2024-02-24 | 100 | Roofing Sheets | Plot 21, Riverside | 29323.06 | 21560.71 | No issues
C001 | Residential Building A | T610 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-11-20 | 2024-11-30 |  | 0 | Concrete | Plot 21, Riverside | 8970.99 | 0 | Not started
C001 | Residential Building A | T352 | Plumbing Installations | Sarah Johnson | In Progress | Medium | 2024-08-26 | 2024-09-06 |  | 42 | PVC Pipes | Plot 21, Riverside | 33411.31 | 26301.78 | In progress
C002 | Shopping Complex B | T850 | Steel Framework Setup | Mike Adams | Not Started | Low | 2024-09-23 | 2024-10-09 |  | 0 | Concrete | Market Street | 6348.61 | 0 | Not started
C002 | Shopping Complex B | T874 | Site Survey | Mike Adams | Not Started | Low | 2023-07-28 | 2023-08-08 |  | 0 | Rebar | Market Street | 24870.82 | 0 | Not started
C004 | Warehouse D | T410 | Plumbing Installations | Carlos Rivera | Not Started | Medium | 2023-12-26 | 2024-01-16 |  | 0 | Steel Beams | Industrial Park | 25530.26 | 0 | Not started
C001 | Residential Building A | T510 | Concrete Pouring | Dave Brown | In Progress | Medium | 2024-09-28 | 2024-10-24 |  | 80 | Copper Wires | Plot 21, Riverside | 37704.55 | 31043.48 | In progress
C001 | Residential Building A | T179 | Foundation Excavation | Emma White | In Progress | Medium | 2023-04-09 | 2023-04-27 |  | 32 | Rebar | Plot 21, Riverside | 16844.72 | 18328.9 | In progress
C001 | Residential Building A | T559 | Interior Painting | Emma White | Blocked | Low | 2023-11-11 | 2023-12-05 |  | 0 | Cement | Plot 21, Riverside | 38383.4 | 42798.59 | Not started
C001 | Residential Building A | T335 | Concrete Pouring | Grace Allen | Blocked | Medium | 2024-10-23 | 2024-11-10 |  | 0 | Copper Wires | Plot 21, Riverside | 19427.74 | 13727.83 | Not started
C003 | Office Tower C | T797 | Foundation Excavation | Emma White | Not Started | High | 2023-08-15 | 2023-08-24 |  | 0 | Copper Wires | Downtown Avenue | 18202.64 | 0 | Not started
C001 | Residential Building A | T960 | Foundation Excavation | Grace Allen | Blocked | Medium | 2024-03-26 | 2024-04-08 |  | 0 | Cement | Plot 21, Riverside | 13468.69 | 13969.54 | Not started
C002 | Shopping Complex B | T714 | Interior Painting | John Miller | Blocked | High | 2023-12-21 | 2024-01-04 |  | 0 | PVC Pipes | Market Street | 15721.25 | 35741.85 | Not started
C001 | Residential Building A | T783 | Site Survey | Dave Brown | In Progress | Low | 2023-03-26 | 2023-04-24 |  | 49 | Roofing Sheets | Plot 21, Riverside | 28054.71 | 21622 | In progress
C001 | Residential Building A | T226 | Plumbing Installations | John Miller | Blocked | High | 2024-09-27 | 2024-10-08 |  | 0 | Copper Wires | Plot 21, Riverside | 17503.51 | 20031.96 | Not started
C004 | Warehouse D | T791 | Roofing | Sarah Johnson | In Progress | Low | 2023-07-03 | 2023-08-01 |  | 99 | Rebar | Industrial Park | 23289.08 | 22516.65 | In progress
C003 | Office Tower C | T155 | Site Survey | Carlos Rivera | Not Started | Low | 2024-03-10 | 2024-03-18 |  | 0 | Copper Wires | Downtown Avenue | 41904.69 | 0 | Not started
C002 | Shopping Complex B | T688 | Interior Painting | Sarah Johnson | Blocked | Medium | 2024-06-12 | 2024-07-03 |  | 0 | Steel Beams | Market Street | 48218.16 | 82744.96 | Not started
C001 | Residential Building A | T777 | Plumbing Installations | Dave Brown | In Progress | High | 2023-11-05 | 2023-11-22 |  | 51 | PVC Pipes | Plot 21, Riverside | 48513.75 | 49182.02 | In progress
C004 | Warehouse D | T659 | Interior Painting | Grace Allen | Completed | Medium | 2024-02-04 | 2024-02-21 | 2024-02-21 | 100 | Paint | Industrial Park | 49394.9 | 48671.63 | No issues
C001 | Residential Building A | T661 | Steel Framework Setup | Rachel Green | In Progress | Low | 2023-08-11 | 2023-09-05 |  | 62 | Concrete | Plot 21, Riverside | 30302.06 | 32708.31 | In progress
C001 | Residential Building A | T741 | Concrete Pouring | Carlos Rivera | Completed | Low | 2024-12-26 | 2025-01-10 | 2025-01-10 | 100 | PVC Pipes | Plot 21, Riverside | 20968.2 | 20161.09 | No issues
C001 | Residential Building A | T220 | Electrical Wiring | Mike Adams | Completed | Medium | 2023-01-03 | 2023-02-01 | 2023-02-01 | 100 | Paint | Plot 21, Riverside | 11708.71 | 8605.98 | No issues
C004 | Warehouse D | T590 | Interior Painting | Grace Allen | In Progress | High | 2024-07-05 | 2024-07-12 |  | 80 | Cement | Industrial Park | 37471.75 | 31289.09 | In progress
C003 | Office Tower C | T301 | Concrete Pouring | Grace Allen | Not Started | High | 2023-10-15 | 2023-11-05 |  | 0 | Rebar | Downtown Avenue | 23630.5 | 0 | Not started
C001 | Residential Building A | T657 | Steel Framework Setup | Emma White | Blocked | Low | 2024-04-24 | 2024-05-18 |  | 0 | Steel Beams | Plot 21, Riverside | 24088.21 | 18432.23 | Not started
C004 | Warehouse D | T777 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-07-19 | 2023-08-16 |  | 0 | Steel Beams | Industrial Park | 41101.22 | 28316.32 | Not started
C001 | Residential Building A | T625 | Foundation Excavation | Rachel Green | Blocked | Medium | 2024-04-22 | 2024-05-09 |  | 0 | Cement | Plot 21, Riverside | 11058.13 | 11431.94 | Not started
C002 | Shopping Complex B | T355 | Plumbing Installations | Rachel Green | In Progress | Medium | 2023-01-15 | 2023-01-27 |  | 29 | Cement | Market Street | 46231.87 | 68522.72 | In progress
C001 | Residential Building A | T839 | Concrete Pouring | Mike Adams | Blocked | Low | 2023-05-22 | 2023-05-31 |  | 0 | Paint | Plot 21, Riverside | 18352.16 | 20744.18 | Not started
C002 | Shopping Complex B | T730 | Electrical Wiring | Emma White | Blocked | Low | 2024-04-23 | 2024-05-01 |  | 0 | Copper Wires | Market Street | 11396.08 | 34795.52 | Not started
C002 | Shopping Complex B | T577 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-04-10 | 2023-04-28 |  | 0 | Rebar | Market Street | 14209.02 | 39498.44 | Not started
C002 | Shopping Complex B | T737 | Roofing | Mike Adams | Not Started | Medium | 2024-01-23 | 2024-02-10 |  | 0 | Copper Wires | Market Street | 12392.9 | 0 | Not started
C002 | Shopping Complex B | T708 | Site Survey | Rachel Green | In Progress | High | 2023-10-21 | 2023-11-10 |  | 73 | Roofing Sheets | Market Street | 22942.25 | 46577.31 | In progress
C002 | Shopping Complex B | T647 | Foundation Excavation | Emma White | Blocked | High | 2023-06-02 | 2023-06-25 |  | 0 | Paint | Market Street | 29137.1 | 52026.65 | Not started
C003 | Office Tower C | T765 | Foundation Excavation | Rachel Green | Completed | Medium | 2023-12-13 | 2023-12-20 | 2023-12-20 | 100 | Roofing Sheets | Downtown Avenue | 27957.63 | 30558.41 | No issues
C001 | Residential Building A | T243 | Electrical Wiring | John Miller | In Progress | High | 2023-07-28 | 2023-08-06 |  | 54 | Roofing Sheets | Plot 21, Riverside | 40564.87 | 28970.1 | In progress
C001 | Residential Building A | T411 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2023-06-15 | 2023-06-25 |  | 34 | PVC Pipes | Plot 21, Riverside | 13184.67 | 11797.6 | In progress
C004 | Warehouse D | T413 | Steel Framework Setup | Grace Allen | Blocked | Low | 2023-12-28 | 2024-01-07 |  | 0 | Roofing Sheets | Industrial Park | 40720.18 | 46157.09 | Not started
C004 | Warehouse D | T925 | Interior Painting | John Miller | Not Started | Medium | 2024-05-09 | 2024-05-20 |  | 0 | Rebar | Industrial Park | 15592.34 | 0 | Not started
C004 | Warehouse D | T579 | Interior Painting | Mike Adams | Blocked | High | 2024-04-14 | 2024-04-30 |  | 0 | Copper Wires | Industrial Park | 11551.29 | 10749.42 | Not started
C001 | Residential Building A | T322 | Roofing | Dave Brown | Not Started | Low | 2024-03-09 | 2024-03-30 |  | 0 | Rebar | Plot 21, Riverside | 45455.25 | 0 | Not started
C002 | Shopping Complex B | T450 | Electrical Wiring | John Miller | Not Started | Medium | 2024-09-08 | 2024-09-25 |  | 0 | Copper Wires | Market Street | 16293.78 | 0 | Not started
C004 | Warehouse D | T864 | Concrete Pouring | Grace Allen | In Progress | Low | 2023-12-26 | 2024-01-09 |  | 53 | Cement | Industrial Park | 14890.66 | 14372.93 | In progress
C003 | Office Tower C | T426 | Electrical Wiring | John Miller | Completed | Low | 2024-06-25 | 2024-07-10 | 2024-07-10 | 100 | PVC Pipes | Downtown Avenue | 21867.66 | 15894.97 | No issues
C001 | Residential Building A | T308 | Plumbing Installations | Sarah Johnson | Completed | Low | 2023-01-17 | 2023-02-05 | 2023-02-05 | 100 | Concrete | Plot 21, Riverside | 15653.72 | 17307.84 | No issues
C004 | Warehouse D | T848 | Site Survey | Dave Brown | Blocked | Medium | 2023-01-15 | 2023-01-30 |  | 0 | Copper Wires | Industrial Park | 18126.2 | 14167.06 | Not started
C003 | Office Tower C | T331 | Plumbing Installations | Mike Adams | Completed | Low | 2023-01-11 | 2023-02-10 | 2023-02-10 | 100 | Roofing Sheets | Downtown Avenue | 19846.91 | 18427.97 | No issues
C003 | Office Tower C | T383 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-01-19 | 2023-02-12 |  | 14 | Cement | Downtown Avenue | 41811.16 | 42617 | In progress
C002 | Shopping Complex B | T196 | Plumbing Installations | Grace Allen | Not Started | Low | 2023-05-03 | 2023-05-18 |  | 0 | Rebar | Market Street | 9809.4 | 0 | Not started
C001 | Residential Building A | T822 | Electrical Wiring | Sarah Johnson | Completed | High | 2024-05-27 | 2024-06-16 | 2024-06-16 | 100 | Rebar | Plot 21, Riverside | 27466.65 | 24352.34 | No issues
C001 | Residential Building A | T739 | Interior Painting | Grace Allen | In Progress | Medium | 2024-06-18 | 2024-07-03 |  | 34 | Cement | Plot 21, Riverside | 45301.15 | 38904.57 | In progress
C004 | Warehouse D | T971 | Electrical Wiring | Emma White | Completed | Medium | 2024-02-11 | 2024-02-18 | 2024-02-18 | 100 | Steel Beams | Industrial Park | 27430.84 | 25342.68 | No issues
C003 | Office Tower C | T952 | Plumbing Installations | Dave Brown | In Progress | High | 2024-10-28 | 2024-11-09 |  | 69 | Copper Wires | Downtown Avenue | 5269.14 | 4756.12 | In progress
C001 | Residential Building A | T754 | Concrete Pouring | Rachel Green | Not Started | Medium | 2024-03-03 | 2024-03-22 |  | 0 | Copper Wires | Plot 21, Riverside | 34838.37 | 0 | Not started
C003 | Office Tower C | T667 | Foundation Excavation | John Miller | Blocked | Low | 2024-07-17 | 2024-07-31 |  | 0 | Paint | Downtown Avenue | 39775.84 | 31450.04 | Not started
C003 | Office Tower C | T574 | Foundation Excavation | Dave Brown | In Progress | Low | 2024-07-27 | 2024-08-13 |  | 8 | Copper Wires | Downtown Avenue | 9543.09 | 7294.4 | In progress
C003 | Office Tower C | T520 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2023-01-23 | 2023-02-21 |  | 57 | Concrete | Downtown Avenue | 16342.58 | 12168.01 | In progress
C001 | Residential Building A | T314 | Foundation Excavation | Mike Adams | Completed | Low | 2024-11-15 | 2024-12-05 | 2024-12-05 | 100 | Concrete | Plot 21, Riverside | 32510.7 | 26766.58 | No issues
C001 | Residential Building A | T789 | Interior Painting | John Miller | In Progress | High | 2024-08-04 | 2024-08-19 |  | 14 | Paint | Plot 21, Riverside | 26324.49 | 30768.82 | In progress
C002 | Shopping Complex B | T518 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2023-02-18 | 2023-03-08 |  | 0 | Roofing Sheets | Market Street | 5774.71 | 0 | Not started
C002 | Shopping Complex B | T656 | Electrical Wiring | Dave Brown | Blocked | Low | 2023-09-28 | 2023-10-20 |  | 0 | PVC Pipes | Market Street | 31604.42 | 50470.2 | Not started
C003 | Office Tower C | T905 | Foundation Excavation | Rachel Green | Completed | Medium | 2024-07-18 | 2024-08-14 | 2024-08-14 | 100 | Copper Wires | Downtown Avenue | 35213.27 | 25430.06 | No issues
C004 | Warehouse D | T195 | Electrical Wiring | Grace Allen | In Progress | Medium | 2023-04-23 | 2023-05-21 |  | 74 | Copper Wires | Industrial Park | 24845.78 | 28349.23 | In progress
C004 | Warehouse D | T752 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2024-05-27 | 2024-06-17 |  | 9 | Copper Wires | Industrial Park | 23813.35 | 15067.77 | In progress
C001 | Residential Building A | T989 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2024-02-23 | 2024-03-10 |  | 0 | Copper Wires | Plot 21, Riverside | 17854.78 | 15812.95 | Not started
C003 | Office Tower C | T607 | Foundation Excavation | Emma White | Not Started | High | 2023-04-27 | 2023-05-14 |  | 0 | Cement | Downtown Avenue | 7649.06 | 0 | Not started
C001 | Residential Building A | T583 | Interior Painting | Carlos Rivera | In Progress | Low | 2023-03-22 | 2023-04-19 |  | 13 | PVC Pipes | Plot 21, Riverside | 16870.19 | 12832.57 | In progress
C002 | Shopping Complex B | T790 | Site Survey | Mike Adams | In Progress | Low | 2024-06-03 | 2024-06-18 |  | 31 | Cement | Market Street | 25796.96 | 51149.7 | In progress
C003 | Office Tower C | T113 | Electrical Wiring | Mike Adams | Not Started | High | 2024-10-04 | 2024-10-14 |  | 0 | Cement | Downtown Avenue | 6697.6 | 0 | Not started
C002 | Shopping Complex B | T252 | Plumbing Installations | John Miller | Completed | High | 2023-08-20 | 2023-08-29 | 2023-08-29 | 100 | Concrete | Market Street | 13785.62 | 35497.44 | No issues
C002 | Shopping Complex B | T179 | Roofing | Dave Brown | Not Started | High | 2024-09-25 | 2024-10-06 |  | 0 | Concrete | Market Street | 39952.9 | 0 | Not started
C003 | Office Tower C | T557 | Steel Framework Setup | John Miller | Not Started | Low | 2024-07-28 | 2024-08-26 |  | 0 | PVC Pipes | Downtown Avenue | 44414.31 | 0 | Not started
C004 | Warehouse D | T484 | Concrete Pouring | John Miller | Not Started | Medium | 2024-05-18 | 2024-06-11 |  | 0 | PVC Pipes | Industrial Park | 18036.21 | 0 | Not started
C002 | Shopping Complex B | T197 | Concrete Pouring | Emma White | Blocked | Low | 2024-05-18 | 2024-06-05 |  | 0 | Cement | Market Street | 38058.14 | 57063.97 | Not started
C004 | Warehouse D | T362 | Interior Painting | John Miller | Blocked | Low | 2023-04-16 | 2023-05-08 |  | 0 | Roofing Sheets | Industrial Park | 8423.81 | 8956.04 | Not started
C002 | Shopping Complex B | T884 | Site Survey | Grace Allen | Not Started | High | 2023-06-21 | 2023-07-14 |  | 0 | Cement | Market Street | 41440.45 | 0 | Not started
C004 | Warehouse D | T328 | Plumbing Installations | Rachel Green | Blocked | High | 2024-12-21 | 2025-01-14 |  | 0 | Roofing Sheets | Industrial Park | 42123.35 | 42644.25 | Not started
C002 | Shopping Complex B | T570 | Plumbing Installations | John Miller | Completed | High | 2023-10-05 | 2023-10-24 | 2023-10-24 | 100 | Cement | Market Street | 27333.88 | 50159.9 | No issues
C001 | Residential Building A | T949 | Site Survey | Grace Allen | In Progress | High | 2024-10-14 | 2024-10-29 |  | 28 | Copper Wires | Plot 21, Riverside | 18884.95 | 22129.36 | In progress
C001 | Residential Building A | T318 | Roofing | Sarah Johnson | Blocked | Low | 2024-08-20 | 2024-09-10 |  | 0 | Roofing Sheets | Plot 21, Riverside | 26716.45 | 19920.47 | Not started
C001 | Residential Building A | T679 | Plumbing Installations | Carlos Rivera | Completed | High | 2023-08-22 | 2023-09-20 | 2023-09-20 | 100 | Paint | Plot 21, Riverside | 45780.12 | 40550.29 | No issues
C003 | Office Tower C | T635 | Electrical Wiring | Rachel Green | In Progress | Low | 2023-08-02 | 2023-08-29 |  | 31 | Roofing Sheets | Downtown Avenue | 21296.77 | 14413.05 | In progress
C004 | Warehouse D | T137 | Roofing | Grace Allen | Not Started | Medium | 2024-06-18 | 2024-07-08 |  | 0 | Steel Beams | Industrial Park | 7921.5 | 0 | Not started
C001 | Residential Building A | T243 | Plumbing Installations | Rachel Green | Completed | Medium | 2024-04-05 | 2024-04-30 | 2024-04-30 | 100 | Concrete | Plot 21, Riverside | 42199.39 | 47125.5 | No issues
C004 | Warehouse D | T832 | Site Survey | Mike Adams | Completed | Medium | 2024-04-17 | 2024-04-25 | 2024-04-25 | 100 | Paint | Industrial Park | 13650.65 | 8972.79 | No issues
C003 | Office Tower C | T291 | Site Survey | Sarah Johnson | In Progress | Low | 2023-04-26 | 2023-05-07 |  | 52 | Rebar | Downtown Avenue | 23947.78 | 16987.89 | In progress
C003 | Office Tower C | T464 | Site Survey | Rachel Green | Completed | High | 2023-03-16 | 2023-03-23 | 2023-03-23 | 100 | PVC Pipes | Downtown Avenue | 11381.57 | 12093.59 | No issues
C001 | Residential Building A | T299 | Site Survey | Grace Allen | In Progress | Low | 2024-08-07 | 2024-08-14 |  | 80 | Copper Wires | Plot 21, Riverside | 21376.73 | 24536.15 | In progress
C003 | Office Tower C | T374 | Concrete Pouring | Grace Allen | Not Started | High | 2024-05-03 | 2024-06-02 |  | 0 | Cement | Downtown Avenue | 12060.1 | 0 | Not started
C002 | Shopping Complex B | T272 | Plumbing Installations | Rachel Green | Not Started | Low | 2024-05-16 | 2024-05-25 |  | 0 | Cement | Market Street | 39811.29 | 0 | Not started
C003 | Office Tower C | T477 | Concrete Pouring | Carlos Rivera | Completed | High | 2024-05-17 | 2024-05-24 | 2024-05-24 | 100 | Paint | Downtown Avenue | 29836.83 | 31325.2 | No issues
C003 | Office Tower C | T427 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2024-08-01 | 2024-08-17 |  | 0 | Roofing Sheets | Downtown Avenue | 46733.79 | 0 | Not started
C001 | Residential Building A | T964 | Roofing | Carlos Rivera | Not Started | Low | 2023-06-17 | 2023-07-10 |  | 0 | Concrete | Plot 21, Riverside | 49099.51 | 0 | Not started
C002 | Shopping Complex B | T825 | Roofing | John Miller | Completed | Medium | 2023-01-01 | 2023-01-29 | 2023-01-29 | 100 | Cement | Market Street | 37670.93 | 68192.77 | No issues
C004 | Warehouse D | T165 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2024-01-13 | 2024-01-21 |  | 0 | Steel Beams | Industrial Park | 7484.64 | 6430.34 | Not started
C001 | Residential Building A | T912 | Concrete Pouring | Emma White | Not Started | High | 2024-06-28 | 2024-07-16 |  | 0 | Paint | Plot 21, Riverside | 33331.07 | 0 | Not started
C001 | Residential Building A | T178 | Site Survey | Emma White | Not Started | Medium | 2024-05-18 | 2024-06-14 |  | 0 | Cement | Plot 21, Riverside | 35292.46 | 0 | Not started
C002 | Shopping Complex B | T612 | Plumbing Installations | Grace Allen | In Progress | Medium | 2024-03-03 | 2024-03-16 |  | 52 | Rebar | Market Street | 49483.26 | 56243.5 | In progress
C004 | Warehouse D | T846 | Site Survey | Dave Brown | Not Started | Medium | 2023-11-22 | 2023-12-10 |  | 0 | Roofing Sheets | Industrial Park | 41346.46 | 0 | Not started
C004 | Warehouse D | T510 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2024-01-04 | 2024-01-29 | 2024-01-29 | 100 | Concrete | Industrial Park | 13029.58 | 10539.38 | No issues
C002 | Shopping Complex B | T858 | Roofing | Emma White | In Progress | High | 2024-05-23 | 2024-06-10 |  | 11 | Paint | Market Street | 16832.58 | 43485.8 | In progress
C001 | Residential Building A | T437 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-06-11 | 2023-06-30 |  | 0 | Concrete | Plot 21, Riverside | 24132.12 | 19706.23 | Not started
C003 | Office Tower C | T493 | Plumbing Installations | Rachel Green | In Progress | Medium | 2024-07-24 | 2024-08-03 |  | 23 | Concrete | Downtown Avenue | 29280.55 | 23347.96 | In progress
C001 | Residential Building A | T813 | Foundation Excavation | John Miller | Completed | Medium | 2023-06-19 | 2023-07-06 | 2023-07-06 | 100 | Rebar | Plot 21, Riverside | 32035.84 | 27078.93 | No issues
C001 | Residential Building A | T762 | Foundation Excavation | Mike Adams | In Progress | Low | 2023-03-17 | 2023-04-10 |  | 61 | Roofing Sheets | Plot 21, Riverside | 19639.85 | 13832.76 | In progress
C002 | Shopping Complex B | T738 | Foundation Excavation | John Miller | Not Started | High | 2023-02-19 | 2023-03-04 |  | 0 | Roofing Sheets | Market Street | 41324.97 | 0 | Not started
C004 | Warehouse D | T571 | Concrete Pouring | John Miller | Completed | Medium | 2023-08-11 | 2023-09-06 | 2023-09-06 | 100 | Steel Beams | Industrial Park | 14379.04 | 17209.39 | No issues
C003 | Office Tower C | T739 | Steel Framework Setup | Carlos Rivera | Not Started | Medium | 2024-10-17 | 2024-10-26 |  | 0 | Copper Wires | Downtown Avenue | 36311.26 | 0 | Not started
C002 | Shopping Complex B | T842 | Interior Painting | Dave Brown | Not Started | High | 2023-08-03 | 2023-09-02 |  | 0 | Rebar | Market Street | 12983.24 | 0 | Not started
C003 | Office Tower C | T480 | Steel Framework Setup | Grace Allen | Completed | Medium | 2023-03-04 | 2023-03-25 | 2023-03-25 | 100 | Concrete | Downtown Avenue | 27802.59 | 18171.72 | No issues
C001 | Residential Building A | T190 | Interior Painting | Emma White | Not Started | High | 2023-12-27 | 2024-01-07 |  | 0 | Concrete | Plot 21, Riverside | 46548.07 | 0 | Not started
C003 | Office Tower C | T965 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2023-09-23 | 2023-10-02 |  | 0 | Copper Wires | Downtown Avenue | 19350.69 | 19924.89 | Not started
C001 | Residential Building A | T503 | Electrical Wiring | John Miller | In Progress | High | 2024-09-15 | 2024-10-05 |  | 98 | PVC Pipes | Plot 21, Riverside | 15116.46 | 15007.6 | In progress
C001 | Residential Building A | T587 | Foundation Excavation | Rachel Green | Completed | High | 2024-04-13 | 2024-05-12 | 2024-05-12 | 100 | Cement | Plot 21, Riverside | 39089.15 | 43716.16 | No issues
C003 | Office Tower C | T908 | Electrical Wiring | Emma White | Blocked | High | 2023-09-24 | 2023-10-05 |  | 0 | Copper Wires | Downtown Avenue | 45118.1 | 42203.48 | Not started
C001 | Residential Building A | T759 | Roofing | Grace Allen | Blocked | Low | 2024-04-18 | 2024-04-30 |  | 0 | Rebar | Plot 21, Riverside | 7258.64 | 6470.31 | Not started
C001 | Residential Building A | T270 | Plumbing Installations | Mike Adams | Not Started | Low | 2024-01-10 | 2024-01-18 |  | 0 | Copper Wires | Plot 21, Riverside | 26379.85 | 0 | Not started
C004 | Warehouse D | T967 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-09-08 | 2024-09-29 |  | 0 | Copper Wires | Industrial Park | 38290.52 | 44282.16 | Not started
C003 | Office Tower C | T426 | Steel Framework Setup | Emma White | Blocked | High | 2023-02-13 | 2023-03-11 |  | 0 | Copper Wires | Downtown Avenue | 42036.36 | 38642.71 | Not started
C003 | Office Tower C | T714 | Electrical Wiring | Rachel Green | Completed | Medium | 2023-10-05 | 2023-10-24 | 2023-10-24 | 100 | Copper Wires | Downtown Avenue | 49585.57 | 33316.68 | No issues
C003 | Office Tower C | T717 | Foundation Excavation | Rachel Green | Completed | High | 2023-09-09 | 2023-09-18 | 2023-09-18 | 100 | Steel Beams | Downtown Avenue | 9991.97 | 9175.24 | No issues
C001 | Residential Building A | T312 | Roofing | Sarah Johnson | In Progress | High | 2023-05-05 | 2023-05-29 |  | 9 | Copper Wires | Plot 21, Riverside | 46469.84 | 30034.26 | In progress
C002 | Shopping Complex B | T240 | Concrete Pouring | Mike Adams | Completed | High | 2023-11-03 | 2023-11-17 | 2023-11-17 | 100 | Steel Beams | Market Street | 42890.73 | 73410.68 | No issues
C002 | Shopping Complex B | T340 | Site Survey | Emma White | Not Started | Low | 2023-04-24 | 2023-05-16 |  | 0 | Paint | Market Street | 42510.66 | 0 | Not started
C001 | Residential Building A | T116 | Electrical Wiring | John Miller | In Progress | Low | 2024-06-27 | 2024-07-13 |  | 52 | Steel Beams | Plot 21, Riverside | 34877.03 | 21239.03 | In progress
C004 | Warehouse D | T820 | Roofing | John Miller | Not Started | Low | 2024-10-05 | 2024-10-18 |  | 0 | Paint | Industrial Park | 32451.78 | 0 | Not started
C002 | Shopping Complex B | T997 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-10-13 | 2024-10-28 |  | 0 | Paint | Market Street | 30966.57 | 52094.25 | Not started
C004 | Warehouse D | T540 | Roofing | Rachel Green | Blocked | Medium | 2023-11-16 | 2023-12-11 |  | 0 | Roofing Sheets | Industrial Park | 34762.66 | 24440.26 | Not started
C003 | Office Tower C | T961 | Concrete Pouring | Emma White | Completed | Low | 2023-09-05 | 2023-10-01 | 2023-10-01 | 100 | Rebar | Downtown Avenue | 18713.85 | 13041.04 | No issues
C004 | Warehouse D | T485 | Interior Painting | Dave Brown | Not Started | Medium | 2023-06-02 | 2023-06-10 |  | 0 | Copper Wires | Industrial Park | 21779.27 | 0 | Not started
C003 | Office Tower C | T914 | Foundation Excavation | Emma White | Completed | High | 2024-05-28 | 2024-06-22 | 2024-06-22 | 100 | Rebar | Downtown Avenue | 36032.68 | 25625 | No issues
C004 | Warehouse D | T331 | Site Survey | Dave Brown | Completed | Low | 2024-11-27 | 2024-12-16 | 2024-12-16 | 100 | Rebar | Industrial Park | 44637.61 | 36249.72 | No issues
C003 | Office Tower C | T600 | Electrical Wiring | Grace Allen | Not Started | Low | 2023-03-04 | 2023-03-24 |  | 0 | Rebar | Downtown Avenue | 19895.56 | 0 | Not started
C002 | Shopping Complex B | T360 | Steel Framework Setup | Mike Adams | Not Started | High | 2024-03-10 | 2024-03-19 |  | 0 | Rebar | Market Street | 28527.09 | 0 | Not started
C001 | Residential Building A | T669 | Roofing | Sarah Johnson | Not Started | Low | 2024-08-11 | 2024-09-10 |  | 0 | Copper Wires | Plot 21, Riverside | 48136.7 | 0 | Not started
C001 | Residential Building A | T313 | Concrete Pouring | Carlos Rivera | Completed | High | 2024-03-20 | 2024-04-01 | 2024-04-01 | 100 | Rebar | Plot 21, Riverside | 42412.54 | 44825.49 | No issues
C001 | Residential Building A | T824 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-11-21 | 2024-12-10 |  | 0 | PVC Pipes | Plot 21, Riverside | 41710.16 | 0 | Not started
C002 | Shopping Complex B | T840 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2024-11-23 | 2024-12-17 |  | 0 | PVC Pipes | Market Street | 18801.71 | 42138.29 | Not started
C004 | Warehouse D | T652 | Foundation Excavation | Sarah Johnson | Not Started | High | 2024-07-24 | 2024-08-13 |  | 0 | Steel Beams | Industrial Park | 28722.46 | 0 | Not started
C003 | Office Tower C | T863 | Roofing | Rachel Green | In Progress | Low | 2023-01-03 | 2023-01-12 |  | 84 | PVC Pipes | Downtown Avenue | 40821.38 | 39051.26 | In progress
C001 | Residential Building A | T966 | Site Survey | Mike Adams | Blocked | Low | 2024-01-05 | 2024-02-03 |  | 0 | Paint | Plot 21, Riverside | 36780.51 | 24285.36 | Not started
C003 | Office Tower C | T256 | Interior Painting | Grace Allen | Not Started | Medium | 2023-04-02 | 2023-04-23 |  | 0 | Steel Beams | Downtown Avenue | 18547.99 | 0 | Not started
C003 | Office Tower C | T734 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-03-22 | 2024-04-11 |  | 0 | Paint | Downtown Avenue | 17983.16 | 18799.03 | Not started
C001 | Residential Building A | T588 | Plumbing Installations | Grace Allen | Completed | Low | 2023-03-04 | 2023-03-22 | 2023-03-22 | 100 | Cement | Plot 21, Riverside | 40465.84 | 26696.24 | No issues
C001 | Residential Building A | T267 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-08-23 | 2024-09-20 |  | 0 | Concrete | Plot 21, Riverside | 19614.46 | 0 | Not started
C003 | Office Tower C | T787 | Site Survey | Carlos Rivera | Completed | Medium | 2024-10-21 | 2024-11-03 | 2024-11-03 | 100 | Steel Beams | Downtown Avenue | 29916.48 | 21145.77 | No issues
C002 | Shopping Complex B | T442 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2024-08-20 | 2024-09-10 |  | 0 | PVC Pipes | Market Street | 20841.89 | 39414.17 | Not started
C002 | Shopping Complex B | T607 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-07-10 | 2024-07-20 |  | 0 | Cement | Market Street | 19925.93 | 0 | Not started
C001 | Residential Building A | T859 | Foundation Excavation | Mike Adams | Not Started | Low | 2023-03-21 | 2023-03-28 |  | 0 | PVC Pipes | Plot 21, Riverside | 13048.63 | 0 | Not started
C002 | Shopping Complex B | T453 | Foundation Excavation | Dave Brown | Completed | High | 2024-06-27 | 2024-07-09 | 2024-07-09 | 100 | Steel Beams | Market Street | 48436.49 | 81079.42 | No issues
C004 | Warehouse D | T628 | Roofing | Grace Allen | Completed | Medium | 2024-12-15 | 2025-01-12 | 2025-01-12 | 100 | Copper Wires | Industrial Park | 21119.37 | 16779.6 | No issues
C002 | Shopping Complex B | T167 | Concrete Pouring | Grace Allen | In Progress | High | 2024-06-19 | 2024-07-05 |  | 93 | Concrete | Market Street | 24025.05 | 49784.15 | In progress
C003 | Office Tower C | T569 | Roofing | Sarah Johnson | In Progress | Low | 2023-06-20 | 2023-07-04 |  | 45 | Paint | Downtown Avenue | 9166.95 | 7130.3 | In progress
C004 | Warehouse D | T773 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2023-03-26 | 2023-04-19 |  | 76 | Cement | Industrial Park | 17573.44 | 13364.92 | In progress
C004 | Warehouse D | T571 | Plumbing Installations | Emma White | Blocked | Medium | 2024-02-03 | 2024-02-11 |  | 0 | Concrete | Industrial Park | 41336.57 | 47314.68 | Not started
C002 | Shopping Complex B | T175 | Electrical Wiring | Rachel Green | Completed | Low | 2023-02-11 | 2023-02-18 | 2023-02-18 | 100 | Steel Beams | Market Street | 25484.86 | 50863.45 | No issues
C004 | Warehouse D | T280 | Interior Painting | Carlos Rivera | In Progress | Low | 2024-09-28 | 2024-10-16 |  | 21 | Rebar | Industrial Park | 26069.15 | 25459.67 | In progress
C001 | Residential Building A | T410 | Interior Painting | John Miller | Completed | Low | 2024-05-10 | 2024-05-23 | 2024-05-23 | 100 | PVC Pipes | Plot 21, Riverside | 35638.5 | 38917.29 | No issues
C003 | Office Tower C | T736 | Plumbing Installations | Rachel Green | In Progress | High | 2024-05-17 | 2024-05-31 |  | 56 | Roofing Sheets | Downtown Avenue | 22278.59 | 18143.39 | In progress
C002 | Shopping Complex B | T193 | Interior Painting | Rachel Green | Not Started | Medium | 2023-01-20 | 2023-02-14 |  | 0 | Cement | Market Street | 46679.31 | 0 | Not started
C001 | Residential Building A | T615 | Electrical Wiring | Emma White | Not Started | Low | 2023-08-01 | 2023-08-15 |  | 0 | Steel Beams | Plot 21, Riverside | 21340.34 | 0 | Not started
C003 | Office Tower C | T579 | Roofing | Dave Brown | Completed | Low | 2024-07-28 | 2024-08-27 | 2024-08-27 | 100 | Rebar | Downtown Avenue | 48043.53 | 50389.67 | No issues
C003 | Office Tower C | T321 | Concrete Pouring | Grace Allen | In Progress | Medium | 2024-07-28 | 2024-08-18 |  | 78 | Rebar | Downtown Avenue | 45492.43 | 49263.01 | In progress
C002 | Shopping Complex B | T521 | Roofing | Grace Allen | Blocked | High | 2024-06-06 | 2024-06-13 |  | 0 | Paint | Market Street | 33445.64 | 63665.04 | Not started
C003 | Office Tower C | T559 | Roofing | Rachel Green | Completed | Low | 2023-01-10 | 2023-01-29 | 2023-01-29 | 100 | Roofing Sheets | Downtown Avenue | 34328.17 | 24522.58 | No issues
C002 | Shopping Complex B | T280 | Interior Painting | John Miller | Not Started | Low | 2023-01-09 | 2023-01-18 |  | 0 | PVC Pipes | Market Street | 44028.1 | 0 | Not started
C004 | Warehouse D | T736 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-03-22 | 2024-04-21 |  | 0 | PVC Pipes | Industrial Park | 6440.85 | 0 | Not started
C003 | Office Tower C | T556 | Site Survey | Dave Brown | In Progress | Medium | 2023-12-27 | 2024-01-05 |  | 56 | Copper Wires | Downtown Avenue | 35944.08 | 42587.75 | In progress
C003 | Office Tower C | T885 | Roofing | Carlos Rivera | Not Started | Low | 2024-12-24 | 2025-01-12 |  | 0 | Paint | Downtown Avenue | 47793.18 | 0 | Not started
C001 | Residential Building A | T592 | Site Survey | Emma White | Not Started | Low | 2023-10-24 | 2023-11-10 |  | 0 | Steel Beams | Plot 21, Riverside | 34044.33 | 0 | Not started
C004 | Warehouse D | T425 | Steel Framework Setup | Mike Adams | Not Started | Low | 2023-03-14 | 2023-04-04 |  | 0 | Copper Wires | Industrial Park | 34972.35 | 0 | Not started
C004 | Warehouse D | T421 | Interior Painting | Dave Brown | Not Started | Medium | 2024-07-10 | 2024-07-18 |  | 0 | Roofing Sheets | Industrial Park | 33617.87 | 0 | Not started
C003 | Office Tower C | T660 | Steel Framework Setup | Emma White | Blocked | Medium | 2023-08-06 | 2023-08-22 |  | 0 | Copper Wires | Downtown Avenue | 42595.16 | 43231.68 | Not started
C004 | Warehouse D | T572 | Concrete Pouring | Sarah Johnson | Blocked | High | 2023-10-10 | 2023-10-23 |  | 0 | Concrete | Industrial Park | 29013.1 | 24369.91 | Not started
C003 | Office Tower C | T714 | Roofing | Carlos Rivera | Not Started | Medium | 2024-02-20 | 2024-03-14 |  | 0 | PVC Pipes | Downtown Avenue | 20903.66 | 0 | Not started
C002 | Shopping Complex B | T958 | Foundation Excavation | Dave Brown | In Progress | Medium | 2023-06-19 | 2023-07-16 |  | 78 | Copper Wires | Market Street | 25909.53 | 44620.9 | In progress
C004 | Warehouse D | T159 | Steel Framework Setup | Sarah Johnson | Completed | High | 2024-07-01 | 2024-07-25 | 2024-07-25 | 100 | Rebar | Industrial Park | 32944.82 | 32503.76 | No issues
C001 | Residential Building A | T336 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-06-11 | 2023-07-10 |  | 0 | Paint | Plot 21, Riverside | 37431.02 | 27998.09 | Not started
C001 | Residential Building A | T895 | Interior Painting | Emma White | Completed | Medium | 2023-10-22 | 2023-11-13 | 2023-11-13 | 100 | Rebar | Plot 21, Riverside | 5246.6 | 5510.17 | No issues
C004 | Warehouse D | T838 | Plumbing Installations | Mike Adams | Completed | Medium | 2023-05-12 | 2023-06-03 | 2023-06-03 | 100 | PVC Pipes | Industrial Park | 27571.76 | 25890.68 | No issues
C002 | Shopping Complex B | T707 | Interior Painting | Grace Allen | Not Started | High | 2024-03-24 | 2024-04-07 |  | 0 | Copper Wires | Market Street | 29592.92 | 0 | Not started
C004 | Warehouse D | T733 | Concrete Pouring | Rachel Green | Not Started | High | 2024-12-04 | 2025-01-02 |  | 0 | PVC Pipes | Industrial Park | 23044.92 | 0 | Not started
C001 | Residential Building A | T147 | Roofing | Grace Allen | In Progress | Medium | 2023-09-07 | 2023-09-20 |  | 56 | Paint | Plot 21, Riverside | 22687.93 | 18100.69 | In progress
C003 | Office Tower C | T847 | Electrical Wiring | Emma White | Blocked | Medium | 2023-02-24 | 2023-03-21 |  | 0 | Steel Beams | Downtown Avenue | 32022.04 | 29920.56 | Not started
C002 | Shopping Complex B | T276 | Plumbing Installations | Grace Allen | Not Started | High | 2024-03-20 | 2024-03-28 |  | 0 | Concrete | Market Street | 46015.61 | 0 | Not started
C004 | Warehouse D | T172 | Electrical Wiring | Emma White | Not Started | Medium | 2024-01-06 | 2024-01-23 |  | 0 | PVC Pipes | Industrial Park | 13686.09 | 0 | Not started
C004 | Warehouse D | T833 | Roofing | Emma White | Completed | Medium | 2024-11-05 | 2024-11-23 | 2024-11-23 | 100 | Concrete | Industrial Park | 40997.86 | 44245.31 | No issues
C001 | Residential Building A | T835 | Interior Painting | Dave Brown | In Progress | High | 2024-02-04 | 2024-02-28 |  | 97 | Roofing Sheets | Plot 21, Riverside | 37790.22 | 38402.28 | In progress
C002 | Shopping Complex B | T276 | Steel Framework Setup | John Miller | Completed | High | 2023-11-06 | 2023-11-19 | 2023-11-19 | 100 | PVC Pipes | Market Street | 25274.94 | 49294.11 | No issues
C003 | Office Tower C | T384 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2023-07-20 | 2023-08-16 |  | 34 | Copper Wires | Downtown Avenue | 14560.12 | 17358.92 | In progress
C001 | Residential Building A | T583 | Site Survey | Carlos Rivera | Blocked | Low | 2023-02-16 | 2023-03-02 |  | 0 | Cement | Plot 21, Riverside | 30482.8 | 25531.03 | Not started
C004 | Warehouse D | T145 | Interior Painting | Grace Allen | Blocked | Low | 2024-11-27 | 2024-12-16 |  | 0 | Roofing Sheets | Industrial Park | 30927.32 | 36046.59 | Not started
C004 | Warehouse D | T320 | Electrical Wiring | Carlos Rivera | Completed | Low | 2024-02-28 | 2024-03-14 | 2024-03-14 | 100 | Copper Wires | Industrial Park | 24215 | 25496.68 | No issues
C002 | Shopping Complex B | T247 | Electrical Wiring | Rachel Green | Completed | Medium | 2023-11-09 | 2023-11-27 | 2023-11-27 | 100 | PVC Pipes | Market Street | 37261.66 | 57389.27 | No issues
C001 | Residential Building A | T524 | Steel Framework Setup | Emma White | Completed | Low | 2023-04-01 | 2023-04-08 | 2023-04-08 | 100 | Paint | Plot 21, Riverside | 27723.06 | 31868.46 | No issues
C003 | Office Tower C | T103 | Roofing | Sarah Johnson | Blocked | Low | 2024-05-27 | 2024-06-23 |  | 0 | Rebar | Downtown Avenue | 30226.14 | 22089.84 | Not started
C003 | Office Tower C | T560 | Site Survey | Rachel Green | Completed | Low | 2024-11-21 | 2024-12-05 | 2024-12-05 | 100 | Cement | Downtown Avenue | 33484.94 | 30456.88 | No issues
C004 | Warehouse D | T866 | Electrical Wiring | Sarah Johnson | Completed | Low | 2024-05-21 | 2024-05-30 | 2024-05-30 | 100 | Paint | Industrial Park | 29460.79 | 19278.98 | No issues
C001 | Residential Building A | T798 | Roofing | Mike Adams | In Progress | Medium | 2023-12-28 | 2024-01-15 |  | 56 | Paint | Plot 21, Riverside | 25478.11 | 24317.09 | In progress
C002 | Shopping Complex B | T726 | Electrical Wiring | Grace Allen | In Progress | High | 2023-07-05 | 2023-07-27 |  | 69 | Steel Beams | Market Street | 34905.54 | 64807.31 | In progress
C004 | Warehouse D | T694 | Concrete Pouring | Emma White | In Progress | High | 2023-10-15 | 2023-11-07 |  | 38 | Roofing Sheets | Industrial Park | 5349.63 | 6076.15 | In progress
C003 | Office Tower C | T756 | Concrete Pouring | Dave Brown | In Progress | Medium | 2024-12-09 | 2024-12-21 |  | 1 | Steel Beams | Downtown Avenue | 39409.36 | 35039.97 | In progress
C004 | Warehouse D | T209 | Interior Painting | Emma White | Completed | Low | 2024-02-08 | 2024-02-21 | 2024-02-21 | 100 | Roofing Sheets | Industrial Park | 28858.08 | 28064.06 | No issues
C004 | Warehouse D | T784 | Site Survey | Dave Brown | Blocked | Low | 2023-07-03 | 2023-07-18 |  | 0 | Roofing Sheets | Industrial Park | 17525.91 | 13800.25 | Not started
C004 | Warehouse D | T595 | Site Survey | Dave Brown | In Progress | High | 2023-07-24 | 2023-08-11 |  | 13 | Steel Beams | Industrial Park | 41760.63 | 48068.02 | In progress
C002 | Shopping Complex B | T746 | Steel Framework Setup | Carlos Rivera | In Progress | High | 2024-09-09 | 2024-09-22 |  | 67 | Rebar | Market Street | 20154.94 | 38729.63 | In progress
C001 | Residential Building A | T989 | Interior Painting | Grace Allen | Blocked | High | 2023-06-04 | 2023-06-26 |  | 0 | Concrete | Plot 21, Riverside | 16580.1 | 11906.57 | Not started
C004 | Warehouse D | T220 | Site Survey | Emma White | Completed | High | 2024-09-28 | 2024-10-18 | 2024-10-18 | 100 | Steel Beams | Industrial Park | 8794.62 | 5844.88 | No issues
C002 | Shopping Complex B | T695 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-03-08 | 2024-03-27 |  | 1 | Cement | Market Street | 28915.02 | 54157.01 | In progress
C004 | Warehouse D | T860 | Electrical Wiring | John Miller | Blocked | Medium | 2024-07-27 | 2024-08-16 |  | 0 | PVC Pipes | Industrial Park | 23341.68 | 25321.94 | Not started
C003 | Office Tower C | T848 | Roofing | Carlos Rivera | In Progress | Medium | 2023-02-12 | 2023-03-01 |  | 67 | Roofing Sheets | Downtown Avenue | 23690.77 | 24318.59 | In progress
C004 | Warehouse D | T394 | Roofing | John Miller | Completed | High | 2023-11-14 | 2023-12-14 | 2023-12-14 | 100 | PVC Pipes | Industrial Park | 46077.94 | 39374.98 | No issues
C003 | Office Tower C | T658 | Interior Painting | Rachel Green | Completed | Low | 2024-03-07 | 2024-03-28 | 2024-03-28 | 100 | Roofing Sheets | Downtown Avenue | 12714.92 | 9674.58 | No issues
C003 | Office Tower C | T303 | Concrete Pouring | Emma White | In Progress | Medium | 2023-03-14 | 2023-04-06 |  | 76 | Copper Wires | Downtown Avenue | 7856.57 | 7696.29 | In progress
C004 | Warehouse D | T383 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2023-11-20 | 2023-12-03 |  | 0 | Cement | Industrial Park | 37647.18 | 40883.12 | Not started
C002 | Shopping Complex B | T606 | Interior Painting | Sarah Johnson | Not Started | Low | 2023-04-17 | 2023-05-16 |  | 0 | Cement | Market Street | 24516.62 | 0 | Not started
C001 | Residential Building A | T261 | Interior Painting | Grace Allen | In Progress | Low | 2023-10-19 | 2023-11-16 |  | 99 | Paint | Plot 21, Riverside | 44210.63 | 33152.1 | In progress
C003 | Office Tower C | T536 | Electrical Wiring | John Miller | Blocked | Medium | 2024-01-21 | 2024-02-13 |  | 0 | Concrete | Downtown Avenue | 18200.89 | 13567.83 | Not started
C002 | Shopping Complex B | T690 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-10-21 | 2023-11-13 |  | 0 | Rebar | Market Street | 13294.37 | 38852.51 | Not started
C002 | Shopping Complex B | T906 | Concrete Pouring | John Miller | In Progress | Low | 2023-01-20 | 2023-01-30 |  | 4 | Concrete | Market Street | 5784.56 | 30780.4 | In progress
C002 | Shopping Complex B | T127 | Site Survey | John Miller | Blocked | High | 2024-06-28 | 2024-07-16 |  | 0 | Steel Beams | Market Street | 21897.93 | 47571.41 | Not started
C003 | Office Tower C | T474 | Electrical Wiring | Dave Brown | Not Started | Medium | 2024-09-01 | 2024-09-28 |  | 0 | Rebar | Downtown Avenue | 11394.25 | 0 | Not started
C004 | Warehouse D | T650 | Site Survey | Emma White | Blocked | Medium | 2024-08-04 | 2024-08-18 |  | 0 | Steel Beams | Industrial Park | 27184.5 | 32589.34 | Not started
C001 | Residential Building A | T149 | Interior Painting | Rachel Green | Blocked | High | 2023-02-02 | 2023-03-01 |  | 0 | Roofing Sheets | Plot 21, Riverside | 28702.34 | 27518.01 | Not started
C004 | Warehouse D | T358 | Concrete Pouring | Mike Adams | Completed | Low | 2024-05-17 | 2024-06-14 | 2024-06-14 | 100 | Cement | Industrial Park | 22402.95 | 17590.29 | No issues
C004 | Warehouse D | T927 | Plumbing Installations | Sarah Johnson | Completed | Low | 2024-10-21 | 2024-10-28 | 2024-10-28 | 100 | PVC Pipes | Industrial Park | 20430.05 | 22740.56 | No issues
C004 | Warehouse D | T119 | Roofing | Rachel Green | Completed | High | 2024-06-11 | 2024-06-20 | 2024-06-20 | 100 | Concrete | Industrial Park | 11186.19 | 10904.98 | No issues
C002 | Shopping Complex B | T468 | Roofing | Dave Brown | Blocked | Low | 2024-08-11 | 2024-09-07 |  | 0 | Cement | Market Street | 35624.71 | 50143.81 | Not started
C003 | Office Tower C | T199 | Concrete Pouring | John Miller | Blocked | Low | 2024-01-06 | 2024-01-25 |  | 0 | Roofing Sheets | Downtown Avenue | 40681.02 | 46635.14 | Not started
C001 | Residential Building A | T580 | Electrical Wiring | Grace Allen | Not Started | High | 2023-06-16 | 2023-07-12 |  | 0 | Concrete | Plot 21, Riverside | 36875.02 | 0 | Not started
C004 | Warehouse D | T668 | Roofing | Sarah Johnson | Blocked | Medium | 2023-06-23 | 2023-07-11 |  | 0 | Cement | Industrial Park | 36712.37 | 23100.56 | Not started
C003 | Office Tower C | T240 | Site Survey | John Miller | Completed | High | 2024-09-12 | 2024-10-07 | 2024-10-07 | 100 | Cement | Downtown Avenue | 10928.97 | 8144.83 | No issues
C002 | Shopping Complex B | T431 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-08-19 | 2024-09-15 |  | 0 | Paint | Market Street | 36378.92 | 0 | Not started
C001 | Residential Building A | T751 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-04-15 | 2023-05-10 |  | 59 | Paint | Plot 21, Riverside | 44714.47 | 28069.82 | In progress
C003 | Office Tower C | T193 | Plumbing Installations | John Miller | Completed | Low | 2024-04-26 | 2024-05-15 | 2024-05-15 | 100 | Roofing Sheets | Downtown Avenue | 40709.04 | 42779.19 | No issues
C002 | Shopping Complex B | T301 | Site Survey | John Miller | In Progress | Medium | 2023-06-02 | 2023-06-11 |  | 76 | Paint | Market Street | 27069.42 | 49961.99 | In progress
C001 | Residential Building A | T729 | Plumbing Installations | Mike Adams | Completed | High | 2023-03-01 | 2023-03-16 | 2023-03-16 | 100 | Paint | Plot 21, Riverside | 20583.05 | 21552.41 | No issues
C001 | Residential Building A | T763 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2024-07-14 | 2024-08-06 |  | 74 | Cement | Plot 21, Riverside | 42939.76 | 35920.11 | In progress
C004 | Warehouse D | T963 | Plumbing Installations | John Miller | Not Started | Medium | 2023-01-04 | 2023-01-23 |  | 0 | PVC Pipes | Industrial Park | 42654.04 | 0 | Not started
C004 | Warehouse D | T865 | Foundation Excavation | Dave Brown | In Progress | High | 2024-06-05 | 2024-06-15 |  | 61 | Cement | Industrial Park | 9658.83 | 6178.44 | In progress
C002 | Shopping Complex B | T388 | Interior Painting | Mike Adams | Not Started | High | 2023-06-06 | 2023-06-30 |  | 0 | Concrete | Market Street | 48248.14 | 0 | Not started
C002 | Shopping Complex B | T598 | Steel Framework Setup | Emma White | Completed | High | 2023-12-24 | 2024-01-16 | 2024-01-16 | 100 | Paint | Market Street | 8451.15 | 30606.45 | No issues
C004 | Warehouse D | T279 | Site Survey | Dave Brown | Completed | High | 2023-09-23 | 2023-10-21 | 2023-10-21 | 100 | Rebar | Industrial Park | 36733.9 | 25403.5 | No issues
C002 | Shopping Complex B | T993 | Electrical Wiring | Carlos Rivera | Blocked | High | 2023-10-26 | 2023-11-02 |  | 0 | Copper Wires | Market Street | 43829.7 | 67452.91 | Not started
C002 | Shopping Complex B | T804 | Electrical Wiring | John Miller | Completed | High | 2024-04-28 | 2024-05-22 | 2024-05-22 | 100 | Rebar | Market Street | 42045.12 | 51787.37 | No issues
C003 | Office Tower C | T472 | Interior Painting | Dave Brown | Blocked | Low | 2023-02-25 | 2023-03-20 |  | 0 | Rebar | Downtown Avenue | 33404.29 | 21861.05 | Not started
C004 | Warehouse D | T843 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2023-12-07 | 2023-12-21 |  | 53 | Cement | Industrial Park | 35372.5 | 26353.65 | In progress
C003 | Office Tower C | T486 | Foundation Excavation | Carlos Rivera | Completed | High | 2024-01-09 | 2024-02-01 | 2024-02-01 | 100 | Rebar | Downtown Avenue | 42596.36 | 27289.69 | No issues
C002 | Shopping Complex B | T497 | Roofing | Dave Brown | Not Started | Medium | 2024-12-05 | 2024-12-31 |  | 0 | Roofing Sheets | Market Street | 46948.2 | 0 | Not started
C004 | Warehouse D | T313 | Foundation Excavation | Mike Adams | Completed | Low | 2023-12-24 | 2024-01-01 | 2024-01-01 | 100 | Concrete | Industrial Park | 24508.94 | 28444.18 | No issues
C002 | Shopping Complex B | T415 | Site Survey | Dave Brown | Completed | High | 2023-06-19 | 2023-07-15 | 2023-07-15 | 100 | Concrete | Market Street | 30375.29 | 51415.14 | No issues
C002 | Shopping Complex B | T941 | Foundation Excavation | Rachel Green | Not Started | High | 2024-06-22 | 2024-07-03 |  | 0 | Rebar | Market Street | 48708.46 | 0 | Not started
C003 | Office Tower C | T947 | Site Survey | Emma White | Blocked | Low | 2023-02-26 | 2023-03-23 |  | 0 | Concrete | Downtown Avenue | 27457.14 | 25255.41 | Not started
C004 | Warehouse D | T925 | Electrical Wiring | Emma White | Blocked | Medium | 2024-01-03 | 2024-01-27 |  | 0 | PVC Pipes | Industrial Park | 11588.72 | 12719.91 | Not started
C003 | Office Tower C | T131 | Concrete Pouring | John Miller | Completed | High | 2023-09-27 | 2023-10-04 | 2023-10-04 | 100 | Steel Beams | Downtown Avenue | 15440.81 | 11334.58 | No issues
C001 | Residential Building A | T566 | Electrical Wiring | Dave Brown | In Progress | High | 2023-12-27 | 2024-01-03 |  | 62 | Concrete | Plot 21, Riverside | 36034.79 | 22285.81 | In progress
C002 | Shopping Complex B | T503 | Foundation Excavation | Mike Adams | Completed | Medium | 2023-06-25 | 2023-07-06 | 2023-07-06 | 100 | Rebar | Market Street | 25005.38 | 52108.47 | No issues
C004 | Warehouse D | T633 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-12-23 | 2025-01-12 | 2025-01-12 | 100 | Paint | Industrial Park | 29234.06 | 19607.14 | No issues
C004 | Warehouse D | T630 | Interior Painting | Dave Brown | Blocked | Low | 2024-07-08 | 2024-08-06 |  | 0 | Cement | Industrial Park | 22394.89 | 14408.09 | Not started
C003 | Office Tower C | T130 | Site Survey | Mike Adams | In Progress | Low | 2024-02-13 | 2024-03-10 |  | 35 | Cement | Downtown Avenue | 24874.69 | 21953.55 | In progress
C001 | Residential Building A | T956 | Electrical Wiring | Mike Adams | In Progress | High | 2023-02-18 | 2023-03-15 |  | 9 | Concrete | Plot 21, Riverside | 5198.89 | 4271.46 | In progress
C003 | Office Tower C | T876 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-01-16 | 2024-02-13 |  | 22 | Copper Wires | Downtown Avenue | 7911.39 | 5202.82 | In progress
C004 | Warehouse D | T448 | Site Survey | Mike Adams | Not Started | Medium | 2024-05-11 | 2024-06-07 |  | 0 | Paint | Industrial Park | 39530.58 | 0 | Not started
C001 | Residential Building A | T620 | Foundation Excavation | Mike Adams | Completed | Medium | 2023-06-28 | 2023-07-19 | 2023-07-19 | 100 | Paint | Plot 21, Riverside | 19837.57 | 16168.57 | No issues
C002 | Shopping Complex B | T611 | Interior Painting | Dave Brown | Completed | Low | 2023-08-18 | 2023-09-06 | 2023-09-06 | 100 | PVC Pipes | Market Street | 43716.33 | 58193.15 | No issues
C001 | Residential Building A | T587 | Roofing | Emma White | Blocked | Medium | 2023-07-07 | 2023-08-03 |  | 0 | Cement | Plot 21, Riverside | 14645.48 | 12422.91 | Not started
C004 | Warehouse D | T502 | Interior Painting | Carlos Rivera | Completed | Low | 2024-10-23 | 2024-11-12 | 2024-11-12 | 100 | PVC Pipes | Industrial Park | 21869.57 | 23410.99 | No issues
C003 | Office Tower C | T928 | Concrete Pouring | Rachel Green | Not Started | Low | 2024-01-15 | 2024-01-23 |  | 0 | Paint | Downtown Avenue | 26440.89 | 0 | Not started
C002 | Shopping Complex B | T646 | Interior Painting | Rachel Green | Blocked | High | 2024-06-28 | 2024-07-18 |  | 0 | Copper Wires | Market Street | 23856.33 | 50538.34 | Not started
C003 | Office Tower C | T209 | Interior Painting | Grace Allen | Completed | High | 2023-02-17 | 2023-03-08 | 2023-03-08 | 100 | Rebar | Downtown Avenue | 17068.3 | 18227.65 | No issues
C003 | Office Tower C | T737 | Interior Painting | Emma White | In Progress | Low | 2023-03-13 | 2023-03-21 |  | 29 | Concrete | Downtown Avenue | 19137.19 | 18263.82 | In progress
C003 | Office Tower C | T899 | Foundation Excavation | Mike Adams | Completed | Medium | 2024-05-19 | 2024-05-31 | 2024-05-31 | 100 | Cement | Downtown Avenue | 35384.31 | 27668.69 | No issues
C004 | Warehouse D | T635 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-11-01 | 2023-11-17 |  | 0 | Paint | Industrial Park | 32189.23 | 33289.19 | Not started
C001 | Residential Building A | T142 | Steel Framework Setup | Emma White | Not Started | High | 2023-01-09 | 2023-02-04 |  | 0 | Cement | Plot 21, Riverside | 26569.04 | 0 | Not started
C001 | Residential Building A | T676 | Roofing | Grace Allen | Not Started | High | 2024-07-21 | 2024-08-07 |  | 0 | Roofing Sheets | Plot 21, Riverside | 41204.36 | 0 | Not started
C004 | Warehouse D | T208 | Site Survey | Emma White | Completed | High | 2024-11-02 | 2024-11-20 | 2024-11-20 | 100 | PVC Pipes | Industrial Park | 23711.88 | 25395.18 | No issues
C003 | Office Tower C | T813 | Plumbing Installations | John Miller | Blocked | High | 2024-09-06 | 2024-10-05 |  | 0 | Paint | Downtown Avenue | 36087.52 | 34913.83 | Not started
C003 | Office Tower C | T369 | Site Survey | John Miller | Not Started | Medium | 2023-08-28 | 2023-09-22 |  | 0 | Concrete | Downtown Avenue | 42965.85 | 0 | Not started
C001 | Residential Building A | T616 | Electrical Wiring | Grace Allen | Completed | High | 2024-04-14 | 2024-04-26 | 2024-04-26 | 100 | Steel Beams | Plot 21, Riverside | 13077.95 | 10959.01 | No issues
C001 | Residential Building A | T685 | Roofing | Dave Brown | Completed | Medium | 2023-04-27 | 2023-05-27 | 2023-05-27 | 100 | Cement | Plot 21, Riverside | 42987.76 | 29518.48 | No issues
C004 | Warehouse D | T129 | Site Survey | Carlos Rivera | Not Started | Medium | 2023-09-23 | 2023-10-04 |  | 0 | PVC Pipes | Industrial Park | 11898.29 | 0 | Not started
C004 | Warehouse D | T663 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2024-08-14 | 2024-08-27 |  | 0 | Rebar | Industrial Park | 9855 | 0 | Not started
C001 | Residential Building A | T211 | Foundation Excavation | Mike Adams | Not Started | Medium | 2024-08-12 | 2024-09-06 |  | 0 | Paint | Plot 21, Riverside | 44959.03 | 0 | Not started
C004 | Warehouse D | T689 | Site Survey | Emma White | In Progress | High | 2023-09-10 | 2023-10-03 |  | 58 | Rebar | Industrial Park | 11012.9 | 8034.56 | In progress
C004 | Warehouse D | T579 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2023-04-23 | 2023-05-11 | 2023-05-11 | 100 | Concrete | Industrial Park | 37611.19 | 44545.27 | No issues
C003 | Office Tower C | T453 | Roofing | Mike Adams | Completed | High | 2024-01-06 | 2024-01-16 | 2024-01-16 | 100 | Paint | Downtown Avenue | 16071.3 | 16483.5 | No issues
C004 | Warehouse D | T341 | Site Survey | Grace Allen | Completed | Medium | 2023-06-03 | 2023-06-12 | 2023-06-12 | 100 | Paint | Industrial Park | 37498.74 | 40708.87 | No issues
C001 | Residential Building A | T267 | Roofing | Sarah Johnson | Blocked | Low | 2023-01-20 | 2023-02-02 |  | 0 | Paint | Plot 21, Riverside | 42417.75 | 26098.96 | Not started
C004 | Warehouse D | T786 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-07-17 | 2024-08-12 | 2024-08-12 | 100 | Roofing Sheets | Industrial Park | 25990.46 | 16509.14 | No issues
C001 | Residential Building A | T750 | Interior Painting | Mike Adams | In Progress | Low | 2023-06-22 | 2023-07-17 |  | 78 | Cement | Plot 21, Riverside | 22894.97 | 18992.14 | In progress
C001 | Residential Building A | T134 | Steel Framework Setup | John Miller | Not Started | High | 2024-04-12 | 2024-05-12 |  | 0 | Roofing Sheets | Plot 21, Riverside | 30592.4 | 0 | Not started
C004 | Warehouse D | T506 | Site Survey | Sarah Johnson | Completed | High | 2023-05-24 | 2023-06-23 | 2023-06-23 | 100 | Paint | Industrial Park | 13161.72 | 9387.12 | No issues
C004 | Warehouse D | T732 | Electrical Wiring | Sarah Johnson | Blocked | Low | 2023-12-19 | 2024-01-15 |  | 0 | Paint | Industrial Park | 9702.78 | 9131.27 | Not started
C004 | Warehouse D | T103 | Plumbing Installations | Mike Adams | Not Started | High | 2023-07-06 | 2023-07-27 |  | 0 | Cement | Industrial Park | 41015.73 | 0 | Not started
C002 | Shopping Complex B | T984 | Interior Painting | Dave Brown | In Progress | Low | 2024-05-25 | 2024-06-07 |  | 52 | PVC Pipes | Market Street | 28075.84 | 56177.11 | In progress
C002 | Shopping Complex B | T317 | Roofing | Grace Allen | Not Started | High | 2024-05-12 | 2024-06-07 |  | 0 | Steel Beams | Market Street | 29016.28 | 0 | Not started
C002 | Shopping Complex B | T532 | Roofing | Grace Allen | In Progress | Medium | 2023-11-04 | 2023-11-30 |  | 42 | Copper Wires | Market Street | 28181.18 | 45302.61 | In progress
C001 | Residential Building A | T948 | Interior Painting | Carlos Rivera | Completed | Low | 2023-02-06 | 2023-02-25 | 2023-02-25 | 100 | Roofing Sheets | Plot 21, Riverside | 12858.08 | 8123.7 | No issues
C001 | Residential Building A | T474 | Interior Painting | Dave Brown | Blocked | Low | 2024-08-23 | 2024-09-06 |  | 0 | PVC Pipes | Plot 21, Riverside | 16619.96 | 14178.31 | Not started
C003 | Office Tower C | T752 | Interior Painting | Grace Allen | Not Started | Low | 2023-10-23 | 2023-11-15 |  | 0 | Concrete | Downtown Avenue | 45807.13 | 0 | Not started
C002 | Shopping Complex B | T477 | Concrete Pouring | Emma White | Completed | Medium | 2023-05-08 | 2023-05-22 | 2023-05-22 | 100 | Roofing Sheets | Market Street | 5272.81 | 28837.95 | No issues
C001 | Residential Building A | T158 | Electrical Wiring | Emma White | In Progress | High | 2024-07-15 | 2024-08-09 |  | 87 | Rebar | Plot 21, Riverside | 26414.35 | 25250.09 | In progress
C001 | Residential Building A | T382 | Roofing | Carlos Rivera | Not Started | Low | 2023-01-28 | 2023-02-22 |  | 0 | Paint | Plot 21, Riverside | 23807.19 | 0 | Not started
C002 | Shopping Complex B | T816 | Site Survey | John Miller | Not Started | High | 2023-06-09 | 2023-06-19 |  | 0 | Concrete | Market Street | 25460.38 | 0 | Not started
C003 | Office Tower C | T970 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-05-08 | 2024-06-01 |  | 12 | Rebar | Downtown Avenue | 46942.52 | 34573.36 | In progress
C004 | Warehouse D | T815 | Concrete Pouring | Grace Allen | In Progress | Low | 2024-05-15 | 2024-06-11 |  | 39 | Steel Beams | Industrial Park | 43300.96 | 31181.68 | In progress
C002 | Shopping Complex B | T221 | Steel Framework Setup | Grace Allen | In Progress | Low | 2023-07-05 | 2023-07-19 |  | 79 | Roofing Sheets | Market Street | 39989.22 | 70451.68 | In progress
C001 | Residential Building A | T894 | Electrical Wiring | Dave Brown | Completed | Medium | 2023-08-10 | 2023-09-08 | 2023-09-08 | 100 | Cement | Plot 21, Riverside | 26838.58 | 30233 | No issues
C001 | Residential Building A | T107 | Interior Painting | Emma White | In Progress | Medium | 2024-06-17 | 2024-07-13 |  | 1 | Paint | Plot 21, Riverside | 11574.17 | 9606.06 | In progress
C001 | Residential Building A | T107 | Steel Framework Setup | John Miller | In Progress | Low | 2024-12-05 | 2024-12-23 |  | 9 | Roofing Sheets | Plot 21, Riverside | 18884.97 | 22587.06 | In progress
C003 | Office Tower C | T807 | Roofing | Rachel Green | Not Started | Medium | 2023-12-15 | 2024-01-08 |  | 0 | Steel Beams | Downtown Avenue | 45305.82 | 0 | Not started
C002 | Shopping Complex B | T131 | Roofing | Emma White | In Progress | Low | 2023-09-01 | 2023-09-15 |  | 16 | Concrete | Market Street | 48141.8 | 63526.63 | In progress
C001 | Residential Building A | T431 | Steel Framework Setup | Emma White | Blocked | High | 2024-08-19 | 2024-09-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 26028.41 | 16075.69 | Not started
C003 | Office Tower C | T578 | Interior Painting | Mike Adams | In Progress | Medium | 2023-02-13 | 2023-03-10 |  | 71 | Copper Wires | Downtown Avenue | 19881.5 | 21132.67 | In progress
C001 | Residential Building A | T979 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-03-01 | 2023-03-14 |  | 0 | Paint | Plot 21, Riverside | 31133.99 | 0 | Not started
C001 | Residential Building A | T503 | Electrical Wiring | Emma White | Completed | Low | 2024-10-26 | 2024-11-14 | 2024-11-14 | 100 | Steel Beams | Plot 21, Riverside | 46104.43 | 38873.55 | No issues
C004 | Warehouse D | T770 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2024-03-25 | 2024-04-15 |  | 96 | Copper Wires | Industrial Park | 27552.75 | 23817.02 | In progress
C001 | Residential Building A | T707 | Electrical Wiring | John Miller | Completed | Medium | 2023-12-25 | 2024-01-15 | 2024-01-15 | 100 | PVC Pipes | Plot 21, Riverside | 29101.15 | 26886.35 | No issues
C003 | Office Tower C | T666 | Roofing | Sarah Johnson | In Progress | High | 2023-06-22 | 2023-07-09 |  | 79 | Copper Wires | Downtown Avenue | 46843.68 | 52818.8 | In progress
C001 | Residential Building A | T555 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2024-07-17 | 2024-08-11 | 2024-08-11 | 100 | Roofing Sheets | Plot 21, Riverside | 38905.99 | 23679.13 | No issues
C002 | Shopping Complex B | T387 | Roofing | Emma White | In Progress | High | 2023-05-10 | 2023-05-18 |  | 9 | Roofing Sheets | Market Street | 47451.21 | 77412.08 | In progress
C001 | Residential Building A | T154 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2024-09-19 | 2024-10-14 |  | 32 | Copper Wires | Plot 21, Riverside | 20721.72 | 16991.37 | In progress
C002 | Shopping Complex B | T189 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2024-12-06 | 2024-12-16 |  | 0 | Paint | Market Street | 25906.65 | 0 | Not started
C004 | Warehouse D | T367 | Foundation Excavation | Grace Allen | In Progress | High | 2024-01-20 | 2024-02-13 |  | 10 | Rebar | Industrial Park | 28073.91 | 29041.24 | In progress
C003 | Office Tower C | T540 | Interior Painting | Mike Adams | Blocked | Low | 2023-01-21 | 2023-02-11 |  | 0 | Concrete | Downtown Avenue | 21717.91 | 24102.5 | Not started
C001 | Residential Building A | T243 | Roofing | Dave Brown | Not Started | High | 2023-07-08 | 2023-08-02 |  | 0 | Steel Beams | Plot 21, Riverside | 26031.99 | 0 | Not started
C004 | Warehouse D | T896 | Interior Painting | Sarah Johnson | Completed | Medium | 2023-01-08 | 2023-02-05 | 2023-02-05 | 100 | Steel Beams | Industrial Park | 17729.17 | 11987.67 | No issues
C001 | Residential Building A | T306 | Foundation Excavation | John Miller | Blocked | High | 2024-06-27 | 2024-07-22 |  | 0 | Roofing Sheets | Plot 21, Riverside | 13852.64 | 11653.22 | Not started
C003 | Office Tower C | T703 | Concrete Pouring | Grace Allen | In Progress | High | 2023-08-01 | 2023-08-09 |  | 2 | Paint | Downtown Avenue | 12478.96 | 9155.77 | In progress
C004 | Warehouse D | T587 | Electrical Wiring | Mike Adams | Completed | High | 2024-09-22 | 2024-10-18 | 2024-10-18 | 100 | Cement | Industrial Park | 19525.84 | 15831.2 | No issues
C004 | Warehouse D | T969 | Interior Painting | Sarah Johnson | In Progress | High | 2024-02-26 | 2024-03-21 |  | 2 | Cement | Industrial Park | 22812.92 | 18368.17 | In progress
C001 | Residential Building A | T948 | Plumbing Installations | Mike Adams | In Progress | Medium | 2024-05-03 | 2024-05-25 |  | 12 | Cement | Plot 21, Riverside | 27172.55 | 19884.1 | In progress
C004 | Warehouse D | T442 | Concrete Pouring | Mike Adams | In Progress | High | 2024-03-21 | 2024-04-17 |  | 65 | Roofing Sheets | Industrial Park | 45251.55 | 35567.96 | In progress
C001 | Residential Building A | T943 | Electrical Wiring | Carlos Rivera | In Progress | High | 2023-06-05 | 2023-06-21 |  | 82 | Steel Beams | Plot 21, Riverside | 39258.35 | 31377.89 | In progress
C001 | Residential Building A | T268 | Roofing | Mike Adams | In Progress | High | 2023-11-22 | 2023-12-15 |  | 95 | Rebar | Plot 21, Riverside | 39574.63 | 34325.03 | In progress
C001 | Residential Building A | T961 | Plumbing Installations | John Miller | Completed | High | 2023-05-09 | 2023-06-07 | 2023-06-07 | 100 | Paint | Plot 21, Riverside | 28429.55 | 25736.16 | No issues
C001 | Residential Building A | T110 | Foundation Excavation | Dave Brown | Completed | Medium | 2024-10-13 | 2024-10-22 | 2024-10-22 | 100 | Roofing Sheets | Plot 21, Riverside | 18805.13 | 13898.38 | No issues
C002 | Shopping Complex B | T894 | Steel Framework Setup | Mike Adams | Blocked | Low | 2023-07-09 | 2023-08-04 |  | 0 | Rebar | Market Street | 27522.43 | 49980.63 | Not started
C002 | Shopping Complex B | T905 | Interior Painting | Emma White | Not Started | Medium | 2023-04-09 | 2023-04-27 |  | 0 | Roofing Sheets | Market Street | 10530.46 | 0 | Not started
C002 | Shopping Complex B | T347 | Site Survey | Rachel Green | Not Started | Medium | 2024-01-11 | 2024-01-20 |  | 0 | Concrete | Market Street | 44907.91 | 0 | Not started
C002 | Shopping Complex B | T785 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-09-06 | 2024-09-23 |  | 0 | Steel Beams | Market Street | 38185.42 | 66122.24 | In progress
C002 | Shopping Complex B | T869 | Concrete Pouring | Dave Brown | In Progress | Medium | 2023-05-05 | 2023-05-31 |  | 44 | Steel Beams | Market Street | 43143.82 | 70914.51 | In progress
C001 | Residential Building A | T430 | Site Survey | Rachel Green | In Progress | High | 2023-11-02 | 2023-11-15 |  | 72 | Cement | Plot 21, Riverside | 44456.2 | 40688.01 | In progress
C003 | Office Tower C | T224 | Interior Painting | Mike Adams | Blocked | High | 2024-06-13 | 2024-07-12 |  | 0 | PVC Pipes | Downtown Avenue | 34375.11 | 32883.84 | Not started
C002 | Shopping Complex B | T916 | Steel Framework Setup | Rachel Green | Blocked | Low | 2023-10-15 | 2023-11-12 |  | 0 | PVC Pipes | Market Street | 5385.13 | 29081.66 | Not started
C003 | Office Tower C | T254 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2024-06-11 | 2024-07-09 | 2024-07-09 | 100 | Rebar | Downtown Avenue | 49344.59 | 55524.72 | No issues
C004 | Warehouse D | T333 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2024-06-25 | 2024-07-09 |  | 0 | PVC Pipes | Industrial Park | 27081.94 | 0 | Not started
C003 | Office Tower C | T165 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2024-11-09 | 2024-12-02 |  | 0 | Concrete | Downtown Avenue | 9790.65 | 8598.15 | Not started
C001 | Residential Building A | T348 | Interior Painting | Emma White | Completed | Low | 2023-01-16 | 2023-02-06 | 2023-02-06 | 100 | Cement | Plot 21, Riverside | 48017.58 | 36165.3 | No issues
C004 | Warehouse D | T945 | Plumbing Installations | Rachel Green | Blocked | High | 2024-06-17 | 2024-07-12 |  | 0 | Copper Wires | Industrial Park | 42823.44 | 26211.02 | Not started
C003 | Office Tower C | T555 | Concrete Pouring | Rachel Green | Completed | Low | 2024-03-12 | 2024-04-01 | 2024-04-01 | 100 | Copper Wires | Downtown Avenue | 22377.91 | 24088.92 | No issues
C003 | Office Tower C | T373 | Plumbing Installations | Sarah Johnson | Blocked | Low | 2023-01-04 | 2023-01-30 |  | 0 | Concrete | Downtown Avenue | 16387.63 | 11663.28 | Not started
C001 | Residential Building A | T526 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-09-09 | 2024-09-17 |  | 0 | PVC Pipes | Plot 21, Riverside | 22360.94 | 0 | Not started
C004 | Warehouse D | T786 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2024-07-02 | 2024-07-20 |  | 89 | Paint | Industrial Park | 24803.6 | 17855.71 | In progress
C003 | Office Tower C | T952 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-12-03 | 2024-12-31 |  | 0 | Paint | Downtown Avenue | 10572.83 | 10975.88 | Not started
C003 | Office Tower C | T914 | Foundation Excavation | Emma White | Completed | Low | 2023-04-06 | 2023-04-27 | 2023-04-27 | 100 | Concrete | Downtown Avenue | 40937.58 | 41893.69 | No issues
C004 | Warehouse D | T481 | Foundation Excavation | Rachel Green | Blocked | Low | 2023-07-26 | 2023-08-03 |  | 0 | Paint | Industrial Park | 35869.22 | 40232.92 | Not started
C002 | Shopping Complex B | T526 | Site Survey | Grace Allen | In Progress | Low | 2023-09-12 | 2023-10-03 |  | 61 | Concrete | Market Street | 7687.08 | 31176.19 | In progress
C001 | Residential Building A | T792 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2023-02-07 | 2023-03-05 |  | 0 | Copper Wires | Plot 21, Riverside | 19177.79 | 11746.94 | Not started
C003 | Office Tower C | T311 | Foundation Excavation | Grace Allen | In Progress | Low | 2024-12-26 | 2025-01-24 |  | 80 | Paint | Downtown Avenue | 40117.47 | 45992.74 | In progress
C004 | Warehouse D | T238 | Roofing | Sarah Johnson | In Progress | Medium | 2024-06-10 | 2024-06-30 |  | 17 | Paint | Industrial Park | 36765.07 | 41060.29 | In progress
C003 | Office Tower C | T322 | Interior Painting | Sarah Johnson | In Progress | Low | 2023-03-27 | 2023-04-17 |  | 47 | Cement | Downtown Avenue | 28391.3 | 29143.47 | In progress
C001 | Residential Building A | T530 | Interior Painting | Carlos Rivera | Completed | High | 2024-12-05 | 2024-12-27 | 2024-12-27 | 100 | Roofing Sheets | Plot 21, Riverside | 23878.3 | 15356 | No issues
C004 | Warehouse D | T643 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2024-06-22 | 2024-07-12 |  | 0 | Concrete | Industrial Park | 21253.14 | 14078.51 | Not started
C002 | Shopping Complex B | T451 | Site Survey | Mike Adams | In Progress | Low | 2023-10-11 | 2023-10-27 |  | 64 | Cement | Market Street | 25477.67 | 42646.76 | In progress
C004 | Warehouse D | T396 | Foundation Excavation | Emma White | Blocked | Low | 2024-09-25 | 2024-10-13 |  | 0 | Paint | Industrial Park | 33784.06 | 23450.63 | Not started
C002 | Shopping Complex B | T166 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2024-06-20 | 2024-06-29 |  | 0 | Roofing Sheets | Market Street | 16434.33 | 42348.11 | Not started
C003 | Office Tower C | T212 | Interior Painting | Rachel Green | In Progress | Medium | 2024-06-21 | 2024-07-08 |  | 98 | Rebar | Downtown Avenue | 21044.08 | 23166.29 | In progress
C001 | Residential Building A | T483 | Steel Framework Setup | Emma White | Blocked | Low | 2023-09-07 | 2023-09-27 |  | 0 | Rebar | Plot 21, Riverside | 33800.46 | 33977.85 | Not started
C001 | Residential Building A | T644 | Plumbing Installations | Mike Adams | Not Started | High | 2023-12-12 | 2023-12-19 |  | 0 | Roofing Sheets | Plot 21, Riverside | 48807.17 | 0 | Not started
C002 | Shopping Complex B | T118 | Electrical Wiring | Grace Allen | Completed | High | 2024-06-12 | 2024-06-25 | 2024-06-25 | 100 | Cement | Market Street | 43499.96 | 71339.18 | No issues
C001 | Residential Building A | T277 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-07-26 | 2024-08-07 |  | 67 | PVC Pipes | Plot 21, Riverside | 42116.4 | 27539.2 | In progress
C003 | Office Tower C | T634 | Foundation Excavation | Rachel Green | Completed | High | 2024-12-21 | 2024-12-31 | 2024-12-31 | 100 | PVC Pipes | Downtown Avenue | 12926.01 | 14084.63 | No issues
C003 | Office Tower C | T347 | Site Survey | Rachel Green | Blocked | High | 2023-06-03 | 2023-06-22 |  | 0 | Steel Beams | Downtown Avenue | 48879.27 | 58644.68 | Not started
C004 | Warehouse D | T646 | Steel Framework Setup | John Miller | Blocked | Low | 2024-10-04 | 2024-10-27 |  | 0 | Roofing Sheets | Industrial Park | 6752.8 | 5371.23 | Not started
C001 | Residential Building A | T759 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-06-24 | 2024-07-11 | 2024-07-11 | 100 | Copper Wires | Plot 21, Riverside | 37086.48 | 22520.69 | No issues
C004 | Warehouse D | T609 | Foundation Excavation | Sarah Johnson | Completed | Low | 2023-11-12 | 2023-12-08 | 2023-12-08 | 100 | Cement | Industrial Park | 44386.49 | 28019.04 | No issues
C002 | Shopping Complex B | T756 | Interior Painting | Sarah Johnson | Completed | High | 2023-12-16 | 2023-12-24 | 2023-12-24 | 100 | Paint | Market Street | 19650.59 | 47688.31 | No issues
C004 | Warehouse D | T786 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2024-01-08 | 2024-01-29 |  | 0 | PVC Pipes | Industrial Park | 39941.4 | 0 | Not started
C001 | Residential Building A | T570 | Concrete Pouring | Sarah Johnson | Not Started | High | 2023-03-16 | 2023-04-10 |  | 0 | Rebar | Plot 21, Riverside | 38154.59 | 0 | Not started
C001 | Residential Building A | T658 | Site Survey | Carlos Rivera | In Progress | High | 2023-01-09 | 2023-01-21 |  | 68 | Rebar | Plot 21, Riverside | 48604.32 | 54830.15 | In progress
C002 | Shopping Complex B | T656 | Interior Painting | Carlos Rivera | Completed | Medium | 2023-10-25 | 2023-11-16 | 2023-11-16 | 100 | Copper Wires | Market Street | 49978.15 | 84497.41 | No issues
C002 | Shopping Complex B | T108 | Foundation Excavation | Mike Adams | Blocked | High | 2024-07-03 | 2024-07-12 |  | 0 | Steel Beams | Market Street | 12489.44 | 33975.08 | Not started
C001 | Residential Building A | T379 | Foundation Excavation | Rachel Green | Blocked | Low | 2023-11-03 | 2023-11-14 |  | 0 | Cement | Plot 21, Riverside | 13774.67 | 13964.35 | Not started
C004 | Warehouse D | T515 | Roofing | Rachel Green | Completed | High | 2024-12-02 | 2024-12-27 | 2024-12-27 | 100 | Concrete | Industrial Park | 43692.49 | 31363.16 | No issues
C003 | Office Tower C | T321 | Site Survey | Grace Allen | Blocked | High | 2024-07-20 | 2024-08-09 |  | 0 | Roofing Sheets | Downtown Avenue | 13521.82 | 14807.96 | Not started
C004 | Warehouse D | T678 | Roofing | Grace Allen | Blocked | Low | 2024-11-01 | 2024-11-23 |  | 0 | PVC Pipes | Industrial Park | 19106.33 | 14807.53 | Not started
C002 | Shopping Complex B | T720 | Site Survey | Emma White | In Progress | High | 2024-10-17 | 2024-11-06 |  | 17 | Steel Beams | Market Street | 30213.35 | 46813.71 | In progress
C001 | Residential Building A | T736 | Foundation Excavation | Dave Brown | Completed | High | 2024-05-28 | 2024-06-06 | 2024-06-06 | 100 | Concrete | Plot 21, Riverside | 45893.63 | 38271.67 | No issues
C004 | Warehouse D | T316 | Concrete Pouring | Grace Allen | In Progress | Medium | 2024-04-07 | 2024-04-15 |  | 93 | Steel Beams | Industrial Park | 8665.04 | 5927.97 | In progress
C002 | Shopping Complex B | T146 | Roofing | Sarah Johnson | Not Started | Low | 2024-02-01 | 2024-02-14 |  | 0 | Rebar | Market Street | 33120.04 | 0 | Not started
C001 | Residential Building A | T767 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2024-06-08 | 2024-07-07 |  | 0 | Steel Beams | Plot 21, Riverside | 16505.97 | 16314.14 | Not started
C003 | Office Tower C | T878 | Roofing | Carlos Rivera | Completed | Low | 2023-11-06 | 2023-11-18 | 2023-11-18 | 100 | Paint | Downtown Avenue | 15717.7 | 13479.45 | No issues
C004 | Warehouse D | T144 | Steel Framework Setup | Grace Allen | In Progress | Low | 2023-05-17 | 2023-06-07 |  | 44 | Roofing Sheets | Industrial Park | 9832.14 | 8102 | In progress
C001 | Residential Building A | T559 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-12-04 | 2024-12-17 | 2024-12-17 | 100 | Copper Wires | Plot 21, Riverside | 13213.96 | 13226.39 | No issues
C002 | Shopping Complex B | T866 | Foundation Excavation | Rachel Green | Blocked | Medium | 2024-04-05 | 2024-04-13 |  | 0 | Steel Beams | Market Street | 47180.74 | 74411.92 | Not started
C004 | Warehouse D | T220 | Steel Framework Setup | John Miller | Not Started | High | 2023-09-15 | 2023-10-08 |  | 0 | PVC Pipes | Industrial Park | 16334.63 | 0 | Not started
C003 | Office Tower C | T610 | Concrete Pouring | Mike Adams | Not Started | Low | 2023-08-14 | 2023-09-13 |  | 0 | Roofing Sheets | Downtown Avenue | 42744.65 | 0 | Not started
C004 | Warehouse D | T376 | Site Survey | Dave Brown | In Progress | Medium | 2023-06-08 | 2023-06-29 |  | 71 | Steel Beams | Industrial Park | 46499.15 | 44558.2 | In progress
C002 | Shopping Complex B | T457 | Plumbing Installations | Dave Brown | Completed | High | 2024-05-28 | 2024-06-20 | 2024-06-20 | 100 | Concrete | Market Street | 19555.14 | 38114.99 | No issues
C003 | Office Tower C | T763 | Site Survey | Mike Adams | Not Started | High | 2024-06-18 | 2024-07-16 |  | 0 | PVC Pipes | Downtown Avenue | 12642.19 | 0 | Not started
C004 | Warehouse D | T137 | Site Survey | Rachel Green | In Progress | High | 2023-05-05 | 2023-05-27 |  | 88 | Paint | Industrial Park | 14748.47 | 11656.64 | In progress
C001 | Residential Building A | T245 | Steel Framework Setup | John Miller | Completed | Low | 2024-09-05 | 2024-09-13 | 2024-09-13 | 100 | Copper Wires | Plot 21, Riverside | 27137.93 | 18086.37 | No issues
C004 | Warehouse D | T516 | Steel Framework Setup | Emma White | In Progress | High | 2024-04-26 | 2024-05-04 |  | 45 | Roofing Sheets | Industrial Park | 28052.35 | 19436.18 | In progress
C002 | Shopping Complex B | T489 | Concrete Pouring | Emma White | Blocked | Low | 2024-02-26 | 2024-03-26 |  | 0 | Cement | Market Street | 9306.62 | 34732.44 | Not started
C004 | Warehouse D | T840 | Steel Framework Setup | Emma White | In Progress | Low | 2024-11-23 | 2024-12-17 |  | 35 | Roofing Sheets | Industrial Park | 37858.68 | 29885.6 | In progress
C003 | Office Tower C | T423 | Electrical Wiring | Emma White | Blocked | Medium | 2024-09-27 | 2024-10-26 |  | 0 | Copper Wires | Downtown Avenue | 13495.81 | 10048.51 | Not started
C002 | Shopping Complex B | T718 | Foundation Excavation | Sarah Johnson | Not Started | Medium | 2024-05-03 | 2024-05-28 |  | 0 | Copper Wires | Market Street | 18945.12 | 0 | Not started
C004 | Warehouse D | T914 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-10-20 | 2024-11-04 |  | 0 | PVC Pipes | Industrial Park | 49299.24 | 54377.45 | Not started
C004 | Warehouse D | T730 | Interior Painting | Emma White | Blocked | High | 2024-06-27 | 2024-07-18 |  | 0 | Concrete | Industrial Park | 43288.36 | 47178.42 | Not started
C002 | Shopping Complex B | T491 | Foundation Excavation | Carlos Rivera | Completed | Low | 2024-05-11 | 2024-05-21 | 2024-05-21 | 100 | Roofing Sheets | Market Street | 48165.17 | 58632.36 | No issues
C001 | Residential Building A | T603 | Foundation Excavation | Rachel Green | Blocked | Low | 2023-05-15 | 2023-06-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 5759.91 | 6609.84 | Not started
C003 | Office Tower C | T738 | Foundation Excavation | Emma White | Blocked | High | 2023-04-13 | 2023-04-24 |  | 0 | Rebar | Downtown Avenue | 22281.13 | 26083.94 | Not started
C004 | Warehouse D | T887 | Concrete Pouring | Mike Adams | Not Started | Low | 2023-05-18 | 2023-05-30 |  | 0 | Paint | Industrial Park | 26733.4 | 0 | Not started
C002 | Shopping Complex B | T572 | Electrical Wiring | Mike Adams | Not Started | Low | 2023-02-09 | 2023-02-26 |  | 0 | Roofing Sheets | Market Street | 16943.13 | 0 | Not started
C001 | Residential Building A | T435 | Electrical Wiring | Rachel Green | Completed | Medium | 2023-01-17 | 2023-02-12 | 2023-02-12 | 100 | Copper Wires | Plot 21, Riverside | 40256.71 | 46695.56 | No issues
C003 | Office Tower C | T100 | Foundation Excavation | Sarah Johnson | Not Started | Medium | 2024-05-12 | 2024-05-19 |  | 0 | Roofing Sheets | Downtown Avenue | 32793.33 | 0 | Not started
C001 | Residential Building A | T876 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2023-02-25 | 2023-03-14 |  | 96 | Copper Wires | Plot 21, Riverside | 38566.13 | 23853.62 | In progress
C003 | Office Tower C | T241 | Concrete Pouring | Dave Brown | Blocked | High | 2024-02-19 | 2024-03-13 |  | 0 | Steel Beams | Downtown Avenue | 29391.95 | 17990.13 | Not started
C001 | Residential Building A | T321 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-01-26 | 2024-02-12 |  | 0 | Cement | Plot 21, Riverside | 37362.18 | 32005.6 | Not started
C002 | Shopping Complex B | T492 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2024-06-28 | 2024-07-17 |  | 0 | Concrete | Market Street | 36032.59 | 0 | Not started
C004 | Warehouse D | T346 | Site Survey | Sarah Johnson | Completed | Medium | 2024-02-14 | 2024-03-08 | 2024-03-08 | 100 | Steel Beams | Industrial Park | 13832.93 | 9032.98 | No issues
C003 | Office Tower C | T331 | Plumbing Installations | Rachel Green | Blocked | Low | 2024-08-04 | 2024-08-19 |  | 0 | PVC Pipes | Downtown Avenue | 46812.9 | 42295.18 | Not started
C001 | Residential Building A | T839 | Interior Painting | Sarah Johnson | Blocked | High | 2024-01-05 | 2024-01-28 |  | 0 | Roofing Sheets | Plot 21, Riverside | 45863.22 | 37022.56 | Not started
C004 | Warehouse D | T582 | Roofing | Sarah Johnson | Completed | High | 2024-05-19 | 2024-06-07 | 2024-06-07 | 100 | Roofing Sheets | Industrial Park | 29556.47 | 23333.1 | No issues
C003 | Office Tower C | T108 | Plumbing Installations | Sarah Johnson | Not Started | High | 2024-09-06 | 2024-10-02 |  | 0 | Steel Beams | Downtown Avenue | 43121.17 | 0 | Not started
C001 | Residential Building A | T492 | Concrete Pouring | Mike Adams | Completed | High | 2024-08-08 | 2024-08-30 | 2024-08-30 | 100 | Rebar | Plot 21, Riverside | 44264.43 | 35801.2 | No issues
C002 | Shopping Complex B | T493 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2023-03-12 | 2023-04-09 |  | 0 | Concrete | Market Street | 7357.68 | 31150.24 | Not started
C001 | Residential Building A | T287 | Plumbing Installations | John Miller | In Progress | Medium | 2024-11-01 | 2024-11-20 |  | 75 | Rebar | Plot 21, Riverside | 38095.49 | 38859.25 | In progress
C001 | Residential Building A | T957 | Interior Painting | Carlos Rivera | In Progress | Low | 2024-10-04 | 2024-11-01 |  | 49 | Roofing Sheets | Plot 21, Riverside | 28758.48 | 33639.18 | In progress
C002 | Shopping Complex B | T286 | Roofing | Dave Brown | In Progress | Low | 2024-09-25 | 2024-10-17 |  | 27 | PVC Pipes | Market Street | 36680.9 | 60735.69 | In progress
C001 | Residential Building A | T111 | Foundation Excavation | Emma White | Not Started | Low | 2023-02-27 | 2023-03-09 |  | 0 | Concrete | Plot 21, Riverside | 6425.75 | 0 | Not started
C002 | Shopping Complex B | T117 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2024-01-01 | 2024-01-25 |  | 51 | Cement | Market Street | 37379.15 | 60014.69 | In progress
C001 | Residential Building A | T860 | Interior Painting | Sarah Johnson | Completed | High | 2024-06-17 | 2024-06-27 | 2024-06-27 | 100 | Roofing Sheets | Plot 21, Riverside | 13110.93 | 12703.45 | No issues
C002 | Shopping Complex B | T789 | Plumbing Installations | Grace Allen | Not Started | Low | 2024-04-10 | 2024-05-04 |  | 0 | Rebar | Market Street | 30723.08 | 0 | Not started
C004 | Warehouse D | T542 | Electrical Wiring | Grace Allen | In Progress | High | 2024-07-13 | 2024-08-03 |  | 96 | PVC Pipes | Industrial Park | 21322.32 | 22351.39 | In progress
C002 | Shopping Complex B | T386 | Roofing | Mike Adams | In Progress | Medium | 2024-06-18 | 2024-07-10 |  | 50 | PVC Pipes | Market Street | 49809.6 | 58023.2 | In progress
C001 | Residential Building A | T368 | Plumbing Installations | John Miller | Completed | Medium | 2024-02-10 | 2024-02-27 | 2024-02-27 | 100 | Roofing Sheets | Plot 21, Riverside | 18385.2 | 17395.97 | No issues
C003 | Office Tower C | T582 | Roofing | Carlos Rivera | In Progress | Low | 2023-12-02 | 2023-12-11 |  | 92 | Steel Beams | Downtown Avenue | 13366.04 | 9971.98 | In progress
C001 | Residential Building A | T543 | Concrete Pouring | Dave Brown | Completed | Low | 2023-07-09 | 2023-07-21 | 2023-07-21 | 100 | Steel Beams | Plot 21, Riverside | 12212.26 | 12832.93 | No issues
C003 | Office Tower C | T164 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2024-01-14 | 2024-01-29 |  | 89 | Steel Beams | Downtown Avenue | 49342.7 | 49653.53 | In progress
C002 | Shopping Complex B | T171 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2023-08-06 | 2023-08-21 |  | 52 | Concrete | Market Street | 42686.3 | 57489.81 | In progress
C002 | Shopping Complex B | T497 | Site Survey | Rachel Green | Completed | Low | 2024-10-02 | 2024-10-31 | 2024-10-31 | 100 | Rebar | Market Street | 18312.04 | 42268.45 | No issues
C001 | Residential Building A | T327 | Concrete Pouring | Dave Brown | Not Started | High | 2023-04-24 | 2023-05-13 |  | 0 | Paint | Plot 21, Riverside | 6718.81 | 0 | Not started
C004 | Warehouse D | T690 | Roofing | Sarah Johnson | In Progress | Medium | 2023-04-20 | 2023-05-12 |  | 89 | Cement | Industrial Park | 34830.7 | 39386.43 | In progress
C002 | Shopping Complex B | T182 | Roofing | John Miller | In Progress | Medium | 2023-01-03 | 2023-01-28 |  | 87 | Concrete | Market Street | 5951.17 | 30128.46 | In progress
C003 | Office Tower C | T688 | Steel Framework Setup | John Miller | Completed | High | 2024-10-18 | 2024-10-29 | 2024-10-29 | 100 | Roofing Sheets | Downtown Avenue | 26919.55 | 19103.44 | No issues
C003 | Office Tower C | T895 | Concrete Pouring | Mike Adams | Completed | High | 2024-12-24 | 2025-01-05 | 2025-01-05 | 100 | Paint | Downtown Avenue | 8654.54 | 7577.96 | No issues
C003 | Office Tower C | T601 | Steel Framework Setup | Grace Allen | Not Started | High | 2023-02-07 | 2023-03-03 |  | 0 | Roofing Sheets | Downtown Avenue | 15137.02 | 0 | Not started
C004 | Warehouse D | T663 | Steel Framework Setup | Rachel Green | In Progress | Low | 2023-12-09 | 2023-12-23 |  | 90 | PVC Pipes | Industrial Park | 14498.3 | 17080.26 | In progress
C004 | Warehouse D | T330 | Electrical Wiring | Dave Brown | Blocked | High | 2024-08-09 | 2024-09-06 |  | 0 | Copper Wires | Industrial Park | 22468.34 | 13877.46 | Not started
C004 | Warehouse D | T857 | Electrical Wiring | John Miller | Blocked | Low | 2023-02-14 | 2023-03-02 |  | 0 | PVC Pipes | Industrial Park | 5218.53 | 4784.28 | Not started
C003 | Office Tower C | T749 | Plumbing Installations | Emma White | Not Started | Medium | 2023-06-17 | 2023-06-28 |  | 0 | Concrete | Downtown Avenue | 26183.77 | 0 | Not started
C002 | Shopping Complex B | T849 | Plumbing Installations | Dave Brown | Blocked | High | 2024-01-26 | 2024-02-06 |  | 0 | Roofing Sheets | Market Street | 35164.29 | 48473.28 | Not started
C003 | Office Tower C | T416 | Electrical Wiring | Dave Brown | In Progress | Low | 2024-02-03 | 2024-02-28 |  | 3 | PVC Pipes | Downtown Avenue | 40758.7 | 31904.26 | In progress
C004 | Warehouse D | T756 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2024-07-26 | 2024-08-08 |  | 75 | Paint | Industrial Park | 7006.16 | 4396.09 | In progress
C001 | Residential Building A | T599 | Interior Painting | Grace Allen | Blocked | Low | 2023-11-07 | 2023-12-05 |  | 0 | Roofing Sheets | Plot 21, Riverside | 32512.95 | 20183.61 | Not started
C004 | Warehouse D | T417 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-03-19 | 2024-04-07 |  | 32 | Paint | Industrial Park | 8009.64 | 4926.59 | In progress
C003 | Office Tower C | T796 | Concrete Pouring | Grace Allen | Not Started | Low | 2023-04-28 | 2023-05-19 |  | 0 | Steel Beams | Downtown Avenue | 49173.77 | 0 | Not started
C001 | Residential Building A | T490 | Roofing | Mike Adams | In Progress | Medium | 2023-03-22 | 2023-04-18 |  | 93 | PVC Pipes | Plot 21, Riverside | 15684.89 | 12374.12 | In progress
C003 | Office Tower C | T140 | Plumbing Installations | Carlos Rivera | Not Started | High | 2024-04-16 | 2024-04-23 |  | 0 | Paint | Downtown Avenue | 26211.5 | 0 | Not started
C004 | Warehouse D | T585 | Concrete Pouring | Mike Adams | Blocked | Medium | 2024-12-14 | 2025-01-09 |  | 0 | Rebar | Industrial Park | 31581.72 | 25030.65 | Not started
C004 | Warehouse D | T974 | Electrical Wiring | Grace Allen | Not Started | Low | 2023-08-03 | 2023-08-30 |  | 0 | Concrete | Industrial Park | 49994.46 | 0 | Not started
C003 | Office Tower C | T642 | Concrete Pouring | Grace Allen | In Progress | High | 2024-03-26 | 2024-04-21 |  | 99 | Roofing Sheets | Downtown Avenue | 44945.26 | 50515.69 | In progress
C002 | Shopping Complex B | T793 | Concrete Pouring | Carlos Rivera | Completed | Low | 2023-06-17 | 2023-07-14 | 2023-07-14 | 100 | Rebar | Market Street | 35964.4 | 56122.64 | No issues
C002 | Shopping Complex B | T494 | Plumbing Installations | Dave Brown | Not Started | High | 2023-07-05 | 2023-07-20 |  | 0 | Cement | Market Street | 36117.15 | 0 | Not started
C001 | Residential Building A | T916 | Roofing | Grace Allen | Not Started | High | 2023-01-11 | 2023-01-26 |  | 0 | Paint | Plot 21, Riverside | 47722.99 | 0 | Not started
C004 | Warehouse D | T372 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-04-02 | 2023-05-02 |  | 0 | Rebar | Industrial Park | 44749.55 | 0 | Not started
C002 | Shopping Complex B | T292 | Roofing | Sarah Johnson | In Progress | High | 2024-07-08 | 2024-08-01 |  | 58 | Copper Wires | Market Street | 9712.75 | 36710.17 | In progress
C004 | Warehouse D | T605 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2024-11-25 | 2024-12-07 |  | 38 | Copper Wires | Industrial Park | 18079.99 | 11806.18 | In progress
C001 | Residential Building A | T194 | Roofing | Carlos Rivera | Not Started | High | 2023-06-23 | 2023-07-07 |  | 0 | Paint | Plot 21, Riverside | 22593.12 | 0 | Not started
C001 | Residential Building A | T858 | Site Survey | Grace Allen | Completed | Medium | 2023-11-19 | 2023-12-16 | 2023-12-16 | 100 | Steel Beams | Plot 21, Riverside | 49500.39 | 56592.22 | No issues
C001 | Residential Building A | T886 | Electrical Wiring | Mike Adams | Completed | High | 2024-06-18 | 2024-07-13 | 2024-07-13 | 100 | Cement | Plot 21, Riverside | 24302.34 | 26461.97 | No issues
C004 | Warehouse D | T672 | Interior Painting | Grace Allen | Completed | Low | 2024-11-12 | 2024-11-28 | 2024-11-28 | 100 | Concrete | Industrial Park | 31542.81 | 25193.27 | No issues
C001 | Residential Building A | T298 | Roofing | Sarah Johnson | Not Started | Medium | 2023-02-20 | 2023-03-15 |  | 0 | Roofing Sheets | Plot 21, Riverside | 13580.58 | 0 | Not started
C003 | Office Tower C | T203 | Interior Painting | Carlos Rivera | Completed | High | 2023-01-25 | 2023-02-15 | 2023-02-15 | 100 | Concrete | Downtown Avenue | 13475.05 | 13830.51 | No issues
C003 | Office Tower C | T732 | Steel Framework Setup | Dave Brown | Blocked | Low | 2024-01-04 | 2024-01-24 |  | 0 | Steel Beams | Downtown Avenue | 17904.09 | 19271.32 | Not started
C001 | Residential Building A | T856 | Steel Framework Setup | Carlos Rivera | Completed | High | 2024-02-08 | 2024-03-01 | 2024-03-01 | 100 | Steel Beams | Plot 21, Riverside | 11333.83 | 11287.37 | No issues
C004 | Warehouse D | T748 | Interior Painting | Emma White | Not Started | High | 2023-08-18 | 2023-09-05 |  | 0 | Rebar | Industrial Park | 13654.35 | 0 | Not started
C003 | Office Tower C | T277 | Electrical Wiring | John Miller | Completed | Medium | 2024-01-11 | 2024-02-02 | 2024-02-02 | 100 | Paint | Downtown Avenue | 16181.18 | 16569.27 | No issues
C003 | Office Tower C | T666 | Foundation Excavation | Mike Adams | Blocked | High | 2024-12-26 | 2025-01-10 |  | 0 | Roofing Sheets | Downtown Avenue | 39460.26 | 23750.24 | Not started
C001 | Residential Building A | T231 | Interior Painting | Mike Adams | In Progress | Medium | 2024-03-20 | 2024-04-06 |  | 75 | Copper Wires | Plot 21, Riverside | 35651.96 | 37695.33 | In progress
C003 | Office Tower C | T961 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-01-22 | 2023-02-12 |  | 0 | Rebar | Downtown Avenue | 39658.12 | 0 | Not started
C002 | Shopping Complex B | T471 | Roofing | Mike Adams | Blocked | High | 2024-12-23 | 2024-12-31 |  | 0 | Steel Beams | Market Street | 9811.21 | 33890.42 | Not started
C001 | Residential Building A | T959 | Steel Framework Setup | Dave Brown | Not Started | High | 2024-03-04 | 2024-03-27 |  | 0 | PVC Pipes | Plot 21, Riverside | 38718.63 | 0 | Not started
C002 | Shopping Complex B | T525 | Foundation Excavation | Rachel Green | Not Started | High | 2023-10-12 | 2023-10-21 |  | 0 | Concrete | Market Street | 48835.1 | 0 | Not started
C003 | Office Tower C | T745 | Roofing | Grace Allen | Blocked | Low | 2023-01-09 | 2023-01-24 |  | 0 | Roofing Sheets | Downtown Avenue | 8725.88 | 5927.2 | Not started
C002 | Shopping Complex B | T362 | Interior Painting | John Miller | Blocked | Low | 2024-02-13 | 2024-02-24 |  | 0 | Concrete | Market Street | 38430.15 | 51178.2 | Not started
C003 | Office Tower C | T726 | Electrical Wiring | Carlos Rivera | In Progress | Medium | 2023-03-16 | 2023-04-03 |  | 26 | Copper Wires | Downtown Avenue | 42157.33 | 44705.97 | In progress
C001 | Residential Building A | T131 | Electrical Wiring | Mike Adams | Completed | High | 2023-04-23 | 2023-05-14 | 2023-05-14 | 100 | Rebar | Plot 21, Riverside | 8460.61 | 5675.71 | No issues
C002 | Shopping Complex B | T568 | Steel Framework Setup | Emma White | Blocked | Low | 2024-01-11 | 2024-01-22 |  | 0 | Steel Beams | Market Street | 16128.5 | 41018.11 | Not started
C001 | Residential Building A | T417 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2024-09-05 | 2024-09-26 |  | 58 | Concrete | Plot 21, Riverside | 46684.27 | 31723.44 | In progress
C002 | Shopping Complex B | T589 | Electrical Wiring | John Miller | Not Started | Medium | 2024-06-27 | 2024-07-11 |  | 0 | Cement | Market Street | 46674.59 | 0 | Not started
C003 | Office Tower C | T694 | Concrete Pouring | Rachel Green | Blocked | High | 2024-12-28 | 2025-01-18 |  | 0 | Cement | Downtown Avenue | 39669.44 | 34133.79 | Not started
C004 | Warehouse D | T190 | Plumbing Installations | Carlos Rivera | Blocked | High | 2024-02-25 | 2024-03-15 |  | 0 | PVC Pipes | Industrial Park | 38605.93 | 45998.97 | Not started
C001 | Residential Building A | T315 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-02-15 | 2023-03-01 |  | 0 | PVC Pipes | Plot 21, Riverside | 33963.17 | 0 | Not started
C003 | Office Tower C | T297 | Foundation Excavation | John Miller | Not Started | Medium | 2024-06-27 | 2024-07-21 |  | 0 | Copper Wires | Downtown Avenue | 37700.05 | 0 | Not started
C001 | Residential Building A | T386 | Site Survey | Rachel Green | Not Started | High | 2024-04-02 | 2024-04-16 |  | 0 | PVC Pipes | Plot 21, Riverside | 40137.37 | 0 | Not started
C001 | Residential Building A | T199 | Concrete Pouring | Rachel Green | Completed | Low | 2024-12-17 | 2024-12-30 | 2024-12-30 | 100 | Steel Beams | Plot 21, Riverside | 24647.78 | 18494.34 | No issues
C004 | Warehouse D | T304 | Electrical Wiring | Rachel Green | Not Started | Low | 2024-01-21 | 2024-01-29 |  | 0 | Roofing Sheets | Industrial Park | 46206.42 | 0 | Not started
C003 | Office Tower C | T916 | Interior Painting | Sarah Johnson | Not Started | Low | 2024-10-28 | 2024-11-06 |  | 0 | Steel Beams | Downtown Avenue | 43426.5 | 0 | Not started
C002 | Shopping Complex B | T748 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-10-04 | 2023-10-29 |  | 0 | Cement | Market Street | 33710.16 | 0 | Not started
C001 | Residential Building A | T206 | Plumbing Installations | Dave Brown | Completed | Medium | 2024-07-07 | 2024-08-03 | 2024-08-03 | 100 | Steel Beams | Plot 21, Riverside | 40970.68 | 30134.64 | No issues
C002 | Shopping Complex B | T726 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-12-08 | 2023-12-17 |  | 0 | Steel Beams | Market Street | 5251.89 | 31215.8 | Not started
C002 | Shopping Complex B | T227 | Steel Framework Setup | Mike Adams | Completed | Low | 2024-07-11 | 2024-07-25 | 2024-07-25 | 100 | PVC Pipes | Market Street | 7978.92 | 30602.27 | No issues
C002 | Shopping Complex B | T115 | Plumbing Installations | Dave Brown | Not Started | Low | 2023-01-04 | 2023-01-23 |  | 0 | Steel Beams | Market Street | 40863.8 | 0 | Not started
C002 | Shopping Complex B | T696 | Roofing | Mike Adams | Not Started | Medium | 2024-02-03 | 2024-02-21 |  | 0 | Copper Wires | Market Street | 46055.16 | 0 | Not started
C002 | Shopping Complex B | T188 | Roofing | Sarah Johnson | In Progress | Low | 2024-12-07 | 2024-12-14 |  | 71 | Rebar | Market Street | 36898.63 | 62997.8 | In progress
C003 | Office Tower C | T375 | Concrete Pouring | Dave Brown | Blocked | High | 2023-12-26 | 2024-01-22 |  | 0 | Concrete | Downtown Avenue | 30043.53 | 23777.77 | Not started
C002 | Shopping Complex B | T839 | Roofing | John Miller | In Progress | Low | 2024-05-20 | 2024-06-04 |  | 46 | Paint | Market Street | 49397.88 | 64024.1 | In progress
C002 | Shopping Complex B | T567 | Foundation Excavation | Emma White | In Progress | Low | 2023-01-25 | 2023-02-14 |  | 37 | PVC Pipes | Market Street | 17320.74 | 43941.31 | In progress
C001 | Residential Building A | T487 | Roofing | Mike Adams | Blocked | Low | 2023-11-21 | 2023-12-02 |  | 0 | Cement | Plot 21, Riverside | 5290.79 | 3967.05 | Not started
C001 | Residential Building A | T778 | Foundation Excavation | Emma White | Blocked | High | 2024-06-04 | 2024-06-12 |  | 0 | Rebar | Plot 21, Riverside | 44501.96 | 34418.98 | Not started
C004 | Warehouse D | T362 | Interior Painting | Grace Allen | In Progress | Low | 2023-06-22 | 2023-07-13 |  | 83 | Rebar | Industrial Park | 41407.55 | 45541.11 | In progress
C004 | Warehouse D | T944 | Interior Painting | Sarah Johnson | Blocked | High | 2024-10-21 | 2024-11-08 |  | 0 | Steel Beams | Industrial Park | 5019.11 | 5981.85 | Not started
C004 | Warehouse D | T806 | Foundation Excavation | Rachel Green | Completed | Low | 2024-07-19 | 2024-08-15 | 2024-08-15 | 100 | Cement | Industrial Park | 19418.7 | 19876.8 | No issues
C003 | Office Tower C | T785 | Plumbing Installations | Emma White | In Progress | Low | 2024-04-15 | 2024-05-10 |  | 49 | Paint | Downtown Avenue | 17457.23 | 11837.51 | In progress
C001 | Residential Building A | T371 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2024-10-02 | 2024-11-01 |  | 97 | Steel Beams | Plot 21, Riverside | 6167.54 | 7105.19 | In progress
C003 | Office Tower C | T765 | Site Survey | Emma White | Completed | Medium | 2024-08-15 | 2024-09-07 | 2024-09-07 | 100 | Paint | Downtown Avenue | 31366.76 | 32558.57 | No issues
C003 | Office Tower C | T300 | Foundation Excavation | Emma White | Blocked | Low | 2023-10-12 | 2023-10-22 |  | 0 | Roofing Sheets | Downtown Avenue | 49402.97 | 48574.28 | Not started
C003 | Office Tower C | T122 | Electrical Wiring | Dave Brown | In Progress | Medium | 2024-11-03 | 2024-11-14 |  | 30 | Cement | Downtown Avenue | 14177.88 | 9593.71 | In progress
C001 | Residential Building A | T957 | Roofing | Grace Allen | Not Started | Low | 2024-07-17 | 2024-07-30 |  | 0 | Cement | Plot 21, Riverside | 24595.9 | 0 | Not started
C002 | Shopping Complex B | T760 | Foundation Excavation | Emma White | Blocked | High | 2023-05-11 | 2023-05-30 |  | 0 | PVC Pipes | Market Street | 37876.39 | 57814.12 | Not started
C004 | Warehouse D | T199 | Concrete Pouring | Grace Allen | Completed | High | 2024-11-14 | 2024-12-02 | 2024-12-02 | 100 | PVC Pipes | Industrial Park | 39507.24 | 23976.67 | No issues
C003 | Office Tower C | T349 | Electrical Wiring | Sarah Johnson | Blocked | High | 2023-08-12 | 2023-09-02 |  | 0 | Paint | Downtown Avenue | 34222.14 | 21481.42 | Not started
C004 | Warehouse D | T837 | Roofing | John Miller | In Progress | High | 2024-06-06 | 2024-07-02 |  | 96 | Copper Wires | Industrial Park | 5673.76 | 5229.09 | In progress
C002 | Shopping Complex B | T322 | Steel Framework Setup | Mike Adams | In Progress | Low | 2023-02-10 | 2023-02-25 |  | 67 | Concrete | Market Street | 22828.64 | 44948.38 | In progress
C001 | Residential Building A | T423 | Electrical Wiring | Carlos Rivera | Blocked | Low | 2024-04-03 | 2024-05-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 35111.89 | 29981.53 | Not started
C002 | Shopping Complex B | T573 | Site Survey | Grace Allen | Blocked | High | 2023-04-26 | 2023-05-20 |  | 0 | Roofing Sheets | Market Street | 15071.46 | 35302.92 | Not started
C002 | Shopping Complex B | T229 | Foundation Excavation | Emma White | In Progress | High | 2024-11-11 | 2024-11-30 |  | 38 | Rebar | Market Street | 36620.68 | 61344.63 | In progress
C003 | Office Tower C | T378 | Steel Framework Setup | John Miller | In Progress | Medium | 2023-11-20 | 2023-12-11 |  | 70 | Concrete | Downtown Avenue | 37520.35 | 24401.38 | In progress
C001 | Residential Building A | T807 | Foundation Excavation | Grace Allen | Blocked | Medium | 2023-09-02 | 2023-09-17 |  | 0 | Steel Beams | Plot 21, Riverside | 23300.55 | 18491.89 | Not started
C003 | Office Tower C | T948 | Foundation Excavation | Rachel Green | Blocked | High | 2023-05-25 | 2023-06-09 |  | 0 | Concrete | Downtown Avenue | 34807.47 | 26503.8 | Not started
C001 | Residential Building A | T988 | Electrical Wiring | Emma White | Completed | High | 2024-06-19 | 2024-07-14 | 2024-07-14 | 100 | Rebar | Plot 21, Riverside | 12540.04 | 12075.49 | No issues
C004 | Warehouse D | T809 | Site Survey | Carlos Rivera | Not Started | Low | 2024-01-04 | 2024-01-19 |  | 0 | Steel Beams | Industrial Park | 23901.02 | 0 | Not started
C002 | Shopping Complex B | T124 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2023-11-08 | 2023-11-20 |  | 74 | Copper Wires | Market Street | 11913.03 | 37843.37 | In progress
C002 | Shopping Complex B | T678 | Concrete Pouring | Dave Brown | Blocked | Medium | 2023-03-28 | 2023-04-07 |  | 0 | PVC Pipes | Market Street | 9090.34 | 32698.03 | Not started
C001 | Residential Building A | T123 | Concrete Pouring | Emma White | Not Started | Medium | 2024-11-01 | 2024-11-29 |  | 0 | PVC Pipes | Plot 21, Riverside | 42600.28 | 0 | Not started
C001 | Residential Building A | T533 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2023-08-19 | 2023-09-07 |  | 0 | Copper Wires | Plot 21, Riverside | 22414.83 | 15082.82 | Not started
C001 | Residential Building A | T397 | Foundation Excavation | Rachel Green | Not Started | Medium | 2023-06-20 | 2023-07-05 |  | 0 | Concrete | Plot 21, Riverside | 17411.52 | 0 | Not started
C001 | Residential Building A | T396 | Concrete Pouring | Rachel Green | In Progress | High | 2023-05-05 | 2023-05-25 |  | 91 | PVC Pipes | Plot 21, Riverside | 8431.71 | 5340.14 | In progress
C002 | Shopping Complex B | T430 | Interior Painting | Emma White | Completed | High | 2023-03-19 | 2023-04-04 | 2023-04-04 | 100 | PVC Pipes | Market Street | 36821.01 | 64454.15 | No issues
C003 | Office Tower C | T132 | Plumbing Installations | Emma White | Completed | Medium | 2023-05-25 | 2023-06-09 | 2023-06-09 | 100 | Paint | Downtown Avenue | 8912.84 | 6243.69 | No issues
C002 | Shopping Complex B | T884 | Roofing | Mike Adams | In Progress | High | 2023-04-26 | 2023-05-22 |  | 86 | Paint | Market Street | 27467.37 | 43699.01 | In progress
C004 | Warehouse D | T137 | Roofing | Emma White | Not Started | Low | 2024-04-07 | 2024-04-27 |  | 0 | Cement | Industrial Park | 9414.61 | 0 | Not started
C001 | Residential Building A | T271 | Interior Painting | Rachel Green | Not Started | Low | 2023-01-04 | 2023-01-27 |  | 0 | Copper Wires | Plot 21, Riverside | 16348.6 | 0 | Not started
C004 | Warehouse D | T616 | Foundation Excavation | John Miller | Not Started | High | 2023-06-26 | 2023-07-14 |  | 0 | Cement | Industrial Park | 8283.09 | 0 | Not started
C004 | Warehouse D | T735 | Plumbing Installations | Emma White | In Progress | Low | 2024-06-06 | 2024-06-25 |  | 8 | Cement | Industrial Park | 33662.36 | 24016.24 | In progress
C002 | Shopping Complex B | T560 | Steel Framework Setup | John Miller | Blocked | High | 2023-01-09 | 2023-02-01 |  | 0 | Copper Wires | Market Street | 46194.48 | 71948.97 | Not started
C003 | Office Tower C | T247 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-03-11 | 2023-03-31 |  | 11 | Roofing Sheets | Downtown Avenue | 49262.86 | 38410.45 | In progress
C004 | Warehouse D | T718 | Foundation Excavation | Dave Brown | In Progress | High | 2024-05-08 | 2024-05-20 |  | 53 | Concrete | Industrial Park | 10719.91 | 8892.09 | In progress
C004 | Warehouse D | T896 | Concrete Pouring | Grace Allen | In Progress | High | 2023-01-03 | 2023-01-22 |  | 62 | Paint | Industrial Park | 11009.16 | 10050.26 | In progress
C001 | Residential Building A | T298 | Roofing | Dave Brown | Completed | High | 2024-08-05 | 2024-08-12 | 2024-08-12 | 100 | Copper Wires | Plot 21, Riverside | 32203.65 | 35998.52 | No issues
C002 | Shopping Complex B | T417 | Roofing | Mike Adams | Blocked | Medium | 2024-08-13 | 2024-09-12 |  | 0 | Roofing Sheets | Market Street | 27373.67 | 53784.31 | Not started
C004 | Warehouse D | T468 | Site Survey | John Miller | Not Started | Medium | 2023-12-19 | 2023-12-29 |  | 0 | Roofing Sheets | Industrial Park | 36083.8 | 0 | Not started
C001 | Residential Building A | T650 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-01-02 | 2024-01-29 |  | 0 | Paint | Plot 21, Riverside | 26911.38 | 30254.35 | Not started
C003 | Office Tower C | T701 | Interior Painting | Mike Adams | Completed | High | 2023-07-17 | 2023-07-31 | 2023-07-31 | 100 | Copper Wires | Downtown Avenue | 17007.93 | 11039.31 | No issues
C003 | Office Tower C | T889 | Site Survey | Carlos Rivera | Blocked | High | 2023-03-07 | 2023-03-31 |  | 0 | Rebar | Downtown Avenue | 25328.17 | 19236.6 | Not started
C002 | Shopping Complex B | T139 | Roofing | Grace Allen | In Progress | Low | 2024-08-22 | 2024-09-19 |  | 27 | Concrete | Market Street | 21102.54 | 46629.67 | In progress
C004 | Warehouse D | T327 | Electrical Wiring | Rachel Green | In Progress | Low | 2023-03-13 | 2023-04-02 |  | 77 | Cement | Industrial Park | 16981.17 | 16931.25 | In progress
C002 | Shopping Complex B | T785 | Concrete Pouring | Emma White | In Progress | Low | 2023-06-05 | 2023-06-21 |  | 60 | Paint | Market Street | 32267.36 | 56298.06 | In progress
C002 | Shopping Complex B | T758 | Electrical Wiring | Grace Allen | Not Started | Low | 2024-12-21 | 2025-01-11 |  | 0 | PVC Pipes | Market Street | 31042.76 | 0 | Not started
C003 | Office Tower C | T868 | Foundation Excavation | Emma White | Not Started | Medium | 2024-11-01 | 2024-11-25 |  | 0 | Cement | Downtown Avenue | 46915.88 | 0 | Not started
C003 | Office Tower C | T701 | Electrical Wiring | Emma White | Completed | Low | 2023-07-08 | 2023-07-31 | 2023-07-31 | 100 | Cement | Downtown Avenue | 39159.51 | 45412.22 | No issues
C003 | Office Tower C | T187 | Electrical Wiring | Grace Allen | Completed | Low | 2023-01-10 | 2023-01-18 | 2023-01-18 | 100 | PVC Pipes | Downtown Avenue | 47984.42 | 55647.36 | No issues
C003 | Office Tower C | T246 | Electrical Wiring | Emma White | Not Started | Medium | 2024-11-13 | 2024-12-09 |  | 0 | Rebar | Downtown Avenue | 11383.44 | 0 | Not started
C003 | Office Tower C | T956 | Interior Painting | Grace Allen | Not Started | Low | 2023-01-15 | 2023-01-27 |  | 0 | Roofing Sheets | Downtown Avenue | 25831.33 | 0 | Not started
C001 | Residential Building A | T419 | Plumbing Installations | Rachel Green | In Progress | High | 2024-03-10 | 2024-03-18 |  | 43 | Rebar | Plot 21, Riverside | 31267.21 | 25870.69 | In progress
C003 | Office Tower C | T422 | Roofing | Carlos Rivera | Not Started | Low | 2024-10-17 | 2024-11-03 |  | 0 | Copper Wires | Downtown Avenue | 33037.82 | 0 | Not started
C002 | Shopping Complex B | T283 | Roofing | Mike Adams | In Progress | High | 2023-07-16 | 2023-07-26 |  | 88 | Rebar | Market Street | 21210.07 | 50765.12 | In progress
C003 | Office Tower C | T375 | Concrete Pouring | John Miller | In Progress | Low | 2024-05-25 | 2024-06-04 |  | 61 | PVC Pipes | Downtown Avenue | 33698.66 | 39188.13 | In progress
C002 | Shopping Complex B | T430 | Concrete Pouring | John Miller | Completed | Medium | 2024-12-19 | 2025-01-06 | 2025-01-06 | 100 | Concrete | Market Street | 11503.88 | 39186.2 | No issues
C002 | Shopping Complex B | T156 | Steel Framework Setup | Mike Adams | Not Started | High | 2024-04-01 | 2024-04-21 |  | 0 | PVC Pipes | Market Street | 29336.76 | 0 | Not started
C004 | Warehouse D | T999 | Concrete Pouring | Dave Brown | Blocked | Low | 2024-02-16 | 2024-02-24 |  | 0 | Copper Wires | Industrial Park | 16047.79 | 15697.07 | Not started
C003 | Office Tower C | T844 | Site Survey | Mike Adams | In Progress | Medium | 2024-03-19 | 2024-03-27 |  | 89 | Cement | Downtown Avenue | 29340.87 | 18931.4 | In progress
C004 | Warehouse D | T827 | Electrical Wiring | Dave Brown | Not Started | Low | 2024-03-04 | 2024-03-31 |  | 0 | Copper Wires | Industrial Park | 14682.08 | 0 | Not started
C001 | Residential Building A | T155 | Foundation Excavation | John Miller | Not Started | Medium | 2023-08-05 | 2023-08-19 |  | 0 | Concrete | Plot 21, Riverside | 34980.13 | 0 | Not started
C003 | Office Tower C | T878 | Roofing | Mike Adams | Not Started | High | 2023-01-11 | 2023-01-24 |  | 0 | Concrete | Downtown Avenue | 45049.82 | 0 | Not started
C001 | Residential Building A | T619 | Plumbing Installations | Rachel Green | In Progress | Medium | 2023-01-28 | 2023-02-27 |  | 76 | Roofing Sheets | Plot 21, Riverside | 49351.02 | 42299.48 | In progress
C004 | Warehouse D | T315 | Foundation Excavation | John Miller | Completed | High | 2024-11-28 | 2024-12-12 | 2024-12-12 | 100 | Concrete | Industrial Park | 40658.87 | 25417.46 | No issues
C003 | Office Tower C | T808 | Concrete Pouring | Emma White | In Progress | Medium | 2024-09-07 | 2024-09-24 |  | 7 | Concrete | Downtown Avenue | 18103.04 | 17389.5 | In progress
C001 | Residential Building A | T440 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-09-22 | 2023-10-21 |  | 75 | Steel Beams | Plot 21, Riverside | 18292.75 | 11504.26 | In progress
C001 | Residential Building A | T894 | Steel Framework Setup | Mike Adams | Not Started | High | 2024-09-04 | 2024-09-18 |  | 0 | Rebar | Plot 21, Riverside | 49516.72 | 0 | Not started
C001 | Residential Building A | T769 | Site Survey | Grace Allen | Blocked | High | 2024-01-24 | 2024-02-08 |  | 0 | Concrete | Plot 21, Riverside | 8273.43 | 5497.89 | Not started
C002 | Shopping Complex B | T140 | Foundation Excavation | Dave Brown | In Progress | Medium | 2023-03-27 | 2023-04-20 |  | 3 | Rebar | Market Street | 39493.68 | 56322.17 | In progress
C004 | Warehouse D | T108 | Electrical Wiring | Carlos Rivera | Not Started | High | 2024-01-10 | 2024-01-31 |  | 0 | Cement | Industrial Park | 49476.34 | 0 | Not started
C001 | Residential Building A | T268 | Electrical Wiring | Mike Adams | Completed | Low | 2024-01-19 | 2024-01-29 | 2024-01-29 | 100 | Copper Wires | Plot 21, Riverside | 11138.94 | 11937.72 | No issues
C004 | Warehouse D | T794 | Electrical Wiring | Rachel Green | Blocked | Low | 2023-12-15 | 2023-12-28 |  | 0 | Cement | Industrial Park | 14151.03 | 14464.55 | Not started
C004 | Warehouse D | T581 | Site Survey | Emma White | In Progress | Low | 2023-11-19 | 2023-12-12 |  | 27 | PVC Pipes | Industrial Park | 33245.06 | 20475 | In progress
C004 | Warehouse D | T550 | Concrete Pouring | Dave Brown | Completed | Low | 2023-03-27 | 2023-04-09 | 2023-04-09 | 100 | Cement | Industrial Park | 28408.68 | 22822.2 | No issues
C003 | Office Tower C | T227 | Site Survey | Rachel Green | In Progress | Low | 2024-04-05 | 2024-04-27 |  | 15 | Concrete | Downtown Avenue | 26128.44 | 19416.26 | In progress
C001 | Residential Building A | T281 | Roofing | Mike Adams | In Progress | High | 2023-08-04 | 2023-08-29 |  | 70 | Concrete | Plot 21, Riverside | 18030.74 | 20636.73 | In progress
C004 | Warehouse D | T126 | Plumbing Installations | Rachel Green | Not Started | Low | 2023-05-13 | 2023-06-04 |  | 0 | Concrete | Industrial Park | 23896.68 | 0 | Not started
C002 | Shopping Complex B | T180 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-01-14 | 2024-02-11 |  | 0 | Copper Wires | Market Street | 18235.76 | 43486.1 | Not started
C004 | Warehouse D | T613 | Site Survey | Dave Brown | Completed | Low | 2023-03-19 | 2023-04-13 | 2023-04-13 | 100 | Steel Beams | Industrial Park | 32103.54 | 32143.02 | No issues
C003 | Office Tower C | T668 | Roofing | Emma White | Not Started | Medium | 2023-04-18 | 2023-05-12 |  | 0 | Cement | Downtown Avenue | 30109.36 | 0 | Not started
C003 | Office Tower C | T687 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2023-12-07 | 2023-12-28 |  | 90 | Roofing Sheets | Downtown Avenue | 43059.01 | 42336.58 | In progress
C004 | Warehouse D | T673 | Interior Painting | Mike Adams | Not Started | High | 2024-06-11 | 2024-06-28 |  | 0 | Copper Wires | Industrial Park | 39456.62 | 0 | Not started
C003 | Office Tower C | T735 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2024-11-28 | 2024-12-16 |  | 0 | Roofing Sheets | Downtown Avenue | 41688.78 | 40810.65 | Not started
C002 | Shopping Complex B | T507 | Roofing | Sarah Johnson | Completed | Medium | 2024-06-13 | 2024-06-22 | 2024-06-22 | 100 | Steel Beams | Market Street | 45460.81 | 75692.13 | No issues
C004 | Warehouse D | T461 | Foundation Excavation | Dave Brown | Completed | High | 2024-05-17 | 2024-05-31 | 2024-05-31 | 100 | Concrete | Industrial Park | 5584.07 | 5517.79 | No issues
C003 | Office Tower C | T356 | Plumbing Installations | Rachel Green | Completed | High | 2024-01-08 | 2024-01-24 | 2024-01-24 | 100 | Cement | Downtown Avenue | 7077.91 | 5961.68 | No issues
C001 | Residential Building A | T938 | Steel Framework Setup | Carlos Rivera | In Progress | High | 2023-05-12 | 2023-06-02 |  | 41 | Concrete | Plot 21, Riverside | 19506.83 | 21800.51 | In progress
C003 | Office Tower C | T884 | Site Survey | Emma White | Blocked | High | 2023-02-02 | 2023-02-15 |  | 0 | Cement | Downtown Avenue | 27729.76 | 27049.28 | Not started
C003 | Office Tower C | T587 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-05-14 | 2024-06-02 |  | 0 | Paint | Downtown Avenue | 27906.47 | 0 | Not started
C001 | Residential Building A | T635 | Foundation Excavation | Mike Adams | In Progress | Medium | 2024-03-08 | 2024-03-15 |  | 77 | Rebar | Plot 21, Riverside | 22132.08 | 14792.26 | In progress
C004 | Warehouse D | T772 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2023-01-19 | 2023-02-10 |  | 0 | Copper Wires | Industrial Park | 42168.71 | 49606.65 | Not started
C002 | Shopping Complex B | T295 | Electrical Wiring | Mike Adams | Completed | High | 2023-04-12 | 2023-05-05 | 2023-05-05 | 100 | Cement | Market Street | 46251.81 | 54292.71 | No issues
C001 | Residential Building A | T641 | Plumbing Installations | Dave Brown | Completed | Medium | 2023-04-06 | 2023-04-14 | 2023-04-14 | 100 | Concrete | Plot 21, Riverside | 46788.81 | 34698.91 | No issues
C001 | Residential Building A | T105 | Plumbing Installations | Dave Brown | Completed | High | 2023-11-03 | 2023-11-16 | 2023-11-16 | 100 | Rebar | Plot 21, Riverside | 34363.43 | 40210.77 | No issues
C002 | Shopping Complex B | T230 | Site Survey | Dave Brown | Blocked | Medium | 2024-07-10 | 2024-08-04 |  | 0 | PVC Pipes | Market Street | 15321.23 | 37888.31 | Not started
C003 | Office Tower C | T260 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-01-28 | 2024-02-21 |  | 5 | Steel Beams | Downtown Avenue | 17884.21 | 18688.32 | In progress
C002 | Shopping Complex B | T960 | Foundation Excavation | Sarah Johnson | In Progress | High | 2023-07-26 | 2023-08-22 |  | 51 | Concrete | Market Street | 21725.63 | 50513.68 | In progress
C004 | Warehouse D | T224 | Foundation Excavation | Mike Adams | Completed | Medium | 2024-01-13 | 2024-02-04 | 2024-02-04 | 100 | Roofing Sheets | Industrial Park | 36965.26 | 38338.41 | No issues
C004 | Warehouse D | T284 | Interior Painting | Rachel Green | Blocked | Low | 2023-05-26 | 2023-06-02 |  | 0 | Concrete | Industrial Park | 30699.56 | 28830.71 | Not started
C001 | Residential Building A | T918 | Site Survey | Rachel Green | Blocked | Medium | 2024-07-28 | 2024-08-06 |  | 0 | Roofing Sheets | Plot 21, Riverside | 35636.75 | 38333.28 | Not started
C003 | Office Tower C | T691 | Interior Painting | Emma White | Completed | High | 2024-06-28 | 2024-07-05 | 2024-07-05 | 100 | Paint | Downtown Avenue | 6345.8 | 7499.71 | No issues
C003 | Office Tower C | T631 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2023-08-21 | 2023-08-28 |  | 1 | Copper Wires | Downtown Avenue | 14569.04 | 13936.22 | In progress
C004 | Warehouse D | T361 | Electrical Wiring | Grace Allen | Not Started | High | 2023-02-16 | 2023-03-12 |  | 0 | Copper Wires | Industrial Park | 30286.47 | 0 | Not started
C002 | Shopping Complex B | T349 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2023-09-12 | 2023-10-11 |  | 0 | PVC Pipes | Market Street | 26021.03 | 43470.61 | Not started
C004 | Warehouse D | T971 | Steel Framework Setup | Emma White | Not Started | High | 2023-11-07 | 2023-11-19 |  | 0 | Copper Wires | Industrial Park | 47424.23 | 0 | Not started
C002 | Shopping Complex B | T624 | Roofing | Sarah Johnson | Not Started | Medium | 2023-09-23 | 2023-10-16 |  | 0 | Concrete | Market Street | 38179.32 | 0 | Not started
C002 | Shopping Complex B | T717 | Interior Painting | Dave Brown | Completed | Low | 2023-12-05 | 2024-01-02 | 2024-01-02 | 100 | Roofing Sheets | Market Street | 38983.69 | 71134.01 | No issues
C004 | Warehouse D | T804 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2024-06-02 | 2024-07-02 |  | 0 | Cement | Industrial Park | 49522.25 | 56914.02 | Not started
C003 | Office Tower C | T367 | Interior Painting | John Miller | Blocked | Medium | 2023-09-07 | 2023-09-17 |  | 0 | Paint | Downtown Avenue | 38220.61 | 23952.93 | Not started
C001 | Residential Building A | T305 | Steel Framework Setup | Grace Allen | Completed | Low | 2023-11-07 | 2023-11-15 | 2023-11-15 | 100 | Rebar | Plot 21, Riverside | 6203.25 | 6287.31 | No issues
C002 | Shopping Complex B | T832 | Steel Framework Setup | Emma White | Blocked | High | 2023-04-05 | 2023-04-16 |  | 0 | Steel Beams | Market Street | 11370.28 | 38458 | Not started
C002 | Shopping Complex B | T753 | Site Survey | Rachel Green | Completed | High | 2023-12-21 | 2024-01-14 | 2024-01-14 | 100 | PVC Pipes | Market Street | 8497.48 | 34783.43 | No issues
C004 | Warehouse D | T492 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2023-11-01 | 2023-11-20 |  | 94 | Copper Wires | Industrial Park | 33708.41 | 39822 | In progress
C004 | Warehouse D | T572 | Site Survey | Carlos Rivera | Completed | Medium | 2024-02-07 | 2024-02-14 | 2024-02-14 | 100 | PVC Pipes | Industrial Park | 34653.14 | 20810.29 | No issues
C003 | Office Tower C | T367 | Roofing | Grace Allen | Not Started | Medium | 2023-07-02 | 2023-07-31 |  | 0 | Cement | Downtown Avenue | 11317.71 | 0 | Not started
C002 | Shopping Complex B | T610 | Concrete Pouring | Dave Brown | Not Started | High | 2023-09-04 | 2023-09-17 |  | 0 | Steel Beams | Market Street | 7498.52 | 0 | Not started
C002 | Shopping Complex B | T411 | Site Survey | Mike Adams | In Progress | Low | 2023-10-08 | 2023-10-24 |  | 65 | Rebar | Market Street | 46894.49 | 73756.42 | In progress
C003 | Office Tower C | T333 | Steel Framework Setup | Emma White | Not Started | Low | 2023-05-18 | 2023-06-09 |  | 0 | Rebar | Downtown Avenue | 12458.15 | 0 | Not started
C001 | Residential Building A | T596 | Electrical Wiring | Sarah Johnson | Completed | Medium | 2023-09-24 | 2023-10-24 | 2023-10-24 | 100 | Steel Beams | Plot 21, Riverside | 43257.57 | 31754.24 | No issues
C001 | Residential Building A | T187 | Interior Painting | Rachel Green | Blocked | Low | 2023-09-13 | 2023-10-09 |  | 0 | Rebar | Plot 21, Riverside | 10215.69 | 12141.26 | Not started
C004 | Warehouse D | T857 | Electrical Wiring | Sarah Johnson | Blocked | High | 2024-01-19 | 2024-02-09 |  | 0 | Steel Beams | Industrial Park | 25313.34 | 22463.35 | Not started
C002 | Shopping Complex B | T900 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2024-05-09 | 2024-05-17 |  | 0 | Steel Beams | Market Street | 15646.87 | 34894.33 | Not started
C003 | Office Tower C | T541 | Steel Framework Setup | Emma White | Blocked | High | 2024-06-25 | 2024-07-09 |  | 0 | Rebar | Downtown Avenue | 36427.37 | 41647.69 | Not started
C002 | Shopping Complex B | T774 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-06-06 | 2024-06-23 |  | 0 | Cement | Market Street | 14866.93 | 36258.53 | Not started
C003 | Office Tower C | T798 | Roofing | Sarah Johnson | Blocked | Low | 2023-09-12 | 2023-09-23 |  | 0 | Cement | Downtown Avenue | 12489.92 | 14231.36 | Not started
C004 | Warehouse D | T806 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-11-20 | 2024-12-05 | 2024-12-05 | 100 | Paint | Industrial Park | 5826.33 | 6140.66 | No issues
C001 | Residential Building A | T808 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-12-17 | 2025-01-02 |  | 0 | Concrete | Plot 21, Riverside | 42163.23 | 0 | Not started
C002 | Shopping Complex B | T241 | Site Survey | Dave Brown | Not Started | Low | 2023-02-02 | 2023-02-16 |  | 0 | Roofing Sheets | Market Street | 33589.31 | 0 | Not started
C004 | Warehouse D | T402 | Interior Painting | Emma White | Blocked | High | 2023-07-02 | 2023-07-29 |  | 0 | PVC Pipes | Industrial Park | 44219.49 | 52852.73 | Not started
C003 | Office Tower C | T910 | Electrical Wiring | Emma White | Blocked | High | 2023-07-18 | 2023-08-07 |  | 0 | Concrete | Downtown Avenue | 49367.41 | 41601.66 | Not started
C001 | Residential Building A | T908 | Interior Painting | Dave Brown | Blocked | High | 2024-11-14 | 2024-11-21 |  | 0 | Copper Wires | Plot 21, Riverside | 42420.69 | 27344.91 | Not started
C003 | Office Tower C | T130 | Electrical Wiring | John Miller | In Progress | Medium | 2024-02-04 | 2024-02-18 |  | 22 | Roofing Sheets | Downtown Avenue | 25360.5 | 26303.3 | In progress
C001 | Residential Building A | T475 | Foundation Excavation | Sarah Johnson | Blocked | High | 2024-01-22 | 2024-01-31 |  | 0 | PVC Pipes | Plot 21, Riverside | 31964.36 | 30437.85 | Not started
C001 | Residential Building A | T943 | Roofing | Rachel Green | In Progress | Low | 2023-04-13 | 2023-05-02 |  | 56 | Steel Beams | Plot 21, Riverside | 34773.13 | 24257.14 | In progress
C003 | Office Tower C | T950 | Site Survey | Grace Allen | In Progress | High | 2023-01-26 | 2023-02-09 |  | 82 | Paint | Downtown Avenue | 24727.17 | 26775.86 | In progress
C001 | Residential Building A | T340 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-10-12 | 2024-11-11 |  | 0 | Roofing Sheets | Plot 21, Riverside | 33732.18 | 32433.76 | Not started
C002 | Shopping Complex B | T612 | Plumbing Installations | Grace Allen | Not Started | High | 2023-02-07 | 2023-03-06 |  | 0 | Roofing Sheets | Market Street | 39405.14 | 0 | Not started
C002 | Shopping Complex B | T186 | Foundation Excavation | Dave Brown | Completed | Medium | 2024-09-03 | 2024-09-23 | 2024-09-23 | 100 | Rebar | Market Street | 36314.37 | 61084.47 | No issues
C003 | Office Tower C | T105 | Site Survey | Carlos Rivera | Completed | Medium | 2023-08-03 | 2023-08-18 | 2023-08-18 | 100 | Steel Beams | Downtown Avenue | 40911.69 | 45998.34 | No issues
C003 | Office Tower C | T887 | Roofing | Rachel Green | Not Started | Medium | 2024-07-03 | 2024-08-02 |  | 0 | Rebar | Downtown Avenue | 17599.75 | 0 | Not started
C004 | Warehouse D | T642 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-06-24 | 2023-07-02 | 2023-07-02 | 100 | Paint | Industrial Park | 18403.96 | 15100.71 | No issues
C003 | Office Tower C | T511 | Interior Painting | Sarah Johnson | In Progress | High | 2023-11-19 | 2023-12-19 |  | 36 | Roofing Sheets | Downtown Avenue | 19498.52 | 14147.67 | In progress
C003 | Office Tower C | T219 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-07-24 | 2024-08-06 |  | 0 | Cement | Downtown Avenue | 39376.09 | 27672.69 | Not started
C003 | Office Tower C | T688 | Electrical Wiring | John Miller | Completed | Low | 2024-12-19 | 2024-12-27 | 2024-12-27 | 100 | Paint | Downtown Avenue | 25126.74 | 17800.41 | No issues
C003 | Office Tower C | T594 | Site Survey | Grace Allen | Not Started | High | 2024-04-03 | 2024-04-24 |  | 0 | Cement | Downtown Avenue | 11020.35 | 0 | Not started
C001 | Residential Building A | T125 | Steel Framework Setup | Mike Adams | Completed | High | 2023-08-12 | 2023-09-11 | 2023-09-11 | 100 | Rebar | Plot 21, Riverside | 17904.52 | 15526.4 | No issues
C001 | Residential Building A | T481 | Steel Framework Setup | Dave Brown | In Progress | High | 2023-04-19 | 2023-05-04 |  | 87 | Steel Beams | Plot 21, Riverside | 25006.55 | 17727.34 | In progress
C001 | Residential Building A | T577 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-04-02 | 2024-04-27 |  | 9 | PVC Pipes | Plot 21, Riverside | 10755.31 | 7511.63 | In progress
C004 | Warehouse D | T718 | Foundation Excavation | Grace Allen | Not Started | Medium | 2023-09-02 | 2023-09-18 |  | 0 | Rebar | Industrial Park | 14138.73 | 0 | Not started
C001 | Residential Building A | T441 | Concrete Pouring | John Miller | Not Started | High | 2024-05-24 | 2024-06-05 |  | 0 | Concrete | Plot 21, Riverside | 36603.81 | 0 | Not started
C004 | Warehouse D | T548 | Site Survey | Rachel Green | Not Started | High | 2024-05-22 | 2024-05-29 |  | 0 | Concrete | Industrial Park | 21496.11 | 0 | Not started
C002 | Shopping Complex B | T454 | Concrete Pouring | John Miller | Completed | Medium | 2024-12-18 | 2025-01-16 | 2025-01-16 | 100 | Rebar | Market Street | 28027.12 | 54337.17 | No issues
C003 | Office Tower C | T134 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2024-12-16 | 2024-12-26 |  | 0 | Paint | Downtown Avenue | 45398.98 | 0 | Not started
C003 | Office Tower C | T108 | Interior Painting | Emma White | Blocked | High | 2023-04-07 | 2023-04-19 |  | 0 | Copper Wires | Downtown Avenue | 34635.64 | 38712.33 | Not started
C004 | Warehouse D | T609 | Site Survey | Rachel Green | In Progress | Low | 2023-02-23 | 2023-03-04 |  | 83 | Roofing Sheets | Industrial Park | 10234.35 | 11332.55 | In progress
C002 | Shopping Complex B | T936 | Plumbing Installations | Grace Allen | Not Started | Medium | 2023-08-21 | 2023-09-03 |  | 0 | PVC Pipes | Market Street | 28219.38 | 0 | Not started
C004 | Warehouse D | T159 | Foundation Excavation | Rachel Green | Completed | Low | 2023-11-19 | 2023-12-03 | 2023-12-03 | 100 | Paint | Industrial Park | 21532.52 | 18589.13 | No issues
C003 | Office Tower C | T183 | Roofing | Carlos Rivera | Completed | Medium | 2024-12-19 | 2025-01-06 | 2025-01-06 | 100 | Copper Wires | Downtown Avenue | 12152.41 | 8214.33 | No issues
C001 | Residential Building A | T698 | Concrete Pouring | Grace Allen | Not Started | Low | 2023-08-05 | 2023-08-24 |  | 0 | PVC Pipes | Plot 21, Riverside | 21041.2 | 0 | Not started
C002 | Shopping Complex B | T751 | Plumbing Installations | Dave Brown | Completed | Low | 2023-01-04 | 2023-01-29 | 2023-01-29 | 100 | PVC Pipes | Market Street | 16731.54 | 41584.6 | No issues
C002 | Shopping Complex B | T824 | Concrete Pouring | Emma White | Completed | Low | 2023-06-26 | 2023-07-24 | 2023-07-24 | 100 | Roofing Sheets | Market Street | 33549.17 | 57724.52 | No issues
C002 | Shopping Complex B | T538 | Roofing | Carlos Rivera | Not Started | Low | 2023-08-19 | 2023-08-29 |  | 0 | Paint | Market Street | 26144.49 | 0 | Not started
C004 | Warehouse D | T517 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-07-15 | 2023-07-27 | 2023-07-27 | 100 | Steel Beams | Industrial Park | 23969.3 | 16581.88 | No issues
C004 | Warehouse D | T479 | Concrete Pouring | Grace Allen | Blocked | Low | 2023-04-08 | 2023-05-03 |  | 0 | Roofing Sheets | Industrial Park | 46258.27 | 48069.71 | Not started
C002 | Shopping Complex B | T401 | Steel Framework Setup | Emma White | In Progress | High | 2023-02-24 | 2023-03-20 |  | 5 | Cement | Market Street | 28382.12 | 55069.46 | In progress
C002 | Shopping Complex B | T256 | Interior Painting | Grace Allen | Not Started | High | 2024-10-06 | 2024-10-25 |  | 0 | PVC Pipes | Market Street | 20989.64 | 0 | Not started
C002 | Shopping Complex B | T938 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2023-11-02 | 2023-11-12 |  | 0 | Cement | Market Street | 34675.16 | 0 | Not started
C002 | Shopping Complex B | T413 | Interior Painting | Dave Brown | Blocked | Low | 2024-05-01 | 2024-05-27 |  | 0 | Steel Beams | Market Street | 44334.1 | 77459.18 | Not started
C001 | Residential Building A | T160 | Site Survey | Mike Adams | Not Started | Medium | 2024-06-11 | 2024-06-29 |  | 0 | Cement | Plot 21, Riverside | 13892.44 | 0 | Not started
C002 | Shopping Complex B | T758 | Interior Painting | Dave Brown | Completed | Medium | 2023-05-06 | 2023-05-19 | 2023-05-19 | 100 | Concrete | Market Street | 37510.71 | 52995.3 | No issues
C004 | Warehouse D | T474 | Plumbing Installations | Mike Adams | Not Started | High | 2024-08-18 | 2024-09-17 |  | 0 | Paint | Industrial Park | 27799.05 | 0 | Not started
C004 | Warehouse D | T766 | Interior Painting | Rachel Green | In Progress | Low | 2023-02-02 | 2023-02-22 |  | 14 | Copper Wires | Industrial Park | 31855.55 | 23121.57 | In progress
C001 | Residential Building A | T551 | Site Survey | Carlos Rivera | Completed | Low | 2023-04-13 | 2023-04-24 | 2023-04-24 | 100 | Copper Wires | Plot 21, Riverside | 19160.77 | 19867.45 | No issues
C004 | Warehouse D | T211 | Site Survey | Carlos Rivera | Blocked | Medium | 2023-01-19 | 2023-02-14 |  | 0 | Copper Wires | Industrial Park | 38478.26 | 40365.83 | Not started
C002 | Shopping Complex B | T416 | Electrical Wiring | Mike Adams | Completed | Medium | 2023-01-01 | 2023-01-27 | 2023-01-27 | 100 | Copper Wires | Market Street | 26383.18 | 45024.26 | No issues
C002 | Shopping Complex B | T521 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2023-04-24 | 2023-05-10 |  | 0 | Paint | Market Street | 12309.78 | 39986.56 | Not started
C001 | Residential Building A | T947 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-10-26 | 2023-11-14 |  | 0 | Rebar | Plot 21, Riverside | 28263.88 | 18190.57 | Not started
C004 | Warehouse D | T486 | Steel Framework Setup | Mike Adams | Completed | High | 2023-10-18 | 2023-11-14 | 2023-11-14 | 100 | Steel Beams | Industrial Park | 48910.1 | 34174.09 | No issues
C003 | Office Tower C | T885 | Plumbing Installations | Mike Adams | Blocked | Medium | 2024-08-17 | 2024-09-15 |  | 0 | Roofing Sheets | Downtown Avenue | 48711.21 | 55191.71 | Not started
C003 | Office Tower C | T562 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-05-18 | 2023-05-31 |  | 32 | Roofing Sheets | Downtown Avenue | 5807.71 | 5438.78 | In progress
C004 | Warehouse D | T660 | Foundation Excavation | Emma White | Not Started | Low | 2023-06-11 | 2023-06-22 |  | 0 | Steel Beams | Industrial Park | 31540.15 | 0 | Not started
C001 | Residential Building A | T909 | Electrical Wiring | Mike Adams | Not Started | Medium | 2024-11-13 | 2024-11-29 |  | 0 | Copper Wires | Plot 21, Riverside | 23648.82 | 0 | Not started
C002 | Shopping Complex B | T856 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2024-05-10 | 2024-06-02 |  | 21 | Roofing Sheets | Market Street | 31609.19 | 52506.27 | In progress
C003 | Office Tower C | T263 | Foundation Excavation | Rachel Green | Blocked | Medium | 2024-12-25 | 2025-01-21 |  | 0 | Concrete | Downtown Avenue | 10620.91 | 10054.25 | Not started
C003 | Office Tower C | T759 | Site Survey | Emma White | Blocked | Medium | 2024-02-15 | 2024-02-23 |  | 0 | Rebar | Downtown Avenue | 14621.43 | 10788.79 | Not started
C004 | Warehouse D | T983 | Electrical Wiring | Carlos Rivera | In Progress | High | 2024-04-14 | 2024-05-08 |  | 39 | Concrete | Industrial Park | 36122.97 | 34594.41 | In progress
C001 | Residential Building A | T418 | Roofing | Emma White | Not Started | High | 2024-10-05 | 2024-10-21 |  | 0 | Concrete | Plot 21, Riverside | 47207.44 | 0 | Not started
C004 | Warehouse D | T603 | Foundation Excavation | Mike Adams | Not Started | High | 2023-12-11 | 2024-01-07 |  | 0 | PVC Pipes | Industrial Park | 15669.38 | 0 | Not started
C001 | Residential Building A | T886 | Electrical Wiring | Emma White | Completed | High | 2024-07-25 | 2024-08-01 | 2024-08-01 | 100 | Rebar | Plot 21, Riverside | 29989.81 | 25603.79 | No issues
C004 | Warehouse D | T349 | Roofing | Grace Allen | Blocked | Low | 2024-04-10 | 2024-04-29 |  | 0 | Rebar | Industrial Park | 29339.54 | 21812.06 | Not started
C002 | Shopping Complex B | T607 | Roofing | Dave Brown | Not Started | Medium | 2023-12-01 | 2023-12-29 |  | 0 | Roofing Sheets | Market Street | 44906.49 | 0 | Not started
C004 | Warehouse D | T338 | Site Survey | Emma White | Not Started | Medium | 2023-11-09 | 2023-11-24 |  | 0 | Rebar | Industrial Park | 35790.09 | 0 | Not started
C003 | Office Tower C | T996 | Roofing | Mike Adams | Blocked | High | 2024-02-05 | 2024-03-02 |  | 0 | Concrete | Downtown Avenue | 43108.01 | 37221.51 | Not started
C002 | Shopping Complex B | T335 | Plumbing Installations | Emma White | In Progress | High | 2024-08-04 | 2024-09-02 |  | 7 | Rebar | Market Street | 42964.44 | 51491.51 | In progress
C001 | Residential Building A | T832 | Roofing | Grace Allen | Blocked | Low | 2023-07-14 | 2023-07-24 |  | 0 | Steel Beams | Plot 21, Riverside | 38121.6 | 32938.61 | Not started
C001 | Residential Building A | T153 | Interior Painting | Carlos Rivera | Blocked | Medium | 2024-07-07 | 2024-08-05 |  | 0 | Concrete | Plot 21, Riverside | 23089.79 | 25348.88 | Not started
C003 | Office Tower C | T109 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2024-12-28 | 2025-01-23 |  | 0 | Paint | Downtown Avenue | 16399 | 0 | Not started
C003 | Office Tower C | T108 | Interior Painting | Rachel Green | Not Started | Low | 2024-10-06 | 2024-10-31 |  | 0 | Roofing Sheets | Downtown Avenue | 29430.78 | 0 | Not started
C002 | Shopping Complex B | T559 | Site Survey | Rachel Green | Completed | High | 2024-01-22 | 2024-02-13 | 2024-02-13 | 100 | Copper Wires | Market Street | 29014.7 | 45557.21 | No issues
C002 | Shopping Complex B | T194 | Concrete Pouring | Grace Allen | In Progress | High | 2024-08-16 | 2024-08-28 |  | 52 | Steel Beams | Market Street | 5500.6 | 30000.45 | In progress
C004 | Warehouse D | T484 | Foundation Excavation | Emma White | Not Started | Low | 2024-01-10 | 2024-02-09 |  | 0 | Paint | Industrial Park | 35480.21 | 0 | Not started
C004 | Warehouse D | T231 | Electrical Wiring | Mike Adams | Blocked | High | 2023-10-17 | 2023-11-11 |  | 0 | Paint | Industrial Park | 9881.59 | 11492.43 | Not started
C003 | Office Tower C | T209 | Site Survey | Grace Allen | In Progress | Medium | 2024-10-08 | 2024-10-31 |  | 54 | Rebar | Downtown Avenue | 9365.19 | 8430.24 | In progress
C001 | Residential Building A | T660 | Plumbing Installations | Carlos Rivera | Blocked | High | 2024-11-21 | 2024-12-18 |  | 0 | Rebar | Plot 21, Riverside | 10418.92 | 8908.81 | Not started
C003 | Office Tower C | T863 | Interior Painting | Grace Allen | Completed | High | 2023-10-28 | 2023-11-04 | 2023-11-04 | 100 | Cement | Downtown Avenue | 31911.54 | 34396.48 | No issues
C003 | Office Tower C | T939 | Electrical Wiring | Dave Brown | Not Started | High | 2024-11-06 | 2024-12-03 |  | 0 | Concrete | Downtown Avenue | 8237.08 | 0 | Not started
C001 | Residential Building A | T970 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-12-01 | 2023-12-08 |  | 77 | Copper Wires | Plot 21, Riverside | 25379.83 | 15829.25 | In progress
C002 | Shopping Complex B | T555 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-12-28 | 2024-01-24 |  | 0 | Paint | Market Street | 9169.34 | 34839.54 | Not started
C002 | Shopping Complex B | T207 | Plumbing Installations | Dave Brown | Completed | High | 2023-03-13 | 2023-04-10 | 2023-04-10 | 100 | Copper Wires | Market Street | 9784.02 | 36895.61 | No issues
C002 | Shopping Complex B | T181 | Concrete Pouring | Rachel Green | Blocked | High | 2024-11-10 | 2024-12-09 |  | 0 | Paint | Market Street | 9360.45 | 35796.34 | Not started
C001 | Residential Building A | T424 | Concrete Pouring | Grace Allen | Not Started | High | 2023-08-23 | 2023-09-02 |  | 0 | Cement | Plot 21, Riverside | 24998.64 | 0 | Not started
C001 | Residential Building A | T927 | Site Survey | Mike Adams | In Progress | Low | 2024-09-18 | 2024-10-01 |  | 12 | Copper Wires | Plot 21, Riverside | 14333.71 | 12565.08 | In progress
C001 | Residential Building A | T195 | Concrete Pouring | Dave Brown | Blocked | Low | 2023-02-13 | 2023-02-23 |  | 0 | PVC Pipes | Plot 21, Riverside | 36009.79 | 29966.92 | Not started
C004 | Warehouse D | T695 | Steel Framework Setup | Rachel Green | Completed | Medium | 2023-06-16 | 2023-07-12 | 2023-07-12 | 100 | Copper Wires | Industrial Park | 13424.38 | 9616.71 | No issues
C003 | Office Tower C | T860 | Plumbing Installations | Rachel Green | Completed | Low | 2024-03-20 | 2024-04-06 | 2024-04-06 | 100 | Steel Beams | Downtown Avenue | 25395.55 | 25539.92 | No issues
C001 | Residential Building A | T993 | Foundation Excavation | Emma White | Blocked | Low | 2023-10-17 | 2023-11-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 10938.32 | 10253.68 | Not started
C004 | Warehouse D | T430 | Steel Framework Setup | Sarah Johnson | Completed | High | 2024-10-16 | 2024-11-13 | 2024-11-13 | 100 | Concrete | Industrial Park | 14813.4 | 10625.18 | No issues
C003 | Office Tower C | T164 | Plumbing Installations | Carlos Rivera | Not Started | High | 2023-06-06 | 2023-06-28 |  | 0 | Copper Wires | Downtown Avenue | 24802.45 | 0 | Not started
C004 | Warehouse D | T210 | Electrical Wiring | Emma White | Not Started | High | 2024-01-11 | 2024-01-28 |  | 0 | Rebar | Industrial Park | 26057.51 | 0 | Not started
C001 | Residential Building A | T987 | Roofing | Sarah Johnson | In Progress | Low | 2023-11-28 | 2023-12-23 |  | 80 | Cement | Plot 21, Riverside | 24359.69 | 19827.39 | In progress
C001 | Residential Building A | T683 | Site Survey | Sarah Johnson | Blocked | Medium | 2024-02-25 | 2024-03-05 |  | 0 | Steel Beams | Plot 21, Riverside | 7575.81 | 7143.67 | Not started
C004 | Warehouse D | T993 | Site Survey | Dave Brown | Completed | Medium | 2023-05-17 | 2023-05-25 | 2023-05-25 | 100 | Roofing Sheets | Industrial Park | 44669.02 | 34407.31 | No issues
C001 | Residential Building A | T843 | Site Survey | Carlos Rivera | Not Started | Medium | 2023-02-01 | 2023-02-20 |  | 0 | Cement | Plot 21, Riverside | 36453.58 | 0 | Not started
C004 | Warehouse D | T132 | Site Survey | Mike Adams | Not Started | Medium | 2024-10-26 | 2024-11-09 |  | 0 | Cement | Industrial Park | 22112.82 | 0 | Not started
C003 | Office Tower C | T124 | Interior Painting | Emma White | Blocked | High | 2023-06-03 | 2023-06-28 |  | 0 | Roofing Sheets | Downtown Avenue | 47413.74 | 38165.55 | Not started
C003 | Office Tower C | T305 | Interior Painting | John Miller | In Progress | Medium | 2023-04-26 | 2023-05-19 |  | 92 | Roofing Sheets | Downtown Avenue | 7985.67 | 6370.34 | In progress
C001 | Residential Building A | T255 | Roofing | John Miller | Blocked | Medium | 2023-03-15 | 2023-04-08 |  | 0 | Rebar | Plot 21, Riverside | 9192 | 10896.15 | Not started
C002 | Shopping Complex B | T430 | Electrical Wiring | Rachel Green | In Progress | Low | 2024-12-08 | 2024-12-24 |  | 9 | Concrete | Market Street | 10544.77 | 34445.38 | In progress
C002 | Shopping Complex B | T840 | Concrete Pouring | Grace Allen | Completed | High | 2023-02-16 | 2023-02-23 | 2023-02-23 | 100 | PVC Pipes | Market Street | 19194.13 | 47911.59 | No issues
C001 | Residential Building A | T125 | Plumbing Installations | Mike Adams | Blocked | High | 2023-10-12 | 2023-10-27 |  | 0 | Roofing Sheets | Plot 21, Riverside | 26663.27 | 29085.53 | Not started
C002 | Shopping Complex B | T275 | Interior Painting | Rachel Green | Blocked | High | 2023-05-05 | 2023-05-20 |  | 0 | Steel Beams | Market Street | 15219.41 | 38002.36 | Not started
C004 | Warehouse D | T707 | Concrete Pouring | John Miller | In Progress | Low | 2023-10-07 | 2023-11-04 |  | 47 | Paint | Industrial Park | 37043.59 | 40991.36 | In progress
C004 | Warehouse D | T580 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2024-04-07 | 2024-04-20 |  | 0 | Cement | Industrial Park | 31402.56 | 0 | Not started
C002 | Shopping Complex B | T517 | Electrical Wiring | John Miller | In Progress | Medium | 2024-05-23 | 2024-06-10 |  | 78 | Steel Beams | Market Street | 19962.56 | 38671.87 | In progress
C001 | Residential Building A | T627 | Site Survey | Emma White | In Progress | High | 2023-09-14 | 2023-10-04 |  | 74 | Concrete | Plot 21, Riverside | 19858.99 | 12650.87 | In progress
C003 | Office Tower C | T143 | Plumbing Installations | Dave Brown | In Progress | Medium | 2024-01-08 | 2024-01-24 |  | 91 | Steel Beams | Downtown Avenue | 38467.92 | 27993.95 | In progress
C001 | Residential Building A | T262 | Steel Framework Setup | John Miller | Completed | Medium | 2024-04-01 | 2024-04-19 | 2024-04-19 | 100 | Copper Wires | Plot 21, Riverside | 27057.61 | 18549.9 | No issues
C003 | Office Tower C | T225 | Interior Painting | Grace Allen | Not Started | Low | 2024-12-28 | 2025-01-18 |  | 0 | Paint | Downtown Avenue | 7945.21 | 0 | Not started
C001 | Residential Building A | T165 | Foundation Excavation | Dave Brown | Blocked | High | 2024-07-10 | 2024-08-06 |  | 0 | Roofing Sheets | Plot 21, Riverside | 40325.32 | 39350.04 | Not started
C003 | Office Tower C | T696 | Foundation Excavation | John Miller | In Progress | High | 2023-10-11 | 2023-11-06 |  | 58 | Paint | Downtown Avenue | 9420.46 | 6284.69 | In progress
C001 | Residential Building A | T187 | Concrete Pouring | Emma White | Not Started | Low | 2024-12-13 | 2025-01-03 |  | 0 | Concrete | Plot 21, Riverside | 33105.33 | 0 | Not started
C004 | Warehouse D | T572 | Roofing | Sarah Johnson | Not Started | High | 2024-12-08 | 2025-01-06 |  | 0 | Cement | Industrial Park | 9689.57 | 0 | Not started
C003 | Office Tower C | T551 | Concrete Pouring | Grace Allen | Completed | Medium | 2023-07-19 | 2023-08-04 | 2023-08-04 | 100 | Copper Wires | Downtown Avenue | 21025.36 | 24676.41 | No issues
C004 | Warehouse D | T859 | Site Survey | Grace Allen | In Progress | Medium | 2024-10-19 | 2024-11-18 |  | 53 | PVC Pipes | Industrial Park | 8381.47 | 6395.18 | In progress
C004 | Warehouse D | T991 | Roofing | Carlos Rivera | Completed | Medium | 2024-06-22 | 2024-07-14 | 2024-07-14 | 100 | Copper Wires | Industrial Park | 46334.23 | 53316.38 | No issues
C003 | Office Tower C | T338 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2023-12-18 | 2023-12-27 |  | 0 | Paint | Downtown Avenue | 22932 | 17230.06 | Not started
C002 | Shopping Complex B | T985 | Foundation Excavation | Grace Allen | Not Started | Medium | 2023-01-19 | 2023-02-10 |  | 0 | Concrete | Market Street | 30237.34 | 0 | Not started
C002 | Shopping Complex B | T112 | Concrete Pouring | Mike Adams | Blocked | Medium | 2024-07-07 | 2024-08-01 |  | 0 | Steel Beams | Market Street | 15238.82 | 37157.61 | Not started
C004 | Warehouse D | T354 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2023-01-06 | 2023-01-25 |  | 0 | Steel Beams | Industrial Park | 16428.5 | 13128.88 | Not started
C002 | Shopping Complex B | T147 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-10-02 | 2024-10-30 |  | 0 | Cement | Market Street | 43726.84 | 72511.06 | Not started
C001 | Residential Building A | T400 | Electrical Wiring | Emma White | Not Started | Medium | 2024-07-12 | 2024-07-22 |  | 0 | Paint | Plot 21, Riverside | 5848.2 | 0 | Not started
C003 | Office Tower C | T796 | Site Survey | Mike Adams | In Progress | Low | 2024-03-04 | 2024-03-14 |  | 73 | Concrete | Downtown Avenue | 9928.3 | 10023.33 | In progress
C004 | Warehouse D | T419 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2024-12-15 | 2025-01-09 |  | 0 | Cement | Industrial Park | 22679.27 | 14886.55 | Not started
C003 | Office Tower C | T154 | Interior Painting | John Miller | Completed | High | 2024-10-03 | 2024-10-16 | 2024-10-16 | 100 | PVC Pipes | Downtown Avenue | 45170.35 | 36115.16 | No issues
C001 | Residential Building A | T548 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-05-20 | 2023-06-05 |  | 0 | Roofing Sheets | Plot 21, Riverside | 10477.74 | 11290.04 | Not started
C002 | Shopping Complex B | T836 | Interior Painting | Grace Allen | Not Started | Medium | 2024-12-11 | 2025-01-05 |  | 0 | Concrete | Market Street | 12172.84 | 0 | Not started
C004 | Warehouse D | T902 | Roofing | Dave Brown | Blocked | High | 2023-07-01 | 2023-07-30 |  | 0 | Rebar | Industrial Park | 8282.79 | 7397.06 | Not started
C004 | Warehouse D | T929 | Interior Painting | Sarah Johnson | In Progress | Medium | 2024-11-20 | 2024-12-12 |  | 4 | PVC Pipes | Industrial Park | 14285.42 | 9903.36 | In progress
C004 | Warehouse D | T515 | Electrical Wiring | Grace Allen | Not Started | Low | 2023-09-14 | 2023-10-13 |  | 0 | Rebar | Industrial Park | 30371.62 | 0 | Not started
C003 | Office Tower C | T931 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2023-06-13 | 2023-06-22 |  | 54 | Concrete | Downtown Avenue | 7786.8 | 7615.21 | In progress
C001 | Residential Building A | T733 | Foundation Excavation | Rachel Green | Completed | Medium | 2024-12-24 | 2025-01-11 | 2025-01-11 | 100 | Concrete | Plot 21, Riverside | 39953.43 | 35504.78 | No issues
C004 | Warehouse D | T108 | Foundation Excavation | John Miller | Not Started | Low | 2023-10-08 | 2023-11-04 |  | 0 | Cement | Industrial Park | 24801.56 | 0 | Not started
C001 | Residential Building A | T253 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-08-06 | 2024-08-21 | 2024-08-21 | 100 | PVC Pipes | Plot 21, Riverside | 29755.42 | 29838.83 | No issues
C002 | Shopping Complex B | T314 | Concrete Pouring | Mike Adams | Completed | Medium | 2024-03-05 | 2024-03-30 | 2024-03-30 | 100 | Copper Wires | Market Street | 38733.94 | 51960.03 | No issues
C004 | Warehouse D | T330 | Plumbing Installations | Emma White | Completed | Medium | 2023-02-21 | 2023-03-01 | 2023-03-01 | 100 | PVC Pipes | Industrial Park | 44665.9 | 30216.26 | No issues
C002 | Shopping Complex B | T674 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2024-12-02 | 2024-12-31 |  | 0 | Steel Beams | Market Street | 14947.02 | 0 | Not started
C002 | Shopping Complex B | T350 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2024-04-23 | 2024-05-08 | 2024-05-08 | 100 | Cement | Market Street | 33273.7 | 59102.29 | No issues
C001 | Residential Building A | T820 | Concrete Pouring | Carlos Rivera | Blocked | High | 2024-06-14 | 2024-07-08 |  | 0 | PVC Pipes | Plot 21, Riverside | 8411.64 | 8579.54 | Not started
C004 | Warehouse D | T818 | Foundation Excavation | Emma White | In Progress | Medium | 2024-11-06 | 2024-11-22 |  | 80 | Copper Wires | Industrial Park | 11901.11 | 12962.6 | In progress
C002 | Shopping Complex B | T358 | Plumbing Installations | Dave Brown | Blocked | Low | 2024-02-09 | 2024-03-10 |  | 0 | PVC Pipes | Market Street | 44435.11 | 52258.72 | Not started
C003 | Office Tower C | T446 | Roofing | Mike Adams | In Progress | Low | 2023-05-12 | 2023-06-07 |  | 68 | PVC Pipes | Downtown Avenue | 27549.93 | 23677.08 | In progress
C001 | Residential Building A | T941 | Roofing | John Miller | In Progress | Low | 2023-08-09 | 2023-09-05 |  | 8 | Cement | Plot 21, Riverside | 25046.3 | 19717.91 | In progress
C003 | Office Tower C | T732 | Concrete Pouring | Carlos Rivera | In Progress | High | 2024-03-18 | 2024-04-14 |  | 34 | Rebar | Downtown Avenue | 14543.48 | 16249.05 | In progress
C002 | Shopping Complex B | T197 | Interior Painting | John Miller | Blocked | Low | 2023-09-25 | 2023-10-10 |  | 0 | Roofing Sheets | Market Street | 29231.3 | 55551.84 | Not started
C002 | Shopping Complex B | T901 | Interior Painting | Grace Allen | Blocked | Low | 2024-06-26 | 2024-07-04 |  | 0 | Cement | Market Street | 20135.78 | 48514.54 | Not started
C001 | Residential Building A | T795 | Electrical Wiring | Rachel Green | Blocked | Low | 2023-02-04 | 2023-02-13 |  | 0 | Roofing Sheets | Plot 21, Riverside | 44352.62 | 49033.86 | Not started
C004 | Warehouse D | T348 | Site Survey | Mike Adams | Not Started | High | 2024-02-02 | 2024-03-01 |  | 0 | Cement | Industrial Park | 49709.11 | 0 | Not started
C002 | Shopping Complex B | T835 | Electrical Wiring | Grace Allen | Completed | High | 2024-10-15 | 2024-11-14 | 2024-11-14 | 100 | Paint | Market Street | 32872.65 | 61470.41 | No issues
C001 | Residential Building A | T951 | Steel Framework Setup | John Miller | Completed | High | 2023-07-01 | 2023-07-28 | 2023-07-28 | 100 | Copper Wires | Plot 21, Riverside | 16503.66 | 10540.01 | No issues
C004 | Warehouse D | T927 | Site Survey | Carlos Rivera | In Progress | Medium | 2023-01-17 | 2023-02-02 |  | 78 | Paint | Industrial Park | 46545.17 | 54098.94 | In progress
C004 | Warehouse D | T285 | Plumbing Installations | Grace Allen | Not Started | Low | 2023-08-14 | 2023-09-04 |  | 0 | Roofing Sheets | Industrial Park | 37235.41 | 0 | Not started
C002 | Shopping Complex B | T648 | Plumbing Installations | Sarah Johnson | In Progress | High | 2024-11-24 | 2024-12-17 |  | 93 | PVC Pipes | Market Street | 13275.95 | 38626.83 | In progress
C002 | Shopping Complex B | T683 | Site Survey | Carlos Rivera | Not Started | High | 2024-02-27 | 2024-03-15 |  | 0 | Paint | Market Street | 26302.43 | 0 | Not started
C004 | Warehouse D | T531 | Concrete Pouring | Emma White | Not Started | Medium | 2023-04-01 | 2023-04-11 |  | 0 | Cement | Industrial Park | 40767.66 | 0 | Not started
C004 | Warehouse D | T691 | Plumbing Installations | Rachel Green | Blocked | High | 2023-09-26 | 2023-10-19 |  | 0 | Copper Wires | Industrial Park | 45496.59 | 31778.94 | Not started
C001 | Residential Building A | T149 | Interior Painting | John Miller | Not Started | High | 2023-01-06 | 2023-01-31 |  | 0 | Paint | Plot 21, Riverside | 16497.04 | 0 | Not started
C004 | Warehouse D | T562 | Electrical Wiring | Emma White | In Progress | Low | 2023-08-15 | 2023-08-25 |  | 58 | Rebar | Industrial Park | 19372.05 | 22422.72 | In progress
C003 | Office Tower C | T493 | Foundation Excavation | Mike Adams | Not Started | High | 2024-03-23 | 2024-04-20 |  | 0 | Roofing Sheets | Downtown Avenue | 49568.35 | 0 | Not started
C003 | Office Tower C | T266 | Interior Painting | Mike Adams | Blocked | High | 2024-11-05 | 2024-11-13 |  | 0 | Roofing Sheets | Downtown Avenue | 45340.71 | 48952.02 | Not started
C002 | Shopping Complex B | T384 | Foundation Excavation | Emma White | Completed | Medium | 2023-01-04 | 2023-01-29 | 2023-01-29 | 100 | PVC Pipes | Market Street | 19303.55 | 46249.7 | No issues
C003 | Office Tower C | T765 | Foundation Excavation | Sarah Johnson | Completed | High | 2023-07-22 | 2023-07-29 | 2023-07-29 | 100 | Concrete | Downtown Avenue | 6011.95 | 6765.9 | No issues
C002 | Shopping Complex B | T840 | Site Survey | Grace Allen | In Progress | Low | 2024-10-17 | 2024-11-04 |  | 59 | PVC Pipes | Market Street | 36852.3 | 55099.99 | In progress
C004 | Warehouse D | T481 | Roofing | Mike Adams | In Progress | Medium | 2024-05-26 | 2024-06-19 |  | 53 | Cement | Industrial Park | 5005 | 4263.37 | In progress
C002 | Shopping Complex B | T913 | Concrete Pouring | Carlos Rivera | Not Started | High | 2024-03-27 | 2024-04-13 |  | 0 | Concrete | Market Street | 32709.03 | 0 | Not started
C001 | Residential Building A | T630 | Interior Painting | Sarah Johnson | Completed | Low | 2023-08-11 | 2023-08-20 | 2023-08-20 | 100 | Concrete | Plot 21, Riverside | 23642.44 | 17260.4 | No issues
C003 | Office Tower C | T875 | Roofing | Rachel Green | Completed | Medium | 2023-05-21 | 2023-06-06 | 2023-06-06 | 100 | Copper Wires | Downtown Avenue | 48001.57 | 53769.03 | No issues
C001 | Residential Building A | T659 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-04-12 | 2023-05-03 |  | 0 | Copper Wires | Plot 21, Riverside | 31997.49 | 0 | Not started
C002 | Shopping Complex B | T138 | Plumbing Installations | Dave Brown | Blocked | High | 2023-01-13 | 2023-02-02 |  | 0 | Cement | Market Street | 17435.84 | 36325.28 | Not started
C004 | Warehouse D | T637 | Site Survey | Sarah Johnson | Completed | Medium | 2024-11-01 | 2024-11-15 | 2024-11-15 | 100 | PVC Pipes | Industrial Park | 47546.63 | 49929 | No issues
C003 | Office Tower C | T653 | Interior Painting | Grace Allen | Not Started | High | 2024-06-10 | 2024-06-19 |  | 0 | PVC Pipes | Downtown Avenue | 24739.47 | 0 | Not started
C003 | Office Tower C | T944 | Site Survey | Carlos Rivera | Completed | High | 2023-11-24 | 2023-12-24 | 2023-12-24 | 100 | Roofing Sheets | Downtown Avenue | 40200.35 | 32632.79 | No issues
C004 | Warehouse D | T333 | Interior Painting | Rachel Green | Completed | Low | 2023-02-14 | 2023-03-15 | 2023-03-15 | 100 | Cement | Industrial Park | 9387.05 | 6817.64 | No issues
C004 | Warehouse D | T453 | Concrete Pouring | Grace Allen | In Progress | Medium | 2024-03-28 | 2024-04-27 |  | 26 | Paint | Industrial Park | 8538.9 | 10069.98 | In progress
C001 | Residential Building A | T168 | Site Survey | Rachel Green | Completed | Low | 2024-08-08 | 2024-08-20 | 2024-08-20 | 100 | Cement | Plot 21, Riverside | 36205.41 | 29789.08 | No issues
C003 | Office Tower C | T366 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-07-08 | 2024-07-27 |  | 0 | Concrete | Downtown Avenue | 35670.75 | 37613.42 | Not started
C003 | Office Tower C | T680 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-09-18 | 2023-09-25 |  | 83 | Roofing Sheets | Downtown Avenue | 15551.75 | 18522.02 | In progress
C003 | Office Tower C | T233 | Foundation Excavation | Rachel Green | Blocked | Medium | 2024-12-05 | 2024-12-17 |  | 0 | Rebar | Downtown Avenue | 37674.03 | 38446.12 | Not started
C001 | Residential Building A | T217 | Interior Painting | Carlos Rivera | Completed | High | 2023-12-09 | 2023-12-25 | 2023-12-25 | 100 | Paint | Plot 21, Riverside | 39994.57 | 46943.93 | No issues
C003 | Office Tower C | T822 | Site Survey | Dave Brown | Completed | Low | 2024-01-28 | 2024-02-21 | 2024-02-21 | 100 | Rebar | Downtown Avenue | 30003.36 | 30938.3 | No issues
C004 | Warehouse D | T710 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-07-10 | 2023-07-18 |  | 0 | Rebar | Industrial Park | 12427.48 | 13853.1 | Not started
C001 | Residential Building A | T673 | Plumbing Installations | John Miller | Blocked | High | 2024-03-06 | 2024-03-19 |  | 0 | Cement | Plot 21, Riverside | 34251.92 | 26354.84 | Not started
C001 | Residential Building A | T416 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2024-03-16 | 2024-04-10 |  | 43 | Paint | Plot 21, Riverside | 14777.79 | 12929.77 | In progress
C003 | Office Tower C | T362 | Interior Painting | John Miller | Blocked | High | 2024-05-09 | 2024-05-22 |  | 0 | PVC Pipes | Downtown Avenue | 12455.78 | 12880.28 | Not started
C004 | Warehouse D | T623 | Roofing | John Miller | In Progress | Low | 2023-04-16 | 2023-05-10 |  | 61 | Paint | Industrial Park | 44002.75 | 46494.51 | In progress
C003 | Office Tower C | T659 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-08-23 | 2024-09-11 |  | 0 | Copper Wires | Downtown Avenue | 16893.25 | 14260.76 | Not started
C004 | Warehouse D | T325 | Steel Framework Setup | Emma White | Blocked | Medium | 2024-05-18 | 2024-05-26 |  | 0 | Roofing Sheets | Industrial Park | 31215.97 | 32248.27 | Not started
C003 | Office Tower C | T181 | Interior Painting | Mike Adams | In Progress | High | 2023-10-24 | 2023-11-10 |  | 72 | Steel Beams | Downtown Avenue | 49531.04 | 46664.51 | In progress
C003 | Office Tower C | T540 | Plumbing Installations | Sarah Johnson | Completed | High | 2023-02-14 | 2023-02-21 | 2023-02-21 | 100 | Rebar | Downtown Avenue | 31112.3 | 33768.42 | No issues
C004 | Warehouse D | T938 | Steel Framework Setup | Sarah Johnson | Completed | Low | 2024-10-12 | 2024-10-20 | 2024-10-20 | 100 | Steel Beams | Industrial Park | 8685.86 | 6312.76 | No issues
C001 | Residential Building A | T740 | Site Survey | Rachel Green | Not Started | Medium | 2023-07-16 | 2023-08-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 47772.02 | 0 | Not started
C001 | Residential Building A | T662 | Site Survey | Emma White | Not Started | Medium | 2024-05-22 | 2024-06-08 |  | 0 | Cement | Plot 21, Riverside | 38598.49 | 0 | Not started
C003 | Office Tower C | T653 | Foundation Excavation | John Miller | In Progress | High | 2023-11-03 | 2023-11-24 |  | 80 | PVC Pipes | Downtown Avenue | 38762.6 | 43111.01 | In progress
C001 | Residential Building A | T578 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2023-09-05 | 2023-10-05 |  | 0 | Rebar | Plot 21, Riverside | 19568.75 | 0 | Not started
C002 | Shopping Complex B | T227 | Roofing | Rachel Green | Blocked | Medium | 2024-08-19 | 2024-08-30 |  | 0 | Paint | Market Street | 30237.17 | 47379.61 | Not started
C002 | Shopping Complex B | T909 | Concrete Pouring | Emma White | In Progress | Medium | 2023-07-05 | 2023-07-14 |  | 6 | Paint | Market Street | 17970.68 | 37080.61 | In progress
C001 | Residential Building A | T443 | Site Survey | Carlos Rivera | Not Started | High | 2024-02-06 | 2024-02-18 |  | 0 | Paint | Plot 21, Riverside | 8271.28 | 0 | Not started
C001 | Residential Building A | T405 | Steel Framework Setup | Rachel Green | Not Started | High | 2024-07-11 | 2024-08-09 |  | 0 | PVC Pipes | Plot 21, Riverside | 5561.26 | 0 | Not started
C003 | Office Tower C | T271 | Interior Painting | Mike Adams | Not Started | Medium | 2024-03-23 | 2024-04-12 |  | 0 | Rebar | Downtown Avenue | 6896.43 | 0 | Not started
C004 | Warehouse D | T738 | Steel Framework Setup | Rachel Green | Completed | High | 2024-02-24 | 2024-03-23 | 2024-03-23 | 100 | Copper Wires | Industrial Park | 32947.28 | 28703.95 | No issues
C003 | Office Tower C | T343 | Plumbing Installations | John Miller | Completed | Medium | 2024-11-21 | 2024-12-07 | 2024-12-07 | 100 | PVC Pipes | Downtown Avenue | 12704.89 | 15206.11 | No issues
C004 | Warehouse D | T116 | Electrical Wiring | Mike Adams | Not Started | Low | 2023-05-09 | 2023-05-29 |  | 0 | Copper Wires | Industrial Park | 6742.39 | 0 | Not started
C003 | Office Tower C | T582 | Site Survey | Mike Adams | Not Started | High | 2023-02-04 | 2023-03-01 |  | 0 | PVC Pipes | Downtown Avenue | 18997.04 | 0 | Not started
C001 | Residential Building A | T611 | Site Survey | John Miller | Completed | Medium | 2024-12-06 | 2024-12-15 | 2024-12-15 | 100 | Rebar | Plot 21, Riverside | 5912.03 | 5916.26 | No issues
C002 | Shopping Complex B | T186 | Steel Framework Setup | Emma White | Blocked | Low | 2023-11-25 | 2023-12-08 |  | 0 | Rebar | Market Street | 48001.51 | 75240.92 | Not started
C004 | Warehouse D | T107 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-10-10 | 2024-11-08 |  | 97 | Concrete | Industrial Park | 49609.26 | 56062.06 | In progress
C004 | Warehouse D | T532 | Steel Framework Setup | Sarah Johnson | Blocked | High | 2024-01-16 | 2024-01-23 |  | 0 | Cement | Industrial Park | 13449.64 | 9874.44 | Not started
C003 | Office Tower C | T964 | Site Survey | Sarah Johnson | Blocked | Low | 2023-09-01 | 2023-09-12 |  | 0 | Rebar | Downtown Avenue | 33832.79 | 22448.71 | Not started
C001 | Residential Building A | T431 | Concrete Pouring | Dave Brown | Completed | Medium | 2024-07-12 | 2024-07-30 | 2024-07-30 | 100 | Roofing Sheets | Plot 21, Riverside | 8268.07 | 7282 | No issues
C002 | Shopping Complex B | T936 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-12-21 | 2024-12-29 |  | 0 | Concrete | Market Street | 13589.03 | 38146.47 | Not started
C001 | Residential Building A | T986 | Roofing | Grace Allen | Not Started | High | 2023-04-04 | 2023-04-15 |  | 0 | Steel Beams | Plot 21, Riverside | 18565.26 | 0 | Not started
C004 | Warehouse D | T718 | Electrical Wiring | Rachel Green | Completed | Low | 2024-09-24 | 2024-10-21 | 2024-10-21 | 100 | Concrete | Industrial Park | 10622.97 | 8344.17 | No issues
C004 | Warehouse D | T345 | Interior Painting | Rachel Green | In Progress | Low | 2024-09-06 | 2024-09-23 |  | 45 | Concrete | Industrial Park | 12481.57 | 10843.42 | In progress
C004 | Warehouse D | T362 | Roofing | Carlos Rivera | Not Started | Low | 2024-10-19 | 2024-11-08 |  | 0 | Concrete | Industrial Park | 28645.22 | 0 | Not started
C002 | Shopping Complex B | T432 | Electrical Wiring | Dave Brown | In Progress | Medium | 2023-04-06 | 2023-04-17 |  | 98 | Rebar | Market Street | 39256.64 | 72019.3 | In progress
C001 | Residential Building A | T725 | Roofing | John Miller | Not Started | Low | 2023-06-16 | 2023-07-02 |  | 0 | PVC Pipes | Plot 21, Riverside | 33127.68 | 0 | Not started
C001 | Residential Building A | T639 | Steel Framework Setup | Mike Adams | Not Started | Low | 2023-09-02 | 2023-09-11 |  | 0 | Rebar | Plot 21, Riverside | 10089.25 | 0 | Not started
C004 | Warehouse D | T620 | Interior Painting | Mike Adams | Completed | Low | 2023-04-24 | 2023-05-09 | 2023-05-09 | 100 | Concrete | Industrial Park | 23002.39 | 23116.47 | No issues
C001 | Residential Building A | T209 | Electrical Wiring | Dave Brown | Blocked | Medium | 2024-03-07 | 2024-03-21 |  | 0 | Steel Beams | Plot 21, Riverside | 47469.76 | 56524.12 | Not started
C003 | Office Tower C | T102 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-05-19 | 2024-05-28 |  | 0 | Copper Wires | Downtown Avenue | 45209.92 | 0 | Not started
C003 | Office Tower C | T362 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2023-05-03 | 2023-05-22 |  | 0 | Paint | Downtown Avenue | 7369.92 | 0 | Not started
C002 | Shopping Complex B | T597 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-10-09 | 2024-10-21 |  | 43 | Roofing Sheets | Market Street | 38820.37 | 69094.24 | In progress
C004 | Warehouse D | T112 | Foundation Excavation | Grace Allen | In Progress | High | 2024-09-24 | 2024-10-15 |  | 96 | Roofing Sheets | Industrial Park | 13244.96 | 13281.01 | In progress
C001 | Residential Building A | T287 | Foundation Excavation | Sarah Johnson | Blocked | Low | 2024-07-06 | 2024-07-21 |  | 0 | Paint | Plot 21, Riverside | 7809.58 | 4710.74 | Not started
C003 | Office Tower C | T717 | Plumbing Installations | Mike Adams | Blocked | Medium | 2023-10-04 | 2023-10-16 |  | 0 | Concrete | Downtown Avenue | 20026.21 | 24000.21 | Not started
C004 | Warehouse D | T646 | Electrical Wiring | Carlos Rivera | Not Started | High | 2024-08-09 | 2024-09-05 |  | 0 | Copper Wires | Industrial Park | 40694.8 | 0 | Not started
C004 | Warehouse D | T935 | Roofing | Rachel Green | Completed | Medium | 2024-09-07 | 2024-09-28 | 2024-09-28 | 100 | Copper Wires | Industrial Park | 18972.06 | 20310.43 | No issues
C002 | Shopping Complex B | T616 | Roofing | John Miller | Not Started | High | 2023-07-11 | 2023-07-25 |  | 0 | PVC Pipes | Market Street | 14793.85 | 0 | Not started
C004 | Warehouse D | T567 | Foundation Excavation | Carlos Rivera | In Progress | High | 2024-05-19 | 2024-06-12 |  | 65 | Copper Wires | Industrial Park | 37617.98 | 26460.61 | In progress
C001 | Residential Building A | T690 | Site Survey | Carlos Rivera | Completed | Medium | 2024-08-13 | 2024-09-10 | 2024-09-10 | 100 | Paint | Plot 21, Riverside | 47721.89 | 37707.59 | No issues
C002 | Shopping Complex B | T111 | Site Survey | Mike Adams | Not Started | Low | 2024-06-26 | 2024-07-25 |  | 0 | Roofing Sheets | Market Street | 12463.91 | 0 | Not started
C003 | Office Tower C | T862 | Site Survey | Carlos Rivera | Not Started | High | 2023-09-20 | 2023-10-01 |  | 0 | Steel Beams | Downtown Avenue | 41590.4 | 0 | Not started
C001 | Residential Building A | T656 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-10-24 | 2023-11-16 |  | 12 | Cement | Plot 21, Riverside | 30158.27 | 25875.13 | In progress
C001 | Residential Building A | T754 | Roofing | Carlos Rivera | In Progress | High | 2023-03-09 | 2023-03-19 |  | 1 | Concrete | Plot 21, Riverside | 43926.99 | 46121.09 | In progress
C003 | Office Tower C | T898 | Concrete Pouring | Grace Allen | In Progress | Medium | 2023-08-03 | 2023-08-24 |  | 65 | Rebar | Downtown Avenue | 6307.77 | 6423.28 | In progress
C003 | Office Tower C | T615 | Interior Painting | Sarah Johnson | In Progress | Medium | 2024-05-05 | 2024-06-02 |  | 25 | Cement | Downtown Avenue | 32552.95 | 30224.56 | In progress
C002 | Shopping Complex B | T757 | Interior Painting | John Miller | Completed | High | 2024-05-05 | 2024-05-20 | 2024-05-20 | 100 | Cement | Market Street | 7005.44 | 32209.54 | No issues
C002 | Shopping Complex B | T646 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-05-06 | 2023-05-31 | 2023-05-31 | 100 | Paint | Market Street | 6711.61 | 29894.44 | No issues
C002 | Shopping Complex B | T960 | Steel Framework Setup | Emma White | Blocked | High | 2023-01-28 | 2023-02-16 |  | 0 | Copper Wires | Market Street | 36766.64 | 65820.64 | Not started
C002 | Shopping Complex B | T128 | Plumbing Installations | Rachel Green | Blocked | High | 2023-10-05 | 2023-10-23 |  | 0 | Cement | Market Street | 30370.37 | 58160.49 | Not started
C002 | Shopping Complex B | T795 | Steel Framework Setup | Emma White | Not Started | Low | 2023-12-24 | 2024-01-12 |  | 0 | Rebar | Market Street | 16856.65 | 0 | Not started
C001 | Residential Building A | T947 | Interior Painting | Sarah Johnson | Not Started | High | 2024-08-23 | 2024-09-04 |  | 0 | PVC Pipes | Plot 21, Riverside | 23114.41 | 0 | Not started
C004 | Warehouse D | T628 | Interior Painting | John Miller | Not Started | Low | 2023-09-09 | 2023-10-04 |  | 0 | Cement | Industrial Park | 25099.62 | 0 | Not started
C003 | Office Tower C | T747 | Foundation Excavation | Rachel Green | Not Started | Low | 2024-04-05 | 2024-04-30 |  | 0 | Roofing Sheets | Downtown Avenue | 41937.96 | 0 | Not started
C003 | Office Tower C | T870 | Site Survey | Grace Allen | In Progress | High | 2023-06-11 | 2023-07-09 |  | 28 | Roofing Sheets | Downtown Avenue | 35394.85 | 24162.72 | In progress
C001 | Residential Building A | T435 | Electrical Wiring | Rachel Green | Not Started | Low | 2024-09-20 | 2024-09-30 |  | 0 | Paint | Plot 21, Riverside | 18987.92 | 0 | Not started
C003 | Office Tower C | T926 | Interior Painting | Rachel Green | Completed | High | 2023-08-10 | 2023-08-30 | 2023-08-30 | 100 | Copper Wires | Downtown Avenue | 42592.52 | 45643.86 | No issues
C004 | Warehouse D | T416 | Foundation Excavation | John Miller | In Progress | Medium | 2023-05-06 | 2023-06-01 |  | 73 | Cement | Industrial Park | 8562.17 | 9887.15 | In progress
C001 | Residential Building A | T222 | Site Survey | Emma White | Completed | High | 2023-08-24 | 2023-09-03 | 2023-09-03 | 100 | Steel Beams | Plot 21, Riverside | 36889.8 | 35608.87 | No issues
C001 | Residential Building A | T207 | Electrical Wiring | Rachel Green | Not Started | Medium | 2024-11-04 | 2024-12-03 |  | 0 | Copper Wires | Plot 21, Riverside | 9844.24 | 0 | Not started
C002 | Shopping Complex B | T294 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-05-25 | 2024-06-21 |  | 67 | PVC Pipes | Market Street | 17405.72 | 37420.07 | In progress
C002 | Shopping Complex B | T688 | Roofing | Dave Brown | In Progress | Medium | 2024-10-21 | 2024-11-17 |  | 87 | Concrete | Market Street | 25252.16 | 44589.79 | In progress
C001 | Residential Building A | T387 | Steel Framework Setup | Carlos Rivera | Completed | Low | 2023-04-27 | 2023-05-04 | 2023-05-04 | 100 | Cement | Plot 21, Riverside | 37034.7 | 33363.21 | No issues
C002 | Shopping Complex B | T874 | Foundation Excavation | Carlos Rivera | Blocked | High | 2023-09-21 | 2023-10-06 |  | 0 | Roofing Sheets | Market Street | 9852.03 | 33049.73 | Not started
C003 | Office Tower C | T290 | Interior Painting | Sarah Johnson | Completed | High | 2024-11-12 | 2024-12-11 | 2024-12-11 | 100 | Cement | Downtown Avenue | 27879.3 | 29744.69 | No issues
C003 | Office Tower C | T336 | Concrete Pouring | Sarah Johnson | Not Started | High | 2023-10-20 | 2023-11-13 |  | 0 | Copper Wires | Downtown Avenue | 7955.82 | 0 | Not started
C001 | Residential Building A | T332 | Roofing | Sarah Johnson | In Progress | High | 2024-11-20 | 2024-11-28 |  | 70 | Copper Wires | Plot 21, Riverside | 16267.32 | 18870.51 | In progress
C002 | Shopping Complex B | T461 | Plumbing Installations | Dave Brown | In Progress | Low | 2023-05-16 | 2023-06-06 |  | 36 | Copper Wires | Market Street | 10942.61 | 36766.76 | In progress
C001 | Residential Building A | T956 | Site Survey | Carlos Rivera | In Progress | Low | 2023-03-18 | 2023-04-17 |  | 5 | Steel Beams | Plot 21, Riverside | 9296.06 | 8516.57 | In progress
C002 | Shopping Complex B | T772 | Plumbing Installations | Sarah Johnson | Completed | Low | 2023-06-18 | 2023-07-18 | 2023-07-18 | 100 | Concrete | Market Street | 18715.89 | 43221.13 | No issues
C004 | Warehouse D | T720 | Steel Framework Setup | Emma White | Blocked | High | 2023-09-18 | 2023-09-26 |  | 0 | Paint | Industrial Park | 29671.76 | 26239.71 | Not started
C004 | Warehouse D | T429 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2024-05-06 | 2024-05-28 |  | 85 | Concrete | Industrial Park | 31235.76 | 30740.26 | In progress
C004 | Warehouse D | T880 | Concrete Pouring | Emma White | Completed | Medium | 2024-06-01 | 2024-06-09 | 2024-06-09 | 100 | Concrete | Industrial Park | 38947.13 | 36951.07 | No issues
C004 | Warehouse D | T977 | Interior Painting | Mike Adams | In Progress | Medium | 2023-10-26 | 2023-11-24 |  | 21 | PVC Pipes | Industrial Park | 32348 | 34950.16 | In progress
C001 | Residential Building A | T811 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-02-09 | 2024-03-04 |  | 0 | Concrete | Plot 21, Riverside | 14930.04 | 0 | Not started
C004 | Warehouse D | T174 | Electrical Wiring | Sarah Johnson | Completed | Low | 2023-03-21 | 2023-03-30 | 2023-03-30 | 100 | Copper Wires | Industrial Park | 27262.9 | 26071.32 | No issues
C002 | Shopping Complex B | T969 | Concrete Pouring | Grace Allen | Blocked | Medium | 2024-03-02 | 2024-03-15 |  | 0 | Rebar | Market Street | 7613.69 | 34497.38 | Not started
C001 | Residential Building A | T941 | Interior Painting | Carlos Rivera | Completed | Low | 2024-07-16 | 2024-07-23 | 2024-07-23 | 100 | Concrete | Plot 21, Riverside | 5969.26 | 6622.12 | No issues
C001 | Residential Building A | T761 | Roofing | Grace Allen | Completed | Low | 2023-03-25 | 2023-04-08 | 2023-04-08 | 100 | Concrete | Plot 21, Riverside | 9814.02 | 10631.98 | No issues
C001 | Residential Building A | T313 | Steel Framework Setup | Rachel Green | In Progress | High | 2024-03-19 | 2024-04-14 |  | 43 | Concrete | Plot 21, Riverside | 7681.11 | 5170.84 | In progress
C001 | Residential Building A | T743 | Concrete Pouring | Grace Allen | Blocked | High | 2024-08-06 | 2024-09-03 |  | 0 | Copper Wires | Plot 21, Riverside | 6765.72 | 4805.14 | Not started
C002 | Shopping Complex B | T702 | Roofing | Grace Allen | Blocked | Medium | 2023-05-22 | 2023-06-09 |  | 0 | Copper Wires | Market Street | 19700.34 | 43181.96 | Not started
C001 | Residential Building A | T294 | Plumbing Installations | Mike Adams | Not Started | High | 2023-11-21 | 2023-12-19 |  | 0 | Steel Beams | Plot 21, Riverside | 48671.19 | 0 | Not started
C003 | Office Tower C | T620 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-03-08 | 2024-03-29 |  | 0 | PVC Pipes | Downtown Avenue | 34212.06 | 21288.71 | Not started
C003 | Office Tower C | T676 | Plumbing Installations | Rachel Green | Completed | High | 2024-01-28 | 2024-02-06 | 2024-02-06 | 100 | Concrete | Downtown Avenue | 46033.88 | 33616.26 | No issues
C004 | Warehouse D | T793 | Roofing | Dave Brown | In Progress | Medium | 2024-08-04 | 2024-08-17 |  | 60 | Cement | Industrial Park | 5520.94 | 6270.73 | In progress
C004 | Warehouse D | T920 | Roofing | Sarah Johnson | In Progress | High | 2023-09-22 | 2023-10-07 |  | 17 | Rebar | Industrial Park | 10747.74 | 6543.08 | In progress
C002 | Shopping Complex B | T274 | Steel Framework Setup | Emma White | In Progress | Medium | 2024-07-04 | 2024-07-11 |  | 4 | PVC Pipes | Market Street | 48389.34 | 68824.9 | In progress
C001 | Residential Building A | T420 | Electrical Wiring | Rachel Green | In Progress | Low | 2024-08-20 | 2024-09-07 |  | 61 | Roofing Sheets | Plot 21, Riverside | 32073.03 | 33629.86 | In progress
C002 | Shopping Complex B | T446 | Roofing | Sarah Johnson | In Progress | Medium | 2024-11-03 | 2024-11-21 |  | 8 | Roofing Sheets | Market Street | 21339.67 | 38789.77 | In progress
C001 | Residential Building A | T840 | Site Survey | Dave Brown | Completed | Medium | 2024-04-14 | 2024-05-06 | 2024-05-06 | 100 | Rebar | Plot 21, Riverside | 24716.94 | 21893.86 | No issues
C001 | Residential Building A | T249 | Interior Painting | John Miller | Not Started | High | 2023-05-02 | 2023-05-13 |  | 0 | Concrete | Plot 21, Riverside | 38041.97 | 0 | Not started
C001 | Residential Building A | T746 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2024-01-28 | 2024-02-27 |  | 0 | Rebar | Plot 21, Riverside | 42386.88 | 33871.32 | Not started
C003 | Office Tower C | T178 | Plumbing Installations | Carlos Rivera | Not Started | Low | 2023-11-09 | 2023-12-09 |  | 0 | PVC Pipes | Downtown Avenue | 48423.07 | 0 | Not started
C003 | Office Tower C | T770 | Roofing | Carlos Rivera | Not Started | Medium | 2024-02-03 | 2024-02-20 |  | 0 | Roofing Sheets | Downtown Avenue | 35998.93 | 0 | Not started
C003 | Office Tower C | T285 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2024-12-11 | 2024-12-19 | 2024-12-19 | 100 | Rebar | Downtown Avenue | 25385.22 | 18525.04 | No issues
C001 | Residential Building A | T648 | Electrical Wiring | Grace Allen | In Progress | Low | 2023-10-17 | 2023-11-05 |  | 59 | Copper Wires | Plot 21, Riverside | 26652.94 | 23105.42 | In progress
C004 | Warehouse D | T971 | Foundation Excavation | Emma White | Completed | Medium | 2023-03-11 | 2023-03-19 | 2023-03-19 | 100 | Cement | Industrial Park | 8147.53 | 8075.87 | No issues
C001 | Residential Building A | T250 | Interior Painting | Carlos Rivera | Completed | Medium | 2023-04-07 | 2023-04-16 | 2023-04-16 | 100 | Roofing Sheets | Plot 21, Riverside | 49727.99 | 52681.45 | No issues
C002 | Shopping Complex B | T603 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2024-01-05 | 2024-01-19 |  | 0 | PVC Pipes | Market Street | 19352.14 | 0 | Not started
C003 | Office Tower C | T890 | Roofing | Dave Brown | Not Started | Low | 2023-11-04 | 2023-11-18 |  | 0 | PVC Pipes | Downtown Avenue | 23535.73 | 0 | Not started
C004 | Warehouse D | T309 | Interior Painting | Rachel Green | Not Started | High | 2024-05-12 | 2024-05-31 |  | 0 | Concrete | Industrial Park | 11246.26 | 0 | Not started
C003 | Office Tower C | T298 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-04-08 | 2024-05-02 |  | 69 | Rebar | Downtown Avenue | 11400.06 | 9161.65 | In progress
C001 | Residential Building A | T194 | Interior Painting | Rachel Green | In Progress | High | 2023-07-22 | 2023-08-19 |  | 74 | Roofing Sheets | Plot 21, Riverside | 11257.38 | 11439.18 | In progress
C003 | Office Tower C | T627 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-04-06 | 2023-05-02 |  | 50 | Copper Wires | Downtown Avenue | 38364.13 | 26416.88 | In progress
C004 | Warehouse D | T713 | Plumbing Installations | Mike Adams | Blocked | Low | 2024-11-17 | 2024-11-26 |  | 0 | Concrete | Industrial Park | 22809.18 | 19587.73 | Not started
C002 | Shopping Complex B | T795 | Interior Painting | Grace Allen | Not Started | Low | 2024-05-17 | 2024-05-26 |  | 0 | Paint | Market Street | 46986.15 | 0 | Not started
C004 | Warehouse D | T419 | Plumbing Installations | Rachel Green | Completed | Medium | 2023-06-10 | 2023-07-01 | 2023-07-01 | 100 | Paint | Industrial Park | 35940.74 | 26726.4 | No issues
C002 | Shopping Complex B | T417 | Electrical Wiring | John Miller | In Progress | High | 2023-02-21 | 2023-03-07 |  | 72 | Paint | Market Street | 42169.39 | 54154.41 | In progress
C004 | Warehouse D | T970 | Roofing | Carlos Rivera | Not Started | Medium | 2024-01-10 | 2024-01-19 |  | 0 | Roofing Sheets | Industrial Park | 47133.78 | 0 | Not started
C003 | Office Tower C | T701 | Foundation Excavation | John Miller | Completed | Low | 2024-10-02 | 2024-10-17 | 2024-10-17 | 100 | Copper Wires | Downtown Avenue | 41593.75 | 34716.81 | No issues
C004 | Warehouse D | T443 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-08-02 | 2023-08-16 |  | 12 | Concrete | Industrial Park | 5252.6 | 6188.34 | In progress
C001 | Residential Building A | T536 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-01-24 | 2023-02-18 |  | 0 | Rebar | Plot 21, Riverside | 49423.97 | 36621.35 | Not started
C004 | Warehouse D | T736 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2023-03-08 | 2023-03-15 |  | 0 | Copper Wires | Industrial Park | 28657.41 | 20340.5 | Not started
C003 | Office Tower C | T342 | Electrical Wiring | Mike Adams | Completed | High | 2024-02-09 | 2024-03-08 | 2024-03-08 | 100 | Paint | Downtown Avenue | 41324.86 | 44327.03 | No issues
C004 | Warehouse D | T753 | Steel Framework Setup | Emma White | Completed | High | 2024-09-23 | 2024-10-18 | 2024-10-18 | 100 | Rebar | Industrial Park | 23020.6 | 17587.7 | No issues
C004 | Warehouse D | T720 | Plumbing Installations | Dave Brown | Completed | High | 2024-02-09 | 2024-02-18 | 2024-02-18 | 100 | Cement | Industrial Park | 38517.07 | 23842.36 | No issues
C003 | Office Tower C | T436 | Site Survey | Emma White | In Progress | High | 2024-06-04 | 2024-06-25 |  | 93 | Cement | Downtown Avenue | 20263.48 | 19750.99 | In progress
C002 | Shopping Complex B | T102 | Roofing | John Miller | Blocked | High | 2024-02-02 | 2024-02-13 |  | 0 | Roofing Sheets | Market Street | 11681.49 | 39447.16 | Not started
C003 | Office Tower C | T985 | Concrete Pouring | Rachel Green | Not Started | Medium | 2023-03-21 | 2023-03-28 |  | 0 | Roofing Sheets | Downtown Avenue | 22342.79 | 0 | Not started
C001 | Residential Building A | T648 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2023-09-10 | 2023-09-23 |  | 0 | Cement | Plot 21, Riverside | 12140.94 | 0 | Not started
C001 | Residential Building A | T340 | Site Survey | Sarah Johnson | Completed | Low | 2023-02-15 | 2023-03-01 | 2023-03-01 | 100 | Rebar | Plot 21, Riverside | 25958.57 | 25903.9 | No issues
C002 | Shopping Complex B | T653 | Roofing | Grace Allen | In Progress | Medium | 2023-11-11 | 2023-11-21 |  | 51 | Cement | Market Street | 5415.46 | 31708.93 | In progress
C004 | Warehouse D | T386 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2023-01-15 | 2023-02-07 |  | 0 | Cement | Industrial Park | 18182.95 | 19190.62 | Not started
C003 | Office Tower C | T426 | Interior Painting | Carlos Rivera | In Progress | Low | 2024-07-12 | 2024-08-11 |  | 93 | Concrete | Downtown Avenue | 6190.07 | 3730.72 | In progress
C003 | Office Tower C | T307 | Foundation Excavation | Mike Adams | Completed | Low | 2023-02-27 | 2023-03-15 | 2023-03-15 | 100 | Roofing Sheets | Downtown Avenue | 8541.6 | 8436.68 | No issues
C001 | Residential Building A | T402 | Steel Framework Setup | Emma White | Not Started | Medium | 2024-10-25 | 2024-11-23 |  | 0 | Concrete | Plot 21, Riverside | 48862.6 | 0 | Not started
C002 | Shopping Complex B | T827 | Site Survey | Grace Allen | In Progress | Low | 2023-10-21 | 2023-11-10 |  | 45 | Steel Beams | Market Street | 13173.12 | 35002.14 | In progress
C004 | Warehouse D | T532 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-10-21 | 2024-11-14 |  | 0 | Roofing Sheets | Industrial Park | 40122.15 | 29827.52 | Not started
C004 | Warehouse D | T322 | Roofing | Emma White | Not Started | High | 2024-02-19 | 2024-03-20 |  | 0 | Steel Beams | Industrial Park | 16296.49 | 0 | Not started
C002 | Shopping Complex B | T832 | Electrical Wiring | Carlos Rivera | Completed | Low | 2024-05-12 | 2024-06-10 | 2024-06-10 | 100 | Rebar | Market Street | 20074.48 | 40147.23 | No issues
C002 | Shopping Complex B | T382 | Steel Framework Setup | John Miller | Blocked | Low | 2024-12-13 | 2024-12-23 |  | 0 | PVC Pipes | Market Street | 27711.63 | 45941.63 | Not started
C004 | Warehouse D | T719 | Interior Painting | Dave Brown | In Progress | Low | 2024-07-04 | 2024-07-17 |  | 50 | Cement | Industrial Park | 18031.56 | 14822.04 | In progress
C002 | Shopping Complex B | T110 | Steel Framework Setup | Mike Adams | Completed | Low | 2024-01-23 | 2024-02-05 | 2024-02-05 | 100 | Paint | Market Street | 23167.01 | 48210.02 | No issues
C003 | Office Tower C | T919 | Interior Painting | Emma White | Not Started | Medium | 2024-01-11 | 2024-02-06 |  | 0 | Roofing Sheets | Downtown Avenue | 30154.21 | 0 | Not started
C003 | Office Tower C | T277 | Interior Painting | John Miller | Not Started | Low | 2023-04-10 | 2023-04-24 |  | 0 | Roofing Sheets | Downtown Avenue | 31234.78 | 0 | Not started
C001 | Residential Building A | T484 | Roofing | John Miller | Completed | Medium | 2024-01-07 | 2024-01-26 | 2024-01-26 | 100 | Copper Wires | Plot 21, Riverside | 32897.49 | 29649.59 | No issues
C001 | Residential Building A | T115 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-07-24 | 2024-08-08 |  | 0 | Steel Beams | Plot 21, Riverside | 18476.92 | 0 | Not started
C003 | Office Tower C | T418 | Site Survey | Sarah Johnson | Completed | High | 2024-01-09 | 2024-02-02 | 2024-02-02 | 100 | PVC Pipes | Downtown Avenue | 47753.7 | 33690.77 | No issues
C001 | Residential Building A | T622 | Concrete Pouring | Grace Allen | Not Started | High | 2023-11-27 | 2023-12-05 |  | 0 | Cement | Plot 21, Riverside | 5714.92 | 0 | Not started
C003 | Office Tower C | T458 | Foundation Excavation | John Miller | Blocked | Low | 2023-12-16 | 2024-01-04 |  | 0 | PVC Pipes | Downtown Avenue | 45630.38 | 52979.28 | Not started
C002 | Shopping Complex B | T591 | Site Survey | John Miller | Blocked | Medium | 2024-08-07 | 2024-08-21 |  | 0 | Concrete | Market Street | 19748.97 | 41525.53 | Not started
C004 | Warehouse D | T432 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2023-12-20 | 2024-01-01 |  | 0 | Steel Beams | Industrial Park | 10437.63 | 7798.52 | Not started
C002 | Shopping Complex B | T907 | Electrical Wiring | Emma White | Not Started | Low | 2024-06-20 | 2024-07-01 |  | 0 | Cement | Market Street | 19619.82 | 0 | Not started
C001 | Residential Building A | T800 | Electrical Wiring | Grace Allen | Not Started | Low | 2024-11-10 | 2024-11-21 |  | 0 | Steel Beams | Plot 21, Riverside | 39693.7 | 0 | Not started
C003 | Office Tower C | T251 | Concrete Pouring | Sarah Johnson | Completed | Low | 2023-06-12 | 2023-06-23 | 2023-06-23 | 100 | Paint | Downtown Avenue | 36135.52 | 31128.94 | No issues
C004 | Warehouse D | T337 | Steel Framework Setup | Grace Allen | In Progress | Low | 2023-08-21 | 2023-09-12 |  | 64 | PVC Pipes | Industrial Park | 20353.31 | 20199.13 | In progress
C003 | Office Tower C | T872 | Foundation Excavation | Rachel Green | Not Started | Medium | 2024-10-11 | 2024-11-08 |  | 0 | Concrete | Downtown Avenue | 13208.65 | 0 | Not started
C002 | Shopping Complex B | T779 | Electrical Wiring | Emma White | In Progress | High | 2024-12-13 | 2024-12-20 |  | 67 | Rebar | Market Street | 36407.38 | 53114.4 | In progress
C002 | Shopping Complex B | T819 | Electrical Wiring | Carlos Rivera | In Progress | Medium | 2023-08-27 | 2023-09-26 |  | 99 | Paint | Market Street | 14863.33 | 35552.89 | In progress
C003 | Office Tower C | T307 | Concrete Pouring | Rachel Green | Completed | Low | 2024-04-07 | 2024-05-02 | 2024-05-02 | 100 | Roofing Sheets | Downtown Avenue | 42926.05 | 33033.46 | No issues
C004 | Warehouse D | T896 | Concrete Pouring | Sarah Johnson | Blocked | High | 2024-09-12 | 2024-10-05 |  | 0 | Concrete | Industrial Park | 32264.99 | 38187.44 | Not started
C002 | Shopping Complex B | T423 | Concrete Pouring | Emma White | Not Started | High | 2023-05-17 | 2023-06-02 |  | 0 | Rebar | Market Street | 15900.14 | 0 | Not started
C001 | Residential Building A | T268 | Roofing | Carlos Rivera | Blocked | High | 2024-09-19 | 2024-10-10 |  | 0 | Roofing Sheets | Plot 21, Riverside | 6340.56 | 5474.32 | Not started
C002 | Shopping Complex B | T545 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2024-09-21 | 2024-10-21 |  | 63 | Cement | Market Street | 28569.25 | 50506.14 | In progress
C001 | Residential Building A | T994 | Site Survey | Carlos Rivera | In Progress | High | 2023-07-02 | 2023-07-30 |  | 59 | Roofing Sheets | Plot 21, Riverside | 29994.11 | 20492.89 | In progress
C002 | Shopping Complex B | T782 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-04-28 | 2024-05-06 |  | 0 | Cement | Market Street | 44286.65 | 0 | Not started
C001 | Residential Building A | T205 | Steel Framework Setup | Emma White | In Progress | Low | 2024-10-21 | 2024-10-31 |  | 98 | Cement | Plot 21, Riverside | 24211.45 | 21210.18 | In progress
C002 | Shopping Complex B | T893 | Interior Painting | Rachel Green | Blocked | Low | 2024-09-19 | 2024-10-17 |  | 0 | Steel Beams | Market Street | 37260.47 | 69859.38 | Not started
C003 | Office Tower C | T893 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2023-05-27 | 2023-06-11 |  | 0 | Cement | Downtown Avenue | 6821.2 | 5563.69 | Not started
C003 | Office Tower C | T822 | Concrete Pouring | Mike Adams | Completed | Medium | 2023-07-16 | 2023-07-23 | 2023-07-23 | 100 | Steel Beams | Downtown Avenue | 9025.39 | 7823.73 | No issues
C003 | Office Tower C | T370 | Plumbing Installations | Grace Allen | Blocked | Medium | 2024-12-05 | 2024-12-20 |  | 0 | Rebar | Downtown Avenue | 29089.06 | 34288.93 | Not started
C002 | Shopping Complex B | T528 | Steel Framework Setup | Rachel Green | Blocked | High | 2023-10-06 | 2023-10-19 |  | 0 | Copper Wires | Market Street | 43595.41 | 58726.74 | Not started
C002 | Shopping Complex B | T897 | Concrete Pouring | John Miller | Not Started | Medium | 2023-06-14 | 2023-07-03 |  | 0 | Roofing Sheets | Market Street | 6904.57 | 0 | Not started
C003 | Office Tower C | T884 | Interior Painting | Mike Adams | Completed | Low | 2024-04-18 | 2024-05-10 | 2024-05-10 | 100 | Steel Beams | Downtown Avenue | 35018.28 | 41028.46 | No issues
C001 | Residential Building A | T655 | Roofing | Dave Brown | Completed | Medium | 2024-09-08 | 2024-09-25 | 2024-09-25 | 100 | Rebar | Plot 21, Riverside | 16664.28 | 19263.58 | No issues
C003 | Office Tower C | T481 | Site Survey | Grace Allen | In Progress | Medium | 2024-10-03 | 2024-10-12 |  | 59 | Concrete | Downtown Avenue | 17534.21 | 15566.63 | In progress
C002 | Shopping Complex B | T880 | Concrete Pouring | Emma White | Blocked | Low | 2024-09-26 | 2024-10-03 |  | 0 | PVC Pipes | Market Street | 38621.86 | 57812.7 | Not started
C001 | Residential Building A | T579 | Concrete Pouring | John Miller | Completed | High | 2024-11-19 | 2024-12-10 | 2024-12-10 | 100 | Steel Beams | Plot 21, Riverside | 14719.07 | 16915.08 | No issues
C004 | Warehouse D | T992 | Foundation Excavation | Dave Brown | Completed | Medium | 2024-10-12 | 2024-11-08 | 2024-11-08 | 100 | Rebar | Industrial Park | 43015.35 | 41845.85 | No issues
C002 | Shopping Complex B | T238 | Site Survey | Grace Allen | Completed | Medium | 2024-06-04 | 2024-06-19 | 2024-06-19 | 100 | Concrete | Market Street | 32236.65 | 50745.18 | No issues
C001 | Residential Building A | T397 | Site Survey | Dave Brown | In Progress | High | 2024-09-12 | 2024-10-09 |  | 82 | Steel Beams | Plot 21, Riverside | 8544.76 | 8157.32 | In progress
C003 | Office Tower C | T831 | Concrete Pouring | Mike Adams | Completed | Low | 2023-05-06 | 2023-05-25 | 2023-05-25 | 100 | Copper Wires | Downtown Avenue | 47552.31 | 31119.9 | No issues
C003 | Office Tower C | T381 | Steel Framework Setup | Emma White | Blocked | Medium | 2023-08-13 | 2023-09-06 |  | 0 | Cement | Downtown Avenue | 29948.62 | 18941.34 | Not started
C004 | Warehouse D | T951 | Concrete Pouring | Dave Brown | Blocked | High | 2024-02-18 | 2024-03-16 |  | 0 | Rebar | Industrial Park | 11781.34 | 13707.11 | Not started
C002 | Shopping Complex B | T559 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2023-11-08 | 2023-12-07 |  | 32 | Roofing Sheets | Market Street | 10439.72 | 35131.83 | In progress
C003 | Office Tower C | T116 | Site Survey | Dave Brown | Blocked | Low | 2024-10-15 | 2024-10-27 |  | 0 | Paint | Downtown Avenue | 33055.03 | 27279.85 | Not started
C004 | Warehouse D | T562 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-12-28 | 2024-01-18 |  | 0 | Roofing Sheets | Industrial Park | 49682.45 | 44971.47 | Not started
C001 | Residential Building A | T657 | Site Survey | Emma White | Blocked | Low | 2024-12-26 | 2025-01-16 |  | 0 | PVC Pipes | Plot 21, Riverside | 17642.57 | 19273.7 | Not started
C003 | Office Tower C | T975 | Foundation Excavation | John Miller | Completed | Low | 2023-09-25 | 2023-10-02 | 2023-10-02 | 100 | Rebar | Downtown Avenue | 49748.3 | 53654.61 | No issues
C004 | Warehouse D | T932 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2023-11-17 | 2023-12-10 |  | 33 | PVC Pipes | Industrial Park | 6909.76 | 6829.96 | In progress
C003 | Office Tower C | T890 | Interior Painting | Emma White | Completed | Low | 2023-09-08 | 2023-09-16 | 2023-09-16 | 100 | Paint | Downtown Avenue | 48677.22 | 43989.94 | No issues
C002 | Shopping Complex B | T455 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2024-09-15 | 2024-10-13 |  | 0 | Paint | Market Street | 6710.12 | 0 | Not started
C004 | Warehouse D | T296 | Roofing | Grace Allen | In Progress | High | 2024-02-13 | 2024-03-08 |  | 94 | Rebar | Industrial Park | 7536.57 | 7703.35 | In progress
C004 | Warehouse D | T421 | Interior Painting | Mike Adams | In Progress | High | 2023-01-16 | 2023-01-31 |  | 21 | Concrete | Industrial Park | 6630.9 | 5968.19 | In progress
C001 | Residential Building A | T290 | Roofing | Dave Brown | Completed | Medium | 2024-03-11 | 2024-03-31 | 2024-03-31 | 100 | Cement | Plot 21, Riverside | 44246.24 | 46090.82 | No issues
C001 | Residential Building A | T800 | Steel Framework Setup | Emma White | Not Started | High | 2024-10-16 | 2024-11-11 |  | 0 | Roofing Sheets | Plot 21, Riverside | 31473.29 | 0 | Not started
C004 | Warehouse D | T843 | Site Survey | Grace Allen | Blocked | Low | 2024-05-11 | 2024-05-26 |  | 0 | Cement | Industrial Park | 20288.02 | 18671.22 | Not started
C002 | Shopping Complex B | T217 | Electrical Wiring | John Miller | Completed | Low | 2024-07-02 | 2024-07-12 | 2024-07-12 | 100 | Rebar | Market Street | 9402.36 | 32967.62 | No issues
C004 | Warehouse D | T114 | Interior Painting | John Miller | Completed | High | 2023-12-04 | 2024-01-02 | 2024-01-02 | 100 | Copper Wires | Industrial Park | 10940.24 | 12072.43 | No issues
C004 | Warehouse D | T693 | Roofing | John Miller | In Progress | Medium | 2023-11-17 | 2023-12-09 |  | 48 | Paint | Industrial Park | 26298.79 | 25920.64 | In progress
C002 | Shopping Complex B | T302 | Interior Painting | Sarah Johnson | Completed | High | 2023-12-23 | 2024-01-08 | 2024-01-08 | 100 | Steel Beams | Market Street | 37121.81 | 51567.02 | No issues
C004 | Warehouse D | T922 | Plumbing Installations | Emma White | Blocked | High | 2024-12-01 | 2024-12-22 |  | 0 | Paint | Industrial Park | 46341.5 | 37729.66 | Not started
C004 | Warehouse D | T971 | Plumbing Installations | Grace Allen | Completed | Low | 2023-10-04 | 2023-10-31 | 2023-10-31 | 100 | Steel Beams | Industrial Park | 33960.42 | 38319.86 | No issues
C004 | Warehouse D | T571 | Plumbing Installations | Carlos Rivera | Not Started | Medium | 2023-09-08 | 2023-09-30 |  | 0 | Roofing Sheets | Industrial Park | 12289.4 | 0 | Not started
C004 | Warehouse D | T174 | Plumbing Installations | Grace Allen | Completed | Medium | 2023-05-25 | 2023-06-13 | 2023-06-13 | 100 | Concrete | Industrial Park | 5964.92 | 5488.59 | No issues
C003 | Office Tower C | T228 | Electrical Wiring | Grace Allen | In Progress | Low | 2023-05-23 | 2023-06-15 |  | 2 | Roofing Sheets | Downtown Avenue | 21990.14 | 18025.05 | In progress
C003 | Office Tower C | T680 | Roofing | Mike Adams | Completed | Low | 2023-09-17 | 2023-10-08 | 2023-10-08 | 100 | Copper Wires | Downtown Avenue | 32636.94 | 22669.15 | No issues
C004 | Warehouse D | T746 | Interior Painting | Mike Adams | Completed | Low | 2023-12-28 | 2024-01-18 | 2024-01-18 | 100 | Cement | Industrial Park | 25153.84 | 22798.72 | No issues
C004 | Warehouse D | T675 | Concrete Pouring | Rachel Green | Completed | High | 2024-03-05 | 2024-03-12 | 2024-03-12 | 100 | Concrete | Industrial Park | 33429.47 | 29697.71 | No issues
C001 | Residential Building A | T528 | Roofing | Grace Allen | Blocked | Medium | 2024-12-06 | 2024-12-26 |  | 0 | Concrete | Plot 21, Riverside | 49522.57 | 42647.52 | Not started
C003 | Office Tower C | T840 | Interior Painting | Grace Allen | In Progress | Medium | 2024-08-05 | 2024-08-14 |  | 23 | Paint | Downtown Avenue | 35158.79 | 27787.95 | In progress
C002 | Shopping Complex B | T511 | Plumbing Installations | Grace Allen | In Progress | Low | 2023-07-07 | 2023-07-30 |  | 97 | Concrete | Market Street | 20887.99 | 41371.56 | In progress
C003 | Office Tower C | T742 | Electrical Wiring | Grace Allen | Not Started | High | 2023-08-04 | 2023-08-29 |  | 0 | Copper Wires | Downtown Avenue | 26673.67 | 0 | Not started
C003 | Office Tower C | T510 | Steel Framework Setup | Carlos Rivera | Blocked | Medium | 2024-04-28 | 2024-05-20 |  | 0 | Copper Wires | Downtown Avenue | 37970.14 | 25674.36 | Not started
C003 | Office Tower C | T546 | Concrete Pouring | Dave Brown | Blocked | Low | 2024-02-14 | 2024-03-12 |  | 0 | Roofing Sheets | Downtown Avenue | 18656.46 | 20688.12 | Not started
C003 | Office Tower C | T582 | Interior Painting | Rachel Green | Blocked | High | 2023-12-13 | 2023-12-29 |  | 0 | Cement | Downtown Avenue | 30051.37 | 31228.19 | Not started
C002 | Shopping Complex B | T419 | Interior Painting | Rachel Green | Not Started | High | 2024-10-11 | 2024-10-23 |  | 0 | Roofing Sheets | Market Street | 46461.82 | 0 | Not started
C001 | Residential Building A | T736 | Foundation Excavation | Dave Brown | In Progress | Low | 2023-02-16 | 2023-02-25 |  | 6 | Concrete | Plot 21, Riverside | 8518.7 | 9172.13 | In progress
C003 | Office Tower C | T984 | Foundation Excavation | Rachel Green | Not Started | High | 2023-08-18 | 2023-09-03 |  | 0 | Rebar | Downtown Avenue | 43906.54 | 0 | Not started
C004 | Warehouse D | T888 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2024-07-17 | 2024-08-14 |  | 0 | Steel Beams | Industrial Park | 49171.7 | 0 | Not started
C004 | Warehouse D | T300 | Steel Framework Setup | Grace Allen | In Progress | High | 2024-05-25 | 2024-06-02 |  | 49 | Steel Beams | Industrial Park | 10875.52 | 10272.59 | In progress
C004 | Warehouse D | T978 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-11-13 | 2024-12-06 |  | 0 | Rebar | Industrial Park | 39913.23 | 0 | Not started
C003 | Office Tower C | T145 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-03-27 | 2024-04-16 |  | 0 | Rebar | Downtown Avenue | 34669.83 | 0 | Not started
C002 | Shopping Complex B | T481 | Site Survey | Grace Allen | Not Started | Low | 2023-07-08 | 2023-07-29 |  | 0 | Rebar | Market Street | 27513.31 | 0 | Not started
C001 | Residential Building A | T669 | Interior Painting | John Miller | Completed | High | 2024-09-19 | 2024-10-03 | 2024-10-03 | 100 | Copper Wires | Plot 21, Riverside | 33674.25 | 32985.72 | No issues
C003 | Office Tower C | T841 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2024-12-26 | 2025-01-18 |  | 0 | PVC Pipes | Downtown Avenue | 24368.2 | 20501.28 | Not started
C003 | Office Tower C | T679 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-04-24 | 2024-05-02 |  | 0 | Copper Wires | Downtown Avenue | 7547.19 | 0 | Not started
C004 | Warehouse D | T582 | Plumbing Installations | Rachel Green | Completed | High | 2024-02-22 | 2024-03-07 | 2024-03-07 | 100 | Cement | Industrial Park | 43531.39 | 43951.18 | No issues
C001 | Residential Building A | T899 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2024-03-26 | 2024-04-02 |  | 0 | Paint | Plot 21, Riverside | 10047.48 | 0 | Not started
C001 | Residential Building A | T663 | Electrical Wiring | Dave Brown | In Progress | Medium | 2023-02-24 | 2023-03-24 |  | 88 | Cement | Plot 21, Riverside | 16469.6 | 13553.23 | In progress
C003 | Office Tower C | T584 | Plumbing Installations | Emma White | Completed | Medium | 2023-04-18 | 2023-05-07 | 2023-05-07 | 100 | Steel Beams | Downtown Avenue | 35845.76 | 40412.77 | No issues
C002 | Shopping Complex B | T910 | Site Survey | John Miller | Not Started | Low | 2023-11-09 | 2023-11-25 |  | 0 | Copper Wires | Market Street | 6870.9 | 0 | Not started
C001 | Residential Building A | T743 | Foundation Excavation | Grace Allen | Not Started | Low | 2023-08-18 | 2023-09-17 |  | 0 | PVC Pipes | Plot 21, Riverside | 25347.75 | 0 | Not started
C001 | Residential Building A | T208 | Electrical Wiring | Mike Adams | In Progress | High | 2023-08-02 | 2023-09-01 |  | 94 | Rebar | Plot 21, Riverside | 26307.7 | 29335.96 | In progress
C001 | Residential Building A | T373 | Steel Framework Setup | Emma White | In Progress | Low | 2023-01-10 | 2023-02-09 |  | 36 | Concrete | Plot 21, Riverside | 13653.36 | 14879.28 | In progress
C003 | Office Tower C | T269 | Concrete Pouring | Carlos Rivera | Blocked | High | 2023-09-11 | 2023-10-04 |  | 0 | Paint | Downtown Avenue | 44915.1 | 29305.84 | Not started
C004 | Warehouse D | T881 | Plumbing Installations | John Miller | In Progress | High | 2023-05-01 | 2023-05-26 |  | 51 | Copper Wires | Industrial Park | 7341.28 | 7259.4 | In progress
C001 | Residential Building A | T143 | Concrete Pouring | Carlos Rivera | Blocked | High | 2023-02-22 | 2023-03-03 |  | 0 | Cement | Plot 21, Riverside | 48329.31 | 39937.82 | Not started
C002 | Shopping Complex B | T901 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-11-02 | 2023-11-22 |  | 0 | Rebar | Market Street | 32363.2 | 51191.87 | Not started
C004 | Warehouse D | T522 | Electrical Wiring | Emma White | Completed | High | 2023-07-26 | 2023-08-17 | 2023-08-17 | 100 | Concrete | Industrial Park | 6623.14 | 6829.58 | No issues
C004 | Warehouse D | T231 | Foundation Excavation | Sarah Johnson | Blocked | High | 2024-09-01 | 2024-09-25 |  | 0 | Roofing Sheets | Industrial Park | 7098.89 | 5623.72 | Not started
C001 | Residential Building A | T856 | Plumbing Installations | Rachel Green | Completed | High | 2023-09-08 | 2023-09-17 | 2023-09-17 | 100 | Cement | Plot 21, Riverside | 13980.91 | 8664.48 | No issues
C003 | Office Tower C | T836 | Interior Painting | Sarah Johnson | In Progress | Medium | 2023-07-10 | 2023-08-09 |  | 8 | PVC Pipes | Downtown Avenue | 22118.9 | 22147.95 | In progress
C002 | Shopping Complex B | T415 | Plumbing Installations | Sarah Johnson | In Progress | Medium | 2024-03-26 | 2024-04-04 |  | 89 | Cement | Market Street | 43407.52 | 53034.76 | In progress
C002 | Shopping Complex B | T179 | Electrical Wiring | Dave Brown | Completed | High | 2023-04-07 | 2023-04-18 | 2023-04-18 | 100 | Paint | Market Street | 37558.38 | 68922.22 | No issues
C001 | Residential Building A | T388 | Plumbing Installations | Mike Adams | In Progress | Medium | 2023-09-25 | 2023-10-24 |  | 22 | Cement | Plot 21, Riverside | 48101.38 | 50695.99 | In progress
C002 | Shopping Complex B | T871 | Plumbing Installations | Rachel Green | Blocked | High | 2023-10-26 | 2023-11-23 |  | 0 | Roofing Sheets | Market Street | 19284.24 | 38342 | Not started
C004 | Warehouse D | T212 | Site Survey | John Miller | Blocked | Medium | 2023-08-02 | 2023-08-30 |  | 0 | Rebar | Industrial Park | 44569.17 | 38053.3 | Not started
C004 | Warehouse D | T489 | Concrete Pouring | Dave Brown | Not Started | High | 2024-01-11 | 2024-02-07 |  | 0 | PVC Pipes | Industrial Park | 22871.1 | 0 | Not started
C003 | Office Tower C | T790 | Concrete Pouring | Rachel Green | Completed | High | 2023-05-02 | 2023-05-30 | 2023-05-30 | 100 | Cement | Downtown Avenue | 7658.36 | 8986.23 | No issues
C001 | Residential Building A | T209 | Concrete Pouring | Emma White | Not Started | Medium | 2024-03-04 | 2024-03-24 |  | 0 | PVC Pipes | Plot 21, Riverside | 18723.28 | 0 | Not started
C004 | Warehouse D | T763 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2024-01-02 | 2024-01-09 |  | 56 | Paint | Industrial Park | 13883.68 | 10722.99 | In progress
C004 | Warehouse D | T386 | Site Survey | Carlos Rivera | Not Started | High | 2023-03-13 | 2023-03-20 |  | 0 | Concrete | Industrial Park | 45796.26 | 0 | Not started
C002 | Shopping Complex B | T590 | Site Survey | Sarah Johnson | Not Started | Medium | 2024-10-23 | 2024-11-15 |  | 0 | Roofing Sheets | Market Street | 42638.09 | 0 | Not started
C001 | Residential Building A | T419 | Plumbing Installations | Dave Brown | Completed | Low | 2023-02-20 | 2023-03-02 | 2023-03-02 | 100 | Paint | Plot 21, Riverside | 14732.44 | 14400.19 | No issues
C003 | Office Tower C | T140 | Site Survey | Carlos Rivera | Completed | Low | 2024-11-08 | 2024-11-30 | 2024-11-30 | 100 | Roofing Sheets | Downtown Avenue | 29730.22 | 18413.56 | No issues
C001 | Residential Building A | T983 | Site Survey | Grace Allen | Blocked | High | 2024-12-20 | 2025-01-02 |  | 0 | Cement | Plot 21, Riverside | 40203.44 | 47338.28 | Not started
C002 | Shopping Complex B | T544 | Steel Framework Setup | Rachel Green | Completed | High | 2023-11-12 | 2023-12-01 | 2023-12-01 | 100 | Paint | Market Street | 30898.7 | 57811.81 | No issues
C002 | Shopping Complex B | T927 | Foundation Excavation | John Miller | Not Started | Low | 2024-09-18 | 2024-10-01 |  | 0 | Roofing Sheets | Market Street | 40709.25 | 0 | Not started
C001 | Residential Building A | T463 | Electrical Wiring | John Miller | Blocked | High | 2023-09-04 | 2023-09-20 |  | 0 | Concrete | Plot 21, Riverside | 14642.18 | 10876.92 | Not started
C003 | Office Tower C | T586 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2023-05-02 | 2023-05-10 |  | 0 | Paint | Downtown Avenue | 45048.03 | 51963.05 | Not started
C002 | Shopping Complex B | T130 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-03-10 | 2024-03-21 |  | 0 | Roofing Sheets | Market Street | 30084.11 | 48662.06 | Not started
C002 | Shopping Complex B | T973 | Concrete Pouring | Dave Brown | Completed | Low | 2024-07-19 | 2024-08-12 | 2024-08-12 | 100 | Steel Beams | Market Street | 31226.77 | 59369.45 | No issues
C001 | Residential Building A | T688 | Concrete Pouring | John Miller | Blocked | High | 2024-06-27 | 2024-07-04 |  | 0 | Roofing Sheets | Plot 21, Riverside | 46829.54 | 34689.03 | Not started
C002 | Shopping Complex B | T770 | Electrical Wiring | Mike Adams | Blocked | Low | 2023-10-13 | 2023-11-12 |  | 0 | Copper Wires | Market Street | 13555.38 | 39036.74 | Not started
C004 | Warehouse D | T716 | Steel Framework Setup | Rachel Green | Completed | Low | 2023-08-07 | 2023-09-05 | 2023-09-05 | 100 | Rebar | Industrial Park | 21490 | 22885.28 | No issues
C004 | Warehouse D | T522 | Plumbing Installations | Rachel Green | Blocked | Low | 2023-04-02 | 2023-04-14 |  | 0 | Concrete | Industrial Park | 7660.99 | 7405.19 | Not started
C001 | Residential Building A | T437 | Concrete Pouring | Mike Adams | Completed | Medium | 2023-09-08 | 2023-10-08 | 2023-10-08 | 100 | Copper Wires | Plot 21, Riverside | 14072.02 | 14572.58 | No issues
C004 | Warehouse D | T168 | Concrete Pouring | Rachel Green | Completed | Low | 2023-04-18 | 2023-05-07 | 2023-05-07 | 100 | Rebar | Industrial Park | 10224.9 | 11854.29 | No issues
C003 | Office Tower C | T835 | Concrete Pouring | Grace Allen | In Progress | High | 2023-05-09 | 2023-05-23 |  | 48 | Concrete | Downtown Avenue | 44535.7 | 39663.83 | In progress
C002 | Shopping Complex B | T597 | Interior Painting | Carlos Rivera | In Progress | Low | 2024-05-06 | 2024-05-13 |  | 36 | Copper Wires | Market Street | 38599.1 | 62390.29 | In progress
C003 | Office Tower C | T609 | Site Survey | Grace Allen | Completed | Low | 2024-01-11 | 2024-02-01 | 2024-02-01 | 100 | Roofing Sheets | Downtown Avenue | 45888.81 | 37796.5 | No issues
C001 | Residential Building A | T693 | Electrical Wiring | Sarah Johnson | Completed | Low | 2023-09-26 | 2023-10-22 | 2023-10-22 | 100 | Steel Beams | Plot 21, Riverside | 44575.45 | 51075.76 | No issues
C002 | Shopping Complex B | T135 | Electrical Wiring | Emma White | In Progress | Low | 2023-10-05 | 2023-10-12 |  | 49 | Steel Beams | Market Street | 5153.16 | 31033.18 | In progress
C004 | Warehouse D | T583 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-01-12 | 2023-01-21 |  | 0 | Cement | Industrial Park | 39563.66 | 0 | Not started
C001 | Residential Building A | T956 | Concrete Pouring | Mike Adams | Blocked | Medium | 2023-10-04 | 2023-10-12 |  | 0 | Rebar | Plot 21, Riverside | 26038.88 | 27958.78 | Not started
C004 | Warehouse D | T206 | Plumbing Installations | Emma White | Completed | Low | 2023-12-20 | 2024-01-18 | 2024-01-18 | 100 | Steel Beams | Industrial Park | 36956.89 | 23912.46 | No issues
C004 | Warehouse D | T805 | Interior Painting | Emma White | In Progress | Medium | 2023-09-13 | 2023-10-07 |  | 86 | Concrete | Industrial Park | 46576.65 | 29433.34 | In progress
C004 | Warehouse D | T960 | Roofing | John Miller | Not Started | Low | 2023-02-01 | 2023-03-03 |  | 0 | Rebar | Industrial Park | 17547.02 | 0 | Not started
C001 | Residential Building A | T583 | Site Survey | Grace Allen | Completed | Low | 2023-05-16 | 2023-05-29 | 2023-05-29 | 100 | PVC Pipes | Plot 21, Riverside | 21302.75 | 23947.04 | No issues
C004 | Warehouse D | T470 | Concrete Pouring | John Miller | Completed | Low | 2023-01-03 | 2023-01-22 | 2023-01-22 | 100 | Steel Beams | Industrial Park | 37915.69 | 40922.51 | No issues
C003 | Office Tower C | T158 | Roofing | Carlos Rivera | Completed | Low | 2023-09-13 | 2023-09-27 | 2023-09-27 | 100 | PVC Pipes | Downtown Avenue | 11511.1 | 11941.35 | No issues
C001 | Residential Building A | T163 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-11-22 | 2024-12-21 | 2024-12-21 | 100 | Cement | Plot 21, Riverside | 9313.28 | 9770.37 | No issues
C003 | Office Tower C | T132 | Interior Painting | John Miller | Completed | Medium | 2023-06-19 | 2023-07-03 | 2023-07-03 | 100 | Rebar | Downtown Avenue | 35788.71 | 23481.24 | No issues
C002 | Shopping Complex B | T455 | Plumbing Installations | John Miller | Not Started | High | 2023-01-12 | 2023-01-23 |  | 0 | Concrete | Market Street | 31605.44 | 0 | Not started
C004 | Warehouse D | T213 | Roofing | Rachel Green | Not Started | Medium | 2023-11-07 | 2023-11-22 |  | 0 | Cement | Industrial Park | 16193.67 | 0 | Not started
C003 | Office Tower C | T603 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-02-18 | 2023-03-16 |  | 0 | Rebar | Downtown Avenue | 23079.78 | 25459.05 | Not started
C003 | Office Tower C | T740 | Interior Painting | Rachel Green | Blocked | Low | 2024-08-20 | 2024-09-08 |  | 0 | Concrete | Downtown Avenue | 5354.25 | 5612.23 | Not started
C001 | Residential Building A | T932 | Steel Framework Setup | Dave Brown | Completed | Low | 2024-01-24 | 2024-02-11 | 2024-02-11 | 100 | Roofing Sheets | Plot 21, Riverside | 34112.91 | 23591.86 | No issues
C001 | Residential Building A | T358 | Electrical Wiring | John Miller | Blocked | Medium | 2023-02-01 | 2023-02-19 |  | 0 | Cement | Plot 21, Riverside | 7854.78 | 9039.88 | Not started
C002 | Shopping Complex B | T138 | Plumbing Installations | Dave Brown | Not Started | Medium | 2023-07-16 | 2023-08-11 |  | 0 | PVC Pipes | Market Street | 42630.38 | 0 | Not started
C003 | Office Tower C | T420 | Interior Painting | Rachel Green | Blocked | High | 2023-10-25 | 2023-11-19 |  | 0 | Cement | Downtown Avenue | 27121.82 | 31942.02 | Not started
C001 | Residential Building A | T356 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-02-10 | 2023-02-24 |  | 0 | Steel Beams | Plot 21, Riverside | 14068.61 | 0 | Not started
C003 | Office Tower C | T892 | Electrical Wiring | Sarah Johnson | In Progress | High | 2023-06-22 | 2023-07-01 |  | 78 | Concrete | Downtown Avenue | 10443.69 | 6675.43 | In progress
C002 | Shopping Complex B | T875 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-07-16 | 2023-08-05 |  | 0 | Steel Beams | Market Street | 34959.12 | 46679.95 | Not started
C001 | Residential Building A | T545 | Roofing | Carlos Rivera | In Progress | High | 2023-09-24 | 2023-10-12 |  | 41 | Cement | Plot 21, Riverside | 13199.07 | 13409.68 | In progress
C004 | Warehouse D | T373 | Interior Painting | Emma White | In Progress | High | 2024-02-01 | 2024-03-02 |  | 49 | PVC Pipes | Industrial Park | 5813.85 | 4909.74 | In progress
C001 | Residential Building A | T383 | Steel Framework Setup | John Miller | Not Started | High | 2023-10-22 | 2023-10-31 |  | 0 | Roofing Sheets | Plot 21, Riverside | 39942.36 | 0 | Not started
C004 | Warehouse D | T265 | Concrete Pouring | Dave Brown | In Progress | Medium | 2023-12-13 | 2024-01-12 |  | 5 | Roofing Sheets | Industrial Park | 43462.86 | 28720.77 | In progress
C003 | Office Tower C | T779 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-08-23 | 2024-09-01 |  | 0 | Concrete | Downtown Avenue | 38594.76 | 27974.29 | Not started
C002 | Shopping Complex B | T576 | Foundation Excavation | Mike Adams | Not Started | High | 2024-07-13 | 2024-07-26 |  | 0 | PVC Pipes | Market Street | 5369.27 | 0 | Not started
C002 | Shopping Complex B | T834 | Roofing | Sarah Johnson | Not Started | High | 2023-12-19 | 2024-01-11 |  | 0 | Copper Wires | Market Street | 34913.29 | 0 | Not started
C002 | Shopping Complex B | T269 | Interior Painting | Mike Adams | Completed | Medium | 2023-09-09 | 2023-10-09 | 2023-10-09 | 100 | Rebar | Market Street | 45892.26 | 66374.97 | No issues
C002 | Shopping Complex B | T636 | Foundation Excavation | Grace Allen | Completed | Medium | 2024-01-16 | 2024-02-04 | 2024-02-04 | 100 | Steel Beams | Market Street | 41060.82 | 51078.62 | No issues
C003 | Office Tower C | T468 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-03-09 | 2023-04-02 |  | 0 | Roofing Sheets | Downtown Avenue | 29469.88 | 0 | Not started
C002 | Shopping Complex B | T930 | Concrete Pouring | Mike Adams | Blocked | Low | 2023-07-03 | 2023-07-10 |  | 0 | Concrete | Market Street | 28116.8 | 46511.49 | Not started
C004 | Warehouse D | T324 | Roofing | Emma White | Blocked | High | 2024-10-11 | 2024-10-29 |  | 0 | Cement | Industrial Park | 6128.8 | 6830.1 | Not started
C001 | Residential Building A | T895 | Foundation Excavation | Rachel Green | Completed | High | 2024-10-11 | 2024-10-22 | 2024-10-22 | 100 | Cement | Plot 21, Riverside | 35953.48 | 36590.91 | No issues
C004 | Warehouse D | T647 | Interior Painting | Mike Adams | Not Started | Low | 2023-01-23 | 2023-02-12 |  | 0 | PVC Pipes | Industrial Park | 13564.74 | 0 | Not started
C003 | Office Tower C | T863 | Concrete Pouring | Emma White | Not Started | High | 2023-06-28 | 2023-07-06 |  | 0 | PVC Pipes | Downtown Avenue | 42300.31 | 0 | Not started
C003 | Office Tower C | T366 | Interior Painting | Grace Allen | Blocked | High | 2024-09-06 | 2024-09-24 |  | 0 | Paint | Downtown Avenue | 29250.82 | 23406.66 | Not started
C004 | Warehouse D | T385 | Site Survey | Rachel Green | Blocked | Low | 2023-03-01 | 2023-03-30 |  | 0 | PVC Pipes | Industrial Park | 24430.81 | 20052.13 | Not started
C004 | Warehouse D | T112 | Electrical Wiring | Mike Adams | In Progress | Medium | 2024-08-16 | 2024-08-28 |  | 95 | Paint | Industrial Park | 42367.92 | 33914.61 | In progress
C001 | Residential Building A | T380 | Roofing | John Miller | Not Started | High | 2023-10-20 | 2023-11-04 |  | 0 | Copper Wires | Plot 21, Riverside | 23623.29 | 0 | Not started
C001 | Residential Building A | T580 | Interior Painting | Dave Brown | Not Started | High | 2023-09-19 | 2023-10-08 |  | 0 | Copper Wires | Plot 21, Riverside | 42853.93 | 0 | Not started
C002 | Shopping Complex B | T360 | Interior Painting | Sarah Johnson | Blocked | Low | 2023-02-08 | 2023-02-17 |  | 0 | Cement | Market Street | 11624.4 | 36675.63 | Not started
C003 | Office Tower C | T941 | Concrete Pouring | Carlos Rivera | Blocked | Low | 2023-10-18 | 2023-11-07 |  | 0 | Rebar | Downtown Avenue | 49693.57 | 34732.45 | Not started
C001 | Residential Building A | T448 | Roofing | Mike Adams | Blocked | High | 2023-09-25 | 2023-10-12 |  | 0 | Cement | Plot 21, Riverside | 40795.32 | 30864.98 | Not started
C004 | Warehouse D | T489 | Plumbing Installations | Emma White | In Progress | Medium | 2024-06-26 | 2024-07-08 |  | 55 | Paint | Industrial Park | 48773.78 | 31047.07 | In progress
C002 | Shopping Complex B | T154 | Roofing | John Miller | Blocked | Low | 2024-01-04 | 2024-01-21 |  | 0 | Copper Wires | Market Street | 40199.02 | 71360.73 | Not started
C002 | Shopping Complex B | T677 | Steel Framework Setup | Sarah Johnson | Completed | Low | 2024-07-14 | 2024-07-30 | 2024-07-30 | 100 | Steel Beams | Market Street | 40242.73 | 55183.42 | No issues
C001 | Residential Building A | T388 | Plumbing Installations | Emma White | Completed | Low | 2023-10-06 | 2023-10-19 | 2023-10-19 | 100 | Paint | Plot 21, Riverside | 47408.06 | 50533.19 | No issues
C001 | Residential Building A | T893 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-05-17 | 2024-06-12 |  | 0 | Concrete | Plot 21, Riverside | 36364.48 | 30572.37 | Not started
C003 | Office Tower C | T600 | Interior Painting | Mike Adams | Not Started | Medium | 2024-05-07 | 2024-05-18 |  | 0 | Steel Beams | Downtown Avenue | 21327.72 | 0 | Not started
C003 | Office Tower C | T496 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2023-08-01 | 2023-08-26 |  | 75 | Cement | Downtown Avenue | 34618.5 | 40516.07 | In progress
C002 | Shopping Complex B | T130 | Roofing | Rachel Green | Not Started | Medium | 2023-03-28 | 2023-04-22 |  | 0 | Copper Wires | Market Street | 30151.62 | 0 | Not started
C001 | Residential Building A | T963 | Site Survey | Grace Allen | Completed | Medium | 2024-07-24 | 2024-08-15 | 2024-08-15 | 100 | PVC Pipes | Plot 21, Riverside | 24083.54 | 22410.51 | No issues
C001 | Residential Building A | T836 | Interior Painting | Rachel Green | Completed | Low | 2023-11-02 | 2023-11-20 | 2023-11-20 | 100 | Concrete | Plot 21, Riverside | 15530.76 | 18566.57 | No issues
C002 | Shopping Complex B | T653 | Roofing | Dave Brown | Blocked | Medium | 2024-08-20 | 2024-09-17 |  | 0 | Concrete | Market Street | 31800.96 | 48064.21 | Not started
C003 | Office Tower C | T373 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2023-05-25 | 2023-06-12 | 2023-06-12 | 100 | PVC Pipes | Downtown Avenue | 17738.31 | 21063.24 | No issues
C004 | Warehouse D | T140 | Steel Framework Setup | Emma White | Completed | Medium | 2024-12-28 | 2025-01-11 | 2025-01-11 | 100 | PVC Pipes | Industrial Park | 9307.9 | 9481.42 | No issues
C002 | Shopping Complex B | T756 | Plumbing Installations | Rachel Green | Completed | High | 2023-01-23 | 2023-02-06 | 2023-02-06 | 100 | Concrete | Market Street | 5586.98 | 31145.99 | No issues
C002 | Shopping Complex B | T915 | Roofing | Emma White | In Progress | Medium | 2023-07-25 | 2023-08-22 |  | 8 | Copper Wires | Market Street | 35367.07 | 54422.51 | In progress
C001 | Residential Building A | T590 | Interior Painting | Dave Brown | Not Started | High | 2024-04-28 | 2024-05-09 |  | 0 | Steel Beams | Plot 21, Riverside | 27448.11 | 0 | Not started
C003 | Office Tower C | T654 | Interior Painting | John Miller | Blocked | High | 2024-06-08 | 2024-07-04 |  | 0 | Roofing Sheets | Downtown Avenue | 48943.13 | 48615.55 | Not started
C002 | Shopping Complex B | T387 | Concrete Pouring | John Miller | In Progress | High | 2024-02-10 | 2024-02-27 |  | 73 | PVC Pipes | Market Street | 26087 | 55319.52 | In progress
C004 | Warehouse D | T982 | Site Survey | Sarah Johnson | Not Started | High | 2023-01-20 | 2023-02-03 |  | 0 | Copper Wires | Industrial Park | 16662.43 | 0 | Not started
C002 | Shopping Complex B | T394 | Concrete Pouring | Emma White | Completed | High | 2024-04-04 | 2024-04-14 | 2024-04-14 | 100 | Copper Wires | Market Street | 6466.34 | 32625 | No issues
C003 | Office Tower C | T235 | Site Survey | Rachel Green | Not Started | Medium | 2023-08-08 | 2023-08-27 |  | 0 | Rebar | Downtown Avenue | 18877.29 | 0 | Not started
C003 | Office Tower C | T498 | Site Survey | Dave Brown | Not Started | Low | 2024-05-16 | 2024-06-14 |  | 0 | Paint | Downtown Avenue | 5428.42 | 0 | Not started
C003 | Office Tower C | T328 | Steel Framework Setup | John Miller | In Progress | Medium | 2023-07-21 | 2023-08-20 |  | 31 | Rebar | Downtown Avenue | 10256.58 | 9771.05 | In progress
C002 | Shopping Complex B | T875 | Interior Painting | John Miller | In Progress | High | 2023-11-25 | 2023-12-06 |  | 4 | Rebar | Market Street | 18170.32 | 45992.25 | In progress
C002 | Shopping Complex B | T650 | Electrical Wiring | Carlos Rivera | Not Started | High | 2024-03-18 | 2024-04-14 |  | 0 | Paint | Market Street | 21724.86 | 0 | Not started
C001 | Residential Building A | T538 | Site Survey | Emma White | Not Started | High | 2024-03-21 | 2024-04-17 |  | 0 | Cement | Plot 21, Riverside | 30328.74 | 0 | Not started
C003 | Office Tower C | T612 | Electrical Wiring | Carlos Rivera | In Progress | High | 2024-11-08 | 2024-11-26 |  | 30 | Copper Wires | Downtown Avenue | 28414.77 | 30180.51 | In progress
C003 | Office Tower C | T115 | Interior Painting | Dave Brown | In Progress | High | 2023-07-01 | 2023-07-24 |  | 39 | Steel Beams | Downtown Avenue | 16449.46 | 17959.35 | In progress
C004 | Warehouse D | T506 | Site Survey | Sarah Johnson | In Progress | High | 2023-04-24 | 2023-05-14 |  | 13 | Roofing Sheets | Industrial Park | 23913.2 | 27818.6 | In progress
C002 | Shopping Complex B | T869 | Roofing | Carlos Rivera | Completed | High | 2024-07-11 | 2024-08-03 | 2024-08-03 | 100 | PVC Pipes | Market Street | 49358.22 | 73564.03 | No issues
C002 | Shopping Complex B | T130 | Roofing | Sarah Johnson | Completed | Low | 2023-12-16 | 2024-01-13 | 2024-01-13 | 100 | Steel Beams | Market Street | 39130.98 | 67449.9 | No issues
C003 | Office Tower C | T938 | Plumbing Installations | Carlos Rivera | Completed | Low | 2023-10-21 | 2023-11-19 | 2023-11-19 | 100 | Copper Wires | Downtown Avenue | 8020.64 | 7829.79 | No issues
C003 | Office Tower C | T616 | Roofing | Emma White | In Progress | Low | 2023-08-24 | 2023-09-12 |  | 29 | Concrete | Downtown Avenue | 17337.94 | 15844.31 | In progress
C001 | Residential Building A | T733 | Electrical Wiring | Dave Brown | Blocked | High | 2024-11-26 | 2024-12-21 |  | 0 | Steel Beams | Plot 21, Riverside | 21473.33 | 19511.37 | Not started
C002 | Shopping Complex B | T781 | Interior Painting | Grace Allen | Completed | Medium | 2024-07-04 | 2024-07-31 | 2024-07-31 | 100 | Copper Wires | Market Street | 30450.21 | 47056.82 | No issues
C001 | Residential Building A | T473 | Steel Framework Setup | John Miller | Not Started | High | 2023-03-24 | 2023-04-19 |  | 0 | Cement | Plot 21, Riverside | 39614.58 | 0 | Not started
C002 | Shopping Complex B | T737 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2023-02-14 | 2023-03-11 |  | 3 | Concrete | Market Street | 39041.76 | 60122.37 | In progress
C004 | Warehouse D | T396 | Interior Painting | John Miller | Blocked | Medium | 2024-12-27 | 2025-01-14 |  | 0 | Rebar | Industrial Park | 39909.1 | 44231.22 | Not started
C002 | Shopping Complex B | T291 | Steel Framework Setup | Mike Adams | Completed | Low | 2023-08-05 | 2023-08-20 | 2023-08-20 | 100 | Cement | Market Street | 26650.83 | 53238.24 | No issues
C003 | Office Tower C | T847 | Concrete Pouring | John Miller | Completed | High | 2024-11-28 | 2024-12-08 | 2024-12-08 | 100 | Rebar | Downtown Avenue | 23948.07 | 16059.55 | No issues
C004 | Warehouse D | T372 | Interior Painting | Mike Adams | Not Started | Medium | 2023-02-02 | 2023-02-23 |  | 0 | Paint | Industrial Park | 12887.35 | 0 | Not started
C002 | Shopping Complex B | T937 | Steel Framework Setup | Carlos Rivera | Completed | High | 2024-03-12 | 2024-03-19 | 2024-03-19 | 100 | Paint | Market Street | 17575.79 | 43344.75 | No issues
C002 | Shopping Complex B | T456 | Roofing | Mike Adams | Not Started | High | 2023-03-15 | 2023-04-14 |  | 0 | Steel Beams | Market Street | 38980.66 | 0 | Not started
C002 | Shopping Complex B | T780 | Concrete Pouring | Dave Brown | Blocked | Low | 2023-07-12 | 2023-07-21 |  | 0 | Cement | Market Street | 12611.28 | 38974.29 | Not started
C004 | Warehouse D | T491 | Plumbing Installations | Dave Brown | Not Started | High | 2024-03-22 | 2024-04-21 |  | 0 | Steel Beams | Industrial Park | 14380.45 | 0 | Not started
C004 | Warehouse D | T683 | Electrical Wiring | John Miller | In Progress | Medium | 2024-04-07 | 2024-04-18 |  | 99 | PVC Pipes | Industrial Park | 38933.66 | 43651.99 | In progress
C001 | Residential Building A | T560 | Interior Painting | Sarah Johnson | Completed | High | 2024-03-10 | 2024-04-05 | 2024-04-05 | 100 | Cement | Plot 21, Riverside | 36747.75 | 38577.39 | No issues
C003 | Office Tower C | T165 | Electrical Wiring | Carlos Rivera | In Progress | High | 2024-10-10 | 2024-10-26 |  | 11 | Rebar | Downtown Avenue | 28337.43 | 19055.56 | In progress
C004 | Warehouse D | T980 | Electrical Wiring | Grace Allen | Blocked | High | 2024-09-15 | 2024-10-14 |  | 0 | Paint | Industrial Park | 13183.76 | 10420.89 | Not started
C001 | Residential Building A | T155 | Foundation Excavation | Emma White | In Progress | High | 2024-02-28 | 2024-03-28 |  | 19 | Rebar | Plot 21, Riverside | 6705.04 | 4181.09 | In progress
C002 | Shopping Complex B | T462 | Concrete Pouring | Grace Allen | Blocked | Medium | 2023-07-18 | 2023-08-16 |  | 0 | Roofing Sheets | Market Street | 36960.46 | 65106.99 | Not started
C002 | Shopping Complex B | T431 | Site Survey | Rachel Green | Blocked | High | 2023-03-27 | 2023-04-17 |  | 0 | Steel Beams | Market Street | 28922.79 | 50996.26 | Not started
C002 | Shopping Complex B | T934 | Roofing | Rachel Green | Completed | High | 2023-01-08 | 2023-01-29 | 2023-01-29 | 100 | Steel Beams | Market Street | 15329.52 | 37623.92 | No issues
C004 | Warehouse D | T504 | Site Survey | Grace Allen | Not Started | Medium | 2023-01-06 | 2023-02-02 |  | 0 | Copper Wires | Industrial Park | 9564.76 | 0 | Not started
C003 | Office Tower C | T269 | Roofing | Sarah Johnson | Blocked | Medium | 2023-02-25 | 2023-03-23 |  | 0 | Roofing Sheets | Downtown Avenue | 19102.85 | 18207.84 | Not started
C003 | Office Tower C | T142 | Site Survey | Sarah Johnson | Blocked | Low | 2023-05-17 | 2023-05-28 |  | 0 | Roofing Sheets | Downtown Avenue | 16352.79 | 16276.26 | Not started
C003 | Office Tower C | T758 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2023-04-12 | 2023-04-20 |  | 0 | Rebar | Downtown Avenue | 24123.77 | 0 | Not started
C002 | Shopping Complex B | T348 | Electrical Wiring | Carlos Rivera | Blocked | Low | 2024-04-28 | 2024-05-15 |  | 0 | Cement | Market Street | 19589 | 37946.94 | Not started
C001 | Residential Building A | T369 | Concrete Pouring | Mike Adams | Blocked | Medium | 2024-08-07 | 2024-09-03 |  | 0 | Rebar | Plot 21, Riverside | 8619.26 | 8770.12 | Not started
C003 | Office Tower C | T571 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-01-21 | 2023-02-08 | 2023-02-08 | 100 | PVC Pipes | Downtown Avenue | 17348.63 | 20651.31 | No issues
C001 | Residential Building A | T561 | Steel Framework Setup | Dave Brown | Completed | Low | 2023-03-08 | 2023-03-19 | 2023-03-19 | 100 | Paint | Plot 21, Riverside | 41641.88 | 40505.69 | No issues
C003 | Office Tower C | T920 | Steel Framework Setup | Mike Adams | Blocked | High | 2024-08-08 | 2024-09-05 |  | 0 | Steel Beams | Downtown Avenue | 38731.22 | 33205.91 | Not started
C004 | Warehouse D | T169 | Site Survey | Carlos Rivera | Blocked | Low | 2024-07-24 | 2024-08-23 |  | 0 | Paint | Industrial Park | 21037.49 | 20469.99 | Not started
C003 | Office Tower C | T968 | Concrete Pouring | Carlos Rivera | Completed | High | 2024-05-20 | 2024-06-15 | 2024-06-15 | 100 | Steel Beams | Downtown Avenue | 36257.91 | 30847.61 | No issues
C004 | Warehouse D | T488 | Electrical Wiring | Sarah Johnson | In Progress | High | 2023-11-03 | 2023-11-13 |  | 25 | PVC Pipes | Industrial Park | 31747.14 | 22752.28 | In progress
C003 | Office Tower C | T557 | Interior Painting | Mike Adams | Not Started | High | 2024-06-20 | 2024-07-12 |  | 0 | Paint | Downtown Avenue | 27201.08 | 0 | Not started
C002 | Shopping Complex B | T910 | Steel Framework Setup | Mike Adams | In Progress | High | 2024-05-02 | 2024-05-12 |  | 67 | Paint | Market Street | 29177.88 | 44777.31 | In progress
C004 | Warehouse D | T893 | Plumbing Installations | John Miller | Not Started | Medium | 2024-03-23 | 2024-03-31 |  | 0 | Copper Wires | Industrial Park | 30911.97 | 0 | Not started
C002 | Shopping Complex B | T264 | Foundation Excavation | John Miller | In Progress | Low | 2023-04-06 | 2023-04-29 |  | 22 | Roofing Sheets | Market Street | 39332.2 | 67469.74 | In progress
C001 | Residential Building A | T555 | Foundation Excavation | Emma White | Blocked | High | 2023-09-10 | 2023-10-03 |  | 0 | PVC Pipes | Plot 21, Riverside | 12484.21 | 11581.09 | Not started
C001 | Residential Building A | T734 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-09-08 | 2024-10-06 | 2024-10-06 | 100 | Cement | Plot 21, Riverside | 43667.22 | 37673.73 | No issues
C002 | Shopping Complex B | T420 | Concrete Pouring | Rachel Green | In Progress | High | 2024-06-14 | 2024-07-05 |  | 76 | Concrete | Market Street | 20019.5 | 43574.12 | In progress
C004 | Warehouse D | T374 | Plumbing Installations | Rachel Green | Completed | Low | 2023-08-05 | 2023-08-31 | 2023-08-31 | 100 | Steel Beams | Industrial Park | 16713.33 | 16626.94 | No issues
C001 | Residential Building A | T907 | Electrical Wiring | John Miller | Not Started | Medium | 2023-08-17 | 2023-08-30 |  | 0 | Roofing Sheets | Plot 21, Riverside | 41520.03 | 0 | Not started
C004 | Warehouse D | T201 | Steel Framework Setup | Emma White | Not Started | Low | 2024-02-15 | 2024-02-26 |  | 0 | Roofing Sheets | Industrial Park | 33699.98 | 0 | Not started
C001 | Residential Building A | T718 | Foundation Excavation | Sarah Johnson | Completed | Low | 2024-01-17 | 2024-02-10 | 2024-02-10 | 100 | Roofing Sheets | Plot 21, Riverside | 12973.7 | 10661.22 | No issues
C001 | Residential Building A | T895 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2024-10-13 | 2024-11-01 |  | 50 | Steel Beams | Plot 21, Riverside | 36736.97 | 23340.11 | In progress
C001 | Residential Building A | T681 | Concrete Pouring | Grace Allen | Completed | Medium | 2024-08-22 | 2024-09-03 | 2024-09-03 | 100 | Cement | Plot 21, Riverside | 10491.97 | 10212.16 | No issues
C001 | Residential Building A | T115 | Electrical Wiring | Rachel Green | Blocked | Medium | 2024-04-05 | 2024-04-18 |  | 0 | Cement | Plot 21, Riverside | 6811.35 | 4093.68 | Not started
C002 | Shopping Complex B | T688 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2024-06-02 | 2024-07-02 |  | 0 | Cement | Market Street | 7851.68 | 0 | Not started
C002 | Shopping Complex B | T532 | Interior Painting | Carlos Rivera | Completed | Low | 2023-02-08 | 2023-03-09 | 2023-03-09 | 100 | Paint | Market Street | 47963.45 | 74786.67 | No issues
C003 | Office Tower C | T648 | Roofing | Mike Adams | In Progress | High | 2023-06-13 | 2023-07-04 |  | 55 | Roofing Sheets | Downtown Avenue | 30827.74 | 27564.9 | In progress
C001 | Residential Building A | T596 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-08-10 | 2024-08-29 |  | 0 | Concrete | Plot 21, Riverside | 5040.95 | 4634.27 | Not started
C002 | Shopping Complex B | T727 | Concrete Pouring | Emma White | Not Started | High | 2024-12-22 | 2025-01-14 |  | 0 | Cement | Market Street | 37978.65 | 0 | Not started
C004 | Warehouse D | T564 | Concrete Pouring | Dave Brown | Completed | Low | 2023-08-26 | 2023-09-12 | 2023-09-12 | 100 | Paint | Industrial Park | 37178.91 | 38624.9 | No issues
C003 | Office Tower C | T932 | Interior Painting | Rachel Green | Completed | Medium | 2024-10-02 | 2024-10-18 | 2024-10-18 | 100 | Paint | Downtown Avenue | 22248.83 | 16446.49 | No issues
C002 | Shopping Complex B | T708 | Interior Painting | Rachel Green | Blocked | Low | 2024-06-22 | 2024-07-16 |  | 0 | Steel Beams | Market Street | 47287.84 | 65274.11 | Not started
C002 | Shopping Complex B | T229 | Foundation Excavation | Rachel Green | Completed | High | 2023-07-17 | 2023-08-11 | 2023-08-11 | 100 | PVC Pipes | Market Street | 13671.09 | 33893.07 | No issues
C002 | Shopping Complex B | T325 | Concrete Pouring | Mike Adams | Completed | High | 2023-05-24 | 2023-06-22 | 2023-06-22 | 100 | Concrete | Market Street | 32044.4 | 47457.35 | No issues
C003 | Office Tower C | T195 | Electrical Wiring | Dave Brown | Blocked | Low | 2023-02-26 | 2023-03-06 |  | 0 | Concrete | Downtown Avenue | 11085.78 | 7094.97 | Not started
C002 | Shopping Complex B | T275 | Foundation Excavation | Emma White | In Progress | High | 2023-05-11 | 2023-05-20 |  | 78 | Copper Wires | Market Street | 20431.83 | 49477.04 | In progress
C001 | Residential Building A | T931 | Roofing | Emma White | Not Started | Medium | 2023-01-20 | 2023-02-11 |  | 0 | Rebar | Plot 21, Riverside | 7901.36 | 0 | Not started
C003 | Office Tower C | T586 | Foundation Excavation | Dave Brown | Blocked | Low | 2024-08-10 | 2024-09-08 |  | 0 | PVC Pipes | Downtown Avenue | 47469.67 | 53573.97 | Not started
C002 | Shopping Complex B | T821 | Interior Painting | Carlos Rivera | In Progress | Medium | 2023-03-24 | 2023-04-23 |  | 31 | Concrete | Market Street | 17390.02 | 38542.27 | In progress
C001 | Residential Building A | T285 | Roofing | Carlos Rivera | Blocked | Low | 2023-07-14 | 2023-07-21 |  | 0 | PVC Pipes | Plot 21, Riverside | 6863.49 | 5279.73 | Not started
C003 | Office Tower C | T921 | Steel Framework Setup | Mike Adams | In Progress | High | 2024-12-26 | 2025-01-13 |  | 10 | PVC Pipes | Downtown Avenue | 9692.93 | 7976.69 | In progress
C004 | Warehouse D | T427 | Site Survey | Emma White | Not Started | Medium | 2023-04-12 | 2023-05-07 |  | 0 | Steel Beams | Industrial Park | 20587.71 | 0 | Not started
C004 | Warehouse D | T851 | Site Survey | Rachel Green | Not Started | Medium | 2023-09-03 | 2023-09-17 |  | 0 | Steel Beams | Industrial Park | 21947.21 | 0 | Not started
C002 | Shopping Complex B | T162 | Steel Framework Setup | Carlos Rivera | Completed | Low | 2023-10-25 | 2023-11-05 | 2023-11-05 | 100 | Copper Wires | Market Street | 27463.01 | 47321.36 | No issues
C003 | Office Tower C | T317 | Plumbing Installations | Dave Brown | Completed | Low | 2023-09-08 | 2023-09-25 | 2023-09-25 | 100 | Paint | Downtown Avenue | 47650.15 | 32737.99 | No issues
C003 | Office Tower C | T816 | Steel Framework Setup | Mike Adams | In Progress | High | 2023-12-25 | 2024-01-04 |  | 4 | Cement | Downtown Avenue | 18687.56 | 21610.61 | In progress
C002 | Shopping Complex B | T382 | Electrical Wiring | Mike Adams | Not Started | High | 2024-01-18 | 2024-01-27 |  | 0 | Rebar | Market Street | 48432.4 | 0 | Not started
C001 | Residential Building A | T385 | Roofing | Sarah Johnson | Completed | High | 2024-05-13 | 2024-06-07 | 2024-06-07 | 100 | Copper Wires | Plot 21, Riverside | 40389.45 | 29338.21 | No issues
C002 | Shopping Complex B | T550 | Plumbing Installations | John Miller | Blocked | High | 2024-09-20 | 2024-09-30 |  | 0 | Paint | Market Street | 35648.43 | 57394.45 | Not started
C003 | Office Tower C | T954 | Concrete Pouring | John Miller | Blocked | Medium | 2023-08-01 | 2023-08-12 |  | 0 | Rebar | Downtown Avenue | 42314.42 | 49246.79 | Not started
C002 | Shopping Complex B | T222 | Plumbing Installations | Mike Adams | Not Started | High | 2023-01-14 | 2023-01-26 |  | 0 | Copper Wires | Market Street | 21039.75 | 0 | Not started
C001 | Residential Building A | T487 | Roofing | Mike Adams | Blocked | Medium | 2023-03-12 | 2023-03-20 |  | 0 | PVC Pipes | Plot 21, Riverside | 25388.98 | 20616.39 | Not started
C001 | Residential Building A | T233 | Steel Framework Setup | Rachel Green | Completed | Medium | 2023-06-03 | 2023-06-25 | 2023-06-25 | 100 | Paint | Plot 21, Riverside | 21496.38 | 21975.73 | No issues
C004 | Warehouse D | T578 | Site Survey | Sarah Johnson | In Progress | High | 2023-05-27 | 2023-06-26 |  | 54 | PVC Pipes | Industrial Park | 35510.19 | 30047.97 | In progress
C001 | Residential Building A | T685 | Site Survey | Rachel Green | In Progress | High | 2024-11-03 | 2024-11-28 |  | 80 | Paint | Plot 21, Riverside | 46567.01 | 34337.06 | In progress
C004 | Warehouse D | T151 | Interior Painting | John Miller | Completed | High | 2023-01-27 | 2023-02-10 | 2023-02-10 | 100 | Paint | Industrial Park | 30891.13 | 22864.02 | No issues
C004 | Warehouse D | T906 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2023-05-28 | 2023-06-21 | 2023-06-21 | 100 | Rebar | Industrial Park | 7790.19 | 5361.94 | No issues
C003 | Office Tower C | T596 | Site Survey | Mike Adams | Completed | High | 2024-10-03 | 2024-10-25 | 2024-10-25 | 100 | Paint | Downtown Avenue | 30123.09 | 27289.7 | No issues
C004 | Warehouse D | T666 | Roofing | Rachel Green | Completed | Medium | 2023-01-15 | 2023-01-24 | 2023-01-24 | 100 | Cement | Industrial Park | 44516.19 | 36993.06 | No issues
C002 | Shopping Complex B | T907 | Foundation Excavation | Emma White | Blocked | Low | 2023-12-22 | 2023-12-29 |  | 0 | Cement | Market Street | 20409.89 | 41570.56 | Not started
C003 | Office Tower C | T663 | Roofing | Emma White | Completed | Low | 2024-04-04 | 2024-04-13 | 2024-04-13 | 100 | Cement | Downtown Avenue | 29968.61 | 33571.23 | No issues
C004 | Warehouse D | T142 | Site Survey | Sarah Johnson | In Progress | High | 2024-12-21 | 2025-01-06 |  | 44 | Paint | Industrial Park | 42102.52 | 25822.42 | In progress
C004 | Warehouse D | T856 | Plumbing Installations | Emma White | Not Started | Low | 2024-10-12 | 2024-11-07 |  | 0 | Copper Wires | Industrial Park | 17948.39 | 0 | Not started
C001 | Residential Building A | T196 | Steel Framework Setup | Emma White | Completed | Low | 2023-07-05 | 2023-07-28 | 2023-07-28 | 100 | Copper Wires | Plot 21, Riverside | 7596.53 | 4672.97 | No issues
C003 | Office Tower C | T381 | Roofing | Carlos Rivera | Completed | Low | 2024-03-10 | 2024-04-01 | 2024-04-01 | 100 | Roofing Sheets | Downtown Avenue | 6847.77 | 5260.51 | No issues
C001 | Residential Building A | T708 | Roofing | Emma White | Blocked | Medium | 2024-11-14 | 2024-12-08 |  | 0 | PVC Pipes | Plot 21, Riverside | 15751.41 | 17616.29 | Not started
C002 | Shopping Complex B | T470 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2024-10-21 | 2024-11-05 |  | 0 | Concrete | Market Street | 46143.51 | 0 | Not started
C002 | Shopping Complex B | T826 | Roofing | Sarah Johnson | Blocked | Medium | 2023-10-02 | 2023-10-27 |  | 0 | Rebar | Market Street | 18219.04 | 42414 | Not started
C004 | Warehouse D | T253 | Concrete Pouring | John Miller | Completed | Low | 2023-02-26 | 2023-03-17 | 2023-03-17 | 100 | Cement | Industrial Park | 36219.02 | 31121.61 | No issues
C003 | Office Tower C | T606 | Plumbing Installations | Emma White | In Progress | High | 2024-02-10 | 2024-03-02 |  | 69 | Paint | Downtown Avenue | 25850.66 | 15625.28 | In progress
C001 | Residential Building A | T360 | Electrical Wiring | Dave Brown | In Progress | Medium | 2024-11-16 | 2024-11-26 |  | 71 | Roofing Sheets | Plot 21, Riverside | 19204.59 | 21380.58 | In progress
C001 | Residential Building A | T922 | Electrical Wiring | Grace Allen | In Progress | High | 2024-02-13 | 2024-02-24 |  | 32 | Rebar | Plot 21, Riverside | 44737.32 | 31750.41 | In progress
C002 | Shopping Complex B | T746 | Site Survey | Mike Adams | Not Started | Low | 2024-10-03 | 2024-10-28 |  | 0 | Steel Beams | Market Street | 42977.49 | 0 | Not started
C001 | Residential Building A | T443 | Concrete Pouring | Mike Adams | Blocked | Low | 2023-10-18 | 2023-11-14 |  | 0 | Copper Wires | Plot 21, Riverside | 45971 | 29671.7 | Not started
C004 | Warehouse D | T815 | Foundation Excavation | John Miller | Completed | Medium | 2024-05-08 | 2024-06-04 | 2024-06-04 | 100 | Copper Wires | Industrial Park | 38772.95 | 42308.86 | No issues
C004 | Warehouse D | T570 | Electrical Wiring | Sarah Johnson | In Progress | High | 2023-07-26 | 2023-08-17 |  | 84 | Steel Beams | Industrial Park | 13490.25 | 10562.37 | In progress
C003 | Office Tower C | T470 | Foundation Excavation | Emma White | Completed | Low | 2023-11-11 | 2023-11-27 | 2023-11-27 | 100 | Concrete | Downtown Avenue | 16979.59 | 17882.09 | No issues
C002 | Shopping Complex B | T551 | Interior Painting | Sarah Johnson | Completed | High | 2024-07-10 | 2024-07-24 | 2024-07-24 | 100 | Paint | Market Street | 8378.1 | 34212.49 | No issues
C001 | Residential Building A | T819 | Site Survey | Rachel Green | Completed | High | 2024-10-16 | 2024-11-04 | 2024-11-04 | 100 | Cement | Plot 21, Riverside | 21917.1 | 25534.76 | No issues
C001 | Residential Building A | T318 | Electrical Wiring | Grace Allen | Not Started | Medium | 2024-04-04 | 2024-04-11 |  | 0 | Rebar | Plot 21, Riverside | 39695.03 | 0 | Not started
C004 | Warehouse D | T143 | Steel Framework Setup | Emma White | Blocked | Medium | 2024-06-25 | 2024-07-09 |  | 0 | Steel Beams | Industrial Park | 26295.86 | 28528.64 | Not started
C003 | Office Tower C | T857 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-11-16 | 2024-12-15 |  | 0 | Paint | Downtown Avenue | 41934.05 | 32742.82 | Not started
C004 | Warehouse D | T694 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-05-26 | 2024-06-18 |  | 0 | Concrete | Industrial Park | 48507.51 | 0 | Not started
C003 | Office Tower C | T581 | Electrical Wiring | Grace Allen | Not Started | High | 2024-12-20 | 2025-01-04 |  | 0 | Concrete | Downtown Avenue | 24558.54 | 0 | Not started
C004 | Warehouse D | T124 | Plumbing Installations | Rachel Green | Completed | Low | 2024-04-15 | 2024-05-09 | 2024-05-09 | 100 | Steel Beams | Industrial Park | 17575.46 | 20722.52 | No issues
C004 | Warehouse D | T267 | Interior Painting | Grace Allen | Completed | High | 2023-02-26 | 2023-03-05 | 2023-03-05 | 100 | Rebar | Industrial Park | 35622.55 | 29007.93 | No issues
C004 | Warehouse D | T350 | Plumbing Installations | Dave Brown | Blocked | Low | 2023-04-11 | 2023-04-18 |  | 0 | Copper Wires | Industrial Park | 8937.02 | 10031.4 | Not started
C003 | Office Tower C | T236 | Interior Painting | Emma White | Blocked | Medium | 2024-01-02 | 2024-01-13 |  | 0 | Cement | Downtown Avenue | 22582.06 | 17778.21 | Not started
C001 | Residential Building A | T765 | Roofing | Carlos Rivera | Not Started | Low | 2024-12-25 | 2025-01-20 |  | 0 | Rebar | Plot 21, Riverside | 6985.71 | 0 | Not started
C001 | Residential Building A | T393 | Plumbing Installations | Mike Adams | Blocked | High | 2024-02-16 | 2024-03-09 |  | 0 | Copper Wires | Plot 21, Riverside | 18929.38 | 16137.23 | Not started
C003 | Office Tower C | T246 | Interior Painting | John Miller | In Progress | Low | 2024-09-18 | 2024-10-02 |  | 87 | Cement | Downtown Avenue | 35281.25 | 40886.58 | In progress
C004 | Warehouse D | T672 | Interior Painting | Mike Adams | In Progress | High | 2023-09-08 | 2023-10-02 |  | 63 | PVC Pipes | Industrial Park | 13369.23 | 10994.71 | In progress
C004 | Warehouse D | T611 | Electrical Wiring | Emma White | Blocked | High | 2024-11-25 | 2024-12-23 |  | 0 | PVC Pipes | Industrial Park | 40609.32 | 34068.83 | Not started
C003 | Office Tower C | T388 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-11-20 | 2023-12-01 |  | 0 | Concrete | Downtown Avenue | 15387.48 | 13558.79 | Not started
C004 | Warehouse D | T866 | Roofing | Dave Brown | In Progress | Low | 2024-05-19 | 2024-06-11 |  | 34 | Copper Wires | Industrial Park | 20400.9 | 16678.89 | In progress
C004 | Warehouse D | T868 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-07-05 | 2024-07-31 | 2024-07-31 | 100 | Steel Beams | Industrial Park | 43519.86 | 44042.43 | No issues
C002 | Shopping Complex B | T249 | Plumbing Installations | Dave Brown | In Progress | Medium | 2023-02-24 | 2023-03-21 |  | 43 | Cement | Market Street | 49710.19 | 63228.71 | In progress
C004 | Warehouse D | T140 | Concrete Pouring | John Miller | Not Started | High | 2023-12-14 | 2024-01-07 |  | 0 | Rebar | Industrial Park | 31312.67 | 0 | Not started
C001 | Residential Building A | T666 | Interior Painting | Rachel Green | In Progress | Medium | 2023-08-08 | 2023-08-17 |  | 54 | Rebar | Plot 21, Riverside | 40942.55 | 27534.13 | In progress
C001 | Residential Building A | T166 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-12-01 | 2024-12-12 |  | 38 | Steel Beams | Plot 21, Riverside | 41912.34 | 38169.49 | In progress
C003 | Office Tower C | T723 | Electrical Wiring | Dave Brown | In Progress | Medium | 2023-04-28 | 2023-05-09 |  | 96 | Copper Wires | Downtown Avenue | 6234.11 | 6816.81 | In progress
C003 | Office Tower C | T431 | Interior Painting | Grace Allen | Completed | Low | 2023-09-25 | 2023-10-10 | 2023-10-10 | 100 | Steel Beams | Downtown Avenue | 20941.35 | 22045.39 | No issues
C001 | Residential Building A | T176 | Roofing | John Miller | Blocked | High | 2023-07-16 | 2023-08-13 |  | 0 | Paint | Plot 21, Riverside | 44296.51 | 42146.86 | Not started
C002 | Shopping Complex B | T702 | Electrical Wiring | Mike Adams | Blocked | High | 2024-06-19 | 2024-06-27 |  | 0 | Copper Wires | Market Street | 29914.23 | 55838.97 | Not started
C003 | Office Tower C | T126 | Site Survey | Mike Adams | Completed | Low | 2023-10-23 | 2023-11-22 | 2023-11-22 | 100 | PVC Pipes | Downtown Avenue | 27844.58 | 28827.4 | No issues
C003 | Office Tower C | T421 | Concrete Pouring | Sarah Johnson | Completed | Low | 2024-03-05 | 2024-03-25 | 2024-03-25 | 100 | Roofing Sheets | Downtown Avenue | 8908.54 | 5348.87 | No issues
C004 | Warehouse D | T389 | Electrical Wiring | John Miller | Blocked | High | 2024-03-26 | 2024-04-17 |  | 0 | Roofing Sheets | Industrial Park | 43952.26 | 37758.69 | Not started
C004 | Warehouse D | T306 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-01-09 | 2024-01-25 |  | 0 | Steel Beams | Industrial Park | 19260.83 | 0 | Not started
C002 | Shopping Complex B | T653 | Roofing | Carlos Rivera | Completed | Medium | 2023-05-18 | 2023-05-30 | 2023-05-30 | 100 | Cement | Market Street | 5794.05 | 30450.7 | No issues
C001 | Residential Building A | T988 | Plumbing Installations | Grace Allen | In Progress | Low | 2023-09-28 | 2023-10-08 |  | 40 | Steel Beams | Plot 21, Riverside | 7226.81 | 6104.76 | In progress
C004 | Warehouse D | T239 | Site Survey | Mike Adams | Not Started | Medium | 2024-08-14 | 2024-09-04 |  | 0 | Paint | Industrial Park | 18905.89 | 0 | Not started
C002 | Shopping Complex B | T682 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2024-11-13 | 2024-12-12 |  | 0 | Steel Beams | Market Street | 16592.46 | 42310.55 | Not started
C002 | Shopping Complex B | T502 | Plumbing Installations | Sarah Johnson | Completed | High | 2024-08-21 | 2024-09-08 | 2024-09-08 | 100 | Paint | Market Street | 42784.03 | 68284.84 | No issues
C001 | Residential Building A | T317 | Site Survey | Rachel Green | In Progress | Low | 2023-05-17 | 2023-05-31 |  | 44 | Copper Wires | Plot 21, Riverside | 39865.79 | 29730.38 | In progress
C002 | Shopping Complex B | T761 | Plumbing Installations | Dave Brown | Not Started | Medium | 2023-08-04 | 2023-08-25 |  | 0 | Cement | Market Street | 46900.18 | 0 | Not started
C002 | Shopping Complex B | T360 | Electrical Wiring | Rachel Green | In Progress | Low | 2023-02-20 | 2023-03-18 |  | 38 | Paint | Market Street | 11019.82 | 32796.59 | In progress
C003 | Office Tower C | T479 | Roofing | Dave Brown | Blocked | High | 2023-07-25 | 2023-08-06 |  | 0 | Concrete | Downtown Avenue | 12980.28 | 7882.86 | Not started
C003 | Office Tower C | T498 | Roofing | Mike Adams | Blocked | Low | 2024-10-09 | 2024-10-18 |  | 0 | Paint | Downtown Avenue | 13266.72 | 13006.09 | Not started
C002 | Shopping Complex B | T542 | Foundation Excavation | Dave Brown | In Progress | Low | 2024-04-05 | 2024-04-21 |  | 98 | Steel Beams | Market Street | 36634.9 | 62077.09 | In progress
C004 | Warehouse D | T939 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2023-02-05 | 2023-02-15 |  | 74 | PVC Pipes | Industrial Park | 39333.95 | 28427.13 | In progress
C004 | Warehouse D | T824 | Roofing | Emma White | In Progress | Medium | 2023-04-28 | 2023-05-15 |  | 71 | Paint | Industrial Park | 20109.76 | 21577.75 | In progress
C002 | Shopping Complex B | T424 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-08-10 | 2023-09-08 |  | 0 | Steel Beams | Market Street | 18736.59 | 47100.3 | Not started
C004 | Warehouse D | T651 | Site Survey | Emma White | In Progress | Low | 2023-05-27 | 2023-06-14 |  | 63 | Cement | Industrial Park | 11922.42 | 8793.85 | In progress
C001 | Residential Building A | T828 | Steel Framework Setup | Sarah Johnson | Completed | Low | 2023-04-10 | 2023-04-21 | 2023-04-21 | 100 | Concrete | Plot 21, Riverside | 29267.23 | 25274.58 | No issues
C002 | Shopping Complex B | T594 | Plumbing Installations | Rachel Green | Not Started | High | 2023-02-27 | 2023-03-20 |  | 0 | Copper Wires | Market Street | 25606.27 | 0 | Not started
C003 | Office Tower C | T246 | Site Survey | John Miller | Not Started | High | 2024-08-21 | 2024-09-20 |  | 0 | PVC Pipes | Downtown Avenue | 33573.34 | 0 | Not started
C001 | Residential Building A | T534 | Roofing | Rachel Green | In Progress | Low | 2023-03-14 | 2023-03-23 |  | 9 | Steel Beams | Plot 21, Riverside | 40968.37 | 42832.91 | In progress
C004 | Warehouse D | T197 | Electrical Wiring | Carlos Rivera | Not Started | Medium | 2024-04-13 | 2024-05-06 |  | 0 | Steel Beams | Industrial Park | 26218.27 | 0 | Not started
C004 | Warehouse D | T264 | Foundation Excavation | Grace Allen | Blocked | High | 2023-03-02 | 2023-03-23 |  | 0 | Concrete | Industrial Park | 5973.11 | 6764.54 | Not started
C004 | Warehouse D | T353 | Interior Painting | Dave Brown | Completed | High | 2023-10-03 | 2023-10-10 | 2023-10-10 | 100 | Concrete | Industrial Park | 48408.15 | 53518.03 | No issues
C003 | Office Tower C | T731 | Foundation Excavation | John Miller | Not Started | High | 2024-06-15 | 2024-07-15 |  | 0 | Concrete | Downtown Avenue | 17948.9 | 0 | Not started
C004 | Warehouse D | T427 | Steel Framework Setup | Dave Brown | Blocked | High | 2024-01-15 | 2024-02-02 |  | 0 | Copper Wires | Industrial Park | 24516.34 | 21591.84 | Not started
C004 | Warehouse D | T224 | Electrical Wiring | Dave Brown | Blocked | High | 2024-03-21 | 2024-04-11 |  | 0 | Steel Beams | Industrial Park | 22008.37 | 19091.94 | Not started
C002 | Shopping Complex B | T723 | Electrical Wiring | Emma White | Blocked | Low | 2023-12-18 | 2023-12-30 |  | 0 | Concrete | Market Street | 43130.93 | 65715.01 | Not started
C003 | Office Tower C | T302 | Steel Framework Setup | Rachel Green | Completed | Low | 2023-10-10 | 2023-11-05 | 2023-11-05 | 100 | Rebar | Downtown Avenue | 12779.89 | 13274.4 | No issues
C002 | Shopping Complex B | T320 | Steel Framework Setup | Mike Adams | Not Started | High | 2023-12-07 | 2024-01-05 |  | 0 | Paint | Market Street | 33523.24 | 0 | Not started
C004 | Warehouse D | T674 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2023-07-22 | 2023-08-05 |  | 0 | Rebar | Industrial Park | 30907.65 | 0 | Not started
C003 | Office Tower C | T858 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-08-10 | 2024-09-08 |  | 0 | Roofing Sheets | Downtown Avenue | 28617.02 | 0 | Not started
C001 | Residential Building A | T177 | Plumbing Installations | Emma White | In Progress | Medium | 2023-12-21 | 2024-01-10 |  | 28 | Copper Wires | Plot 21, Riverside | 40903.91 | 36689.16 | In progress
C002 | Shopping Complex B | T869 | Site Survey | Carlos Rivera | In Progress | Medium | 2024-01-05 | 2024-01-14 |  | 43 | Steel Beams | Market Street | 23333.52 | 46219.17 | In progress
C001 | Residential Building A | T228 | Steel Framework Setup | John Miller | Blocked | Low | 2023-10-16 | 2023-10-28 |  | 0 | Concrete | Plot 21, Riverside | 43195.64 | 47569.25 | Not started
C004 | Warehouse D | T757 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2024-08-07 | 2024-09-03 |  | 0 | Roofing Sheets | Industrial Park | 47416.1 | 0 | Not started
C002 | Shopping Complex B | T880 | Foundation Excavation | Sarah Johnson | Completed | High | 2024-01-26 | 2024-02-13 | 2024-02-13 | 100 | Copper Wires | Market Street | 41730.5 | 72311.04 | No issues
C003 | Office Tower C | T368 | Site Survey | Mike Adams | Not Started | Low | 2024-02-12 | 2024-03-12 |  | 0 | PVC Pipes | Downtown Avenue | 15294.43 | 0 | Not started
C003 | Office Tower C | T724 | Interior Painting | John Miller | In Progress | High | 2023-07-25 | 2023-08-07 |  | 98 | Concrete | Downtown Avenue | 19517.49 | 11848.87 | In progress
C002 | Shopping Complex B | T850 | Concrete Pouring | Rachel Green | Completed | Low | 2024-09-01 | 2024-09-24 | 2024-09-24 | 100 | Copper Wires | Market Street | 16449.07 | 41461.83 | No issues
C004 | Warehouse D | T205 | Roofing | Sarah Johnson | Completed | High | 2023-01-27 | 2023-02-10 | 2023-02-10 | 100 | Concrete | Industrial Park | 8351.06 | 9419.32 | No issues
C003 | Office Tower C | T414 | Foundation Excavation | Dave Brown | In Progress | High | 2023-07-23 | 2023-08-08 |  | 77 | Paint | Downtown Avenue | 9735.83 | 10172.49 | In progress
C003 | Office Tower C | T813 | Foundation Excavation | Carlos Rivera | Completed | Medium | 2023-09-04 | 2023-09-24 | 2023-09-24 | 100 | Rebar | Downtown Avenue | 20433.72 | 21865.16 | No issues
C002 | Shopping Complex B | T196 | Steel Framework Setup | Carlos Rivera | Blocked | Low | 2024-11-04 | 2024-12-01 |  | 0 | Cement | Market Street | 27712.91 | 53795.68 | Not started
C002 | Shopping Complex B | T826 | Steel Framework Setup | Emma White | Not Started | Medium | 2023-10-15 | 2023-11-07 |  | 0 | Steel Beams | Market Street | 27310.03 | 0 | Not started
C004 | Warehouse D | T874 | Roofing | Grace Allen | Blocked | High | 2024-02-06 | 2024-02-18 |  | 0 | Roofing Sheets | Industrial Park | 44256.27 | 49676.84 | Not started
C002 | Shopping Complex B | T650 | Steel Framework Setup | Sarah Johnson | Not Started | High | 2023-09-08 | 2023-09-23 |  | 0 | Steel Beams | Market Street | 36179.69 | 0 | Not started
C003 | Office Tower C | T256 | Foundation Excavation | Mike Adams | Not Started | High | 2024-02-05 | 2024-02-13 |  | 0 | Concrete | Downtown Avenue | 45729.3 | 0 | Not started
C001 | Residential Building A | T830 | Electrical Wiring | Emma White | Not Started | High | 2023-02-09 | 2023-03-01 |  | 0 | Copper Wires | Plot 21, Riverside | 19634.9 | 0 | Not started
C003 | Office Tower C | T466 | Foundation Excavation | Dave Brown | In Progress | Medium | 2023-03-22 | 2023-04-06 |  | 33 | Paint | Downtown Avenue | 44596.46 | 35352.77 | In progress
C004 | Warehouse D | T379 | Interior Painting | Dave Brown | In Progress | High | 2023-08-13 | 2023-08-24 |  | 41 | PVC Pipes | Industrial Park | 17439.23 | 17892.97 | In progress
C004 | Warehouse D | T935 | Site Survey | Emma White | In Progress | Low | 2023-05-10 | 2023-06-06 |  | 98 | Rebar | Industrial Park | 24274.31 | 14601.69 | In progress
C003 | Office Tower C | T432 | Interior Painting | Carlos Rivera | In Progress | Medium | 2023-03-18 | 2023-04-09 |  | 64 | Steel Beams | Downtown Avenue | 17845.8 | 15781.01 | In progress
C003 | Office Tower C | T921 | Electrical Wiring | Rachel Green | Completed | High | 2024-08-14 | 2024-08-21 | 2024-08-21 | 100 | Cement | Downtown Avenue | 41654.33 | 29976.39 | No issues
C002 | Shopping Complex B | T414 | Roofing | Sarah Johnson | Blocked | Low | 2024-05-22 | 2024-06-20 |  | 0 | Rebar | Market Street | 30174.2 | 47007.38 | Not started
C002 | Shopping Complex B | T370 | Plumbing Installations | Dave Brown | Completed | High | 2024-01-18 | 2024-02-16 | 2024-02-16 | 100 | Roofing Sheets | Market Street | 14473.47 | 35029.74 | No issues
C002 | Shopping Complex B | T472 | Roofing | Emma White | Not Started | Medium | 2023-08-01 | 2023-08-23 |  | 0 | Concrete | Market Street | 17335.29 | 0 | Not started
C001 | Residential Building A | T297 | Plumbing Installations | Grace Allen | Completed | Low | 2023-02-05 | 2023-02-23 | 2023-02-23 | 100 | Concrete | Plot 21, Riverside | 21748.56 | 23530.6 | No issues
C001 | Residential Building A | T692 | Plumbing Installations | Emma White | Blocked | Medium | 2023-03-28 | 2023-04-21 |  | 0 | Concrete | Plot 21, Riverside | 9894.79 | 11645.56 | Not started
C002 | Shopping Complex B | T459 | Electrical Wiring | Dave Brown | Not Started | Low | 2023-03-09 | 2023-03-31 |  | 0 | Roofing Sheets | Market Street | 15953.5 | 0 | Not started
C001 | Residential Building A | T230 | Steel Framework Setup | Dave Brown | Completed | High | 2024-11-16 | 2024-12-09 | 2024-12-09 | 100 | PVC Pipes | Plot 21, Riverside | 25022.52 | 26224.23 | No issues
C003 | Office Tower C | T256 | Electrical Wiring | Mike Adams | Blocked | Medium | 2024-05-22 | 2024-06-10 |  | 0 | Copper Wires | Downtown Avenue | 12272.53 | 11070.66 | Not started
C002 | Shopping Complex B | T198 | Plumbing Installations | Mike Adams | In Progress | Low | 2023-06-02 | 2023-06-14 |  | 21 | Steel Beams | Market Street | 12288.03 | 33464.68 | In progress
C002 | Shopping Complex B | T244 | Roofing | Carlos Rivera | Not Started | High | 2024-01-19 | 2024-01-26 |  | 0 | Cement | Market Street | 30959.08 | 0 | Not started
C003 | Office Tower C | T685 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-05-17 | 2023-06-06 | 2023-06-06 | 100 | Roofing Sheets | Downtown Avenue | 16760.22 | 13360.5 | No issues
C003 | Office Tower C | T253 | Electrical Wiring | Dave Brown | Completed | High | 2024-04-24 | 2024-05-05 | 2024-05-05 | 100 | Steel Beams | Downtown Avenue | 40465.72 | 33071.17 | No issues
C004 | Warehouse D | T616 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2024-01-21 | 2024-02-20 |  | 0 | Concrete | Industrial Park | 6043.58 | 0 | Not started
C004 | Warehouse D | T325 | Roofing | Mike Adams | Blocked | Low | 2024-08-17 | 2024-09-02 |  | 0 | Cement | Industrial Park | 6956.49 | 6502.88 | Not started
C001 | Residential Building A | T214 | Interior Painting | Carlos Rivera | In Progress | Medium | 2024-02-03 | 2024-02-29 |  | 25 | Roofing Sheets | Plot 21, Riverside | 11090.13 | 7577.5 | In progress
C001 | Residential Building A | T739 | Foundation Excavation | John Miller | Completed | Low | 2024-03-22 | 2024-04-07 | 2024-04-07 | 100 | Rebar | Plot 21, Riverside | 12588.73 | 14401.3 | No issues
C001 | Residential Building A | T446 | Interior Painting | John Miller | Blocked | Low | 2024-11-13 | 2024-12-10 |  | 0 | Copper Wires | Plot 21, Riverside | 17350.62 | 11441.08 | Not started
C004 | Warehouse D | T310 | Roofing | Carlos Rivera | Completed | Low | 2023-12-07 | 2023-12-16 | 2023-12-16 | 100 | Steel Beams | Industrial Park | 21119.03 | 24172.91 | No issues
C001 | Residential Building A | T787 | Plumbing Installations | Rachel Green | Completed | High | 2023-12-05 | 2023-12-30 | 2023-12-30 | 100 | Copper Wires | Plot 21, Riverside | 42540.35 | 29919.23 | No issues
C004 | Warehouse D | T224 | Plumbing Installations | Grace Allen | In Progress | High | 2024-04-03 | 2024-04-20 |  | 34 | Copper Wires | Industrial Park | 21172.27 | 20884.07 | In progress
C001 | Residential Building A | T798 | Electrical Wiring | Emma White | Not Started | High | 2023-02-22 | 2023-03-18 |  | 0 | Copper Wires | Plot 21, Riverside | 47169.41 | 0 | Not started
C003 | Office Tower C | T939 | Plumbing Installations | Rachel Green | Blocked | High | 2024-08-14 | 2024-09-11 |  | 0 | Cement | Downtown Avenue | 20086.62 | 16403.98 | Not started
C002 | Shopping Complex B | T289 | Roofing | Emma White | Not Started | Low | 2023-12-17 | 2024-01-02 |  | 0 | Rebar | Market Street | 34304.51 | 0 | Not started
C004 | Warehouse D | T408 | Electrical Wiring | Rachel Green | Not Started | Medium | 2023-12-11 | 2024-01-04 |  | 0 | Roofing Sheets | Industrial Park | 42178.24 | 0 | Not started
C002 | Shopping Complex B | T890 | Interior Painting | Sarah Johnson | In Progress | Low | 2023-05-12 | 2023-05-26 |  | 37 | PVC Pipes | Market Street | 15582.65 | 42317.86 | In progress
C001 | Residential Building A | T250 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2023-07-03 | 2023-07-25 | 2023-07-25 | 100 | Paint | Plot 21, Riverside | 23575.51 | 21440.2 | No issues
C002 | Shopping Complex B | T416 | Roofing | Dave Brown | Not Started | Medium | 2024-02-12 | 2024-03-09 |  | 0 | PVC Pipes | Market Street | 12190.75 | 0 | Not started
C001 | Residential Building A | T878 | Roofing | Rachel Green | Completed | Low | 2024-10-22 | 2024-11-18 | 2024-11-18 | 100 | Rebar | Plot 21, Riverside | 16005.64 | 10780.17 | No issues
C002 | Shopping Complex B | T146 | Foundation Excavation | Mike Adams | Not Started | High | 2023-05-13 | 2023-05-24 |  | 0 | Copper Wires | Market Street | 8117.74 | 0 | Not started
C003 | Office Tower C | T309 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2023-05-14 | 2023-05-21 |  | 0 | Paint | Downtown Avenue | 12222.94 | 0 | Not started
C003 | Office Tower C | T257 | Interior Painting | Carlos Rivera | Completed | Medium | 2023-08-23 | 2023-09-18 | 2023-09-18 | 100 | Rebar | Downtown Avenue | 37710.98 | 37643.57 | No issues
C003 | Office Tower C | T740 | Concrete Pouring | Dave Brown | Blocked | High | 2023-01-23 | 2023-02-12 |  | 0 | Concrete | Downtown Avenue | 23589.41 | 17846.69 | Not started
C001 | Residential Building A | T328 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2024-03-24 | 2024-04-20 |  | 0 | Roofing Sheets | Plot 21, Riverside | 5633.02 | 0 | Not started
C003 | Office Tower C | T538 | Concrete Pouring | Emma White | Blocked | Medium | 2023-08-06 | 2023-08-28 |  | 0 | Paint | Downtown Avenue | 28612.82 | 31851.15 | Not started
C002 | Shopping Complex B | T552 | Steel Framework Setup | Mike Adams | In Progress | Low | 2023-07-11 | 2023-07-30 |  | 24 | Roofing Sheets | Market Street | 48397.31 | 65380.43 | In progress
C002 | Shopping Complex B | T469 | Roofing | Carlos Rivera | Blocked | Medium | 2023-01-15 | 2023-01-31 |  | 0 | Rebar | Market Street | 12472.01 | 37424.82 | Not started
C002 | Shopping Complex B | T340 | Plumbing Installations | Emma White | In Progress | High | 2023-09-13 | 2023-10-07 |  | 87 | PVC Pipes | Market Street | 30698.29 | 49876.11 | In progress
C003 | Office Tower C | T659 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2023-04-27 | 2023-05-15 |  | 0 | Roofing Sheets | Downtown Avenue | 10456.46 | 11983.67 | Not started
C004 | Warehouse D | T246 | Concrete Pouring | Rachel Green | Blocked | Low | 2023-08-21 | 2023-09-04 |  | 0 | Rebar | Industrial Park | 38492.39 | 31826.93 | Not started
C001 | Residential Building A | T918 | Interior Painting | John Miller | Blocked | Low | 2024-08-25 | 2024-09-24 |  | 0 | Cement | Plot 21, Riverside | 17828.23 | 14154.43 | Not started
C002 | Shopping Complex B | T426 | Site Survey | Dave Brown | In Progress | Low | 2024-04-16 | 2024-05-06 |  | 7 | Roofing Sheets | Market Street | 14779.86 | 42870.6 | In progress
C004 | Warehouse D | T312 | Steel Framework Setup | Rachel Green | In Progress | Low | 2024-12-05 | 2024-12-15 |  | 25 | Cement | Industrial Park | 15668.76 | 13051.85 | In progress
C003 | Office Tower C | T390 | Steel Framework Setup | Mike Adams | Completed | Medium | 2023-03-22 | 2023-04-18 | 2023-04-18 | 100 | Cement | Downtown Avenue | 23598.91 | 24344.5 | No issues
C003 | Office Tower C | T442 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-03-02 | 2024-03-24 |  | 0 | Paint | Downtown Avenue | 19630.94 | 21323.42 | Not started
C002 | Shopping Complex B | T218 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2024-06-09 | 2024-07-01 | 2024-07-01 | 100 | Roofing Sheets | Market Street | 39615.99 | 65541.64 | No issues
C002 | Shopping Complex B | T739 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2023-02-25 | 2023-03-10 | 2023-03-10 | 100 | Rebar | Market Street | 37668.42 | 54272.07 | No issues
C001 | Residential Building A | T380 | Plumbing Installations | Sarah Johnson | Not Started | High | 2024-03-05 | 2024-03-14 |  | 0 | Rebar | Plot 21, Riverside | 26948.87 | 0 | Not started
C002 | Shopping Complex B | T601 | Interior Painting | Rachel Green | Not Started | High | 2024-08-06 | 2024-08-20 |  | 0 | Concrete | Market Street | 48929.4 | 0 | Not started
C001 | Residential Building A | T915 | Plumbing Installations | John Miller | Completed | Low | 2024-03-09 | 2024-03-20 | 2024-03-20 | 100 | Copper Wires | Plot 21, Riverside | 35607.49 | 34326.81 | No issues
C002 | Shopping Complex B | T404 | Roofing | Emma White | Completed | Medium | 2024-07-07 | 2024-07-30 | 2024-07-30 | 100 | Cement | Market Street | 42854.46 | 63608.34 | No issues
C001 | Residential Building A | T399 | Concrete Pouring | Sarah Johnson | Completed | Low | 2024-10-21 | 2024-10-28 | 2024-10-28 | 100 | Rebar | Plot 21, Riverside | 39176.39 | 36743.95 | No issues
C001 | Residential Building A | T683 | Concrete Pouring | Emma White | In Progress | Low | 2024-02-19 | 2024-03-09 |  | 36 | Copper Wires | Plot 21, Riverside | 21585.03 | 14615.33 | In progress
C001 | Residential Building A | T454 | Plumbing Installations | Rachel Green | In Progress | Medium | 2023-06-26 | 2023-07-07 |  | 44 | Roofing Sheets | Plot 21, Riverside | 48296.13 | 47512.89 | In progress
C001 | Residential Building A | T219 | Concrete Pouring | Carlos Rivera | Completed | Low | 2023-02-05 | 2023-02-28 | 2023-02-28 | 100 | Steel Beams | Plot 21, Riverside | 6489.06 | 7464.52 | No issues
C004 | Warehouse D | T218 | Plumbing Installations | Emma White | Completed | Medium | 2023-01-17 | 2023-02-10 | 2023-02-10 | 100 | PVC Pipes | Industrial Park | 39260.6 | 39092.95 | No issues
C004 | Warehouse D | T651 | Site Survey | Emma White | Blocked | Low | 2024-05-13 | 2024-05-28 |  | 0 | Rebar | Industrial Park | 17486.8 | 18249.85 | Not started
C003 | Office Tower C | T828 | Foundation Excavation | Emma White | Blocked | Medium | 2024-12-09 | 2025-01-02 |  | 0 | PVC Pipes | Downtown Avenue | 43834.42 | 35071.58 | Not started
C004 | Warehouse D | T307 | Concrete Pouring | Mike Adams | In Progress | Low | 2023-03-20 | 2023-04-02 |  | 83 | Rebar | Industrial Park | 10739.92 | 11561.92 | In progress
C001 | Residential Building A | T734 | Roofing | Rachel Green | Completed | Medium | 2024-01-15 | 2024-02-02 | 2024-02-02 | 100 | Copper Wires | Plot 21, Riverside | 28701.23 | 23877.18 | No issues
C001 | Residential Building A | T305 | Roofing | Carlos Rivera | Not Started | Low | 2024-11-03 | 2024-11-13 |  | 0 | PVC Pipes | Plot 21, Riverside | 43171.64 | 0 | Not started
C003 | Office Tower C | T465 | Steel Framework Setup | Sarah Johnson | Completed | Low | 2024-10-09 | 2024-10-20 | 2024-10-20 | 100 | Concrete | Downtown Avenue | 19525.76 | 17140.59 | No issues
C001 | Residential Building A | T575 | Roofing | John Miller | Blocked | Medium | 2023-12-13 | 2024-01-09 |  | 0 | Cement | Plot 21, Riverside | 46561.34 | 33638.12 | Not started
C003 | Office Tower C | T199 | Electrical Wiring | Rachel Green | In Progress | High | 2023-12-18 | 2023-12-28 |  | 12 | Roofing Sheets | Downtown Avenue | 19131 | 21465.64 | In progress
C003 | Office Tower C | T642 | Site Survey | Carlos Rivera | Completed | High | 2023-04-01 | 2023-04-20 | 2023-04-20 | 100 | Rebar | Downtown Avenue | 7890.76 | 6950.87 | No issues
C002 | Shopping Complex B | T845 | Foundation Excavation | Dave Brown | Blocked | High | 2024-04-07 | 2024-05-03 |  | 0 | Rebar | Market Street | 45494.57 | 73681.53 | Not started
C004 | Warehouse D | T626 | Plumbing Installations | Grace Allen | Completed | Medium | 2024-05-18 | 2024-06-02 | 2024-06-02 | 100 | Copper Wires | Industrial Park | 16123.75 | 16089.11 | No issues
C001 | Residential Building A | T818 | Site Survey | Grace Allen | In Progress | Medium | 2023-12-05 | 2023-12-31 |  | 23 | Rebar | Plot 21, Riverside | 8173.15 | 8664.71 | In progress
C003 | Office Tower C | T630 | Roofing | Carlos Rivera | Not Started | High | 2023-11-08 | 2023-11-25 |  | 0 | Rebar | Downtown Avenue | 14886.41 | 0 | Not started
C002 | Shopping Complex B | T177 | Plumbing Installations | Mike Adams | Blocked | Medium | 2024-07-18 | 2024-08-16 |  | 0 | Steel Beams | Market Street | 25305.7 | 50005.99 | Not started
C003 | Office Tower C | T719 | Concrete Pouring | Emma White | In Progress | Low | 2023-09-21 | 2023-10-09 |  | 33 | Paint | Downtown Avenue | 22723.19 | 25785.16 | In progress
C002 | Shopping Complex B | T415 | Site Survey | John Miller | Blocked | High | 2023-11-22 | 2023-12-14 |  | 0 | Paint | Market Street | 15614.64 | 38627.05 | Not started
C001 | Residential Building A | T755 | Concrete Pouring | Grace Allen | Blocked | High | 2024-06-17 | 2024-07-01 |  | 0 | Rebar | Plot 21, Riverside | 31635.78 | 26052.32 | Not started
C003 | Office Tower C | T850 | Concrete Pouring | Grace Allen | Completed | Medium | 2024-01-02 | 2024-01-28 | 2024-01-28 | 100 | Cement | Downtown Avenue | 20869.47 | 23968.76 | No issues
C001 | Residential Building A | T296 | Plumbing Installations | Dave Brown | Not Started | Low | 2023-08-17 | 2023-08-25 |  | 0 | Paint | Plot 21, Riverside | 37930.28 | 0 | Not started
C001 | Residential Building A | T227 | Plumbing Installations | Emma White | In Progress | High | 2023-12-17 | 2023-12-25 |  | 15 | Cement | Plot 21, Riverside | 33938.04 | 22334.81 | In progress
C003 | Office Tower C | T935 | Plumbing Installations | Dave Brown | Blocked | High | 2023-09-28 | 2023-10-05 |  | 0 | Cement | Downtown Avenue | 31690.28 | 28050.3 | Not started
C003 | Office Tower C | T626 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-05-09 | 2024-05-31 |  | 0 | PVC Pipes | Downtown Avenue | 47332.22 | 32475.34 | Not started
C002 | Shopping Complex B | T271 | Electrical Wiring | John Miller | In Progress | High | 2023-04-12 | 2023-05-01 |  | 12 | Copper Wires | Market Street | 43594.42 | 69393.12 | In progress
C002 | Shopping Complex B | T306 | Concrete Pouring | John Miller | In Progress | Medium | 2023-10-24 | 2023-11-11 |  | 21 | Roofing Sheets | Market Street | 15545.91 | 40079.98 | In progress
C003 | Office Tower C | T425 | Site Survey | Mike Adams | In Progress | Medium | 2023-11-10 | 2023-12-08 |  | 56 | Paint | Downtown Avenue | 47992.79 | 31493.01 | In progress
C001 | Residential Building A | T582 | Interior Painting | Emma White | In Progress | Low | 2024-02-26 | 2024-03-06 |  | 94 | Paint | Plot 21, Riverside | 31905.21 | 27488.17 | In progress
C002 | Shopping Complex B | T263 | Foundation Excavation | John Miller | In Progress | Medium | 2023-01-19 | 2023-02-17 |  | 48 | Steel Beams | Market Street | 28297.28 | 59431.32 | In progress
C003 | Office Tower C | T514 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2023-11-07 | 2023-12-07 |  | 0 | Steel Beams | Downtown Avenue | 5467.14 | 0 | Not started
C001 | Residential Building A | T955 | Electrical Wiring | Dave Brown | Blocked | High | 2023-03-09 | 2023-04-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 23176.63 | 18755.51 | Not started
C003 | Office Tower C | T203 | Roofing | Grace Allen | In Progress | High | 2024-01-14 | 2024-02-08 |  | 14 | Steel Beams | Downtown Avenue | 46514.05 | 48833.11 | In progress
C001 | Residential Building A | T364 | Interior Painting | Rachel Green | In Progress | Medium | 2023-01-27 | 2023-02-15 |  | 47 | Cement | Plot 21, Riverside | 17361.05 | 12202.01 | In progress
C004 | Warehouse D | T737 | Roofing | Dave Brown | Not Started | Low | 2023-12-22 | 2024-01-10 |  | 0 | Paint | Industrial Park | 12560.62 | 0 | Not started
C004 | Warehouse D | T279 | Steel Framework Setup | Mike Adams | In Progress | Low | 2023-02-08 | 2023-02-19 |  | 57 | Steel Beams | Industrial Park | 34667.27 | 32947.84 | In progress
C002 | Shopping Complex B | T549 | Plumbing Installations | Grace Allen | Blocked | High | 2023-09-16 | 2023-10-05 |  | 0 | Steel Beams | Market Street | 36853.62 | 56406.77 | Not started
C004 | Warehouse D | T238 | Roofing | Carlos Rivera | Completed | Low | 2024-01-06 | 2024-02-02 | 2024-02-02 | 100 | PVC Pipes | Industrial Park | 7273.04 | 4513.83 | No issues
C002 | Shopping Complex B | T920 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-07-24 | 2023-08-12 |  | 60 | Rebar | Market Street | 32558.05 | 57693.94 | In progress
C001 | Residential Building A | T856 | Electrical Wiring | Carlos Rivera | Completed | High | 2023-08-09 | 2023-08-16 | 2023-08-16 | 100 | Concrete | Plot 21, Riverside | 8368.77 | 6159.56 | No issues
C003 | Office Tower C | T126 | Foundation Excavation | Emma White | In Progress | High | 2023-09-14 | 2023-09-23 |  | 50 | PVC Pipes | Downtown Avenue | 12668.85 | 10618.68 | In progress
C001 | Residential Building A | T660 | Concrete Pouring | Sarah Johnson | Completed | Low | 2024-02-01 | 2024-03-01 | 2024-03-01 | 100 | Paint | Plot 21, Riverside | 17409.3 | 13174.5 | No issues
C003 | Office Tower C | T227 | Steel Framework Setup | Emma White | Blocked | Low | 2024-07-03 | 2024-07-25 |  | 0 | Roofing Sheets | Downtown Avenue | 37787.12 | 36098.25 | Not started
C004 | Warehouse D | T398 | Concrete Pouring | Rachel Green | Not Started | Medium | 2023-04-15 | 2023-04-23 |  | 0 | Cement | Industrial Park | 27702.68 | 0 | Not started
C002 | Shopping Complex B | T153 | Site Survey | Mike Adams | Blocked | Low | 2023-10-09 | 2023-10-20 |  | 0 | PVC Pipes | Market Street | 37222.08 | 58402.57 | Not started
C002 | Shopping Complex B | T871 | Electrical Wiring | Emma White | Not Started | Medium | 2024-01-16 | 2024-02-05 |  | 0 | Roofing Sheets | Market Street | 11819.04 | 0 | Not started
C001 | Residential Building A | T231 | Electrical Wiring | Rachel Green | Blocked | Low | 2024-09-10 | 2024-10-09 |  | 0 | Rebar | Plot 21, Riverside | 38654.97 | 35658.19 | Not started
C004 | Warehouse D | T951 | Concrete Pouring | Grace Allen | In Progress | Medium | 2023-06-04 | 2023-06-22 |  | 64 | Concrete | Industrial Park | 43601.34 | 48914.28 | In progress
C001 | Residential Building A | T128 | Site Survey | Emma White | Completed | Low | 2024-01-26 | 2024-02-14 | 2024-02-14 | 100 | Cement | Plot 21, Riverside | 5922.13 | 5805.24 | No issues
C001 | Residential Building A | T529 | Roofing | Dave Brown | Blocked | Low | 2023-10-05 | 2023-10-25 |  | 0 | Rebar | Plot 21, Riverside | 19993.89 | 12146.29 | Not started
C003 | Office Tower C | T765 | Site Survey | Carlos Rivera | Not Started | Low | 2024-05-13 | 2024-06-03 |  | 0 | Copper Wires | Downtown Avenue | 24154.15 | 0 | Not started
C004 | Warehouse D | T885 | Concrete Pouring | Mike Adams | Blocked | Low | 2024-10-13 | 2024-10-20 |  | 0 | Concrete | Industrial Park | 24428.08 | 19800.78 | Not started
C002 | Shopping Complex B | T379 | Roofing | Rachel Green | Completed | Low | 2024-08-03 | 2024-08-29 | 2024-08-29 | 100 | PVC Pipes | Market Street | 45280.16 | 56029.71 | No issues
C004 | Warehouse D | T964 | Electrical Wiring | Carlos Rivera | Completed | Low | 2023-11-08 | 2023-11-17 | 2023-11-17 | 100 | Copper Wires | Industrial Park | 32274.12 | 28306.89 | No issues
C004 | Warehouse D | T598 | Foundation Excavation | Emma White | In Progress | High | 2024-04-01 | 2024-04-12 |  | 1 | Concrete | Industrial Park | 15360.95 | 16056.53 | In progress
C003 | Office Tower C | T374 | Concrete Pouring | Emma White | Blocked | High | 2023-11-22 | 2023-12-08 |  | 0 | Roofing Sheets | Downtown Avenue | 25685.55 | 18088.84 | Not started
C004 | Warehouse D | T718 | Site Survey | Dave Brown | In Progress | Medium | 2023-10-10 | 2023-11-08 |  | 52 | Rebar | Industrial Park | 48828.42 | 30047.06 | In progress
C001 | Residential Building A | T603 | Site Survey | Rachel Green | In Progress | High | 2024-10-01 | 2024-10-19 |  | 62 | PVC Pipes | Plot 21, Riverside | 25623.76 | 19836.46 | In progress
C002 | Shopping Complex B | T122 | Roofing | Dave Brown | In Progress | High | 2024-10-14 | 2024-11-07 |  | 64 | Rebar | Market Street | 32562.63 | 48838.07 | In progress
C003 | Office Tower C | T515 | Interior Painting | Emma White | Blocked | Low | 2023-03-05 | 2023-03-25 |  | 0 | Paint | Downtown Avenue | 12289.61 | 13731.53 | Not started
C002 | Shopping Complex B | T110 | Site Survey | John Miller | Not Started | Medium | 2024-11-13 | 2024-11-25 |  | 0 | Rebar | Market Street | 37619.55 | 0 | Not started
C004 | Warehouse D | T274 | Concrete Pouring | Emma White | Blocked | High | 2024-05-15 | 2024-05-25 |  | 0 | Steel Beams | Industrial Park | 8189.57 | 8650.76 | Not started
C001 | Residential Building A | T141 | Foundation Excavation | Mike Adams | Not Started | Medium | 2024-06-02 | 2024-06-29 |  | 0 | Steel Beams | Plot 21, Riverside | 37696.31 | 0 | Not started
C001 | Residential Building A | T757 | Concrete Pouring | Emma White | Completed | Low | 2023-08-19 | 2023-09-10 | 2023-09-10 | 100 | Steel Beams | Plot 21, Riverside | 16533.67 | 11704.93 | No issues
C003 | Office Tower C | T614 | Plumbing Installations | Mike Adams | Completed | High | 2023-10-04 | 2023-10-26 | 2023-10-26 | 100 | Copper Wires | Downtown Avenue | 10563.04 | 12470.15 | No issues
C004 | Warehouse D | T648 | Interior Painting | Mike Adams | Completed | Medium | 2024-06-16 | 2024-06-29 | 2024-06-29 | 100 | Rebar | Industrial Park | 26583.94 | 30560.21 | No issues
C001 | Residential Building A | T639 | Site Survey | Emma White | Completed | High | 2024-04-11 | 2024-04-29 | 2024-04-29 | 100 | Concrete | Plot 21, Riverside | 25146.5 | 28359.33 | No issues
C002 | Shopping Complex B | T777 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-10-28 | 2024-11-20 |  | 0 | Steel Beams | Market Street | 43308.5 | 60728.31 | Not started
C001 | Residential Building A | T923 | Interior Painting | Mike Adams | Blocked | High | 2023-11-07 | 2023-11-24 |  | 0 | Roofing Sheets | Plot 21, Riverside | 35521.37 | 31334.91 | Not started
C004 | Warehouse D | T381 | Concrete Pouring | Grace Allen | Not Started | Low | 2024-05-12 | 2024-05-21 |  | 0 | Paint | Industrial Park | 33994.92 | 0 | Not started
C003 | Office Tower C | T807 | Interior Painting | Carlos Rivera | Completed | Medium | 2024-05-28 | 2024-06-11 | 2024-06-11 | 100 | Paint | Downtown Avenue | 44243.2 | 44429.22 | No issues
C001 | Residential Building A | T649 | Plumbing Installations | John Miller | In Progress | Medium | 2024-12-15 | 2024-12-27 |  | 21 | Steel Beams | Plot 21, Riverside | 25014.42 | 17685.72 | In progress
C001 | Residential Building A | T625 | Site Survey | Sarah Johnson | Blocked | Low | 2024-11-18 | 2024-11-26 |  | 0 | Copper Wires | Plot 21, Riverside | 8585.97 | 5215.3 | Not started
C004 | Warehouse D | T159 | Interior Painting | Grace Allen | Completed | High | 2024-11-04 | 2024-11-14 | 2024-11-14 | 100 | Roofing Sheets | Industrial Park | 40071.59 | 37203.52 | No issues
C001 | Residential Building A | T549 | Concrete Pouring | Emma White | In Progress | High | 2024-09-07 | 2024-09-19 |  | 98 | PVC Pipes | Plot 21, Riverside | 47949 | 44223.61 | In progress
C003 | Office Tower C | T567 | Roofing | Mike Adams | In Progress | Low | 2024-05-14 | 2024-05-28 |  | 38 | Steel Beams | Downtown Avenue | 21841.88 | 15283.36 | In progress
C001 | Residential Building A | T528 | Plumbing Installations | Sarah Johnson | In Progress | High | 2024-04-14 | 2024-04-30 |  | 83 | Copper Wires | Plot 21, Riverside | 21702.07 | 20463.21 | In progress
C003 | Office Tower C | T992 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-05-14 | 2024-06-03 |  | 0 | PVC Pipes | Downtown Avenue | 26906.46 | 0 | Not started
C004 | Warehouse D | T190 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2024-01-03 | 2024-01-15 | 2024-01-15 | 100 | Copper Wires | Industrial Park | 13550.49 | 9094.06 | No issues
C002 | Shopping Complex B | T346 | Roofing | Sarah Johnson | In Progress | High | 2024-12-17 | 2025-01-16 |  | 50 | Roofing Sheets | Market Street | 18929.45 | 41956.37 | In progress
C003 | Office Tower C | T943 | Roofing | John Miller | Completed | Low | 2024-02-22 | 2024-03-09 | 2024-03-09 | 100 | Concrete | Downtown Avenue | 45016.52 | 50285.64 | No issues
C002 | Shopping Complex B | T199 | Steel Framework Setup | Grace Allen | Completed | High | 2023-04-18 | 2023-05-03 | 2023-05-03 | 100 | Roofing Sheets | Market Street | 32065.34 | 44989.2 | No issues
C004 | Warehouse D | T727 | Foundation Excavation | Sarah Johnson | Not Started | High | 2023-03-17 | 2023-04-11 |  | 0 | Roofing Sheets | Industrial Park | 16028.89 | 0 | Not started
C003 | Office Tower C | T125 | Plumbing Installations | Carlos Rivera | Completed | Medium | 2024-09-15 | 2024-10-05 | 2024-10-05 | 100 | Concrete | Downtown Avenue | 39729.13 | 40289.32 | No issues
C002 | Shopping Complex B | T782 | Concrete Pouring | Carlos Rivera | Completed | High | 2023-10-10 | 2023-11-02 | 2023-11-02 | 100 | Concrete | Market Street | 36132.28 | 51300.57 | No issues
C003 | Office Tower C | T295 | Steel Framework Setup | John Miller | In Progress | Medium | 2023-12-03 | 2023-12-16 |  | 58 | Concrete | Downtown Avenue | 44186.93 | 29190.07 | In progress
C001 | Residential Building A | T525 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2023-08-06 | 2023-08-30 |  | 2 | PVC Pipes | Plot 21, Riverside | 43053.52 | 46344.67 | In progress
C002 | Shopping Complex B | T895 | Site Survey | Sarah Johnson | Blocked | Low | 2023-07-04 | 2023-07-11 |  | 0 | Concrete | Market Street | 30178.34 | 56214.81 | Not started
C002 | Shopping Complex B | T383 | Interior Painting | Carlos Rivera | Blocked | High | 2024-06-14 | 2024-06-27 |  | 0 | PVC Pipes | Market Street | 7668.8 | 33843.8 | Not started
C003 | Office Tower C | T910 | Roofing | Carlos Rivera | Blocked | Medium | 2023-11-04 | 2023-11-23 |  | 0 | Rebar | Downtown Avenue | 46407.65 | 38786.43 | Not started
C001 | Residential Building A | T166 | Site Survey | Carlos Rivera | Completed | Low | 2024-08-09 | 2024-08-18 | 2024-08-18 | 100 | Paint | Plot 21, Riverside | 46101.48 | 43363.18 | No issues
C003 | Office Tower C | T326 | Roofing | Grace Allen | Completed | Low | 2024-07-21 | 2024-08-01 | 2024-08-01 | 100 | Concrete | Downtown Avenue | 33872.36 | 30815.94 | No issues
C004 | Warehouse D | T968 | Electrical Wiring | Carlos Rivera | In Progress | Medium | 2023-02-19 | 2023-03-21 |  | 36 | PVC Pipes | Industrial Park | 25805.25 | 25162.63 | In progress
C001 | Residential Building A | T908 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2024-08-23 | 2024-09-21 |  | 0 | Rebar | Plot 21, Riverside | 19851.57 | 20828.11 | Not started
C001 | Residential Building A | T712 | Electrical Wiring | Emma White | Completed | High | 2024-03-12 | 2024-03-20 | 2024-03-20 | 100 | PVC Pipes | Plot 21, Riverside | 32026.46 | 34351.68 | No issues
C001 | Residential Building A | T421 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-11-11 | 2023-11-24 |  | 0 | Cement | Plot 21, Riverside | 39780.75 | 44682.69 | Not started
C003 | Office Tower C | T700 | Interior Painting | Mike Adams | Not Started | High | 2024-11-16 | 2024-11-26 |  | 0 | Cement | Downtown Avenue | 6601.56 | 0 | Not started
C003 | Office Tower C | T767 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2024-01-06 | 2024-01-21 |  | 37 | Rebar | Downtown Avenue | 32397.19 | 30994.61 | In progress
C004 | Warehouse D | T936 | Site Survey | Dave Brown | In Progress | High | 2023-11-08 | 2023-11-26 |  | 70 | Steel Beams | Industrial Park | 16740.99 | 16339.93 | In progress
C004 | Warehouse D | T509 | Steel Framework Setup | Emma White | Not Started | Medium | 2024-12-14 | 2025-01-03 |  | 0 | PVC Pipes | Industrial Park | 47704.96 | 0 | Not started
C002 | Shopping Complex B | T526 | Site Survey | Carlos Rivera | In Progress | Low | 2023-12-19 | 2023-12-28 |  | 27 | Roofing Sheets | Market Street | 6164.92 | 32053.54 | In progress
C004 | Warehouse D | T161 | Plumbing Installations | Dave Brown | Not Started | Medium | 2023-11-05 | 2023-11-16 |  | 0 | Steel Beams | Industrial Park | 14918.48 | 0 | Not started
C003 | Office Tower C | T668 | Site Survey | Dave Brown | In Progress | High | 2023-07-15 | 2023-08-07 |  | 39 | Steel Beams | Downtown Avenue | 38300.62 | 44671.1 | In progress
C001 | Residential Building A | T879 | Plumbing Installations | Emma White | Not Started | Low | 2023-06-08 | 2023-07-08 |  | 0 | Roofing Sheets | Plot 21, Riverside | 21411.06 | 0 | Not started
C004 | Warehouse D | T582 | Plumbing Installations | Mike Adams | Blocked | Medium | 2023-10-07 | 2023-11-04 |  | 0 | Roofing Sheets | Industrial Park | 40195.86 | 36066.95 | Not started
C003 | Office Tower C | T665 | Concrete Pouring | Emma White | Not Started | Medium | 2024-03-10 | 2024-04-06 |  | 0 | Concrete | Downtown Avenue | 35679.46 | 0 | Not started
C003 | Office Tower C | T946 | Roofing | Emma White | Completed | High | 2024-12-17 | 2024-12-25 | 2024-12-25 | 100 | Copper Wires | Downtown Avenue | 12010.33 | 11749.1 | No issues
C001 | Residential Building A | T959 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2023-03-09 | 2023-03-21 |  | 0 | Copper Wires | Plot 21, Riverside | 10216.49 | 7550.13 | Not started
C001 | Residential Building A | T747 | Interior Painting | Emma White | Not Started | High | 2024-08-01 | 2024-08-15 |  | 0 | Steel Beams | Plot 21, Riverside | 37227.34 | 0 | Not started
C004 | Warehouse D | T463 | Concrete Pouring | Mike Adams | Completed | Medium | 2024-06-28 | 2024-07-20 | 2024-07-20 | 100 | Paint | Industrial Park | 24461.53 | 26226.74 | No issues
C004 | Warehouse D | T750 | Roofing | Carlos Rivera | In Progress | Low | 2023-01-13 | 2023-01-20 |  | 35 | PVC Pipes | Industrial Park | 15291.67 | 9524.33 | In progress
C004 | Warehouse D | T232 | Electrical Wiring | Grace Allen | Not Started | Low | 2024-02-08 | 2024-03-01 |  | 0 | Copper Wires | Industrial Park | 28698.46 | 0 | Not started
C003 | Office Tower C | T951 | Roofing | Sarah Johnson | In Progress | Low | 2023-05-12 | 2023-06-08 |  | 60 | Steel Beams | Downtown Avenue | 28443.06 | 24312.23 | In progress
C001 | Residential Building A | T155 | Interior Painting | Rachel Green | In Progress | Medium | 2024-10-13 | 2024-11-02 |  | 4 | Copper Wires | Plot 21, Riverside | 26811.96 | 18232.06 | In progress
C001 | Residential Building A | T349 | Steel Framework Setup | Emma White | In Progress | High | 2024-03-24 | 2024-04-18 |  | 41 | Paint | Plot 21, Riverside | 8794.32 | 5566.39 | In progress
C002 | Shopping Complex B | T839 | Site Survey | Dave Brown | Not Started | High | 2024-11-07 | 2024-11-22 |  | 0 | Steel Beams | Market Street | 22790.46 | 0 | Not started
C002 | Shopping Complex B | T222 | Site Survey | Sarah Johnson | Completed | Low | 2023-05-10 | 2023-05-24 | 2023-05-24 | 100 | Cement | Market Street | 15123.54 | 36141.33 | No issues
C004 | Warehouse D | T738 | Plumbing Installations | John Miller | Not Started | High | 2024-04-28 | 2024-05-08 |  | 0 | Steel Beams | Industrial Park | 13130.49 | 0 | Not started
C001 | Residential Building A | T806 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2024-09-04 | 2024-09-22 |  | 0 | Concrete | Plot 21, Riverside | 42137.61 | 0 | Not started
C001 | Residential Building A | T627 | Plumbing Installations | Dave Brown | In Progress | Medium | 2024-03-11 | 2024-04-03 |  | 0 | Copper Wires | Plot 21, Riverside | 11387.61 | 8795.59 | In progress
C003 | Office Tower C | T507 | Site Survey | Carlos Rivera | Not Started | Medium | 2023-05-16 | 2023-06-13 |  | 0 | Steel Beams | Downtown Avenue | 22172.63 | 0 | Not started
C004 | Warehouse D | T505 | Roofing | Rachel Green | Not Started | High | 2024-07-09 | 2024-07-30 |  | 0 | Steel Beams | Industrial Park | 39242.66 | 0 | Not started
C001 | Residential Building A | T564 | Interior Painting | Carlos Rivera | Blocked | Low | 2023-01-14 | 2023-01-27 |  | 0 | Cement | Plot 21, Riverside | 15831.27 | 13896.63 | Not started
C004 | Warehouse D | T129 | Interior Painting | Carlos Rivera | Not Started | Medium | 2024-05-06 | 2024-05-13 |  | 0 | Roofing Sheets | Industrial Park | 29340.21 | 0 | Not started
C004 | Warehouse D | T961 | Concrete Pouring | Dave Brown | Completed | Medium | 2023-11-11 | 2023-12-02 | 2023-12-02 | 100 | Steel Beams | Industrial Park | 17803.34 | 13374.71 | No issues
C002 | Shopping Complex B | T663 | Interior Painting | Sarah Johnson | In Progress | High | 2023-03-14 | 2023-03-24 |  | 69 | Concrete | Market Street | 25108.37 | 40919.27 | In progress
C001 | Residential Building A | T398 | Steel Framework Setup | Mike Adams | In Progress | Low | 2023-11-25 | 2023-12-03 |  | 32 | Concrete | Plot 21, Riverside | 18816.16 | 19310.55 | In progress
C004 | Warehouse D | T550 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-09-02 | 2023-09-24 |  | 0 | Cement | Industrial Park | 44913.51 | 37124.48 | Not started
C002 | Shopping Complex B | T892 | Steel Framework Setup | Emma White | Blocked | Low | 2023-12-11 | 2023-12-24 |  | 0 | Concrete | Market Street | 20473 | 39504.58 | Not started
C003 | Office Tower C | T893 | Site Survey | Grace Allen | Not Started | Medium | 2023-03-11 | 2023-03-21 |  | 0 | Paint | Downtown Avenue | 18488.71 | 0 | Not started
C001 | Residential Building A | T168 | Site Survey | Grace Allen | Completed | Low | 2024-07-18 | 2024-08-15 | 2024-08-15 | 100 | PVC Pipes | Plot 21, Riverside | 21546.74 | 21412.98 | No issues
C004 | Warehouse D | T444 | Interior Painting | John Miller | Not Started | Medium | 2024-06-15 | 2024-07-10 |  | 0 | PVC Pipes | Industrial Park | 23978.77 | 0 | Not started
C001 | Residential Building A | T849 | Concrete Pouring | Grace Allen | Completed | Medium | 2023-09-08 | 2023-10-03 | 2023-10-03 | 100 | Concrete | Plot 21, Riverside | 27695.03 | 25426.94 | No issues
C004 | Warehouse D | T563 | Steel Framework Setup | John Miller | Completed | Medium | 2023-05-20 | 2023-06-15 | 2023-06-15 | 100 | Rebar | Industrial Park | 39895.96 | 35324.79 | No issues
C003 | Office Tower C | T144 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-02-04 | 2024-02-24 | 2024-02-24 | 100 | Rebar | Downtown Avenue | 31299.3 | 27236.58 | No issues
C001 | Residential Building A | T941 | Foundation Excavation | Emma White | Blocked | Low | 2024-01-10 | 2024-01-29 |  | 0 | PVC Pipes | Plot 21, Riverside | 49772.43 | 31255.1 | Not started
C002 | Shopping Complex B | T936 | Foundation Excavation | John Miller | In Progress | Low | 2024-07-12 | 2024-07-24 |  | 50 | Concrete | Market Street | 15591.63 | 42290.25 | In progress
C003 | Office Tower C | T447 | Electrical Wiring | Dave Brown | Not Started | Low | 2024-05-25 | 2024-06-16 |  | 0 | PVC Pipes | Downtown Avenue | 24629.38 | 0 | Not started
C003 | Office Tower C | T631 | Concrete Pouring | Grace Allen | Not Started | High | 2023-04-08 | 2023-04-17 |  | 0 | PVC Pipes | Downtown Avenue | 37554.62 | 0 | Not started
C004 | Warehouse D | T557 | Interior Painting | John Miller | Completed | Medium | 2024-07-20 | 2024-08-11 | 2024-08-11 | 100 | PVC Pipes | Industrial Park | 19649.63 | 16212.14 | No issues
C004 | Warehouse D | T790 | Electrical Wiring | Grace Allen | Completed | Low | 2024-02-24 | 2024-03-08 | 2024-03-08 | 100 | Paint | Industrial Park | 29021.49 | 18740.31 | No issues
C003 | Office Tower C | T960 | Electrical Wiring | John Miller | Not Started | Medium | 2023-02-01 | 2023-02-18 |  | 0 | Cement | Downtown Avenue | 34548.21 | 0 | Not started
C004 | Warehouse D | T441 | Electrical Wiring | Emma White | Completed | High | 2024-02-17 | 2024-03-17 | 2024-03-17 | 100 | Cement | Industrial Park | 14668.29 | 12855.31 | No issues
C002 | Shopping Complex B | T268 | Site Survey | Emma White | Completed | High | 2024-10-24 | 2024-11-22 | 2024-11-22 | 100 | Concrete | Market Street | 27940.87 | 58899.18 | No issues
C001 | Residential Building A | T674 | Steel Framework Setup | Rachel Green | Not Started | High | 2023-02-06 | 2023-02-28 |  | 0 | Paint | Plot 21, Riverside | 35394.29 | 0 | Not started
C004 | Warehouse D | T234 | Electrical Wiring | Grace Allen | In Progress | High | 2023-05-12 | 2023-05-25 |  | 33 | Roofing Sheets | Industrial Park | 13954.01 | 15798.03 | In progress
C003 | Office Tower C | T626 | Plumbing Installations | Dave Brown | Completed | Low | 2023-06-19 | 2023-07-02 | 2023-07-02 | 100 | PVC Pipes | Downtown Avenue | 30440.49 | 25578.01 | No issues
C003 | Office Tower C | T471 | Roofing | Mike Adams | Completed | Medium | 2023-11-26 | 2023-12-10 | 2023-12-10 | 100 | Steel Beams | Downtown Avenue | 9346.65 | 7704.77 | No issues
C004 | Warehouse D | T553 | Foundation Excavation | Emma White | In Progress | Medium | 2023-06-25 | 2023-07-03 |  | 62 | Rebar | Industrial Park | 18209.2 | 14205.3 | In progress
C001 | Residential Building A | T449 | Concrete Pouring | Carlos Rivera | Not Started | High | 2024-08-09 | 2024-08-31 |  | 0 | PVC Pipes | Plot 21, Riverside | 28000.39 | 0 | Not started
C002 | Shopping Complex B | T728 | Site Survey | Carlos Rivera | Completed | Medium | 2024-04-20 | 2024-05-02 | 2024-05-02 | 100 | Cement | Market Street | 24717.04 | 42918.14 | No issues
C004 | Warehouse D | T188 | Steel Framework Setup | Grace Allen | In Progress | High | 2023-08-14 | 2023-08-31 |  | 32 | Copper Wires | Industrial Park | 25881.34 | 30467.32 | In progress
C002 | Shopping Complex B | T782 | Concrete Pouring | Emma White | Blocked | Low | 2023-10-25 | 2023-11-24 |  | 0 | Steel Beams | Market Street | 10525.18 | 34500.08 | Not started
C001 | Residential Building A | T968 | Steel Framework Setup | Dave Brown | Completed | Medium | 2023-03-26 | 2023-04-12 | 2023-04-12 | 100 | PVC Pipes | Plot 21, Riverside | 6441.83 | 5776.5 | No issues
C002 | Shopping Complex B | T190 | Roofing | Dave Brown | Completed | High | 2024-01-28 | 2024-02-27 | 2024-02-27 | 100 | Cement | Market Street | 35881.8 | 47052.49 | No issues
C003 | Office Tower C | T637 | Electrical Wiring | Emma White | Blocked | High | 2024-03-16 | 2024-04-12 |  | 0 | Roofing Sheets | Downtown Avenue | 17161.88 | 16457.39 | Not started
C003 | Office Tower C | T554 | Site Survey | Grace Allen | In Progress | High | 2024-04-22 | 2024-05-02 |  | 37 | Cement | Downtown Avenue | 24476.82 | 16653.19 | In progress
C001 | Residential Building A | T908 | Roofing | Carlos Rivera | In Progress | High | 2024-10-19 | 2024-10-31 |  | 29 | Rebar | Plot 21, Riverside | 6095.55 | 5828.57 | In progress
C001 | Residential Building A | T819 | Electrical Wiring | Grace Allen | Completed | Medium | 2023-01-09 | 2023-02-08 | 2023-02-08 | 100 | Steel Beams | Plot 21, Riverside | 22919.39 | 26876.97 | No issues
C001 | Residential Building A | T873 | Plumbing Installations | Emma White | Not Started | Medium | 2023-07-06 | 2023-08-05 |  | 0 | Steel Beams | Plot 21, Riverside | 48209.73 | 0 | Not started
C003 | Office Tower C | T677 | Concrete Pouring | Rachel Green | In Progress | Low | 2024-09-10 | 2024-09-27 |  | 24 | Paint | Downtown Avenue | 13370.12 | 15775.44 | In progress
C003 | Office Tower C | T361 | Concrete Pouring | Mike Adams | Not Started | Low | 2024-07-10 | 2024-07-22 |  | 0 | Copper Wires | Downtown Avenue | 37572.55 | 0 | Not started
C001 | Residential Building A | T800 | Concrete Pouring | Dave Brown | Completed | High | 2023-08-26 | 2023-09-02 | 2023-09-02 | 100 | Cement | Plot 21, Riverside | 32880.87 | 29492.87 | No issues
C003 | Office Tower C | T990 | Steel Framework Setup | Emma White | Completed | High | 2023-05-02 | 2023-05-24 | 2023-05-24 | 100 | Paint | Downtown Avenue | 7509.55 | 4637.15 | No issues
C001 | Residential Building A | T332 | Steel Framework Setup | Emma White | In Progress | Low | 2024-05-04 | 2024-05-13 |  | 12 | PVC Pipes | Plot 21, Riverside | 29941.53 | 27152.59 | In progress
C002 | Shopping Complex B | T743 | Concrete Pouring | Dave Brown | Completed | Medium | 2023-02-04 | 2023-02-27 | 2023-02-27 | 100 | Concrete | Market Street | 10719.94 | 37025.33 | No issues
C004 | Warehouse D | T578 | Roofing | Emma White | Completed | Low | 2023-05-05 | 2023-05-19 | 2023-05-19 | 100 | Steel Beams | Industrial Park | 20377.45 | 17585.68 | No issues
C004 | Warehouse D | T536 | Foundation Excavation | Sarah Johnson | Blocked | High | 2024-11-01 | 2024-12-01 |  | 0 | Steel Beams | Industrial Park | 48477.92 | 57023.92 | Not started
C004 | Warehouse D | T549 | Concrete Pouring | Emma White | Not Started | High | 2024-01-09 | 2024-02-04 |  | 0 | Paint | Industrial Park | 31156 | 0 | Not started
C002 | Shopping Complex B | T620 | Roofing | Dave Brown | Not Started | High | 2024-10-19 | 2024-11-12 |  | 0 | Cement | Market Street | 14653.69 | 0 | Not started
C004 | Warehouse D | T810 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-01-13 | 2023-01-25 |  | 0 | Rebar | Industrial Park | 20081.6 | 0 | Not started
C001 | Residential Building A | T883 | Concrete Pouring | Mike Adams | In Progress | Low | 2024-09-16 | 2024-10-05 |  | 10 | Rebar | Plot 21, Riverside | 49249.88 | 52050.26 | In progress
C001 | Residential Building A | T393 | Concrete Pouring | Mike Adams | Not Started | High | 2024-05-19 | 2024-05-29 |  | 0 | Copper Wires | Plot 21, Riverside | 24707.58 | 0 | Not started
C001 | Residential Building A | T673 | Interior Painting | Dave Brown | Completed | Low | 2023-12-06 | 2024-01-03 | 2024-01-03 | 100 | PVC Pipes | Plot 21, Riverside | 12175.53 | 11266.63 | No issues
C004 | Warehouse D | T287 | Concrete Pouring | John Miller | Completed | Low | 2024-08-21 | 2024-09-13 | 2024-09-13 | 100 | Concrete | Industrial Park | 45019.41 | 53658.8 | No issues
C001 | Residential Building A | T532 | Site Survey | John Miller | Not Started | High | 2024-10-14 | 2024-11-09 |  | 0 | Roofing Sheets | Plot 21, Riverside | 42652.75 | 0 | Not started
C004 | Warehouse D | T979 | Concrete Pouring | Grace Allen | Blocked | Low | 2023-06-20 | 2023-07-18 |  | 0 | PVC Pipes | Industrial Park | 40551.54 | 24944.78 | Not started
C001 | Residential Building A | T753 | Interior Painting | John Miller | Blocked | High | 2024-05-03 | 2024-05-24 |  | 0 | Steel Beams | Plot 21, Riverside | 45615.82 | 43927.82 | Not started
C002 | Shopping Complex B | T785 | Roofing | Emma White | In Progress | High | 2024-08-19 | 2024-09-14 |  | 91 | Roofing Sheets | Market Street | 42075.89 | 73096 | In progress
C002 | Shopping Complex B | T923 | Concrete Pouring | Mike Adams | In Progress | High | 2023-03-08 | 2023-03-20 |  | 95 | Copper Wires | Market Street | 39309.08 | 70243.73 | In progress
C002 | Shopping Complex B | T861 | Site Survey | Dave Brown | Blocked | Low | 2024-08-23 | 2024-09-21 |  | 0 | PVC Pipes | Market Street | 45838.59 | 77820.37 | Not started
C001 | Residential Building A | T689 | Plumbing Installations | John Miller | Blocked | Medium | 2024-05-25 | 2024-06-12 |  | 0 | Rebar | Plot 21, Riverside | 25763.83 | 15577.35 | Not started
C003 | Office Tower C | T881 | Steel Framework Setup | Dave Brown | Completed | Medium | 2024-07-16 | 2024-08-11 | 2024-08-11 | 100 | Paint | Downtown Avenue | 26580.93 | 18370.46 | No issues
C003 | Office Tower C | T465 | Interior Painting | Rachel Green | Completed | Low | 2023-12-10 | 2023-12-23 | 2023-12-23 | 100 | PVC Pipes | Downtown Avenue | 44836.78 | 38355.76 | No issues
C003 | Office Tower C | T534 | Electrical Wiring | Dave Brown | In Progress | Low | 2023-02-16 | 2023-03-17 |  | 78 | Rebar | Downtown Avenue | 29293.5 | 25791.84 | In progress
C001 | Residential Building A | T952 | Interior Painting | Dave Brown | Completed | Low | 2024-07-18 | 2024-08-06 | 2024-08-06 | 100 | Cement | Plot 21, Riverside | 26758.87 | 30125.54 | No issues
C001 | Residential Building A | T183 | Foundation Excavation | Dave Brown | Blocked | High | 2024-05-25 | 2024-06-09 |  | 0 | Rebar | Plot 21, Riverside | 17794.89 | 16218.24 | Not started
C003 | Office Tower C | T334 | Steel Framework Setup | Dave Brown | Completed | Low | 2023-01-07 | 2023-02-04 | 2023-02-04 | 100 | Rebar | Downtown Avenue | 21330.7 | 20780.62 | No issues
C002 | Shopping Complex B | T483 | Site Survey | Carlos Rivera | In Progress | Medium | 2023-08-15 | 2023-09-04 |  | 90 | Steel Beams | Market Street | 21456.76 | 47729.47 | In progress
C001 | Residential Building A | T498 | Roofing | Grace Allen | Not Started | Low | 2023-03-11 | 2023-04-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 24222.19 | 0 | Not started
C003 | Office Tower C | T243 | Concrete Pouring | Dave Brown | Not Started | Low | 2024-06-01 | 2024-06-08 |  | 0 | Copper Wires | Downtown Avenue | 46141.17 | 0 | Not started
C002 | Shopping Complex B | T977 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-10-25 | 2023-11-05 |  | 0 | Roofing Sheets | Market Street | 44179.57 | 0 | Not started
C004 | Warehouse D | T627 | Foundation Excavation | Mike Adams | Completed | Medium | 2023-03-25 | 2023-04-12 | 2023-04-12 | 100 | Concrete | Industrial Park | 25584.22 | 17803.51 | No issues
C004 | Warehouse D | T361 | Foundation Excavation | Sarah Johnson | Not Started | High | 2024-12-05 | 2024-12-13 |  | 0 | PVC Pipes | Industrial Park | 18103.95 | 0 | Not started
C004 | Warehouse D | T217 | Foundation Excavation | Rachel Green | Not Started | Low | 2024-06-19 | 2024-07-13 |  | 0 | Copper Wires | Industrial Park | 34202.24 | 0 | Not started
C001 | Residential Building A | T276 | Electrical Wiring | Mike Adams | Completed | High | 2023-02-25 | 2023-03-06 | 2023-03-06 | 100 | Copper Wires | Plot 21, Riverside | 25813.54 | 22767.14 | No issues
C003 | Office Tower C | T884 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2023-03-27 | 2023-04-06 |  | 36 | Steel Beams | Downtown Avenue | 23661.89 | 26655.21 | In progress
C003 | Office Tower C | T608 | Steel Framework Setup | John Miller | In Progress | High | 2023-06-01 | 2023-06-16 |  | 37 | Roofing Sheets | Downtown Avenue | 10246.09 | 8171.8 | In progress
C002 | Shopping Complex B | T328 | Interior Painting | Sarah Johnson | Completed | Medium | 2024-04-08 | 2024-04-19 | 2024-04-19 | 100 | Cement | Market Street | 22725.4 | 41627.58 | No issues
C002 | Shopping Complex B | T835 | Roofing | Grace Allen | Completed | Medium | 2024-01-13 | 2024-02-11 | 2024-02-11 | 100 | Paint | Market Street | 5395.67 | 31418.23 | No issues
C002 | Shopping Complex B | T879 | Foundation Excavation | Emma White | In Progress | High | 2023-03-12 | 2023-03-31 |  | 80 | PVC Pipes | Market Street | 6942.94 | 30954.79 | In progress
C001 | Residential Building A | T677 | Concrete Pouring | Dave Brown | Completed | High | 2024-02-04 | 2024-02-11 | 2024-02-11 | 100 | Concrete | Plot 21, Riverside | 11177.09 | 12495.59 | No issues
C004 | Warehouse D | T449 | Concrete Pouring | Mike Adams | Completed | Medium | 2023-11-04 | 2023-12-03 | 2023-12-03 | 100 | Steel Beams | Industrial Park | 42783.29 | 44593.91 | No issues
C001 | Residential Building A | T131 | Interior Painting | Rachel Green | Not Started | Medium | 2023-02-15 | 2023-03-15 |  | 0 | Paint | Plot 21, Riverside | 39442.09 | 0 | Not started
C004 | Warehouse D | T432 | Interior Painting | Mike Adams | Completed | Medium | 2023-09-13 | 2023-09-22 | 2023-09-22 | 100 | Rebar | Industrial Park | 36355.01 | 41504.89 | No issues
C003 | Office Tower C | T216 | Interior Painting | Rachel Green | In Progress | Medium | 2023-01-12 | 2023-02-11 |  | 82 | Roofing Sheets | Downtown Avenue | 39105.77 | 33517.54 | In progress
C004 | Warehouse D | T123 | Concrete Pouring | Rachel Green | Blocked | High | 2024-10-12 | 2024-11-07 |  | 0 | Concrete | Industrial Park | 9188.03 | 10811.04 | Not started
C004 | Warehouse D | T185 | Foundation Excavation | Emma White | In Progress | Low | 2024-06-18 | 2024-06-25 |  | 76 | PVC Pipes | Industrial Park | 47265.52 | 31939.35 | In progress
C003 | Office Tower C | T829 | Plumbing Installations | Dave Brown | Blocked | High | 2024-06-08 | 2024-06-17 |  | 0 | Concrete | Downtown Avenue | 46454.86 | 50749.73 | Not started
C002 | Shopping Complex B | T333 | Steel Framework Setup | Dave Brown | Not Started | Low | 2024-10-04 | 2024-10-24 |  | 0 | Cement | Market Street | 39480.72 | 0 | Not started
C002 | Shopping Complex B | T446 | Roofing | Dave Brown | Completed | Medium | 2023-07-19 | 2023-08-17 | 2023-08-17 | 100 | Rebar | Market Street | 41985.09 | 65956.59 | No issues
C003 | Office Tower C | T170 | Site Survey | John Miller | Blocked | Low | 2024-03-06 | 2024-03-28 |  | 0 | Paint | Downtown Avenue | 5431.99 | 3425.11 | Not started
C001 | Residential Building A | T470 | Interior Painting | Dave Brown | In Progress | High | 2024-06-02 | 2024-06-27 |  | 32 | Rebar | Plot 21, Riverside | 8316.42 | 7910.84 | In progress
C004 | Warehouse D | T487 | Plumbing Installations | Dave Brown | Blocked | Low | 2023-12-24 | 2024-01-12 |  | 0 | PVC Pipes | Industrial Park | 37526.88 | 28921.73 | Not started
C002 | Shopping Complex B | T619 | Steel Framework Setup | Mike Adams | Not Started | Medium | 2023-08-26 | 2023-09-13 |  | 0 | Cement | Market Street | 25255.57 | 0 | Not started
C004 | Warehouse D | T173 | Electrical Wiring | Carlos Rivera | Blocked | High | 2023-07-13 | 2023-07-29 |  | 0 | Copper Wires | Industrial Park | 7227.95 | 5558.89 | Not started
C003 | Office Tower C | T385 | Foundation Excavation | Grace Allen | Blocked | High | 2024-12-10 | 2024-12-29 |  | 0 | Copper Wires | Downtown Avenue | 27923.89 | 21150.16 | Not started
C003 | Office Tower C | T772 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-04-12 | 2023-04-22 |  | 0 | PVC Pipes | Downtown Avenue | 43830.39 | 0 | Not started
C003 | Office Tower C | T574 | Concrete Pouring | Dave Brown | Not Started | Low | 2024-05-01 | 2024-05-18 |  | 0 | Paint | Downtown Avenue | 41759.52 | 0 | Not started
C004 | Warehouse D | T918 | Site Survey | Mike Adams | In Progress | Medium | 2024-07-24 | 2024-08-21 |  | 92 | Roofing Sheets | Industrial Park | 37454.09 | 24499.19 | In progress
C003 | Office Tower C | T995 | Steel Framework Setup | Dave Brown | Completed | High | 2023-08-11 | 2023-08-25 | 2023-08-25 | 100 | Roofing Sheets | Downtown Avenue | 31632.2 | 21900.08 | No issues
C002 | Shopping Complex B | T590 | Roofing | Dave Brown | Blocked | High | 2023-04-01 | 2023-04-17 |  | 0 | PVC Pipes | Market Street | 9399.18 | 33298.86 | Not started
C003 | Office Tower C | T850 | Site Survey | Grace Allen | Not Started | Low | 2023-10-10 | 2023-10-28 |  | 0 | Paint | Downtown Avenue | 12931.67 | 0 | Not started
C003 | Office Tower C | T959 | Roofing | Emma White | Blocked | High | 2024-07-02 | 2024-07-24 |  | 0 | PVC Pipes | Downtown Avenue | 41874.64 | 48402.71 | Not started
C001 | Residential Building A | T405 | Steel Framework Setup | Emma White | Not Started | High | 2023-02-19 | 2023-03-11 |  | 0 | Roofing Sheets | Plot 21, Riverside | 23060.93 | 0 | Not started
C002 | Shopping Complex B | T775 | Concrete Pouring | Dave Brown | Blocked | Medium | 2024-10-09 | 2024-10-21 |  | 0 | Cement | Market Street | 30345.71 | 52873.57 | Not started
C001 | Residential Building A | T843 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-07-03 | 2023-07-10 | 2023-07-10 | 100 | Copper Wires | Plot 21, Riverside | 42056.94 | 33781.42 | No issues
C004 | Warehouse D | T935 | Steel Framework Setup | Grace Allen | In Progress | Low | 2024-05-13 | 2024-06-01 |  | 98 | Rebar | Industrial Park | 19018.6 | 12226.45 | In progress
C004 | Warehouse D | T134 | Interior Painting | Mike Adams | In Progress | Medium | 2024-07-05 | 2024-07-12 |  | 16 | PVC Pipes | Industrial Park | 8628.98 | 9795.37 | In progress
C001 | Residential Building A | T464 | Plumbing Installations | Sarah Johnson | In Progress | High | 2024-07-10 | 2024-08-06 |  | 97 | Rebar | Plot 21, Riverside | 14100.72 | 13223.46 | In progress
C004 | Warehouse D | T245 | Foundation Excavation | Emma White | In Progress | Medium | 2023-06-16 | 2023-07-11 |  | 95 | Copper Wires | Industrial Park | 33875.07 | 32124.62 | In progress
C004 | Warehouse D | T672 | Roofing | Grace Allen | Not Started | Low | 2023-06-22 | 2023-07-03 |  | 0 | Roofing Sheets | Industrial Park | 10202.59 | 0 | Not started
C004 | Warehouse D | T573 | Site Survey | John Miller | In Progress | Low | 2024-02-06 | 2024-02-28 |  | 98 | Roofing Sheets | Industrial Park | 10232.68 | 10277.53 | In progress
C001 | Residential Building A | T112 | Interior Painting | Dave Brown | Completed | Low | 2024-01-16 | 2024-02-05 | 2024-02-05 | 100 | Paint | Plot 21, Riverside | 7432.96 | 6686.87 | No issues
C003 | Office Tower C | T560 | Site Survey | Dave Brown | Not Started | High | 2023-02-22 | 2023-03-06 |  | 0 | PVC Pipes | Downtown Avenue | 38758.05 | 0 | Not started
C003 | Office Tower C | T970 | Roofing | Sarah Johnson | Not Started | High | 2024-02-13 | 2024-02-21 |  | 0 | Rebar | Downtown Avenue | 15174.88 | 0 | Not started
C004 | Warehouse D | T543 | Plumbing Installations | Emma White | In Progress | Medium | 2024-10-03 | 2024-10-11 |  | 58 | PVC Pipes | Industrial Park | 43976 | 29060.97 | In progress
C004 | Warehouse D | T743 | Foundation Excavation | Emma White | In Progress | High | 2023-12-17 | 2024-01-08 |  | 76 | Paint | Industrial Park | 6543.72 | 6765.46 | In progress
C001 | Residential Building A | T966 | Roofing | Emma White | Completed | Low | 2024-04-13 | 2024-05-08 | 2024-05-08 | 100 | Steel Beams | Plot 21, Riverside | 30767.42 | 22600.25 | No issues
C002 | Shopping Complex B | T561 | Foundation Excavation | Carlos Rivera | Blocked | Low | 2023-09-13 | 2023-10-03 |  | 0 | Concrete | Market Street | 11696.57 | 34889.42 | Not started
C004 | Warehouse D | T227 | Roofing | Emma White | Not Started | Low | 2023-08-08 | 2023-09-07 |  | 0 | Concrete | Industrial Park | 44062.45 | 0 | Not started
C003 | Office Tower C | T503 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2024-03-17 | 2024-04-07 |  | 0 | Copper Wires | Downtown Avenue | 17207.03 | 12576.82 | Not started
C001 | Residential Building A | T369 | Roofing | Carlos Rivera | Not Started | High | 2024-09-08 | 2024-09-27 |  | 0 | PVC Pipes | Plot 21, Riverside | 22455.84 | 0 | Not started
C002 | Shopping Complex B | T380 | Roofing | John Miller | In Progress | Low | 2024-06-20 | 2024-07-02 |  | 94 | PVC Pipes | Market Street | 11384.6 | 32724.43 | In progress
C003 | Office Tower C | T423 | Interior Painting | John Miller | Not Started | High | 2023-10-06 | 2023-10-19 |  | 0 | Roofing Sheets | Downtown Avenue | 36465.9 | 0 | Not started
C002 | Shopping Complex B | T275 | Interior Painting | Mike Adams | Completed | High | 2023-05-24 | 2023-06-10 | 2023-06-10 | 100 | Roofing Sheets | Market Street | 14042.07 | 38898.64 | No issues
C004 | Warehouse D | T129 | Site Survey | Grace Allen | Blocked | Medium | 2023-12-24 | 2024-01-07 |  | 0 | Roofing Sheets | Industrial Park | 27683.22 | 19967.6 | Not started
C004 | Warehouse D | T421 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-02-07 | 2023-02-20 |  | 0 | Cement | Industrial Park | 32298.19 | 0 | Not started
C001 | Residential Building A | T803 | Roofing | Mike Adams | Completed | Medium | 2024-09-26 | 2024-10-07 | 2024-10-07 | 100 | Concrete | Plot 21, Riverside | 10384.29 | 8887.7 | No issues
C003 | Office Tower C | T319 | Roofing | Carlos Rivera | Blocked | Low | 2023-06-28 | 2023-07-07 |  | 0 | Paint | Downtown Avenue | 15150.52 | 11724.69 | Not started
C004 | Warehouse D | T376 | Foundation Excavation | Mike Adams | Completed | Medium | 2024-10-16 | 2024-11-12 | 2024-11-12 | 100 | Concrete | Industrial Park | 35866.75 | 24024.29 | No issues
C003 | Office Tower C | T796 | Concrete Pouring | Rachel Green | Not Started | Low | 2023-12-11 | 2024-01-09 |  | 0 | Paint | Downtown Avenue | 42633.9 | 0 | Not started
C004 | Warehouse D | T250 | Interior Painting | Emma White | Not Started | Low | 2023-03-02 | 2023-03-25 |  | 0 | PVC Pipes | Industrial Park | 15140.31 | 0 | Not started
C003 | Office Tower C | T331 | Foundation Excavation | Emma White | Blocked | Medium | 2023-01-07 | 2023-01-16 |  | 0 | Concrete | Downtown Avenue | 22500.95 | 22341.43 | Not started
C002 | Shopping Complex B | T153 | Interior Painting | Rachel Green | Not Started | High | 2024-12-06 | 2025-01-04 |  | 0 | Rebar | Market Street | 40416.73 | 0 | Not started
C001 | Residential Building A | T901 | Interior Painting | Emma White | Completed | Low | 2023-10-06 | 2023-10-16 | 2023-10-16 | 100 | Roofing Sheets | Plot 21, Riverside | 36605.35 | 30366.44 | No issues
C002 | Shopping Complex B | T363 | Site Survey | Sarah Johnson | Not Started | High | 2023-05-23 | 2023-06-15 |  | 0 | Paint | Market Street | 21341.92 | 0 | Not started
C004 | Warehouse D | T610 | Site Survey | Rachel Green | Not Started | Medium | 2024-09-04 | 2024-10-01 |  | 0 | Rebar | Industrial Park | 27115.74 | 0 | Not started
C001 | Residential Building A | T930 | Plumbing Installations | Dave Brown | Completed | High | 2024-01-09 | 2024-01-22 | 2024-01-22 | 100 | Roofing Sheets | Plot 21, Riverside | 9306.49 | 9489 | No issues
C004 | Warehouse D | T420 | Electrical Wiring | Grace Allen | Blocked | Low | 2023-01-10 | 2023-01-31 |  | 0 | PVC Pipes | Industrial Park | 31745.59 | 34539.07 | Not started
C001 | Residential Building A | T738 | Electrical Wiring | Dave Brown | Completed | High | 2024-06-21 | 2024-07-17 | 2024-07-17 | 100 | PVC Pipes | Plot 21, Riverside | 7407.19 | 8592.24 | No issues
C003 | Office Tower C | T152 | Electrical Wiring | Carlos Rivera | In Progress | High | 2023-07-10 | 2023-07-21 |  | 74 | PVC Pipes | Downtown Avenue | 45345.59 | 53674.59 | In progress
C004 | Warehouse D | T550 | Electrical Wiring | John Miller | Blocked | High | 2024-04-28 | 2024-05-19 |  | 0 | Copper Wires | Industrial Park | 35764.43 | 36558.71 | Not started
C002 | Shopping Complex B | T636 | Interior Painting | Grace Allen | Completed | Low | 2023-10-27 | 2023-11-22 | 2023-11-22 | 100 | Copper Wires | Market Street | 45059.57 | 64040.2 | No issues
C003 | Office Tower C | T221 | Concrete Pouring | Grace Allen | Completed | High | 2024-05-24 | 2024-06-04 | 2024-06-04 | 100 | Copper Wires | Downtown Avenue | 18664.81 | 19381.16 | No issues
C003 | Office Tower C | T771 | Site Survey | Sarah Johnson | Completed | Low | 2024-12-09 | 2025-01-07 | 2025-01-07 | 100 | Paint | Downtown Avenue | 23622.52 | 15957.31 | No issues
C002 | Shopping Complex B | T356 | Steel Framework Setup | Dave Brown | In Progress | High | 2023-07-26 | 2023-08-17 |  | 3 | Roofing Sheets | Market Street | 20114.68 | 46334.39 | In progress
C002 | Shopping Complex B | T194 | Electrical Wiring | Grace Allen | In Progress | Low | 2024-04-12 | 2024-04-19 |  | 79 | Concrete | Market Street | 19750.77 | 46501.35 | In progress
C002 | Shopping Complex B | T609 | Site Survey | Carlos Rivera | Blocked | Low | 2023-05-18 | 2023-06-12 |  | 0 | Concrete | Market Street | 39259.55 | 55017.29 | Not started
C001 | Residential Building A | T660 | Concrete Pouring | Mike Adams | Not Started | Medium | 2024-08-05 | 2024-08-27 |  | 0 | Copper Wires | Plot 21, Riverside | 40582.35 | 0 | Not started
C002 | Shopping Complex B | T636 | Electrical Wiring | Rachel Green | Not Started | High | 2023-04-03 | 2023-04-19 |  | 0 | Concrete | Market Street | 23146.48 | 0 | Not started
C001 | Residential Building A | T173 | Steel Framework Setup | John Miller | Blocked | Low | 2024-04-09 | 2024-04-23 |  | 0 | Rebar | Plot 21, Riverside | 11863.58 | 12635.45 | Not started
C004 | Warehouse D | T781 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-10-15 | 2024-11-13 |  | 0 | Rebar | Industrial Park | 13906.63 | 0 | Not started
C002 | Shopping Complex B | T934 | Electrical Wiring | Mike Adams | Blocked | Low | 2023-12-02 | 2023-12-30 |  | 0 | Concrete | Market Street | 33449.68 | 53795.89 | Not started
C004 | Warehouse D | T591 | Roofing | John Miller | In Progress | Medium | 2023-12-07 | 2023-12-29 |  | 17 | PVC Pipes | Industrial Park | 40709.33 | 46093.4 | In progress
C003 | Office Tower C | T910 | Steel Framework Setup | Mike Adams | In Progress | Low | 2023-03-07 | 2023-03-27 |  | 81 | Copper Wires | Downtown Avenue | 44724.94 | 28660.6 | In progress
C002 | Shopping Complex B | T354 | Roofing | Mike Adams | Not Started | High | 2024-11-28 | 2024-12-26 |  | 0 | Copper Wires | Market Street | 26531.6 | 0 | Not started
C002 | Shopping Complex B | T633 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-10-11 | 2024-10-28 |  | 15 | Cement | Market Street | 6539.18 | 32760.52 | In progress
C003 | Office Tower C | T745 | Electrical Wiring | Sarah Johnson | In Progress | High | 2023-05-12 | 2023-05-28 |  | 9 | Roofing Sheets | Downtown Avenue | 22735 | 25263.37 | In progress
C004 | Warehouse D | T514 | Steel Framework Setup | Dave Brown | Not Started | Medium | 2023-04-18 | 2023-04-30 |  | 0 | Steel Beams | Industrial Park | 42300.87 | 0 | Not started
C001 | Residential Building A | T726 | Interior Painting | Dave Brown | Completed | Medium | 2023-05-27 | 2023-06-09 | 2023-06-09 | 100 | Cement | Plot 21, Riverside | 35893.76 | 41153.17 | No issues
C004 | Warehouse D | T813 | Roofing | Carlos Rivera | Not Started | High | 2023-07-23 | 2023-08-02 |  | 0 | Steel Beams | Industrial Park | 27709.02 | 0 | Not started
C003 | Office Tower C | T156 | Concrete Pouring | Dave Brown | In Progress | Low | 2024-12-27 | 2025-01-22 |  | 80 | Roofing Sheets | Downtown Avenue | 25417.37 | 21492.54 | In progress
C004 | Warehouse D | T710 | Electrical Wiring | John Miller | Completed | Low | 2024-12-14 | 2025-01-07 | 2025-01-07 | 100 | Steel Beams | Industrial Park | 5421.68 | 4702.79 | No issues
C001 | Residential Building A | T461 | Foundation Excavation | Dave Brown | Blocked | Low | 2024-01-28 | 2024-02-07 |  | 0 | Copper Wires | Plot 21, Riverside | 24486.72 | 17349.79 | Not started
C003 | Office Tower C | T461 | Interior Painting | Carlos Rivera | In Progress | Medium | 2023-10-18 | 2023-10-31 |  | 88 | Copper Wires | Downtown Avenue | 26254.74 | 30964.93 | In progress
C001 | Residential Building A | T572 | Interior Painting | Emma White | Completed | Low | 2023-07-04 | 2023-08-01 | 2023-08-01 | 100 | Roofing Sheets | Plot 21, Riverside | 41963.08 | 25990.42 | No issues
C004 | Warehouse D | T483 | Steel Framework Setup | Grace Allen | Not Started | Low | 2024-12-18 | 2025-01-01 |  | 0 | Rebar | Industrial Park | 19282.09 | 0 | Not started
C003 | Office Tower C | T802 | Roofing | Grace Allen | Not Started | Low | 2024-01-18 | 2024-02-02 |  | 0 | Steel Beams | Downtown Avenue | 39990.17 | 0 | Not started
C001 | Residential Building A | T944 | Foundation Excavation | Mike Adams | Completed | High | 2023-01-27 | 2023-02-26 | 2023-02-26 | 100 | Cement | Plot 21, Riverside | 35222.16 | 40355.68 | No issues
C001 | Residential Building A | T813 | Concrete Pouring | Sarah Johnson | Not Started | Low | 2024-10-27 | 2024-11-25 |  | 0 | Rebar | Plot 21, Riverside | 21707.27 | 0 | Not started
C003 | Office Tower C | T921 | Plumbing Installations | John Miller | Completed | Low | 2024-09-28 | 2024-10-19 | 2024-10-19 | 100 | Cement | Downtown Avenue | 42472.73 | 29477.3 | No issues
C004 | Warehouse D | T783 | Concrete Pouring | Mike Adams | Completed | High | 2023-12-12 | 2023-12-27 | 2023-12-27 | 100 | Rebar | Industrial Park | 38403.96 | 23627.91 | No issues
C003 | Office Tower C | T352 | Electrical Wiring | Mike Adams | In Progress | Medium | 2024-11-07 | 2024-11-22 |  | 93 | Cement | Downtown Avenue | 17453.44 | 14234.89 | In progress
C002 | Shopping Complex B | T156 | Site Survey | Rachel Green | Completed | High | 2023-08-05 | 2023-08-31 | 2023-08-31 | 100 | Steel Beams | Market Street | 14252.81 | 36395.77 | No issues
C001 | Residential Building A | T872 | Foundation Excavation | Grace Allen | In Progress | Medium | 2024-10-18 | 2024-10-25 |  | 48 | Concrete | Plot 21, Riverside | 25975.25 | 22535.24 | In progress
C003 | Office Tower C | T239 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2024-03-12 | 2024-03-25 |  | 79 | Cement | Downtown Avenue | 21226.25 | 14592.57 | In progress
C004 | Warehouse D | T676 | Foundation Excavation | John Miller | Not Started | Low | 2023-03-27 | 2023-04-04 |  | 0 | PVC Pipes | Industrial Park | 7015.28 | 0 | Not started
C001 | Residential Building A | T839 | Interior Painting | Carlos Rivera | Completed | Low | 2024-08-03 | 2024-08-22 | 2024-08-22 | 100 | Copper Wires | Plot 21, Riverside | 33959.16 | 24602.75 | No issues
C001 | Residential Building A | T328 | Roofing | Grace Allen | Not Started | High | 2024-05-19 | 2024-06-16 |  | 0 | PVC Pipes | Plot 21, Riverside | 19216.26 | 0 | Not started
C003 | Office Tower C | T118 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2023-04-02 | 2023-04-29 |  | 75 | Rebar | Downtown Avenue | 21745.42 | 23472.72 | In progress
C003 | Office Tower C | T849 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2024-05-22 | 2024-06-02 |  | 0 | Rebar | Downtown Avenue | 49663.6 | 31250.37 | Not started
C003 | Office Tower C | T688 | Interior Painting | Sarah Johnson | Blocked | Medium | 2023-04-07 | 2023-05-02 |  | 0 | Copper Wires | Downtown Avenue | 14953.77 | 15882.28 | Not started
C002 | Shopping Complex B | T663 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2024-01-28 | 2024-02-10 |  | 87 | Rebar | Market Street | 18157.66 | 37733.13 | In progress
C003 | Office Tower C | T130 | Concrete Pouring | Rachel Green | Blocked | Low | 2023-10-18 | 2023-10-26 |  | 0 | Cement | Downtown Avenue | 37861.52 | 39726.6 | Not started
C003 | Office Tower C | T106 | Foundation Excavation | Emma White | Not Started | Low | 2024-01-16 | 2024-01-28 |  | 0 | PVC Pipes | Downtown Avenue | 42951.51 | 0 | Not started
C003 | Office Tower C | T517 | Electrical Wiring | Rachel Green | Not Started | High | 2023-04-24 | 2023-05-22 |  | 0 | Paint | Downtown Avenue | 12135.56 | 0 | Not started
C004 | Warehouse D | T903 | Site Survey | Dave Brown | In Progress | High | 2023-04-04 | 2023-04-15 |  | 9 | Steel Beams | Industrial Park | 8200.44 | 7125.35 | In progress
C004 | Warehouse D | T960 | Steel Framework Setup | Emma White | Not Started | Medium | 2023-12-23 | 2024-01-01 |  | 0 | Roofing Sheets | Industrial Park | 24050.42 | 0 | Not started
C003 | Office Tower C | T448 | Electrical Wiring | Mike Adams | Not Started | High | 2023-12-06 | 2023-12-27 |  | 0 | Copper Wires | Downtown Avenue | 16185.36 | 0 | Not started
C003 | Office Tower C | T621 | Steel Framework Setup | John Miller | Not Started | High | 2024-07-19 | 2024-08-10 |  | 0 | Concrete | Downtown Avenue | 27231.11 | 0 | Not started
C003 | Office Tower C | T247 | Interior Painting | Emma White | Completed | Medium | 2023-09-01 | 2023-10-01 | 2023-10-01 | 100 | Copper Wires | Downtown Avenue | 22797.19 | 13742.95 | No issues
C004 | Warehouse D | T928 | Interior Painting | John Miller | Completed | Low | 2023-08-06 | 2023-08-30 | 2023-08-30 | 100 | Paint | Industrial Park | 29208.23 | 28427.54 | No issues
C004 | Warehouse D | T969 | Plumbing Installations | Mike Adams | Not Started | High | 2024-02-12 | 2024-02-29 |  | 0 | Steel Beams | Industrial Park | 49424.4 | 0 | Not started
C003 | Office Tower C | T808 | Electrical Wiring | Sarah Johnson | Not Started | High | 2023-08-27 | 2023-09-14 |  | 0 | Concrete | Downtown Avenue | 25705.05 | 0 | Not started
C003 | Office Tower C | T834 | Steel Framework Setup | Emma White | Completed | High | 2023-08-09 | 2023-08-27 | 2023-08-27 | 100 | Steel Beams | Downtown Avenue | 25390.77 | 28881.94 | No issues
C002 | Shopping Complex B | T381 | Roofing | Mike Adams | Not Started | Low | 2023-10-25 | 2023-11-22 |  | 0 | Paint | Market Street | 6618.8 | 0 | Not started
C001 | Residential Building A | T958 | Plumbing Installations | Emma White | In Progress | Low | 2024-02-16 | 2024-02-24 |  | 59 | PVC Pipes | Plot 21, Riverside | 28235.1 | 27126.19 | In progress
C003 | Office Tower C | T871 | Electrical Wiring | Rachel Green | Not Started | High | 2024-03-03 | 2024-03-25 |  | 0 | Cement | Downtown Avenue | 35493.75 | 0 | Not started
C001 | Residential Building A | T481 | Electrical Wiring | Carlos Rivera | In Progress | High | 2023-12-20 | 2023-12-31 |  | 65 | Copper Wires | Plot 21, Riverside | 28729.45 | 21404.13 | In progress
C003 | Office Tower C | T360 | Roofing | Dave Brown | Completed | High | 2023-03-28 | 2023-04-11 | 2023-04-11 | 100 | Cement | Downtown Avenue | 40865.95 | 39693.51 | No issues
C003 | Office Tower C | T152 | Foundation Excavation | Rachel Green | Not Started | Medium | 2023-04-25 | 2023-05-25 |  | 0 | Steel Beams | Downtown Avenue | 7168.2 | 0 | Not started
C003 | Office Tower C | T457 | Plumbing Installations | Mike Adams | Not Started | Low | 2024-09-14 | 2024-10-09 |  | 0 | Concrete | Downtown Avenue | 26942.21 | 0 | Not started
C004 | Warehouse D | T610 | Electrical Wiring | Dave Brown | In Progress | Low | 2023-03-16 | 2023-04-08 |  | 41 | Cement | Industrial Park | 7645.97 | 7490.25 | In progress
C004 | Warehouse D | T142 | Interior Painting | Dave Brown | Blocked | Medium | 2024-08-19 | 2024-09-14 |  | 0 | PVC Pipes | Industrial Park | 18605.68 | 17163.23 | Not started
C001 | Residential Building A | T334 | Foundation Excavation | Rachel Green | Completed | Low | 2023-11-08 | 2023-12-08 | 2023-12-08 | 100 | Cement | Plot 21, Riverside | 35330.91 | 34169.47 | No issues
C003 | Office Tower C | T725 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2023-11-21 | 2023-12-13 |  | 0 | Rebar | Downtown Avenue | 16692.42 | 0 | Not started
C002 | Shopping Complex B | T651 | Foundation Excavation | Grace Allen | Not Started | High | 2023-08-11 | 2023-08-21 |  | 0 | PVC Pipes | Market Street | 32645.96 | 0 | Not started
C003 | Office Tower C | T456 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2023-09-24 | 2023-10-06 |  | 0 | Paint | Downtown Avenue | 13828.28 | 15719.89 | Not started
C004 | Warehouse D | T170 | Steel Framework Setup | Sarah Johnson | In Progress | High | 2023-12-08 | 2024-01-03 |  | 83 | Steel Beams | Industrial Park | 37805.66 | 33971.75 | In progress
C002 | Shopping Complex B | T464 | Roofing | Dave Brown | In Progress | Medium | 2024-02-05 | 2024-02-22 |  | 6 | Rebar | Market Street | 22476.67 | 50738.31 | In progress
C001 | Residential Building A | T620 | Electrical Wiring | Grace Allen | Completed | Medium | 2023-10-02 | 2023-10-31 | 2023-10-31 | 100 | Rebar | Plot 21, Riverside | 30825.82 | 24275.74 | No issues
C002 | Shopping Complex B | T470 | Foundation Excavation | John Miller | In Progress | High | 2023-02-27 | 2023-03-12 |  | 45 | Paint | Market Street | 42751.5 | 52937.21 | In progress
C001 | Residential Building A | T100 | Site Survey | Grace Allen | Completed | Low | 2023-06-25 | 2023-07-08 | 2023-07-08 | 100 | Copper Wires | Plot 21, Riverside | 31670.41 | 32924.73 | No issues
C001 | Residential Building A | T419 | Roofing | Dave Brown | In Progress | Low | 2023-01-05 | 2023-01-29 |  | 15 | Steel Beams | Plot 21, Riverside | 35040.41 | 23319.32 | In progress
C002 | Shopping Complex B | T752 | Roofing | Dave Brown | In Progress | Low | 2024-01-02 | 2024-01-31 |  | 73 | Concrete | Market Street | 36792.24 | 68322.37 | In progress
C002 | Shopping Complex B | T927 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-07-06 | 2023-07-18 |  | 0 | Roofing Sheets | Market Street | 45073.83 | 0 | Not started
C003 | Office Tower C | T315 | Plumbing Installations | Emma White | Completed | Low | 2023-11-19 | 2023-12-07 | 2023-12-07 | 100 | Roofing Sheets | Downtown Avenue | 21956.62 | 16866.68 | No issues
C003 | Office Tower C | T934 | Interior Painting | Dave Brown | Blocked | Medium | 2024-02-23 | 2024-03-02 |  | 0 | Cement | Downtown Avenue | 19469.64 | 16021.58 | Not started
C002 | Shopping Complex B | T326 | Interior Painting | Rachel Green | Blocked | Medium | 2024-02-13 | 2024-02-20 |  | 0 | Concrete | Market Street | 21846.48 | 48350.85 | Not started
C002 | Shopping Complex B | T295 | Foundation Excavation | Emma White | Not Started | Low | 2023-09-10 | 2023-10-02 |  | 0 | Steel Beams | Market Street | 25636.11 | 0 | Not started
C002 | Shopping Complex B | T912 | Roofing | Dave Brown | In Progress | High | 2023-03-16 | 2023-04-13 |  | 98 | Copper Wires | Market Street | 47450.26 | 67961.13 | In progress
C003 | Office Tower C | T363 | Roofing | Mike Adams | Not Started | Medium | 2023-10-17 | 2023-11-15 |  | 0 | Cement | Downtown Avenue | 15905.98 | 0 | Not started
C001 | Residential Building A | T807 | Interior Painting | Dave Brown | Blocked | Low | 2023-12-25 | 2024-01-08 |  | 0 | Copper Wires | Plot 21, Riverside | 33647.67 | 31030.67 | Not started
C002 | Shopping Complex B | T722 | Foundation Excavation | Mike Adams | Not Started | Low | 2023-10-15 | 2023-11-13 |  | 0 | Roofing Sheets | Market Street | 32268.66 | 0 | Not started
C003 | Office Tower C | T518 | Site Survey | Carlos Rivera | Blocked | High | 2023-12-21 | 2023-12-31 |  | 0 | Roofing Sheets | Downtown Avenue | 13782.6 | 10640.11 | Not started
C003 | Office Tower C | T985 | Plumbing Installations | Emma White | Completed | Low | 2023-05-04 | 2023-05-28 | 2023-05-28 | 100 | PVC Pipes | Downtown Avenue | 20483.75 | 23889.14 | No issues
C003 | Office Tower C | T394 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2024-03-04 | 2024-04-02 |  | 0 | Rebar | Downtown Avenue | 42220.11 | 0 | Not started
C004 | Warehouse D | T785 | Site Survey | Sarah Johnson | Completed | High | 2024-01-24 | 2024-02-05 | 2024-02-05 | 100 | Paint | Industrial Park | 13963.54 | 15337.21 | No issues
C004 | Warehouse D | T290 | Interior Painting | Mike Adams | Completed | High | 2023-05-13 | 2023-05-24 | 2023-05-24 | 100 | Roofing Sheets | Industrial Park | 8977.49 | 5606.21 | No issues
C003 | Office Tower C | T336 | Concrete Pouring | Rachel Green | Not Started | Low | 2023-11-18 | 2023-12-13 |  | 0 | Rebar | Downtown Avenue | 8765.65 | 0 | Not started
C001 | Residential Building A | T238 | Plumbing Installations | Rachel Green | Not Started | Medium | 2024-02-24 | 2024-03-25 |  | 0 | Rebar | Plot 21, Riverside | 8881.74 | 0 | Not started
C003 | Office Tower C | T350 | Steel Framework Setup | John Miller | Not Started | Medium | 2024-07-04 | 2024-07-28 |  | 0 | Concrete | Downtown Avenue | 47794.83 | 0 | Not started
C001 | Residential Building A | T520 | Roofing | Carlos Rivera | In Progress | Medium | 2024-06-23 | 2024-07-08 |  | 84 | Steel Beams | Plot 21, Riverside | 28248.76 | 17513.12 | In progress
C002 | Shopping Complex B | T818 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-09-06 | 2023-09-17 |  | 0 | Roofing Sheets | Market Street | 46511.12 | 73286.72 | Not started
C002 | Shopping Complex B | T314 | Roofing | Rachel Green | In Progress | Low | 2023-12-24 | 2024-01-02 |  | 13 | Rebar | Market Street | 30026.03 | 53755.4 | In progress
C002 | Shopping Complex B | T447 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-07-05 | 2023-08-04 |  | 0 | Cement | Market Street | 9215.35 | 34072.35 | Not started
C001 | Residential Building A | T438 | Roofing | Grace Allen | Blocked | Low | 2023-11-18 | 2023-12-08 |  | 0 | Rebar | Plot 21, Riverside | 9043.42 | 9243.99 | Not started
C003 | Office Tower C | T846 | Plumbing Installations | Mike Adams | Blocked | Low | 2023-03-14 | 2023-04-13 |  | 0 | Concrete | Downtown Avenue | 48365.67 | 45668.74 | Not started
C004 | Warehouse D | T430 | Interior Painting | Rachel Green | Completed | High | 2024-12-01 | 2024-12-13 | 2024-12-13 | 100 | Steel Beams | Industrial Park | 42465.32 | 46532.68 | No issues
C001 | Residential Building A | T137 | Plumbing Installations | Grace Allen | In Progress | Medium | 2023-05-17 | 2023-06-08 |  | 74 | Concrete | Plot 21, Riverside | 18397.01 | 17974.1 | In progress
C004 | Warehouse D | T929 | Roofing | Dave Brown | Blocked | Low | 2023-03-07 | 2023-03-22 |  | 0 | Copper Wires | Industrial Park | 27305.61 | 18557.92 | Not started
C001 | Residential Building A | T604 | Electrical Wiring | Carlos Rivera | Completed | High | 2024-03-17 | 2024-04-02 | 2024-04-02 | 100 | Roofing Sheets | Plot 21, Riverside | 46636.71 | 54032.3 | No issues
C004 | Warehouse D | T542 | Interior Painting | Mike Adams | In Progress | High | 2024-08-12 | 2024-08-28 |  | 58 | PVC Pipes | Industrial Park | 18677.04 | 16287.13 | In progress
C002 | Shopping Complex B | T302 | Interior Painting | Emma White | Not Started | High | 2024-08-25 | 2024-09-04 |  | 0 | Roofing Sheets | Market Street | 17724.07 | 0 | Not started
C003 | Office Tower C | T715 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2023-07-08 | 2023-07-19 |  | 48 | Rebar | Downtown Avenue | 48204.75 | 55314.57 | In progress
C003 | Office Tower C | T575 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-01-07 | 2023-02-02 |  | 12 | Copper Wires | Downtown Avenue | 28589.53 | 34258.79 | In progress
C003 | Office Tower C | T608 | Plumbing Installations | Emma White | Blocked | Medium | 2023-04-28 | 2023-05-20 |  | 0 | PVC Pipes | Downtown Avenue | 28800.96 | 33871.35 | Not started
C003 | Office Tower C | T825 | Interior Painting | Grace Allen | Blocked | Low | 2023-03-01 | 2023-03-31 |  | 0 | Rebar | Downtown Avenue | 18845.12 | 12749.48 | Not started
C003 | Office Tower C | T227 | Foundation Excavation | Grace Allen | Not Started | High | 2024-09-11 | 2024-09-27 |  | 0 | Paint | Downtown Avenue | 14930.78 | 0 | Not started
C002 | Shopping Complex B | T870 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-04-27 | 2024-05-27 |  | 0 | Concrete | Market Street | 12274.15 | 34335.8 | Not started
C003 | Office Tower C | T487 | Roofing | Emma White | Completed | High | 2023-09-08 | 2023-09-23 | 2023-09-23 | 100 | Copper Wires | Downtown Avenue | 8055.96 | 5663.42 | No issues
C001 | Residential Building A | T836 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-10-22 | 2024-11-02 |  | 0 | PVC Pipes | Plot 21, Riverside | 26860.32 | 0 | Not started
C004 | Warehouse D | T803 | Steel Framework Setup | Grace Allen | Completed | Low | 2023-04-16 | 2023-05-06 | 2023-05-06 | 100 | Copper Wires | Industrial Park | 7858.9 | 8038.09 | No issues
C001 | Residential Building A | T856 | Steel Framework Setup | Grace Allen | Completed | Medium | 2023-01-03 | 2023-01-15 | 2023-01-15 | 100 | PVC Pipes | Plot 21, Riverside | 21335.21 | 22986.66 | No issues
C002 | Shopping Complex B | T781 | Concrete Pouring | Emma White | Blocked | High | 2023-12-10 | 2023-12-18 |  | 0 | Roofing Sheets | Market Street | 48798.92 | 70176.58 | Not started
C003 | Office Tower C | T971 | Steel Framework Setup | Emma White | Not Started | High | 2023-03-03 | 2023-04-02 |  | 0 | Rebar | Downtown Avenue | 9957.66 | 0 | Not started
C004 | Warehouse D | T957 | Steel Framework Setup | Sarah Johnson | Completed | High | 2024-01-06 | 2024-01-18 | 2024-01-18 | 100 | Cement | Industrial Park | 37053.4 | 40984.12 | No issues
C001 | Residential Building A | T548 | Electrical Wiring | Rachel Green | Not Started | Low | 2024-07-28 | 2024-08-06 |  | 0 | PVC Pipes | Plot 21, Riverside | 48071.67 | 0 | Not started
C001 | Residential Building A | T110 | Site Survey | Sarah Johnson | Not Started | High | 2024-07-02 | 2024-07-29 |  | 0 | Rebar | Plot 21, Riverside | 35638.48 | 0 | Not started
C001 | Residential Building A | T661 | Site Survey | John Miller | In Progress | High | 2024-12-05 | 2024-12-28 |  | 64 | Concrete | Plot 21, Riverside | 12621.27 | 10439.43 | In progress
C004 | Warehouse D | T952 | Interior Painting | Dave Brown | Blocked | Medium | 2024-07-26 | 2024-08-22 |  | 0 | Paint | Industrial Park | 31249.83 | 35983.62 | Not started
C001 | Residential Building A | T638 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-07-14 | 2023-07-21 |  | 57 | Paint | Plot 21, Riverside | 42617.38 | 39830.98 | In progress
C002 | Shopping Complex B | T478 | Concrete Pouring | Grace Allen | In Progress | Low | 2023-12-28 | 2024-01-25 |  | 17 | Copper Wires | Market Street | 20063.81 | 46398.69 | In progress
C001 | Residential Building A | T744 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2023-03-24 | 2023-04-12 |  | 0 | Copper Wires | Plot 21, Riverside | 10007.39 | 10452.16 | Not started
C002 | Shopping Complex B | T838 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-07-21 | 2024-08-02 |  | 35 | Steel Beams | Market Street | 38437.16 | 64849.02 | In progress
C002 | Shopping Complex B | T654 | Steel Framework Setup | John Miller | Completed | High | 2024-10-22 | 2024-11-03 | 2024-11-03 | 100 | Copper Wires | Market Street | 25484.5 | 43718.16 | No issues
C001 | Residential Building A | T927 | Steel Framework Setup | Carlos Rivera | Completed | Low | 2023-07-28 | 2023-08-07 | 2023-08-07 | 100 | Roofing Sheets | Plot 21, Riverside | 20910.09 | 15574.66 | No issues
C003 | Office Tower C | T759 | Foundation Excavation | Grace Allen | Blocked | Medium | 2023-04-12 | 2023-04-24 |  | 0 | Cement | Downtown Avenue | 19783.39 | 23159.11 | Not started
C002 | Shopping Complex B | T783 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-10-27 | 2024-11-05 | 2024-11-05 | 100 | Roofing Sheets | Market Street | 42700.63 | 70805.79 | No issues
C003 | Office Tower C | T278 | Foundation Excavation | Grace Allen | In Progress | Low | 2024-04-20 | 2024-05-04 |  | 91 | Steel Beams | Downtown Avenue | 21743.31 | 19210.48 | In progress
C002 | Shopping Complex B | T807 | Interior Painting | Grace Allen | Completed | High | 2023-07-11 | 2023-07-23 | 2023-07-23 | 100 | PVC Pipes | Market Street | 27063.37 | 46360.06 | No issues
C001 | Residential Building A | T897 | Electrical Wiring | Carlos Rivera | In Progress | High | 2023-02-05 | 2023-02-18 |  | 4 | Paint | Plot 21, Riverside | 44681.9 | 37663.02 | In progress
C001 | Residential Building A | T376 | Site Survey | Rachel Green | Completed | High | 2023-09-11 | 2023-09-29 | 2023-09-29 | 100 | Concrete | Plot 21, Riverside | 38694.26 | 27879.45 | No issues
C002 | Shopping Complex B | T553 | Roofing | Sarah Johnson | Not Started | Medium | 2024-11-12 | 2024-11-26 |  | 0 | Steel Beams | Market Street | 29716.1 | 0 | Not started
C002 | Shopping Complex B | T546 | Steel Framework Setup | John Miller | Not Started | High | 2024-11-10 | 2024-11-27 |  | 0 | PVC Pipes | Market Street | 14066.99 | 0 | Not started
C002 | Shopping Complex B | T214 | Roofing | John Miller | Completed | High | 2023-02-21 | 2023-03-11 | 2023-03-11 | 100 | Roofing Sheets | Market Street | 28228.5 | 53282.44 | No issues
C002 | Shopping Complex B | T862 | Site Survey | John Miller | In Progress | Low | 2024-12-25 | 2025-01-06 |  | 13 | Cement | Market Street | 26769.87 | 50952.08 | In progress
C001 | Residential Building A | T670 | Plumbing Installations | John Miller | Blocked | Low | 2024-10-23 | 2024-11-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 36972.64 | 27976.45 | Not started
C003 | Office Tower C | T306 | Plumbing Installations | Dave Brown | In Progress | High | 2023-08-12 | 2023-08-28 |  | 42 | Concrete | Downtown Avenue | 49025.33 | 35564.25 | In progress
C003 | Office Tower C | T836 | Foundation Excavation | Carlos Rivera | Blocked | Low | 2024-05-26 | 2024-06-17 |  | 0 | PVC Pipes | Downtown Avenue | 10858.08 | 12423.21 | Not started
C004 | Warehouse D | T743 | Electrical Wiring | Dave Brown | In Progress | Medium | 2023-07-01 | 2023-07-10 |  | 26 | Concrete | Industrial Park | 19686.27 | 18559.84 | In progress
C004 | Warehouse D | T663 | Electrical Wiring | Sarah Johnson | Blocked | High | 2023-07-22 | 2023-08-06 |  | 0 | Roofing Sheets | Industrial Park | 28779.18 | 29667.54 | Not started
C003 | Office Tower C | T110 | Electrical Wiring | Emma White | In Progress | Medium | 2024-10-15 | 2024-10-24 |  | 89 | Copper Wires | Downtown Avenue | 31123.09 | 34409.2 | In progress
C001 | Residential Building A | T940 | Foundation Excavation | Grace Allen | Blocked | High | 2024-03-02 | 2024-03-09 |  | 0 | Paint | Plot 21, Riverside | 15995.6 | 13808.83 | Not started
C004 | Warehouse D | T493 | Foundation Excavation | John Miller | Blocked | Low | 2024-02-01 | 2024-02-13 |  | 0 | Concrete | Industrial Park | 26680.35 | 19001.29 | Not started
C001 | Residential Building A | T760 | Electrical Wiring | Rachel Green | Blocked | Low | 2023-09-12 | 2023-09-22 |  | 0 | Steel Beams | Plot 21, Riverside | 14295.23 | 16276.55 | Not started
C001 | Residential Building A | T983 | Steel Framework Setup | Carlos Rivera | In Progress | High | 2024-11-02 | 2024-11-10 |  | 10 | Steel Beams | Plot 21, Riverside | 12532.24 | 13569.2 | In progress
C004 | Warehouse D | T228 | Foundation Excavation | Carlos Rivera | Completed | High | 2023-09-03 | 2023-09-17 | 2023-09-17 | 100 | Concrete | Industrial Park | 10852.56 | 12875.64 | No issues
C004 | Warehouse D | T626 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2024-08-12 | 2024-09-06 |  | 0 | Concrete | Industrial Park | 8587.07 | 5505.86 | Not started
C004 | Warehouse D | T854 | Plumbing Installations | Carlos Rivera | Not Started | High | 2024-06-22 | 2024-07-16 |  | 0 | Concrete | Industrial Park | 27401.6 | 0 | Not started
C002 | Shopping Complex B | T701 | Steel Framework Setup | Emma White | Not Started | Medium | 2023-07-12 | 2023-08-07 |  | 0 | Rebar | Market Street | 33641.68 | 0 | Not started
C001 | Residential Building A | T447 | Site Survey | Mike Adams | Blocked | High | 2023-10-25 | 2023-11-15 |  | 0 | Rebar | Plot 21, Riverside | 28368.7 | 25331.76 | Not started
C002 | Shopping Complex B | T122 | Site Survey | Rachel Green | Completed | High | 2023-05-19 | 2023-06-16 | 2023-06-16 | 100 | Copper Wires | Market Street | 27293.7 | 53257.8 | No issues
C004 | Warehouse D | T498 | Steel Framework Setup | Dave Brown | In Progress | Low | 2023-04-16 | 2023-04-28 |  | 19 | Roofing Sheets | Industrial Park | 9164.71 | 8588.85 | In progress
C001 | Residential Building A | T665 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-10-02 | 2023-11-01 |  | 2 | Paint | Plot 21, Riverside | 22851.13 | 13966.88 | In progress
C004 | Warehouse D | T287 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-09-16 | 2024-10-15 | 2024-10-15 | 100 | Steel Beams | Industrial Park | 35338.67 | 32274.1 | No issues
C004 | Warehouse D | T190 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-10-20 | 2024-11-13 | 2024-11-13 | 100 | Paint | Industrial Park | 47108.84 | 55287.52 | No issues
C004 | Warehouse D | T285 | Roofing | Carlos Rivera | In Progress | High | 2023-07-15 | 2023-07-26 |  | 66 | Rebar | Industrial Park | 23406.1 | 20344.57 | In progress
C003 | Office Tower C | T907 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-01-19 | 2023-01-26 |  | 0 | Steel Beams | Downtown Avenue | 19606.29 | 0 | Not started
C002 | Shopping Complex B | T180 | Site Survey | Grace Allen | Not Started | High | 2023-01-19 | 2023-02-18 |  | 0 | Roofing Sheets | Market Street | 17909.22 | 0 | Not started
C001 | Residential Building A | T227 | Site Survey | Mike Adams | Completed | Medium | 2023-01-14 | 2023-01-23 | 2023-01-23 | 100 | Paint | Plot 21, Riverside | 11612.88 | 11170 | No issues
C002 | Shopping Complex B | T160 | Concrete Pouring | Rachel Green | Blocked | Medium | 2023-03-02 | 2023-03-18 |  | 0 | Rebar | Market Street | 11045.96 | 32534.91 | Not started
C004 | Warehouse D | T984 | Roofing | Dave Brown | Completed | High | 2023-08-20 | 2023-09-06 | 2023-09-06 | 100 | Rebar | Industrial Park | 15633.45 | 13493.47 | No issues
C001 | Residential Building A | T214 | Steel Framework Setup | Rachel Green | Blocked | Low | 2023-02-01 | 2023-02-26 |  | 0 | Cement | Plot 21, Riverside | 19054.63 | 16549.09 | Not started
C001 | Residential Building A | T995 | Foundation Excavation | Dave Brown | Completed | High | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100 | Rebar | Plot 21, Riverside | 16680.93 | 19980.87 | No issues
C004 | Warehouse D | T482 | Site Survey | John Miller | In Progress | Low | 2024-10-10 | 2024-11-02 |  | 85 | Concrete | Industrial Park | 27731.46 | 23651.22 | In progress
C003 | Office Tower C | T686 | Interior Painting | John Miller | Blocked | High | 2024-09-09 | 2024-10-06 |  | 0 | Copper Wires | Downtown Avenue | 28120.89 | 24448.81 | Not started
C003 | Office Tower C | T336 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2024-07-28 | 2024-08-08 |  | 0 | Roofing Sheets | Downtown Avenue | 15890.46 | 11855.7 | Not started
C002 | Shopping Complex B | T658 | Electrical Wiring | Grace Allen | Completed | Medium | 2024-11-23 | 2024-12-04 | 2024-12-04 | 100 | PVC Pipes | Market Street | 27796.44 | 46678.6 | No issues
C003 | Office Tower C | T993 | Electrical Wiring | Emma White | Not Started | Low | 2023-01-09 | 2023-01-18 |  | 0 | Cement | Downtown Avenue | 8101.48 | 0 | Not started
C002 | Shopping Complex B | T132 | Roofing | Emma White | Blocked | Low | 2024-07-22 | 2024-08-07 |  | 0 | Paint | Market Street | 42083.49 | 57347.85 | Not started
C004 | Warehouse D | T159 | Foundation Excavation | Mike Adams | In Progress | Low | 2024-01-09 | 2024-02-06 |  | 45 | Paint | Industrial Park | 19844.03 | 20754.06 | In progress
C002 | Shopping Complex B | T929 | Site Survey | Dave Brown | Completed | Medium | 2024-07-26 | 2024-08-04 | 2024-08-04 | 100 | PVC Pipes | Market Street | 28317.92 | 55431.86 | No issues
C002 | Shopping Complex B | T574 | Electrical Wiring | Dave Brown | Not Started | Low | 2024-11-19 | 2024-12-07 |  | 0 | Concrete | Market Street | 22132.71 | 0 | Not started
C001 | Residential Building A | T916 | Steel Framework Setup | Mike Adams | Blocked | Low | 2023-08-15 | 2023-08-29 |  | 0 | Rebar | Plot 21, Riverside | 8124.01 | 9272 | Not started
C003 | Office Tower C | T983 | Roofing | Grace Allen | In Progress | Low | 2023-09-01 | 2023-09-25 |  | 33 | Roofing Sheets | Downtown Avenue | 24890.42 | 23125.84 | In progress
C001 | Residential Building A | T953 | Electrical Wiring | Dave Brown | Not Started | Low | 2024-05-11 | 2024-06-06 |  | 0 | Roofing Sheets | Plot 21, Riverside | 33934.01 | 0 | Not started
C003 | Office Tower C | T747 | Electrical Wiring | Rachel Green | Not Started | Low | 2023-10-24 | 2023-11-23 |  | 0 | Cement | Downtown Avenue | 25671.02 | 0 | Not started
C002 | Shopping Complex B | T592 | Steel Framework Setup | Sarah Johnson | Completed | Medium | 2024-07-25 | 2024-08-21 | 2024-08-21 | 100 | Roofing Sheets | Market Street | 6118.61 | 30001.02 | No issues
C001 | Residential Building A | T565 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2024-03-01 | 2024-03-16 |  | 96 | Roofing Sheets | Plot 21, Riverside | 44479.76 | 41512.23 | In progress
C002 | Shopping Complex B | T937 | Concrete Pouring | Mike Adams | Completed | High | 2024-01-21 | 2024-01-29 | 2024-01-29 | 100 | Concrete | Market Street | 41500.46 | 69744.86 | No issues
C001 | Residential Building A | T164 | Concrete Pouring | Emma White | Not Started | Low | 2024-04-15 | 2024-05-08 |  | 0 | Steel Beams | Plot 21, Riverside | 21685.35 | 0 | Not started
C004 | Warehouse D | T141 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-09-18 | 2023-10-03 |  | 0 | Rebar | Industrial Park | 40917 | 46840.99 | Not started
C003 | Office Tower C | T455 | Interior Painting | Mike Adams | Not Started | High | 2023-02-18 | 2023-03-20 |  | 0 | PVC Pipes | Downtown Avenue | 5836.38 | 0 | Not started
C001 | Residential Building A | T956 | Site Survey | Mike Adams | Blocked | Medium | 2024-07-23 | 2024-08-17 |  | 0 | Concrete | Plot 21, Riverside | 48891.26 | 31283.19 | Not started
C002 | Shopping Complex B | T204 | Roofing | Dave Brown | Completed | Medium | 2024-11-04 | 2024-11-13 | 2024-11-13 | 100 | Rebar | Market Street | 27878.88 | 55438.54 | No issues
C004 | Warehouse D | T206 | Roofing | Mike Adams | Not Started | Medium | 2024-05-12 | 2024-05-26 |  | 0 | Paint | Industrial Park | 18150.17 | 0 | Not started
C001 | Residential Building A | T890 | Site Survey | John Miller | In Progress | High | 2023-04-16 | 2023-05-05 |  | 80 | Paint | Plot 21, Riverside | 7664.77 | 4901.52 | In progress
C001 | Residential Building A | T565 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-10-13 | 2023-10-25 |  | 90 | PVC Pipes | Plot 21, Riverside | 29734.73 | 20687.01 | In progress
C004 | Warehouse D | T472 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-02-10 | 2023-02-26 | 2023-02-26 | 100 | Rebar | Industrial Park | 33851.42 | 27718.32 | No issues
C002 | Shopping Complex B | T858 | Electrical Wiring | Dave Brown | Not Started | Medium | 2024-08-10 | 2024-09-01 |  | 0 | Roofing Sheets | Market Street | 35647.89 | 0 | Not started
C002 | Shopping Complex B | T768 | Foundation Excavation | Mike Adams | Blocked | Medium | 2023-06-22 | 2023-06-30 |  | 0 | Rebar | Market Street | 27416.07 | 54538.83 | Not started
C003 | Office Tower C | T707 | Interior Painting | Dave Brown | Blocked | High | 2024-10-08 | 2024-10-25 |  | 0 | Steel Beams | Downtown Avenue | 26907.59 | 23458.77 | Not started
C004 | Warehouse D | T743 | Plumbing Installations | Grace Allen | Blocked | Medium | 2023-04-26 | 2023-05-24 |  | 0 | Cement | Industrial Park | 6542.66 | 5453.38 | Not started
C004 | Warehouse D | T167 | Interior Painting | Grace Allen | Completed | Medium | 2023-06-10 | 2023-07-07 | 2023-07-07 | 100 | PVC Pipes | Industrial Park | 6910.23 | 4925.16 | No issues
C001 | Residential Building A | T276 | Electrical Wiring | Sarah Johnson | Completed | High | 2024-07-07 | 2024-07-14 | 2024-07-14 | 100 | Rebar | Plot 21, Riverside | 28324.46 | 32259.04 | No issues
C004 | Warehouse D | T475 | Site Survey | Grace Allen | Not Started | Medium | 2023-10-01 | 2023-10-08 |  | 0 | Cement | Industrial Park | 48432.2 | 0 | Not started
C001 | Residential Building A | T213 | Steel Framework Setup | Mike Adams | Not Started | High | 2023-07-09 | 2023-08-02 |  | 0 | PVC Pipes | Plot 21, Riverside | 29814.98 | 0 | Not started
C004 | Warehouse D | T533 | Steel Framework Setup | Emma White | Blocked | Low | 2024-05-14 | 2024-05-28 |  | 0 | Steel Beams | Industrial Park | 37631.36 | 35957.39 | Not started
C003 | Office Tower C | T444 | Foundation Excavation | Grace Allen | Not Started | Low | 2024-05-07 | 2024-05-24 |  | 0 | Cement | Downtown Avenue | 23179.89 | 0 | Not started
C004 | Warehouse D | T633 | Site Survey | Sarah Johnson | Not Started | Medium | 2023-06-27 | 2023-07-07 |  | 0 | Copper Wires | Industrial Park | 45651.79 | 0 | Not started
C001 | Residential Building A | T849 | Interior Painting | Carlos Rivera | Completed | Low | 2024-12-22 | 2025-01-04 | 2025-01-04 | 100 | Rebar | Plot 21, Riverside | 14918.37 | 14419.09 | No issues
C002 | Shopping Complex B | T787 | Interior Painting | Mike Adams | Not Started | High | 2023-02-27 | 2023-03-07 |  | 0 | Cement | Market Street | 21124.75 | 0 | Not started
C001 | Residential Building A | T979 | Plumbing Installations | Mike Adams | Completed | Medium | 2024-11-02 | 2024-11-22 | 2024-11-22 | 100 | Cement | Plot 21, Riverside | 22493.19 | 20382.45 | No issues
C004 | Warehouse D | T467 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2024-07-11 | 2024-07-19 |  | 21 | PVC Pipes | Industrial Park | 9797.53 | 10200.54 | In progress
C003 | Office Tower C | T615 | Interior Painting | Rachel Green | Not Started | Low | 2023-08-28 | 2023-09-06 |  | 0 | Steel Beams | Downtown Avenue | 20466.02 | 0 | Not started
C003 | Office Tower C | T884 | Interior Painting | Emma White | In Progress | High | 2023-10-28 | 2023-11-21 |  | 97 | Concrete | Downtown Avenue | 11466.81 | 11854.21 | In progress
C001 | Residential Building A | T807 | Steel Framework Setup | Rachel Green | Completed | High | 2024-09-01 | 2024-09-14 | 2024-09-14 | 100 | Rebar | Plot 21, Riverside | 9416.31 | 8094.07 | No issues
C003 | Office Tower C | T612 | Interior Painting | Rachel Green | Not Started | Low | 2023-07-02 | 2023-07-25 |  | 0 | PVC Pipes | Downtown Avenue | 48119.57 | 0 | Not started
C003 | Office Tower C | T451 | Steel Framework Setup | John Miller | In Progress | High | 2024-10-20 | 2024-11-12 |  | 67 | Roofing Sheets | Downtown Avenue | 8297.15 | 5824.75 | In progress
C002 | Shopping Complex B | T664 | Roofing | Grace Allen | Not Started | Medium | 2023-03-08 | 2023-03-16 |  | 0 | PVC Pipes | Market Street | 12161.17 | 0 | Not started
C001 | Residential Building A | T645 | Site Survey | Mike Adams | Not Started | High | 2024-07-24 | 2024-08-10 |  | 0 | Copper Wires | Plot 21, Riverside | 27378.59 | 0 | Not started
C002 | Shopping Complex B | T570 | Site Survey | Mike Adams | In Progress | Medium | 2023-12-18 | 2024-01-13 |  | 7 | Copper Wires | Market Street | 21232.07 | 50457.98 | In progress
C003 | Office Tower C | T181 | Roofing | Grace Allen | Blocked | Medium | 2024-08-04 | 2024-08-23 |  | 0 | Roofing Sheets | Downtown Avenue | 9088.31 | 7162.35 | Not started
C002 | Shopping Complex B | T232 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-10-04 | 2023-10-19 |  | 0 | Steel Beams | Market Street | 21295.26 | 0 | Not started
C002 | Shopping Complex B | T687 | Site Survey | Emma White | Blocked | High | 2024-09-05 | 2024-09-14 |  | 0 | PVC Pipes | Market Street | 27606.6 | 57757.63 | Not started
C003 | Office Tower C | T831 | Interior Painting | Sarah Johnson | Not Started | Medium | 2024-06-13 | 2024-06-26 |  | 0 | Paint | Downtown Avenue | 16915.64 | 0 | Not started
C002 | Shopping Complex B | T945 | Site Survey | Sarah Johnson | Blocked | Medium | 2024-02-12 | 2024-03-05 |  | 0 | PVC Pipes | Market Street | 12031.32 | 34387.49 | Not started
C003 | Office Tower C | T409 | Concrete Pouring | Emma White | Blocked | High | 2023-10-04 | 2023-10-24 |  | 0 | Rebar | Downtown Avenue | 35035.61 | 27584.41 | Not started
C001 | Residential Building A | T191 | Foundation Excavation | Carlos Rivera | In Progress | High | 2023-04-22 | 2023-05-20 |  | 60 | Paint | Plot 21, Riverside | 39794.31 | 41350.34 | In progress
C003 | Office Tower C | T985 | Concrete Pouring | Sarah Johnson | Completed | High | 2023-03-05 | 2023-03-23 | 2023-03-23 | 100 | Steel Beams | Downtown Avenue | 14525 | 12692.88 | No issues
C003 | Office Tower C | T328 | Interior Painting | Mike Adams | In Progress | Medium | 2023-07-12 | 2023-07-27 |  | 51 | Concrete | Downtown Avenue | 31247.72 | 32303.28 | In progress
C004 | Warehouse D | T332 | Roofing | John Miller | Not Started | Medium | 2023-02-07 | 2023-02-21 |  | 0 | Steel Beams | Industrial Park | 26583.7 | 0 | Not started
C003 | Office Tower C | T808 | Foundation Excavation | Sarah Johnson | In Progress | Medium | 2024-10-19 | 2024-11-05 |  | 86 | Paint | Downtown Avenue | 11567.11 | 10612.73 | In progress
C003 | Office Tower C | T487 | Site Survey | Mike Adams | Completed | Low | 2024-10-03 | 2024-10-16 | 2024-10-16 | 100 | Steel Beams | Downtown Avenue | 34269.91 | 38032.88 | No issues
C003 | Office Tower C | T552 | Roofing | Emma White | Completed | Low | 2024-12-11 | 2025-01-10 | 2025-01-10 | 100 | Steel Beams | Downtown Avenue | 26699.43 | 25832.55 | No issues
C002 | Shopping Complex B | T904 | Steel Framework Setup | Rachel Green | Blocked | High | 2023-12-27 | 2024-01-24 |  | 0 | Rebar | Market Street | 48202.45 | 81505.4 | Not started
C004 | Warehouse D | T555 | Roofing | John Miller | Blocked | Low | 2023-12-19 | 2024-01-06 |  | 0 | Steel Beams | Industrial Park | 20591.19 | 15064.56 | Not started
C001 | Residential Building A | T200 | Interior Painting | Emma White | Blocked | High | 2024-11-19 | 2024-12-12 |  | 0 | Rebar | Plot 21, Riverside | 34546.31 | 27384.76 | Not started
C002 | Shopping Complex B | T734 | Plumbing Installations | Dave Brown | Not Started | High | 2024-08-10 | 2024-08-31 |  | 0 | Concrete | Market Street | 48458.55 | 0 | Not started
C004 | Warehouse D | T540 | Roofing | Carlos Rivera | In Progress | High | 2024-09-01 | 2024-09-12 |  | 61 | Cement | Industrial Park | 8719.9 | 8738.57 | In progress
C003 | Office Tower C | T764 | Plumbing Installations | Emma White | In Progress | High | 2023-12-16 | 2024-01-08 |  | 61 | Cement | Downtown Avenue | 28515.5 | 18900.66 | In progress
C004 | Warehouse D | T110 | Roofing | Grace Allen | In Progress | Low | 2024-12-16 | 2025-01-14 |  | 37 | Paint | Industrial Park | 5411.83 | 5093.53 | In progress
C004 | Warehouse D | T719 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-06-17 | 2024-06-25 |  | 0 | PVC Pipes | Industrial Park | 41980.77 | 0 | Not started
C002 | Shopping Complex B | T652 | Interior Painting | Mike Adams | Blocked | Medium | 2024-10-12 | 2024-10-22 |  | 0 | Steel Beams | Market Street | 17532.25 | 36941.26 | Not started
C003 | Office Tower C | T718 | Plumbing Installations | Dave Brown | In Progress | Low | 2023-04-10 | 2023-05-07 |  | 39 | Steel Beams | Downtown Avenue | 18142.75 | 17130.65 | In progress
C002 | Shopping Complex B | T370 | Electrical Wiring | John Miller | Completed | High | 2024-11-01 | 2024-11-18 | 2024-11-18 | 100 | Roofing Sheets | Market Street | 25357.44 | 42372.97 | No issues
C001 | Residential Building A | T869 | Site Survey | John Miller | Not Started | High | 2024-01-15 | 2024-01-26 |  | 0 | Paint | Plot 21, Riverside | 49636 | 0 | Not started
C001 | Residential Building A | T739 | Plumbing Installations | John Miller | Completed | Medium | 2024-12-19 | 2025-01-02 | 2025-01-02 | 100 | Roofing Sheets | Plot 21, Riverside | 6194.96 | 4773.25 | No issues
C001 | Residential Building A | T778 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2023-04-13 | 2023-05-01 |  | 0 | Paint | Plot 21, Riverside | 46969.02 | 45035.77 | Not started
C003 | Office Tower C | T882 | Concrete Pouring | Carlos Rivera | In Progress | High | 2023-02-05 | 2023-03-05 |  | 0 | Steel Beams | Downtown Avenue | 35147.28 | 36887.73 | In progress
C004 | Warehouse D | T368 | Interior Painting | Sarah Johnson | In Progress | Medium | 2023-02-21 | 2023-03-17 |  | 37 | Steel Beams | Industrial Park | 43290.94 | 41195.7 | In progress
C001 | Residential Building A | T486 | Steel Framework Setup | Dave Brown | Blocked | High | 2023-12-25 | 2024-01-16 |  | 0 | Paint | Plot 21, Riverside | 8030.17 | 7464.32 | Not started
C001 | Residential Building A | T437 | Roofing | Dave Brown | Blocked | Low | 2023-04-20 | 2023-05-17 |  | 0 | Concrete | Plot 21, Riverside | 23943.41 | 26851.47 | Not started
C002 | Shopping Complex B | T800 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2023-06-17 | 2023-06-29 |  | 0 | Cement | Market Street | 37725.64 | 66791.43 | Not started
C004 | Warehouse D | T225 | Foundation Excavation | John Miller | Completed | Low | 2023-07-12 | 2023-07-21 | 2023-07-21 | 100 | Concrete | Industrial Park | 43121.62 | 31231.79 | No issues
C001 | Residential Building A | T841 | Foundation Excavation | John Miller | Completed | Low | 2024-08-28 | 2024-09-25 | 2024-09-25 | 100 | Copper Wires | Plot 21, Riverside | 14696.44 | 9372.7 | No issues
C004 | Warehouse D | T466 | Interior Painting | Mike Adams | Not Started | Low | 2024-10-18 | 2024-10-28 |  | 0 | Copper Wires | Industrial Park | 10458.49 | 0 | Not started
C003 | Office Tower C | T917 | Interior Painting | John Miller | Completed | Low | 2023-10-20 | 2023-11-09 | 2023-11-09 | 100 | Concrete | Downtown Avenue | 14959.92 | 14537 | No issues
C003 | Office Tower C | T478 | Steel Framework Setup | Dave Brown | Completed | High | 2023-02-03 | 2023-03-03 | 2023-03-03 | 100 | Copper Wires | Downtown Avenue | 49117.08 | 30548.71 | No issues
C002 | Shopping Complex B | T212 | Foundation Excavation | Grace Allen | Completed | Low | 2023-10-17 | 2023-11-01 | 2023-11-01 | 100 | Concrete | Market Street | 10002.74 | 35158.94 | No issues
C003 | Office Tower C | T113 | Roofing | Grace Allen | In Progress | Medium | 2024-05-09 | 2024-06-08 |  | 62 | Paint | Downtown Avenue | 11193.33 | 12269.35 | In progress
C002 | Shopping Complex B | T349 | Site Survey | Carlos Rivera | In Progress | High | 2024-10-24 | 2024-11-20 |  | 62 | Roofing Sheets | Market Street | 18951.57 | 45595.89 | In progress
C003 | Office Tower C | T799 | Roofing | Rachel Green | Not Started | High | 2024-06-13 | 2024-07-04 |  | 0 | Rebar | Downtown Avenue | 26360.75 | 0 | Not started
C004 | Warehouse D | T149 | Electrical Wiring | John Miller | In Progress | Low | 2023-05-12 | 2023-05-28 |  | 14 | Rebar | Industrial Park | 28369.56 | 22893.09 | In progress
C002 | Shopping Complex B | T398 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-06-19 | 2023-07-12 |  | 0 | Rebar | Market Street | 36574.77 | 54534.22 | Not started
C002 | Shopping Complex B | T687 | Concrete Pouring | Rachel Green | Not Started | Medium | 2023-08-23 | 2023-08-31 |  | 0 | Steel Beams | Market Street | 35408.55 | 0 | Not started
C003 | Office Tower C | T696 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2024-01-28 | 2024-02-27 |  | 73 | Steel Beams | Downtown Avenue | 35838.06 | 27205.74 | In progress
C003 | Office Tower C | T904 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2024-10-21 | 2024-11-18 |  | 66 | Steel Beams | Downtown Avenue | 46582.31 | 46934.82 | In progress
C004 | Warehouse D | T750 | Site Survey | Sarah Johnson | Not Started | Medium | 2024-10-14 | 2024-10-31 |  | 0 | Concrete | Industrial Park | 21457.74 | 0 | Not started
C004 | Warehouse D | T892 | Steel Framework Setup | Rachel Green | Not Started | High | 2024-10-22 | 2024-11-11 |  | 0 | Rebar | Industrial Park | 36076.24 | 0 | Not started
C004 | Warehouse D | T244 | Concrete Pouring | Emma White | In Progress | High | 2023-09-14 | 2023-09-28 |  | 58 | Rebar | Industrial Park | 47308.75 | 38034.26 | In progress
C003 | Office Tower C | T392 | Foundation Excavation | Rachel Green | Not Started | Medium | 2023-11-21 | 2023-12-10 |  | 0 | Paint | Downtown Avenue | 14758.27 | 0 | Not started
C004 | Warehouse D | T523 | Plumbing Installations | Grace Allen | Blocked | Low | 2023-12-06 | 2024-01-05 |  | 0 | Paint | Industrial Park | 13020.12 | 12069.68 | Not started
C004 | Warehouse D | T632 | Concrete Pouring | Dave Brown | Blocked | Low | 2024-12-18 | 2025-01-15 |  | 0 | Copper Wires | Industrial Park | 33460.35 | 34149.36 | Not started
C001 | Residential Building A | T507 | Foundation Excavation | Mike Adams | In Progress | Medium | 2024-08-20 | 2024-09-13 |  | 75 | Concrete | Plot 21, Riverside | 43896.36 | 39666.11 | In progress
C002 | Shopping Complex B | T705 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-11-23 | 2023-11-30 |  | 0 | Roofing Sheets | Market Street | 35018.89 | 0 | Not started
C002 | Shopping Complex B | T960 | Concrete Pouring | Dave Brown | Completed | High | 2024-08-24 | 2024-09-17 | 2024-09-17 | 100 | Steel Beams | Market Street | 17639.55 | 43922.08 | No issues
C004 | Warehouse D | T617 | Roofing | John Miller | Not Started | Medium | 2023-07-20 | 2023-07-31 |  | 0 | Concrete | Industrial Park | 44839.95 | 0 | Not started
C001 | Residential Building A | T222 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2023-08-15 | 2023-09-08 |  | 0 | Cement | Plot 21, Riverside | 42642.96 | 0 | Not started
C004 | Warehouse D | T385 | Site Survey | Mike Adams | In Progress | Low | 2024-06-23 | 2024-07-06 |  | 76 | Roofing Sheets | Industrial Park | 42534.29 | 29658.49 | In progress
C002 | Shopping Complex B | T648 | Site Survey | Emma White | Blocked | High | 2023-11-13 | 2023-12-10 |  | 0 | Cement | Market Street | 11833.59 | 35229.73 | Not started
C003 | Office Tower C | T103 | Roofing | John Miller | Not Started | High | 2024-11-06 | 2024-11-21 |  | 0 | Steel Beams | Downtown Avenue | 32490.18 | 0 | Not started
C002 | Shopping Complex B | T878 | Electrical Wiring | Dave Brown | Completed | Medium | 2023-03-08 | 2023-03-16 | 2023-03-16 | 100 | Roofing Sheets | Market Street | 43491.21 | 62436.73 | No issues
C002 | Shopping Complex B | T874 | Foundation Excavation | John Miller | Blocked | Medium | 2023-09-13 | 2023-10-10 |  | 0 | Roofing Sheets | Market Street | 42479.08 | 59258.14 | Not started
C004 | Warehouse D | T930 | Electrical Wiring | Mike Adams | Blocked | Medium | 2024-05-06 | 2024-05-24 |  | 0 | Steel Beams | Industrial Park | 44362.01 | 34899.78 | Not started
C004 | Warehouse D | T900 | Site Survey | Emma White | Completed | Medium | 2024-06-25 | 2024-07-05 | 2024-07-05 | 100 | Copper Wires | Industrial Park | 19991.88 | 17068.68 | No issues
C001 | Residential Building A | T427 | Site Survey | Grace Allen | Not Started | Medium | 2023-06-10 | 2023-06-18 |  | 0 | Rebar | Plot 21, Riverside | 28384.48 | 0 | Not started
C004 | Warehouse D | T365 | Concrete Pouring | Carlos Rivera | Completed | High | 2023-11-27 | 2023-12-23 | 2023-12-23 | 100 | Rebar | Industrial Park | 18216.19 | 11311.05 | No issues
C002 | Shopping Complex B | T517 | Concrete Pouring | Mike Adams | Blocked | Medium | 2024-12-16 | 2025-01-03 |  | 0 | Steel Beams | Market Street | 22759.99 | 40304.48 | Not started
C001 | Residential Building A | T123 | Plumbing Installations | Mike Adams | Blocked | High | 2023-09-10 | 2023-09-23 |  | 0 | Copper Wires | Plot 21, Riverside | 23117.49 | 15009.93 | Not started
C001 | Residential Building A | T789 | Roofing | Carlos Rivera | Blocked | Medium | 2023-08-07 | 2023-09-03 |  | 0 | Rebar | Plot 21, Riverside | 19671.84 | 22917.93 | Not started
C002 | Shopping Complex B | T923 | Site Survey | Dave Brown | Blocked | High | 2024-09-09 | 2024-09-22 |  | 0 | Rebar | Market Street | 36084.56 | 68689.14 | Not started
C003 | Office Tower C | T528 | Interior Painting | Emma White | Blocked | Low | 2023-07-27 | 2023-08-12 |  | 0 | Roofing Sheets | Downtown Avenue | 15441.12 | 18227.55 | Not started
C001 | Residential Building A | T920 | Concrete Pouring | Dave Brown | Completed | Medium | 2024-08-25 | 2024-09-02 | 2024-09-02 | 100 | Copper Wires | Plot 21, Riverside | 22606.77 | 23079.53 | No issues
C002 | Shopping Complex B | T559 | Roofing | Emma White | Blocked | High | 2024-12-28 | 2025-01-26 |  | 0 | Cement | Market Street | 10272.84 | 36385.88 | Not started
C002 | Shopping Complex B | T144 | Site Survey | Rachel Green | Blocked | Medium | 2024-01-20 | 2024-02-12 |  | 0 | Paint | Market Street | 44789.43 | 65794.23 | Not started
C003 | Office Tower C | T598 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-10-21 | 2023-11-02 | 2023-11-02 | 100 | Steel Beams | Downtown Avenue | 11154.8 | 9454.3 | No issues
C003 | Office Tower C | T693 | Interior Painting | Grace Allen | In Progress | High | 2024-11-12 | 2024-11-23 |  | 50 | PVC Pipes | Downtown Avenue | 26046.83 | 16889.53 | In progress
C002 | Shopping Complex B | T182 | Site Survey | Rachel Green | Not Started | Medium | 2023-09-19 | 2023-10-13 |  | 0 | PVC Pipes | Market Street | 12477.38 | 0 | Not started
C003 | Office Tower C | T682 | Electrical Wiring | Emma White | Completed | High | 2024-07-02 | 2024-07-30 | 2024-07-30 | 100 | Roofing Sheets | Downtown Avenue | 5896.56 | 6463.11 | No issues
C002 | Shopping Complex B | T147 | Concrete Pouring | Dave Brown | Completed | Medium | 2024-11-26 | 2024-12-10 | 2024-12-10 | 100 | Steel Beams | Market Street | 6856.66 | 33362.72 | No issues
C004 | Warehouse D | T520 | Concrete Pouring | Sarah Johnson | Blocked | Medium | 2024-12-05 | 2024-12-23 |  | 0 | Cement | Industrial Park | 5042.4 | 4763.24 | Not started
C003 | Office Tower C | T357 | Interior Painting | Mike Adams | Completed | High | 2023-03-23 | 2023-04-16 | 2023-04-16 | 100 | PVC Pipes | Downtown Avenue | 27697.17 | 20363.07 | No issues
C001 | Residential Building A | T116 | Roofing | Dave Brown | Not Started | Medium | 2024-02-03 | 2024-02-27 |  | 0 | Roofing Sheets | Plot 21, Riverside | 45443.62 | 0 | Not started
C001 | Residential Building A | T871 | Concrete Pouring | Rachel Green | Blocked | Low | 2023-06-08 | 2023-06-23 |  | 0 | Cement | Plot 21, Riverside | 44169.2 | 46567.56 | Not started
C004 | Warehouse D | T188 | Plumbing Installations | Mike Adams | In Progress | Medium | 2024-06-09 | 2024-06-20 |  | 0 | Paint | Industrial Park | 7446.12 | 5510.73 | In progress
C002 | Shopping Complex B | T637 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2023-04-25 | 2023-05-22 |  | 16 | Copper Wires | Market Street | 36173.6 | 58863.81 | In progress
C003 | Office Tower C | T593 | Electrical Wiring | Rachel Green | In Progress | High | 2024-02-16 | 2024-02-28 |  | 55 | Concrete | Downtown Avenue | 45337.43 | 28740.77 | In progress
C003 | Office Tower C | T428 | Plumbing Installations | Mike Adams | Completed | Low | 2023-09-15 | 2023-10-11 | 2023-10-11 | 100 | Steel Beams | Downtown Avenue | 32175.4 | 38246.05 | No issues
C004 | Warehouse D | T760 | Electrical Wiring | John Miller | In Progress | Low | 2023-08-28 | 2023-09-23 |  | 65 | Steel Beams | Industrial Park | 44714.33 | 27998.87 | In progress
C001 | Residential Building A | T812 | Plumbing Installations | Emma White | Not Started | Low | 2024-03-03 | 2024-03-23 |  | 0 | Steel Beams | Plot 21, Riverside | 9698.56 | 0 | Not started
C001 | Residential Building A | T479 | Foundation Excavation | Carlos Rivera | Not Started | High | 2023-06-07 | 2023-06-23 |  | 0 | Roofing Sheets | Plot 21, Riverside | 26917.19 | 0 | Not started
C001 | Residential Building A | T868 | Interior Painting | Sarah Johnson | Not Started | High | 2024-04-21 | 2024-04-28 |  | 0 | Roofing Sheets | Plot 21, Riverside | 22017.32 | 0 | Not started
C003 | Office Tower C | T505 | Interior Painting | John Miller | Completed | Medium | 2023-11-22 | 2023-12-10 | 2023-12-10 | 100 | Rebar | Downtown Avenue | 8441.94 | 8861.32 | No issues
C003 | Office Tower C | T132 | Steel Framework Setup | Grace Allen | Not Started | Low | 2024-11-22 | 2024-12-11 |  | 0 | Paint | Downtown Avenue | 48331.67 | 0 | Not started
C002 | Shopping Complex B | T606 | Site Survey | Sarah Johnson | Not Started | Medium | 2023-01-04 | 2023-01-31 |  | 0 | PVC Pipes | Market Street | 22878.24 | 0 | Not started
C002 | Shopping Complex B | T881 | Roofing | Dave Brown | Completed | High | 2023-12-14 | 2024-01-07 | 2024-01-07 | 100 | Paint | Market Street | 24447.52 | 45305.06 | No issues
C004 | Warehouse D | T630 | Interior Painting | Sarah Johnson | Not Started | Medium | 2023-10-19 | 2023-11-17 |  | 0 | PVC Pipes | Industrial Park | 8071.98 | 0 | Not started
C004 | Warehouse D | T655 | Concrete Pouring | John Miller | Completed | Medium | 2024-05-25 | 2024-06-02 | 2024-06-02 | 100 | Rebar | Industrial Park | 24006.6 | 25543.9 | No issues
C001 | Residential Building A | T904 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-09-06 | 2023-09-15 |  | 0 | Rebar | Plot 21, Riverside | 30850.02 | 36023.52 | Not started
C004 | Warehouse D | T591 | Roofing | Emma White | Blocked | High | 2023-09-28 | 2023-10-13 |  | 0 | Roofing Sheets | Industrial Park | 28765.65 | 29616.5 | Not started
C004 | Warehouse D | T812 | Roofing | Rachel Green | In Progress | Low | 2023-08-09 | 2023-08-20 |  | 36 | Cement | Industrial Park | 31699.67 | 20007.28 | In progress
C003 | Office Tower C | T330 | Foundation Excavation | Grace Allen | In Progress | High | 2024-10-19 | 2024-11-02 |  | 20 | Cement | Downtown Avenue | 47296.04 | 34110.85 | In progress
C002 | Shopping Complex B | T497 | Plumbing Installations | Mike Adams | Completed | Low | 2024-07-25 | 2024-08-06 | 2024-08-06 | 100 | Rebar | Market Street | 29846 | 57613.34 | No issues
C001 | Residential Building A | T186 | Plumbing Installations | Dave Brown | In Progress | High | 2024-04-13 | 2024-05-11 |  | 1 | PVC Pipes | Plot 21, Riverside | 48029.35 | 39383.91 | In progress
C004 | Warehouse D | T820 | Site Survey | John Miller | Not Started | Medium | 2023-12-21 | 2024-01-12 |  | 0 | Roofing Sheets | Industrial Park | 17316.62 | 0 | Not started
C004 | Warehouse D | T204 | Electrical Wiring | John Miller | Completed | Low | 2024-08-20 | 2024-09-01 | 2024-09-01 | 100 | Rebar | Industrial Park | 34777.22 | 26439.91 | No issues
C001 | Residential Building A | T840 | Steel Framework Setup | Dave Brown | In Progress | Low | 2023-06-17 | 2023-07-16 |  | 69 | Steel Beams | Plot 21, Riverside | 44000.66 | 34205.66 | In progress
C004 | Warehouse D | T126 | Concrete Pouring | Grace Allen | In Progress | High | 2024-01-23 | 2024-02-20 |  | 97 | PVC Pipes | Industrial Park | 31292.11 | 37377.39 | In progress
C003 | Office Tower C | T895 | Site Survey | Sarah Johnson | Blocked | High | 2024-07-12 | 2024-08-09 |  | 0 | Steel Beams | Downtown Avenue | 15404.91 | 9422.66 | Not started
C002 | Shopping Complex B | T257 | Electrical Wiring | Sarah Johnson | Completed | Low | 2023-11-03 | 2023-11-11 | 2023-11-11 | 100 | Paint | Market Street | 14845.46 | 40254.17 | No issues
C001 | Residential Building A | T781 | Roofing | Grace Allen | Not Started | Low | 2023-05-20 | 2023-06-10 |  | 0 | Paint | Plot 21, Riverside | 8089.8 | 0 | Not started
C004 | Warehouse D | T405 | Electrical Wiring | Mike Adams | Blocked | Low | 2024-11-15 | 2024-12-04 |  | 0 | Rebar | Industrial Park | 6790.38 | 7063.87 | Not started
C001 | Residential Building A | T207 | Foundation Excavation | Emma White | Not Started | High | 2024-10-10 | 2024-10-22 |  | 0 | Paint | Plot 21, Riverside | 43372.31 | 0 | Not started
C001 | Residential Building A | T886 | Foundation Excavation | Mike Adams | Completed | Low | 2023-07-07 | 2023-07-19 | 2023-07-19 | 100 | PVC Pipes | Plot 21, Riverside | 29386.56 | 30329.53 | No issues
C002 | Shopping Complex B | T829 | Foundation Excavation | Grace Allen | In Progress | High | 2024-12-16 | 2025-01-04 |  | 93 | Cement | Market Street | 7664.6 | 32320.24 | In progress
C002 | Shopping Complex B | T509 | Electrical Wiring | Emma White | Not Started | High | 2023-11-01 | 2023-11-18 |  | 0 | Steel Beams | Market Street | 10787.83 | 0 | Not started
C002 | Shopping Complex B | T902 | Concrete Pouring | Dave Brown | Blocked | Medium | 2024-05-13 | 2024-06-02 |  | 0 | Steel Beams | Market Street | 39882.35 | 60251.87 | Not started
C001 | Residential Building A | T976 | Site Survey | Sarah Johnson | Not Started | Low | 2024-02-18 | 2024-02-28 |  | 0 | Concrete | Plot 21, Riverside | 15917.05 | 0 | Not started
C004 | Warehouse D | T443 | Electrical Wiring | John Miller | Blocked | Medium | 2024-11-28 | 2024-12-17 |  | 0 | Paint | Industrial Park | 19520.78 | 18811.47 | Not started
C002 | Shopping Complex B | T578 | Electrical Wiring | John Miller | Blocked | Medium | 2024-09-03 | 2024-09-15 |  | 0 | Rebar | Market Street | 47248.63 | 80403.42 | Not started
C002 | Shopping Complex B | T330 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-12-06 | 2024-01-03 |  | 82 | Rebar | Market Street | 49362.86 | 64006.68 | In progress
C004 | Warehouse D | T344 | Electrical Wiring | Emma White | Blocked | Low | 2023-03-14 | 2023-03-27 |  | 0 | Concrete | Industrial Park | 21954.44 | 14458.89 | Not started
C002 | Shopping Complex B | T518 | Concrete Pouring | Carlos Rivera | Blocked | High | 2023-03-09 | 2023-03-29 |  | 0 | Cement | Market Street | 14875.12 | 36290.91 | Not started
C003 | Office Tower C | T293 | Steel Framework Setup | Sarah Johnson | In Progress | Medium | 2024-11-04 | 2024-11-24 |  | 73 | Cement | Downtown Avenue | 18490.4 | 20988.7 | In progress
C001 | Residential Building A | T299 | Interior Painting | Carlos Rivera | In Progress | High | 2023-04-16 | 2023-04-30 |  | 31 | Concrete | Plot 21, Riverside | 22939.28 | 20474.4 | In progress
C004 | Warehouse D | T456 | Plumbing Installations | John Miller | Blocked | Low | 2023-04-15 | 2023-04-26 |  | 0 | Paint | Industrial Park | 15645 | 17683.17 | Not started
C003 | Office Tower C | T619 | Concrete Pouring | Rachel Green | In Progress | Medium | 2024-09-12 | 2024-10-11 |  | 99 | Roofing Sheets | Downtown Avenue | 42477.96 | 29282.72 | In progress
C003 | Office Tower C | T581 | Electrical Wiring | Rachel Green | Not Started | High | 2023-06-11 | 2023-06-27 |  | 0 | Steel Beams | Downtown Avenue | 37491.85 | 0 | Not started
C001 | Residential Building A | T408 | Steel Framework Setup | John Miller | Not Started | High | 2024-07-08 | 2024-07-24 |  | 0 | Paint | Plot 21, Riverside | 11930.93 | 0 | Not started
C003 | Office Tower C | T737 | Roofing | Dave Brown | In Progress | Medium | 2023-12-13 | 2024-01-12 |  | 4 | Paint | Downtown Avenue | 27954.53 | 30718.55 | In progress
C004 | Warehouse D | T351 | Roofing | Mike Adams | Completed | Low | 2024-11-27 | 2024-12-12 | 2024-12-12 | 100 | Paint | Industrial Park | 40478.61 | 40117.81 | No issues
C002 | Shopping Complex B | T694 | Interior Painting | Grace Allen | Blocked | Low | 2024-04-21 | 2024-05-12 |  | 0 | PVC Pipes | Market Street | 28510.79 | 46829.58 | Not started
C002 | Shopping Complex B | T773 | Plumbing Installations | Rachel Green | Completed | Low | 2023-04-15 | 2023-05-06 | 2023-05-06 | 100 | Paint | Market Street | 44056.8 | 66697.65 | No issues
C001 | Residential Building A | T718 | Roofing | Dave Brown | Blocked | Medium | 2023-10-03 | 2023-10-11 |  | 0 | Roofing Sheets | Plot 21, Riverside | 16619.33 | 13046.63 | Not started
C001 | Residential Building A | T302 | Interior Painting | John Miller | Not Started | High | 2024-07-27 | 2024-08-21 |  | 0 | Steel Beams | Plot 21, Riverside | 27264.87 | 0 | Not started
C001 | Residential Building A | T308 | Plumbing Installations | Sarah Johnson | Completed | Low | 2024-12-19 | 2024-12-27 | 2024-12-27 | 100 | Cement | Plot 21, Riverside | 12371.55 | 13634.96 | No issues
C001 | Residential Building A | T323 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-01-28 | 2024-02-24 |  | 0 | Rebar | Plot 21, Riverside | 16462.08 | 17813.54 | Not started
C004 | Warehouse D | T607 | Concrete Pouring | Grace Allen | Blocked | Medium | 2024-12-05 | 2024-12-20 |  | 0 | Copper Wires | Industrial Park | 19102.07 | 13987.97 | Not started
C002 | Shopping Complex B | T999 | Concrete Pouring | Sarah Johnson | Not Started | Medium | 2023-03-05 | 2023-03-23 |  | 0 | PVC Pipes | Market Street | 21571.01 | 0 | Not started
C001 | Residential Building A | T892 | Electrical Wiring | Grace Allen | Blocked | High | 2023-04-03 | 2023-04-14 |  | 0 | Roofing Sheets | Plot 21, Riverside | 12851.72 | 14275.51 | Not started
C002 | Shopping Complex B | T386 | Plumbing Installations | Rachel Green | Completed | Medium | 2024-06-24 | 2024-07-10 | 2024-07-10 | 100 | Rebar | Market Street | 17794.5 | 37929.02 | No issues
C004 | Warehouse D | T625 | Electrical Wiring | Carlos Rivera | Completed | Low | 2023-12-01 | 2023-12-20 | 2023-12-20 | 100 | Roofing Sheets | Industrial Park | 44160.76 | 44877.64 | No issues
C001 | Residential Building A | T959 | Foundation Excavation | Dave Brown | Blocked | Low | 2024-02-24 | 2024-03-02 |  | 0 | Paint | Plot 21, Riverside | 16462.71 | 15463.59 | Not started
C003 | Office Tower C | T788 | Plumbing Installations | Grace Allen | Completed | Low | 2024-09-19 | 2024-10-15 | 2024-10-15 | 100 | Roofing Sheets | Downtown Avenue | 27853.55 | 23409.9 | No issues
C002 | Shopping Complex B | T108 | Roofing | Sarah Johnson | Blocked | High | 2023-02-03 | 2023-02-26 |  | 0 | Copper Wires | Market Street | 17692.44 | 43051.6 | Not started
C004 | Warehouse D | T719 | Plumbing Installations | Emma White | Blocked | Low | 2024-01-21 | 2024-02-03 |  | 0 | Rebar | Industrial Park | 48985.6 | 57586.38 | Not started
C004 | Warehouse D | T871 | Electrical Wiring | Grace Allen | Not Started | High | 2023-07-22 | 2023-07-29 |  | 0 | Paint | Industrial Park | 39259.56 | 0 | Not started
C003 | Office Tower C | T278 | Plumbing Installations | Rachel Green | Not Started | High | 2023-02-05 | 2023-03-03 |  | 0 | Roofing Sheets | Downtown Avenue | 37121.01 | 0 | Not started
C002 | Shopping Complex B | T600 | Plumbing Installations | Dave Brown | In Progress | Low | 2024-02-08 | 2024-03-05 |  | 11 | Rebar | Market Street | 10679.91 | 33523.08 | In progress
C004 | Warehouse D | T168 | Roofing | Dave Brown | Completed | High | 2023-03-14 | 2023-04-12 | 2023-04-12 | 100 | PVC Pipes | Industrial Park | 23117.75 | 24370.53 | No issues
C003 | Office Tower C | T311 | Steel Framework Setup | John Miller | Not Started | High | 2024-07-12 | 2024-07-28 |  | 0 | Cement | Downtown Avenue | 28918.19 | 0 | Not started
C003 | Office Tower C | T471 | Roofing | Emma White | Not Started | Medium | 2024-05-17 | 2024-06-06 |  | 0 | Copper Wires | Downtown Avenue | 15467.57 | 0 | Not started
C002 | Shopping Complex B | T968 | Steel Framework Setup | Grace Allen | Completed | Medium | 2024-02-25 | 2024-03-18 | 2024-03-18 | 100 | Roofing Sheets | Market Street | 41915.3 | 72879.01 | No issues
C001 | Residential Building A | T249 | Electrical Wiring | Grace Allen | In Progress | Low | 2024-01-14 | 2024-02-13 |  | 98 | Rebar | Plot 21, Riverside | 18362.37 | 14750.26 | In progress
C001 | Residential Building A | T612 | Concrete Pouring | Sarah Johnson | Blocked | High | 2023-11-20 | 2023-12-19 |  | 0 | Copper Wires | Plot 21, Riverside | 39415.67 | 32189.19 | Not started
C004 | Warehouse D | T645 | Site Survey | Grace Allen | Blocked | Low | 2024-02-08 | 2024-03-03 |  | 0 | PVC Pipes | Industrial Park | 30683.02 | 28186.1 | Not started
C001 | Residential Building A | T729 | Interior Painting | Grace Allen | Not Started | High | 2023-04-25 | 2023-05-25 |  | 0 | PVC Pipes | Plot 21, Riverside | 27428.41 | 0 | Not started
C001 | Residential Building A | T216 | Foundation Excavation | Sarah Johnson | Not Started | Medium | 2023-05-11 | 2023-05-25 |  | 0 | Concrete | Plot 21, Riverside | 27549.08 | 0 | Not started
C002 | Shopping Complex B | T692 | Foundation Excavation | Sarah Johnson | Blocked | High | 2023-11-20 | 2023-12-13 |  | 0 | Rebar | Market Street | 16355.31 | 41339.02 | Not started
C003 | Office Tower C | T722 | Plumbing Installations | Emma White | In Progress | Medium | 2024-03-24 | 2024-04-17 |  | 38 | PVC Pipes | Downtown Avenue | 36982.95 | 29326.7 | In progress
C001 | Residential Building A | T587 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-10-11 | 2023-11-09 |  | 33 | Copper Wires | Plot 21, Riverside | 45053.83 | 44811.96 | In progress
C003 | Office Tower C | T735 | Plumbing Installations | Sarah Johnson | Blocked | Low | 2024-03-18 | 2024-03-26 |  | 0 | Cement | Downtown Avenue | 41745.81 | 46606.55 | Not started
C001 | Residential Building A | T915 | Interior Painting | Dave Brown | Not Started | Low | 2024-03-28 | 2024-04-16 |  | 0 | PVC Pipes | Plot 21, Riverside | 32647.39 | 0 | Not started
C004 | Warehouse D | T351 | Roofing | John Miller | In Progress | High | 2023-07-16 | 2023-08-07 |  | 21 | Steel Beams | Industrial Park | 39962.35 | 42158.02 | In progress
C003 | Office Tower C | T862 | Roofing | Emma White | In Progress | Low | 2024-06-13 | 2024-06-28 |  | 14 | Copper Wires | Downtown Avenue | 5139.02 | 3712.96 | In progress
C001 | Residential Building A | T180 | Steel Framework Setup | Dave Brown | Not Started | High | 2023-06-22 | 2023-06-29 |  | 0 | Roofing Sheets | Plot 21, Riverside | 47686.81 | 0 | Not started
C003 | Office Tower C | T921 | Site Survey | Emma White | Not Started | Medium | 2023-03-22 | 2023-04-13 |  | 0 | PVC Pipes | Downtown Avenue | 44077.46 | 0 | Not started
C002 | Shopping Complex B | T182 | Plumbing Installations | Grace Allen | Completed | High | 2024-10-19 | 2024-11-07 | 2024-11-07 | 100 | Rebar | Market Street | 14717.69 | 38317.19 | No issues
C003 | Office Tower C | T389 | Foundation Excavation | Emma White | In Progress | High | 2024-11-22 | 2024-11-29 |  | 19 | Steel Beams | Downtown Avenue | 6762.62 | 5104.96 | In progress
C003 | Office Tower C | T377 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2023-04-05 | 2023-04-24 |  | 0 | PVC Pipes | Downtown Avenue | 46167.22 | 44777.34 | Not started
C001 | Residential Building A | T416 | Roofing | Carlos Rivera | Not Started | High | 2024-05-05 | 2024-05-18 |  | 0 | Concrete | Plot 21, Riverside | 22424.34 | 0 | Not started
C004 | Warehouse D | T338 | Concrete Pouring | Sarah Johnson | Blocked | High | 2024-12-06 | 2024-12-22 |  | 0 | Paint | Industrial Park | 18873.02 | 11690.15 | Not started
C002 | Shopping Complex B | T853 | Site Survey | Carlos Rivera | Blocked | High | 2023-12-11 | 2023-12-23 |  | 0 | Steel Beams | Market Street | 34158.2 | 65338.4 | Not started
C002 | Shopping Complex B | T825 | Concrete Pouring | John Miller | Not Started | Medium | 2023-10-27 | 2023-11-14 |  | 0 | PVC Pipes | Market Street | 25876.86 | 0 | Not started
C002 | Shopping Complex B | T349 | Foundation Excavation | Rachel Green | In Progress | Low | 2024-01-03 | 2024-01-30 |  | 13 | Roofing Sheets | Market Street | 47606.01 | 68476.48 | In progress
C004 | Warehouse D | T774 | Interior Painting | Dave Brown | In Progress | High | 2023-07-20 | 2023-07-28 |  | 6 | Concrete | Industrial Park | 12658.06 | 9542.19 | In progress
C001 | Residential Building A | T530 | Electrical Wiring | Carlos Rivera | Completed | Low | 2024-10-16 | 2024-11-04 | 2024-11-04 | 100 | Steel Beams | Plot 21, Riverside | 27035.15 | 21098.88 | No issues
C001 | Residential Building A | T129 | Electrical Wiring | Rachel Green | Completed | High | 2023-01-14 | 2023-02-08 | 2023-02-08 | 100 | Cement | Plot 21, Riverside | 33495.89 | 27889.32 | No issues
C004 | Warehouse D | T476 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2024-03-20 | 2024-03-28 |  | 0 | Paint | Industrial Park | 23377.04 | 22676.75 | Not started
C001 | Residential Building A | T799 | Interior Painting | Carlos Rivera | Completed | High | 2024-09-09 | 2024-10-02 | 2024-10-02 | 100 | Paint | Plot 21, Riverside | 44158.31 | 31342.65 | No issues
C002 | Shopping Complex B | T547 | Electrical Wiring | Grace Allen | Blocked | High | 2023-08-12 | 2023-09-09 |  | 0 | Copper Wires | Market Street | 39853.2 | 50728.47 | Not started
C004 | Warehouse D | T672 | Steel Framework Setup | Rachel Green | Blocked | Low | 2024-02-06 | 2024-03-03 |  | 0 | Cement | Industrial Park | 25551.15 | 17389.52 | Not started
C004 | Warehouse D | T775 | Roofing | Emma White | Not Started | High | 2023-01-04 | 2023-01-31 |  | 0 | Roofing Sheets | Industrial Park | 38547.87 | 0 | Not started
C001 | Residential Building A | T892 | Site Survey | Sarah Johnson | In Progress | Low | 2023-04-05 | 2023-05-01 |  | 43 | PVC Pipes | Plot 21, Riverside | 31064.41 | 34316.4 | In progress
C001 | Residential Building A | T777 | Foundation Excavation | John Miller | In Progress | High | 2023-07-07 | 2023-07-18 |  | 13 | Paint | Plot 21, Riverside | 16037.32 | 16637.68 | In progress
C002 | Shopping Complex B | T871 | Roofing | Emma White | In Progress | Medium | 2024-05-07 | 2024-05-18 |  | 16 | Copper Wires | Market Street | 7254.95 | 30955.42 | In progress
C003 | Office Tower C | T742 | Electrical Wiring | Sarah Johnson | In Progress | High | 2023-11-08 | 2023-12-04 |  | 22 | Concrete | Downtown Avenue | 6538.1 | 5859.94 | In progress
C002 | Shopping Complex B | T740 | Interior Painting | John Miller | Not Started | Medium | 2024-05-25 | 2024-06-06 |  | 0 | Steel Beams | Market Street | 42724.98 | 0 | Not started
C003 | Office Tower C | T507 | Interior Painting | Dave Brown | Not Started | Medium | 2023-11-21 | 2023-12-16 |  | 0 | Roofing Sheets | Downtown Avenue | 33166.84 | 0 | Not started
C001 | Residential Building A | T684 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-05-24 | 2024-06-06 |  | 36 | Cement | Plot 21, Riverside | 20805.74 | 24556.82 | In progress
C001 | Residential Building A | T940 | Steel Framework Setup | Rachel Green | Not Started | High | 2023-03-23 | 2023-04-02 |  | 0 | Rebar | Plot 21, Riverside | 47480.67 | 0 | Not started
C003 | Office Tower C | T262 | Interior Painting | Mike Adams | Completed | High | 2024-08-16 | 2024-08-31 | 2024-08-31 | 100 | PVC Pipes | Downtown Avenue | 7933.79 | 8010.64 | No issues
C001 | Residential Building A | T787 | Concrete Pouring | John Miller | In Progress | Low | 2024-12-16 | 2024-12-23 |  | 48 | Steel Beams | Plot 21, Riverside | 28355 | 26280.89 | In progress
C004 | Warehouse D | T638 | Plumbing Installations | Emma White | Blocked | Medium | 2024-11-24 | 2024-12-13 |  | 0 | Roofing Sheets | Industrial Park | 31792.44 | 19565.34 | Not started
C003 | Office Tower C | T244 | Roofing | John Miller | Completed | Medium | 2023-12-05 | 2023-12-19 | 2023-12-19 | 100 | Steel Beams | Downtown Avenue | 11846.05 | 13896.92 | No issues
C001 | Residential Building A | T966 | Steel Framework Setup | Carlos Rivera | Blocked | High | 2023-10-11 | 2023-11-02 |  | 0 | Rebar | Plot 21, Riverside | 16405.37 | 19571.03 | Not started
C001 | Residential Building A | T679 | Site Survey | Dave Brown | In Progress | Medium | 2023-02-14 | 2023-03-04 |  | 46 | Roofing Sheets | Plot 21, Riverside | 33791.02 | 35980.24 | In progress
C004 | Warehouse D | T347 | Roofing | John Miller | Blocked | Low | 2024-04-13 | 2024-04-21 |  | 0 | Cement | Industrial Park | 27335.13 | 18991.75 | Not started
C003 | Office Tower C | T877 | Electrical Wiring | Mike Adams | Not Started | Medium | 2024-04-01 | 2024-04-12 |  | 0 | PVC Pipes | Downtown Avenue | 36313.09 | 0 | Not started
C003 | Office Tower C | T408 | Site Survey | Dave Brown | Blocked | High | 2024-10-23 | 2024-11-17 |  | 0 | Cement | Downtown Avenue | 47725.23 | 31731.68 | Not started
C004 | Warehouse D | T252 | Plumbing Installations | Carlos Rivera | Blocked | High | 2023-05-11 | 2023-05-22 |  | 0 | Rebar | Industrial Park | 21177.73 | 23008.96 | Not started
C003 | Office Tower C | T869 | Concrete Pouring | Grace Allen | In Progress | High | 2024-08-20 | 2024-09-06 |  | 22 | Concrete | Downtown Avenue | 32537.91 | 29285.22 | In progress
C001 | Residential Building A | T460 | Plumbing Installations | Rachel Green | Completed | High | 2024-02-05 | 2024-02-14 | 2024-02-14 | 100 | Copper Wires | Plot 21, Riverside | 28227.53 | 30447.43 | No issues
C004 | Warehouse D | T224 | Electrical Wiring | Emma White | Blocked | Medium | 2023-12-04 | 2023-12-14 |  | 0 | Rebar | Industrial Park | 20580.35 | 20305.74 | Not started
C003 | Office Tower C | T416 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-04-07 | 2023-04-21 |  | 0 | Steel Beams | Downtown Avenue | 46404.1 | 0 | Not started
C001 | Residential Building A | T124 | Roofing | Emma White | Blocked | High | 2024-03-06 | 2024-03-29 |  | 0 | Roofing Sheets | Plot 21, Riverside | 7711.82 | 8715.38 | Not started
C003 | Office Tower C | T700 | Electrical Wiring | Mike Adams | Completed | Low | 2024-03-12 | 2024-03-31 | 2024-03-31 | 100 | Cement | Downtown Avenue | 22134.79 | 19137.6 | No issues
C004 | Warehouse D | T689 | Foundation Excavation | Rachel Green | Completed | Medium | 2024-07-25 | 2024-08-20 | 2024-08-20 | 100 | Steel Beams | Industrial Park | 46732.47 | 45506.86 | No issues
C003 | Office Tower C | T810 | Interior Painting | Grace Allen | Completed | Low | 2023-12-05 | 2024-01-02 | 2024-01-02 | 100 | PVC Pipes | Downtown Avenue | 31327.14 | 29969.63 | No issues
C003 | Office Tower C | T456 | Concrete Pouring | John Miller | Completed | High | 2024-12-11 | 2024-12-26 | 2024-12-26 | 100 | Concrete | Downtown Avenue | 8041.5 | 5873.15 | No issues
C004 | Warehouse D | T203 | Foundation Excavation | John Miller | Blocked | Low | 2024-03-18 | 2024-03-26 |  | 0 | Roofing Sheets | Industrial Park | 9036.38 | 8150.13 | Not started
C002 | Shopping Complex B | T426 | Concrete Pouring | Emma White | Completed | High | 2023-10-07 | 2023-10-23 | 2023-10-23 | 100 | Copper Wires | Market Street | 47911.18 | 81523.77 | No issues
C004 | Warehouse D | T597 | Steel Framework Setup | Grace Allen | In Progress | High | 2024-06-04 | 2024-06-23 |  | 27 | Concrete | Industrial Park | 37234.04 | 40049.63 | In progress
C003 | Office Tower C | T845 | Foundation Excavation | Dave Brown | In Progress | High | 2023-07-28 | 2023-08-09 |  | 14 | Copper Wires | Downtown Avenue | 18553.79 | 17552.79 | In progress
C003 | Office Tower C | T893 | Site Survey | Grace Allen | Blocked | Medium | 2024-09-23 | 2024-10-20 |  | 0 | Rebar | Downtown Avenue | 43374.51 | 33242.28 | Not started
C002 | Shopping Complex B | T525 | Plumbing Installations | Emma White | Not Started | Low | 2023-05-13 | 2023-05-20 |  | 0 | PVC Pipes | Market Street | 23831.66 | 0 | Not started
C004 | Warehouse D | T320 | Electrical Wiring | John Miller | In Progress | High | 2023-11-17 | 2023-12-15 |  | 54 | Cement | Industrial Park | 47455 | 52055.04 | In progress
C002 | Shopping Complex B | T677 | Roofing | Rachel Green | Completed | Low | 2024-10-01 | 2024-10-13 | 2024-10-13 | 100 | Concrete | Market Street | 47404.33 | 70334.77 | No issues
C002 | Shopping Complex B | T586 | Concrete Pouring | Carlos Rivera | Completed | Low | 2024-03-14 | 2024-04-11 | 2024-04-11 | 100 | Steel Beams | Market Street | 13277.73 | 35510.38 | No issues
C004 | Warehouse D | T181 | Roofing | Dave Brown | Completed | Medium | 2024-10-28 | 2024-11-09 | 2024-11-09 | 100 | Cement | Industrial Park | 31505.17 | 27979.05 | No issues
C004 | Warehouse D | T193 | Site Survey | Mike Adams | Completed | Low | 2024-09-07 | 2024-10-03 | 2024-10-03 | 100 | Copper Wires | Industrial Park | 44950.96 | 34842.98 | No issues
C001 | Residential Building A | T517 | Foundation Excavation | Grace Allen | Completed | Low | 2023-07-13 | 2023-07-31 | 2023-07-31 | 100 | Cement | Plot 21, Riverside | 18457.99 | 20487.09 | No issues
C002 | Shopping Complex B | T522 | Roofing | Grace Allen | Blocked | Low | 2023-02-21 | 2023-03-05 |  | 0 | PVC Pipes | Market Street | 40307.61 | 55646.69 | Not started
C004 | Warehouse D | T228 | Plumbing Installations | Carlos Rivera | Blocked | High | 2024-06-14 | 2024-07-08 |  | 0 | Cement | Industrial Park | 18554.24 | 17409.72 | Not started
C004 | Warehouse D | T896 | Roofing | Sarah Johnson | Not Started | High | 2023-02-15 | 2023-02-25 |  | 0 | Roofing Sheets | Industrial Park | 33213.41 | 0 | Not started
C001 | Residential Building A | T220 | Foundation Excavation | John Miller | Not Started | Low | 2024-07-27 | 2024-08-22 |  | 0 | Paint | Plot 21, Riverside | 37577.63 | 0 | Not started
C003 | Office Tower C | T958 | Steel Framework Setup | Sarah Johnson | Blocked | High | 2024-07-16 | 2024-08-07 |  | 0 | Rebar | Downtown Avenue | 29287 | 26669.04 | Not started
C002 | Shopping Complex B | T288 | Foundation Excavation | Grace Allen | Blocked | High | 2024-07-24 | 2024-08-14 |  | 0 | PVC Pipes | Market Street | 10271.66 | 33943.6 | Not started
C001 | Residential Building A | T879 | Steel Framework Setup | Carlos Rivera | Completed | High | 2023-08-13 | 2023-08-27 | 2023-08-27 | 100 | Steel Beams | Plot 21, Riverside | 35113.93 | 35059.82 | No issues
C003 | Office Tower C | T145 | Foundation Excavation | Rachel Green | Not Started | High | 2023-08-28 | 2023-09-25 |  | 0 | PVC Pipes | Downtown Avenue | 7706.36 | 0 | Not started
C004 | Warehouse D | T798 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2024-06-10 | 2024-07-03 |  | 0 | PVC Pipes | Industrial Park | 16685.44 | 0 | Not started
C003 | Office Tower C | T606 | Site Survey | Carlos Rivera | Blocked | Low | 2024-03-28 | 2024-04-19 |  | 0 | PVC Pipes | Downtown Avenue | 10065.99 | 6409.44 | Not started
C004 | Warehouse D | T320 | Interior Painting | Grace Allen | Completed | Medium | 2024-11-09 | 2024-11-29 | 2024-11-29 | 100 | Copper Wires | Industrial Park | 42860.54 | 44316.13 | No issues
C004 | Warehouse D | T508 | Foundation Excavation | Grace Allen | In Progress | High | 2023-11-10 | 2023-11-30 |  | 96 | Cement | Industrial Park | 22091.24 | 13546.89 | In progress
C001 | Residential Building A | T404 | Concrete Pouring | John Miller | Blocked | Low | 2024-07-28 | 2024-08-26 |  | 0 | Concrete | Plot 21, Riverside | 44200.63 | 38242.53 | Not started
C001 | Residential Building A | T347 | Steel Framework Setup | Grace Allen | Blocked | High | 2023-06-23 | 2023-07-13 |  | 0 | Rebar | Plot 21, Riverside | 8218.04 | 5124.33 | Not started
C003 | Office Tower C | T394 | Site Survey | Dave Brown | Not Started | High | 2023-09-04 | 2023-09-12 |  | 0 | Rebar | Downtown Avenue | 28567.66 | 0 | Not started
C001 | Residential Building A | T729 | Foundation Excavation | Grace Allen | Completed | Medium | 2023-01-02 | 2023-01-11 | 2023-01-11 | 100 | Roofing Sheets | Plot 21, Riverside | 5974.91 | 5985.74 | No issues
C002 | Shopping Complex B | T623 | Site Survey | Grace Allen | Completed | High | 2024-07-23 | 2024-08-10 | 2024-08-10 | 100 | Paint | Market Street | 48853.26 | 66892.84 | No issues
C002 | Shopping Complex B | T832 | Interior Painting | Carlos Rivera | Not Started | High | 2024-01-07 | 2024-02-05 |  | 0 | Rebar | Market Street | 5797.85 | 0 | Not started
C003 | Office Tower C | T998 | Interior Painting | Dave Brown | Blocked | High | 2024-07-05 | 2024-07-13 |  | 0 | Roofing Sheets | Downtown Avenue | 41039.88 | 28877.64 | Not started
C003 | Office Tower C | T326 | Electrical Wiring | Rachel Green | Completed | Low | 2024-07-01 | 2024-07-16 | 2024-07-16 | 100 | Rebar | Downtown Avenue | 41563.35 | 48993.57 | No issues
C003 | Office Tower C | T120 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-04-07 | 2023-04-29 |  | 68 | Cement | Downtown Avenue | 34405.27 | 21188.83 | In progress
C003 | Office Tower C | T627 | Steel Framework Setup | John Miller | Not Started | High | 2023-08-09 | 2023-09-03 |  | 0 | Rebar | Downtown Avenue | 8928.6 | 0 | Not started
C004 | Warehouse D | T304 | Steel Framework Setup | Mike Adams | Completed | Medium | 2023-09-14 | 2023-09-27 | 2023-09-27 | 100 | Concrete | Industrial Park | 24529.25 | 19352.87 | No issues
C004 | Warehouse D | T483 | Interior Painting | John Miller | In Progress | Medium | 2024-07-05 | 2024-07-12 |  | 61 | Rebar | Industrial Park | 12426.45 | 14535.83 | In progress
C004 | Warehouse D | T192 | Site Survey | Sarah Johnson | Not Started | Medium | 2024-02-01 | 2024-02-29 |  | 0 | Rebar | Industrial Park | 43855.86 | 0 | Not started
C002 | Shopping Complex B | T256 | Roofing | Dave Brown | Completed | Medium | 2024-12-02 | 2024-12-25 | 2024-12-25 | 100 | Rebar | Market Street | 48407.63 | 67487.98 | No issues
C003 | Office Tower C | T988 | Steel Framework Setup | Dave Brown | In Progress | Low | 2024-03-06 | 2024-03-20 |  | 19 | Concrete | Downtown Avenue | 43343.41 | 50008.16 | In progress
C004 | Warehouse D | T431 | Interior Painting | Dave Brown | Completed | Low | 2023-03-17 | 2023-04-06 | 2023-04-06 | 100 | Copper Wires | Industrial Park | 30560.32 | 31795.27 | No issues
C003 | Office Tower C | T612 | Roofing | Dave Brown | Completed | High | 2024-10-07 | 2024-10-14 | 2024-10-14 | 100 | Concrete | Downtown Avenue | 7485.3 | 6473.62 | No issues
C003 | Office Tower C | T980 | Roofing | John Miller | Blocked | Low | 2024-09-21 | 2024-10-11 |  | 0 | Roofing Sheets | Downtown Avenue | 9365.05 | 8910.63 | Not started
C004 | Warehouse D | T229 | Foundation Excavation | Emma White | Blocked | Medium | 2024-12-14 | 2025-01-09 |  | 0 | Rebar | Industrial Park | 27859.92 | 18213.96 | Not started
C004 | Warehouse D | T512 | Plumbing Installations | Emma White | Blocked | Low | 2024-09-21 | 2024-10-01 |  | 0 | Copper Wires | Industrial Park | 27788.21 | 28854.72 | Not started
C003 | Office Tower C | T793 | Site Survey | Sarah Johnson | In Progress | High | 2023-07-24 | 2023-08-07 |  | 18 | Cement | Downtown Avenue | 19158.46 | 18398.51 | In progress
C004 | Warehouse D | T867 | Plumbing Installations | Emma White | Not Started | Medium | 2023-12-23 | 2024-01-04 |  | 0 | Rebar | Industrial Park | 28286.96 | 0 | Not started
C002 | Shopping Complex B | T371 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-12-23 | 2025-01-15 |  | 0 | Roofing Sheets | Market Street | 5352.08 | 29640.95 | Not started
C002 | Shopping Complex B | T739 | Foundation Excavation | Mike Adams | Not Started | High | 2024-07-17 | 2024-07-25 |  | 0 | Cement | Market Street | 33515.45 | 0 | Not started
C002 | Shopping Complex B | T788 | Plumbing Installations | John Miller | Completed | High | 2023-01-02 | 2023-01-20 | 2023-01-20 | 100 | Paint | Market Street | 48885.76 | 68488.81 | No issues
C002 | Shopping Complex B | T519 | Roofing | Sarah Johnson | Blocked | Medium | 2024-10-07 | 2024-10-23 |  | 0 | Rebar | Market Street | 16162.98 | 40525.33 | Not started
C003 | Office Tower C | T470 | Interior Painting | Carlos Rivera | Blocked | Low | 2023-01-24 | 2023-02-08 |  | 0 | PVC Pipes | Downtown Avenue | 31792.04 | 31658.16 | Not started
C001 | Residential Building A | T956 | Site Survey | John Miller | Completed | High | 2024-07-22 | 2024-08-14 | 2024-08-14 | 100 | Steel Beams | Plot 21, Riverside | 17130.42 | 11557.4 | No issues
C003 | Office Tower C | T339 | Interior Painting | Rachel Green | In Progress | Medium | 2023-08-27 | 2023-09-26 |  | 50 | Rebar | Downtown Avenue | 39504.83 | 35865.07 | In progress
C003 | Office Tower C | T819 | Roofing | Mike Adams | In Progress | Medium | 2024-10-04 | 2024-10-23 |  | 10 | Rebar | Downtown Avenue | 38324.63 | 29617.9 | In progress
C002 | Shopping Complex B | T876 | Interior Painting | Sarah Johnson | Blocked | Low | 2024-07-12 | 2024-08-08 |  | 0 | PVC Pipes | Market Street | 18869.06 | 45463.08 | Not started
C002 | Shopping Complex B | T854 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2024-06-24 | 2024-07-15 |  | 46 | Copper Wires | Market Street | 47327.61 | 67150.09 | In progress
C001 | Residential Building A | T829 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2024-03-28 | 2024-04-08 |  | 0 | Steel Beams | Plot 21, Riverside | 34370.24 | 32637.47 | Not started
C002 | Shopping Complex B | T938 | Electrical Wiring | John Miller | Not Started | Medium | 2024-09-04 | 2024-09-27 |  | 0 | Paint | Market Street | 36433.44 | 0 | Not started
C002 | Shopping Complex B | T731 | Steel Framework Setup | Dave Brown | Blocked | Low | 2023-05-05 | 2023-05-17 |  | 0 | Rebar | Market Street | 19362.84 | 45808.36 | Not started
C002 | Shopping Complex B | T207 | Electrical Wiring | Rachel Green | Completed | High | 2023-07-04 | 2023-07-17 | 2023-07-17 | 100 | PVC Pipes | Market Street | 28060.21 | 47287.99 | No issues
C003 | Office Tower C | T156 | Concrete Pouring | Dave Brown | Not Started | Low | 2024-05-19 | 2024-06-13 |  | 0 | Copper Wires | Downtown Avenue | 39840.51 | 0 | Not started
C003 | Office Tower C | T148 | Roofing | Mike Adams | In Progress | Low | 2023-09-14 | 2023-10-14 |  | 79 | Cement | Downtown Avenue | 36811.81 | 40666.19 | In progress
C001 | Residential Building A | T520 | Foundation Excavation | Emma White | Blocked | Low | 2024-07-17 | 2024-08-09 |  | 0 | Cement | Plot 21, Riverside | 6527.78 | 6557.78 | Not started
C001 | Residential Building A | T526 | Interior Painting | Carlos Rivera | In Progress | Medium | 2023-05-19 | 2023-05-29 |  | 99 | Steel Beams | Plot 21, Riverside | 15098.83 | 15281.68 | In progress
C003 | Office Tower C | T902 | Interior Painting | Grace Allen | Not Started | Medium | 2023-09-17 | 2023-10-16 |  | 0 | Steel Beams | Downtown Avenue | 47690.81 | 0 | Not started
C001 | Residential Building A | T380 | Interior Painting | Carlos Rivera | Completed | High | 2024-04-23 | 2024-05-01 | 2024-05-01 | 100 | PVC Pipes | Plot 21, Riverside | 11562.74 | 9868.02 | No issues
C001 | Residential Building A | T841 | Foundation Excavation | Rachel Green | In Progress | Low | 2024-11-11 | 2024-12-09 |  | 59 | Roofing Sheets | Plot 21, Riverside | 17111.24 | 14029.83 | In progress
C001 | Residential Building A | T534 | Interior Painting | Dave Brown | Blocked | Medium | 2023-02-14 | 2023-03-08 |  | 0 | Paint | Plot 21, Riverside | 30584.88 | 23749.95 | Not started
C003 | Office Tower C | T116 | Electrical Wiring | Grace Allen | In Progress | Low | 2024-12-18 | 2025-01-04 |  | 8 | Roofing Sheets | Downtown Avenue | 31718.72 | 35487.29 | In progress
C004 | Warehouse D | T155 | Concrete Pouring | Carlos Rivera | Not Started | High | 2024-11-21 | 2024-12-09 |  | 0 | Concrete | Industrial Park | 32440.19 | 0 | Not started
C004 | Warehouse D | T388 | Concrete Pouring | Rachel Green | Completed | High | 2024-09-01 | 2024-09-08 | 2024-09-08 | 100 | PVC Pipes | Industrial Park | 16805.04 | 15699.94 | No issues
C003 | Office Tower C | T719 | Foundation Excavation | Carlos Rivera | Blocked | Medium | 2023-05-21 | 2023-06-03 |  | 0 | Paint | Downtown Avenue | 7952.82 | 5076.11 | Not started
C002 | Shopping Complex B | T886 | Foundation Excavation | Sarah Johnson | Completed | High | 2024-02-06 | 2024-02-19 | 2024-02-19 | 100 | Rebar | Market Street | 15262.95 | 36436.75 | No issues
C004 | Warehouse D | T653 | Steel Framework Setup | John Miller | Completed | High | 2023-01-14 | 2023-01-23 | 2023-01-23 | 100 | PVC Pipes | Industrial Park | 18243.61 | 12444.79 | No issues
C004 | Warehouse D | T331 | Electrical Wiring | Mike Adams | Not Started | Medium | 2023-08-14 | 2023-09-01 |  | 0 | Paint | Industrial Park | 48061.45 | 0 | Not started
C001 | Residential Building A | T196 | Steel Framework Setup | Rachel Green | Blocked | Low | 2024-07-02 | 2024-07-15 |  | 0 | Copper Wires | Plot 21, Riverside | 40044.66 | 42516.98 | Not started
C003 | Office Tower C | T337 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2024-09-05 | 2024-10-02 |  | 0 | Cement | Downtown Avenue | 20353.84 | 16205.73 | Not started
C003 | Office Tower C | T966 | Steel Framework Setup | Dave Brown | Blocked | Medium | 2023-11-23 | 2023-12-14 |  | 0 | Rebar | Downtown Avenue | 16695.73 | 17275.53 | Not started
C004 | Warehouse D | T834 | Foundation Excavation | Rachel Green | Blocked | Low | 2024-05-07 | 2024-05-17 |  | 0 | PVC Pipes | Industrial Park | 41750.93 | 43679.91 | Not started
C004 | Warehouse D | T549 | Concrete Pouring | Dave Brown | Blocked | Medium | 2024-08-07 | 2024-08-24 |  | 0 | Steel Beams | Industrial Park | 23464.99 | 19486.09 | Not started
C003 | Office Tower C | T653 | Plumbing Installations | John Miller | Blocked | Medium | 2024-05-11 | 2024-06-01 |  | 0 | Steel Beams | Downtown Avenue | 34890.65 | 33965.82 | Not started
C003 | Office Tower C | T546 | Steel Framework Setup | Rachel Green | Not Started | Low | 2024-05-08 | 2024-05-25 |  | 0 | PVC Pipes | Downtown Avenue | 21045.33 | 0 | Not started
C004 | Warehouse D | T613 | Steel Framework Setup | Dave Brown | In Progress | Medium | 2023-10-07 | 2023-10-19 |  | 37 | Paint | Industrial Park | 21345.93 | 18919.13 | In progress
C002 | Shopping Complex B | T115 | Foundation Excavation | Grace Allen | Completed | Medium | 2023-10-08 | 2023-10-16 | 2023-10-16 | 100 | Concrete | Market Street | 38200.98 | 65399.34 | No issues
C002 | Shopping Complex B | T660 | Roofing | Carlos Rivera | Not Started | Medium | 2023-01-27 | 2023-02-10 |  | 0 | Concrete | Market Street | 20748.58 | 0 | Not started
C004 | Warehouse D | T623 | Foundation Excavation | Mike Adams | Not Started | Low | 2024-11-23 | 2024-12-01 |  | 0 | Steel Beams | Industrial Park | 36125.1 | 0 | Not started
C004 | Warehouse D | T542 | Site Survey | Grace Allen | Not Started | Low | 2024-03-18 | 2024-04-12 |  | 0 | PVC Pipes | Industrial Park | 40767.46 | 0 | Not started
C003 | Office Tower C | T184 | Interior Painting | Carlos Rivera | Completed | Low | 2024-03-07 | 2024-03-23 | 2024-03-23 | 100 | Concrete | Downtown Avenue | 39844.59 | 39380.49 | No issues
C004 | Warehouse D | T418 | Steel Framework Setup | Grace Allen | In Progress | Medium | 2024-03-02 | 2024-03-13 |  | 93 | Paint | Industrial Park | 23255.68 | 17131.3 | In progress
C003 | Office Tower C | T231 | Site Survey | Mike Adams | Not Started | High | 2023-07-12 | 2023-08-08 |  | 0 | Cement | Downtown Avenue | 35563.23 | 0 | Not started
C004 | Warehouse D | T856 | Concrete Pouring | Dave Brown | Blocked | High | 2024-08-25 | 2024-09-18 |  | 0 | Paint | Industrial Park | 28648.19 | 18599.15 | Not started
C002 | Shopping Complex B | T868 | Plumbing Installations | Dave Brown | Blocked | Medium | 2023-04-06 | 2023-04-23 |  | 0 | Roofing Sheets | Market Street | 25473.22 | 54117.24 | Not started
C001 | Residential Building A | T762 | Electrical Wiring | Emma White | Blocked | High | 2023-07-09 | 2023-08-02 |  | 0 | Roofing Sheets | Plot 21, Riverside | 16593.81 | 18279.52 | Not started
C004 | Warehouse D | T545 | Electrical Wiring | John Miller | Blocked | Low | 2023-11-19 | 2023-11-28 |  | 0 | Paint | Industrial Park | 20653.56 | 18204.47 | Not started
C001 | Residential Building A | T824 | Interior Painting | Carlos Rivera | Not Started | Medium | 2024-05-11 | 2024-06-07 |  | 0 | Rebar | Plot 21, Riverside | 38576.33 | 0 | Not started
C001 | Residential Building A | T519 | Foundation Excavation | Rachel Green | Not Started | Low | 2023-03-01 | 2023-03-15 |  | 0 | Copper Wires | Plot 21, Riverside | 7647.24 | 0 | Not started
C004 | Warehouse D | T157 | Site Survey | John Miller | Completed | Medium | 2024-07-02 | 2024-07-12 | 2024-07-12 | 100 | Steel Beams | Industrial Park | 15450.7 | 15347.61 | No issues
C001 | Residential Building A | T215 | Foundation Excavation | Sarah Johnson | In Progress | Low | 2024-08-08 | 2024-09-02 |  | 59 | PVC Pipes | Plot 21, Riverside | 36284.81 | 41534.24 | In progress
C001 | Residential Building A | T112 | Site Survey | Carlos Rivera | Completed | High | 2023-03-05 | 2023-03-31 | 2023-03-31 | 100 | Concrete | Plot 21, Riverside | 9152.3 | 9001.78 | No issues
C001 | Residential Building A | T936 | Interior Painting | Emma White | Completed | Low | 2023-03-22 | 2023-04-19 | 2023-04-19 | 100 | Rebar | Plot 21, Riverside | 10375.27 | 7129.19 | No issues
C001 | Residential Building A | T364 | Plumbing Installations | Rachel Green | Completed | High | 2024-03-22 | 2024-04-07 | 2024-04-07 | 100 | Steel Beams | Plot 21, Riverside | 11558.25 | 7706.37 | No issues
C003 | Office Tower C | T129 | Concrete Pouring | Emma White | Completed | High | 2023-12-27 | 2024-01-10 | 2024-01-10 | 100 | Steel Beams | Downtown Avenue | 21944.94 | 20581.98 | No issues
C004 | Warehouse D | T701 | Interior Painting | Dave Brown | Completed | Medium | 2023-06-13 | 2023-06-27 | 2023-06-27 | 100 | Roofing Sheets | Industrial Park | 43789.78 | 45058.88 | No issues
C001 | Residential Building A | T752 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2024-01-26 | 2024-02-23 |  | 0 | Cement | Plot 21, Riverside | 40305.55 | 34557.27 | Not started
C002 | Shopping Complex B | T917 | Roofing | Rachel Green | Completed | Medium | 2023-05-06 | 2023-06-02 | 2023-06-02 | 100 | Paint | Market Street | 22974.91 | 47438.25 | No issues
C001 | Residential Building A | T135 | Roofing | John Miller | In Progress | Medium | 2023-07-08 | 2023-08-07 |  | 60 | Steel Beams | Plot 21, Riverside | 20694 | 19943.26 | In progress
C001 | Residential Building A | T336 | Roofing | Carlos Rivera | Not Started | High | 2023-07-18 | 2023-08-13 |  | 0 | Roofing Sheets | Plot 21, Riverside | 18377.1 | 0 | Not started
C003 | Office Tower C | T710 | Concrete Pouring | Dave Brown | Not Started | High | 2024-07-12 | 2024-08-11 |  | 0 | Rebar | Downtown Avenue | 35383.21 | 0 | Not started
C002 | Shopping Complex B | T437 | Foundation Excavation | Dave Brown | In Progress | Medium | 2023-08-06 | 2023-08-14 |  | 23 | Cement | Market Street | 18356.11 | 40486.74 | In progress
C004 | Warehouse D | T735 | Electrical Wiring | Mike Adams | Blocked | High | 2024-03-28 | 2024-04-09 |  | 0 | PVC Pipes | Industrial Park | 6723.02 | 4663.12 | Not started
C003 | Office Tower C | T462 | Concrete Pouring | John Miller | Completed | High | 2023-10-14 | 2023-10-27 | 2023-10-27 | 100 | Copper Wires | Downtown Avenue | 14146.52 | 10919.9 | No issues
C001 | Residential Building A | T364 | Foundation Excavation | John Miller | In Progress | Low | 2024-02-25 | 2024-03-26 |  | 84 | Concrete | Plot 21, Riverside | 28416.3 | 19403.62 | In progress
C001 | Residential Building A | T656 | Roofing | Mike Adams | Not Started | High | 2023-03-15 | 2023-04-06 |  | 0 | Roofing Sheets | Plot 21, Riverside | 22585.44 | 0 | Not started
C002 | Shopping Complex B | T734 | Site Survey | John Miller | Not Started | Medium | 2024-03-05 | 2024-03-17 |  | 0 | Paint | Market Street | 26406.27 | 0 | Not started
C001 | Residential Building A | T565 | Interior Painting | Rachel Green | Not Started | Medium | 2024-04-25 | 2024-05-21 |  | 0 | PVC Pipes | Plot 21, Riverside | 15605.11 | 0 | Not started
C001 | Residential Building A | T887 | Site Survey | Mike Adams | Not Started | Low | 2023-12-12 | 2023-12-19 |  | 0 | Paint | Plot 21, Riverside | 12378.62 | 0 | Not started
C004 | Warehouse D | T132 | Electrical Wiring | Carlos Rivera | In Progress | High | 2023-11-21 | 2023-12-13 |  | 47 | Copper Wires | Industrial Park | 28320.92 | 31743.93 | In progress
C003 | Office Tower C | T541 | Site Survey | Emma White | In Progress | High | 2024-11-11 | 2024-11-25 |  | 10 | Cement | Downtown Avenue | 22223.36 | 18081.61 | In progress
C004 | Warehouse D | T268 | Plumbing Installations | John Miller | In Progress | Medium | 2024-01-03 | 2024-01-19 |  | 92 | Rebar | Industrial Park | 10886.06 | 12884.19 | In progress
C004 | Warehouse D | T774 | Site Survey | Dave Brown | Completed | Medium | 2023-01-24 | 2023-02-11 | 2023-02-11 | 100 | Paint | Industrial Park | 18266.59 | 19014.54 | No issues
C004 | Warehouse D | T638 | Site Survey | John Miller | Not Started | Low | 2023-08-02 | 2023-08-17 |  | 0 | Copper Wires | Industrial Park | 8182.92 | 0 | Not started
C001 | Residential Building A | T708 | Foundation Excavation | Grace Allen | Blocked | Low | 2023-04-07 | 2023-05-01 |  | 0 | PVC Pipes | Plot 21, Riverside | 36892.48 | 27397.04 | Not started
C002 | Shopping Complex B | T560 | Electrical Wiring | Mike Adams | In Progress | Medium | 2024-01-05 | 2024-02-03 |  | 13 | Steel Beams | Market Street | 20195.41 | 40291.29 | In progress
C004 | Warehouse D | T938 | Concrete Pouring | Dave Brown | Not Started | Low | 2024-04-10 | 2024-05-08 |  | 0 | Paint | Industrial Park | 18469.86 | 0 | Not started
C002 | Shopping Complex B | T936 | Interior Painting | John Miller | Completed | Low | 2024-08-27 | 2024-09-20 | 2024-09-20 | 100 | Concrete | Market Street | 16556.72 | 39496.94 | No issues
C004 | Warehouse D | T244 | Plumbing Installations | Rachel Green | In Progress | Medium | 2024-12-12 | 2024-12-19 |  | 83 | Paint | Industrial Park | 19481.22 | 15194.49 | In progress
C003 | Office Tower C | T264 | Interior Painting | Carlos Rivera | Not Started | High | 2024-09-17 | 2024-10-14 |  | 0 | Roofing Sheets | Downtown Avenue | 17864.1 | 0 | Not started
C002 | Shopping Complex B | T536 | Concrete Pouring | Grace Allen | Not Started | Low | 2023-11-22 | 2023-12-14 |  | 0 | Roofing Sheets | Market Street | 13748.79 | 0 | Not started
C004 | Warehouse D | T819 | Electrical Wiring | Carlos Rivera | In Progress | Low | 2023-04-17 | 2023-04-29 |  | 5 | Steel Beams | Industrial Park | 45220.82 | 32790.12 | In progress
C002 | Shopping Complex B | T471 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2023-04-08 | 2023-04-15 |  | 0 | Rebar | Market Street | 24080.34 | 0 | Not started
C001 | Residential Building A | T407 | Steel Framework Setup | Rachel Green | Completed | Medium | 2024-05-07 | 2024-06-04 | 2024-06-04 | 100 | Roofing Sheets | Plot 21, Riverside | 6739.06 | 5284.71 | No issues
C002 | Shopping Complex B | T875 | Steel Framework Setup | Rachel Green | In Progress | Medium | 2024-03-17 | 2024-03-29 |  | 35 | Steel Beams | Market Street | 17727.2 | 44596.78 | In progress
C004 | Warehouse D | T967 | Interior Painting | Dave Brown | Not Started | Medium | 2024-08-08 | 2024-08-30 |  | 0 | PVC Pipes | Industrial Park | 7300.67 | 0 | Not started
C002 | Shopping Complex B | T916 | Concrete Pouring | Mike Adams | Not Started | Low | 2023-05-22 | 2023-06-03 |  | 0 | Cement | Market Street | 23459.68 | 0 | Not started
C004 | Warehouse D | T211 | Plumbing Installations | Mike Adams | In Progress | Low | 2023-11-13 | 2023-11-30 |  | 51 | Rebar | Industrial Park | 5523.68 | 3941.63 | In progress
C001 | Residential Building A | T556 | Plumbing Installations | Grace Allen | Blocked | High | 2024-04-22 | 2024-05-07 |  | 0 | Paint | Plot 21, Riverside | 19537.5 | 21432.9 | Not started
C001 | Residential Building A | T202 | Electrical Wiring | John Miller | In Progress | Medium | 2024-03-16 | 2024-04-09 |  | 82 | Concrete | Plot 21, Riverside | 31578.32 | 29548.45 | In progress
C002 | Shopping Complex B | T678 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2024-11-13 | 2024-11-25 |  | 37 | Concrete | Market Street | 22821.49 | 45062.32 | In progress
C001 | Residential Building A | T310 | Steel Framework Setup | Emma White | Not Started | Medium | 2023-01-17 | 2023-02-16 |  | 0 | PVC Pipes | Plot 21, Riverside | 36915.67 | 0 | Not started
C003 | Office Tower C | T748 | Steel Framework Setup | Rachel Green | Not Started | Low | 2023-01-26 | 2023-02-20 |  | 0 | Steel Beams | Downtown Avenue | 10923.53 | 0 | Not started
C003 | Office Tower C | T802 | Interior Painting | Dave Brown | In Progress | Low | 2023-09-07 | 2023-09-19 |  | 42 | Steel Beams | Downtown Avenue | 30833.83 | 30334.37 | In progress
C001 | Residential Building A | T394 | Electrical Wiring | Grace Allen | Blocked | Medium | 2024-07-05 | 2024-08-04 |  | 0 | Cement | Plot 21, Riverside | 14823.03 | 12775.14 | Not started
C003 | Office Tower C | T510 | Interior Painting | Dave Brown | Completed | High | 2024-09-04 | 2024-10-04 | 2024-10-04 | 100 | Roofing Sheets | Downtown Avenue | 34139.37 | 32126.07 | No issues
C004 | Warehouse D | T368 | Site Survey | Sarah Johnson | Not Started | Low | 2023-11-10 | 2023-11-24 |  | 0 | Paint | Industrial Park | 8501.39 | 0 | Not started
C003 | Office Tower C | T412 | Concrete Pouring | Sarah Johnson | Completed | Medium | 2024-07-25 | 2024-08-19 | 2024-08-19 | 100 | Paint | Downtown Avenue | 49811.12 | 36250.28 | No issues
C001 | Residential Building A | T655 | Electrical Wiring | Emma White | In Progress | Low | 2024-05-17 | 2024-06-16 |  | 41 | PVC Pipes | Plot 21, Riverside | 28174.05 | 17848.53 | In progress
C002 | Shopping Complex B | T502 | Foundation Excavation | Grace Allen | Completed | High | 2024-01-06 | 2024-01-21 | 2024-01-21 | 100 | PVC Pipes | Market Street | 6728.34 | 29604.03 | No issues
C003 | Office Tower C | T426 | Concrete Pouring | John Miller | Completed | Medium | 2024-03-16 | 2024-04-10 | 2024-04-10 | 100 | Cement | Downtown Avenue | 33435.78 | 24719.13 | No issues
C003 | Office Tower C | T599 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2023-11-24 | 2023-12-23 |  | 0 | Steel Beams | Downtown Avenue | 10652.2 | 0 | Not started
C001 | Residential Building A | T757 | Electrical Wiring | Mike Adams | In Progress | Low | 2024-12-27 | 2025-01-13 |  | 68 | Copper Wires | Plot 21, Riverside | 27959.19 | 25994.45 | In progress
C001 | Residential Building A | T312 | Foundation Excavation | Grace Allen | Not Started | High | 2023-09-14 | 2023-09-27 |  | 0 | Cement | Plot 21, Riverside | 41371.98 | 0 | Not started
C003 | Office Tower C | T146 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2024-09-14 | 2024-10-08 |  | 0 | Paint | Downtown Avenue | 36433.23 | 22835.88 | Not started
C001 | Residential Building A | T859 | Steel Framework Setup | Dave Brown | Completed | Medium | 2024-02-01 | 2024-02-17 | 2024-02-17 | 100 | Paint | Plot 21, Riverside | 11690.06 | 11895.87 | No issues
C004 | Warehouse D | T776 | Roofing | Grace Allen | Not Started | Medium | 2023-10-04 | 2023-10-23 |  | 0 | Copper Wires | Industrial Park | 45805.1 | 0 | Not started
C003 | Office Tower C | T415 | Plumbing Installations | Emma White | Blocked | Low | 2023-10-21 | 2023-11-10 |  | 0 | Steel Beams | Downtown Avenue | 42065.79 | 34298.42 | Not started
C003 | Office Tower C | T812 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2023-04-26 | 2023-05-16 |  | 0 | Concrete | Downtown Avenue | 9793.07 | 10540.32 | Not started
C002 | Shopping Complex B | T495 | Foundation Excavation | Dave Brown | In Progress | Medium | 2024-05-22 | 2024-06-21 |  | 58 | Steel Beams | Market Street | 36437.28 | 53205.86 | In progress
C004 | Warehouse D | T779 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2024-10-23 | 2024-11-03 |  | 0 | PVC Pipes | Industrial Park | 6610.5 | 7766.48 | Not started
C004 | Warehouse D | T841 | Concrete Pouring | Sarah Johnson | Blocked | Low | 2023-03-16 | 2023-04-10 |  | 0 | Roofing Sheets | Industrial Park | 45967.48 | 49294.6 | Not started
C002 | Shopping Complex B | T420 | Concrete Pouring | Mike Adams | In Progress | High | 2024-10-22 | 2024-11-18 |  | 95 | Roofing Sheets | Market Street | 7249.83 | 30465.56 | In progress
C004 | Warehouse D | T664 | Interior Painting | Dave Brown | Not Started | High | 2024-02-21 | 2024-03-17 |  | 0 | Steel Beams | Industrial Park | 20953.58 | 0 | Not started
C003 | Office Tower C | T185 | Interior Painting | Sarah Johnson | In Progress | High | 2024-07-27 | 2024-08-12 |  | 21 | Cement | Downtown Avenue | 20775.38 | 14767.85 | In progress
C001 | Residential Building A | T533 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-03-17 | 2023-04-11 |  | 0 | PVC Pipes | Plot 21, Riverside | 5911.54 | 5610.96 | Not started
C002 | Shopping Complex B | T201 | Steel Framework Setup | Rachel Green | Not Started | High | 2023-02-14 | 2023-03-07 |  | 0 | PVC Pipes | Market Street | 34503.36 | 0 | Not started
C003 | Office Tower C | T550 | Plumbing Installations | Sarah Johnson | Completed | Low | 2024-10-25 | 2024-11-22 | 2024-11-22 | 100 | PVC Pipes | Downtown Avenue | 13217.83 | 11007.92 | No issues
C004 | Warehouse D | T724 | Interior Painting | Grace Allen | Not Started | Low | 2023-03-19 | 2023-04-05 |  | 0 | Paint | Industrial Park | 14677.88 | 0 | Not started
C003 | Office Tower C | T323 | Roofing | Grace Allen | Not Started | High | 2023-06-17 | 2023-06-25 |  | 0 | Rebar | Downtown Avenue | 15467.73 | 0 | Not started
C003 | Office Tower C | T162 | Steel Framework Setup | Emma White | Blocked | High | 2023-11-07 | 2023-11-23 |  | 0 | Copper Wires | Downtown Avenue | 39750.97 | 24458.98 | Not started
C002 | Shopping Complex B | T516 | Concrete Pouring | Mike Adams | Completed | Medium | 2023-10-05 | 2023-10-15 | 2023-10-15 | 100 | PVC Pipes | Market Street | 28625.44 | 51641.22 | No issues
C002 | Shopping Complex B | T199 | Foundation Excavation | Mike Adams | In Progress | Low | 2024-08-05 | 2024-08-18 |  | 28 | Copper Wires | Market Street | 19957.88 | 42890.31 | In progress
C001 | Residential Building A | T732 | Site Survey | Grace Allen | Completed | Medium | 2023-09-19 | 2023-10-01 | 2023-10-01 | 100 | Steel Beams | Plot 21, Riverside | 30596.25 | 25074.85 | No issues
C002 | Shopping Complex B | T895 | Concrete Pouring | Grace Allen | Completed | Low | 2024-07-07 | 2024-08-06 | 2024-08-06 | 100 | Concrete | Market Street | 44424.44 | 56017.54 | No issues
C002 | Shopping Complex B | T834 | Steel Framework Setup | John Miller | Blocked | High | 2023-11-07 | 2023-11-27 |  | 0 | Rebar | Market Street | 24749.77 | 45021.08 | Not started
C004 | Warehouse D | T835 | Electrical Wiring | Dave Brown | In Progress | High | 2023-11-22 | 2023-12-08 |  | 81 | Cement | Industrial Park | 28629.12 | 33685.16 | In progress
C003 | Office Tower C | T381 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2023-02-28 | 2023-03-07 |  | 75 | Concrete | Downtown Avenue | 22711.58 | 13763.17 | In progress
C001 | Residential Building A | T780 | Interior Painting | Mike Adams | Blocked | Medium | 2023-09-14 | 2023-09-30 |  | 0 | PVC Pipes | Plot 21, Riverside | 20202.79 | 21415.92 | Not started
C001 | Residential Building A | T683 | Site Survey | Sarah Johnson | Not Started | High | 2023-06-03 | 2023-06-26 |  | 0 | Cement | Plot 21, Riverside | 48529.21 | 0 | Not started
C002 | Shopping Complex B | T101 | Foundation Excavation | John Miller | Blocked | Medium | 2024-07-04 | 2024-07-31 |  | 0 | PVC Pipes | Market Street | 38591.99 | 52317.46 | Not started
C003 | Office Tower C | T616 | Steel Framework Setup | John Miller | Completed | Low | 2023-09-28 | 2023-10-09 | 2023-10-09 | 100 | Cement | Downtown Avenue | 32403.22 | 26356.89 | No issues
C003 | Office Tower C | T825 | Roofing | Rachel Green | Completed | High | 2024-04-04 | 2024-04-12 | 2024-04-12 | 100 | Concrete | Downtown Avenue | 33326.94 | 38894.92 | No issues
C002 | Shopping Complex B | T110 | Concrete Pouring | Grace Allen | In Progress | Low | 2023-02-26 | 2023-03-17 |  | 67 | Concrete | Market Street | 31504.67 | 56685.44 | In progress
C002 | Shopping Complex B | T116 | Interior Painting | Carlos Rivera | Blocked | High | 2023-10-09 | 2023-10-20 |  | 0 | Roofing Sheets | Market Street | 26237 | 42849.62 | Not started
C004 | Warehouse D | T149 | Electrical Wiring | Rachel Green | In Progress | Medium | 2023-10-01 | 2023-10-26 |  | 40 | Steel Beams | Industrial Park | 26241.82 | 26258.02 | In progress
C004 | Warehouse D | T752 | Concrete Pouring | Emma White | Not Started | High | 2024-04-06 | 2024-04-25 |  | 0 | Steel Beams | Industrial Park | 40744.98 | 0 | Not started
C003 | Office Tower C | T338 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-02-04 | 2024-03-05 |  | 0 | PVC Pipes | Downtown Avenue | 42826.35 | 27656.88 | Not started
C001 | Residential Building A | T515 | Steel Framework Setup | Emma White | Completed | Medium | 2023-02-16 | 2023-03-06 | 2023-03-06 | 100 | PVC Pipes | Plot 21, Riverside | 17661.96 | 19666.93 | No issues
C001 | Residential Building A | T532 | Interior Painting | Emma White | Completed | High | 2023-05-02 | 2023-05-12 | 2023-05-12 | 100 | Rebar | Plot 21, Riverside | 17633.77 | 13108.79 | No issues
C003 | Office Tower C | T177 | Site Survey | Mike Adams | Blocked | High | 2023-05-18 | 2023-06-11 |  | 0 | PVC Pipes | Downtown Avenue | 13471.18 | 11681.28 | Not started
C004 | Warehouse D | T823 | Plumbing Installations | Grace Allen | Completed | High | 2023-01-19 | 2023-02-01 | 2023-02-01 | 100 | Steel Beams | Industrial Park | 36445.21 | 31795.48 | No issues
C001 | Residential Building A | T280 | Concrete Pouring | Dave Brown | Completed | High | 2024-08-03 | 2024-08-19 | 2024-08-19 | 100 | Steel Beams | Plot 21, Riverside | 42959.94 | 48457.08 | No issues
C004 | Warehouse D | T684 | Plumbing Installations | John Miller | Completed | Medium | 2024-03-20 | 2024-04-06 | 2024-04-06 | 100 | Steel Beams | Industrial Park | 5211.21 | 4939.59 | No issues
C001 | Residential Building A | T849 | Interior Painting | Rachel Green | Completed | Medium | 2024-10-28 | 2024-11-08 | 2024-11-08 | 100 | Concrete | Plot 21, Riverside | 41770.06 | 41226.22 | No issues
C001 | Residential Building A | T738 | Foundation Excavation | John Miller | In Progress | Low | 2024-06-25 | 2024-07-22 |  | 89 | Roofing Sheets | Plot 21, Riverside | 6041.88 | 5111.28 | In progress
C003 | Office Tower C | T271 | Site Survey | Dave Brown | Completed | Medium | 2024-01-25 | 2024-02-01 | 2024-02-01 | 100 | Roofing Sheets | Downtown Avenue | 41127.94 | 31869.19 | No issues
C002 | Shopping Complex B | T681 | Plumbing Installations | John Miller | Not Started | High | 2023-11-12 | 2023-12-04 |  | 0 | Rebar | Market Street | 25560.88 | 0 | Not started
C001 | Residential Building A | T812 | Electrical Wiring | Carlos Rivera | Not Started | Low | 2024-04-28 | 2024-05-25 |  | 0 | Steel Beams | Plot 21, Riverside | 46216.5 | 0 | Not started
C002 | Shopping Complex B | T643 | Roofing | Rachel Green | Not Started | Low | 2024-08-09 | 2024-09-08 |  | 0 | Cement | Market Street | 24138.94 | 0 | Not started
C001 | Residential Building A | T420 | Plumbing Installations | Dave Brown | Not Started | High | 2024-07-17 | 2024-07-25 |  | 0 | Roofing Sheets | Plot 21, Riverside | 45363.89 | 0 | Not started
C003 | Office Tower C | T898 | Site Survey | John Miller | Not Started | Medium | 2024-07-03 | 2024-07-24 |  | 0 | Concrete | Downtown Avenue | 40442.49 | 0 | Not started
C002 | Shopping Complex B | T640 | Steel Framework Setup | Emma White | Not Started | High | 2023-11-19 | 2023-12-17 |  | 0 | Steel Beams | Market Street | 21644.12 | 0 | Not started
C003 | Office Tower C | T334 | Plumbing Installations | Rachel Green | Completed | High | 2024-04-24 | 2024-05-06 | 2024-05-06 | 100 | Roofing Sheets | Downtown Avenue | 42700.98 | 50360.18 | No issues
C001 | Residential Building A | T422 | Electrical Wiring | Mike Adams | Not Started | Low | 2024-01-08 | 2024-02-03 |  | 0 | Concrete | Plot 21, Riverside | 27280.71 | 0 | Not started
C004 | Warehouse D | T940 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-06-04 | 2023-06-13 |  | 0 | Roofing Sheets | Industrial Park | 20120.65 | 0 | Not started
C002 | Shopping Complex B | T240 | Roofing | Sarah Johnson | Blocked | High | 2023-08-03 | 2023-08-27 |  | 0 | Copper Wires | Market Street | 13405.75 | 35483.45 | Not started
C001 | Residential Building A | T643 | Concrete Pouring | Rachel Green | Completed | Low | 2024-07-17 | 2024-08-04 | 2024-08-04 | 100 | Cement | Plot 21, Riverside | 25342.29 | 15935.51 | No issues
C003 | Office Tower C | T232 | Roofing | Mike Adams | Blocked | High | 2024-11-18 | 2024-11-25 |  | 0 | Paint | Downtown Avenue | 20586.5 | 19138.02 | Not started
C003 | Office Tower C | T581 | Concrete Pouring | Mike Adams | Not Started | Low | 2023-08-27 | 2023-09-15 |  | 0 | Concrete | Downtown Avenue | 36310.31 | 0 | Not started
C001 | Residential Building A | T484 | Interior Painting | John Miller | Not Started | Low | 2023-05-12 | 2023-05-29 |  | 0 | Steel Beams | Plot 21, Riverside | 38365.54 | 0 | Not started
C002 | Shopping Complex B | T777 | Foundation Excavation | Mike Adams | Completed | Low | 2023-04-02 | 2023-04-22 | 2023-04-22 | 100 | Rebar | Market Street | 36104.92 | 49081.01 | No issues
C004 | Warehouse D | T739 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2024-05-17 | 2024-06-04 |  | 8 | Concrete | Industrial Park | 13183.43 | 13146.6 | In progress
C001 | Residential Building A | T247 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-06-09 | 2023-06-18 |  | 0 | Concrete | Plot 21, Riverside | 40469.93 | 0 | Not started
C002 | Shopping Complex B | T382 | Roofing | Grace Allen | Completed | High | 2024-02-19 | 2024-03-09 | 2024-03-09 | 100 | Copper Wires | Market Street | 49125.11 | 60414.74 | No issues
C002 | Shopping Complex B | T929 | Roofing | Grace Allen | Blocked | Low | 2023-01-07 | 2023-01-30 |  | 0 | Concrete | Market Street | 13895.6 | 39572.88 | Not started
C002 | Shopping Complex B | T594 | Roofing | Grace Allen | Not Started | Low | 2024-11-19 | 2024-12-16 |  | 0 | Copper Wires | Market Street | 21461.33 | 0 | Not started
C003 | Office Tower C | T742 | Concrete Pouring | Carlos Rivera | Not Started | Medium | 2024-08-14 | 2024-08-26 |  | 0 | PVC Pipes | Downtown Avenue | 39117.53 | 0 | Not started
C003 | Office Tower C | T435 | Interior Painting | Sarah Johnson | Not Started | High | 2023-03-04 | 2023-03-22 |  | 0 | Steel Beams | Downtown Avenue | 14093.52 | 0 | Not started
C002 | Shopping Complex B | T208 | Steel Framework Setup | Dave Brown | In Progress | Low | 2024-05-25 | 2024-06-07 |  | 16 | Roofing Sheets | Market Street | 15394.11 | 42068.65 | In progress
C001 | Residential Building A | T499 | Concrete Pouring | Sarah Johnson | In Progress | High | 2024-06-27 | 2024-07-05 |  | 13 | Concrete | Plot 21, Riverside | 17361.8 | 16248.83 | In progress
C004 | Warehouse D | T109 | Electrical Wiring | Sarah Johnson | Not Started | Low | 2023-04-06 | 2023-04-29 |  | 0 | Cement | Industrial Park | 12112.41 | 0 | Not started
C002 | Shopping Complex B | T396 | Roofing | Sarah Johnson | Not Started | High | 2024-05-11 | 2024-05-25 |  | 0 | Steel Beams | Market Street | 9779.64 | 0 | Not started
C001 | Residential Building A | T318 | Plumbing Installations | Grace Allen | Not Started | Low | 2023-01-09 | 2023-01-29 |  | 0 | Cement | Plot 21, Riverside | 5351.1 | 0 | Not started
C004 | Warehouse D | T280 | Roofing | John Miller | Not Started | High | 2024-08-14 | 2024-09-12 |  | 0 | Rebar | Industrial Park | 42423.73 | 0 | Not started
C003 | Office Tower C | T953 | Site Survey | Rachel Green | Blocked | Medium | 2024-04-19 | 2024-05-03 |  | 0 | Copper Wires | Downtown Avenue | 24525.01 | 21879.59 | Not started
C002 | Shopping Complex B | T479 | Concrete Pouring | Sarah Johnson | Blocked | High | 2023-01-10 | 2023-01-17 |  | 0 | Steel Beams | Market Street | 48177.32 | 82005.58 | Not started
C002 | Shopping Complex B | T428 | Concrete Pouring | Emma White | In Progress | High | 2024-12-22 | 2025-01-09 |  | 6 | Paint | Market Street | 41827.9 | 70659.98 | In progress
C003 | Office Tower C | T635 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-01-22 | 2024-02-13 |  | 0 | Roofing Sheets | Downtown Avenue | 45685.71 | 0 | Not started
C002 | Shopping Complex B | T801 | Roofing | Emma White | Blocked | High | 2024-05-25 | 2024-06-22 |  | 0 | Paint | Market Street | 25846.64 | 49244.52 | Not started
C004 | Warehouse D | T609 | Foundation Excavation | Grace Allen | Completed | Medium | 2023-04-07 | 2023-05-01 | 2023-05-01 | 100 | PVC Pipes | Industrial Park | 29685.46 | 20421.77 | No issues
C003 | Office Tower C | T210 | Roofing | Mike Adams | Blocked | Low | 2024-11-06 | 2024-11-17 |  | 0 | Copper Wires | Downtown Avenue | 40762.93 | 45315.97 | Not started
C002 | Shopping Complex B | T615 | Interior Painting | John Miller | Completed | High | 2024-06-01 | 2024-06-11 | 2024-06-11 | 100 | Roofing Sheets | Market Street | 17722.85 | 40874.32 | No issues
C003 | Office Tower C | T514 | Steel Framework Setup | Mike Adams | Not Started | Medium | 2024-08-10 | 2024-09-08 |  | 0 | Cement | Downtown Avenue | 23279.2 | 0 | Not started
C004 | Warehouse D | T756 | Site Survey | Grace Allen | In Progress | Medium | 2023-01-23 | 2023-02-22 |  | 48 | Roofing Sheets | Industrial Park | 29598.49 | 28297.06 | In progress
C002 | Shopping Complex B | T684 | Interior Painting | Sarah Johnson | In Progress | Low | 2024-06-23 | 2024-07-23 |  | 41 | Paint | Market Street | 37979.53 | 54276.61 | In progress
C004 | Warehouse D | T636 | Plumbing Installations | Rachel Green | Not Started | Low | 2023-03-04 | 2023-03-17 |  | 0 | Roofing Sheets | Industrial Park | 36472.37 | 0 | Not started
C003 | Office Tower C | T429 | Steel Framework Setup | Emma White | Not Started | Medium | 2023-05-04 | 2023-05-17 |  | 0 | Cement | Downtown Avenue | 28567.01 | 0 | Not started
C002 | Shopping Complex B | T153 | Plumbing Installations | Carlos Rivera | Completed | High | 2024-11-12 | 2024-11-30 | 2024-11-30 | 100 | Roofing Sheets | Market Street | 30182.91 | 57119.97 | No issues
C002 | Shopping Complex B | T334 | Site Survey | Rachel Green | Blocked | High | 2023-08-28 | 2023-09-12 |  | 0 | Cement | Market Street | 9203.01 | 34886.37 | Not started
C004 | Warehouse D | T436 | Concrete Pouring | Emma White | Not Started | High | 2024-10-01 | 2024-10-13 |  | 0 | Cement | Industrial Park | 36056.43 | 0 | Not started
C004 | Warehouse D | T616 | Plumbing Installations | Sarah Johnson | Not Started | Medium | 2024-06-13 | 2024-07-13 |  | 0 | Paint | Industrial Park | 23202.07 | 0 | Not started
C004 | Warehouse D | T186 | Electrical Wiring | Mike Adams | Blocked | Medium | 2023-08-19 | 2023-09-01 |  | 0 | Roofing Sheets | Industrial Park | 37419.61 | 27292.74 | Not started
C003 | Office Tower C | T479 | Steel Framework Setup | Emma White | Completed | Medium | 2023-11-07 | 2023-11-27 | 2023-11-27 | 100 | Concrete | Downtown Avenue | 39182.92 | 31000.47 | No issues
C002 | Shopping Complex B | T527 | Plumbing Installations | Dave Brown | Completed | High | 2024-01-04 | 2024-01-14 | 2024-01-14 | 100 | Steel Beams | Market Street | 41232.62 | 51920.91 | No issues
C002 | Shopping Complex B | T169 | Site Survey | Rachel Green | In Progress | Low | 2023-01-22 | 2023-02-18 |  | 10 | Rebar | Market Street | 10212.87 | 35953.01 | In progress
C001 | Residential Building A | T305 | Roofing | Grace Allen | Blocked | High | 2023-09-24 | 2023-10-18 |  | 0 | Rebar | Plot 21, Riverside | 10777.66 | 9719.26 | Not started
C004 | Warehouse D | T493 | Roofing | Emma White | Not Started | High | 2024-07-10 | 2024-07-27 |  | 0 | Rebar | Industrial Park | 41996.32 | 0 | Not started
C001 | Residential Building A | T617 | Interior Painting | Grace Allen | Blocked | Medium | 2023-05-20 | 2023-06-05 |  | 0 | PVC Pipes | Plot 21, Riverside | 44837.22 | 44385.26 | Not started
C002 | Shopping Complex B | T809 | Concrete Pouring | Grace Allen | Blocked | Medium | 2024-10-23 | 2024-10-30 |  | 0 | Concrete | Market Street | 9374.21 | 36166.15 | Not started
C001 | Residential Building A | T964 | Electrical Wiring | Grace Allen | Not Started | Medium | 2024-07-28 | 2024-08-20 |  | 0 | Copper Wires | Plot 21, Riverside | 14734.1 | 0 | Not started
C003 | Office Tower C | T500 | Steel Framework Setup | Sarah Johnson | Completed | High | 2023-06-23 | 2023-07-13 | 2023-07-13 | 100 | Steel Beams | Downtown Avenue | 20836.45 | 16351.79 | No issues
C001 | Residential Building A | T679 | Roofing | Grace Allen | Blocked | High | 2024-08-27 | 2024-09-16 |  | 0 | Cement | Plot 21, Riverside | 10753.88 | 9701.82 | Not started
C002 | Shopping Complex B | T494 | Concrete Pouring | Dave Brown | Not Started | Medium | 2023-02-09 | 2023-02-20 |  | 0 | PVC Pipes | Market Street | 27033.2 | 0 | Not started
C001 | Residential Building A | T805 | Plumbing Installations | Carlos Rivera | Not Started | High | 2024-11-05 | 2024-11-12 |  | 0 | PVC Pipes | Plot 21, Riverside | 48315.57 | 0 | Not started
C003 | Office Tower C | T948 | Foundation Excavation | Emma White | In Progress | High | 2023-08-21 | 2023-09-12 |  | 87 | PVC Pipes | Downtown Avenue | 48440.66 | 42302.95 | In progress
C004 | Warehouse D | T970 | Roofing | Carlos Rivera | Not Started | Medium | 2023-06-11 | 2023-07-09 |  | 0 | Paint | Industrial Park | 30543.84 | 0 | Not started
C002 | Shopping Complex B | T588 | Plumbing Installations | Carlos Rivera | Blocked | High | 2024-04-13 | 2024-05-04 |  | 0 | Cement | Market Street | 24463.11 | 54480.12 | Not started
C003 | Office Tower C | T728 | Concrete Pouring | Rachel Green | Completed | Low | 2024-01-09 | 2024-02-08 | 2024-02-08 | 100 | Cement | Downtown Avenue | 21242.02 | 19168.89 | No issues
C003 | Office Tower C | T930 | Site Survey | Carlos Rivera | In Progress | Low | 2023-02-28 | 2023-03-10 |  | 53 | Rebar | Downtown Avenue | 35727.16 | 31406.63 | In progress
C003 | Office Tower C | T727 | Roofing | Mike Adams | Blocked | Low | 2024-05-04 | 2024-05-27 |  | 0 | Paint | Downtown Avenue | 46253.16 | 34765.58 | Not started
C003 | Office Tower C | T350 | Plumbing Installations | Rachel Green | Completed | Low | 2023-07-10 | 2023-07-17 | 2023-07-17 | 100 | Cement | Downtown Avenue | 41864.56 | 31397.11 | No issues
C003 | Office Tower C | T346 | Concrete Pouring | Rachel Green | In Progress | High | 2023-03-19 | 2023-04-04 |  | 10 | Cement | Downtown Avenue | 7520.55 | 6046.48 | In progress
C002 | Shopping Complex B | T208 | Concrete Pouring | Mike Adams | Blocked | High | 2024-05-15 | 2024-06-08 |  | 0 | Concrete | Market Street | 41552.67 | 51697.02 | Not started
C002 | Shopping Complex B | T415 | Roofing | Emma White | Completed | Medium | 2023-02-09 | 2023-03-07 | 2023-03-07 | 100 | Steel Beams | Market Street | 15598.34 | 36170.25 | No issues
C004 | Warehouse D | T906 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-02-14 | 2024-03-12 | 2024-03-12 | 100 | Roofing Sheets | Industrial Park | 19816.46 | 13830.63 | No issues
C004 | Warehouse D | T946 | Site Survey | John Miller | Completed | Low | 2023-08-14 | 2023-09-02 | 2023-09-02 | 100 | Paint | Industrial Park | 31951.34 | 34292.54 | No issues
C001 | Residential Building A | T856 | Plumbing Installations | John Miller | In Progress | Medium | 2023-11-22 | 2023-12-17 |  | 30 | Cement | Plot 21, Riverside | 7342.33 | 6036.6 | In progress
C003 | Office Tower C | T993 | Steel Framework Setup | John Miller | In Progress | Medium | 2024-12-26 | 2025-01-24 |  | 72 | Steel Beams | Downtown Avenue | 27953.41 | 21434.53 | In progress
C001 | Residential Building A | T961 | Foundation Excavation | Grace Allen | Blocked | High | 2024-09-08 | 2024-09-21 |  | 0 | Concrete | Plot 21, Riverside | 30427.51 | 19604.18 | Not started
C001 | Residential Building A | T751 | Site Survey | Mike Adams | Blocked | Low | 2023-04-05 | 2023-05-02 |  | 0 | Steel Beams | Plot 21, Riverside | 5023.73 | 4741.16 | Not started
C004 | Warehouse D | T953 | Site Survey | Sarah Johnson | Blocked | Low | 2024-05-14 | 2024-06-10 |  | 0 | Paint | Industrial Park | 32030.5 | 24739.28 | Not started
C003 | Office Tower C | T202 | Foundation Excavation | Grace Allen | In Progress | Medium | 2023-05-10 | 2023-05-30 |  | 47 | Steel Beams | Downtown Avenue | 23577.57 | 23494.93 | In progress
C004 | Warehouse D | T829 | Plumbing Installations | Grace Allen | Completed | High | 2024-01-17 | 2024-02-08 | 2024-02-08 | 100 | Roofing Sheets | Industrial Park | 31701.09 | 23954.54 | No issues
C002 | Shopping Complex B | T919 | Site Survey | Emma White | Blocked | High | 2024-07-02 | 2024-07-24 |  | 0 | Paint | Market Street | 46940.14 | 77414.86 | Not started
C004 | Warehouse D | T526 | Interior Painting | Mike Adams | Not Started | High | 2024-12-28 | 2025-01-09 |  | 0 | Roofing Sheets | Industrial Park | 43285.82 | 0 | Not started
C003 | Office Tower C | T436 | Electrical Wiring | Dave Brown | Completed | High | 2024-10-03 | 2024-10-13 | 2024-10-13 | 100 | Steel Beams | Downtown Avenue | 22765.43 | 22383.48 | No issues
C003 | Office Tower C | T405 | Electrical Wiring | Emma White | Completed | Low | 2023-04-06 | 2023-05-06 | 2023-05-06 | 100 | Roofing Sheets | Downtown Avenue | 34984.33 | 28638.9 | No issues
C001 | Residential Building A | T548 | Roofing | Sarah Johnson | Blocked | High | 2024-07-22 | 2024-07-31 |  | 0 | Copper Wires | Plot 21, Riverside | 42158.35 | 32305.25 | Not started
C001 | Residential Building A | T579 | Concrete Pouring | Dave Brown | In Progress | Medium | 2023-11-24 | 2023-12-16 |  | 37 | Copper Wires | Plot 21, Riverside | 24706.85 | 18604.69 | In progress
C003 | Office Tower C | T729 | Roofing | Emma White | Blocked | Medium | 2023-11-06 | 2023-11-22 |  | 0 | Roofing Sheets | Downtown Avenue | 32933.66 | 38562.31 | Not started
C001 | Residential Building A | T775 | Interior Painting | Dave Brown | Not Started | Low | 2024-11-13 | 2024-12-04 |  | 0 | PVC Pipes | Plot 21, Riverside | 25196.49 | 0 | Not started
C001 | Residential Building A | T411 | Interior Painting | Rachel Green | Completed | Low | 2023-09-27 | 2023-10-25 | 2023-10-25 | 100 | Steel Beams | Plot 21, Riverside | 36123.56 | 23457.62 | No issues
C004 | Warehouse D | T813 | Foundation Excavation | Sarah Johnson | Completed | Low | 2023-02-28 | 2023-03-28 | 2023-03-28 | 100 | Roofing Sheets | Industrial Park | 13745.64 | 9271.41 | No issues
C003 | Office Tower C | T205 | Plumbing Installations | Rachel Green | In Progress | Low | 2023-11-17 | 2023-12-04 |  | 26 | Paint | Downtown Avenue | 17223.56 | 13353.4 | In progress
C004 | Warehouse D | T128 | Site Survey | Emma White | Not Started | Low | 2023-03-10 | 2023-04-08 |  | 0 | Steel Beams | Industrial Park | 13561.83 | 0 | Not started
C003 | Office Tower C | T840 | Interior Painting | Rachel Green | In Progress | Medium | 2023-03-13 | 2023-04-02 |  | 86 | Steel Beams | Downtown Avenue | 6883.14 | 7466.49 | In progress
C002 | Shopping Complex B | T647 | Steel Framework Setup | Sarah Johnson | Not Started | Medium | 2023-08-10 | 2023-08-21 |  | 0 | Cement | Market Street | 14459.5 | 0 | Not started
C001 | Residential Building A | T702 | Interior Painting | Mike Adams | Blocked | Medium | 2023-10-19 | 2023-11-08 |  | 0 | Rebar | Plot 21, Riverside | 40791.99 | 35573.69 | Not started
C004 | Warehouse D | T561 | Concrete Pouring | John Miller | Blocked | Medium | 2023-10-11 | 2023-10-21 |  | 0 | Cement | Industrial Park | 34974.51 | 34335.91 | Not started
C004 | Warehouse D | T424 | Interior Painting | Grace Allen | Completed | Low | 2023-07-09 | 2023-07-25 | 2023-07-25 | 100 | Rebar | Industrial Park | 48081.63 | 47616.49 | No issues
C003 | Office Tower C | T527 | Interior Painting | Rachel Green | In Progress | High | 2023-11-24 | 2023-12-11 |  | 41 | Copper Wires | Downtown Avenue | 19413.29 | 18142.15 | In progress
C004 | Warehouse D | T499 | Interior Painting | Rachel Green | In Progress | Medium | 2024-12-22 | 2025-01-14 |  | 6 | Paint | Industrial Park | 45082.91 | 46593.05 | In progress
C003 | Office Tower C | T958 | Roofing | Grace Allen | Blocked | Low | 2023-06-22 | 2023-07-02 |  | 0 | PVC Pipes | Downtown Avenue | 42877.72 | 41324.85 | Not started
C003 | Office Tower C | T388 | Roofing | John Miller | Completed | Medium | 2023-07-11 | 2023-07-18 | 2023-07-18 | 100 | Concrete | Downtown Avenue | 48886.52 | 49899.86 | No issues
C003 | Office Tower C | T481 | Foundation Excavation | Grace Allen | Blocked | High | 2024-08-01 | 2024-08-18 |  | 0 | Copper Wires | Downtown Avenue | 32178.52 | 37199.22 | Not started
C004 | Warehouse D | T864 | Steel Framework Setup | Rachel Green | In Progress | Low | 2024-03-26 | 2024-04-15 |  | 50 | PVC Pipes | Industrial Park | 21992.74 | 22003.54 | In progress
C004 | Warehouse D | T224 | Site Survey | Emma White | Completed | Medium | 2023-09-08 | 2023-09-23 | 2023-09-23 | 100 | Rebar | Industrial Park | 41319.62 | 30083.23 | No issues
C001 | Residential Building A | T360 | Concrete Pouring | John Miller | In Progress | Medium | 2024-06-07 | 2024-06-14 |  | 84 | PVC Pipes | Plot 21, Riverside | 21337.78 | 21080.38 | In progress
C004 | Warehouse D | T376 | Roofing | Emma White | Completed | High | 2024-01-28 | 2024-02-24 | 2024-02-24 | 100 | Steel Beams | Industrial Park | 20518.89 | 24170.59 | No issues
C001 | Residential Building A | T181 | Roofing | John Miller | Completed | Medium | 2023-02-02 | 2023-03-03 | 2023-03-03 | 100 | Copper Wires | Plot 21, Riverside | 32022.25 | 22651.37 | No issues
C003 | Office Tower C | T388 | Electrical Wiring | Sarah Johnson | Not Started | High | 2023-12-16 | 2023-12-29 |  | 0 | Paint | Downtown Avenue | 30872.34 | 0 | Not started
C002 | Shopping Complex B | T807 | Roofing | Sarah Johnson | Blocked | Medium | 2023-03-28 | 2023-04-17 |  | 0 | Cement | Market Street | 49511.05 | 62134.87 | Not started
C002 | Shopping Complex B | T599 | Concrete Pouring | Grace Allen | Completed | High | 2024-03-08 | 2024-03-18 | 2024-03-18 | 100 | Steel Beams | Market Street | 36039.8 | 66218.82 | No issues
C004 | Warehouse D | T857 | Plumbing Installations | Emma White | Not Started | High | 2023-01-12 | 2023-02-08 |  | 0 | Steel Beams | Industrial Park | 34423.33 | 0 | Not started
C001 | Residential Building A | T971 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2023-05-18 | 2023-06-10 | 2023-06-10 | 100 | Rebar | Plot 21, Riverside | 13178.31 | 8632.84 | No issues
C003 | Office Tower C | T440 | Foundation Excavation | Rachel Green | Blocked | High | 2024-09-16 | 2024-10-11 |  | 0 | Steel Beams | Downtown Avenue | 9848.64 | 10696.38 | Not started
C004 | Warehouse D | T223 | Site Survey | Rachel Green | Not Started | Medium | 2024-11-03 | 2024-11-20 |  | 0 | PVC Pipes | Industrial Park | 26709.09 | 0 | Not started
C001 | Residential Building A | T827 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-07-17 | 2024-07-24 |  | 0 | Steel Beams | Plot 21, Riverside | 24092.67 | 27518.93 | Not started
C001 | Residential Building A | T945 | Plumbing Installations | Rachel Green | In Progress | Medium | 2023-04-17 | 2023-04-25 |  | 85 | Cement | Plot 21, Riverside | 22811.97 | 17463.17 | In progress
C003 | Office Tower C | T823 | Interior Painting | Carlos Rivera | Blocked | High | 2024-03-23 | 2024-04-18 |  | 0 | Copper Wires | Downtown Avenue | 31179.77 | 20896.36 | Not started
C003 | Office Tower C | T438 | Interior Painting | Dave Brown | Blocked | Low | 2023-06-16 | 2023-07-15 |  | 0 | Steel Beams | Downtown Avenue | 5207.56 | 3500.11 | Not started
C001 | Residential Building A | T795 | Concrete Pouring | Dave Brown | Blocked | High | 2023-08-08 | 2023-08-28 |  | 0 | Paint | Plot 21, Riverside | 24142.08 | 14521.21 | Not started
C004 | Warehouse D | T913 | Foundation Excavation | John Miller | Blocked | Medium | 2023-01-07 | 2023-01-27 |  | 0 | Roofing Sheets | Industrial Park | 32211.1 | 26564.11 | Not started
C004 | Warehouse D | T649 | Electrical Wiring | Carlos Rivera | Blocked | High | 2023-12-14 | 2023-12-25 |  | 0 | Steel Beams | Industrial Park | 17988.72 | 20727.74 | Not started
C002 | Shopping Complex B | T227 | Concrete Pouring | Grace Allen | Blocked | Low | 2024-07-16 | 2024-07-31 |  | 0 | Paint | Market Street | 23524.1 | 50510.87 | Not started
C003 | Office Tower C | T941 | Plumbing Installations | Grace Allen | Blocked | Low | 2024-05-17 | 2024-06-05 |  | 0 | Steel Beams | Downtown Avenue | 22391.67 | 18095.32 | Not started
C002 | Shopping Complex B | T949 | Roofing | Emma White | Blocked | Low | 2024-12-20 | 2024-12-28 |  | 0 | PVC Pipes | Market Street | 32632.19 | 48720.16 | Not started
C002 | Shopping Complex B | T939 | Roofing | John Miller | Not Started | Low | 2024-01-21 | 2024-02-11 |  | 0 | PVC Pipes | Market Street | 32299.39 | 0 | Not started
C001 | Residential Building A | T280 | Steel Framework Setup | Sarah Johnson | Not Started | Low | 2024-03-08 | 2024-03-20 |  | 0 | PVC Pipes | Plot 21, Riverside | 23711.13 | 0 | Not started
C002 | Shopping Complex B | T893 | Roofing | Grace Allen | Blocked | High | 2023-05-16 | 2023-06-08 |  | 0 | Cement | Market Street | 17034.78 | 43366.94 | Not started
C002 | Shopping Complex B | T787 | Steel Framework Setup | Rachel Green | Completed | Medium | 2023-04-11 | 2023-04-27 | 2023-04-27 | 100 | Rebar | Market Street | 43204.46 | 74928.95 | No issues
C002 | Shopping Complex B | T526 | Roofing | Carlos Rivera | Not Started | Medium | 2023-08-10 | 2023-09-06 |  | 0 | Copper Wires | Market Street | 29309 | 0 | Not started
C002 | Shopping Complex B | T488 | Concrete Pouring | Mike Adams | Completed | Medium | 2023-11-17 | 2023-12-15 | 2023-12-15 | 100 | Rebar | Market Street | 22695.61 | 47982.44 | No issues
C002 | Shopping Complex B | T608 | Foundation Excavation | Emma White | Completed | Medium | 2024-08-24 | 2024-09-17 | 2024-09-17 | 100 | Concrete | Market Street | 6023.58 | 29314.5 | No issues
C003 | Office Tower C | T759 | Plumbing Installations | Emma White | Completed | Medium | 2023-12-17 | 2024-01-07 | 2024-01-07 | 100 | Roofing Sheets | Downtown Avenue | 18289.31 | 13943.52 | No issues
C001 | Residential Building A | T105 | Interior Painting | Dave Brown | In Progress | Low | 2023-09-15 | 2023-10-12 |  | 75 | Copper Wires | Plot 21, Riverside | 27412.36 | 26683.24 | In progress
C001 | Residential Building A | T808 | Concrete Pouring | Grace Allen | Blocked | High | 2024-06-13 | 2024-07-03 |  | 0 | Cement | Plot 21, Riverside | 8296.59 | 5552.14 | Not started
C001 | Residential Building A | T329 | Foundation Excavation | Emma White | Blocked | Medium | 2023-07-03 | 2023-07-15 |  | 0 | Paint | Plot 21, Riverside | 35951.08 | 24300.7 | Not started
C003 | Office Tower C | T795 | Concrete Pouring | Sarah Johnson | Blocked | High | 2023-02-06 | 2023-02-16 |  | 0 | Rebar | Downtown Avenue | 27301.75 | 23958.08 | Not started
C002 | Shopping Complex B | T161 | Concrete Pouring | Carlos Rivera | In Progress | High | 2024-08-15 | 2024-09-07 |  | 20 | Concrete | Market Street | 11453.51 | 32962.52 | In progress
C002 | Shopping Complex B | T552 | Interior Painting | Dave Brown | In Progress | High | 2023-10-20 | 2023-10-31 |  | 35 | Cement | Market Street | 18885.13 | 42870 | In progress
C003 | Office Tower C | T350 | Steel Framework Setup | John Miller | Blocked | High | 2024-07-05 | 2024-07-17 |  | 0 | Paint | Downtown Avenue | 40246.37 | 26084.85 | Not started
C001 | Residential Building A | T607 | Site Survey | Grace Allen | Not Started | Low | 2024-09-18 | 2024-10-07 |  | 0 | Steel Beams | Plot 21, Riverside | 23381.78 | 0 | Not started
C001 | Residential Building A | T746 | Site Survey | Grace Allen | In Progress | High | 2023-09-18 | 2023-10-08 |  | 2 | Roofing Sheets | Plot 21, Riverside | 22769.76 | 16300.28 | In progress
C003 | Office Tower C | T254 | Concrete Pouring | Emma White | In Progress | High | 2024-07-18 | 2024-07-29 |  | 91 | Roofing Sheets | Downtown Avenue | 15592.89 | 11145.33 | In progress
C001 | Residential Building A | T304 | Foundation Excavation | Mike Adams | Not Started | Medium | 2024-08-28 | 2024-09-10 |  | 0 | Steel Beams | Plot 21, Riverside | 29308.41 | 0 | Not started
C003 | Office Tower C | T147 | Electrical Wiring | Rachel Green | Completed | High | 2023-08-02 | 2023-08-20 | 2023-08-20 | 100 | Roofing Sheets | Downtown Avenue | 12992.21 | 9432.95 | No issues
C001 | Residential Building A | T392 | Plumbing Installations | Emma White | Completed | Low | 2024-12-21 | 2025-01-20 | 2025-01-20 | 100 | Cement | Plot 21, Riverside | 8229 | 7346.78 | No issues
C003 | Office Tower C | T287 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-11-24 | 2024-12-15 |  | 40 | Rebar | Downtown Avenue | 36561.19 | 27033.76 | In progress
C004 | Warehouse D | T493 | Interior Painting | Carlos Rivera | Completed | Medium | 2024-06-20 | 2024-07-07 | 2024-07-07 | 100 | Paint | Industrial Park | 14368.61 | 17180.03 | No issues
C001 | Residential Building A | T887 | Site Survey | Mike Adams | In Progress | Medium | 2023-04-14 | 2023-05-05 |  | 49 | Rebar | Plot 21, Riverside | 5281.25 | 6256.05 | In progress
C002 | Shopping Complex B | T272 | Interior Painting | Carlos Rivera | Completed | Low | 2023-12-11 | 2023-12-26 | 2023-12-26 | 100 | Rebar | Market Street | 11016.39 | 35943.58 | No issues
C002 | Shopping Complex B | T275 | Site Survey | Dave Brown | Blocked | Low | 2024-07-06 | 2024-07-20 |  | 0 | PVC Pipes | Market Street | 31566.11 | 48414.66 | Not started
C001 | Residential Building A | T659 | Plumbing Installations | Carlos Rivera | Blocked | Medium | 2023-07-05 | 2023-07-25 |  | 0 | Cement | Plot 21, Riverside | 40567.07 | 42504.96 | Not started
C002 | Shopping Complex B | T943 | Concrete Pouring | Mike Adams | Completed | Low | 2024-12-26 | 2025-01-17 | 2025-01-17 | 100 | Copper Wires | Market Street | 26706.64 | 47750.52 | No issues
C001 | Residential Building A | T251 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2024-07-08 | 2024-07-16 |  | 0 | Copper Wires | Plot 21, Riverside | 18885.42 | 0 | Not started
C003 | Office Tower C | T576 | Steel Framework Setup | John Miller | Not Started | Medium | 2024-12-01 | 2024-12-14 |  | 0 | PVC Pipes | Downtown Avenue | 6240.35 | 0 | Not started
C002 | Shopping Complex B | T895 | Electrical Wiring | Sarah Johnson | Blocked | High | 2024-05-07 | 2024-05-29 |  | 0 | Concrete | Market Street | 49146.27 | 74234.06 | Not started
C001 | Residential Building A | T860 | Steel Framework Setup | Dave Brown | Completed | High | 2023-07-17 | 2023-08-16 | 2023-08-16 | 100 | Rebar | Plot 21, Riverside | 39451.61 | 26518.48 | No issues
C002 | Shopping Complex B | T267 | Interior Painting | Mike Adams | In Progress | High | 2023-11-07 | 2023-12-05 |  | 45 | Copper Wires | Market Street | 24404.9 | 45333.53 | In progress
C004 | Warehouse D | T410 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2023-09-01 | 2023-09-13 | 2023-09-13 | 100 | Paint | Industrial Park | 27322.2 | 27680.43 | No issues
C001 | Residential Building A | T122 | Roofing | Emma White | Completed | High | 2023-09-13 | 2023-09-26 | 2023-09-26 | 100 | Steel Beams | Plot 21, Riverside | 14190.96 | 8666.68 | No issues
C001 | Residential Building A | T489 | Steel Framework Setup | Rachel Green | Completed | Medium | 2023-03-02 | 2023-03-22 | 2023-03-22 | 100 | Roofing Sheets | Plot 21, Riverside | 30641.14 | 28184.36 | No issues
C002 | Shopping Complex B | T694 | Roofing | Carlos Rivera | Blocked | Low | 2024-05-15 | 2024-06-05 |  | 0 | Steel Beams | Market Street | 5489.47 | 32013.59 | Not started
C002 | Shopping Complex B | T472 | Interior Painting | Grace Allen | Not Started | Low | 2024-06-07 | 2024-06-23 |  | 0 | Steel Beams | Market Street | 8537.48 | 0 | Not started
C002 | Shopping Complex B | T822 | Electrical Wiring | Dave Brown | Not Started | Medium | 2023-04-27 | 2023-05-09 |  | 0 | Cement | Market Street | 7066.01 | 0 | Not started
C002 | Shopping Complex B | T894 | Roofing | Carlos Rivera | In Progress | High | 2024-07-28 | 2024-08-18 |  | 77 | Paint | Market Street | 11208.76 | 37205.65 | In progress
C002 | Shopping Complex B | T764 | Foundation Excavation | Emma White | Completed | Medium | 2023-12-05 | 2023-12-23 | 2023-12-23 | 100 | Roofing Sheets | Market Street | 34541.81 | 57516.97 | No issues
C004 | Warehouse D | T200 | Concrete Pouring | Carlos Rivera | Completed | Medium | 2024-01-08 | 2024-01-24 | 2024-01-24 | 100 | Roofing Sheets | Industrial Park | 7738.85 | 5383.18 | No issues
C004 | Warehouse D | T923 | Electrical Wiring | Mike Adams | Blocked | High | 2024-12-11 | 2024-12-22 |  | 0 | Roofing Sheets | Industrial Park | 8942.01 | 5704.88 | Not started
C004 | Warehouse D | T690 | Plumbing Installations | Mike Adams | Not Started | High | 2023-07-17 | 2023-08-01 |  | 0 | Copper Wires | Industrial Park | 9802.5 | 0 | Not started
C002 | Shopping Complex B | T369 | Steel Framework Setup | Grace Allen | In Progress | Low | 2023-08-17 | 2023-08-30 |  | 70 | Concrete | Market Street | 36639.36 | 62731.26 | In progress
C003 | Office Tower C | T253 | Foundation Excavation | Emma White | In Progress | High | 2023-03-06 | 2023-04-03 |  | 91 | Steel Beams | Downtown Avenue | 32488.05 | 24117.12 | In progress
C004 | Warehouse D | T587 | Site Survey | Mike Adams | In Progress | High | 2024-12-19 | 2024-12-28 |  | 12 | Roofing Sheets | Industrial Park | 47465.36 | 38132.2 | In progress
C004 | Warehouse D | T558 | Concrete Pouring | Emma White | Blocked | High | 2023-11-20 | 2023-11-29 |  | 0 | PVC Pipes | Industrial Park | 20436.47 | 19910.63 | Not started
C004 | Warehouse D | T222 | Concrete Pouring | Rachel Green | Blocked | High | 2023-03-18 | 2023-04-01 |  | 0 | Concrete | Industrial Park | 29645.33 | 21133.34 | Not started
C004 | Warehouse D | T609 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2024-02-03 | 2024-02-12 |  | 0 | Concrete | Industrial Park | 35976.36 | 25147.94 | Not started
C003 | Office Tower C | T723 | Roofing | Mike Adams | Not Started | High | 2024-08-06 | 2024-09-05 |  | 0 | Copper Wires | Downtown Avenue | 25609.66 | 0 | Not started
C001 | Residential Building A | T607 | Roofing | Rachel Green | Not Started | High | 2023-01-07 | 2023-01-17 |  | 0 | Rebar | Plot 21, Riverside | 13100.83 | 0 | Not started
C001 | Residential Building A | T417 | Electrical Wiring | Rachel Green | Not Started | Medium | 2024-01-02 | 2024-01-27 |  | 0 | Cement | Plot 21, Riverside | 7727.44 | 0 | Not started
C004 | Warehouse D | T802 | Electrical Wiring | Dave Brown | Completed | Medium | 2023-01-03 | 2023-01-16 | 2023-01-16 | 100 | Concrete | Industrial Park | 21396.82 | 13221.97 | No issues
C003 | Office Tower C | T466 | Plumbing Installations | Dave Brown | Completed | Low | 2024-01-11 | 2024-01-24 | 2024-01-24 | 100 | Rebar | Downtown Avenue | 39999.34 | 44964.54 | No issues
C001 | Residential Building A | T808 | Electrical Wiring | Dave Brown | In Progress | Low | 2024-09-10 | 2024-09-26 |  | 11 | Roofing Sheets | Plot 21, Riverside | 33130.03 | 27017.14 | In progress
C003 | Office Tower C | T768 | Electrical Wiring | Carlos Rivera | Completed | Medium | 2024-02-22 | 2024-03-08 | 2024-03-08 | 100 | PVC Pipes | Downtown Avenue | 15567.68 | 14029.72 | No issues
C001 | Residential Building A | T940 | Roofing | John Miller | Not Started | Low | 2023-04-14 | 2023-05-02 |  | 0 | Concrete | Plot 21, Riverside | 19343.58 | 0 | Not started
C002 | Shopping Complex B | T482 | Steel Framework Setup | Emma White | Not Started | Low | 2024-02-12 | 2024-03-06 |  | 0 | Copper Wires | Market Street | 37120.67 | 0 | Not started
C004 | Warehouse D | T540 | Site Survey | Grace Allen | In Progress | Low | 2023-10-27 | 2023-11-10 |  | 33 | Concrete | Industrial Park | 25790.11 | 20090.27 | In progress
C002 | Shopping Complex B | T170 | Roofing | Grace Allen | Not Started | Low | 2024-01-12 | 2024-01-23 |  | 0 | Cement | Market Street | 20806.85 | 0 | Not started
C002 | Shopping Complex B | T957 | Foundation Excavation | Rachel Green | Completed | Medium | 2023-11-20 | 2023-12-11 | 2023-12-11 | 100 | PVC Pipes | Market Street | 22317.49 | 45307.63 | No issues
C002 | Shopping Complex B | T698 | Interior Painting | Grace Allen | In Progress | Medium | 2024-01-15 | 2024-01-29 |  | 32 | Paint | Market Street | 27904.92 | 46910.28 | In progress
C001 | Residential Building A | T322 | Site Survey | Rachel Green | Not Started | High | 2024-02-01 | 2024-02-22 |  | 0 | Roofing Sheets | Plot 21, Riverside | 8425.87 | 0 | Not started
C004 | Warehouse D | T502 | Foundation Excavation | Sarah Johnson | Blocked | Medium | 2024-10-23 | 2024-11-18 |  | 0 | PVC Pipes | Industrial Park | 31983.59 | 28826.24 | Not started
C004 | Warehouse D | T182 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2023-07-09 | 2023-08-02 |  | 0 | PVC Pipes | Industrial Park | 25130.37 | 0 | Not started
C003 | Office Tower C | T126 | Concrete Pouring | Sarah Johnson | In Progress | Medium | 2024-06-14 | 2024-07-04 |  | 74 | Steel Beams | Downtown Avenue | 32834 | 39122.02 | In progress
C002 | Shopping Complex B | T353 | Site Survey | Grace Allen | Blocked | Low | 2023-11-27 | 2023-12-26 |  | 0 | Concrete | Market Street | 49127.8 | 80816.17 | Not started
C003 | Office Tower C | T416 | Concrete Pouring | Carlos Rivera | In Progress | Medium | 2023-12-08 | 2023-12-19 |  | 52 | PVC Pipes | Downtown Avenue | 20982.08 | 13506.98 | In progress
C003 | Office Tower C | T552 | Steel Framework Setup | John Miller | Not Started | High | 2023-07-14 | 2023-07-27 |  | 0 | Steel Beams | Downtown Avenue | 42824.11 | 0 | Not started
C001 | Residential Building A | T606 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-03-20 | 2024-04-09 |  | 0 | Roofing Sheets | Plot 21, Riverside | 14429.61 | 11848.37 | Not started
C001 | Residential Building A | T317 | Concrete Pouring | John Miller | Not Started | Medium | 2023-08-12 | 2023-08-30 |  | 0 | Cement | Plot 21, Riverside | 35317.59 | 0 | Not started
C003 | Office Tower C | T869 | Site Survey | Dave Brown | Not Started | Low | 2023-05-05 | 2023-05-15 |  | 0 | Concrete | Downtown Avenue | 23780.27 | 0 | Not started
C001 | Residential Building A | T279 | Steel Framework Setup | Grace Allen | In Progress | High | 2023-10-28 | 2023-11-17 |  | 59 | Roofing Sheets | Plot 21, Riverside | 31855.15 | 32982.16 | In progress
C003 | Office Tower C | T509 | Site Survey | Rachel Green | Blocked | Low | 2024-06-04 | 2024-07-04 |  | 0 | Paint | Downtown Avenue | 8587.38 | 7939.25 | Not started
C003 | Office Tower C | T109 | Concrete Pouring | Emma White | Completed | Low | 2024-11-12 | 2024-11-21 | 2024-11-21 | 100 | Copper Wires | Downtown Avenue | 17553.62 | 13354.25 | No issues
C003 | Office Tower C | T574 | Roofing | Emma White | Completed | Medium | 2024-04-20 | 2024-05-02 | 2024-05-02 | 100 | Concrete | Downtown Avenue | 45569.83 | 36319.53 | No issues
C004 | Warehouse D | T798 | Steel Framework Setup | Sarah Johnson | Blocked | Low | 2023-10-24 | 2023-11-04 |  | 0 | Steel Beams | Industrial Park | 10876.48 | 11997.09 | Not started
C004 | Warehouse D | T386 | Foundation Excavation | Grace Allen | Completed | High | 2024-01-20 | 2024-02-04 | 2024-02-04 | 100 | Copper Wires | Industrial Park | 21820.35 | 25157.69 | No issues
C003 | Office Tower C | T388 | Plumbing Installations | Rachel Green | Blocked | Medium | 2023-03-02 | 2023-03-31 |  | 0 | Roofing Sheets | Downtown Avenue | 49566.05 | 39606.19 | Not started
C003 | Office Tower C | T516 | Steel Framework Setup | Emma White | Blocked | High | 2024-04-12 | 2024-05-10 |  | 0 | PVC Pipes | Downtown Avenue | 5068.86 | 4612.17 | Not started
C003 | Office Tower C | T636 | Foundation Excavation | Carlos Rivera | Completed | Low | 2023-12-04 | 2023-12-13 | 2023-12-13 | 100 | Steel Beams | Downtown Avenue | 5835.25 | 6439.49 | No issues
C003 | Office Tower C | T159 | Steel Framework Setup | Grace Allen | Blocked | Low | 2024-11-04 | 2024-12-02 |  | 0 | Paint | Downtown Avenue | 31424.75 | 33795.24 | Not started
C004 | Warehouse D | T419 | Concrete Pouring | Mike Adams | Blocked | Medium | 2024-05-11 | 2024-06-06 |  | 0 | Rebar | Industrial Park | 32095.31 | 33131.56 | Not started
C001 | Residential Building A | T865 | Plumbing Installations | Grace Allen | Blocked | Low | 2024-04-18 | 2024-05-05 |  | 0 | Cement | Plot 21, Riverside | 12654.35 | 11760.1 | Not started
C003 | Office Tower C | T152 | Steel Framework Setup | Mike Adams | Completed | Medium | 2023-04-04 | 2023-04-21 | 2023-04-21 | 100 | PVC Pipes | Downtown Avenue | 42125.83 | 27402.32 | No issues
C003 | Office Tower C | T806 | Site Survey | Dave Brown | Blocked | High | 2024-12-24 | 2025-01-23 |  | 0 | Roofing Sheets | Downtown Avenue | 11983.52 | 11548.62 | Not started
C004 | Warehouse D | T226 | Plumbing Installations | Dave Brown | Completed | High | 2024-12-17 | 2024-12-24 | 2024-12-24 | 100 | Concrete | Industrial Park | 49450.84 | 35699.97 | No issues
C001 | Residential Building A | T404 | Plumbing Installations | Carlos Rivera | Blocked | High | 2024-04-16 | 2024-05-12 |  | 0 | Copper Wires | Plot 21, Riverside | 6990.51 | 6145.3 | Not started
C004 | Warehouse D | T897 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-03-16 | 2024-03-30 |  | 0 | Roofing Sheets | Industrial Park | 43734.75 | 44833.58 | Not started
C004 | Warehouse D | T924 | Roofing | Dave Brown | Not Started | Low | 2023-09-11 | 2023-10-10 |  | 0 | Rebar | Industrial Park | 44589.77 | 0 | Not started
C001 | Residential Building A | T903 | Electrical Wiring | Emma White | Not Started | Low | 2023-07-07 | 2023-08-01 |  | 0 | Cement | Plot 21, Riverside | 44588.53 | 0 | Not started
C003 | Office Tower C | T826 | Interior Painting | Carlos Rivera | Not Started | Medium | 2023-10-24 | 2023-11-11 |  | 0 | Paint | Downtown Avenue | 38739.96 | 0 | Not started
C004 | Warehouse D | T463 | Interior Painting | Rachel Green | Completed | Medium | 2024-07-13 | 2024-07-24 | 2024-07-24 | 100 | Copper Wires | Industrial Park | 13312.1 | 10725.76 | No issues
C002 | Shopping Complex B | T643 | Plumbing Installations | Dave Brown | Blocked | Medium | 2024-09-10 | 2024-10-05 |  | 0 | Roofing Sheets | Market Street | 7572.84 | 30478.55 | Not started
C003 | Office Tower C | T171 | Roofing | Dave Brown | Completed | Low | 2023-03-02 | 2023-03-26 | 2023-03-26 | 100 | Steel Beams | Downtown Avenue | 31950.59 | 35243.54 | No issues
C002 | Shopping Complex B | T390 | Electrical Wiring | Rachel Green | Blocked | Medium | 2023-04-17 | 2023-05-08 |  | 0 | Cement | Market Street | 33451.12 | 50118.41 | Not started
C004 | Warehouse D | T199 | Concrete Pouring | Dave Brown | Completed | Medium | 2023-01-17 | 2023-01-25 | 2023-01-25 | 100 | Concrete | Industrial Park | 40174.79 | 43669 | No issues
C004 | Warehouse D | T323 | Concrete Pouring | Sarah Johnson | Completed | Low | 2024-06-15 | 2024-06-24 | 2024-06-24 | 100 | Concrete | Industrial Park | 5826.38 | 4544.36 | No issues
C004 | Warehouse D | T237 | Site Survey | Emma White | Completed | Low | 2023-04-17 | 2023-05-05 | 2023-05-05 | 100 | Steel Beams | Industrial Park | 38127.79 | 40854.48 | No issues
C003 | Office Tower C | T550 | Concrete Pouring | Grace Allen | Not Started | Medium | 2023-08-13 | 2023-08-26 |  | 0 | Concrete | Downtown Avenue | 47075.56 | 0 | Not started
C003 | Office Tower C | T745 | Plumbing Installations | Rachel Green | In Progress | Medium | 2023-04-04 | 2023-04-13 |  | 62 | Roofing Sheets | Downtown Avenue | 19415.91 | 20024.52 | In progress
C004 | Warehouse D | T556 | Electrical Wiring | Carlos Rivera | Completed | High | 2024-12-16 | 2024-12-29 | 2024-12-29 | 100 | Roofing Sheets | Industrial Park | 27663.02 | 29650.22 | No issues
C004 | Warehouse D | T452 | Foundation Excavation | Sarah Johnson | Not Started | Medium | 2024-05-07 | 2024-05-27 |  | 0 | Rebar | Industrial Park | 19794.59 | 0 | Not started
C003 | Office Tower C | T976 | Concrete Pouring | Dave Brown | Completed | High | 2023-02-05 | 2023-02-16 | 2023-02-16 | 100 | Roofing Sheets | Downtown Avenue | 33888.01 | 31464.51 | No issues
C001 | Residential Building A | T140 | Electrical Wiring | Grace Allen | Not Started | High | 2023-10-20 | 2023-11-06 |  | 0 | Concrete | Plot 21, Riverside | 39538.16 | 0 | Not started
C001 | Residential Building A | T224 | Steel Framework Setup | John Miller | In Progress | Medium | 2024-09-16 | 2024-10-07 |  | 48 | Rebar | Plot 21, Riverside | 16464.29 | 19270.51 | In progress
C004 | Warehouse D | T993 | Steel Framework Setup | Emma White | Blocked | Low | 2024-07-08 | 2024-07-31 |  | 0 | Steel Beams | Industrial Park | 18170.45 | 21204.95 | Not started
C001 | Residential Building A | T178 | Steel Framework Setup | Mike Adams | Completed | Medium | 2024-05-24 | 2024-06-23 | 2024-06-23 | 100 | Rebar | Plot 21, Riverside | 41767.08 | 41674.85 | No issues
C004 | Warehouse D | T647 | Plumbing Installations | John Miller | In Progress | High | 2023-12-04 | 2023-12-12 |  | 44 | Paint | Industrial Park | 29992.3 | 27274.05 | In progress
C002 | Shopping Complex B | T584 | Steel Framework Setup | Emma White | Blocked | High | 2023-08-02 | 2023-08-28 |  | 0 | Copper Wires | Market Street | 39793.26 | 49761.95 | Not started
C001 | Residential Building A | T490 | Foundation Excavation | Emma White | Not Started | Low | 2024-12-15 | 2025-01-12 |  | 0 | Steel Beams | Plot 21, Riverside | 36648.5 | 0 | Not started
C002 | Shopping Complex B | T528 | Site Survey | Carlos Rivera | Blocked | High | 2023-02-26 | 2023-03-21 |  | 0 | Steel Beams | Market Street | 6128.39 | 32216.35 | Not started
C004 | Warehouse D | T954 | Steel Framework Setup | Mike Adams | Blocked | Medium | 2024-12-19 | 2025-01-17 |  | 0 | Roofing Sheets | Industrial Park | 18437.79 | 16478.91 | Not started
C001 | Residential Building A | T443 | Interior Painting | Emma White | In Progress | High | 2023-01-05 | 2023-02-03 |  | 76 | Copper Wires | Plot 21, Riverside | 28818.33 | 18985.35 | In progress
C002 | Shopping Complex B | T615 | Concrete Pouring | John Miller | Blocked | High | 2024-11-07 | 2024-11-20 |  | 0 | Steel Beams | Market Street | 45069.09 | 78892.22 | Not started
C002 | Shopping Complex B | T510 | Plumbing Installations | Mike Adams | Blocked | Medium | 2023-05-21 | 2023-06-09 |  | 0 | Paint | Market Street | 22624.71 | 46820.65 | Not started
C001 | Residential Building A | T319 | Electrical Wiring | Rachel Green | Completed | Medium | 2024-07-02 | 2024-07-13 | 2024-07-13 | 100 | Concrete | Plot 21, Riverside | 15225.79 | 15659.31 | No issues
C003 | Office Tower C | T793 | Roofing | Emma White | In Progress | High | 2024-02-04 | 2024-02-29 |  | 91 | PVC Pipes | Downtown Avenue | 21446.16 | 13096.4 | In progress
C004 | Warehouse D | T487 | Site Survey | Emma White | In Progress | Low | 2023-04-10 | 2023-04-29 |  | 26 | Roofing Sheets | Industrial Park | 35473.3 | 38849.93 | In progress
C004 | Warehouse D | T235 | Interior Painting | Mike Adams | In Progress | Low | 2023-08-22 | 2023-09-16 |  | 52 | Rebar | Industrial Park | 11284.2 | 8439.8 | In progress
C002 | Shopping Complex B | T974 | Concrete Pouring | Rachel Green | Not Started | Medium | 2023-12-07 | 2023-12-20 |  | 0 | Cement | Market Street | 44698.43 | 0 | Not started
C002 | Shopping Complex B | T616 | Roofing | Grace Allen | In Progress | High | 2023-06-20 | 2023-07-06 |  | 68 | Concrete | Market Street | 21312.12 | 38898.45 | In progress
C002 | Shopping Complex B | T438 | Roofing | Mike Adams | In Progress | High | 2024-05-10 | 2024-06-02 |  | 78 | Paint | Market Street | 5356.91 | 31765.15 | In progress
C001 | Residential Building A | T938 | Electrical Wiring | Mike Adams | In Progress | Medium | 2023-09-13 | 2023-10-01 |  | 89 | Copper Wires | Plot 21, Riverside | 6641.69 | 5113.49 | In progress
C004 | Warehouse D | T287 | Foundation Excavation | Rachel Green | In Progress | High | 2024-07-19 | 2024-07-26 |  | 48 | Concrete | Industrial Park | 44337.99 | 31466.41 | In progress
C001 | Residential Building A | T512 | Electrical Wiring | Carlos Rivera | Blocked | Medium | 2023-07-15 | 2023-07-23 |  | 0 | Rebar | Plot 21, Riverside | 40263.61 | 46793.62 | Not started
C001 | Residential Building A | T891 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2024-01-06 | 2024-01-15 |  | 0 | Rebar | Plot 21, Riverside | 14933.61 | 0 | Not started
C003 | Office Tower C | T772 | Plumbing Installations | Grace Allen | In Progress | Medium | 2024-08-20 | 2024-09-19 |  | 65 | Steel Beams | Downtown Avenue | 16408.98 | 10447.66 | In progress
C003 | Office Tower C | T608 | Electrical Wiring | Carlos Rivera | Blocked | High | 2024-10-09 | 2024-11-08 |  | 0 | Roofing Sheets | Downtown Avenue | 18150.47 | 17721.56 | Not started
C003 | Office Tower C | T343 | Roofing | Grace Allen | Completed | High | 2023-03-15 | 2023-03-24 | 2023-03-24 | 100 | Steel Beams | Downtown Avenue | 37971.61 | 41880.82 | No issues
C004 | Warehouse D | T537 | Roofing | Carlos Rivera | Blocked | Medium | 2023-02-09 | 2023-02-20 |  | 0 | Rebar | Industrial Park | 45110.37 | 34523.64 | Not started
C003 | Office Tower C | T931 | Foundation Excavation | Dave Brown | Completed | High | 2023-08-07 | 2023-08-21 | 2023-08-21 | 100 | Rebar | Downtown Avenue | 20469.12 | 19745.15 | No issues
C001 | Residential Building A | T482 | Foundation Excavation | Dave Brown | Blocked | High | 2024-03-09 | 2024-03-27 |  | 0 | Cement | Plot 21, Riverside | 42038.51 | 46350.02 | Not started
C004 | Warehouse D | T225 | Concrete Pouring | Grace Allen | Completed | Low | 2023-12-11 | 2023-12-26 | 2023-12-26 | 100 | Rebar | Industrial Park | 15734.31 | 17310.47 | No issues
C001 | Residential Building A | T971 | Site Survey | Carlos Rivera | Blocked | Low | 2024-02-03 | 2024-03-04 |  | 0 | Paint | Plot 21, Riverside | 19232.44 | 17002.17 | Not started
C002 | Shopping Complex B | T974 | Site Survey | Mike Adams | In Progress | High | 2024-04-18 | 2024-05-06 |  | 3 | Paint | Market Street | 33523 | 53912.19 | In progress
C003 | Office Tower C | T229 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-07-14 | 2024-07-31 |  | 0 | Cement | Downtown Avenue | 14148.51 | 13695.61 | Not started
C004 | Warehouse D | T136 | Roofing | Carlos Rivera | Not Started | High | 2023-03-23 | 2023-04-11 |  | 0 | Copper Wires | Industrial Park | 7804.37 | 0 | Not started
C003 | Office Tower C | T789 | Concrete Pouring | Mike Adams | Completed | High | 2024-07-11 | 2024-08-08 | 2024-08-08 | 100 | Copper Wires | Downtown Avenue | 16799.92 | 14101.94 | No issues
C001 | Residential Building A | T629 | Plumbing Installations | Sarah Johnson | Blocked | Low | 2024-09-17 | 2024-09-25 |  | 0 | Cement | Plot 21, Riverside | 9133.9 | 6027.26 | Not started
C004 | Warehouse D | T769 | Foundation Excavation | John Miller | Not Started | High | 2024-04-23 | 2024-05-22 |  | 0 | PVC Pipes | Industrial Park | 20992.85 | 0 | Not started
C003 | Office Tower C | T231 | Foundation Excavation | John Miller | Blocked | Low | 2024-02-17 | 2024-03-08 |  | 0 | Steel Beams | Downtown Avenue | 49041.18 | 29710.41 | Not started
C001 | Residential Building A | T644 | Interior Painting | Carlos Rivera | Not Started | High | 2024-09-12 | 2024-09-27 |  | 0 | PVC Pipes | Plot 21, Riverside | 41522.64 | 0 | Not started
C001 | Residential Building A | T238 | Interior Painting | Emma White | Blocked | Medium | 2024-10-21 | 2024-11-09 |  | 0 | Paint | Plot 21, Riverside | 16933.58 | 15702.07 | Not started
C001 | Residential Building A | T304 | Electrical Wiring | John Miller | Completed | Low | 2024-02-15 | 2024-03-11 | 2024-03-11 | 100 | Concrete | Plot 21, Riverside | 10326.72 | 9955.64 | No issues
C004 | Warehouse D | T497 | Plumbing Installations | Dave Brown | Not Started | High | 2023-06-26 | 2023-07-12 |  | 0 | Paint | Industrial Park | 10249.76 | 0 | Not started
C001 | Residential Building A | T534 | Roofing | Carlos Rivera | Completed | High | 2023-07-06 | 2023-07-20 | 2023-07-20 | 100 | Copper Wires | Plot 21, Riverside | 11081.3 | 10678.01 | No issues
C004 | Warehouse D | T100 | Roofing | Emma White | Not Started | Low | 2024-07-19 | 2024-08-01 |  | 0 | Concrete | Industrial Park | 9171.01 | 0 | Not started
C003 | Office Tower C | T309 | Steel Framework Setup | Grace Allen | Blocked | High | 2024-03-06 | 2024-04-03 |  | 0 | Paint | Downtown Avenue | 38623.42 | 23908.19 | Not started
C002 | Shopping Complex B | T139 | Plumbing Installations | Sarah Johnson | Blocked | High | 2024-11-17 | 2024-12-09 |  | 0 | Cement | Market Street | 22269.25 | 39414.72 | Not started
C002 | Shopping Complex B | T342 | Site Survey | John Miller | Completed | High | 2023-07-27 | 2023-08-15 | 2023-08-15 | 100 | Roofing Sheets | Market Street | 16275.75 | 43821.59 | No issues
C003 | Office Tower C | T268 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-12-19 | 2024-12-31 |  | 0 | Paint | Downtown Avenue | 20048.96 | 17546.15 | Not started
C004 | Warehouse D | T349 | Foundation Excavation | Rachel Green | Blocked | Low | 2024-05-21 | 2024-06-05 |  | 0 | Copper Wires | Industrial Park | 40101.4 | 46880.85 | Not started
C004 | Warehouse D | T613 | Concrete Pouring | John Miller | Completed | High | 2023-12-19 | 2024-01-16 | 2024-01-16 | 100 | Roofing Sheets | Industrial Park | 23681.48 | 20595 | No issues
C001 | Residential Building A | T483 | Concrete Pouring | Emma White | Blocked | Low | 2024-04-15 | 2024-05-08 |  | 0 | Paint | Plot 21, Riverside | 10306.76 | 8615.01 | Not started
C004 | Warehouse D | T720 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2023-10-02 | 2023-10-19 |  | 0 | Concrete | Industrial Park | 8224.7 | 7593.76 | Not started
C004 | Warehouse D | T278 | Electrical Wiring | Emma White | Completed | Low | 2023-08-16 | 2023-09-10 | 2023-09-10 | 100 | Concrete | Industrial Park | 41834.23 | 30140.9 | No issues
C004 | Warehouse D | T284 | Foundation Excavation | Carlos Rivera | In Progress | Low | 2023-03-02 | 2023-03-26 |  | 14 | Concrete | Industrial Park | 36833.72 | 28674.22 | In progress
C002 | Shopping Complex B | T543 | Electrical Wiring | Dave Brown | Not Started | Low | 2024-09-21 | 2024-10-03 |  | 0 | Roofing Sheets | Market Street | 10852.37 | 0 | Not started
C003 | Office Tower C | T371 | Foundation Excavation | Rachel Green | In Progress | Medium | 2024-12-04 | 2024-12-16 |  | 14 | Cement | Downtown Avenue | 17133.52 | 13121.64 | In progress
C002 | Shopping Complex B | T379 | Site Survey | Grace Allen | In Progress | High | 2023-10-18 | 2023-11-07 |  | 5 | Copper Wires | Market Street | 40240.23 | 70446.61 | In progress
C002 | Shopping Complex B | T257 | Interior Painting | Carlos Rivera | Not Started | Low | 2023-04-01 | 2023-04-23 |  | 0 | Concrete | Market Street | 32547.81 | 0 | Not started
C001 | Residential Building A | T169 | Interior Painting | John Miller | Completed | High | 2023-05-26 | 2023-06-04 | 2023-06-04 | 100 | Concrete | Plot 21, Riverside | 16125.57 | 19064.2 | No issues
C004 | Warehouse D | T864 | Site Survey | John Miller | Blocked | Medium | 2023-09-06 | 2023-09-19 |  | 0 | Cement | Industrial Park | 47250.81 | 30384.19 | Not started
C003 | Office Tower C | T854 | Site Survey | Mike Adams | Completed | Low | 2024-06-03 | 2024-06-19 | 2024-06-19 | 100 | Roofing Sheets | Downtown Avenue | 23341.7 | 19810.34 | No issues
C004 | Warehouse D | T139 | Electrical Wiring | Rachel Green | In Progress | Medium | 2024-12-27 | 2025-01-19 |  | 79 | Roofing Sheets | Industrial Park | 17668.81 | 14652.44 | In progress
C002 | Shopping Complex B | T511 | Electrical Wiring | John Miller | Not Started | Medium | 2024-11-17 | 2024-12-03 |  | 0 | Steel Beams | Market Street | 30331.33 | 0 | Not started
C001 | Residential Building A | T805 | Electrical Wiring | Rachel Green | Blocked | Medium | 2023-12-25 | 2024-01-22 |  | 0 | Cement | Plot 21, Riverside | 16558.05 | 16904.5 | Not started
C002 | Shopping Complex B | T269 | Electrical Wiring | Emma White | In Progress | High | 2024-07-12 | 2024-08-05 |  | 13 | Paint | Market Street | 46057.22 | 56622.17 | In progress
C001 | Residential Building A | T254 | Roofing | John Miller | Completed | Medium | 2024-09-18 | 2024-09-30 | 2024-09-30 | 100 | PVC Pipes | Plot 21, Riverside | 19490.56 | 12624.66 | No issues
C002 | Shopping Complex B | T400 | Foundation Excavation | Mike Adams | Completed | High | 2024-01-17 | 2024-02-15 | 2024-02-15 | 100 | Roofing Sheets | Market Street | 18102.13 | 40705.98 | No issues
C003 | Office Tower C | T691 | Electrical Wiring | Emma White | In Progress | High | 2023-01-11 | 2023-01-30 |  | 54 | Paint | Downtown Avenue | 27990.26 | 17565.91 | In progress
C003 | Office Tower C | T645 | Interior Painting | Emma White | In Progress | Medium | 2024-06-26 | 2024-07-08 |  | 86 | Cement | Downtown Avenue | 42468.65 | 42050.29 | In progress
C002 | Shopping Complex B | T870 | Steel Framework Setup | Grace Allen | Blocked | High | 2023-02-02 | 2023-02-26 |  | 0 | Roofing Sheets | Market Street | 17110.72 | 40106.65 | Not started
C002 | Shopping Complex B | T208 | Interior Painting | Dave Brown | In Progress | Medium | 2023-07-26 | 2023-08-21 |  | 12 | PVC Pipes | Market Street | 33912.46 | 63606.62 | In progress
C002 | Shopping Complex B | T212 | Roofing | Carlos Rivera | In Progress | High | 2024-12-11 | 2025-01-08 |  | 41 | Rebar | Market Street | 36886.46 | 48628.38 | In progress
C001 | Residential Building A | T394 | Plumbing Installations | Rachel Green | In Progress | High | 2024-02-26 | 2024-03-26 |  | 94 | Cement | Plot 21, Riverside | 47439.18 | 30324.24 | In progress
C002 | Shopping Complex B | T826 | Interior Painting | Mike Adams | In Progress | High | 2023-06-23 | 2023-07-13 |  | 58 | Copper Wires | Market Street | 8823.05 | 31528.81 | In progress
C002 | Shopping Complex B | T781 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-08-06 | 2024-08-30 |  | 43 | Copper Wires | Market Street | 49774.85 | 59993.06 | In progress
C004 | Warehouse D | T576 | Electrical Wiring | Emma White | Blocked | Low | 2023-12-27 | 2024-01-16 |  | 0 | Roofing Sheets | Industrial Park | 34930.39 | 41539.1 | Not started
C004 | Warehouse D | T866 | Site Survey | Grace Allen | Blocked | Medium | 2024-07-25 | 2024-08-10 |  | 0 | Cement | Industrial Park | 24734.71 | 29074.16 | Not started
C002 | Shopping Complex B | T548 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2023-12-08 | 2023-12-28 |  | 0 | Concrete | Market Street | 22499.81 | 0 | Not started
C004 | Warehouse D | T314 | Steel Framework Setup | Emma White | Not Started | Low | 2024-11-15 | 2024-12-11 |  | 0 | Roofing Sheets | Industrial Park | 41667.75 | 0 | Not started
C001 | Residential Building A | T566 | Plumbing Installations | Rachel Green | Blocked | High | 2023-11-28 | 2023-12-27 |  | 0 | Concrete | Plot 21, Riverside | 28286.18 | 25933.44 | Not started
C004 | Warehouse D | T703 | Electrical Wiring | Mike Adams | In Progress | Low | 2023-05-08 | 2023-05-22 |  | 10 | Rebar | Industrial Park | 42671.79 | 33284.17 | In progress
C003 | Office Tower C | T534 | Concrete Pouring | Rachel Green | Blocked | Medium | 2023-03-18 | 2023-04-06 |  | 0 | Cement | Downtown Avenue | 23302.01 | 14010.33 | Not started
C004 | Warehouse D | T682 | Interior Painting | Rachel Green | Blocked | Medium | 2024-03-14 | 2024-04-11 |  | 0 | Copper Wires | Industrial Park | 38501.85 | 39180.67 | Not started
C003 | Office Tower C | T737 | Interior Painting | Carlos Rivera | Blocked | Medium | 2024-10-18 | 2024-11-17 |  | 0 | Paint | Downtown Avenue | 29879.05 | 29142.32 | Not started
C002 | Shopping Complex B | T185 | Site Survey | Sarah Johnson | Blocked | Medium | 2024-01-19 | 2024-01-31 |  | 0 | Concrete | Market Street | 17956.23 | 42908.12 | Not started
C002 | Shopping Complex B | T537 | Concrete Pouring | Rachel Green | In Progress | Low | 2024-11-22 | 2024-12-09 |  | 76 | Steel Beams | Market Street | 35323.83 | 53486.94 | In progress
C003 | Office Tower C | T428 | Concrete Pouring | Emma White | Not Started | High | 2023-01-10 | 2023-01-20 |  | 0 | Paint | Downtown Avenue | 18896.49 | 0 | Not started
C003 | Office Tower C | T859 | Electrical Wiring | Sarah Johnson | In Progress | Medium | 2023-03-18 | 2023-04-08 |  | 39 | Paint | Downtown Avenue | 13868.02 | 16224.9 | In progress
C004 | Warehouse D | T272 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2024-06-26 | 2024-07-13 |  | 0 | Cement | Industrial Park | 14366.35 | 0 | Not started
C003 | Office Tower C | T149 | Concrete Pouring | Emma White | In Progress | Low | 2024-08-25 | 2024-09-10 |  | 34 | Rebar | Downtown Avenue | 42611.47 | 50472.07 | In progress
C001 | Residential Building A | T685 | Foundation Excavation | Emma White | Completed | High | 2023-06-04 | 2023-06-16 | 2023-06-16 | 100 | Paint | Plot 21, Riverside | 16609.22 | 16411.57 | No issues
C001 | Residential Building A | T941 | Concrete Pouring | Sarah Johnson | In Progress | Low | 2023-04-10 | 2023-05-07 |  | 7 | Concrete | Plot 21, Riverside | 14668.1 | 12890.8 | In progress
C003 | Office Tower C | T953 | Roofing | John Miller | In Progress | Medium | 2024-09-26 | 2024-10-26 |  | 70 | PVC Pipes | Downtown Avenue | 49626.03 | 41562.79 | In progress
C003 | Office Tower C | T275 | Plumbing Installations | Emma White | Completed | Low | 2023-01-20 | 2023-01-28 | 2023-01-28 | 100 | PVC Pipes | Downtown Avenue | 32770.19 | 37344.37 | No issues
C003 | Office Tower C | T362 | Steel Framework Setup | John Miller | Not Started | High | 2023-03-10 | 2023-03-25 |  | 0 | Steel Beams | Downtown Avenue | 47105.46 | 0 | Not started
C002 | Shopping Complex B | T141 | Concrete Pouring | Emma White | In Progress | Medium | 2023-03-26 | 2023-04-13 |  | 51 | Paint | Market Street | 7490.63 | 31218.8 | In progress
C002 | Shopping Complex B | T575 | Plumbing Installations | Rachel Green | Not Started | Low | 2023-10-07 | 2023-10-30 |  | 0 | Rebar | Market Street | 37609.35 | 0 | Not started
C004 | Warehouse D | T939 | Site Survey | Sarah Johnson | Blocked | High | 2023-04-02 | 2023-05-01 |  | 0 | Copper Wires | Industrial Park | 43618.76 | 42749.33 | Not started
C002 | Shopping Complex B | T856 | Roofing | Carlos Rivera | Not Started | Medium | 2024-01-18 | 2024-01-30 |  | 0 | Copper Wires | Market Street | 34400.55 | 0 | Not started
C001 | Residential Building A | T100 | Plumbing Installations | John Miller | Not Started | Medium | 2024-04-11 | 2024-04-22 |  | 0 | Roofing Sheets | Plot 21, Riverside | 17837.54 | 0 | Not started
C002 | Shopping Complex B | T182 | Concrete Pouring | Rachel Green | Not Started | Low | 2023-08-06 | 2023-08-29 |  | 0 | PVC Pipes | Market Street | 34570.53 | 0 | Not started
C003 | Office Tower C | T115 | Roofing | Dave Brown | In Progress | High | 2024-03-20 | 2024-04-19 |  | 8 | Concrete | Downtown Avenue | 33322.65 | 23003.29 | In progress
C002 | Shopping Complex B | T860 | Foundation Excavation | Carlos Rivera | Blocked | High | 2023-03-22 | 2023-04-13 |  | 0 | Paint | Market Street | 21646.13 | 41266.9 | Not started
C004 | Warehouse D | T342 | Site Survey | Carlos Rivera | Blocked | Low | 2024-12-07 | 2025-01-03 |  | 0 | Roofing Sheets | Industrial Park | 20376.81 | 17313.14 | Not started
C002 | Shopping Complex B | T185 | Site Survey | Sarah Johnson | In Progress | Medium | 2024-07-18 | 2024-08-07 |  | 10 | Roofing Sheets | Market Street | 7258.08 | 34194.12 | In progress
C003 | Office Tower C | T130 | Interior Painting | John Miller | Completed | High | 2024-06-27 | 2024-07-04 | 2024-07-04 | 100 | Cement | Downtown Avenue | 36529.3 | 42853.35 | No issues
C001 | Residential Building A | T980 | Foundation Excavation | Emma White | Blocked | Medium | 2024-04-07 | 2024-05-04 |  | 0 | Steel Beams | Plot 21, Riverside | 13763.25 | 11281.36 | Not started
C001 | Residential Building A | T960 | Foundation Excavation | Rachel Green | Completed | High | 2024-04-09 | 2024-05-02 | 2024-05-02 | 100 | Paint | Plot 21, Riverside | 37448.18 | 25099.86 | No issues
C002 | Shopping Complex B | T611 | Concrete Pouring | John Miller | Not Started | High | 2024-10-01 | 2024-10-20 |  | 0 | Concrete | Market Street | 5304.42 | 0 | Not started
C004 | Warehouse D | T318 | Concrete Pouring | Dave Brown | In Progress | Medium | 2023-08-07 | 2023-08-26 |  | 90 | Cement | Industrial Park | 29186.08 | 31963.29 | In progress
C004 | Warehouse D | T580 | Interior Painting | Grace Allen | Blocked | High | 2023-10-10 | 2023-10-23 |  | 0 | Roofing Sheets | Industrial Park | 6970.7 | 4809.32 | Not started
C004 | Warehouse D | T494 | Electrical Wiring | Emma White | In Progress | High | 2024-02-05 | 2024-02-17 |  | 17 | Roofing Sheets | Industrial Park | 23029.86 | 26837.97 | In progress
C004 | Warehouse D | T783 | Site Survey | John Miller | Not Started | Medium | 2023-03-28 | 2023-04-12 |  | 0 | Paint | Industrial Park | 36967.94 | 0 | Not started
C002 | Shopping Complex B | T552 | Steel Framework Setup | Rachel Green | In Progress | Low | 2024-11-04 | 2024-11-14 |  | 3 | Paint | Market Street | 38155.77 | 54446.72 | In progress
C002 | Shopping Complex B | T856 | Steel Framework Setup | Grace Allen | Completed | Low | 2024-05-05 | 2024-05-24 | 2024-05-24 | 100 | Concrete | Market Street | 36221.19 | 64878.37 | No issues
C001 | Residential Building A | T391 | Site Survey | Dave Brown | In Progress | High | 2023-05-14 | 2023-05-31 |  | 85 | Rebar | Plot 21, Riverside | 25056.92 | 28759.1 | In progress
C004 | Warehouse D | T246 | Steel Framework Setup | Mike Adams | In Progress | High | 2023-11-24 | 2023-12-18 |  | 22 | Steel Beams | Industrial Park | 48562.37 | 40069.04 | In progress
C003 | Office Tower C | T849 | Concrete Pouring | Grace Allen | In Progress | Low | 2024-10-11 | 2024-11-04 |  | 4 | Cement | Downtown Avenue | 18752.3 | 14827.53 | In progress
C002 | Shopping Complex B | T704 | Plumbing Installations | Dave Brown | In Progress | Medium | 2023-06-07 | 2023-07-04 |  | 77 | Paint | Market Street | 26427.18 | 50004.17 | In progress
C003 | Office Tower C | T674 | Foundation Excavation | Mike Adams | Blocked | Low | 2024-04-06 | 2024-04-29 |  | 0 | Roofing Sheets | Downtown Avenue | 5647.15 | 5149.97 | Not started
C003 | Office Tower C | T965 | Electrical Wiring | John Miller | In Progress | High | 2024-01-11 | 2024-01-22 |  | 22 | Rebar | Downtown Avenue | 11260.04 | 13361.84 | In progress
C002 | Shopping Complex B | T522 | Steel Framework Setup | Sarah Johnson | Blocked | High | 2023-07-15 | 2023-07-23 |  | 0 | Steel Beams | Market Street | 36733.9 | 57365.34 | Not started
C003 | Office Tower C | T595 | Foundation Excavation | John Miller | Not Started | Low | 2024-05-23 | 2024-06-20 |  | 0 | Roofing Sheets | Downtown Avenue | 35581.18 | 0 | Not started
C004 | Warehouse D | T988 | Concrete Pouring | Mike Adams | Blocked | High | 2023-11-09 | 2023-11-23 |  | 0 | Copper Wires | Industrial Park | 24883.93 | 18133.42 | Not started
C002 | Shopping Complex B | T652 | Steel Framework Setup | Grace Allen | Blocked | Medium | 2023-02-22 | 2023-03-06 |  | 0 | Concrete | Market Street | 30456.95 | 45776.44 | Not started
C003 | Office Tower C | T669 | Electrical Wiring | Mike Adams | In Progress | Medium | 2024-09-20 | 2024-10-14 |  | 11 | PVC Pipes | Downtown Avenue | 7466.56 | 6167.62 | In progress
C002 | Shopping Complex B | T395 | Electrical Wiring | Rachel Green | In Progress | Medium | 2024-09-23 | 2024-10-20 |  | 28 | Paint | Market Street | 27550.05 | 56246.24 | In progress
C004 | Warehouse D | T921 | Steel Framework Setup | Rachel Green | Completed | High | 2024-11-04 | 2024-11-19 | 2024-11-19 | 100 | Paint | Industrial Park | 19423.58 | 12222.11 | No issues
C002 | Shopping Complex B | T619 | Foundation Excavation | Grace Allen | Blocked | Medium | 2023-04-02 | 2023-04-10 |  | 0 | Steel Beams | Market Street | 42748.8 | 64736.47 | Not started
C003 | Office Tower C | T850 | Roofing | Rachel Green | Completed | Low | 2024-11-28 | 2024-12-07 | 2024-12-07 | 100 | Concrete | Downtown Avenue | 11482.55 | 11424.84 | No issues
C004 | Warehouse D | T557 | Concrete Pouring | Emma White | Blocked | Medium | 2024-02-18 | 2024-03-11 |  | 0 | Concrete | Industrial Park | 31570.17 | 37105.57 | Not started
C001 | Residential Building A | T158 | Plumbing Installations | Sarah Johnson | Completed | Medium | 2024-04-24 | 2024-05-09 | 2024-05-09 | 100 | Paint | Plot 21, Riverside | 9484.35 | 8440.64 | No issues
C001 | Residential Building A | T383 | Steel Framework Setup | Sarah Johnson | In Progress | Low | 2023-04-01 | 2023-04-16 |  | 61 | Concrete | Plot 21, Riverside | 28837.74 | 25451.74 | In progress
C003 | Office Tower C | T627 | Electrical Wiring | Emma White | In Progress | Low | 2024-01-25 | 2024-02-11 |  | 30 | Paint | Downtown Avenue | 34752.74 | 25297.86 | In progress
C001 | Residential Building A | T652 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-11-03 | 2023-11-17 |  | 0 | Rebar | Plot 21, Riverside | 7012.01 | 0 | Not started
C003 | Office Tower C | T907 | Foundation Excavation | Emma White | Not Started | Medium | 2023-05-10 | 2023-06-08 |  | 0 | Steel Beams | Downtown Avenue | 18578.56 | 0 | Not started
C004 | Warehouse D | T890 | Electrical Wiring | Mike Adams | Blocked | High | 2023-11-03 | 2023-11-30 |  | 0 | Paint | Industrial Park | 34393.5 | 39430.97 | Not started
C002 | Shopping Complex B | T792 | Site Survey | John Miller | In Progress | High | 2024-04-15 | 2024-05-15 |  | 29 | Rebar | Market Street | 39684.95 | 70801.91 | In progress
C001 | Residential Building A | T536 | Roofing | Carlos Rivera | In Progress | High | 2023-08-25 | 2023-09-09 |  | 88 | Concrete | Plot 21, Riverside | 42961.99 | 43529.66 | In progress
C004 | Warehouse D | T247 | Roofing | Grace Allen | In Progress | Low | 2023-01-26 | 2023-02-25 |  | 40 | Steel Beams | Industrial Park | 9960.48 | 6169.5 | In progress
C004 | Warehouse D | T880 | Roofing | Emma White | In Progress | High | 2023-04-10 | 2023-05-01 |  | 53 | PVC Pipes | Industrial Park | 24196.01 | 28037.9 | In progress
C004 | Warehouse D | T152 | Steel Framework Setup | Sarah Johnson | Blocked | High | 2023-09-10 | 2023-10-02 |  | 0 | Copper Wires | Industrial Park | 33591.94 | 22301.01 | Not started
C001 | Residential Building A | T196 | Roofing | Sarah Johnson | In Progress | Medium | 2023-07-19 | 2023-08-18 |  | 55 | Rebar | Plot 21, Riverside | 23353.61 | 16514.51 | In progress
C001 | Residential Building A | T308 | Steel Framework Setup | Mike Adams | In Progress | Medium | 2023-09-07 | 2023-10-04 |  | 52 | Cement | Plot 21, Riverside | 5313.54 | 5130.64 | In progress
C004 | Warehouse D | T245 | Concrete Pouring | Mike Adams | Completed | Medium | 2024-11-23 | 2024-12-16 | 2024-12-16 | 100 | Steel Beams | Industrial Park | 6498.97 | 4975.73 | No issues
C002 | Shopping Complex B | T871 | Concrete Pouring | Carlos Rivera | In Progress | Low | 2024-05-10 | 2024-05-23 |  | 32 | PVC Pipes | Market Street | 17807.51 | 43773.97 | In progress
C001 | Residential Building A | T382 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2023-09-21 | 2023-10-06 |  | 0 | PVC Pipes | Plot 21, Riverside | 40605.89 | 46043.27 | Not started
C001 | Residential Building A | T236 | Concrete Pouring | Sarah Johnson | Completed | Low | 2023-08-24 | 2023-09-19 | 2023-09-19 | 100 | Copper Wires | Plot 21, Riverside | 23134.3 | 18563.66 | No issues
C001 | Residential Building A | T397 | Roofing | Carlos Rivera | Blocked | Medium | 2024-03-23 | 2024-04-20 |  | 0 | Copper Wires | Plot 21, Riverside | 6117.15 | 6514.74 | Not started
C002 | Shopping Complex B | T504 | Foundation Excavation | Mike Adams | Blocked | High | 2024-08-11 | 2024-08-25 |  | 0 | Steel Beams | Market Street | 39366.4 | 54569.17 | Not started
C001 | Residential Building A | T350 | Roofing | Carlos Rivera | Not Started | Medium | 2024-11-20 | 2024-12-11 |  | 0 | PVC Pipes | Plot 21, Riverside | 24783.78 | 0 | Not started
C001 | Residential Building A | T239 | Interior Painting | Sarah Johnson | Completed | High | 2023-01-02 | 2023-01-14 | 2023-01-14 | 100 | Rebar | Plot 21, Riverside | 34396.79 | 23931.73 | No issues
C003 | Office Tower C | T719 | Steel Framework Setup | Grace Allen | Blocked | Low | 2023-01-28 | 2023-02-20 |  | 0 | Steel Beams | Downtown Avenue | 49272.77 | 58349.81 | Not started
C002 | Shopping Complex B | T844 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2023-02-09 | 2023-02-22 |  | 0 | Rebar | Market Street | 33044.99 | 51688.88 | In progress
C001 | Residential Building A | T594 | Electrical Wiring | Dave Brown | Blocked | Low | 2024-01-07 | 2024-02-04 |  | 0 | PVC Pipes | Plot 21, Riverside | 11089.44 | 11581.9 | Not started
C003 | Office Tower C | T888 | Site Survey | John Miller | In Progress | High | 2023-04-13 | 2023-05-03 |  | 30 | PVC Pipes | Downtown Avenue | 43805.58 | 45470.37 | In progress
C002 | Shopping Complex B | T367 | Site Survey | Emma White | Not Started | Low | 2023-07-11 | 2023-07-28 |  | 0 | Paint | Market Street | 35420.9 | 0 | Not started
C003 | Office Tower C | T729 | Roofing | Carlos Rivera | Not Started | High | 2023-09-18 | 2023-10-01 |  | 0 | Cement | Downtown Avenue | 5340.5 | 0 | Not started
C003 | Office Tower C | T830 | Plumbing Installations | Rachel Green | In Progress | Low | 2024-05-16 | 2024-06-04 |  | 11 | Concrete | Downtown Avenue | 29780.88 | 20734.15 | In progress
C001 | Residential Building A | T590 | Steel Framework Setup | John Miller | Blocked | Low | 2023-11-17 | 2023-12-01 |  | 0 | PVC Pipes | Plot 21, Riverside | 12578.57 | 14204.37 | Not started
C004 | Warehouse D | T733 | Concrete Pouring | Rachel Green | Blocked | Medium | 2024-11-26 | 2024-12-20 |  | 0 | Rebar | Industrial Park | 7770.48 | 7597.15 | Not started
C002 | Shopping Complex B | T547 | Interior Painting | Grace Allen | In Progress | High | 2024-12-25 | 2025-01-12 |  | 87 | Copper Wires | Market Street | 19935.19 | 45842.35 | In progress
C003 | Office Tower C | T236 | Interior Painting | Dave Brown | Not Started | Medium | 2023-09-08 | 2023-10-01 |  | 0 | Copper Wires | Downtown Avenue | 25770.89 | 0 | Not started
C003 | Office Tower C | T491 | Plumbing Installations | Rachel Green | Completed | High | 2023-12-01 | 2023-12-18 | 2023-12-18 | 100 | Roofing Sheets | Downtown Avenue | 7397.44 | 4974.09 | No issues
C004 | Warehouse D | T226 | Steel Framework Setup | Emma White | Blocked | Low | 2024-07-26 | 2024-08-16 |  | 0 | Concrete | Industrial Park | 31858.08 | 36762.82 | Not started
C003 | Office Tower C | T417 | Site Survey | Sarah Johnson | Blocked | High | 2023-03-09 | 2023-04-03 |  | 0 | Cement | Downtown Avenue | 13070.31 | 10146.21 | Not started
C003 | Office Tower C | T852 | Steel Framework Setup | Dave Brown | Not Started | Medium | 2024-03-12 | 2024-04-08 |  | 0 | Paint | Downtown Avenue | 41563.62 | 0 | Not started
C004 | Warehouse D | T323 | Concrete Pouring | John Miller | Not Started | Low | 2023-08-01 | 2023-08-10 |  | 0 | Copper Wires | Industrial Park | 5615.33 | 0 | Not started
C004 | Warehouse D | T520 | Steel Framework Setup | Rachel Green | Blocked | Medium | 2024-01-23 | 2024-02-03 |  | 0 | Paint | Industrial Park | 17708.99 | 18446.37 | Not started
C002 | Shopping Complex B | T648 | Foundation Excavation | Dave Brown | Blocked | Medium | 2024-11-11 | 2024-12-10 |  | 0 | Rebar | Market Street | 29491.69 | 60061.68 | Not started
C004 | Warehouse D | T823 | Site Survey | Mike Adams | In Progress | Low | 2023-11-11 | 2023-12-11 |  | 44 | Paint | Industrial Park | 31723.55 | 30716.61 | In progress
C004 | Warehouse D | T805 | Concrete Pouring | Dave Brown | Blocked | Medium | 2024-04-01 | 2024-04-23 |  | 0 | Steel Beams | Industrial Park | 41713.49 | 32623.37 | Not started
C003 | Office Tower C | T174 | Electrical Wiring | Mike Adams | In Progress | High | 2024-03-16 | 2024-04-15 |  | 51 | Roofing Sheets | Downtown Avenue | 49017.68 | 36568.55 | In progress
C004 | Warehouse D | T515 | Concrete Pouring | Grace Allen | In Progress | Low | 2024-07-01 | 2024-07-31 |  | 46 | Paint | Industrial Park | 35292.07 | 37174.65 | In progress
C003 | Office Tower C | T505 | Site Survey | Sarah Johnson | Completed | Medium | 2023-07-04 | 2023-08-02 | 2023-08-02 | 100 | Paint | Downtown Avenue | 30008.88 | 35351.13 | No issues
C001 | Residential Building A | T687 | Concrete Pouring | John Miller | Completed | Low | 2023-08-10 | 2023-08-27 | 2023-08-27 | 100 | Steel Beams | Plot 21, Riverside | 33384.81 | 28574.02 | No issues
C001 | Residential Building A | T190 | Concrete Pouring | Emma White | Blocked | Medium | 2024-10-11 | 2024-10-28 |  | 0 | Copper Wires | Plot 21, Riverside | 24340.07 | 28298.08 | Not started
C003 | Office Tower C | T253 | Concrete Pouring | Grace Allen | Completed | Low | 2023-12-09 | 2023-12-26 | 2023-12-26 | 100 | Rebar | Downtown Avenue | 22146.33 | 19197.82 | No issues
C004 | Warehouse D | T890 | Site Survey | Sarah Johnson | Completed | Medium | 2023-01-01 | 2023-01-09 | 2023-01-09 | 100 | Paint | Industrial Park | 44915.02 | 36545.14 | No issues
C002 | Shopping Complex B | T474 | Interior Painting | Sarah Johnson | Blocked | High | 2024-08-10 | 2024-08-25 |  | 0 | Paint | Market Street | 15410.41 | 35233.9 | Not started
C004 | Warehouse D | T878 | Plumbing Installations | Grace Allen | In Progress | Low | 2024-05-27 | 2024-06-06 |  | 67 | Steel Beams | Industrial Park | 27890.57 | 26343.08 | In progress
C001 | Residential Building A | T949 | Foundation Excavation | Emma White | In Progress | Low | 2024-09-04 | 2024-09-29 |  | 75 | Steel Beams | Plot 21, Riverside | 23945.74 | 28592.32 | In progress
C002 | Shopping Complex B | T664 | Roofing | Emma White | Completed | Low | 2023-02-13 | 2023-03-05 | 2023-03-05 | 100 | Cement | Market Street | 25872.11 | 48725.12 | No issues
C004 | Warehouse D | T765 | Foundation Excavation | Grace Allen | Blocked | Low | 2024-05-09 | 2024-05-29 |  | 0 | PVC Pipes | Industrial Park | 16051.46 | 18948.58 | Not started
C003 | Office Tower C | T685 | Steel Framework Setup | Emma White | Completed | Low | 2023-01-17 | 2023-02-07 | 2023-02-07 | 100 | Roofing Sheets | Downtown Avenue | 24818.79 | 15967.64 | No issues
C002 | Shopping Complex B | T865 | Plumbing Installations | Rachel Green | In Progress | High | 2024-05-23 | 2024-06-09 |  | 56 | Concrete | Market Street | 29883.04 | 46448.69 | In progress
C001 | Residential Building A | T489 | Electrical Wiring | Emma White | Completed | Low | 2023-10-27 | 2023-11-22 | 2023-11-22 | 100 | Cement | Plot 21, Riverside | 16222.53 | 17469.62 | No issues
C001 | Residential Building A | T413 | Roofing | Emma White | Not Started | Low | 2023-03-09 | 2023-04-08 |  | 0 | Roofing Sheets | Plot 21, Riverside | 17055.19 | 0 | Not started
C001 | Residential Building A | T973 | Concrete Pouring | Rachel Green | Completed | Medium | 2023-01-04 | 2023-01-18 | 2023-01-18 | 100 | Steel Beams | Plot 21, Riverside | 7062.55 | 6028.51 | No issues
C004 | Warehouse D | T917 | Foundation Excavation | Mike Adams | Completed | Medium | 2024-04-22 | 2024-05-15 | 2024-05-15 | 100 | Paint | Industrial Park | 13109.29 | 14400.33 | No issues
C004 | Warehouse D | T915 | Electrical Wiring | Rachel Green | In Progress | Medium | 2024-11-26 | 2024-12-23 |  | 27 | Rebar | Industrial Park | 21469.57 | 22312.79 | In progress
C002 | Shopping Complex B | T391 | Plumbing Installations | Emma White | Not Started | High | 2024-07-20 | 2024-08-07 |  | 0 | Rebar | Market Street | 9181.08 | 0 | Not started
C002 | Shopping Complex B | T788 | Site Survey | Rachel Green | In Progress | High | 2023-08-20 | 2023-09-16 |  | 35 | PVC Pipes | Market Street | 8247.42 | 31378.47 | In progress
C003 | Office Tower C | T243 | Roofing | Rachel Green | Completed | Medium | 2024-11-24 | 2024-12-17 | 2024-12-17 | 100 | PVC Pipes | Downtown Avenue | 16815.91 | 15012.71 | No issues
C004 | Warehouse D | T744 | Steel Framework Setup | Emma White | Completed | High | 2023-09-04 | 2023-10-01 | 2023-10-01 | 100 | Cement | Industrial Park | 48971.1 | 51207.33 | No issues
C001 | Residential Building A | T244 | Electrical Wiring | Mike Adams | Not Started | Medium | 2024-06-14 | 2024-06-25 |  | 0 | Concrete | Plot 21, Riverside | 35648.61 | 0 | Not started
C003 | Office Tower C | T770 | Foundation Excavation | Rachel Green | In Progress | High | 2024-07-20 | 2024-07-30 |  | 93 | Roofing Sheets | Downtown Avenue | 19815.83 | 12825.44 | In progress
C002 | Shopping Complex B | T187 | Site Survey | Carlos Rivera | In Progress | Low | 2024-07-10 | 2024-07-24 |  | 25 | Rebar | Market Street | 12642.71 | 37976.29 | In progress
C001 | Residential Building A | T435 | Roofing | Grace Allen | Not Started | Medium | 2024-07-27 | 2024-08-03 |  | 0 | Roofing Sheets | Plot 21, Riverside | 15025.34 | 0 | Not started
C001 | Residential Building A | T104 | Electrical Wiring | Mike Adams | Blocked | Medium | 2024-07-04 | 2024-07-22 |  | 0 | Concrete | Plot 21, Riverside | 13550.61 | 14019.29 | Not started
C002 | Shopping Complex B | T968 | Concrete Pouring | Rachel Green | Not Started | High | 2024-04-18 | 2024-05-12 |  | 0 | Cement | Market Street | 21768.7 | 0 | Not started
C004 | Warehouse D | T172 | Plumbing Installations | Carlos Rivera | In Progress | Low | 2024-06-09 | 2024-07-04 |  | 66 | Roofing Sheets | Industrial Park | 9221.23 | 6533.66 | In progress
C003 | Office Tower C | T416 | Electrical Wiring | Rachel Green | Not Started | Low | 2023-08-04 | 2023-08-18 |  | 0 | Cement | Downtown Avenue | 46276.86 | 0 | Not started
C004 | Warehouse D | T279 | Steel Framework Setup | Emma White | Not Started | High | 2024-12-20 | 2025-01-13 |  | 0 | Rebar | Industrial Park | 26134.57 | 0 | Not started
C004 | Warehouse D | T414 | Steel Framework Setup | John Miller | Blocked | High | 2023-06-26 | 2023-07-06 |  | 0 | Copper Wires | Industrial Park | 32045.81 | 23300.86 | Not started
C004 | Warehouse D | T195 | Site Survey | Dave Brown | In Progress | High | 2024-01-03 | 2024-01-19 |  | 16 | Cement | Industrial Park | 11344.27 | 7111.51 | In progress
C004 | Warehouse D | T582 | Steel Framework Setup | Emma White | Blocked | Low | 2024-02-18 | 2024-03-05 |  | 0 | Concrete | Industrial Park | 24127.73 | 25119.91 | Not started
C004 | Warehouse D | T238 | Interior Painting | John Miller | Completed | Medium | 2023-12-25 | 2024-01-19 | 2024-01-19 | 100 | Paint | Industrial Park | 44439.59 | 47678.47 | No issues
C001 | Residential Building A | T835 | Foundation Excavation | Rachel Green | Blocked | Medium | 2023-12-14 | 2023-12-30 |  | 0 | Roofing Sheets | Plot 21, Riverside | 24531.86 | 16532.25 | Not started
C003 | Office Tower C | T879 | Roofing | Grace Allen | Blocked | Low | 2023-10-15 | 2023-11-06 |  | 0 | Roofing Sheets | Downtown Avenue | 45240.39 | 49668.35 | Not started
C001 | Residential Building A | T962 | Roofing | John Miller | Not Started | Low | 2024-06-23 | 2024-07-19 |  | 0 | Roofing Sheets | Plot 21, Riverside | 40759.07 | 0 | Not started
C001 | Residential Building A | T542 | Steel Framework Setup | Mike Adams | Not Started | Low | 2023-11-02 | 2023-11-14 |  | 0 | Steel Beams | Plot 21, Riverside | 32696.99 | 0 | Not started
C001 | Residential Building A | T142 | Foundation Excavation | Sarah Johnson | Completed | Low | 2024-06-05 | 2024-07-02 | 2024-07-02 | 100 | Copper Wires | Plot 21, Riverside | 22755.6 | 25854.89 | No issues
C001 | Residential Building A | T722 | Foundation Excavation | Mike Adams | Completed | Medium | 2023-01-03 | 2023-01-14 | 2023-01-14 | 100 | Concrete | Plot 21, Riverside | 16221.59 | 16869.06 | No issues
C004 | Warehouse D | T164 | Concrete Pouring | Carlos Rivera | In Progress | High | 2024-05-18 | 2024-06-13 |  | 98 | Steel Beams | Industrial Park | 30148.54 | 23062.45 | In progress
C003 | Office Tower C | T900 | Concrete Pouring | Emma White | Not Started | Medium | 2023-09-08 | 2023-09-21 |  | 0 | Concrete | Downtown Avenue | 44323.21 | 0 | Not started
C003 | Office Tower C | T865 | Roofing | Grace Allen | Not Started | High | 2024-12-05 | 2025-01-02 |  | 0 | Concrete | Downtown Avenue | 44191.26 | 0 | Not started
C001 | Residential Building A | T304 | Electrical Wiring | Sarah Johnson | In Progress | Low | 2023-09-14 | 2023-10-04 |  | 26 | Rebar | Plot 21, Riverside | 15940.48 | 12973.14 | In progress
C001 | Residential Building A | T342 | Site Survey | Emma White | In Progress | Low | 2023-10-11 | 2023-10-24 |  | 17 | Steel Beams | Plot 21, Riverside | 17558.82 | 15510.06 | In progress
C002 | Shopping Complex B | T993 | Site Survey | Sarah Johnson | Completed | Medium | 2023-08-24 | 2023-09-16 | 2023-09-16 | 100 | Cement | Market Street | 48788.14 | 80734.17 | No issues
C004 | Warehouse D | T492 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2024-11-23 | 2024-12-22 |  | 0 | Roofing Sheets | Industrial Park | 46299.09 | 0 | Not started
C001 | Residential Building A | T361 | Plumbing Installations | Rachel Green | Blocked | Medium | 2023-08-08 | 2023-09-06 |  | 0 | Paint | Plot 21, Riverside | 15679.48 | 10485.16 | Not started
C004 | Warehouse D | T823 | Concrete Pouring | Grace Allen | Completed | Medium | 2024-05-24 | 2024-06-12 | 2024-06-12 | 100 | Steel Beams | Industrial Park | 42055.19 | 49830.15 | No issues
C004 | Warehouse D | T899 | Interior Painting | Emma White | Blocked | Low | 2023-10-15 | 2023-11-08 |  | 0 | PVC Pipes | Industrial Park | 44278.85 | 38764 | Not started
C004 | Warehouse D | T688 | Plumbing Installations | John Miller | Blocked | Low | 2024-02-19 | 2024-03-09 |  | 0 | Steel Beams | Industrial Park | 19455.69 | 20688.03 | Not started
C001 | Residential Building A | T288 | Concrete Pouring | Carlos Rivera | Blocked | Medium | 2024-04-25 | 2024-05-17 |  | 0 | PVC Pipes | Plot 21, Riverside | 5660.05 | 3971.38 | Not started
C001 | Residential Building A | T754 | Foundation Excavation | Emma White | Not Started | Medium | 2024-12-05 | 2024-12-30 |  | 0 | PVC Pipes | Plot 21, Riverside | 47199.88 | 0 | Not started
C002 | Shopping Complex B | T725 | Electrical Wiring | Dave Brown | Not Started | High | 2024-04-21 | 2024-05-02 |  | 0 | Concrete | Market Street | 42848.36 | 0 | Not started
C004 | Warehouse D | T852 | Concrete Pouring | Carlos Rivera | Not Started | Low | 2023-01-12 | 2023-02-09 |  | 0 | Paint | Industrial Park | 22689.41 | 0 | Not started
C003 | Office Tower C | T410 | Steel Framework Setup | Emma White | Not Started | Medium | 2024-09-24 | 2024-10-03 |  | 0 | Roofing Sheets | Downtown Avenue | 45031.27 | 0 | Not started
C001 | Residential Building A | T720 | Interior Painting | Dave Brown | Completed | High | 2024-11-27 | 2024-12-24 | 2024-12-24 | 100 | Roofing Sheets | Plot 21, Riverside | 33462.81 | 23264.5 | No issues
C004 | Warehouse D | T397 | Electrical Wiring | Carlos Rivera | Completed | Low | 2023-07-16 | 2023-08-15 | 2023-08-15 | 100 | Cement | Industrial Park | 48961.25 | 39378.48 | No issues
C003 | Office Tower C | T159 | Electrical Wiring | Emma White | Not Started | High | 2024-01-09 | 2024-01-30 |  | 0 | Cement | Downtown Avenue | 7959.8 | 0 | Not started
C003 | Office Tower C | T108 | Foundation Excavation | Mike Adams | Blocked | Medium | 2024-10-07 | 2024-10-30 |  | 0 | Roofing Sheets | Downtown Avenue | 23890.46 | 25297.17 | Not started
C001 | Residential Building A | T711 | Electrical Wiring | Sarah Johnson | Blocked | Medium | 2023-03-06 | 2023-03-27 |  | 0 | Paint | Plot 21, Riverside | 7559.78 | 8582.15 | Not started
C004 | Warehouse D | T211 | Roofing | Mike Adams | Not Started | Medium | 2024-11-18 | 2024-11-25 |  | 0 | Rebar | Industrial Park | 41192.84 | 0 | Not started
C003 | Office Tower C | T215 | Roofing | Dave Brown | Completed | High | 2023-02-16 | 2023-03-01 | 2023-03-01 | 100 | Concrete | Downtown Avenue | 42486.7 | 41859.44 | No issues
C004 | Warehouse D | T118 | Concrete Pouring | Rachel Green | Blocked | Low | 2024-10-11 | 2024-11-02 |  | 0 | Concrete | Industrial Park | 29750.22 | 20571.64 | Not started
C002 | Shopping Complex B | T223 | Concrete Pouring | John Miller | Not Started | Low | 2024-04-08 | 2024-04-17 |  | 0 | PVC Pipes | Market Street | 26413.45 | 0 | Not started
C001 | Residential Building A | T965 | Interior Painting | Rachel Green | Completed | High | 2023-12-14 | 2023-12-31 | 2023-12-31 | 100 | Paint | Plot 21, Riverside | 46109.89 | 34878.99 | No issues
C003 | Office Tower C | T199 | Site Survey | Sarah Johnson | Not Started | High | 2023-01-05 | 2023-02-04 |  | 0 | Concrete | Downtown Avenue | 33554.18 | 0 | Not started
C002 | Shopping Complex B | T925 | Concrete Pouring | Dave Brown | Blocked | High | 2023-12-24 | 2024-01-10 |  | 0 | Rebar | Market Street | 31246.57 | 53606.67 | Not started
C004 | Warehouse D | T886 | Plumbing Installations | Dave Brown | Not Started | Low | 2023-06-14 | 2023-07-08 |  | 0 | Paint | Industrial Park | 16784.56 | 0 | Not started
C004 | Warehouse D | T689 | Foundation Excavation | Grace Allen | Completed | High | 2023-06-25 | 2023-07-21 | 2023-07-21 | 100 | Cement | Industrial Park | 13905.45 | 12690.25 | No issues
C003 | Office Tower C | T596 | Plumbing Installations | Mike Adams | Not Started | Medium | 2024-02-07 | 2024-02-29 |  | 0 | Steel Beams | Downtown Avenue | 16355.72 | 0 | Not started
C001 | Residential Building A | T153 | Electrical Wiring | Rachel Green | Completed | High | 2024-08-13 | 2024-09-11 | 2024-09-11 | 100 | Cement | Plot 21, Riverside | 10876.85 | 8372.1 | No issues
C002 | Shopping Complex B | T688 | Foundation Excavation | Mike Adams | Blocked | High | 2023-09-12 | 2023-10-10 |  | 0 | Cement | Market Street | 30043.38 | 61221.97 | Not started
C002 | Shopping Complex B | T641 | Foundation Excavation | Emma White | In Progress | Low | 2024-09-02 | 2024-09-23 |  | 51 | Steel Beams | Market Street | 43407.91 | 60950.67 | In progress
C004 | Warehouse D | T731 | Foundation Excavation | Carlos Rivera | In Progress | Medium | 2024-10-03 | 2024-10-15 |  | 87 | PVC Pipes | Industrial Park | 41700.8 | 39013.18 | In progress
C003 | Office Tower C | T432 | Electrical Wiring | Emma White | In Progress | High | 2024-08-02 | 2024-08-24 |  | 78 | PVC Pipes | Downtown Avenue | 31932.71 | 27466.11 | In progress
C002 | Shopping Complex B | T314 | Plumbing Installations | Rachel Green | In Progress | Medium | 2024-05-18 | 2024-06-08 |  | 67 | Rebar | Market Street | 22599.98 | 49259.45 | In progress
C003 | Office Tower C | T971 | Concrete Pouring | Rachel Green | Completed | Low | 2024-01-24 | 2024-02-09 | 2024-02-09 | 100 | Rebar | Downtown Avenue | 23564.02 | 19438.78 | No issues
C004 | Warehouse D | T384 | Roofing | Sarah Johnson | Completed | High | 2023-02-06 | 2023-02-13 | 2023-02-13 | 100 | Rebar | Industrial Park | 30523.88 | 25234.54 | No issues
C003 | Office Tower C | T818 | Site Survey | Rachel Green | In Progress | Medium | 2023-03-15 | 2023-04-13 |  | 54 | Copper Wires | Downtown Avenue | 6441.82 | 5722.43 | In progress
C004 | Warehouse D | T583 | Plumbing Installations | Emma White | In Progress | Medium | 2023-02-22 | 2023-03-24 |  | 46 | Copper Wires | Industrial Park | 26445.19 | 15964.14 | In progress
C002 | Shopping Complex B | T648 | Interior Painting | Sarah Johnson | Not Started | Low | 2024-09-08 | 2024-09-22 |  | 0 | Rebar | Market Street | 40663.05 | 0 | Not started
C001 | Residential Building A | T557 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2024-04-10 | 2024-04-27 |  | 0 | Steel Beams | Plot 21, Riverside | 35204.04 | 0 | Not started
C001 | Residential Building A | T324 | Interior Painting | Sarah Johnson | In Progress | High | 2023-04-14 | 2023-04-22 |  | 29 | Concrete | Plot 21, Riverside | 41598.71 | 40443.41 | In progress
C003 | Office Tower C | T349 | Roofing | Sarah Johnson | Completed | High | 2024-09-13 | 2024-10-05 | 2024-10-05 | 100 | Rebar | Downtown Avenue | 14461.49 | 17294.17 | No issues
C001 | Residential Building A | T210 | Plumbing Installations | Grace Allen | In Progress | Low | 2023-11-27 | 2023-12-09 |  | 93 | Paint | Plot 21, Riverside | 26237.84 | 21324.22 | In progress
C004 | Warehouse D | T459 | Site Survey | John Miller | In Progress | Medium | 2024-03-11 | 2024-04-07 |  | 38 | Steel Beams | Industrial Park | 38199.84 | 28928.32 | In progress
C001 | Residential Building A | T721 | Concrete Pouring | Rachel Green | In Progress | Medium | 2023-11-18 | 2023-12-08 |  | 71 | PVC Pipes | Plot 21, Riverside | 44534.02 | 27639.47 | In progress
C003 | Office Tower C | T392 | Roofing | Dave Brown | Blocked | High | 2024-03-27 | 2024-04-17 |  | 0 | Cement | Downtown Avenue | 37551.44 | 33955.55 | Not started
C002 | Shopping Complex B | T864 | Interior Painting | John Miller | Completed | Low | 2024-11-06 | 2024-12-04 | 2024-12-04 | 100 | Rebar | Market Street | 7073.17 | 30011.51 | No issues
C004 | Warehouse D | T198 | Interior Painting | Grace Allen | Not Started | High | 2024-01-26 | 2024-02-22 |  | 0 | Cement | Industrial Park | 21298.69 | 0 | Not started
C003 | Office Tower C | T827 | Plumbing Installations | Rachel Green | Blocked | High | 2024-07-24 | 2024-08-08 |  | 0 | Concrete | Downtown Avenue | 16970.31 | 17122.72 | Not started
C004 | Warehouse D | T851 | Steel Framework Setup | Grace Allen | Not Started | Medium | 2024-04-15 | 2024-05-15 |  | 0 | Concrete | Industrial Park | 41253.13 | 0 | Not started
C002 | Shopping Complex B | T657 | Plumbing Installations | Mike Adams | In Progress | Low | 2024-01-25 | 2024-02-17 |  | 54 | Cement | Market Street | 21117.89 | 48228.35 | In progress
C001 | Residential Building A | T252 | Roofing | Mike Adams | In Progress | Medium | 2023-07-03 | 2023-07-19 |  | 91 | Steel Beams | Plot 21, Riverside | 6770.38 | 7467.5 | In progress
C001 | Residential Building A | T169 | Steel Framework Setup | Carlos Rivera | In Progress | Low | 2024-01-20 | 2024-02-13 |  | 36 | Cement | Plot 21, Riverside | 28099.11 | 31948.71 | In progress
C003 | Office Tower C | T659 | Plumbing Installations | Emma White | In Progress | Low | 2024-03-03 | 2024-03-31 |  | 21 | Copper Wires | Downtown Avenue | 38414.68 | 42643.91 | In progress
C002 | Shopping Complex B | T880 | Roofing | Rachel Green | Not Started | Low | 2023-02-19 | 2023-03-17 |  | 0 | Concrete | Market Street | 7444.78 | 0 | Not started
C004 | Warehouse D | T716 | Interior Painting | Grace Allen | Blocked | High | 2023-12-01 | 2023-12-18 |  | 0 | Rebar | Industrial Park | 6034.88 | 6224.54 | Not started
C003 | Office Tower C | T384 | Plumbing Installations | Emma White | Completed | Low | 2024-09-09 | 2024-10-06 | 2024-10-06 | 100 | Paint | Downtown Avenue | 34081.17 | 27216.35 | No issues
C002 | Shopping Complex B | T602 | Steel Framework Setup | Carlos Rivera | Not Started | Low | 2024-12-12 | 2024-12-26 |  | 0 | PVC Pipes | Market Street | 23341.57 | 0 | Not started
C003 | Office Tower C | T607 | Plumbing Installations | Dave Brown | Blocked | Low | 2023-04-20 | 2023-05-15 |  | 0 | Roofing Sheets | Downtown Avenue | 19377.69 | 15796.38 | Not started
C003 | Office Tower C | T460 | Roofing | John Miller | In Progress | Medium | 2024-12-18 | 2025-01-10 |  | 57 | Roofing Sheets | Downtown Avenue | 49560.16 | 53302.71 | In progress
C003 | Office Tower C | T788 | Electrical Wiring | Emma White | Not Started | Low | 2023-11-28 | 2023-12-15 |  | 0 | Paint | Downtown Avenue | 20915.45 | 0 | Not started
C002 | Shopping Complex B | T975 | Interior Painting | Mike Adams | In Progress | Low | 2023-12-06 | 2023-12-21 |  | 7 | Rebar | Market Street | 42129.8 | 60123.94 | In progress
C004 | Warehouse D | T633 | Concrete Pouring | Mike Adams | Blocked | High | 2024-05-14 | 2024-06-11 |  | 0 | Roofing Sheets | Industrial Park | 26704.69 | 19994.61 | Not started
C003 | Office Tower C | T618 | Roofing | John Miller | Blocked | High | 2023-02-20 | 2023-03-03 |  | 0 | PVC Pipes | Downtown Avenue | 45209.79 | 42896.44 | Not started
C002 | Shopping Complex B | T638 | Site Survey | Mike Adams | Completed | Low | 2023-09-23 | 2023-10-14 | 2023-10-14 | 100 | Cement | Market Street | 36482.13 | 56478.83 | No issues
C002 | Shopping Complex B | T612 | Foundation Excavation | John Miller | In Progress | High | 2023-08-27 | 2023-09-15 |  | 20 | Cement | Market Street | 47901.97 | 79627.84 | In progress
C002 | Shopping Complex B | T905 | Electrical Wiring | Rachel Green | Completed | Medium | 2024-06-22 | 2024-07-08 | 2024-07-08 | 100 | Roofing Sheets | Market Street | 15628.19 | 42594.65 | No issues
C003 | Office Tower C | T258 | Site Survey | Sarah Johnson | In Progress | Medium | 2024-06-11 | 2024-06-21 |  | 20 | Concrete | Downtown Avenue | 37319.22 | 26037.8 | In progress
C002 | Shopping Complex B | T928 | Site Survey | Sarah Johnson | Blocked | High | 2024-01-25 | 2024-02-08 |  | 0 | Rebar | Market Street | 42590.97 | 53669.62 | Not started
C001 | Residential Building A | T686 | Interior Painting | Sarah Johnson | Not Started | Low | 2024-04-19 | 2024-05-09 |  | 0 | Cement | Plot 21, Riverside | 8095 | 0 | Not started
C003 | Office Tower C | T390 | Site Survey | Grace Allen | Not Started | Low | 2024-08-18 | 2024-09-14 |  | 0 | Concrete | Downtown Avenue | 41695.79 | 0 | Not started
C001 | Residential Building A | T815 | Steel Framework Setup | John Miller | In Progress | Low | 2024-03-27 | 2024-04-26 |  | 19 | Paint | Plot 21, Riverside | 23229.71 | 14977.32 | In progress
C003 | Office Tower C | T886 | Steel Framework Setup | John Miller | Blocked | High | 2024-10-01 | 2024-10-19 |  | 0 | Roofing Sheets | Downtown Avenue | 8748.55 | 5389.34 | Not started
C004 | Warehouse D | T843 | Interior Painting | John Miller | Blocked | Low | 2024-06-05 | 2024-06-28 |  | 0 | Paint | Industrial Park | 30452.09 | 35628.59 | Not started
C004 | Warehouse D | T128 | Site Survey | Mike Adams | In Progress | Low | 2024-12-21 | 2025-01-08 |  | 57 | Paint | Industrial Park | 35521 | 30374.7 | In progress
C002 | Shopping Complex B | T646 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-02-27 | 2024-03-26 |  | 15 | Cement | Market Street | 10052.97 | 35059.12 | In progress
C003 | Office Tower C | T343 | Foundation Excavation | Sarah Johnson | In Progress | High | 2023-07-21 | 2023-08-15 |  | 43 | Paint | Downtown Avenue | 48596.31 | 34527.47 | In progress
C004 | Warehouse D | T648 | Plumbing Installations | Rachel Green | Not Started | Medium | 2023-08-07 | 2023-08-21 |  | 0 | PVC Pipes | Industrial Park | 38084.93 | 0 | Not started
C002 | Shopping Complex B | T484 | Interior Painting | Grace Allen | In Progress | Medium | 2024-08-23 | 2024-09-16 |  | 54 | Copper Wires | Market Street | 46155.81 | 77310.2 | In progress
C004 | Warehouse D | T329 | Foundation Excavation | Grace Allen | Not Started | High | 2023-08-08 | 2023-08-20 |  | 0 | Roofing Sheets | Industrial Park | 11006.12 | 0 | Not started
C003 | Office Tower C | T812 | Plumbing Installations | Carlos Rivera | In Progress | Medium | 2023-12-13 | 2024-01-10 |  | 60 | PVC Pipes | Downtown Avenue | 5999.51 | 5614.03 | In progress
C002 | Shopping Complex B | T909 | Site Survey | John Miller | Completed | Medium | 2024-02-27 | 2024-03-05 | 2024-03-05 | 100 | Rebar | Market Street | 37460.93 | 65556.41 | No issues
C002 | Shopping Complex B | T811 | Interior Painting | Carlos Rivera | Blocked | High | 2023-12-02 | 2023-12-11 |  | 0 | PVC Pipes | Market Street | 47991.49 | 82549.74 | Not started
C003 | Office Tower C | T614 | Concrete Pouring | John Miller | Blocked | High | 2024-03-17 | 2024-03-28 |  | 0 | Rebar | Downtown Avenue | 6815.51 | 4130.26 | Not started
C004 | Warehouse D | T864 | Electrical Wiring | Rachel Green | In Progress | Low | 2024-03-17 | 2024-04-01 |  | 54 | Paint | Industrial Park | 35597.52 | 22386.58 | In progress
C002 | Shopping Complex B | T714 | Steel Framework Setup | Grace Allen | In Progress | High | 2024-10-20 | 2024-11-09 |  | 41 | Concrete | Market Street | 10274.75 | 36212.28 | In progress
C003 | Office Tower C | T449 | Plumbing Installations | Grace Allen | Not Started | Medium | 2023-06-08 | 2023-06-22 |  | 0 | Paint | Downtown Avenue | 40508.87 | 0 | Not started
C002 | Shopping Complex B | T476 | Foundation Excavation | Carlos Rivera | Not Started | Medium | 2023-06-10 | 2023-06-29 |  | 0 | Concrete | Market Street | 31719.98 | 0 | Not started
C002 | Shopping Complex B | T534 | Concrete Pouring | Grace Allen | Completed | Low | 2024-11-15 | 2024-12-07 | 2024-12-07 | 100 | Paint | Market Street | 42081.91 | 75515.48 | No issues
C002 | Shopping Complex B | T985 | Plumbing Installations | John Miller | Not Started | Low | 2023-07-08 | 2023-07-18 |  | 0 | Rebar | Market Street | 9934.35 | 0 | Not started
C001 | Residential Building A | T608 | Electrical Wiring | John Miller | Blocked | High | 2023-05-17 | 2023-06-01 |  | 0 | Copper Wires | Plot 21, Riverside | 24945.33 | 22709.57 | Not started
C003 | Office Tower C | T318 | Interior Painting | Grace Allen | In Progress | High | 2024-09-11 | 2024-09-25 |  | 70 | PVC Pipes | Downtown Avenue | 24770.47 | 29276.37 | In progress
C003 | Office Tower C | T713 | Foundation Excavation | Rachel Green | In Progress | Medium | 2024-01-14 | 2024-02-10 |  | 74 | Paint | Downtown Avenue | 29624.96 | 34400.89 | In progress
C001 | Residential Building A | T921 | Plumbing Installations | Grace Allen | Completed | Medium | 2024-11-25 | 2024-12-10 | 2024-12-10 | 100 | Cement | Plot 21, Riverside | 24980.18 | 23435.68 | No issues
C002 | Shopping Complex B | T889 | Plumbing Installations | Mike Adams | Blocked | High | 2024-04-08 | 2024-04-16 |  | 0 | Steel Beams | Market Street | 35389.86 | 58124.27 | Not started
C004 | Warehouse D | T622 | Plumbing Installations | Rachel Green | Blocked | High | 2024-06-18 | 2024-07-06 |  | 0 | Copper Wires | Industrial Park | 28626.25 | 20720.7 | Not started
C002 | Shopping Complex B | T918 | Roofing | Emma White | Not Started | High | 2024-06-05 | 2024-06-30 |  | 0 | Concrete | Market Street | 31318.17 | 0 | Not started
C003 | Office Tower C | T834 | Roofing | Grace Allen | Blocked | Medium | 2023-08-12 | 2023-09-05 |  | 0 | Roofing Sheets | Downtown Avenue | 34149.88 | 25618.85 | Not started
C004 | Warehouse D | T231 | Steel Framework Setup | Emma White | In Progress | Low | 2024-09-08 | 2024-09-20 |  | 49 | Roofing Sheets | Industrial Park | 10746.23 | 11652.68 | In progress
C001 | Residential Building A | T284 | Plumbing Installations | Sarah Johnson | Blocked | Medium | 2023-10-07 | 2023-10-22 |  | 0 | Paint | Plot 21, Riverside | 25946.58 | 23726.17 | Not started
C001 | Residential Building A | T151 | Electrical Wiring | Mike Adams | Completed | Medium | 2023-09-09 | 2023-09-30 | 2023-09-30 | 100 | Steel Beams | Plot 21, Riverside | 27033.56 | 25471.24 | No issues
C002 | Shopping Complex B | T916 | Interior Painting | Mike Adams | Blocked | Low | 2024-10-28 | 2024-11-18 |  | 0 | Copper Wires | Market Street | 45883.34 | 56781.23 | Not started
C002 | Shopping Complex B | T195 | Steel Framework Setup | Rachel Green | Completed | Low | 2024-05-02 | 2024-05-29 | 2024-05-29 | 100 | Rebar | Market Street | 28247.03 | 55577.66 | No issues
C003 | Office Tower C | T978 | Plumbing Installations | Dave Brown | Not Started | Low | 2024-03-16 | 2024-04-14 |  | 0 | Roofing Sheets | Downtown Avenue | 42476.85 | 0 | Not started
C001 | Residential Building A | T268 | Concrete Pouring | Dave Brown | Not Started | Low | 2023-08-22 | 2023-09-04 |  | 0 | PVC Pipes | Plot 21, Riverside | 30572.91 | 0 | Not started
C003 | Office Tower C | T343 | Electrical Wiring | Grace Allen | In Progress | High | 2023-06-17 | 2023-07-15 |  | 0 | Rebar | Downtown Avenue | 25685.3 | 28980.42 | In progress
C001 | Residential Building A | T618 | Roofing | Sarah Johnson | Blocked | Low | 2023-11-13 | 2023-12-09 |  | 0 | Concrete | Plot 21, Riverside | 26132.3 | 21342.76 | Not started
C004 | Warehouse D | T804 | Site Survey | Grace Allen | Not Started | High | 2024-05-10 | 2024-06-09 |  | 0 | Copper Wires | Industrial Park | 23551.01 | 0 | Not started
C002 | Shopping Complex B | T687 | Roofing | Carlos Rivera | Not Started | Low | 2024-01-02 | 2024-01-11 |  | 0 | PVC Pipes | Market Street | 13584.74 | 0 | Not started
C003 | Office Tower C | T785 | Interior Painting | Dave Brown | Completed | High | 2023-11-05 | 2023-11-18 | 2023-11-18 | 100 | Steel Beams | Downtown Avenue | 28498.9 | 17743.52 | No issues
C004 | Warehouse D | T536 | Plumbing Installations | John Miller | In Progress | Low | 2024-08-16 | 2024-09-07 |  | 52 | Copper Wires | Industrial Park | 9816.86 | 9922.67 | In progress
C004 | Warehouse D | T323 | Roofing | Rachel Green | Completed | Low | 2023-02-19 | 2023-03-15 | 2023-03-15 | 100 | Concrete | Industrial Park | 37070.32 | 27883.69 | No issues
C004 | Warehouse D | T532 | Foundation Excavation | Sarah Johnson | Completed | High | 2023-12-03 | 2023-12-20 | 2023-12-20 | 100 | Roofing Sheets | Industrial Park | 27877.47 | 22268.21 | No issues
C004 | Warehouse D | T942 | Site Survey | Mike Adams | In Progress | Medium | 2023-09-07 | 2023-09-27 |  | 32 | Cement | Industrial Park | 30239.19 | 34677.43 | In progress
C001 | Residential Building A | T768 | Electrical Wiring | John Miller | Not Started | Low | 2023-02-07 | 2023-03-03 |  | 0 | Concrete | Plot 21, Riverside | 22348.71 | 0 | Not started
C002 | Shopping Complex B | T436 | Plumbing Installations | Carlos Rivera | Blocked | Low | 2024-05-12 | 2024-05-30 |  | 0 | Cement | Market Street | 11737.15 | 35066.59 | Not started
C004 | Warehouse D | T241 | Roofing | Rachel Green | In Progress | High | 2024-06-09 | 2024-06-19 |  | 45 | Cement | Industrial Park | 23184.32 | 26906.53 | In progress
C004 | Warehouse D | T630 | Plumbing Installations | John Miller | Blocked | Low | 2023-05-15 | 2023-05-29 |  | 0 | Steel Beams | Industrial Park | 20056.41 | 12235.11 | Not started
C001 | Residential Building A | T714 | Foundation Excavation | Rachel Green | In Progress | High | 2024-12-06 | 2024-12-31 |  | 81 | PVC Pipes | Plot 21, Riverside | 16642.72 | 18492.91 | In progress
C002 | Shopping Complex B | T570 | Steel Framework Setup | Sarah Johnson | Blocked | Medium | 2024-07-09 | 2024-07-20 |  | 0 | Roofing Sheets | Market Street | 30819.13 | 60412.33 | Not started
C001 | Residential Building A | T138 | Roofing | Mike Adams | Blocked | High | 2023-10-19 | 2023-11-12 |  | 0 | Concrete | Plot 21, Riverside | 14190.35 | 12496.74 | Not started
C004 | Warehouse D | T223 | Interior Painting | Mike Adams | Not Started | Medium | 2023-02-06 | 2023-02-28 |  | 0 | Roofing Sheets | Industrial Park | 46845.72 | 0 | Not started
C004 | Warehouse D | T170 | Roofing | Carlos Rivera | In Progress | High | 2023-04-10 | 2023-05-07 |  | 0 | Copper Wires | Industrial Park | 31414.3 | 20651.74 | In progress
C002 | Shopping Complex B | T432 | Site Survey | Mike Adams | Blocked | High | 2024-08-09 | 2024-09-07 |  | 0 | Steel Beams | Market Street | 31037.92 | 47667.97 | Not started
C002 | Shopping Complex B | T204 | Concrete Pouring | Emma White | Blocked | Low | 2023-03-01 | 2023-03-25 |  | 0 | PVC Pipes | Market Street | 31186.76 | 59157.7 | Not started
C003 | Office Tower C | T977 | Site Survey | Dave Brown | Completed | Low | 2024-03-25 | 2024-04-15 | 2024-04-15 | 100 | PVC Pipes | Downtown Avenue | 44897.42 | 52482.85 | No issues
C003 | Office Tower C | T645 | Interior Painting | John Miller | Not Started | Low | 2024-06-22 | 2024-07-09 |  | 0 | Concrete | Downtown Avenue | 26987.68 | 0 | Not started
C002 | Shopping Complex B | T753 | Steel Framework Setup | John Miller | Not Started | High | 2024-01-04 | 2024-01-13 |  | 0 | Steel Beams | Market Street | 28875.02 | 0 | Not started
C001 | Residential Building A | T636 | Roofing | Rachel Green | Not Started | Low | 2023-04-05 | 2023-04-25 |  | 0 | Cement | Plot 21, Riverside | 30067.51 | 0 | Not started
C003 | Office Tower C | T736 | Foundation Excavation | Dave Brown | In Progress | Medium | 2023-03-06 | 2023-03-19 |  | 30 | Copper Wires | Downtown Avenue | 9549.68 | 10490.06 | In progress
C003 | Office Tower C | T979 | Roofing | Sarah Johnson | In Progress | Medium | 2024-03-17 | 2024-04-08 |  | 6 | Rebar | Downtown Avenue | 5886.69 | 6330.93 | In progress
C002 | Shopping Complex B | T959 | Site Survey | Sarah Johnson | In Progress | High | 2024-08-09 | 2024-08-21 |  | 40 | Cement | Market Street | 29889.83 | 51970.94 | In progress
C004 | Warehouse D | T751 | Steel Framework Setup | Rachel Green | Not Started | Medium | 2023-09-26 | 2023-10-04 |  | 0 | Rebar | Industrial Park | 31363.96 | 0 | Not started
C003 | Office Tower C | T289 | Roofing | Grace Allen | Completed | Low | 2024-11-11 | 2024-12-10 | 2024-12-10 | 100 | Concrete | Downtown Avenue | 43925.8 | 48947.04 | No issues
C001 | Residential Building A | T269 | Plumbing Installations | Sarah Johnson | Not Started | Low | 2024-09-13 | 2024-10-02 |  | 0 | Rebar | Plot 21, Riverside | 35392.57 | 0 | Not started
C002 | Shopping Complex B | T369 | Roofing | John Miller | Blocked | Low | 2023-04-13 | 2023-05-10 |  | 0 | PVC Pipes | Market Street | 5866.73 | 29134.81 | Not started
C004 | Warehouse D | T952 | Concrete Pouring | Mike Adams | In Progress | Medium | 2023-12-02 | 2023-12-23 |  | 67 | Steel Beams | Industrial Park | 42584.89 | 33990.63 | In progress
C001 | Residential Building A | T810 | Plumbing Installations | Grace Allen | Not Started | High | 2024-03-23 | 2024-04-04 |  | 0 | Copper Wires | Plot 21, Riverside | 47298.2 | 0 | Not started
C001 | Residential Building A | T925 | Interior Painting | Mike Adams | In Progress | Low | 2024-05-26 | 2024-06-25 |  | 6 | Cement | Plot 21, Riverside | 7648.58 | 6659.73 | In progress
C001 | Residential Building A | T697 | Site Survey | Rachel Green | Completed | Low | 2024-08-04 | 2024-08-12 | 2024-08-12 | 100 | Paint | Plot 21, Riverside | 29982.41 | 33229.09 | No issues
C001 | Residential Building A | T381 | Concrete Pouring | Carlos Rivera | Not Started | High | 2023-02-23 | 2023-03-13 |  | 0 | Copper Wires | Plot 21, Riverside | 28832.95 | 0 | Not started
C004 | Warehouse D | T218 | Interior Painting | Dave Brown | In Progress | Medium | 2024-07-19 | 2024-08-07 |  | 65 | Roofing Sheets | Industrial Park | 40419.2 | 32150.84 | In progress
C001 | Residential Building A | T544 | Interior Painting | Mike Adams | In Progress | High | 2024-02-10 | 2024-02-23 |  | 88 | Copper Wires | Plot 21, Riverside | 28320.66 | 33211.43 | In progress
C002 | Shopping Complex B | T984 | Electrical Wiring | Mike Adams | Blocked | High | 2023-11-24 | 2023-12-03 |  | 0 | Copper Wires | Market Street | 37433.93 | 66376.97 | Not started
C001 | Residential Building A | T235 | Concrete Pouring | Mike Adams | Completed | Low | 2024-11-13 | 2024-12-09 | 2024-12-09 | 100 | Cement | Plot 21, Riverside | 15142.01 | 11175.66 | No issues
C004 | Warehouse D | T385 | Foundation Excavation | Mike Adams | Not Started | High | 2023-10-26 | 2023-11-04 |  | 0 | Paint | Industrial Park | 30486.63 | 0 | Not started
C004 | Warehouse D | T758 | Foundation Excavation | Sarah Johnson | Not Started | Medium | 2024-09-23 | 2024-10-05 |  | 0 | Roofing Sheets | Industrial Park | 7002.55 | 0 | Not started
C004 | Warehouse D | T503 | Site Survey | Dave Brown | In Progress | High | 2024-01-21 | 2024-02-10 |  | 55 | Paint | Industrial Park | 37771.86 | 44933 | In progress
C003 | Office Tower C | T397 | Site Survey | Dave Brown | In Progress | Medium | 2024-01-26 | 2024-02-10 |  | 45 | Copper Wires | Downtown Avenue | 20252.21 | 23620.17 | In progress
C003 | Office Tower C | T794 | Interior Painting | Carlos Rivera | Blocked | Low | 2023-11-09 | 2023-12-01 |  | 0 | Rebar | Downtown Avenue | 40650.94 | 35549.78 | Not started
C001 | Residential Building A | T788 | Plumbing Installations | Dave Brown | Completed | Medium | 2024-10-28 | 2024-11-24 | 2024-11-24 | 100 | Copper Wires | Plot 21, Riverside | 10881.08 | 11216.88 | No issues
C002 | Shopping Complex B | T125 | Concrete Pouring | Mike Adams | Not Started | Medium | 2024-01-01 | 2024-01-09 |  | 0 | Concrete | Market Street | 31679.57 | 0 | Not started
C002 | Shopping Complex B | T242 | Interior Painting | Sarah Johnson | Completed | Medium | 2023-12-14 | 2023-12-23 | 2023-12-23 | 100 | Rebar | Market Street | 38439.45 | 61787.53 | No issues
C001 | Residential Building A | T282 | Steel Framework Setup | Carlos Rivera | Completed | Medium | 2024-05-26 | 2024-06-19 | 2024-06-19 | 100 | Paint | Plot 21, Riverside | 39538.57 | 37601.81 | No issues
C002 | Shopping Complex B | T199 | Roofing | Rachel Green | Completed | High | 2023-07-26 | 2023-08-15 | 2023-08-15 | 100 | Cement | Market Street | 34948.1 | 55906.87 | No issues
C004 | Warehouse D | T466 | Plumbing Installations | Sarah Johnson | In Progress | Low | 2023-07-10 | 2023-07-28 |  | 80 | Cement | Industrial Park | 29799.21 | 18551.89 | In progress
C004 | Warehouse D | T502 | Site Survey | Dave Brown | Not Started | Low | 2023-03-02 | 2023-03-17 | 2023-03-17 | 0 | Roofing Sheets | Industrial Park | 45820.88 | 0 | Not started
C004 | Warehouse D | T947 | Steel Framework Setup | Mike Adams | Blocked | Low | 2024-11-22 | 2024-12-21 |  | 0 | Paint | Industrial Park | 38477.99 | 39171.76 | Not started
C002 | Shopping Complex B | T634 | Plumbing Installations | Grace Allen | Blocked | Low | 2023-10-17 | 2023-11-04 | 2023-11-04 | 0 | PVC Pipes | Market Street | 36994.42 | 49943.6 | Not started
C003 | Office Tower C | T273 | Site Survey | Grace Allen | Not Started | High | 2023-05-27 | 2023-06-24 | 2023-06-24 | 0 | Paint | Downtown Avenue | 45469.04 | 0 | Not started
C002 | Shopping Complex B | T574 | Concrete Pouring | Dave Brown | Not Started | Medium | 2024-01-09 | 2024-01-18 |  | 0 | Concrete | Market Street | 5574.43 | 0 | Not started
C004 | Warehouse D | T332 | Interior Painting | Sarah Johnson | Not Started | Low | 2024-09-14 | 2024-09-23 |  | 0 | Cement | Industrial Park | 29518 | 0 | Not started
C002 | Shopping Complex B | T203 | Plumbing Installations | Carlos Rivera | In Progress | High | 2024-07-17 | 2024-07-29 |  | 26 | Roofing Sheets | Market Street | 46625.05 | 77149.47 | In progress
C001 | Residential Building A | T898 | Interior Painting | Mike Adams | Blocked | Low | 2023-12-09 | 2023-12-16 | 2023-12-16 | 0 | Steel Beams | Plot 21, Riverside | 38235.07 | 27727.61 | Not started
C003 | Office Tower C | T652 | Foundation Excavation | Emma White | In Progress | Medium | 2023-12-05 | 2023-12-20 | 2023-12-20 | 2 | Copper Wires | Downtown Avenue | 9106.63 | 9796.69 | In progress
C004 | Warehouse D | T110 | Steel Framework Setup | Rachel Green | In Progress | Medium | 2023-08-25 | 2023-09-11 | 2023-09-11 | 56 | Copper Wires | Industrial Park | 33599.55 | 23990.88 | In progress
C004 | Warehouse D | T979 | Interior Painting | Emma White | Not Started | High | 2023-06-27 | 2023-07-11 | 2023-07-11 | 0 | Concrete | Industrial Park | 18500.27 | 0 | Not started
C004 | Warehouse D | T896 | Plumbing Installations | Dave Brown | Completed | Low | 2024-04-05 | 2024-04-26 | 2024-04-26 | 100 | Cement | Industrial Park | 40978.26 | 46836.93 | No issues
C002 | Shopping Complex B | T661 | Electrical Wiring | Grace Allen | Blocked | Low | 2024-04-04 | 2024-04-27 |  | 0 | Roofing Sheets | Market Street | 48578.21 | 81959.99 | Not started
C002 | Shopping Complex B | T701 | Site Survey | Sarah Johnson | Blocked | Medium | 2023-10-27 | 2023-11-09 | 2023-11-09 | 0 | Steel Beams | Market Street | 24682.06 | 45954.8 | Not started
C002 | Shopping Complex B | T122 | Concrete Pouring | Dave Brown | In Progress | Low | 2023-05-15 | 2023-06-14 | 2023-06-14 | 29 | Copper Wires | Market Street | 44119.69 | 72773.89 | In progress
C003 | Office Tower C | T767 | Steel Framework Setup | Emma White | Completed | High | 2024-01-08 | 2024-01-23 | 2024-01-23 | 100 | Paint | Downtown Avenue | 38536.91 | 33713.6 | No issues
C001 | Residential Building A | T621 | Foundation Excavation | Carlos Rivera | Not Started | Low | 2023-12-14 | 2023-12-26 | 2023-12-26 | 0 | PVC Pipes | Plot 21, Riverside | 36046.03 | 0 | Not started
C003 | Office Tower C | T977 | Plumbing Installations | Grace Allen | In Progress | Low | 2023-10-26 | 2023-11-08 | 2023-11-08 | 5 | Rebar | Downtown Avenue | 7089.17 | 4896.87 | In progress
C001 | Residential Building A | T237 | Foundation Excavation | Rachel Green | Blocked | Low | 2024-03-04 | 2024-03-26 |  | 0 | Cement | Plot 21, Riverside | 37614.58 | 34992.18 | Not started
C001 | Residential Building A | T180 | Roofing | Grace Allen | Not Started | Low | 2023-06-27 | 2023-07-09 | 2023-07-09 | 0 | Roofing Sheets | Plot 21, Riverside | 30760.44 | 0 | Not started
C001 | Residential Building A | T957 | Site Survey | John Miller | Blocked | Low | 2024-04-17 | 2024-05-12 |  | 0 | Steel Beams | Plot 21, Riverside | 20739 | 24168.74 | Not started
C004 | Warehouse D | T284 | Roofing | Emma White | Blocked | Medium | 2023-12-12 | 2024-01-07 |  | 0 | Copper Wires | Industrial Park | 37293.92 | 43807.96 | Not started
C002 | Shopping Complex B | T123 | Foundation Excavation | Sarah Johnson | Completed | Medium | 2023-06-04 | 2023-06-11 | 2023-06-11 | 100 | Roofing Sheets | Market Street | 47197.92 | 66100.57 | No issues
C003 | Office Tower C | T873 | Concrete Pouring | Grace Allen | Blocked | High | 2023-02-10 | 2023-03-12 |  | 0 | Rebar | Downtown Avenue | 13798.6 | 8305.08 | Not started
C001 | Residential Building A | T711 | Plumbing Installations | Emma White | Completed | High | 2023-01-20 | 2023-02-03 | 2023-02-03 | 100 | Steel Beams | Plot 21, Riverside | 18642.49 | 19584.04 | No issues
C004 | Warehouse D | T681 | Roofing | Dave Brown | In Progress | Low | 2024-09-14 | 2024-10-12 |  | 41 | Rebar | Industrial Park | 8444.67 | 6591.19 | In progress
C003 | Office Tower C | T707 | Plumbing Installations | Mike Adams | Completed | High | 2024-10-11 | 2024-10-25 | 2024-10-25 | 100 | Cement | Downtown Avenue | 17481.43 | 17154.84 | No issues
C003 | Office Tower C | T171 | Foundation Excavation | Grace Allen | Not Started | Low | 2023-11-02 | 2023-11-25 |  | 0 | Concrete | Downtown Avenue | 32991.3 | 0 | Not started
C001 | Residential Building A | T749 | Roofing | Grace Allen | In Progress | High | 2024-04-18 | 2024-05-14 |  | 62 | Copper Wires | Plot 21, Riverside | 21411.33 | 24835.69 | In progress
C004 | Warehouse D | T441 | Site Survey | Mike Adams | Not Started | Low | 2024-06-12 | 2024-07-04 |  | 0 | Copper Wires | Industrial Park | 34947.52 | 0 | Not started
C001 | Residential Building A | T353 | Concrete Pouring | Grace Allen | Blocked | High | 2024-12-27 | 2025-01-14 |  | 0 | Steel Beams | Plot 21, Riverside | 25819.08 | 30848.35 | Not started
C003 | Office Tower C | T620 | Steel Framework Setup | Rachel Green | In Progress | Low | 2024-09-11 | 2024-09-27 |  | 48 | Roofing Sheets | Downtown Avenue | 44361.07 | 48287.5 | In progress
C003 | Office Tower C | T335 | Foundation Excavation | Carlos Rivera | Blocked | Low | 2023-03-22 | 2023-04-10 |  | 0 | Rebar | Downtown Avenue | 25491.47 | 25659.99 | Not started
C001 | Residential Building A | T515 | Electrical Wiring | Dave Brown | Blocked | High | 2024-11-15 | 2024-12-02 |  | 0 | Concrete | Plot 21, Riverside | 16994.22 | 18521.28 | Not started
C001 | Residential Building A | T292 | Plumbing Installations | Emma White | Completed | High | 2023-04-14 | 2023-04-21 | 2023-04-21 | 100 | Roofing Sheets | Plot 21, Riverside | 32273.06 | 28662.64 | No issues
C002 | Shopping Complex B | T408 | Concrete Pouring | Mike Adams | Blocked | High | 2024-09-20 | 2024-10-03 |  | 0 | Rebar | Market Street | 31785.41 | 60174.64 | Not started
C004 | Warehouse D | T169 | Roofing | Rachel Green | Not Started | Medium | 2023-09-26 | 2023-10-12 |  | 0 | Roofing Sheets | Industrial Park | 11852.42 | 0 | Not started
C004 | Warehouse D | T630 | Site Survey | Emma White | Blocked | Medium | 2024-08-07 | 2024-08-18 |  | 0 | Paint | Industrial Park | 45210.12 | 50928.02 | Not started
C004 | Warehouse D | T612 | Interior Painting | Rachel Green | Not Started | High | 2023-12-05 | 2023-12-14 |  | 0 | Concrete | Industrial Park | 48395.74 | 0 | Not started
C002 | Shopping Complex B | T257 | Electrical Wiring | Sarah Johnson | Not Started | Medium | 2023-10-12 | 2023-10-24 |  | 0 | Concrete | Market Street | 33053.33 | 0 | Not started
C001 | Residential Building A | T598 | Steel Framework Setup | Carlos Rivera | In Progress | Medium | 2024-10-10 | 2024-11-08 |  | 9 | Cement | Plot 21, Riverside | 47199.27 | 45961.95 | In progress
C001 | Residential Building A | T387 | Interior Painting | Dave Brown | Not Started | Low | 2023-08-19 | 2023-09-17 | 2023-09-17 | 0 | Steel Beams | Plot 21, Riverside | 28006.03 | 0 | Not started
C001 | Residential Building A | T782 | Concrete Pouring | Dave Brown | In Progress | Low | 2023-04-12 | 2023-04-22 |  | 18 | PVC Pipes | Plot 21, Riverside | 27557.03 | 19189.58 | In progress
C001 | Residential Building A | T940 | Steel Framework Setup | John Miller | Blocked | Medium | 2023-11-10 | 2023-11-17 |  | 0 | Steel Beams | Plot 21, Riverside | 18529.66 | 15043.16 | Not started
C002 | Shopping Complex B | T331 | Concrete Pouring | Grace Allen | Completed | Medium | 2023-10-13 | 2023-10-24 | 2023-10-24 | 100 | Rebar | Market Street | 19717.81 | 37830.86 | No issues
C003 | Office Tower C | T234 | Electrical Wiring | Rachel Green | Not Started | High | 2023-09-01 | 2023-09-25 |  | 0 | Copper Wires | Downtown Avenue | 31247.41 | 0 | Not started
C001 | Residential Building A | T926 | Concrete Pouring | Dave Brown | Completed | Medium | 2024-10-05 | 2024-10-19 | 2024-10-19 | 100 | Cement | Plot 21, Riverside | 38433.09 | 35122.19 | No issues
C001 | Residential Building A | T289 | Roofing | Dave Brown | Completed | Low | 2024-07-25 | 2024-08-16 | 2024-08-16 | 100 | Paint | Plot 21, Riverside | 49266.87 | 30833.08 | No issues
C002 | Shopping Complex B | T498 | Interior Painting | Carlos Rivera | Completed | High | 2024-12-12 | 2025-01-09 | 2025-01-09 | 100 | Concrete | Market Street | 30969.92 | 49298.45 | No issues
C004 | Warehouse D | T741 | Electrical Wiring | Rachel Green | Not Started | Medium | 2024-02-26 | 2024-03-08 |  | 0 | Copper Wires | Industrial Park | 15669.51 | 0 | Not started
C004 | Warehouse D | T320 | Foundation Excavation | Mike Adams | Not Started | High | 2023-04-12 | 2023-05-10 | 2023-05-10 | 0 | Cement | Industrial Park | 21671.11 | 0 | Not started
C002 | Shopping Complex B | T432 | Electrical Wiring | Emma White | Blocked | Low | 2023-12-14 | 2023-12-30 | 2023-12-30 | 0 | Paint | Market Street | 26429.61 | 48765.5 | Not started
C004 | Warehouse D | T789 | Site Survey | Carlos Rivera | In Progress | High | 2023-05-27 | 2023-06-20 | 2023-06-20 | 16 | Roofing Sheets | Industrial Park | 7607.91 | 8659.88 | In progress